## Master Sheet
Status | PO | PR | Procurement Comments | WIL Comments | Revision | Demand Plant | WO number | WO Description | WO Status | WO Actual Release date | Requirement date (WO component) | WO basic Start date | WO basic Finish date | Material / Component | Material / Component description | Req Urgency for Material/Component | Req Priority for Material/Component | Requirement quantity | Stock on-hand @ Remote | Stock on-hand @ Base | Current document | Supply status | Supply Process | Alert / Exception | Current STO | Purchase Requisition | Purchase Requisition Item | Vendor PO | Vendor | Delivery date (PO) | ETA @ Demand plant | Purchasing Group | Batch/Valudation type(from WO component) | Supplying Plant | Expediting Note / User Comment |  | Release id (" "=rel., X=not yet,1=never) | Campaign (Y/N) | Process Phase | Process Subphase | Operation / Activity | Functional location | Reservation | Reservation Item | Incoterms | Arrival (actual) | Arrival (plan) | BOM item number | Company Code (STO) | Container-ID | Creation Date (STO) | Current STO Item | Delay @ Demand plant | Delay @ Procument plant | Delay @ Supply plant | Delivery date (PR) | Delivery date (STO) | Early start date (WO) | Equipment | ETA @ Procument plant | ETA @ Supply plant | EWM task for GI (STO) | EWM Warehouse for GI (STO) | Final Due Date | GI qty (OBD for STO) | Good Issue (STO) | Good Receipt (PO) | Goods Issue date (STO) | Goods Receipt End date (STO) | Goods Recipient | GR OBD Document (STO) | GR processing time | GR Processing time Demand plant (STO) | GR Processing time Supply plant (PR) | GR qty (IBD for STO) | GR qty (PO) | HU Quantity | Inbound Delivery (PO) | Inbound Delivery (STO) | Incompletion indic. (Y/N) | Internal alert code | Item category (BOM) | Latest GI (STO) | Latest GI STO Year | Latest GR (PO) | Latest GR IBD (STO) | Latest GR IBD Year(STO) | Latest GR PO Year | Latest IBD (PO) | Latest Inbound Delivery (STO) | Latest Outbound Delivery STO | Linked Work-pack/HU | Loading Date (STO) | Maint. Operation Exec. Stage Code | Maintenance Planning Plant | Maintenance Plant | Maintenance Storage Location | Material Description | Material Staging date (STO) | Message log(Orchestration / Derivation) | Nested HU Lvl 2 | Nested HU Lvl 3 | Oper. Phase Status | Oper/Act number of Reservation | Operation Control key | Operation description | Operation System Condition | Order Phase Status | Outbound Delivery (STO) | Person responsible | Picking bin | Planned Deliver Time (in days) (PR) | Planned Delivery Time (in days) (STO) | PO item deletion indic | PO qty | Position | PR Processing State | PR Release Indicator | Procurement plant | Profile Status | Project stock | Purchasing group (STO) | Purchasing Organisation (STO) | Purchasing Processing time(PR) | Receiving Plant (STO) | Ref Latest Outbound Delivery (STO) | Release date (PR) | Remaining quanity | Requirement UOM | Requirements date (PR) | Reservation Item (reverse link) | Reservation item deletion indicator | Reservation Special Stock Ind. | Responsible Buyer (for PO) | Return doc (MvT 262) | Return STO | Return STO Item | Return STO Qty | Revision Type | Route (STO) | Routing number (of WO Operation) | Shipping Point (STO) | Shipping Type | Status of Material (Demand Plant) | Status of Material (Supplying Plant) | STO (Supplying) - 1st STO | STO (Supplying) - 1st STO Item | STO Committed date (STO) | STO for SP97 (2nd STO) | STO for SP97 2ndS STO Item | STO quantity (STO) | STO quantity UoM (STO) | Stock In-Transit into Remote | Storage Location (STO) based on WO | Supplying Plant (STO) | Top HU | Transportation Planning date (STO) | Unloading Point | UoM of HU | User Responsible | User-status | Vehicle departure date | Vendor PO item | Vendor PO Pur Org | Voyage status | Voyage type | Voyage-id | Warehouse | Withdrawn quantity | WO Actual Finish date | WO Actual Start date | WO Company Code | WO Controlling Area | WO created by | WO creation date | WO from PR (reverse link) | WO item number | WO Main work centre | WO Overall Status | WO overall status code | WO Priority | WO Responsible Cost Center | WO Revision | WO Scheduled Finish date | WO Scheduled Release date | WO Scheduled Start date | WO System Status | WO type | WO WBS element | Workpack bin
No Stock at Base | 4500000674/00030 - Due Date | No Req or Processed |  | IP REVIEW 28.02: SIT MLC to receipt in |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001005 | 70001005 (40 SERIES BALL VALVE 3/4" TUBE ENDS) | 30 | 30 | 4 | 4 | 0 | GRST-5000029217_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | Voyage arrived: too late to meet planned Reqmt Dat | 5300005431 | 1000000967 | 10 | 4500000674 | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) | 2024-02-06 | 2024-02-13 | AUS Operations (106) |  | DU01 | IP REVIEW 28.02: SIT MLC to receipt in | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 10 | 2024-02-17 | 2024-02-18 | 0030 | 1130 |  | 2024-01-22 | 30 | 0 | 0 | 4 | 2024-02-06 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-09 | 100000011955 | 1010 | 2024-05-12 | 4 | 4900031513_2024_0003 | 5000017976_2024_0001 | 2024-02-16 | 2024-02-13 | Mac Store | 5000029217_2024_0002 | 0 | 2 | 3 | 4 | 4 | 4 | 180003968/180003880/ | 180005194 | 0 | CPT | 1 | L | 4900031513 | 2024 | 5000017976 | 5000029217 | 2024 | 2024 | 180003968 | 180005194 | 9000081 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 40 SERIES BALL VALVE 3/4" TUBE ENDS | 2024-02-05 | Supply for Order 100068150, Item 10 cannot be changed 9000081 item 30 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 9000081_0030 |  |  | 7 | 7 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-22 |  | 4 | EA | 2024-02-09 | 10 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 30 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 | 101000000018942 | 2024-02-05 | Mac Store | EA |  |  |  | 30 | AU00 | 5-Completed |  | 20000135 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001079 | 70001079 (Freight/Packaging & Cutting) | 30 | 30 | 1 | 0 | 0 | IDPO-0180003968 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver on-time | 5300005431 | 1000001019 | 24 | 4500000674 | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) | 2024-02-06 | 2024-02-15 | AUS Operations (106) |  | DU01 | AT MAC | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 24 |  |  | 0130 | 1130 |  | 2024-01-22 | 110 | 0 | 0 | 5 | 2024-02-07 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-10 |  |  | 2024-05-12 | 0 |  |  | 2024-02-05 | 2024-02-12 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 | 180003968/180003880/ |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  | 180003968 |  | 90000945 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Freight/Packaging & Cutting | 2024-02-05 | Supply for Order 100068150, Item 24 cannot be changed 90000945 item 110 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 90000945_0110 |  |  | 7 | 7 | L | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-23 |  | 1 | EA | 2024-02-10 | 24 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 |  |  |  | 5300005431 | 110 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-02-05 | Mac Store |  |  |  |  | 90 | AU00 |  |  |  | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | AT MAC |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 10015058 | 10015058 (GASKET,SPW,METAFLEX,SG/IR,CL 300/600,80M) | 30 | 30 | 3 | 14 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 15 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-02-26 | [5 empty] | 2024-05-12 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,METAFLEX,SG/IR,CL 300/600,80M | [5 empty] | 0010 | INT | Install Tubing run to bund drain |  |  |  |  | 10-05-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207863 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500000674/00070 - Due Date | No Req or Processed |  | IP REVIEW 28.02: SIT MLC to receipt in |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001009 | 70001009 (UNION 3/4" TUBE) | 30 | 30 | 20 | 20 | 0 | GRST-5000029217_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | Voyage arrived: too late to meet planned Reqmt Dat | 5300005431 | 1000000967 | 14 | 4500000674 | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) | 2024-02-06 | 2024-02-13 | AUS Operations (106) |  | DU01 | IP REVIEW 28.02: SIT MLC to receipt in | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 14 | 2024-02-17 | 2024-02-18 | 0070 | 1130 |  | 2024-01-22 | 70 | 0 | 0 | 4 | 2024-02-06 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-09 | 100000011955 | 1010 | 2024-05-12 | 20 | 4900031513_2024_0011 | 5000017958_2024_0001 | 2024-02-16 | 2024-02-13 | Mac Store | 5000029217_2024_0006 | 0 | 2 | 3 | 20 | 20 | 20 | 180003968/180003880/ | 180005194 | 0 | CPT | 1 | L | 4900031513 | 2024 | 5000017958 | 5000029217 | 2024 | 2024 | 180003968 | 180005194 | 9000081 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | UNION 3/4" TUBE | 2024-02-05 | Supply for Order 100068150, Item 14 cannot be changed 9000081 item 70 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 9000081_0070 |  |  | 7 | 7 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-22 |  | 20 | EA | 2024-02-09 | 14 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 70 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 | 101000000018942 | 2024-02-05 | Mac Store | EA |  |  |  | 70 | AU00 | 5-Completed |  | 20000135 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500000674/00050 - Due Date | No Req or Processed |  | IP REVIEW 28.02: SIT MLC to receipt in |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001007 | 70001007 (HEX NIPPLE 3/4" MNPT) | 30 | 30 | 4 | 4 | 0 | GRST-5000029217_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | Voyage arrived: too late to meet planned Reqmt Dat | 5300005431 | 1000000967 | 12 | 4500000674 | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) | 2024-02-06 | 2024-02-13 | AUS Operations (106) |  | DU01 | IP REVIEW 28.02: SIT MLC to receipt in | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 12 | 2024-02-17 | 2024-02-18 | 0050 | 1130 |  | 2024-01-22 | 50 | 0 | 0 | 4 | 2024-02-06 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-09 | 100000011955 | 1010 | 2024-05-12 | 4 | 4900031513_2024_0007 | 5000017973_2024_0001 | 2024-02-16 | 2024-02-13 | Mac Store | 5000029217_2024_0004 | 0 | 2 | 3 | 4 | 4 | 4 | 180003968/180003880/ | 180005194 | 0 | CPT | 1 | L | 4900031513 | 2024 | 5000017973 | 5000029217 | 2024 | 2024 | 180003968 | 180005194 | 9000081 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HEX NIPPLE 3/4" MNPT | 2024-02-05 | Supply for Order 100068150, Item 12 cannot be changed 9000081 item 50 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 9000081_0050 |  |  | 7 | 7 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-22 |  | 4 | EA | 2024-02-09 | 12 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 50 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 | 101000000018942 | 2024-02-05 | Mac Store | EA |  |  |  | 50 | AU00 | 5-Completed |  | 20000135 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500002761/00030 - Due Date | No Req or Processed |  | IP REVIEW 29.02: Issue with PO rcpt. PBRC working on shipping on next truck |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70002290 | 70002290 (1" NPT PLUG 316SS) | 30 | 30 | 4 | 4 | 0 | GRST-5000029974_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | No issue identified | 5300005431 | 1000002212 | 32 | 4500002761 | ENZED WELSHPOOL BELTRAMO BUSINESS TRUST (30000896) | 2024-02-26 | 2024-03-10 | AUS Operations (106) |  | DU01 | IP REVIEW 29.02: Issue with PO rcpt. PBRC working on shipping on next truck | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 32 |  | 2024-03-07 | 0170 | 1130 |  | 2024-01-22 | 150 | 0 | 0 | 10 | 2024-02-26 | 2024-02-24 | 2024-02-26 |  |  | 2024-02-29 | 100000015941 | 1010 | 2024-05-12 | 4 | 4900034555_2024_0005 | 5000022022_2024_0001 | 2024-03-05 | 2024-02-20 |  | 5000029974_2024_0003 | 0 | 2 | 3 | 4 | 4 | 4 | 180005363/ | 180008281 | 0 | CPT | 3 | L | 4900034555 | 2024 | 5000022022 | 5000029974 | 2024 | 2024 | 180005363 | 180008281 | 90001088 | WorkPackLink | 2024-02-19 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 1" NPT PLUG 316SS | 2024-02-19 | Supply for Order 100068150, Item 32 cannot be changed 90001088 item 30 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 90001088_0030 |  |  | 10 | 10 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001088 | 2024-02-09 |  | 4 | EA | 2024-02-29 | 32 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 150 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 | 101000000019347 | 2024-02-19 |  | EA |  |  |  | 30 | AU00 | 3-In Transit |  | 20000567 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
Onsite - Sloc 5001 | - | - |  | IP REVIEW 28.02: SIT MLC to receipt in |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70000879 | 70000879 (FLANGE-THRD 3"X1" NPT 600 RF/BLIND FLG D) | 30 | 30 | 3 | 3 | 0 | GRST-5000029224_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | Del to Maintenance after Reqmt Date | 5300005431 | 1000001012 | 19 | 4500000773 | AUSTRALASIAN FITTINGS AND FLANGES (30000390) | 2024-02-09 | 2024-02-27 | AUS Operations (106) |  | DU01 | IP REVIEW 28.02: SIT MLC to receipt in | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 19 | 2024-03-02 |  | 0100 | 1130 |  | 2024-01-22 | 80 | 0 | 0 | 11 | 2024-02-13 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-16 | 100000012986 | 1010 | 2024-05-12 | 3 | 4900032556_2024_0001 | 5000012651_2024_0001/5000012612_2024_0001 | 2024-02-23 | 2024-02-06 | Mac Store | 5000029224_2024_0001 | 0 | 2 | 3 | 3 | 3 | 3 | /180002556 | 180006215 | 0 | CPT | 1 | L | 4900032556 | 2024 | 5000012651 | 5000029224 | 2024 | 2024 | /018000255 | 180006215 | 9000216 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FLANGE-THRD 3"X1" NPT 600 RF/BLIND FLG D | 2024-02-05 | Supply for Order 100068150, Item 19 cannot be changed 9000216 item 80 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 9000216_0080 |  |  | 14 | 14 |  | 3 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-22 |  | 3 | EA | 2024-02-16 | 19 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 06-Air Passenger |  |  | 5300005431 | 80 |  |  | 0 | 3 | EA | 0 | 2001 | DU01 | 101000000020429 | 2024-02-05 | Mac Store | EA |  |  | 2024-02-23 | 10 | AU00 | 5-Completed |  | 1000000707 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01) |  | 10-07-02-03B
No Stock at Base | 4500000674/00060 - Due Date | No Req or Processed |  | IP REVIEW 28.02: SIT MLC to receipt in |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001008 | 70001008 (MALE CONNECTOR 3/4" TUBE x 3/4" NPT) | 30 | 30 | 12 | 12 | 0 | GRST-5000029217_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | Voyage arrived: too late to meet planned Reqmt Dat | 5300005431 | 1000000967 | 13 | 4500000674 | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) | 2024-02-06 | 2024-02-13 | AUS Operations (106) |  | DU01 | IP REVIEW 28.02: SIT MLC to receipt in | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 13 | 2024-02-17 | 2024-02-18 | 0060 | 1130 |  | 2024-01-22 | 60 | 0 | 0 | 4 | 2024-02-06 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-09 | 100000011955 | 1010 | 2024-05-12 | 12 | 4900031513_2024_0009 | 5000017909_2024_0001 | 2024-02-16 | 2024-02-13 | Mac Store | 5000029217_2024_0005 | 0 | 2 | 3 | 12 | 12 | 12 | 180003968/180003880/ | 180005194 | 0 | CPT | 1 | L | 4900031513 | 2024 | 5000017909 | 5000029217 | 2024 | 2024 | 180003968 | 180005194 | 9000081 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MALE CONNECTOR 3/4" TUBE x 3/4" NPT | 2024-02-05 | Supply for Order 100068150, Item 13 cannot be changed 9000081 item 60 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 9000081_0060 |  |  | 7 | 7 |  | 12 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-22 |  | 12 | EA | 2024-02-09 | 13 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 60 |  |  | 0 | 12 | EA | 0 | 2001 | DU01 | 101000000018942 | 2024-02-05 | Mac Store | EA |  |  |  | 60 | AU00 | 5-Completed |  | 20000135 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
Remote Pick - Low Stock | 4500003180/00020 - Due Date | - |  | AT MAC - SOH at DU50 x5 |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 10509404 | 10509404 (GASKET,SPW,TYPE CRIR,600LB,DN80,101MM ID) | 30 | 30 | 3 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | WM TO ACTION 28.02: Qty 1 at MAC, NO SOH, PO Del 22.03 | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 16 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-02-26 | [5 empty] | 2024-05-12 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,TYPE CRIR,600LB,DN80,101MM ID | [5 empty] | 0010 | INT | Install Tubing run to bund drain |  |  |  |  | 10-05-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207863 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 4 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500000674/00040 - Due Date | No Req or Processed |  | IP REVIEW 28.02: SIT MLC to receipt in |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001006 | 70001006 ( 60 SERIES BALL VALVE 3/4" FNPT ENDS) | 30 | 30 | 4 | 4 | 0 | GRST-5000029217_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | Voyage arrived: too late to meet planned Reqmt Dat | 5300005431 | 1000000967 | 11 | 4500000674 | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) | 2024-02-06 | 2024-02-13 | AUS Operations (106) |  | DU01 | IP REVIEW 28.02: SIT MLC to receipt in | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 11 | 2024-02-17 | 2024-02-18 | 0040 | 1130 |  | 2024-01-22 | 40 | 0 | 0 | 4 | 2024-02-06 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-09 | 100000011955 | 1010 | 2024-05-12 | 4 | 4900031513_2024_0005 | 5000018033_2024_0001/5000018025_2024_0001/5000018013_2024_0001/5000017999_2024_0001 | 2024-02-16 | 2024-02-13 | Mac Store | 5000029217_2024_0003 | 0 | 2 | 3 | 4 | 4 | 4 | 180003968/180003880/ | 180005194 | 0 | CPT | 1 | L | 4900031513 | 2024 | 5000018033 | 5000029217 | 2024 | 2024 | 180003968 | 180005194 | 9000081 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 60 SERIES BALL VALVE 3/4" FNPT ENDS | 2024-02-05 | Supply for Order 100068150, Item 11 cannot be changed 9000081 item 40 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 9000081_0040 |  |  | 7 | 7 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-22 |  | 4 | EA | 2024-02-09 | 11 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 40 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 | 101000000018942 | 2024-02-05 | Mac Store | EA |  |  |  | 40 | AU00 | 5-Completed |  | 20000135 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500002761/00020 - Due Date | No Req or Processed |  | IP REVIEW 29.02: Issue with PO rcpt. PBRC working on shipping on next truck |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001859 | 70001859 (124224 1" NPT 316 SS NIPPLE) | 30 | 30 | 4 | 4 | 0 | GRST-5000029974_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | No issue identified | 5300005431 | 1000002212 | 30 | 4500002761 | ENZED WELSHPOOL BELTRAMO BUSINESS TRUST (30000896) | 2024-02-26 | 2024-03-10 | AUS Operations (106) |  | DU01 | IP REVIEW 29.02: Issue with PO rcpt. PBRC working on shipping on next truck | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 30 |  | 2024-03-07 | 0160 | 1130 |  | 2024-01-22 | 140 | 0 | 0 | 10 | 2024-02-26 | 2024-02-24 | 2024-02-26 |  |  | 2024-02-29 | 100000015941 | 1010 | 2024-05-12 | 4 | 4900034555_2024_0003 | 5000021966_2024_0001 | 2024-03-05 | 2024-02-20 |  | 5000029974_2024_0002 | 0 | 2 | 3 | 4 | 4 | 4 | 180005363/ | 180008281 | 0 | CPT | 3 | L | 4900034555 | 2024 | 5000021966 | 5000029974 | 2024 | 2024 | 180005363 | 180008281 | 90001088 | WorkPackLink | 2024-02-19 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 124224 1" NPT 316 SS NIPPLE | 2024-02-19 | Supply for Order 100068150, Item 30 cannot be changed 90001088 item 20 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 90001088_0020 |  |  | 10 | 10 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001088 | 2024-02-09 |  | 4 | EA | 2024-02-29 | 30 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 140 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 | 101000000019347 | 2024-02-19 |  | EA |  |  |  | 20 | AU00 | 3-In Transit |  | 20000567 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500002761/00010 - Due Date | No Req or Processed |  | IP REVIEW 29.02: Issue with PO rcpt. PBRC working on shipping on next truck |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001858 | 70001858 (POLYFLEX HOSE -16JICF/1" NPT MALE 316SS) | 30 | 30 | 2 | 2 | 0 | GRST-5000029974_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | No issue identified | 5300005431 | 1000002212 | 28 | 4500002761 | ENZED WELSHPOOL BELTRAMO BUSINESS TRUST (30000896) | 2024-02-26 | 2024-03-10 | AUS Operations (106) |  | DU01 | IP REVIEW 29.02: Issue with PO rcpt. PBRC working on shipping on next truck | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 28 |  | 2024-03-07 | 0150 | 1130 |  | 2024-01-22 | 130 | 0 | 0 | 10 | 2024-02-26 | 2024-02-24 | 2024-02-26 |  |  | 2024-02-29 | 100000015941 | 1010 | 2024-05-12 | 2 | 4900034555_2024_0001 | 5000022014_2024_0001 | 2024-03-05 | 2024-02-20 |  | 5000029974_2024_0001 | 0 | 2 | 3 | 2 | 2 | 2 | 180005363/ | 180008281 | 0 | CPT | 3 | L | 4900034555 | 2024 | 5000022014 | 5000029974 | 2024 | 2024 | 180005363 | 180008281 | 90001088 | WorkPackLink | 2024-02-19 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | POLYFLEX HOSE -16JICF/1" NPT MALE 316SS | 2024-02-19 | Supply for Order 100068150, Item 28 cannot be changed 90001088 item 10 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 90001088_0010 |  |  | 10 | 10 |  | 2 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001088 | 2024-02-09 |  | 2 | EA | 2024-02-29 | 28 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 130 |  |  | 0 | 2 | EA | 0 | 2001 | DU01 | 101000000019347 | 2024-02-19 |  | EA |  |  |  | 10 | AU00 | 3-In Transit |  | 20000567 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
Onsite - Sloc 5001 | - | - |  | AT MAC |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70002738 | 70002738 (25NPT FEMALE FULL ORE BALL VALVE HOKE) | 30 | 30 | 4 | 4 | 0 | GRST-5000029188_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | Del to Maintenance after Reqmt Date | 5300005431 | 1000002723 | 36 | 4500003059 | PROCHEM PIPELINE PRODUCTS PTY LTD (30000271) | 2024-02-22 | 2024-03-26 | AUS Operations (106) |  | DU01 | AT MAC | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 36 | 2024-03-02 |  | 0190 | 1130 |  | 2024-01-22 | 170 | 0 | 0 | 18 | 2024-03-05 | 2024-02-24 | 2024-02-26 |  |  | 2024-03-08 | 100000014466 | 1010 | 2024-05-12 | 4 | 4900033607_2024_0001 | 5000024136_2024_0001 | 2024-02-28 | 2024-02-23 |  | 5000029188_2024_0001 | 0 | 2 | 3 | 4 | 4 | 4 | /180005763 | 180007291 | 0 | CPT | 1 | L | 4900033607 | 2024 | 5000024136 | 5000029188 | 2024 | 2024 | /018000576 | 180007291 | 90001861 | WorkPackLink | 2024-02-19 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 25NPT FEMALE FULL ORE BALL VALVE HOKE | 2024-02-19 | Supply for Order 100068150, Item 36 cannot be changed 90001861 item 10 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 90001861_0010 |  |  | 10 | 10 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001861 | 2024-02-16 |  | 4 | EA | 2024-03-08 | 36 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 06-Air Passenger |  |  | 5300005431 | 170 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 | 101000000020391 | 2024-02-19 |  | EA |  |  | 2024-02-23 | 10 | AU00 | 5-Completed |  | 1000000707 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01) |  | 10-07-02-03B
No Stock at Base | 4500002761/00040 - Due Date | No Req or Processed |  | AT MAC |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70002265 | 70002265 (MATERIAL CERT) | 30 | 30 | 2 | 2 | 0 | GRST-5000029974_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | No issue identified | 5300005431 | 1000002212 | 34 | 4500002761 | ENZED WELSHPOOL BELTRAMO BUSINESS TRUST (30000896) | 2024-02-26 | 2024-03-10 | AUS Operations (106) |  | DU01 | AT MAC | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 34 |  | 2024-03-07 | 0180 | 1130 |  | 2024-01-22 | 160 | 0 | 0 | 10 | 2024-02-26 | 2024-02-24 | 2024-02-26 |  |  | 2024-02-29 | 100000015941 | 1010 | 2024-05-12 | 2 | 4900034555_2024_0007 | 5000022023_2024_0001 | 2024-03-05 | 2024-02-20 |  | 5000029974_2024_0004 | 0 | 2 | 3 | 2 | 2 | 2 | 180005363/ | 180008281 | 0 | CPT | 3 | L | 4900034555 | 2024 | 5000022023 | 5000029974 | 2024 | 2024 | 180005363 | 180008281 | 90001088 | WorkPackLink | 2024-02-19 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MATERIAL CERT | 2024-02-19 | Supply for Order 100068150, Item 34 cannot be changed 90001088 item 40 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 90001088_0040 |  |  | 10 | 10 |  | 2 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001088 | 2024-02-09 |  | 2 | EA | 2024-02-29 | 34 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 160 |  |  | 0 | 2 | EA | 0 | 2001 | DU01 | 101000000019347 | 2024-02-19 |  | EA |  |  |  | 40 | AU00 | 3-In Transit |  | 20000567 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500000674/00020 - Due Date | No Req or Processed |  | IP REVIEW 28.02: SIT MLC to receipt in |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001004 | 70001004 (UNION ELBOW 3/4" TUBE) | 30 | 30 | 12 | 12 | 0 | GRST-5000029217_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | Voyage arrived: too late to meet planned Reqmt Dat | 5300005431 | 1000000967 | 9 | 4500000674 | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) | 2024-02-06 | 2024-02-13 | AUS Operations (106) |  | DU01 | IP REVIEW 28.02: SIT MLC to receipt in | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 9 | 2024-02-17 | 2024-02-18 | 0020 | 1130 |  | 2024-01-22 | 20 | 0 | 0 | 4 | 2024-02-06 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-09 | 100000011955 | 1010 | 2024-05-12 | 12 | 4900031513_2024_0001 | 5000017959_2024_0001 | 2024-02-16 | 2024-02-13 | Mac Store | 5000029217_2024_0001 | 0 | 2 | 3 | 12 | 12 | 12 | 180003968/180003880/ | 180005194 | 0 | CPT | 1 | L | 4900031513 | 2024 | 5000017959 | 5000029217 | 2024 | 2024 | 180003968 | 180005194 | 9000081 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | UNION ELBOW 3/4" TUBE | 2024-02-05 | Supply for Order 100068150, Item 9 cannot be changed 9000081 item 20 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 9000081_0020 |  |  | 7 | 7 |  | 12 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-22 |  | 12 | EA | 2024-02-09 | 9 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 20 |  |  | 0 | 12 | EA | 0 | 2001 | DU01 | 101000000018942 | 2024-02-05 | Mac Store | EA |  |  |  | 20 | AU00 | 5-Completed |  | 20000135 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
Stock Available at Base | - | - |  | AT MAC |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001020 | 70001020 (Additional Charges) | 30 | 30 | 1 | 0 | 1 | ODST-0090000945_0090 | Material is received @DU01 | Directs (Inventory) (SP14) | No issue identified | 5300005431 | 1000001012 | 20 | 4500000773 | AUSTRALASIAN FITTINGS AND FLANGES (30000390) | 2024-02-09 | 2024-02-27 | AUS Operations (106) |  | DU01 | AT MAC | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 20 |  |  | 0110 | 1130 |  | 2024-01-22 | 90 | 0 | 0 | 11 | 2024-02-13 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-16 |  |  | 2024-05-12 | 0 |  | 5000012629_2024_0001 | 2024-02-05 | 2024-02-06 | Mac Store |  | 0 | 2 | 3 | 0 | 1 | 0 | /180002556 |  | 0 | CPT | 3 | L |  | 0 | 5000012629 |  | 0 | 2024 | /018000255 |  | 90000945 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Additional Charges | 2024-02-05 | Supply for Order 100068150, Item 20 cannot be changed 90000945 item 90 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 90000945_0090 |  |  | 14 | 14 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-22 |  | 1 | EA | 2024-02-16 | 20 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 |  |  |  | 5300005431 | 90 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-02-05 | Mac Store |  |  |  |  | 20 | AU00 |  |  |  | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500000674/00080 - Due Date | No Req or Processed |  | IP REVIEW 28.02: SIT MLC to receipt in |  | DU50 | 100068150 | Level bridle flush prior to Feb 22nd S/D (100068150) | Released | 2024-01-01 | 2024-02-26 | 2024-03-22 | 2024-03-22 | 70001078 | 70001078 (3/4` CUSHIONED CLAMP TUBE SUPPORT) | 30 | 30 | 20 | 20 | 0 | GRST-5000029217_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | Voyage arrived: too late to meet planned Reqmt Dat | 5300005431 | 1000001019 | 23 | 4500000674 | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) | 2024-02-06 | 2024-02-15 | AUS Operations (106) |  | DU01 | IP REVIEW 28.02: SIT MLC to receipt in | N | Post Execution (08) | Work Done (Order) (0080) | Install Tubing run to bund drain (0010) | Vessel Regeneration Gas KO Pot (DU50.MA.GCD.10.VP001) | 0000208448 | 23 | 2024-02-17 | 2024-02-18 | 0120 | 1130 |  | 2024-01-22 | 100 | 0 | 0 | 5 | 2024-02-07 | 2024-02-10 | 2024-02-26 |  |  | 2024-02-10 | 100000011955 | 1010 | 2024-05-12 | 20 | 4900031513_2024_0013 | 5000017977_2024_0001 | 2024-02-16 | 2024-02-13 | Mac Store | 5000029217_2024_0007 | 0 | 2 | 3 | 20 | 20 | 20 | 180003968/180003880/ | 180005194 | 0 | CPT | 1 | L | 4900031513 | 2024 | 5000017977 | 5000029217 | 2024 | 2024 | 180003968 | 180005194 | 9000081 | WorkPackLink | 2024-02-05 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 3/4` CUSHIONED CLAMP TUBE SUPPORT | 2024-02-05 | Supply for Order 100068150, Item 23 cannot be changed 9000081 item 100 already exists |  |  |  | 0010 | INT | Install Tubing run to bund drain |  |  | 9000081_0100 |  |  | 7 | 7 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90000945 | 2024-01-23 |  | 20 | EA | 2024-02-10 | 23 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207863 | S001 | 01-Road |  |  | 5300005431 | 100 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 | 101000000018942 | 2024-02-05 | Mac Store | EA |  |  |  | 80 | AU00 | 5-Completed |  | 20000135 | 1270 | 0 |  | 2024-02-26 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208448 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | Released/Order Main Work Completed/Settlement rule created/Pre-costed/Object created/Job Finished/Confirmed/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24ESD | DU50 | 200132551 | 12M ESD Function Test GRC (200132551) | Released | 2024-01-01 | 2024-02-26 | 2024-02-23 | 2024-03-05 |  |  | 5 | 10 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Conduct ESD Test (0020) | ESD Push Buttons (DU50.MA.IES.10.SF001) | 0000207347 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-02-26 | [5 empty] | 2024-03-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Conduct ESD Test | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206710 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  | 2024-02-23 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24ESD | 2024-03-05 | 2024-02-23 | 2024-02-23 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Partially confirmed/Goods movement posted/Job In Process/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | B513596833/00060 - Due Date | No Req or Processed |  | AT MAC - SAP to be updated PDC to action and MLC to receipt into Du50 | 24MCUPS1 | DU50 | 100067899 | Replace DC UPS B Batteries (100067899) | Released | 2024-01-01 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 10618979 | 10618979 (Exide, Absolyte GP 2V Cell, Std. Casing) | 30 | 30 | 60 | 0 | 0 | ODST-0090001864_0010 | Material avail; awaiting work-packing @DU01 | Stock at Base (SP12) | No issue identified | 5300006589 |  | 0 |  |  |  | 2024-03-06 |  |  | DU01 | AT MAC | N | Post Execution (08) | Work Done (Order) (0080) | SPS - Replace DC UPS B Batteries D1 (0010) | Battery Charger DC UPS B (DU50.MA.UEP.40.PW032) | 0000208157 | 3 |  |  | 0030 | 1130 |  | 2024-02-15 | 10 | 0 | 0 | 0 |  | 2024-03-04 | 2024-03-06 | [5 empty] | 2024-04-28 | 0 |  |  | 2024-02-26 | 2024-03-06 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  | 90001864 | WorkPackLink | 2024-02-26 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Exide, Absolyte GP 2V Cell, Std. Casing | 2024-02-26 | Supply for Order 100067899, Item 3 cannot be changed 90001864 item 10 already exists |  |  |  | 0010 | INT | SPS - Replace DC UPS B Batteries D1 |  |  | 90001864_0010 |  |  | 0 | 60 |  | 0 | [5 empty] | 0 | AUS Operations (106) | AU00 |  | DU50 | 90001864 |  |  | 60 | EA |  | 3 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000207572 | S001 |  | 30 | 30 | 5300006589 | 10 |  |  | 0 | 60 | EA | 0 | 2001 | DU01 |  | 2024-02-26 | [5 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-03-06 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208157 | 0 | OPS |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-06 | 2024-03-06 | Partially confirmed/Job Finished/Goods movement posted/Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100067899 | Replace DC UPS B Batteries (100067899) | Released | 2024-01-01 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Post Execution (08) | Work Done (Order) (0080) | SPS - Replace DC UPS B Batteries D1 (0010) | Battery Charger DC UPS B (DU50.MA.UEP.40.PW032) | 0000208157 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-06 | [5 empty] | 2024-04-28 | 0 |  |  |  |  | ELECTRICAL L |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS - Replace DC UPS B Batteries D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207572 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  | 2024-03-06 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | OPS |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-06 | 2024-03-06 | Partially confirmed/Job Finished/Goods movement posted/Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100067980 | Replace DC UPS A batteries (100067980) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-10 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Post Execution (08) | Work Done (Order) (0080) | SPS - Replace DC UPS A Batteries D1 (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000208158 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | ELECTRICAL L |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS - Replace DC UPS A Batteries D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207573 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  | 2024-03-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | OPS |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-10 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage/Goods movement posted/Job Finished/Partially confirmed | Reactive Maintenance (AM01)
No Stock at Base | B513596833/00070 - Due Date | No Req or Processed |  | AT MAC - SAP to be updated PDC to action and MLC to receipt into Du50 | 24MCUPS1 | DU50 | 100067980 | Replace DC UPS A batteries (100067980) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-10 | 10355271 | 10355271 (Exide, Absolyte GP 2V Cell, Std. Casing) | 30 | 30 | 60 | 0 | 0 | ODST-0090001865_0010 | Material avail; awaiting work-packing @DU01 | Stock at Base (SP12) | No issue identified | 5300006590 |  | 0 |  |  |  | 2024-03-08 |  |  | DU01 | AT MAC | N | Post Execution (08) | Work Done (Order) (0080) | SPS - Replace DC UPS A Batteries D1 (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000208158 | 3 |  |  | 0030 | 1130 |  | 2024-02-15 | 10 | 0 | 0 | 0 |  | 2024-03-04 | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  | 2024-02-26 | 2024-03-06 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  | 90001865 | WorkPackLink | 2024-02-26 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Exide, Absolyte GP 2V Cell, Std. Casing | 2024-02-26 | Supply for Order 100067980, Item 3 cannot be changed 90001865 item 10 already exists |  |  |  | 0010 | INT | SPS - Replace DC UPS A Batteries D1 |  |  | 90001865_0010 |  |  | 0 | 60 |  | 0 | [5 empty] | 0 | AUS Operations (106) | AU00 |  | DU50 | 90001865 |  |  | 60 | EA |  | 3 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000207573 | S001 |  | 30 | 30 | 5300006590 | 10 |  |  | 0 | 60 | EA | 0 | 2001 | DU01 |  | 2024-02-26 | [5 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-03-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208158 | 0 | OPS |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-10 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage/Goods movement posted/Job Finished/Partially confirmed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 14 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 14 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 6 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 16 |  |  | 0160 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 17 |  |  | 0170 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 14 |  |  | 0140 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 18 |  |  | 0180 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 6 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 11 |  |  | 0110 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 6 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 8 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 7 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 15 |  |  | 0150 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 13 |  |  | 0130 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 4 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 12 |  |  | 0120 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 4 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 10 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCUPS1 | DU50 | 100070082 | UPSes End fo Life Replacement (100070082) | Released | 2024-01-01 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  | 30 | 30 | 2 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | SPS-UPSes End fo Life Replacement (0010) | Battery Charger DC UPS A (DU50.MA.UEP.40.PW031) | 0000210300 | 9 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-08 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | IE Tech |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SPS-UPSes End fo Life Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209695 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCUPS1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | Reactive Maintenance (AM01)
Remote Pick - Low Stock | 4500009334/00020 - Due Date 45413 | - |  | Material Consumed |  | DU50 | 200127473 | 12M Mech Insp 350-H-318 (200127473) | Released | 2024-01-22 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 10507326 | 10507326 (BELT,POS DRV,224T,FALCON PD,SYNC,HNBR,8M) | 20 | 20 | 1 | 0 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Post Execution (08) | Work Done (Order) (0080) | Inspect Fin Fan Cooler (0010) | Exch Condensate Rundown Cooler (DU50.MA.GCO.10.HX001) | 0000202276 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-18 | [5 empty] | 2024-03-22 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BELT,POS DRV,224T,FALCON PD,SYNC,HNBR,8M | [5 empty] | 0010 | INT | Inspect Fin Fan Cooler | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000201651 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  | 2024-03-18 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-03-18 | 2024-03-18 | 2024-03-18 | Released/Pre-costed/Object created/Job Finished/Confirmed/Goods movement posted/Material committed/Settlement rule created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | Material Consumed |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 11390704 | 11390704 (DIESEL FUEL,ULTRA LOW SULPHUR,ASTM D1500) | 99 | 255 | 806 | 39417 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 10 | [6 empty] | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 |  |  |  |  | Feb24 Usage |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DIESEL FUEL,ULTRA LOW SULPHUR,ASTM D1500 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | Z-CUTOVER-NOBIN | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | L |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 806 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | Material Consumed |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10509369 | 10509369 (HYDROGEN,TECH,320150,SIZE G CYLINDER,GDE) | 99 | 255 | 2 | 2 | 6 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 3 |  |  | X |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 |  |  |  |  | M Wingeatt |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HYDROGEN,TECH,320150,SIZE G CYLINDER,GDE | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 20-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Metering Station |  |  |  |  | 0 |  |  |  |  | 1270 | 2 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | Material Consumed |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10512160 | 10512160 (GREASE,GP,SPHEEROL AP3,LITH BASE,NLGI 3) | 99 | 255 | 2 | 5 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 14 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GREASE,GP,SPHEEROL AP3,LITH BASE,NLGI 3 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 10-08-05-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 2 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10355695 | 10355695 (SODIUM HYPOCHLORITE SOLUTION,12.5%,20L) | 99 | 255 | 1 | 1 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 11 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SODIUM HYPOCHLORITE SOLUTION,12.5%,20L | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | Z-CUTOVER-NOBIN | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | DR |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10202018 | 10202018 (WATER,PURIFIED,DEMINERALISED,IBC/1000KG) | 99 | 255 | 1 | 1 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 5 | [6 empty] | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WATER,PURIFIED,DEMINERALISED,IBC/1000KG | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 21-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10509368 | 10509368 (HELIUM,TECH,336150,SIZE G CYL,GDE 5,99.9) | 99 | 255 | 1 | 3 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | 0000000194 | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 2 |  |  | X |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 |  |  |  |  | WA0GPI |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HELIUM,TECH,336150,SIZE G CYL,GDE 5,99.9 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 20-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Pick - Low Stock | 4500008163/00070 - Due Date 45390 | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10231997 | 10231997 (ACETIC ACID,UN2789,EMERSON C00082) | 99 | 255 | 1 | 0 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 9 | [6 empty] | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ACETIC ACID,UN2789,EMERSON C00082 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10016991 | 10016991 (CLEANING COMPOUND,SOLVENT,SIMPLE GREEN,D) | 99 | 255 | 1 | 1 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 18 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CLEANING COMPOUND,SOLVENT,SIMPLE GREEN,D | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 21-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Pick - Low Stock | No PO | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10504351 | 10504351 (GREASE,TYP MLS CART,COMPAIR SCWG4000120) | 99 | 255 | 3 | 0 | 9 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 8 | [6 empty] | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 |  |  |  |  | Lab Stocktak |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GREASE,TYP MLS CART,COMPAIR SCWG4000120 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 3 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Pick - Low Stock | 4500002068/00020 - Due Date | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 11229501 | 11229501 (WATER BOTTLE,15L,BLKWOODS 01029558DS) | 99 | 255 | 32 | 0 | 32 |  | Material Consumed | Stock at Base and Remote (SP11) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 21 |  |  | 0110 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WATER BOTTLE,15L,BLKWOODS 01029558DS | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 32 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10509368 | 10509368 (HELIUM,TECH,336150,SIZE G CYL,GDE 5,99.9) | 99 | 255 | 1 | 3 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | 0000000196 | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 23 |  |  | 0130 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HELIUM,TECH,336150,SIZE G CYL,GDE 5,99.9 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 20-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Pick - Low Stock | 4500009332/00030 - Due Date 45432 | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10509372 | 10509372 (CALIBRATING GAS,380145,SIZE G 1081 CYLIN) | 99 | 255 | 2 | 0 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 4 | [6 empty] | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 |  |  |  |  | M Wingeatt |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CALIBRATING GAS,380145,SIZE G 1081 CYLIN | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Metering Station |  |  |  |  | 0 |  |  |  |  | 1270 | 2 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Pick - Low Stock | 4500001116/00010 - Due Date | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10232273 | 10232273 (TAPE,SENSING,330FT LG,ENVEENGI 330133XS) | 99 | 255 | 7 | 0 | 8 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 6 |  |  | X |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | TAPE,SENSING,330FT LG,ENVEENGI 330133XS | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 7 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
No Stock at Base | 4500002068/00020 - Due Date | PDC - MAC NG (DU01)2000047717 / 00010 - Due Date 30/04/2024 |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 11229501 | 11229501 (WATER BOTTLE,15L,BLKWOODS 01029558DS) | 99 | 255 | 0 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 19 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WATER BOTTLE,15L,BLKWOODS 01029558DS | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10888808 | 10888808 (GREASE,GP,PREMIUM H/D,LITHIUM COMPLEX BA) | 99 | 255 | 2 | 2 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 15 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GREASE,GP,PREMIUM H/D,LITHIUM COMPLEX BA | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 21-02-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 2 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10509368 | 10509368 (HELIUM,TECH,336150,SIZE G CYL,GDE 5,99.9) | 99 | 255 | 1 | 3 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | 0000000195 | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 22 |  |  | 0120 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HELIUM,TECH,336150,SIZE G CYL,GDE 5,99.9 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 20-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10232596 | 10232596 (CALIBRATING GAS,2 X 34L AL CYL,40PPM H2S) | 99 | 255 | 1 | 1 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 7 | [6 empty] | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CALIBRATING GAS,2 X 34L AL CYL,40PPM H2S | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 11-02-03-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 11086135 | 11086135 (BOTTLE,OIL SAMPLE,1L,SGS SK165) | 99 | 255 | 4 | 15 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 1 | [6 empty] | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 |  |  |  |  | MLC |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BOTTLE,OIL SAMPLE,1L,SGS SK165 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 10-04-04-02A,10-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | MAC Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 4 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 11165576 | 11165576 (GREASE,SPECIAL,CLIMAX 1034MT,SYNTHETIC P) | 99 | 255 | 1 | 3 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 16 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GREASE,SPECIAL,CLIMAX 1034MT,SYNTHETIC P | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order |  |  |  |  | 10-08-05-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Pick - Low Stock | 4500003282/00010 - Due Date | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 10276570 | 10276570 (WATER,DRINKING,BOTTLED,STILL WATER,CTN/2) | 99 | 255 | 57 | 0 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 20 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WATER,DRINKING,BOTTLED,STILL WATER,CTN/2 | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 57 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132898 | 5Y Cft MO-PSV-33067B (200132898) | Released | 2024-01-01 | 2024-03-26 | 2024-03-26 | 2024-05-21 | 11175225 | 11175225 (VALVE,SAFETY,25*D*50,CONVENTIONAL,DIRECT) | 20 | 20 | -1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | Replace Pressure Relief Device (0010) | Vessel Silica Bed Coalescer Regen Gas B (DU50.MA.GCD.10.VP005) | 0000207801 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-26 | [5 empty] | 2024-04-19 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,25*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207156 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-21 | 2024-03-26 | 2024-03-26 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - MLC to receipt into DU50 |  | DU50 | 200131939 | 12M Torque Wrench Test Tool Calibration (200131939) | Released | 2024-01-01 | 2024-03-29 | 2024-03-29 | 2024-04-28 | 11296341 | 11296341 (TESTER,TORQUE,3/4IN,STAHL 709170) | 20 | 20 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [5 empty] | NEW |  | AT MAC - MLC to receipt into DU50 | N | Execution (07) | Main Work Started (Order) (0070) | Collect and Pack Equipment Lot 2 (0031) | Building Workshop/Warehouse (DU50.MA.FBD.06.BG001) | 0000206755 | 3 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-29 | [5 empty] | 2024-03-15 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | TESTER,TORQUE,3/4IN,STAHL 709170 | [5 empty] | 0031 | INT | Collect and Pack Equipment Lot 2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000206118 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-28 | 2024-03-29 | 2024-03-29 | Released/Pre-costed/Object created/Estimated costs/Material shortage/Partially confirmed/Settlement rule created | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100068487 | Install new Coldpress and Fridge (100068487) | Released | 2024-01-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Install new Coldpress and Fridge (0010) | Building Onslow Accom (DU50.MA.FBD.08.BG001) | 0000208756 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-30 | [5 empty] | 2024-05-25 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Install new Coldpress and Fridge | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000208139 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-03-30 | 2024-03-30 | 2024-03-30 | Goods movement posted/Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100068487 | Install new Coldpress and Fridge (100068487) | Released | 2024-01-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Install new Coldpress and Fridge (0010) | Building Onslow Accom (DU50.MA.FBD.08.BG001) | 0000208756 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-30 | [5 empty] | 2024-05-25 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Install new Coldpress and Fridge | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000208139 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-03-30 | 2024-03-30 | 2024-03-30 | Goods movement posted/Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100068487 | Install new Coldpress and Fridge (100068487) | Released | 2024-01-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Install new Coldpress and Fridge (0010) | Building Onslow Accom (DU50.MA.FBD.08.BG001) | 0000208756 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-30 | [5 empty] | 2024-05-25 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Install new Coldpress and Fridge | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000208139 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-03-30 | 2024-03-30 | 2024-03-30 | Goods movement posted/Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | AT MAC |  | DU50 | 200129013 | 2M Oil Sampling Solar Engines (200129013) | Released | 2024-01-02 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 11086108 | 11086108 (BOTTLE,OIL SAMPLE,250ML,SGS SK163) | 20 | 20 | 7 | 17 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Post Execution (08) | Work Done (Order) (0080) | Collect Oil Sample Solar Machines (0010) | Electrical Generation (DU50.MA.UEP.10) | 0000203816 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-01 | [5 empty] | 2024-04-01 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BOTTLE,OIL SAMPLE,250ML,SGS SK163 | [5 empty] | 0010 | INT | Collect Oil Sample Solar Machines |  |  |  |  | 10-04-04-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 7 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203211 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  | 2024-04-01 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | Job Finished/Confirmed/Released/Pre-costed/Object created/Estimated costs/Material shortage/Settlement rule created | Proactive Maintenance (AM02)
No Stock at Base | No PO | Macedon - MAC NG (DU50)2000048044 / 00010 - Due Date 16/04/2024 |  | Material Consumed |  | DU50 | 300000260 | N2 bottle 1 switch leaking (300000260) | Released | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 10283476 | 10283476 (SWITCH,PRESS,N2,SOLATURB 997425C1) | 99 | 255 | 1 | 1 | 0 |  | Material Consumed | Emergency Supply (from local stock) (SP99) | No Issue identified |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N |  |  | N2 bottle 1 switch leaking (0010) | CABINET WATER MIST GENERATOR TURBINE D (DU50.UEP.MO-630-U-907) | 0000229790 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-01 | [6 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 1001 | SWITCH,PRESS,N2,SOLATURB 997425C1 | [5 empty] | 0010 | INT | N2 bottle 1 switch leaking |  |  |  |  | 11-01-03-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000227104 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  | 2024-04-01 | WE Global Pty Ltd (1130) | W001 | WA0GGY | 2024-04-01 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | Object created/Pre-costed/Goods movement posted/Confirmed/Job Finished/Settlement rule created/Released/Material committed/Processed with Fiori App F2023 | Emergency Maintenance (AM03)
No Stock at Base | No PO | No Req or Processed |  | Material Consumed |  | DU50 | 300000260 | N2 bottle 1 switch leaking (300000260) | Released | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 10006971 | 10006971 (NITROGEN,TECHNICAL,034 GAS CODE,SG SIZE) | 99 | 255 | 1 | 14 | 0 |  | Material Consumed | Emergency Supply (from local stock) (SP99) | No Issue identified |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N |  |  | N2 bottle 1 switch leaking (0010) | CABINET WATER MIST GENERATOR TURBINE D (DU50.UEP.MO-630-U-907) | 0000229790 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-01 | [6 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | NITROGEN,TECHNICAL,034 GAS CODE,SG SIZE | [5 empty] | 0010 | INT | N2 bottle 1 switch leaking |  |  |  |  | 20-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000227104 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  | 2024-04-01 | WE Global Pty Ltd (1130) | W001 | WA0GGY | 2024-04-01 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | Object created/Pre-costed/Goods movement posted/Confirmed/Job Finished/Settlement rule created/Released/Material committed/Processed with Fiori App F2023 | Emergency Maintenance (AM03)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 100075235 | GHD-34260 (ZX 399-102) going offline (100075235) | Released | 2024-03-25 | 2024-04-02 | 2024-04-02 | 2024-04-02 | 11311235 | 11311235 (DETECTOR,METHANE GAS,SOLATURB 107832527) | 30 | 30 | 1 | 3 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Post Execution (08) | Work Done (Order) (0080) | GHD-34260 (ZX 399-102) going offline (0010) | DET ENCLOSURE AIR EXHAUST GHD-34260 (DU50.UFP.MO-GHD-34260) | 0000228699 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-02 | [5 empty] | 2025-04-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DETECTOR,METHANE GAS,SOLATURB 107832527 | [5 empty] | 0010 | INT | GHD-34260 (ZX 399-102) going offline |  |  |  |  | 10-01-05-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000226022 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 1 |  | 2024-03-30 | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-25 | 0 | 0 | INLEC |  | 4 |  |  | CC11874501 |  | 2024-04-02 | 2024-04-02 | 2024-04-02 | Object created/Order Approved/Goods movement posted/Pre-costed/Material committed/Settlement rule created/Order Main Work Completed/Confirmed/Job Finished/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100068948 | Replace or Repair TI-34135 (100068948) | Released | 2024-01-01 | 2024-04-04 | 2024-04-04 | 2024-04-04 |  |  | 99 | 255 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | Replace or Repair TI-34135 (0010) | Exch WHRU Unit A (DU50.MA.UHT.10.HX003) | 0000209226 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-04 | [5 empty] | 2024-05-01 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace or Repair TI-34135 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000208641 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-04 | 2024-04-04 | 2024-04-04 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed/Estimated costs | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink | 24MCSGBS | DU50 | 600002762 | SGC-B N2 PDCV Replacement (600002762) | Released | 2024-01-01 | 2024-04-10 | 2024-04-10 | 2024-04-17 | 11392820 | 11392820 (VALVE,JORDVALV MK6363D025S6PTZZZZ15JLSE0) | 30 | 30 | -2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGC-C N2 PDCV Replacement (0010) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000207545 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-10 | [5 empty] | 2024-06-30 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,JORDVALV MK6363D025S6PTZZZZ15JLSE0 | [5 empty] | 0010 | INT | SGC-C N2 PDCV Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206909 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-04-17 | 2024-04-10 | 2024-04-10 | Released/Settlement rule created/Pre-costed/Object created/Estimated costs/Material shortage | Capital (AM06)
No Stock at Base | B513596251/00020 - Due Date 45352 | No Req or Processed |  | WM TO ACTION: Reschedule PO B513596251 Score ETA 08.04 to PDC | 24MCSGBS | DU50 | 600002762 | SGC-B N2 PDCV Replacement (600002762) | Released | 2024-01-01 | 2024-04-10 | 2024-04-10 | 2024-04-17 | 11392820 | 11392820 (VALVE,JORDVALV MK6363D025S6PTZZZZ15JLSE0) | 30 | 30 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | Not Delivered Yet ETA 01 MAR PO B513596251 Score | N | Preparation (05) | In Preparation (Order) (0055) | SGC-C N2 PDCV Replacement (0010) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000207545 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-10 | [5 empty] | 2024-06-30 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,JORDVALV MK6363D025S6PTZZZZ15JLSE0 | [5 empty] | 0010 | INT | SGC-C N2 PDCV Replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206909 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-04-17 | 2024-04-10 | 2024-04-10 | Released/Settlement rule created/Pre-costed/Object created/Estimated costs/Material shortage | Capital (AM06)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10231791 | 10231791 (O-RING,ENVEENGI 330431) | 20 | 20 | 4 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,ENVEENGI 330431 | [5 empty] | 0010 | INT | Service Gas Analyser | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10504952 | 10504952 (MIRROR,AMETEK 10652JE) | 20 | 20 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 9 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MIRROR,AMETEK 10652JE | [5 empty] | 0010 | INT | Service Gas Analyser |  |  |  |  | 11-01-03-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10504700 | 10504700 (MEMBRANE KIT,AMETEK 42891JE) | 20 | 20 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 7 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MEMBRANE KIT,AMETEK 42891JE | [5 empty] | 0010 | INT | Service Gas Analyser |  |  |  |  | 11-01-04-05A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 11074919 | 11074919 (TRAP,AIR,DRAIN,MOISTURE,18IN LG X 2-3/8I) | 20 | 20 | 2 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 10 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | TRAP,AIR,DRAIN,MOISTURE,18IN LG X 2-3/8I | [5 empty] | 0010 | INT | Service Gas Analyser |  |  |  |  | 10-08-01-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10504538 | 10504538 (O-RING KIT,CELL,AMETEK 76152TE) | 20 | 20 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 8 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING KIT,CELL,AMETEK 76152TE | [5 empty] | 0010 | INT | Service Gas Analyser | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
No Stock at Base | 4500000905/00010 - Due Date 45378 | No Req or Processed |  | IP REVIEW: At PDC requested for next truck ETA 09.04 to MAC |  | DU50 | 100068292 | Need new Electronics modules LIT-34300 (100068292) | Released | 2024-01-02 | 2024-04-14 | 2024-04-14 | 2024-04-14 | 70001171 | 70001171 (KTEK LMT200 Magnetostrictive Transmitter) | 30 | 30 | 1 | 0 | 0 | IDPO-/018001385 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver in-full | 5300005522 | 1000001173 | 2 | 4500000905 | PROCHEM PIPELINE PRODUCTS PTY LTD (30000271) | 2024-03-27 | 2024-04-07 | AUS Operations (106) |  | DU01 | Not Delivered Yet ETA MAR 27 | N | Preparation (05) | In Preparation (Order) (0055) | Need new Electronics modules LIT-34300 (0010) | Vessel Sales Gas Suction Scrubber (DU50.MA.GSG.30.VP001) | 0000208590 | 2 |  |  | 0010 | 1130 |  | 2024-01-24 | 10 | 0 | 0 | 0 | 2024-04-04 | 2024-04-12 | 2024-04-14 |  |  | 2024-04-07 |  |  | 2024-06-12 | 0 |  |  | 2024-04-08 | 2024-04-14 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 | /180013852 |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  | /018001385 |  | 90002754 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | KTEK LMT200 Magnetostrictive Transmitter | 2024-04-08 |  |  |  |  | 0010 | INT | Need new Electronics modules LIT-34300 |  |  | 90002754_0010 |  |  | 63 | 63 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002754 | 2024-01-24 |  | 1 | EA | 2024-04-07 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207985 | S001 |  |  |  | 5300005522 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208590 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-14 | 2024-04-14 | 2024-04-14 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
Remote Pick - Low Stock | 4500008163/00080 - Due Date 45390 | - |  | 03.04 ETA 03.04 request PDC to get to MAC 9.04 PO 4500008163 Analytical Con | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10232001 | 10232001 (TUBE,QUARTZ,13IN LG,ENVEENGI 330423) | 20 | 20 | 2 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | WM TO ACTION 27.03: Reschedule ETA 25.04 PO 4500008163 Analytical Control | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | TUBE,QUARTZ,13IN LG,ENVEENGI 330423 | [5 empty] | 0010 | INT | Service Gas Analyser | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500008163/00010 - Due Date 45390 | - |  | 03.04 ETA 03.04 request PDC to get to MAC 9.04 PO 4500008163 Analytical Con | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10231706 | 10231706 (FILTER ELEMENT,HEADLINE 125770C) | 20 | 20 | 2 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,HEADLINE 125770C | [5 empty] | 0010 | INT | Service Gas Analyser | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500008163/00060 - Due Date 45390 | - |  | 03.04 ETA 03.04 request PDC to get to MAC 9.04 PO 4500008163 Analytical Con | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10231709 | 10231709 (GASKET,REAR WINDOW,ENVEENGI 330078) | 20 | 20 | 2 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,REAR WINDOW,ENVEENGI 330078 | [5 empty] | 0010 | INT | Service Gas Analyser | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500008163/00030 - Due Date 45390 | - |  | 03.04 ETA 03.04 request PDC to get to MAC 9.04 PO 4500008163 Analytical Con | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10231999 | 10231999 (WINDOW,REAR,ENVEENGI 330077) | 20 | 20 | 2 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WINDOW,REAR,ENVEENGI 330077 | [5 empty] | 0010 | INT | Service Gas Analyser | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500008163/00040 - Due Date 45390 | - |  | 03.04 ETA 03.04 request PDC to get to MAC 9.04 PO 4500008163 Analytical Con | 24MCGA1 | DU50 | 200129007 | 1Y Inst Svce Gas Analyser (200129007) | Released | 2024-03-19 | 2024-04-14 | 2024-04-14 | 2024-04-15 | 10232005 | 10232005 (O-RING,H/T,KALREZ,EMERSON MC0945) | 20 | 20 | 4 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Analyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203810 | 6 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-14 | [5 empty] | 2024-04-17 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,H/T,KALREZ,EMERSON MC0945 | [5 empty] | 0010 | INT | Service Gas Analyser | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203205 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCGA1 | 2024-04-15 | 2024-04-14 | 2024-04-14 | Pre-costed/Object created/Material shortage/Released/Settlement rule created | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100068676 | Replace PCV 34116 on WHRU A (100068676) | Released | 2024-01-01 | 2024-04-15 | 2024-04-15 | 2024-04-15 |  |  | 99 | 255 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Change PVC 34116 & Leak Test (0010) | Exch WHRU Unit A (DU50.MA.UHT.10.HX003) | 0000208954 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-15 | [5 empty] | 2024-05-01 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Change PVC 34116 & Leak Test | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000208369 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | 4500000998/00010 - Due Date | No Req or Processed |  | IP REVIEW 14.03: SIT to DU01 |  | DU50 | 200126617 | 3M Conduct Electrical Safety Engagement (200126617) | Released | 2024-01-02 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 70001197 | 70001197 (15-20A Single phase test lead adapter) | 20 | 20 | 1 | 1 | 0 | GRST-5000047680_2024 | Material is received @DU50 | Directs (Inventory) (SP14) | No Issue identified | 5300005577 | 1000001254 | 2 | 4500000998 | EX ENGINEERING PTY LTD (30000025) | 2024-04-03 | 2024-04-29 | AUS Operations (106) |  | DU01 | IP REVIEW 14.03: SIT to DU01 | N | Preparation (05) | In Preparation (Order) (0055) | Conduct Electrical Safety Engagement (0010) | Building Admin/Control (DU50.MA.FBD.03.BG001) | 0000201433 | 2 |  | 2024-03-16 | 0010 | 1130 |  | 2024-01-25 | 10 | 0 | 0 | 23 | 2024-04-03 | 2024-03-20 | 2024-04-15 |  |  | 2024-04-06 | 100000019300 | 1010 | 2024-04-15 | 1 | 4900037217_2024_0001 | 5000021427_2024_0001 | 2024-03-14 | 2024-02-19 | S Cowcher | 5000047680_2024_0001 | 0 | 2 | 3 | 1 | 1 | 1 | /180005350 | 180011003 | 0 | CPT | 3 | L | 4900037217 | 2024 | 5000021427 | 5000047680 | 2024 | 2024 | /018000535 | 180011003 | 90002755 | WorkPackLink | 2024-03-14 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 15-20A Single phase test lead adapter | 2024-03-14 |  | 101000000024857 |  |  | 0010 | INT | Conduct Electrical Safety Engagement | 0 |  | 90002755_0010 |  |  | 21 | 21 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002755 | 2024-03-06 |  | 1 | EA | 2024-04-06 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000200797 | S001 | 01-Road |  |  | 5300005577 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 | 101000000025103 | 2024-03-14 | Mac Store | EA |  |  |  | 10 | AU00 | 3-In Transit |  | 20000477 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 201433 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02) |  | 10-07-03-01A
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200130623 | 1Y Test Deluge Fire Suppression GRC (200130623) | Released | 2024-01-01 | 2024-04-15 | 2024-04-15 | 2024-04-30 | 11052392 | 11052392 (FOAM,AR-AFF 1 TO 3%,FIREPROT FS12132202) | 5 | 10 | 2 | 12 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Test Fire Sprn Syst D1 (0080) | Fire Suppression (DU50.MA.UFP.20) | 0000205379 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-15 | [5 empty] | 2024-04-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FOAM,AR-AFF 1 TO 3%,FIREPROT FS12132202 | [5 empty] | 0080 | INT | Test Fire Sprn Syst D1 |  |  |  |  | 21-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000204803 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-04-30 | 2024-04-15 | 2024-04-15 | Released/Settlement rule created/Object created/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132125 | 3Y Cft MO-PSV-37112 (200132125) | Released | 2024-01-01 | 2024-04-15 | 2024-04-15 | 2024-06-10 | 11175286 | 11175286 (VALVE,SAFETY,25*D*50,BELLOWS,CS SA216-WC) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | Replace Pressure Relief Device (0010) | Exch WHRU Unit A (DU50.MA.UHT.10.HX003) | 0000206941 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-15 | [5 empty] | 2024-03-28 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,25*D*50,BELLOWS,CS SA216-WC | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0 | EA |  | 0 | 0 |  | 0 | 4900041689_2024 | 5400000164 | 10 | 1 |  |  | 1000206324 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-10 | 2024-04-15 | 2024-04-15 | Settlement rule created/Pre-costed/Object created/Estimated costs/Goods movement posted/Released/Material committed | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132125 | 3Y Cft MO-PSV-37112 (200132125) | Released | 2024-01-01 | 2024-04-15 | 2024-04-15 | 2024-06-10 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | Replace Pressure Relief Device (0010) | Exch WHRU Unit A (DU50.MA.UHT.10.HX003) | 0000206941 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-15 | [5 empty] | 2024-03-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000206324 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-10 | 2024-04-15 | 2024-04-15 | Settlement rule created/Pre-costed/Object created/Estimated costs/Goods movement posted/Released/Material committed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500007868/00010 - Due Date 45421 | - |  | WM TO ACTION: Reschedule, ETA 09 MAY PO 4500007868 3 x SOH at MAC - Aaron checking with site |  | DU50 | 200130623 | 1Y Test Deluge Fire Suppression GRC (200130623) | Released | 2024-01-01 | 2024-04-15 | 2024-04-15 | 2024-04-30 | 11052391 | 11052391 (FOAM,ARC,FIREPROT FS12132201) | 5 | 10 | 4 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Test Fire Sprn Syst D1 (0080) | Fire Suppression (DU50.MA.UFP.20) | 0000205379 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-15 | [5 empty] | 2024-04-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FOAM,ARC,FIREPROT FS12132201 | [5 empty] | 0080 | INT | Test Fire Sprn Syst D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000204803 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-04-30 | 2024-04-15 | 2024-04-15 | Released/Settlement rule created/Object created/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500006472/00010 - Due Date 45378 | - |  | 03.04 - At PDC requested for next truck ETA 09.04 to MAC |  | DU50 | 200130623 | 1Y Test Deluge Fire Suppression GRC (200130623) | Released | 2024-01-01 | 2024-04-15 | 2024-04-15 | 2024-04-30 | 11153850 | 11153850 (TESTING FLUID,ABLEWEST WC475MV20) | 5 | 10 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | IP REVIEW 20.03: Not Delivered Yet ETA 27.03 4500006472 ABLE WESTCHEM | N | Preparation (05) | In Preparation (Order) (0055) | Test Fire Sprn Syst D1 (0080) | Fire Suppression (DU50.MA.UFP.20) | 0000205379 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-15 | [5 empty] | 2024-04-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | TESTING FLUID,ABLEWEST WC475MV20 | [5 empty] | 0080 | INT | Test Fire Sprn Syst D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000204803 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-04-30 | 2024-04-15 | 2024-04-15 | Released/Settlement rule created/Object created/Material shortage/Pre-costed | Proactive Maintenance (AM02)
No Stock at Base | 4500007339/00010 - Due Date 45373 | No Req or Processed |  | IP REVIEW 19.03: Not delivered yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70004042 | 70004042 (CHLORINE FREE "SWIFTEST" REAGENT DISPENS) | 30 | 30 | 1 | 0 | 0 | IDPO-/018001430 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver in-full | 5300006839 | 1000005692 | 73 | 4500007339 | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-03-22 | 2024-04-06 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: Not delivered yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 73 |  |  | 0350 | 1130 |  | 2024-02-19 | 280 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | Macedon Lab |  | 0 | 2 | 3 | 0 | 0 | 0 | /180014304 |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  | /018001430 |  | 90005891 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CHLORINE FREE "SWIFTEST" REAGENT DISPENS | 2024-04-08 | Supply for Order 500003979, Item 73 cannot be changed 90005891 item 10 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90005891_0010 |  |  | 7 | 7 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90005891 | 2024-03-20 |  | 1 | EA | 2024-04-06 | 73 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 280 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500009340/00060 - Due Date 45405 | No Req or Processed |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70004981 | 70004981 (Loctite 2783777 LB 8009 Heavy Duty Anti) | 30 | 30 | 10 | 0 | 0 | POPO-4500009340_00060 | Vendor PO raised | Directs (Inventory) (SP14) | Issue detected, please check message in derivation | 5300006839 | 1000007165 | 89 | 4500009340 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 2024-08-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 89 |  |  | 0400 | 1130 |  | 2024-02-19 | 350 | 0 | 0 | 60 | 2024-06-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-06-07 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006705 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Loctite 2783777 LB 8009 Heavy Duty Anti | 2024-04-08 | Supply for Order 500003979, Item 89 cannot be changed 90006705 item 60 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90006705_0060 |  |  | 60 | 60 |  | 10 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006705 | 2024-03-27 |  | 10 | EA | 2024-06-07 | 89 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 350 |  |  | 0 | 10 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | [5 empty] | 60 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500005313/00010 - Due Date | No Req or Processed |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70003600 | 70003600 (Bolle 1614401 Safety Spectacles Prism Me) | 30 | 30 | 30 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 52 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 52 | 2024-04-01 | 2024-03-26 | 0190 | 1130 |  | 2024-02-19 | 130 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000022904 | 1010 | 2025-02-10 | 30 | 4900039063_2024_0001 | 5000036822_2024_0001 | 2024-03-21 | 2024-03-14 | PPE Room | 5000047896_2024_0001 | 0 | 2 | 3 | 30 | 30 | 30 | /180010755 | 180012509 | 0 | CPT | 3 | L | 4900039063 | 2024 | 5000036822 | 5000047896 | 2024 | 2024 | /018001075 | 180012509 | 9001232 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Bolle 1614401 Safety Spectacles Prism Me | 2024-04-08 | Supply for Order 500003979, Item 52 cannot be changed 9001232 item 10 already exists | 101000000024818 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9001232_0010 |  |  | 7 | 7 |  | 30 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 0 | EA | 2024-04-06 | 52 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 130 |  |  | 0 | 30 | EA | 0 | 2001 | DU01 | 101000000027245 | 2024-04-08 | Macedon Warehouse | EA |  |  | 2024-03-21 | 10 | AU00 | 5-Completed |  | 20000618 | 1270 | 30 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
In Transit via Road | - | - |  |  |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002839 | 70002839 (CRC 5005 5 56 Multi Purpose Lubricant 40) | 30 | 30 | 18 | 0 | 0 | GIST-4900041306_2024 | Material In-Transit on-01-Road | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002980 | 28 | 4500003342 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-04 | 2024-04-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 28 |  | 2024-03-30 | 0110 | 1130 |  | 2024-02-19 | 70 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000044105 | 1010 | 2025-02-10 | 18 | 4900041306_2024_0001 | 5000047653_2024_0001/5000044886_2024_0001/5000023037_2024_0001 | 2024-03-28 | 2024-03-28 | Techs |  | 0 | 2 | 2 | 0 | 54 | 18 | 180014185//180005873 | 180014411 | 0 | CPT | 3 | L | 4900041306 | 2024 | 5000047653 |  | 0 | 2024 | 180014185 | 180014411 | 9001535 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CRC 5005 5 56 Multi Purpose Lubricant 40 | 2024-04-08 | Supply for Order 500003979, Item 28 cannot be changed 9001535 item 60 already exists | 101000000030143 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9001535_0060 |  |  | 14 | 7 |  | 18 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-14 |  | 18 | EA | 2024-04-06 | 28 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 70 |  |  | 0 | 18 | EA | 18 | 2001 | DU01 | 101000000030040 | 2024-04-08 | Macedon Warehouse | EA |  |  | 2024-03-28 | 70 | AU00 | 3-In Transit |  | 20000762 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500009340/00070 - Due Date 45405 | No Req or Processed |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70005171 | 70005171 (Ansell Earth HyFlex 11 618 General Purpo) | 30 | 30 | 50 | 0 | 0 | POPO-4500009340_00070 | Vendor PO raised | Directs (Inventory) (SP14) | Issue detected, please check message in derivation | 5300006839 | 1000007422 | 91 | 4500009340 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 2024-05-14 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 91 |  |  | 0440 | 1130 |  | 2024-02-19 | 360 | 0 | 0 | 18 | 2024-04-23 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-26 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006936 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Ansell Earth HyFlex 11 618 General Purpo | 2024-04-08 | Supply for Order 500003979, Item 91 cannot be changed 90006936 item 10 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90006936_0010 |  |  | 14 | 14 |  | 50 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006936 | 2024-04-02 |  | 50 | PAA | 2024-04-26 | 91 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 360 |  |  | 0 | 50 | PAA | 0 | 2001 | DU01 |  | 2024-04-08 | [5 empty] | 70 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500003445/00020 - Due Date 45383 | No Req or Processed |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002905 | 70002905 (Thermometer -10/110 degrees P/N GT4750) | 30 | 30 | 1 | 0 | 0 | POPO-4500003445_00020 | Vendor PO raised | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002998 | 40 | 4500003445 | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-01 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 40 |  |  | 0170 | 1130 |  | 2024-02-19 | 110 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | LAB |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 3 | L |  | 0 |  |  | 0 |  |  |  | 90002763 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Thermometer -10/110 degrees P/N GT4750 | 2024-04-08 | Supply for Order 500003979, Item 40 cannot be changed 90002763 item 100 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90002763_0100 |  |  | 7 | 7 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-20 |  | 1 | EA | 2024-04-06 | 40 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 110 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500009340/00020 - Due Date 45405 | No Req or Processed |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70004975 | 70004975 (Bullivants Polypropylene Cable Haul Rope) | 30 | 30 | 1 | 0 | 0 | POPO-4500009340_00020 | Vendor PO raised | Directs (Inventory) (SP14) | Issue detected, please check message in derivation | 5300006839 | 1000007165 | 84 | 4500009340 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 2024-08-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 84 |  |  | 0410 | 1130 |  | 2024-02-19 | 310 | 0 | 0 | 60 | 2024-06-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-06-07 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006705 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Bullivants Polypropylene Cable Haul Rope | 2024-04-08 | Supply for Order 500003979, Item 84 cannot be changed 90006705 item 20 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90006705_0020 |  |  | 60 | 60 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006705 | 2024-03-27 |  | 1 | EA | 2024-06-07 | 84 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 310 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | [5 empty] | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | SOH at DU01 |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000847 | 70000847 (CRC 2016 CO Contact Cleaner Clear 350 gr) | 30 | 30 | 18 | 0 | 18 | ODST-0090002763_0030 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002980 | 25 | 4500003342 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-03 | 2024-04-25 | AUS Operations (106) |  | DU01 | SOH at DU01 | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 25 |  |  | 0120 | 1130 |  | 2024-02-19 | 40 | 0 | 0 | 19 | 2024-04-03 | 2024-03-22 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000023059_2024_0001 | 2024-03-18 | 2024-02-22 | Techs |  | 0 | 2 | 3 | 0 | 18 | 18 | /180005873 |  | 0 | CPT | 3 | L |  | 0 | 5000023059 |  | 0 | 2024 | /018000587 |  | 90002763 | WorkPackLink | 2024-03-18 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CRC 2016 CO Contact Cleaner Clear 350 gr | 2024-03-18 | Supply for Order 500003979, Item 25 cannot be changed 90002763 item 30 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90002763_0030 |  |  | 14 | 14 |  | 18 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-13 |  | 18 | EA | 2024-04-06 | 25 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 40 |  |  | 0 | 18 | EA | 0 | 2001 | DU01 | PACKING | 2024-03-18 | Macedon Warehouse | EA |  |  |  | 40 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | Macedon - MAC NG (DU50)1000007398 / 00114 - Due Date 14/04/2024 |  | ATN PURCHASING 06.03: PR TO PO |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000312 | 70000312 (Sharpie Permanent Marker Fine Tip Black) | 30 | 30 | 5 | 0 | 0 | PRPO-1000004287_00058 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000004287 | 58 |  |  |  | 2024-04-16 |  |  |  | ATN PURCHASING 06.03: PR TO PO | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 58 |  |  | 0260 |  |  |  | 0 | 0 | 0 | 0 | 2024-04-14 |  | 2024-04-16 | [5 empty] | 2025-02-10 | 0 |  |  |  |  | PPE Room |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Sharpie Permanent Marker Fine Tip Black | [5 empty] | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 7 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-04-02 |  | 5 | BOX | 2024-04-16 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000220196 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 0 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007397 / 00113 - Due Date 30/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70005183 | 70005183 (Spirax Notebook Top Opening Black 112x77) | 30 | 30 | 20 | 0 | 0 | PRPO-1000007397_00113 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007397 | 113 |  |  |  | 2024-05-28 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 113 |  |  | 0530 | 1130 |  | 2024-02-19 | 450 | 0 | 0 | 25 | 2024-04-30 | 2024-04-14 | 2024-04-16 |  |  | 2024-05-03 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | Stationary C |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Spirax Notebook Top Opening Black 112x77 | 2024-04-08 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 21 | 21 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 20 | EA | 2024-05-03 | 113 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 450 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007397 / 00112 - Due Date 30/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70005182 | 70005182 (Markrite Notebook Spiral Bound all weath) | 30 | 30 | 20 | 0 | 0 | PRPO-1000007397_00112 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007397 | 112 |  |  |  | 2024-05-28 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 112 |  |  | 0520 | 1130 |  | 2024-02-19 | 440 | 0 | 0 | 25 | 2024-04-30 | 2024-04-14 | 2024-04-16 |  |  | 2024-05-03 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | Stationary C |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Markrite Notebook Spiral Bound all weath | 2024-04-08 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 21 | 21 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 20 | EA | 2024-05-03 | 112 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 440 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500005556/00030 - Due Date 45373 | No Req or Processed |  | IP REVIEW 13.03: Not delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000890 | 70000890 (InvisibleZinc 103699 Mineral Sunscreen S) | 30 | 30 | 20 | 0 | 0 | POPO-4500005556_00030 | Vendor PO raised | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004304 | 68 | 4500005556 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-22 | 2024-04-06 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 68 |  |  | 0310 | 1130 |  | 2024-02-19 | 240 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | PPE Room |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 3 | L |  | 0 |  |  | 0 |  |  |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | InvisibleZinc 103699 Mineral Sunscreen S | 2024-04-08 | Supply for Order 500003979, Item 68 cannot be changed 90003738 item 120 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0120 |  |  | 7 | 7 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 20 | EA | 2024-04-06 | 68 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 240 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 30 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000866 | 70000866 (Ansell HyFlex 11 618 General Purpose Glo) | 30 | 30 | 50 | 0 | 50 | ODST-0090003738_0030 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 54 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 54 |  |  | 0210 | 1130 |  | 2024-02-19 | 150 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000034859_2024_0001 | 2024-04-08 | 2024-03-12 | PPE Room |  | 0 | 2 | 3 | 0 | 50 | 0 | /180010121 |  | 0 | CPT | 3 | L |  | 0 | 5000034859 |  | 0 | 2024 | /018001012 |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Ansell HyFlex 11 618 General Purpose Glo | 2024-04-08 | Supply for Order 500003979, Item 54 cannot be changed 90003738 item 30 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0030 |  |  | 7 | 7 |  | 50 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 50 | PAA | 2024-04-06 | 54 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 150 |  |  | 0 | 50 | PAA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 30 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70003601 | 70003601 (Bolle 1614402 Safety Spectacles Prism Me) | 30 | 30 | 30 | 0 | 30 | ODST-0090003738_0020 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 53 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 53 |  |  | 0200 | 1130 |  | 2024-02-19 | 140 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000034829_2024_0001 | 2024-04-08 | 2024-03-12 | PPE Room |  | 0 | 2 | 3 | 0 | 30 | 0 | /180010121 |  | 0 | CPT | 3 | L |  | 0 | 5000034829 |  | 0 | 2024 | /018001012 |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Bolle 1614402 Safety Spectacles Prism Me | 2024-04-08 | Supply for Order 500003979, Item 53 cannot be changed 90003738 item 20 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0020 |  |  | 7 | 7 |  | 30 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 30 | EA | 2024-04-06 | 53 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 140 |  |  | 0 | 30 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000865 | 70000865 (Ansell HyFlex 11 618 General Purpose Glo) | 30 | 30 | 25 | 0 | 25 | ODST-0090003738_0050 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 56 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 56 |  |  | 0230 | 1130 |  | 2024-02-19 | 170 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000034933_2024_0001 | 2024-04-08 | 2024-03-12 | PPE Room |  | 0 | 2 | 3 | 0 | 25 | 0 | /180010121 |  | 0 | CPT | 3 | L |  | 0 | 5000034933 |  | 0 | 2024 | /018001012 |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Ansell HyFlex 11 618 General Purpose Glo | 2024-04-08 | Supply for Order 500003979, Item 56 cannot be changed 90003738 item 50 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0050 |  |  | 7 | 7 |  | 25 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 25 | PAA | 2024-04-06 | 56 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 170 |  |  | 0 | 25 | PAA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 50 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500009340/00010 - Due Date 45405 | No Req or Processed |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70004974 | 70004974 (Panduit Pan Ty PLT3S C0 Locking Cable Ti) | 30 | 30 | 15 | 0 | 0 | POPO-4500009340_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Issue detected, please check message in derivation | 5300006839 | 1000007165 | 83 | 4500009340 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 2024-08-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 83 |  |  | 0390 | 1130 |  | 2024-02-19 | 300 | 0 | 0 | 60 | 2024-06-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-06-07 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006705 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Panduit Pan Ty PLT3S C0 Locking Cable Ti | 2024-04-08 | Supply for Order 500003979, Item 83 cannot be changed 90006705 item 10 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90006705_0010 |  |  | 60 | 60 |  | 15 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006705 | 2024-03-27 |  | 15 | PAC | 2024-06-07 | 83 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 300 |  |  | 0 | 15 | PAC | 0 | 2001 | DU01 |  | 2024-04-08 | [5 empty] | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500007339/00020 - Due Date 45405 | No Req or Processed |  | IP REVIEW 25.03: MLC confirmed okay for ETA 23.04 Not delivered yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70004051 | 70004051 (ALKALINITY KIT 50-500ppm (K-9815)) | 30 | 30 | 1 | 0 | 0 | IDPO-/018001430 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver in-full | 5300006839 | 1000005731 | 75 | 4500007339 | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-23 | 2024-04-06 | AUS Operations (106) |  | DU01 | IP REVIEW 25.03: MLC confirmed okay for ETA 23.04 Not delivered yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 75 |  |  | 0360 | 1130 |  | 2024-02-19 | 290 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | Macedon Lab |  | 0 | 2 | 3 | 0 | 0 | 0 | /180014304 |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  | /018001430 |  | 90005891 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ALKALINITY KIT 50-500ppm (K-9815) | 2024-04-08 | Supply for Order 500003979, Item 75 cannot be changed 90005891 item 20 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90005891_0020 |  |  | 7 | 7 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90005891 | 2024-03-20 |  | 1 | EA | 2024-04-06 | 75 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 290 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500005556/00010 - Due Date 45373 | No Req or Processed |  | IP REVIEW 13.03: Not delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000954 | 70000954 (Oliver Safety Boots Lace Up Zip 55 332Z) | 30 | 30 | 1 | 0 | 0 | IDPO-/018001096 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver in-full | 5300006839 | 1000004304 | 66 | 4500005556 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-22 | 2024-04-06 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 66 |  |  | 0290 | 1130 |  | 2024-02-19 | 220 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | M Wingeatt |  | 0 | 2 | 3 | 0 | 0 | 0 | /180010968 |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  | /018001096 |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Oliver Safety Boots Lace Up Zip 55 332Z | 2024-04-08 | Supply for Order 500003979, Item 66 cannot be changed 90003738 item 100 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0100 |  |  | 7 | 7 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 1 | PAA | 2024-04-06 | 66 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 220 |  |  | 0 | 1 | PAA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500000229/00040 - Due Date | No Req or Processed |  | IP REVIEW 14.03: SIT to DU01 |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000150 | 70000150 (Capacitor ¦ 8MFD ¦ 450V ¦ Mk450.8) | 30 | 30 | 10 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004631 | 71 | 4500000229 | OCEANIA ENGINEERING SERVICES PTY LTD (30000034) | 2024-01-26 | 2024-04-29 | AUS Operations (106) |  | DU01 | IP REVIEW 14.03: SIT to DU01 | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 71 |  | 2024-03-16 | 0340 | 1130 |  | 2024-02-19 | 270 | 0 | 0 | 23 | 2024-04-04 | 2024-03-20 | 2024-04-16 |  |  | 2024-04-06 | 100000019288 | 1010 | 2025-02-10 | 10 | 4900037358_2024_0001/4900037270_2024_0001 | 5000038184_2024_0001/5000032777_2024_0001 | 2024-03-15 | 2024-03-15 |  | 5000047661_2024_0001/5000038284_2024_0001 | 0 | 2 | 2 | 10 | 10 | 7 | 180011143/180009211/ | 180011195/180011196/180011004 | 0 | EXW | 3 | L | 4900037358 | 2024 | 5000038184 | 5000038284 | 2024 | 2024 | 180011143 | 180011196 | 9000737 | WorkPackLink | 2024-03-14 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Capacitor ¦ 8MFD ¦ 450V ¦ Mk450.8 | 2024-03-14 | Supply for Order 500003979, Item 71 cannot be changed 9000497 item 10 already exists | 101000000025070 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9000737_0010/9000497_0010 |  |  | 1 | 1 |  | 10 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90004665 | 2024-03-25 |  | 0 | EA | 2024-04-06 | 71 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 270 |  |  | 0 | 10 | EA | 0 | 2001 | DU01 | 101000000025103 | 2024-03-14 |  | EA |  |  |  | 40 | AU00 | 3-In Transit |  | 20000477 | 1270 | 10 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500005556/00040 - Due Date 45373 | No Req or Processed |  | IP REVIEW 13.03: Not delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70003609 | 70003609 (JBS Industrial Storage Cupboards Flat To) | 30 | 30 | 1 | 0 | 0 | POPO-4500005556_00040 | Vendor PO raised | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004294 | 62 | 4500005556 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-22 | 2024-04-06 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 62 |  |  | 0280 | 1130 |  | 2024-02-19 | 210 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | M McKenzie |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 3 | L |  | 0 |  |  | 0 |  |  |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | JBS Industrial Storage Cupboards Flat To | 2024-04-08 | Supply for Order 500003979, Item 62 cannot be changed 90003738 item 90 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0090 |  |  | 7 | 7 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 1 | EA | 2024-04-06 | 62 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 210 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon House |  |  |  |  | 40 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002894 | 70002894 (Antibacterial Wipes 'MAXX-PACK' 4 X 1200) | 30 | 30 | 1 | 0 | 1 | ODST-0090002763_0070 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002984 | 31 | 4500003380 | ATOM SUPPLY (30000407) | 2024-03-05 | 2024-04-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 31 |  |  | 0140 | 1130 |  | 2024-02-19 | 80 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000026827_2024_0001 | 2024-04-08 | 2024-02-28 | B Johnson |  | 0 | 2 | 3 | 0 | 1 | 0 | /180006683 |  | 0 | CPT | 3 | L |  | 0 | 5000026827 |  | 0 | 2024 | /018000668 |  | 90002763 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Antibacterial Wipes 'MAXX-PACK' 4 X 1200 | 2024-04-08 | Supply for Order 500003979, Item 31 cannot be changed 90002763 item 70 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90002763_0070 |  |  | 7 | 7 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-20 |  | 1 | PAC | 2024-04-06 | 31 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 80 |  |  | 0 | 1 | PAC | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | Macedon - MAC NG (DU50)1000007398 / 00114 - Due Date 14/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000312 | 70000312 (Sharpie Permanent Marker Fine Tip Black) | 30 | 30 | 4 | 0 | 0 | PRPO-1000007399_00114 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000007399 | 114 |  |  |  | 2024-04-16 |  |  |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 114 |  |  | 0540 |  |  |  | 0 | 0 | 0 | 0 | 2024-04-14 |  | 2024-04-16 | [5 empty] | 2025-02-10 | 0 |  |  |  |  | Stationary C |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Sharpie Permanent Marker Fine Tip Black | [5 empty] | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 7 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-04-02 |  | 4 | BOX | 2024-04-16 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000220196 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 0 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500000229/00040 - Due Date | No Req or Processed |  | IP REVIEW 14.03: SIT to DU01 |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000150 | 70000150 (Capacitor ¦ 8MFD ¦ 450V ¦ Mk450.8) | 30 | 30 | 10 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004631 | 71 | 4500000229 | OCEANIA ENGINEERING SERVICES PTY LTD (30000034) | 2024-01-26 | 2024-04-29 | AUS Operations (106) |  | DU01 | IP REVIEW 14.03: SIT to DU01 | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 71 | 2024-03-15 |  | 0340 | 1130 |  | 2024-02-19 | 270 | 0 | 0 | 23 | 2024-04-04 | 2024-03-20 | 2024-04-16 |  |  | 2024-04-06 | 100000019288 | 1010 | 2025-02-10 | 10 | 4900037358_2024_0001/4900037270_2024_0001 | 5000038184_2024_0001/5000032777_2024_0001 | 2024-03-15 | 2024-03-15 |  | 5000047661_2024_0001/5000038284_2024_0001 | 0 | 2 | 2 | 10 | 10 | 3 | 180011143/180009211/ | 180011195/180011196/180011004 | 0 | EXW | 3 | L | 4900037358 | 2024 | 5000038184 | 5000038284 | 2024 | 2024 | 180011143 | 180011196 | 9000737 | WorkPackLink | 2024-03-14 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Capacitor ¦ 8MFD ¦ 450V ¦ Mk450.8 | 2024-03-14 | Supply for Order 500003979, Item 71 cannot be changed 9000497 item 10 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9000737_0010/9000497_0010 |  |  | 1 | 1 |  | 10 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90004665 | 2024-03-25 |  | 0 | EA | 2024-04-06 | 71 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 270 |  |  | 0 | 10 | EA | 0 | 2001 | DU01 | 101000000025348 | 2024-03-14 |  | EA |  |  |  | 40 | AU00 | 5-Completed |  | 20000592 | 1270 | 10 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
No Stock at Base | 4500002741/00010 - Due Date | No Req or Processed |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002463 | 70002463 (J Burrows A4 Premium Copy Paper 80gsm Wh) | 30 | 30 | 5 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 57 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 57 | 2024-04-01 | 2024-03-26 | 0250 | 1130 |  | 2024-02-19 | 180 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000022904 | 1010 | 2025-02-10 | 5 | 4900039063_2024_0003 | 5000042092_2024_0001/5000042088_2024_0001/5000042047_2024_0001/5000042038_2024_0001/5000041998_2024_0001 | 2024-03-21 | 2024-03-21 | PPE Room | 5000047896_2024_0002 | 0 | 2 | 2 | 5 | 5 | 1 | /180011599 | 180012509 | 0 | CPT | 3 | L | 4900039063 | 2024 | 5000042092 | 5000047896 | 2024 | 2024 | /018001159 | 180012509 | 9001232 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | J Burrows A4 Premium Copy Paper 80gsm Wh | 2024-04-08 | Supply for Order 500003979, Item 57 cannot be changed 9001232 item 60 already exists | 101000000027235 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9001232_0060 |  |  | 7 | 7 |  | 5 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-21 |  | 0 | BOX | 2024-04-06 | 57 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 180 |  |  | 0 | 5 | BOX | 0 | 2001 | DU01 | 101000000027245 | 2024-04-08 | Macedon Warehouse | BOX |  |  | 2024-03-21 | 60 | AU00 | 5-Completed |  | 20000618 | 1270 | 5 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
No Stock at Base | 4500002741/00010 - Due Date | No Req or Processed |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002463 | 70002463 (J Burrows A4 Premium Copy Paper 80gsm Wh) | 30 | 30 | 5 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 57 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 57 | 2024-04-01 | 2024-03-26 | 0250 | 1130 |  | 2024-02-19 | 180 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000022904 | 1010 | 2025-02-10 | 5 | 4900039063_2024_0003 | 5000042092_2024_0001/5000042088_2024_0001/5000042047_2024_0001/5000042038_2024_0001/5000041998_2024_0001 | 2024-03-21 | 2024-03-21 | PPE Room | 5000047896_2024_0002 | 0 | 2 | 2 | 5 | 5 | 1 | /180011599 | 180012509 | 0 | CPT | 3 | L | 4900039063 | 2024 | 5000042092 | 5000047896 | 2024 | 2024 | /018001159 | 180012509 | 9001232 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | J Burrows A4 Premium Copy Paper 80gsm Wh | 2024-04-08 | Supply for Order 500003979, Item 57 cannot be changed 9001232 item 60 already exists | 101000000027242 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9001232_0060 |  |  | 7 | 7 |  | 5 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-21 |  | 0 | BOX | 2024-04-06 | 57 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 180 |  |  | 0 | 5 | BOX | 0 | 2001 | DU01 | 101000000027245 | 2024-04-08 | Macedon Warehouse | BOX |  |  | 2024-03-21 | 60 | AU00 | 5-Completed |  | 20000618 | 1270 | 5 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
No Stock at Base | 4500002741/00010 - Due Date | No Req or Processed |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002463 | 70002463 (J Burrows A4 Premium Copy Paper 80gsm Wh) | 30 | 30 | 5 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 57 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 57 | 2024-04-01 | 2024-03-26 | 0250 | 1130 |  | 2024-02-19 | 180 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000022904 | 1010 | 2025-02-10 | 5 | 4900039063_2024_0003 | 5000042092_2024_0001/5000042088_2024_0001/5000042047_2024_0001/5000042038_2024_0001/5000041998_2024_0001 | 2024-03-21 | 2024-03-21 | PPE Room | 5000047896_2024_0002 | 0 | 2 | 2 | 5 | 5 | 1 | /180011599 | 180012509 | 0 | CPT | 3 | L | 4900039063 | 2024 | 5000042092 | 5000047896 | 2024 | 2024 | /018001159 | 180012509 | 9001232 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | J Burrows A4 Premium Copy Paper 80gsm Wh | 2024-04-08 | Supply for Order 500003979, Item 57 cannot be changed 9001232 item 60 already exists | 101000000027233 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9001232_0060 |  |  | 7 | 7 |  | 5 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-21 |  | 0 | BOX | 2024-04-06 | 57 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 180 |  |  | 0 | 5 | BOX | 0 | 2001 | DU01 | 101000000027245 | 2024-04-08 | Macedon Warehouse | BOX |  |  | 2024-03-21 | 60 | AU00 | 5-Completed |  | 20000618 | 1270 | 5 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
No Stock at Base | 4500002741/00010 - Due Date | No Req or Processed |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002463 | 70002463 (J Burrows A4 Premium Copy Paper 80gsm Wh) | 30 | 30 | 5 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 57 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 57 | 2024-04-01 | 2024-03-26 | 0250 | 1130 |  | 2024-02-19 | 180 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000022904 | 1010 | 2025-02-10 | 5 | 4900039063_2024_0003 | 5000042092_2024_0001/5000042088_2024_0001/5000042047_2024_0001/5000042038_2024_0001/5000041998_2024_0001 | 2024-03-21 | 2024-03-21 | PPE Room | 5000047896_2024_0002 | 0 | 2 | 2 | 5 | 5 | 1 | /180011599 | 180012509 | 0 | CPT | 3 | L | 4900039063 | 2024 | 5000042092 | 5000047896 | 2024 | 2024 | /018001159 | 180012509 | 9001232 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | J Burrows A4 Premium Copy Paper 80gsm Wh | 2024-04-08 | Supply for Order 500003979, Item 57 cannot be changed 9001232 item 60 already exists | 101000000027232 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9001232_0060 |  |  | 7 | 7 |  | 5 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-21 |  | 0 | BOX | 2024-04-06 | 57 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 180 |  |  | 0 | 5 | BOX | 0 | 2001 | DU01 | 101000000027245 | 2024-04-08 | Macedon Warehouse | BOX |  |  | 2024-03-21 | 60 | AU00 | 5-Completed |  | 20000618 | 1270 | 5 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
No Stock at Base | 4500002741/00010 - Due Date | No Req or Processed |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002463 | 70002463 (J Burrows A4 Premium Copy Paper 80gsm Wh) | 30 | 30 | 5 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 57 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 57 | 2024-04-01 | 2024-03-26 | 0250 | 1130 |  | 2024-02-19 | 180 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000022904 | 1010 | 2025-02-10 | 5 | 4900039063_2024_0003 | 5000042092_2024_0001/5000042088_2024_0001/5000042047_2024_0001/5000042038_2024_0001/5000041998_2024_0001 | 2024-03-21 | 2024-03-21 | PPE Room | 5000047896_2024_0002 | 0 | 2 | 2 | 5 | 5 | 1 | /180011599 | 180012509 | 0 | CPT | 3 | L | 4900039063 | 2024 | 5000042092 | 5000047896 | 2024 | 2024 | /018001159 | 180012509 | 9001232 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | J Burrows A4 Premium Copy Paper 80gsm Wh | 2024-04-08 | Supply for Order 500003979, Item 57 cannot be changed 9001232 item 60 already exists | 101000000027234 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9001232_0060 |  |  | 7 | 7 |  | 5 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-21 |  | 0 | BOX | 2024-04-06 | 57 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 180 |  |  | 0 | 5 | BOX | 0 | 2001 | DU01 | 101000000027245 | 2024-04-08 | Macedon Warehouse | BOX |  |  | 2024-03-21 | 60 | AU00 | 5-Completed |  | 20000618 | 1270 | 5 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70003603 | 70003603 (Energizer EN92 Battery Industrial Alkali) | 30 | 30 | 60 | 0 | 60 | ODST-0090003738_0080 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 60 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 60 |  |  | 0240 | 1130 |  | 2024-02-19 | 200 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000033003_2024_0001 | 2024-04-08 | 2024-03-08 | Stationary C |  | 0 | 2 | 3 | 0 | 60 | 0 | /180009684 |  | 0 | CPT | 3 | L |  | 0 | 5000033003 |  | 0 | 2024 | /018000968 |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Energizer EN92 Battery Industrial Alkali | 2024-04-08 | Supply for Order 500003979, Item 60 cannot be changed 90003738 item 80 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0080 |  |  | 7 | 7 |  | 60 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 60 | EA | 2024-04-06 | 60 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 200 |  |  | 0 | 60 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 80 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500005313/00070 - Due Date 45372 | No Req or Processed |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70003602 | 70003602 (New Balance Contour MIDCNTR2E Men Safety) | 30 | 30 | 1 | 0 | 0 | POPO-4500005313_00070 | Vendor PO raised | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 59 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 59 |  |  | 0270 | 1130 |  | 2024-02-19 | 190 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | M McKenzie |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 3 | L |  | 0 |  |  | 0 |  |  |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | New Balance Contour MIDCNTR2E Men Safety | 2024-04-08 | Supply for Order 500003979, Item 59 cannot be changed 90003738 item 70 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0070 |  |  | 7 | 7 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 1 | PAA | 2024-04-06 | 59 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 190 |  |  | 0 | 1 | PAA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 70 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000847 | 70000847 (CRC 2016 CO Contact Cleaner Clear 350 gr) | 30 | 30 | 12 | 0 | 18 | POPO-4500009340_00030 | Vendor PO raised | Directs (Inventory) (SP14) | Issue detected, please check message in derivation | 5300006839 | 1000007165 | 85 | 4500009340 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 2024-05-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 85 |  |  | 0420 | 1130 |  | 2024-02-19 | 320 | 0 | 0 | 14 | 2024-04-19 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-22 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006705 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CRC 2016 CO Contact Cleaner Clear 350 gr | 2024-04-08 | Supply for Order 500003979, Item 85 cannot be changed 90006705 item 30 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90006705_0030 |  |  | 14 | 14 |  | 12 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006705 | 2024-03-27 |  | 12 | EA | 2024-04-22 | 85 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 320 |  |  | 0 | 12 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | [5 empty] | 30 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007452 / 00099 - Due Date 22/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70005166 | 70005166 (DISTILLED (DEMIN.) WATER IN NATURAL HDPE) | 30 | 30 | 1 | 0 | 0 | PRPO-1000007452_00099 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007452 | 99 |  |  |  | 2024-05-12 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 99 |  |  | 0480 | 1130 |  | 2024-02-19 | 400 | 0 | 0 | 17 | 2024-04-22 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-25 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | Macedon Lab |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DISTILLED (DEMIN.) WATER IN NATURAL HDPE | 2024-04-08 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 12 | 12 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-03 |  | 1 | EA | 2024-04-25 | 99 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 400 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
In Transit via Road | - | - |  |  |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002906 | 70002906 (Perfecto HT 5 Heat transfer oil 205l) | 30 | 30 | 4 | 0 | 0 | GIST-4900037160_2024 | Material In-Transit on-01-Road | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002998 | 42 | 4500003488 | CASTROL PERFORMANCE LUBRICANTS CASTROL AUSTRALIA PTY LIMITED (30001101) | 2024-02-22 | 2024-04-25 | AUS Operations (106) |  | DU01 | IP REVIEW 12.03: On track at DU01 awaiting SIT | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 42 | 2024-03-14 | 2024-03-13 | 0180 | 1130 |  | 2024-02-19 | 120 | 0 | 0 | 19 | 2024-04-03 | 2024-03-22 | 2024-04-16 |  |  | 2024-04-06 | 100000018575 | 1010 | 2025-02-10 | 12 | 4900037160_2024_0001/4900037108_2024_0001/4900037105_2024_0001 | 5000033943_2024_0001 | 2024-03-14 | 2024-03-11 | H Lamp |  | 0 | 2 | 3 | 0 | 4 | 4 | 180007424 | 180010890 | 0 | CPT | 3 | L | 4900037160 | 2024 | 5000033943 |  | 0 | 2024 | 180007424 | 180010890 | 9000921 | WorkPackLink | 2024-03-18 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Perfecto HT 5 Heat transfer oil 205l | 2024-03-18 | Supply for Order 500003979, Item 42 cannot be changed 9000921 item 110 already exists | 101000000023843 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9000921_0110 |  |  | 7 | 7 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-20 |  | 4 | EA | 2024-04-06 | 42 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 120 |  |  | 0 | 4 | EA | 4 | 2001 | DU01 | 101000000023849 | 2024-03-18 | Macedon Warehouse | EA |  |  |  | 10 | AU00 | 5-Completed |  | 20000377 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
In Transit via Road | - | - |  |  |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002906 | 70002906 (Perfecto HT 5 Heat transfer oil 205l) | 30 | 30 | 4 | 0 | 0 | GIST-4900037108_2024 | Material In-Transit on-01-Road | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002998 | 42 | 4500003488 | CASTROL PERFORMANCE LUBRICANTS CASTROL AUSTRALIA PTY LIMITED (30001101) | 2024-02-22 | 2024-04-25 | AUS Operations (106) |  | DU01 | IP REVIEW 12.03: On track at DU01 awaiting SIT | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 42 | 2024-03-14 | 2024-03-13 | 0180 | 1130 |  | 2024-02-19 | 120 | 0 | 0 | 19 | 2024-04-03 | 2024-03-22 | 2024-04-16 |  |  | 2024-04-06 | 100000018574 | 1010 | 2025-02-10 | 12 | 4900037160_2024_0001/4900037108_2024_0001/4900037105_2024_0001 | 5000033943_2024_0001 | 2024-03-14 | 2024-03-11 | H Lamp |  | 0 | 2 | 3 | 0 | 4 | 4 | 180007424 | 180010890 | 0 | CPT | 3 | L | 4900037108 | 2024 | 5000033943 |  | 0 | 2024 | 180007424 | 180010890 | 9000921 | WorkPackLink | 2024-03-18 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Perfecto HT 5 Heat transfer oil 205l | 2024-03-18 | Supply for Order 500003979, Item 42 cannot be changed 9000921 item 110 already exists | 101000000023843 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9000921_0110 |  |  | 7 | 7 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-20 |  | 4 | EA | 2024-04-06 | 42 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 120 |  |  | 0 | 4 | EA | 4 | 2001 | DU01 | 101000000023849 | 2024-03-18 | Macedon Warehouse | EA |  |  |  | 10 | AU00 | 5-Completed |  | 20000377 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | Macedon - MAC NG (DU50)1000007456 / 00117 - Due Date 19/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000255 | 70000255 (Thread Sealing Tapes Stainless Steel Sil) | 30 | 30 | 30 | 0 | 0 | PRPO-1000007166_00088 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000007166 | 88 |  |  |  | 2024-04-16 |  |  |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 88 |  |  | 0380 |  |  |  | 0 | 0 | 0 | 0 | 2024-04-14 |  | 2024-04-16 | [5 empty] | 2025-02-10 | 0 | [6 empty] | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Thread Sealing Tapes Stainless Steel Sil | [5 empty] | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 12 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-03-28 |  | 30 | EA | 2024-04-16 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000220196 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 0 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007452 / 00101 - Due Date 16/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70005167 | 70005167 (DRAGER TUBE HYDROGEN SULFIDE 0.2-5ppm (8) | 30 | 30 | 1 | 0 | 0 | PRPO-1000007452_00101 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007452 | 101 |  |  |  | 2024-04-30 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 101 |  |  | 0490 | 1130 |  | 2024-02-19 | 410 | 0 | 0 | 11 | 2024-04-16 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-19 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | Macedon Lab |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DRAGER TUBE HYDROGEN SULFIDE 0.2-5ppm (8 | 2024-04-08 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 7 | 7 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 1 | EA | 2024-04-19 | 101 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 410 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | AT MAC |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70003591 | 70003591 (3M S76SP AT010657586 Spectacles Whim Cre) | 30 | 30 | 5 | 0 | 5 | ODST-0090003738_0110 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004304 | 67 | 4500005556 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-22 | 2024-04-06 | AUS Operations (106) |  | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 67 |  |  | 0300 | 1130 |  | 2024-02-19 | 230 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000033473_2024_0001 | 2024-04-08 | 2024-03-09 | M Wingeatt |  | 0 | 2 | 3 | 0 | 5 | 0 | /180009869 |  | 0 | CPT | 3 | L |  | 0 | 5000033473 |  | 0 | 2024 | /018000986 |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 3M S76SP AT010657586 Spectacles Whim Cre | 2024-04-08 | Supply for Order 500003979, Item 67 cannot be changed 90003738 item 110 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0110 |  |  | 7 | 7 |  | 5 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 5 | EA | 2024-04-06 | 67 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 230 |  |  | 0 | 5 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002850 | 70002850 (Hamilton 7242 Sunscreen Lotion Sensitive) | 30 | 30 | 20 | 0 | 20 | ODST-0090002763_0050 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002980 | 27 | 4500003342 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-04 | 2024-04-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 27 |  |  | 0080 | 1130 |  | 2024-02-19 | 60 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000023057_2024_0001 | 2024-04-08 | 2024-02-22 | M McKenzie |  | 0 | 2 | 2 | 0 | 20 | 0 | /180005868 |  | 0 | CPT | 3 | L |  | 0 | 5000023057 |  | 0 | 2024 | /018000586 |  | 90002763 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Hamilton 7242 Sunscreen Lotion Sensitive | 2024-04-08 | Supply for Order 500003979, Item 27 cannot be changed 90002763 item 50 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90002763_0050 |  |  | 14 | 7 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-14 |  | 20 | EA | 2024-04-06 | 27 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 60 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 60 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500001105/00010 - Due Date | Macedon - MAC NG (DU50)1000007398 / 00111 - Due Date 14/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000305 | 70000305 (Sqwincher Qwik Stiks Mixed Pack Pack of) | 30 | 30 | 10 | 0 | 0 | GRPO-5000023829_2024 | Material received @DU50 | Direct to Remote (SP96) | PO Received; vendor delivered late |  | 1000002981 | 23 | 4500003501 | J BLACKWOOD AND SON LTD (30000394) | 2024-02-20 | 2024-04-16 | AUS Operations (106) |  |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 23 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 | 2024-04-14 |  | 2024-04-16 | [5 empty] | 2025-02-10 | 0 |  | 5000023829_2024_0001 |  | 2024-02-23 | M McKenzie |  | 0 | 0 | 2 | 0 | 10 | 0 | 180006093/ |  | 0 | CPT | 1 | L |  | 0 | 5000023829 |  | 0 | 2024 | 180006093 |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Sqwincher Qwik Stiks Mixed Pack Pack of |  | Supply for Order 500003979, Item 23 cannot be changed – 4500003501 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 7 | 0 |  | 10 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-03-28 |  | 10 | PAC | 2024-04-16 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000220196 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Warehouse |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 0 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500003342/00030 - Due Date 45386 | No Req or Processed |  | IP REVIEW 14.03: Not Delivered Yet ETA 04.04 |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70001767 | 70001767 (Sqwincher Frozen Squeeze Pops Pack of 10) | 30 | 30 | 20 | 0 | 0 | POPO-4500003342_00030 | Vendor PO raised | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002980 | 24 | 4500003342 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-04 | 2024-04-06 | AUS Operations (106) |  | DU01 | IP REVIEW 14.03: Not Delivered Yet ETA 04.04 | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 24 |  |  | 0100 | 1130 |  | 2024-02-19 | 30 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | M McKenzie |  | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | CPT | 3 | L |  | 0 |  |  | 0 |  |  |  | 90002763 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Sqwincher Frozen Squeeze Pops Pack of 10 | 2024-04-08 | Supply for Order 500003979, Item 24 cannot be changed 90002763 item 20 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90002763_0020 |  |  | 14 | 7 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-14 |  | 20 | PAC | 2024-04-06 | 24 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 30 |  |  | 0 | 20 | PAC | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 30 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Low Stock at Base | 4500003342/00050 - Due Date | No Req or Processed |  | IP REVIEW 14.03: SIT to DU01 |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002893 | 70002893 (Cabac 40HDMI1 4MM10 Male Male Cable HDMI) | 30 | 30 | 10 | 0 | 2 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002980 | 26 | 4500003342 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-03 | 2024-04-06 | AUS Operations (106) |  | DU01 | IP REVIEW 14.03: SIT to DU01 | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 26 |  | 2024-03-16 | 0130 | 1130 |  | 2024-02-19 | 50 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000019300 | 1010 | 2025-02-10 | 8 | 4900037273_2024_0003 | 5000029548_2024_0001/5000023034_2024_0001 | 2024-03-14 | 2024-03-05 | B Johnson | 5000047671_2024_0002 | 0 | 2 | 3 | 8 | 10 | 8 | /180005868 | 180011012 | 0 | CPT | 3 | L | 4900037273 | 2024 | 5000029548 | 5000047671 | 2024 | 2024 | /018000586 | 180011012 | 9000498 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Cabac 40HDMI1 4MM10 Male Male Cable HDMI | 2024-04-08 | Supply for Order 500003979, Item 26 cannot be changed 90002763 item 40 already exists | 101000000024858 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90002763_0040/9000498_0040 |  |  | 7 | 7 |  | 10 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-20 |  | 2 | EA | 2024-04-06 | 26 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 50 |  |  | 0 | 10 | EA | 0 | 2001 | DU01 | 101000000025103 | 2024-04-08 | Macedon Warehouse | EA |  |  |  | 50 | AU00 | 3-In Transit |  | 20000477 | 1270 | 8 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007397 / 00115 - Due Date 30/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70005184 | 70005184 (BIC Pen 4 Colour Medium Tip 32mm Box of) | 30 | 30 | 3 | 0 | 0 | PRPO-1000007397_00115 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007397 | 115 |  |  |  | 2024-05-28 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 115 |  |  | 0550 | 1130 |  | 2024-02-19 | 460 | 0 | 0 | 25 | 2024-04-30 | 2024-04-14 | 2024-04-16 |  |  | 2024-05-03 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | Stationary C |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BIC Pen 4 Colour Medium Tip 32mm Box of | 2024-04-08 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 21 | 21 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 3 | BOX | 2024-05-03 | 115 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 460 |  |  | 0 | 3 | BOX | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500003445/00010 - Due Date 45383 | PDC - MAC NG (DU01)1000007452 / 00097 - Due Date 30/04/2024 |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002669 | 70002669 (Sample Cell matched pair 1cm P/N KH2001) | 30 | 30 | 1 | 0 | 0 | POPO-4500003445_00010 | Vendor PO raised | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002998 | 38 | 4500003445 | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-01 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 38 |  |  | 0160 | 1130 |  | 2024-02-19 | 100 | 0 | 0 | 0 | 2024-04-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 | LAB |  | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | CPT | 3 | L |  | 0 |  |  | 0 |  |  |  | 90002763 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Sample Cell matched pair 1cm P/N KH2001 | 2024-04-08 | Supply for Order 500003979, Item 38 cannot be changed 90002763 item 90 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90002763_0090 |  |  | 7 | 7 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-21 |  | 1 | EA | 2024-04-06 | 38 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 100 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500001105/00010 - Due Date | Macedon - MAC NG (DU50)1000007398 / 00111 - Due Date 14/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000305 | 70000305 (Sqwincher Qwik Stiks Mixed Pack Pack of) | 30 | 30 | 5 | 0 | 0 | PRPO-1000007399_00111 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000007399 | 111 |  |  |  | 2024-04-16 |  |  |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 111 |  |  | 0560 |  |  |  | 0 | 0 | 0 | 0 | 2024-04-14 |  | 2024-04-16 | [5 empty] | 2025-02-10 | 0 |  |  |  |  | Crib |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Sqwincher Qwik Stiks Mixed Pack Pack of | [5 empty] | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 7 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-04-02 |  | 5 | PAC | 2024-04-16 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000220196 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 0 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Low Stock at Base | 4500003342/00020 - Due Date | No Req or Processed |  | IP REVIEW 14.03: SIT to DU01 |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002829 | 70002829 (Bullivants Ratchet Assembly J Hook 35mm) | 30 | 30 | 25 | 0 | 15 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002980 | 22 | 4500003342 | J BLACKWOOD AND SON LTD (30000394) | 2024-05-07 | 2024-04-02 | AUS Operations (106) |  | DU01 | IP REVIEW 14.03: SIT to DU01 | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 22 |  | 2024-03-16 | 0070 | 1130 |  | 2024-02-19 | 20 | 0 | 0 | 0 | 2024-03-28 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-02 | 100000019300 | 1010 | 2025-02-10 | 10 | 4900037273_2024_0001 | 5000026753_2024_0001/5000025095_2024_0001/5000024252_2024_0001/5000023113_2024_0001 | 2024-03-14 | 2024-02-28 | M McKenzie | 5000047671_2024_0001 | 0 | 2 | 5 | 10 | 25 | 10 | /180007084/180006600/180006204/180005868 | 180011012 | 0 | CPT | 3 | L | 4900037273 | 2024 | 5000026753 | 5000047671 | 2024 | 2024 | /018000708 | 180011012 | 9000498 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Bullivants Ratchet Assembly J Hook 35mm | 2024-04-08 | Supply for Order 500003979, Item 22 cannot be changed 90002763 item 10 already exists | 101000000024859 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90002763_0010/9000498_0010 |  |  | 14 | 7 |  | 25 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-07 |  | 15 | EA | 2024-04-02 | 22 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 20 |  |  | 0 | 25 | EA | 0 | 2001 | DU01 | 101000000025103 | 2024-04-08 | Macedon Warehouse | EA |  |  |  | 20 | AU00 | 3-In Transit |  | 20000477 | 1270 | 10 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
No Stock at Base | 4500009340/00040 - Due Date 45405 | No Req or Processed |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70004976 | 70004976 (Jamec Pem Air Blow Gun Pistol Grip Brass) | 30 | 30 | 2 | 0 | 0 | POPO-4500009340_00040 | Vendor PO raised | Directs (Inventory) (SP14) | Issue detected, please check message in derivation | 5300006839 | 1000007165 | 86 | 4500009340 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 2024-08-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 86 |  |  | 0430 | 1130 |  | 2024-02-19 | 330 | 0 | 0 | 60 | 2024-06-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-06-07 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006705 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Jamec Pem Air Blow Gun Pistol Grip Brass | 2024-04-08 | Supply for Order 500003979, Item 86 cannot be changed 90006705 item 40 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90006705_0040 |  |  | 60 | 60 |  | 2 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006705 | 2024-03-27 |  | 2 | EA | 2024-06-07 | 86 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 330 |  |  | 0 | 2 | EA | 0 | 2001 | DU01 |  | 2024-04-08 | [5 empty] | 40 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70000864 | 70000864 (Ansell HyFlex 11 618 General Purpose Glo) | 30 | 30 | 50 | 0 | 50 | ODST-0090003738_0040 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000004286 | 55 | 4500005313 | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 2024-04-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 55 |  |  | 0220 | 1130 |  | 2024-02-19 | 160 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 |  |  | 2025-02-10 | 0 |  | 5000034912_2024_0001/5000032538_2024_0001 | 2024-04-08 | 2024-03-12 | PPE Room |  | 0 | 2 | 3 | 0 | 50 | 0 | /180010121/180009573 |  | 0 | CPT | 3 | L |  | 0 | 5000034912 |  | 0 | 2024 | /018001012 |  | 90003738 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Ansell HyFlex 11 618 General Purpose Glo | 2024-04-08 | Supply for Order 500003979, Item 55 cannot be changed 90003738 item 40 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90003738_0040 |  |  | 7 | 7 |  | 50 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90003738 | 2024-03-20 |  | 50 | PAA | 2024-04-06 | 55 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 160 |  |  | 0 | 50 | PAA | 0 | 2001 | DU01 |  | 2024-04-08 | Macedon Warehouse |  |  |  |  | 40 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500009340/00050 - Due Date 45405 | No Req or Processed |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70004980 | 70004980 (Tesa Tape PVC Ducting Rubber Based Silve) | 30 | 30 | 30 | 0 | 0 | POPO-4500009340_00050 | Vendor PO raised | Directs (Inventory) (SP14) | Issue detected, please check message in derivation | 5300006839 | 1000007165 | 87 | 4500009340 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 2024-08-06 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 87 |  |  | 0370 | 1130 |  | 2024-02-19 | 340 | 0 | 0 | 60 | 2024-06-04 | 2024-04-14 | 2024-04-16 |  |  | 2024-06-07 |  |  | 2025-02-10 | 0 |  |  | 2024-04-08 | 2024-04-16 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006705 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Tesa Tape PVC Ducting Rubber Based Silve | 2024-04-08 | Supply for Order 500003979, Item 87 cannot be changed 90006705 item 50 already exists |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 90006705_0050 |  |  | 60 | 60 |  | 30 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006705 | 2024-03-27 |  | 30 | ROL | 2024-06-07 | 87 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 340 |  |  | 0 | 30 | ROL | 0 | 2001 | DU01 |  | 2024-04-08 | [5 empty] | 50 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500003380/00020 - Due Date | No Req or Processed |  | IP REVIEW 19.03: SIT to DU50 |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002895 | 70002895 (Bucket Plastic Dispenser Empty For WOW W) | 30 | 30 | 5 | 0 | 0 |  | Material Consumed | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002984 | 32 | 4500003380 | ATOM SUPPLY (30000407) | 2024-03-05 | 2024-04-06 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: SIT to DU50 | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 32 | 2024-03-27 | 2024-03-09 | 0150 | 1130 | 070324 MACEDON | 2024-02-19 | 90 | 0 | 0 | 0 | 2024-04-03 | 2024-04-14 | 2024-04-16 |  |  | 2024-04-06 | 100000016815 | 1010 | 2025-02-10 | 5 | 4900035457_2024_0001 | 5000030944_2024_0001 | 2024-03-07 | 2024-03-06 | B Johnson | 5000046961_2024_0001 | 0 | 2 | 3 | 5 | 5 | 5 | 180008315/ | 180009476 | 0 | CPT | 3 | L | 4900035457 | 2024 | 5000030944 | 5000046961 | 2024 | 2024 | 180008315 | 180009476 | 9000457 | WorkPackLink | 2024-04-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Bucket Plastic Dispenser Empty For WOW W | 2024-04-08 | Supply for Order 500003979, Item 32 cannot be changed 9000457 item 80 already exists | 101000000022870 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9000457_0080 |  |  | 7 | 7 |  | 5 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-20 |  | 0 | EA | 2024-04-06 | 32 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 90 |  |  | 0 | 5 | EA | 0 | 2001 | DU01 | 101000000023047 | 2024-04-08 | Macedon Warehouse | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 5 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05) |  | 10-07-02-04A
In Transit via Road | - | - |  |  |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 70002906 | 70002906 (Perfecto HT 5 Heat transfer oil 205l) | 30 | 30 | 4 | 0 | 0 | GIST-4900037105_2024 | Material In-Transit on-01-Road | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000002998 | 42 | 4500003488 | CASTROL PERFORMANCE LUBRICANTS CASTROL AUSTRALIA PTY LIMITED (30001101) | 2024-02-22 | 2024-04-25 | AUS Operations (106) |  | DU01 | IP REVIEW 12.03: On track at DU01 awaiting SIT | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 42 | 2024-03-14 | 2024-03-13 | 0180 | 1130 |  | 2024-02-19 | 120 | 0 | 0 | 19 | 2024-04-03 | 2024-03-22 | 2024-04-16 |  |  | 2024-04-06 | 100000018572 | 1010 | 2025-02-10 | 12 | 4900037160_2024_0001/4900037108_2024_0001/4900037105_2024_0001 | 5000033943_2024_0001 | 2024-03-14 | 2024-03-11 | H Lamp |  | 0 | 2 | 3 | 0 | 4 | 4 | 180007424 | 180010890 | 0 | CPT | 3 | L | 4900037105 | 2024 | 5000033943 |  | 0 | 2024 | 180007424 | 180010890 | 9000921 | WorkPackLink | 2024-03-18 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Perfecto HT 5 Heat transfer oil 205l | 2024-03-18 | Supply for Order 500003979, Item 42 cannot be changed 9000921 item 110 already exists | 101000000023843 |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES |  |  | 9000921_0110 |  |  | 7 | 7 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002763 | 2024-03-20 |  | 4 | EA | 2024-04-06 | 42 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 | 01-Road |  |  | 5300006839 | 120 |  |  | 0 | 4 | EA | 4 | 2001 | DU01 | 101000000023849 | 2024-03-18 | Macedon Warehouse | EA |  |  |  | 10 | AU00 | 5-Completed |  | 20000377 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | 4500006100/00020 - Due Date 45383 | No Req or Processed |  | AT MAC |  | DU50 | 100068077 | Replace Urinal Solenoid (100068077) | Released | 2024-01-01 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 70003682 | 70003682 (Procurement and Del to Centurion) | 30 | 30 | 1 | 0 | 0 | POPO-4500006100_00020 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300007500 | 1000004424 | 5 | 4500006100 | ROTATION SOLUTIONS ROTATION SOLUTIONS PTY LTD (30000246) | 2024-04-01 | 2024-04-14 | AUS Operations (106) |  | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Replace Urinal Solenoid (0010) | Building Admin/Control (DU50.MA.FBD.03.BG001) | 0000208386 | 5 |  |  | 0020 | 1130 |  | 2024-03-05 | 20 | 0 | 0 | 2 | 2024-04-09 | 2024-04-16 | 2024-04-18 |  |  | 2024-04-12 |  |  | 2024-05-04 | 0 |  |  | 2024-04-10 | 2024-04-18 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006031 | WorkPackLink | 2024-04-10 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Procurement and Del to Centurion | 2024-04-10 |  |  |  |  | 0010 | INT | Replace Urinal Solenoid |  |  | 90006031_0020 |  |  | 28 | 28 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006031 | 2024-03-05 |  | 1 | EA | 2024-04-12 | 5 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207769 | S001 |  |  |  | 5300007500 | 20 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-10 | Mac Store |  |  |  |  | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208386 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-18 | 2024-04-18 | 2024-04-18 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage/Ready For Scheduling Canceled | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504621 | 10504621 (O-RING,BRANLUEBBE BL090105) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 24 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,BRANLUEBBE BL090105 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504755 | 10504755 (DIAPHRAGM,MEMBRANE,BRANLUEBBE BL051040) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 28 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DIAPHRAGM,MEMBRANE,BRANLUEBBE BL051040 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504731 | 10504731 (RING,BU,SUPPORT,BRANLUEBBE BL150466) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 27 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | RING,BU,SUPPORT,BRANLUEBBE BL150466 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504619 | 10504619 (O-RING,HARDNESS,BRANLUEBBE BL152197) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 22 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,HARDNESS,BRANLUEBBE BL152197 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504620 | 10504620 (SEAL RING,BRANLUEBBE BL051043) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 23 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL RING,BRANLUEBBE BL051043 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504623 | 10504623 (O-RING,BRANLUEBBE BL152228) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 26 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,BRANLUEBBE BL152228 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504622 | 10504622 (O-RING,BRANLUEBBE BL152072) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 25 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,BRANLUEBBE BL152072 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504617 | 10504617 (O-RING,BRANLUEBBE BL051041) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 20 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,BRANLUEBBE BL051041 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10504618 | 10504618 (SEAL RING,GRV,PE,BRANLUEBBE BL369637) | 30 | 30 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 21 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL RING,GRV,PE,BRANLUEBBE BL369637 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Pick - Low Stock | No PO | - |  | WM TO ACTION 03.04:Reschedule ATN PURCHASING PR to PO -1 x SOH at DU50 | 24MCMEOH | DU50 | 100070465 | 1.Overhaul MEOH B Pump / Remove & Replac (100070465) | Released | 2024-01-02 | 2024-04-18 | 2024-01-08 | 2024-04-18 | 10384751 | 10384751 (VALVE,30MM FEEDER,BRANLUEBBE BL051757) | 30 | 30 | 2 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Mech-Reinstall Pump Assembly (0050) | Pump B Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU002) | 0000210743 | 29 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-18 | [5 empty] | 2024-06-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,30MM FEEDER,BRANLUEBBE BL051757 | [5 empty] | 0050 | INT | Mech-Reinstall Pump Assembly | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000210078 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCMEOH | 2024-04-18 | 2024-01-08 | 2024-01-08 | Material shortage/Partially confirmed/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100069639 | Replace Pulsation Dampeners 390-V-303A/B (100069639) | Released | 2024-01-02 | 2024-04-19 | 2024-04-18 | 2024-04-19 |  |  | 99 | 255 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pulsation Dampeners 390-V-303A/B (0020) | Pump A Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU001) | 0000209948 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-19 | [5 empty] | 2024-06-11 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace Pulsation Dampeners 390-V-303A/B | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209331 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCMEOH | 2024-04-19 | 2024-04-18 | 2024-04-18 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100069639 | Replace Pulsation Dampeners 390-V-303A/B (100069639) | Released | 2024-01-02 | 2024-04-19 | 2024-04-18 | 2024-04-19 |  |  | 99 | 255 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pulsation Dampeners 390-V-303A/B (0020) | Pump A Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU001) | 0000209948 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-19 | [5 empty] | 2024-06-11 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace Pulsation Dampeners 390-V-303A/B | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209331 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCMEOH | 2024-04-19 | 2024-04-18 | 2024-04-18 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100069639 | Replace Pulsation Dampeners 390-V-303A/B (100069639) | Released | 2024-01-02 | 2024-04-19 | 2024-04-18 | 2024-04-19 |  |  | 99 | 255 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pulsation Dampeners 390-V-303A/B (0020) | Pump A Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU001) | 0000209948 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-19 | [5 empty] | 2024-06-11 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace Pulsation Dampeners 390-V-303A/B | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209331 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCMEOH | 2024-04-19 | 2024-04-18 | 2024-04-18 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100069639 | Replace Pulsation Dampeners 390-V-303A/B (100069639) | Released | 2024-01-02 | 2024-04-19 | 2024-04-18 | 2024-04-19 |  |  | 99 | 255 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pulsation Dampeners 390-V-303A/B (0020) | Pump A Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU001) | 0000209948 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-19 | [5 empty] | 2024-06-11 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace Pulsation Dampeners 390-V-303A/B | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209331 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCMEOH | 2024-04-19 | 2024-04-18 | 2024-04-18 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCMEOH | DU50 | 100069639 | Replace Pulsation Dampeners 390-V-303A/B (100069639) | Released | 2024-01-02 | 2024-04-19 | 2024-04-18 | 2024-04-19 |  |  | 99 | 255 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pulsation Dampeners 390-V-303A/B (0020) | Pump A Hydrate Inhibitor Injection (DU50.MA.NCI.14.PU001) | 0000209948 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-19 | [5 empty] | 2024-06-11 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace Pulsation Dampeners 390-V-303A/B | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209331 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCMEOH | 2024-04-19 | 2024-04-18 | 2024-04-18 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132889 | 5Y Cft MO-PSV-33045 (200132889) | Released | 2024-01-01 | 2024-04-21 | 2024-04-21 | 2024-06-16 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Regeneration Module Common (DU50.MA.GCD.10.PS001) | 0000207732 | 5 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-21 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Taken |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207147 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Main warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-16 | 2024-04-21 | 2024-04-21 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132889 | 5Y Cft MO-PSV-33045 (200132889) | Released | 2024-01-01 | 2024-04-21 | 2024-04-21 | 2024-06-16 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Regeneration Module Common (DU50.MA.GCD.10.PS001) | 0000207732 | 6 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-21 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207147 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-16 | 2024-04-21 | 2024-04-21 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132889 | 5Y Cft MO-PSV-33045 (200132889) | Released | 2024-01-01 | 2024-04-21 | 2024-04-21 | 2024-06-16 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Regeneration Module Common (DU50.MA.GCD.10.PS001) | 0000207732 | 7 |  |  | 0041 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-21 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207147 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Returned Pre S/4 |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-16 | 2024-04-21 | 2024-04-21 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132889 | 5Y Cft MO-PSV-33045 (200132889) | Released | 2024-01-01 | 2024-04-21 | 2024-04-21 | 2024-06-16 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Regeneration Module Common (DU50.MA.GCD.10.PS001) | 0000207732 | 3 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-21 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | For TAR |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207147 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-16 | 2024-04-21 | 2024-04-21 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132889 | 5Y Cft MO-PSV-33045 (200132889) | Released | 2024-01-01 | 2024-04-21 | 2024-04-21 | 2024-06-16 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Regeneration Module Common (DU50.MA.GCD.10.PS001) | 0000207732 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-21 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | For TAR |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207147 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-16 | 2024-04-21 | 2024-04-21 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132889 | 5Y Cft MO-PSV-33045 (200132889) | Released | 2024-01-01 | 2024-04-21 | 2024-04-21 | 2024-06-16 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Regeneration Module Common (DU50.MA.GCD.10.PS001) | 0000207732 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-21 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207147 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-16 | 2024-04-21 | 2024-04-21 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132889 | 5Y Cft MO-PSV-33045 (200132889) | Released | 2024-01-01 | 2024-04-21 | 2024-04-21 | 2024-06-16 | 11175233 | 11175233 (VALVE,SAFETY,40*F*50,CONVENTIONAL,DIRECT) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Regeneration Module Common (DU50.MA.GCD.10.PS001) | 0000207732 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-21 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,40*F*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207147 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-16 | 2024-04-21 | 2024-04-21 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | AT MAC | 24MCFWVV | DU50 | 100068206 | Replace ring main valve gaskets to CNAF (100068206) | Released | 2024-03-05 | 2024-04-22 | 2024-04-22 | 2024-05-06 | 10022165 | 10022165 (GASKET,FLG,FF,200MM NB,1.5MM THK,KLINGER) | 5 | 10 | 20 | 24 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Scheduling (06) | Ready to Schedule (Order) (0060) | PTW, JRA, Excavation Docs, Parts Check (0010) | Fire Water Common Systems (DU50.MA.UFP.20.PS001) | 0000208488 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-22 | [5 empty] | 2024-05-12 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | 00000127000000000046 |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,FLG,FF,200MM NB,1.5MM THK,KLINGER | [5 empty] | 0010 | INT | PTW, JRA, Excavation Docs, Parts Check |  |  |  |  | 10-04-05-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 20 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207832 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCFWVV | 2024-05-06 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Order Approved/Material committed | Reactive Maintenance (AM01) |  | 10-07-02-03A
ECC6 Material | - | - |  | UserCommentLink | 24MCCTV1 | DU50 | 100068489 | Replace CCTV cameras 4 and 8 and fibre (100068489) | Released | 2024-01-02 | 2024-04-22 | 2024-04-22 | 2024-04-23 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist Western Advance D1 (0010) | Security/Fence/Gate/Yard (DU50.MA.ICM.20.IN001) | 0000208758 | 7 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-22 | [5 empty] | 2024-06-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Assist Western Advance D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208161 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCCTV1 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Goods movement posted/Material shortage/Estimated costs/Order Approved/Pre-costed/Released/Settlement rule created/Object created | Reactive Maintenance (AM01)
No Stock at Base | B513596527/00040 - Due Date | No Req or Processed |  | AT MAC - lite material to be issued to WO -link broken | 24MCCTV1 | DU50 | 100068489 | Replace CCTV cameras 4 and 8 and fibre (100068489) | Released | 2024-01-02 | 2024-04-22 | 2024-04-22 | 2024-04-23 | 10618969 | 10618969 (2M 10GBE ULTRA THIN CAT 6A UTPPATCH CABL) | 30 | 30 | 2 | 0 | 0 | PRPO-1000000199_00004 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000199 | 4 |  |  |  | 2024-03-26 |  |  |  | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Assist Western Advance D1 (0010) | Security/Fence/Gate/Yard (DU50.MA.ICM.20.IN001) | 0000208758 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-24 |  | 2024-04-22 | [5 empty] | 2024-06-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 2M 10GBE ULTRA THIN CAT 6A UTPPATCH CABL | [5 empty] | 0010 | INT | Assist Western Advance D1 | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-19 |  | 2 | EA | 2024-03-26 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208161 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCCTV1 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Goods movement posted/Material shortage/Estimated costs/Order Approved/Pre-costed/Released/Settlement rule created/Object created | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCCTV1 | DU50 | 100068489 | Replace CCTV cameras 4 and 8 and fibre (100068489) | Released | 2024-01-02 | 2024-04-22 | 2024-04-22 | 2024-04-23 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist Western Advance D1 (0010) | Security/Fence/Gate/Yard (DU50.MA.ICM.20.IN001) | 0000208758 | 6 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-22 | [5 empty] | 2024-06-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Assist Western Advance D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208161 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCCTV1 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Goods movement posted/Material shortage/Estimated costs/Order Approved/Pre-costed/Released/Settlement rule created/Object created | Reactive Maintenance (AM01)
No Stock at Base | B513596527/00030 - Due Date | No Req or Processed |  | AT MAC - lite material to be issued to WO -link broken | 24MCCTV1 | DU50 | 100068489 | Replace CCTV cameras 4 and 8 and fibre (100068489) | Released | 2024-01-02 | 2024-04-22 | 2024-04-22 | 2024-04-23 | 10618968 | 10618968 (singlemode or multimode fibers 1000Base-) | 30 | 30 | 2 | 0 | 0 | PRPO-1000000199_00003 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000199 | 3 |  |  |  | 2024-03-26 |  |  |  | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Assist Western Advance D1 (0010) | Security/Fence/Gate/Yard (DU50.MA.ICM.20.IN001) | 0000208758 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-24 |  | 2024-04-22 | [5 empty] | 2024-06-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | singlemode or multimode fibers 1000Base- | [5 empty] | 0010 | INT | Assist Western Advance D1 | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-19 |  | 2 | EA | 2024-03-26 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208161 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCCTV1 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Goods movement posted/Material shortage/Estimated costs/Order Approved/Pre-costed/Released/Settlement rule created/Object created | Reactive Maintenance (AM01)
No Stock at Base | B513596527/00010 - Due Date | No Req or Processed |  | AT MAC - lite material to be issued to WO -link broken | 24MCCTV1 | DU50 | 100068489 | Replace CCTV cameras 4 and 8 and fibre (100068489) | Released | 2024-01-02 | 2024-04-22 | 2024-04-22 | 2024-04-23 | 10618966 | 10618966 (C3000- HD PTZ Camera Station with integr) | 30 | 30 | 2 | 0 | 0 | PRPO-1000000199_00001 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000199 | 1 |  |  |  | 2024-03-26 |  |  |  | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Assist Western Advance D1 (0010) | Security/Fence/Gate/Yard (DU50.MA.ICM.20.IN001) | 0000208758 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-24 |  | 2024-04-22 | [5 empty] | 2024-06-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | C3000- HD PTZ Camera Station with integr | [5 empty] | 0010 | INT | Assist Western Advance D1 | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-19 |  | 2 | EA | 2024-03-26 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208161 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCCTV1 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Goods movement posted/Material shortage/Estimated costs/Order Approved/Pre-costed/Released/Settlement rule created/Object created | Reactive Maintenance (AM01)
No Stock at Base | B513596527/00020 - Due Date | No Req or Processed |  | AT MAC - lite material to be issued to WO -link broken | 24MCCTV1 | DU50 | 100068489 | Replace CCTV cameras 4 and 8 and fibre (100068489) | Released | 2024-01-02 | 2024-04-22 | 2024-04-22 | 2024-04-23 | 10618967 | 10618967 (2-port industrial 10/100/1000BaseT to 10) | 30 | 30 | 2 | 0 | 0 | PRPO-1000000199_00002 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000199 | 2 |  |  |  | 2024-03-26 |  |  |  | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Assist Western Advance D1 (0010) | Security/Fence/Gate/Yard (DU50.MA.ICM.20.IN001) | 0000208758 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-24 |  | 2024-04-22 | [5 empty] | 2024-06-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | 2-port industrial 10/100/1000BaseT to 10 | [5 empty] | 0010 | INT | Assist Western Advance D1 | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-19 |  | 2 | EA | 2024-03-26 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208161 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCCTV1 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Goods movement posted/Material shortage/Estimated costs/Order Approved/Pre-costed/Released/Settlement rule created/Object created | Reactive Maintenance (AM01)
No Stock at Base | B513596527/00050 - Due Date | No Req or Processed |  | AT MAC - lite material to be issued to WO -link broken | 24MCCTV1 | DU50 | 100068489 | Replace CCTV cameras 4 and 8 and fibre (100068489) | Released | 2024-01-02 | 2024-04-22 | 2024-04-22 | 2024-04-23 | 10618970 | 10618970 (LC to SC SM Duplex 1 metre lead) | 30 | 30 | 2 | 0 | 0 | PRPO-1000000199_00005 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000199 | 5 |  |  |  | 2024-03-26 |  |  |  | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Assist Western Advance D1 (0010) | Security/Fence/Gate/Yard (DU50.MA.ICM.20.IN001) | 0000208758 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-24 |  | 2024-04-22 | [5 empty] | 2024-06-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | LC to SC SM Duplex 1 metre lead | [5 empty] | 0010 | INT | Assist Western Advance D1 | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-19 |  | 2 | EA | 2024-03-26 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208161 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCCTV1 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Goods movement posted/Material shortage/Estimated costs/Order Approved/Pre-costed/Released/Settlement rule created/Object created | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100070339 | Materials Outstanding - Install new glob (100070339) | Released | 2024-01-01 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  | 99 | 255 | 4 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Install new globe valve and piping (0020) | UV Sterilizer Package (DU50.MA.UWS.20.WT001) | 0000210661 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-22 | [5 empty] | 2024-04-21 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Mech Install new globe valve and piping | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000210025 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed/Estimated costs | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100070339 | Materials Outstanding - Install new glob (100070339) | Released | 2024-01-01 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  | 99 | 255 | 12 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Install new globe valve and piping (0020) | UV Sterilizer Package (DU50.MA.UWS.20.WT001) | 0000210661 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-22 | [5 empty] | 2024-04-21 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Mech Install new globe valve and piping | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 12 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000210025 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed/Estimated costs | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100070339 | Materials Outstanding - Install new glob (100070339) | Released | 2024-01-01 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  | 99 | 255 | 4 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Install new globe valve and piping (0020) | UV Sterilizer Package (DU50.MA.UWS.20.WT001) | 0000210661 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-22 | [5 empty] | 2024-04-21 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Mech Install new globe valve and piping | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000210025 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed/Estimated costs | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100070339 | Materials Outstanding - Install new glob (100070339) | Released | 2024-01-01 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  | 99 | 255 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Install new globe valve and piping (0020) | UV Sterilizer Package (DU50.MA.UWS.20.WT001) | 0000210661 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-22 | [5 empty] | 2024-04-21 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Mech Install new globe valve and piping | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000210025 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed/Estimated costs | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100070339 | Materials Outstanding - Install new glob (100070339) | Released | 2024-01-01 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  | 99 | 255 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Install new globe valve and piping (0020) | UV Sterilizer Package (DU50.MA.UWS.20.WT001) | 0000210661 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-22 | [5 empty] | 2024-04-21 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Mech Install new globe valve and piping | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000210025 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed/Estimated costs | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132835 | 5Y Cft MO-PVSV-35002 (200132835) | Released | 2024-01-02 | 2024-04-24 | 2024-04-24 | 2024-06-19 | 11175221 | 11175221 (VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | LP Separator (DU50.MA.PPW.02.VP315) | 0000207678 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-24 | [5 empty] | 2024-05-19 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207053 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-19 | 2024-04-24 | 2024-04-24 | Released/Settlement rule created/Pre-costed/Material shortage/Object created | Proactive Maintenance (AM02)
Remote Pick - Low Stock | No PO | - |  | AT MAC - MLC receipting in, PO errors |  | DU50 | 200132835 | 5Y Cft MO-PVSV-35002 (200132835) | Released | 2024-01-02 | 2024-04-24 | 2024-04-24 | 2024-06-19 | 11175221 | 11175221 (VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35) | 20 | 20 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | IP REVIEW 13.03: Not delivered Yet ETA 04.04 B513593296 Callidus Karratha | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | LP Separator (DU50.MA.PPW.02.VP315) | 0000207678 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-24 | [5 empty] | 2024-05-19 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207053 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-19 | 2024-04-24 | 2024-04-24 | Released/Settlement rule created/Pre-costed/Material shortage/Object created | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed |  | 03.04: Callidus Karratha, B513595406 MLC managing delivery confirm ETA |  | DU50 | 200132898 | 5Y Cft MO-PSV-33067B (200132898) | Released | 2024-01-01 | 2024-04-24 | 2024-03-26 | 2024-05-21 | 11175225 | 11175225 (VALVE,SAFETY,25*D*50,CONVENTIONAL,DIRECT) | 20 | 20 | 1 | 0 | 0 |  |  |  | No issue identified |  |  | 0 | [5 empty] | NEW |  | RESCHEDULE ATN PURCHASING 06.03: Uplift PO B513595406. ETA TBC Expediting | N | Execution (07) | Ready for Execution (Order) (0065) | Replace Pressure Relief Device (0010) | Vessel Silica Bed Coalescer Regen Gas B (DU50.MA.GCD.10.VP005) | 0000207801 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-26 | [5 empty] | 2024-04-19 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,25*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207156 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-21 | 2024-03-26 | 2024-03-26 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
No Stock at Base | No PO | PDC - MAC NG (DU01)2000047718 / 00010 - Due Date 45388 |  | AT MAC - SOH at DU50 5001 x12 |  | DU50 | 200129140 | 4Y Service Air Dryer A (200129140) | Released | 2024-01-01 | 2024-04-25 | 2024-04-25 | 2024-04-25 | 10042306 | 10042306 (MUFFLER,8.75 LG,ALLIEDWIT M10) | 20 | 20 | 6 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203923 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-25 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MUFFLER,8.75 LG,ALLIEDWIT M10 | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 6 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203218 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-25 | 2024-04-25 | 2024-04-25 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
No Stock at Base | 4500002641/00010 - Due Date | No Req or Processed |  | AT MAC - SOH at DU50 5001 x6 |  | DU50 | 200129140 | 4Y Service Air Dryer A (200129140) | Released | 2024-01-01 | 2024-04-25 | 2024-04-25 | 2024-04-25 | 11172514 | 11172514 (VALVE,DRAIN,1/2IN,16BAR,230V) | 20 | 20 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203923 | 6 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-25 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,DRAIN,1/2IN,16BAR,230V | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203218 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-25 | 2024-04-25 | 2024-04-25 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
No Stock at Base | No PO | PDC - MAC NG (DU01)2000047715 / 00010 - Due Date 45388 |  | AT MAC - SOH at DU50 5001 x4 |  | DU50 | 200129140 | 4Y Service Air Dryer A (200129140) | Released | 2024-01-01 | 2024-04-25 | 2024-04-25 | 2024-04-25 | 10504691 | 10504691 (FILTER ELEMENT,DUST,COMPAIR CE0258NBE) | 20 | 20 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203923 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-25 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,DUST,COMPAIR CE0258NBE | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203218 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-25 | 2024-04-25 | 2024-04-25 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
No Stock at Base | No PO | PDC - MAC NG (DU01)2000047716 / 00010 - Due Date 45388 |  | AT MAC - SOH at DU50 5001 x2 |  | DU50 | 200129140 | 4Y Service Air Dryer A (200129140) | Released | 2024-01-01 | 2024-04-25 | 2024-04-25 | 2024-04-25 | 10912588 | 10912588 (FILTER ELEMENT,DUST,COMPAIR CE0258ND) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203923 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-25 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,DUST,COMPAIR CE0258ND | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203218 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-25 | 2024-04-25 | 2024-04-25 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500009332/00020 - Due Date 45439 | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-04-25 | 2024-03-25 | 2024-03-25 | 11316098 | 11316098 (GAS,CAL,5PPM H2S,COREGAS 380122E) | 99 | 255 | 2 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 13 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GAS,CAL,5PPM H2S,COREGAS 380122E | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Pick - Low Stock | No PO | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-04-25 | 2024-03-25 | 2024-03-25 | 10324023 | 10324023 (HYDRAULIC FLUID,TRANS,ATF HD,MINERAL OIL) | 99 | 255 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 17 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HYDRAULIC FLUID,TRANS,ATF HD,MINERAL OIL | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
Remote Pick - Low Stock | 4500009332/00010 - Due Date 45425 | - |  | UserCommentLink |  | DU50 | 500004046 | March 2024 consumable Maint Order (500004046) | Released | 2024-03-22 | 2024-04-25 | 2024-03-25 | 2024-03-25 | 11316075 | 11316075 (GAS,CAL,50PPM H20,COREGAS 380122ESIZE) | 99 | 255 | 2 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Ready for Execution (Order) (0065) | March 2024 consumable Maint Order (0010) | MC Operational Costs (DU50.2000) | 0000224893 | 12 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-03-25 | [5 empty] | 2026-02-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GAS,CAL,50PPM H20,COREGAS 380122ESIZE | [5 empty] | 0010 | NCNF | March 2024 consumable Maint Order | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000222355 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLU | 2024-03-01 | 0 | 0 | NOMAINT |  | 4 |  |  | CC11874501 |  | 2024-03-25 | 2024-03-25 | 2024-03-25 | Pre-costed/Object created/Settlement rule created/Error in cost calculation/Material shortage/Released/Goods movement posted | Non-Execution (AM05)
No Stock at Base | 4500001191/00010 - Due Date 45383 | No Req or Processed | 03.04 - GR completed at PDC on 02.04.24 | SOH at DU01 - monitor transit to MAC |  | DU50 | 200129140 | 4Y Service Air Dryer A (200129140) | Released | 2024-01-01 | 2024-04-25 | 2024-04-25 | 2024-04-25 | 11163196 | 11163196 (MAINTENANCE KIT,SERVICE,48 MONTH,RE-SET) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | Not Delivered Yet 01.04 Gardner Denver 4500001191 | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203923 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-25 | [5 empty] | 2024-05-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MAINTENANCE KIT,SERVICE,48 MONTH,RE-SET | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203218 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-25 | 2024-04-25 | 2024-04-25 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
No Stock at Base | No PO | PDC - MAC NG (DU01)2000047715 / 00010 - Due Date 45388 |  | AT MAC - SOH at DU50 5001 x4 |  | DU50 | 200129141 | 4Y Service Air Dryer B (200129141) | Released | 2024-01-01 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 10504691 | 10504691 (FILTER ELEMENT,DUST,COMPAIR CE0258NBE) | 20 | 20 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203924 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-26 | [5 empty] | 2024-05-03 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,DUST,COMPAIR CE0258NBE | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203219 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-26 | 2024-04-26 | 2024-04-26 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | No PO | PDC - MAC NG (DU01)2000047716 / 00010 - Due Date 45388 |  | AT MAC - SOH at DU50 5001 x2 |  | DU50 | 200129141 | 4Y Service Air Dryer B (200129141) | Released | 2024-01-01 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 10912588 | 10912588 (FILTER ELEMENT,DUST,COMPAIR CE0258ND) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203924 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-26 | [5 empty] | 2024-05-03 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,DUST,COMPAIR CE0258ND | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203219 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-26 | 2024-04-26 | 2024-04-26 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | No PO | PDC - MAC NG (DU01)2000047715 / 00010 - Due Date 45388 |  | AT MAC - SOH at DU50 5001 x4 and 1001 x2 |  | DU50 | 200129141 | 4Y Service Air Dryer B (200129141) | Released | 2024-01-01 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 10504691 | 10504691 (FILTER ELEMENT,DUST,COMPAIR CE0258NBE) | 20 | 20 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203924 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-26 | [5 empty] | 2024-05-03 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,DUST,COMPAIR CE0258NBE | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203219 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-26 | 2024-04-26 | 2024-04-26 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | 4500001191/00010 - Due Date 45383 | No Req or Processed |  | IP REVIEW 27.03: SOH in DU01 Del 80003434 17.04 |  | DU50 | 200129141 | 4Y Service Air Dryer B (200129141) | Released | 2024-01-01 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 11163196 | 11163196 (MAINTENANCE KIT,SERVICE,48 MONTH,RE-SET) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | IP REVIEW 27.03: SOH in DU01 Del 80003434 17.04 | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203924 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-26 | [5 empty] | 2024-05-03 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MAINTENANCE KIT,SERVICE,48 MONTH,RE-SET | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203219 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-26 | 2024-04-26 | 2024-04-26 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | 4500002641/00010 - Due Date | No Req or Processed |  | AT MAC - error on spreadsheet |  | DU50 | 200129141 | 4Y Service Air Dryer B (200129141) | Released | 2024-01-01 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 11172514 | 11172514 (VALVE,DRAIN,1/2IN,16BAR,230V) | 20 | 20 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | ATN PURCHASING: PR to PO - qty 1 at MAC 2 more required | N | Preparation (05) | In Preparation (Order) (0055) | Air Dryer Service (0010) | Air Dryer Package (DU50.MA.UCA.10.DY001) | 0000203924 | 6 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-26 | [5 empty] | 2024-05-03 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,DRAIN,1/2IN,16BAR,230V | [5 empty] | 0010 | INT | Air Dryer Service | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203219 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-26 | 2024-04-26 | 2024-04-26 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | 4500006100/00010 - Due Date 45383 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068077 | Replace Urinal Solenoid (100068077) | Released | 2024-01-01 | 2024-04-29 | 2024-04-18 | 2024-04-18 | 70003681 | 70003681 (SCHELL VALVE / URINAL ROUGH IN KIT) | 30 | 30 | 2 | 0 | 0 | POPO-4500006100_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300007500 | 1000004424 | 4 | 4500006100 | ROTATION SOLUTIONS ROTATION SOLUTIONS PTY LTD (30000246) | 2024-04-01 | 2024-04-14 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Urinal Solenoid (0010) | Building Admin/Control (DU50.MA.FBD.03.BG001) | 0000208386 | 4 |  |  | 0010 | 1130 |  | 2024-03-05 | 10 | 0 | 0 | 2 | 2024-04-09 | 2024-04-16 | 2024-04-18 |  |  | 2024-04-12 |  |  | 2024-05-04 | 0 |  |  | 2024-04-10 | 2024-04-18 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90006031 | WorkPackLink | 2024-04-10 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SCHELL VALVE / URINAL ROUGH IN KIT | 2024-04-10 |  |  |  |  | 0010 | INT | Replace Urinal Solenoid |  |  | 90006031_0010 |  |  | 28 | 28 |  | 2 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90006031 | 2024-03-05 |  | 2 | EA | 2024-04-12 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207769 | S001 |  |  |  | 5300007500 | 10 |  |  | 0 | 2 | EA | 0 | 2001 | DU01 |  | 2024-04-10 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208386 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-18 | 2024-04-18 | 2024-04-18 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage/Ready For Scheduling Canceled | Reactive Maintenance (AM01)
No Stock at Base | 4500003399/00020 - Due Date 45373 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068352 | Repairs to outside safety showers (100068352) | Released | 2024-02-19 | 2024-04-30 | 2024-04-15 | 2024-04-16 | 70002854 | 70002854 (VALVE; Ball 1/2 inch BSP Female/Female 3) | 30 | 30 | 8 | 0 | 0 | POPO-4500003399_00020 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300006851 | 1000002990 | 4 | 4500003399 | TRINKOR PTY LTD (30001954) | 2024-03-22 | 2024-04-03 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Repairs to outside safety showers (0010) | Potable Water System (DU50.MA.FBD.08.BG002) | 0000208650 | 4 |  |  | 0020 | 1130 |  | 2024-02-19 | 20 | 0 | 0 | 6 | 2024-03-25 | 2024-03-30 | 2024-04-15 |  |  | 2024-03-28 |  |  | 2024-06-05 | 0 |  |  | 2024-03-22 | 2024-04-01 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90002764 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE; Ball 1/2 inch BSP Female/Female 3 | 2024-03-22 | Supply for Order 100068352, Item 4 cannot be changed 90002764 item 20 already exists |  |  |  | 0010 | INT | Repairs to outside safety showers |  |  | 90002764_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002764 | 2024-02-19 |  | 8 | EA | 2024-03-28 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000208045 | S001 |  |  |  | 5300006851 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208650 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-15 | 2024-04-15 | Order Approved/Material shortage/Released/Object created/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500003399/00050 - Due Date 45373 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068352 | Repairs to outside safety showers (100068352) | Released | 2024-02-19 | 2024-04-30 | 2024-04-15 | 2024-04-16 | 70002900 | 70002900 (BOWL; 316 S/Steel Eyewash) | 30 | 30 | 4 | 0 | 0 | POPO-4500003399_00050 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300006851 | 1000002990 | 10 | 4500003399 | TRINKOR PTY LTD (30001954) | 2024-03-22 | 2024-04-03 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Repairs to outside safety showers (0010) | Potable Water System (DU50.MA.FBD.08.BG002) | 0000208650 | 10 |  |  | 0050 | 1130 |  | 2024-02-19 | 50 | 0 | 0 | 6 | 2024-03-25 | 2024-03-30 | 2024-04-15 |  |  | 2024-03-28 |  |  | 2024-06-05 | 0 |  |  | 2024-03-22 | 2024-04-01 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90002764 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BOWL; 316 S/Steel Eyewash | 2024-03-22 | Supply for Order 100068352, Item 10 cannot be changed 90002764 item 50 already exists |  |  |  | 0010 | INT | Repairs to outside safety showers |  |  | 90002764_0050 |  |  | 28 | 28 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002764 | 2024-02-19 |  | 4 | EA | 2024-03-28 | 10 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000208045 | S001 |  |  |  | 5300006851 | 50 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 50 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208650 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-15 | 2024-04-15 | Order Approved/Material shortage/Released/Object created/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500003399/00060 - Due Date 45373 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068352 | Repairs to outside safety showers (100068352) | Released | 2024-02-19 | 2024-04-30 | 2024-04-15 | 2024-04-16 | 70002901 | 70002901 (ASSEMBLY; Ball Valve) | 30 | 30 | 8 | 0 | 0 | POPO-4500003399_00060 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300006851 | 1000002990 | 12 | 4500003399 | TRINKOR PTY LTD (30001954) | 2024-03-22 | 2024-04-03 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Repairs to outside safety showers (0010) | Potable Water System (DU50.MA.FBD.08.BG002) | 0000208650 | 12 |  |  | 0060 | 1130 |  | 2024-02-19 | 60 | 0 | 0 | 6 | 2024-03-25 | 2024-03-30 | 2024-04-15 |  |  | 2024-03-28 |  |  | 2024-06-05 | 0 |  |  | 2024-03-22 | 2024-04-01 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90002764 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ASSEMBLY; Ball Valve | 2024-03-22 | Supply for Order 100068352, Item 12 cannot be changed 90002764 item 60 already exists |  |  |  | 0010 | INT | Repairs to outside safety showers |  |  | 90002764_0060 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002764 | 2024-02-19 |  | 8 | EA | 2024-03-28 | 12 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000208045 | S001 |  |  |  | 5300006851 | 60 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 60 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208650 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-15 | 2024-04-15 | Order Approved/Material shortage/Released/Object created/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500003399/00030 - Due Date 45373 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068352 | Repairs to outside safety showers (100068352) | Released | 2024-02-19 | 2024-04-30 | 2024-04-15 | 2024-04-16 | 70002855 | 70002855 (ASSEMBLY; Push down plate & Valve leaver) | 30 | 30 | 8 | 0 | 0 | POPO-4500003399_00030 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300006851 | 1000002990 | 6 | 4500003399 | TRINKOR PTY LTD (30001954) | 2024-03-22 | 2024-04-03 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Repairs to outside safety showers (0010) | Potable Water System (DU50.MA.FBD.08.BG002) | 0000208650 | 6 |  |  | 0030 | 1130 |  | 2024-02-19 | 30 | 0 | 0 | 6 | 2024-03-25 | 2024-03-30 | 2024-04-15 |  |  | 2024-03-28 |  |  | 2024-06-05 | 0 |  |  | 2024-03-22 | 2024-04-01 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90002764 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ASSEMBLY; Push down plate & Valve leaver | 2024-03-22 | Supply for Order 100068352, Item 6 cannot be changed 90002764 item 30 already exists |  |  |  | 0010 | INT | Repairs to outside safety showers |  |  | 90002764_0030 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002764 | 2024-02-19 |  | 8 | EA | 2024-03-28 | 6 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000208045 | S001 |  |  |  | 5300006851 | 30 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 30 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208650 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-15 | 2024-04-15 | Order Approved/Material shortage/Released/Object created/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500003399/00080 - Due Date 45373 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068352 | Repairs to outside safety showers (100068352) | Released | 2024-02-19 | 2024-04-30 | 2024-04-15 | 2024-04-16 | 70002903 | 70002903 (ROSE; Shower SS) | 30 | 30 | 4 | 0 | 0 | POPO-4500003399_00080 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300006851 | 1000002990 | 16 | 4500003399 | TRINKOR PTY LTD (30001954) | 2024-03-22 | 2024-04-03 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Repairs to outside safety showers (0010) | Potable Water System (DU50.MA.FBD.08.BG002) | 0000208650 | 16 |  |  | 0080 | 1130 |  | 2024-02-19 | 80 | 0 | 0 | 6 | 2024-03-25 | 2024-03-30 | 2024-04-15 |  |  | 2024-03-28 |  |  | 2024-06-05 | 0 |  |  | 2024-03-22 | 2024-04-01 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90002764 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ROSE; Shower SS | 2024-03-22 | Supply for Order 100068352, Item 16 cannot be changed 90002764 item 80 already exists |  |  |  | 0010 | INT | Repairs to outside safety showers |  |  | 90002764_0080 |  |  | 28 | 28 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002764 | 2024-02-19 |  | 4 | EA | 2024-03-28 | 16 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000208045 | S001 |  |  |  | 5300006851 | 80 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 80 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208650 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-15 | 2024-04-15 | Order Approved/Material shortage/Released/Object created/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500003399/00070 - Due Date 45373 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068352 | Repairs to outside safety showers (100068352) | Released | 2024-02-19 | 2024-04-30 | 2024-04-15 | 2024-04-16 | 70002902 | 70002902 (ROD; Pull Assy) | 30 | 30 | 4 | 0 | 0 | POPO-4500003399_00070 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300006851 | 1000002990 | 14 | 4500003399 | TRINKOR PTY LTD (30001954) | 2024-03-22 | 2024-04-03 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Repairs to outside safety showers (0010) | Potable Water System (DU50.MA.FBD.08.BG002) | 0000208650 | 14 |  |  | 0070 | 1130 |  | 2024-02-19 | 70 | 0 | 0 | 6 | 2024-03-25 | 2024-03-30 | 2024-04-15 |  |  | 2024-03-28 |  |  | 2024-06-05 | 0 |  |  | 2024-03-22 | 2024-04-01 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90002764 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ROD; Pull Assy | 2024-03-22 | Supply for Order 100068352, Item 14 cannot be changed 90002764 item 70 already exists |  |  |  | 0010 | INT | Repairs to outside safety showers |  |  | 90002764_0070 |  |  | 28 | 28 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002764 | 2024-02-19 |  | 4 | EA | 2024-03-28 | 14 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000208045 | S001 |  |  |  | 5300006851 | 70 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 70 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208650 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-15 | 2024-04-15 | Order Approved/Material shortage/Released/Object created/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500003399/00010 - Due Date 45373 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068352 | Repairs to outside safety showers (100068352) | Released | 2024-02-19 | 2024-04-30 | 2024-04-15 | 2024-04-16 | 70002853 | 70002853 (REGULATOR; 1/2" BSP Black Nylon Flow) | 30 | 30 | 8 | 0 | 0 | POPO-4500003399_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300006851 | 1000002990 | 3 | 4500003399 | TRINKOR PTY LTD (30001954) | 2024-03-22 | 2024-04-03 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Repairs to outside safety showers (0010) | Potable Water System (DU50.MA.FBD.08.BG002) | 0000208650 | 3 |  |  | 0010 | 1130 |  | 2024-02-19 | 10 | 0 | 0 | 6 | 2024-03-25 | 2024-03-30 | 2024-04-15 |  |  | 2024-03-28 |  |  | 2024-06-05 | 0 |  |  | 2024-03-22 | 2024-04-01 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90002764 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | REGULATOR; 1/2" BSP Black Nylon Flow | 2024-03-22 | Supply for Order 100068352, Item 3 cannot be changed 90002764 item 10 already exists |  |  |  | 0010 | INT | Repairs to outside safety showers |  |  | 90002764_0010 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002764 | 2024-02-19 |  | 8 | EA | 2024-03-28 | 3 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000208045 | S001 |  |  |  | 5300006851 | 10 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208650 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-15 | 2024-04-15 | Order Approved/Material shortage/Released/Object created/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500003399/00040 - Due Date 45373 | No Req or Processed |  | 03.04 - Expediting in progress ETA TBC |  | DU50 | 100068352 | Repairs to outside safety showers (100068352) | Released | 2024-02-19 | 2024-04-30 | 2024-04-15 | 2024-04-16 | 70002879 | 70002879 (PLATE; Baffle 316L) | 30 | 30 | 8 | 0 | 0 | POPO-4500003399_00040 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300006851 | 1000002990 | 8 | 4500003399 | TRINKOR PTY LTD (30001954) | 2024-03-22 | 2024-04-03 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Repairs to outside safety showers (0010) | Potable Water System (DU50.MA.FBD.08.BG002) | 0000208650 | 8 |  |  | 0040 | 1130 |  | 2024-02-19 | 40 | 0 | 0 | 6 | 2024-03-25 | 2024-03-30 | 2024-04-15 |  |  | 2024-03-28 |  |  | 2024-06-05 | 0 |  |  | 2024-03-22 | 2024-04-01 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90002764 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | PLATE; Baffle 316L | 2024-03-22 | Supply for Order 100068352, Item 8 cannot be changed 90002764 item 40 already exists |  |  |  | 0010 | INT | Repairs to outside safety showers |  |  | 90002764_0040 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002764 | 2024-02-19 |  | 8 | EA | 2024-03-28 | 8 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000208045 | S001 |  |  |  | 5300006851 | 40 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 40 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208650 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-15 | 2024-04-15 | Order Approved/Material shortage/Released/Object created/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100068266 | AT-33025 Screen replacement (100068266) | Released | 2024-01-02 | 2024-04-30 | 2024-04-30 | 2024-04-30 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | AT-33025 Screen replacement (0010) | Analyser Trans Chromatograph (DU50.MA.GCD.20.AN001) | 0000208548 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-07-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | AT-33025 Screen replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207932 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-30 | 2024-04-30 | 2024-04-30 | Object created/Material committed/Estimated costs/Released/Settlement rule created/Order Approved/Pre-costed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100068266 | AT-33025 Screen replacement (100068266) | Released | 2024-01-02 | 2024-04-30 | 2024-04-30 | 2024-04-30 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | AT-33025 Screen replacement (0010) | Analyser Trans Chromatograph (DU50.MA.GCD.20.AN001) | 0000208548 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-07-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | AT-33025 Screen replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207932 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-30 | 2024-04-30 | 2024-04-30 | Object created/Material committed/Estimated costs/Released/Settlement rule created/Order Approved/Pre-costed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100068266 | AT-33025 Screen replacement (100068266) | Released | 2024-01-02 | 2024-04-30 | 2024-04-30 | 2024-04-30 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | AT-33025 Screen replacement (0010) | Analyser Trans Chromatograph (DU50.MA.GCD.20.AN001) | 0000208548 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-07-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | AT-33025 Screen replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207932 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-04-30 | 2024-04-30 | 2024-04-30 | Object created/Material committed/Estimated costs/Released/Settlement rule created/Order Approved/Pre-costed | Reactive Maintenance (AM01)
Remote Pick - Low Stock | 4500001712/00010 - Due Date 45432 | - |  | WM TO ACTION 03.04: Reschedule ETA 20.05 Solar T 4500001712 | 24MCSGA | DU50 | 100068639 | SGC-A Replace Outstanding FHAs Group 1 (100068639) | Released | 2024-01-02 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 10243314 | 10243314 (HOSE,MTL,FLEX,1-1/4N ID X 42-1/2IN LG) | 30 | 30 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | Not Delivered Yet ETA 25.05 Solar T 4500001712 | N | Preparation (05) | In Preparation (Order) (0055) | SGC-A Replace Outstanding FHAs Group 1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000208961 | 2 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HOSE,MTL,FLEX,1-1/4N ID X 42-1/2IN LG | [5 empty] | 0010 | INT | SGC-A Replace Outstanding FHAs Group 1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208345 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-05-01 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | AT MAC | 24MCSGA | DU50 | 100068639 | SGC-A Replace Outstanding FHAs Group 1 (100068639) | Released | 2024-01-02 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 10243316 | 10243316 (HOSE ASSY,MTL,FLEX,SOLATURB 1046484) | 30 | 30 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | SGC-A Replace Outstanding FHAs Group 1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000208961 | 1 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HOSE ASSY,MTL,FLEX,SOLATURB 1046484 | [5 empty] | 0010 | INT | SGC-A Replace Outstanding FHAs Group 1 |  |  |  |  | 11-01-02-08A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208345 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-05-01 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
Remote Pick - Low Stock | 4500001712/00020 - Due Date 45411 | - |  | WM TO ACTION 03.04; Reschedule ETA 29.04 Solar T 4500001712 | 24MCSGA | DU50 | 100068639 | SGC-A Replace Outstanding FHAs Group 1 (100068639) | Released | 2024-01-02 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 10243340 | 10243340 (HOSE ASSY,FLEX,MTL,SOLATURB 945061C1) | 30 | 30 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | Not Delivered Yet ETA 25.05 Solar T 4500001712 | N | Preparation (05) | In Preparation (Order) (0055) | SGC-A Replace Outstanding FHAs Group 1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000208961 | 3 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HOSE ASSY,FLEX,MTL,SOLATURB 945061C1 | [5 empty] | 0010 | INT | SGC-A Replace Outstanding FHAs Group 1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208345 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-05-01 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCSGA | DU50 | 100068806 | SGC-A replace on-crank wash solenoid (100068806) | Released | 2024-01-02 | 2024-04-30 | 2024-04-30 | 2024-04-30 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | E&I replace on-crank wash solenoid (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000209104 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | E&I replace on-crank wash solenoid | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208439 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGA | 2024-04-30 | 2024-04-30 | 2024-04-30 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | AT MAC | 24MCSGA | DU50 | 100069556 | SGC-A Replace Antisurge controller (100069556) | Released | 2024-01-02 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 10992866 | 10992866 (CARD,CTRL,COMPCONT 10500010007) | 30 | 30 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | change UIC-34100 AS controller (0010) | Sales Gas Comp A Module (DU50.MA.GSG.10.ME001) | 0000209854 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CARD,CTRL,COMPCONT 10500010007 | [5 empty] | 0010 | INT | change UIC-34100 AS controller |  |  |  |  | 10-04-06-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209229 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-05-01 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
No Stock at Base | 4500002301/00020 - Due Date 45396 | No Req or Processed |  | IP REVIEW 19.03: AT RISK Not delivered Yet | 24MCEEHA | DU50 | 200129010 | 4Y Inspect EEHA Group 3 GRC (200129010) | Released | 2024-01-29 | 2024-04-30 | 2024-03-14 | 2024-05-16 | 70002202 | 70002202 (Band-IT KE0128 Type 316 SS 4.6x200mm) | 5 | 10 | 5 | 0 | 0 | POPO-4500002301_00020 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300006197 | 1000002102 | 4 | 4500002301 | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 2024-03-18 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: AT RISK Not delivered Yet | N | Execution (07) | Main Work Started (Order) (0070) | EEHA Inspection Campaign Phase 2 (0020) | Gas Dehydration (DU50.MA.GCD.20) | 0000203813 | 4 |  |  | 0020 | 1130 |  | 2024-02-07 | 20 | 0 | 0 | 10 | 2024-03-05 | 2024-03-05 | 2024-04-11 |  |  | 2024-03-08 |  |  | 2024-04-16 | 0 |  |  | 2024-02-27 | 2024-03-07 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90001863 | WorkPackLink | 2024-02-27 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Band-IT KE0128 Type 316 SS 4.6x200mm | 2024-02-27 | Supply for Order 200129010, Item 4 cannot be changed 90001863 item 20 already exists |  |  |  | 0020 | ESRV | EEHA Inspection Campaign Phase 2 |  |  | 90001863_0020 |  |  | 20 | 20 |  | 5 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001863 | 2024-02-07 |  | 5 | EA | 2024-03-08 | 4 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000203208 | S001 |  |  |  | 5300006197 | 20 |  |  | 0 | 5 | EA | 0 | 2001 | DU01 |  | 2024-02-27 | [5 empty] | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 203813 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCEEHA | 2024-05-16 | 2024-03-14 | 2024-03-14 | Released/Pre-costed/Object created/Ready For Scheduling/Goods movement posted/Job In Process/Material shortage/Settlement rule created | Proactive Maintenance (AM02)
No Stock at Base | 4500002301/00030 - Due Date 45396 | No Req or Processed |  | IP REVIEW 19.03: AT RISK Not delivered Yet | 24MCEEHA | DU50 | 200129010 | 4Y Inspect EEHA Group 3 GRC (200129010) | Released | 2024-01-29 | 2024-04-30 | 2024-03-14 | 2024-05-16 | 70002203 | 70002203 (CMP, ADAPTER, M25 MALE TO M20 FEMALE) | 5 | 10 | 20 | 0 | 0 | POPO-4500002301_00030 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300006197 | 1000002102 | 6 | 4500002301 | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 2024-03-18 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: AT RISK Not delivered Yet | N | Execution (07) | Main Work Started (Order) (0070) | EEHA Inspection Campaign Phase 2 (0020) | Gas Dehydration (DU50.MA.GCD.20) | 0000203813 | 6 |  |  | 0030 | 1130 |  | 2024-02-07 | 30 | 0 | 0 | 10 | 2024-03-05 | 2024-03-05 | 2024-04-11 |  |  | 2024-03-08 |  |  | 2024-04-16 | 0 |  |  | 2024-02-27 | 2024-03-07 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90001863 | WorkPackLink | 2024-02-27 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CMP, ADAPTER, M25 MALE TO M20 FEMALE | 2024-02-27 | Supply for Order 200129010, Item 6 cannot be changed 90001863 item 30 already exists |  |  |  | 0020 | ESRV | EEHA Inspection Campaign Phase 2 |  |  | 90001863_0030 |  |  | 20 | 20 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001863 | 2024-02-07 |  | 20 | EA | 2024-03-08 | 6 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000203208 | S001 |  |  |  | 5300006197 | 30 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-02-27 | [5 empty] | 30 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 203813 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCEEHA | 2024-05-16 | 2024-03-14 | 2024-03-14 | Released/Pre-costed/Object created/Ready For Scheduling/Goods movement posted/Job In Process/Material shortage/Settlement rule created | Proactive Maintenance (AM02)
No Stock at Base | 4500002301/00010 - Due Date 45396 | No Req or Processed |  | IP REVIEW 19.03: AT RISK Not delivered Yet | 24MCEEHA | DU50 | 200129010 | 4Y Inspect EEHA Group 3 GRC (200129010) | Released | 2024-01-29 | 2024-04-30 | 2024-03-14 | 2024-05-16 | 70002200 | 70002200 (CMP, CABLE GLAND, 20'S (M20) T3CDS IP66) | 5 | 10 | 20 | 0 | 0 | POPO-4500002301_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300006197 | 1000002102 | 2 | 4500002301 | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 2024-03-18 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: AT RISK Not delivered Yet | N | Execution (07) | Main Work Started (Order) (0070) | EEHA Inspection Campaign Phase 2 (0020) | Gas Dehydration (DU50.MA.GCD.20) | 0000203813 | 2 |  |  | 0010 | 1130 |  | 2024-02-07 | 10 | 0 | 0 | 10 | 2024-03-05 | 2024-03-05 | 2024-04-11 |  |  | 2024-03-08 |  |  | 2024-04-16 | 0 |  |  | 2024-02-27 | 2024-03-07 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90001863 | WorkPackLink | 2024-02-27 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CMP, CABLE GLAND, 20'S (M20) T3CDS IP66 | 2024-02-27 | Supply for Order 200129010, Item 2 cannot be changed 90001863 item 10 already exists |  |  |  | 0020 | ESRV | EEHA Inspection Campaign Phase 2 |  |  | 90001863_0010 |  |  | 20 | 20 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001863 | 2024-02-07 |  | 20 | EA | 2024-03-08 | 2 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000203208 | S001 |  |  |  | 5300006197 | 10 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-02-27 | [5 empty] | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 203813 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCEEHA | 2024-05-16 | 2024-03-14 | 2024-03-14 | Released/Pre-costed/Object created/Ready For Scheduling/Goods movement posted/Job In Process/Material shortage/Settlement rule created | Proactive Maintenance (AM02)
No Stock at Base | 4500002301/00040 - Due Date 45396 | No Req or Processed |  | IP REVIEW 19.03: AT RISK Not delivered Yet | 24MCEEHA | DU50 | 200129010 | 4Y Inspect EEHA Group 3 GRC (200129010) | Released | 2024-01-29 | 2024-04-30 | 2024-03-14 | 2024-05-16 | 70002206 | 70002206 (SEALING WASHER M20 X 2MM WHYITE NYLON) | 5 | 10 | 20 | 0 | 0 | POPO-4500002301_00040 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300006197 | 1000002102 | 8 | 4500002301 | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 2024-03-18 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: AT RISK Not delivered Yet | N | Execution (07) | Main Work Started (Order) (0070) | EEHA Inspection Campaign Phase 2 (0020) | Gas Dehydration (DU50.MA.GCD.20) | 0000203813 | 8 |  |  | 0040 | 1130 |  | 2024-02-07 | 40 | 0 | 0 | 10 | 2024-03-05 | 2024-03-05 | 2024-04-11 |  |  | 2024-03-08 |  |  | 2024-04-16 | 0 |  |  | 2024-02-27 | 2024-03-07 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90001863 | WorkPackLink | 2024-02-27 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEALING WASHER M20 X 2MM WHYITE NYLON | 2024-02-27 | Supply for Order 200129010, Item 8 cannot be changed 90001863 item 40 already exists |  |  |  | 0020 | ESRV | EEHA Inspection Campaign Phase 2 |  |  | 90001863_0040 |  |  | 20 | 20 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001863 | 2024-02-07 |  | 20 | EA | 2024-03-08 | 8 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000203208 | S001 |  |  |  | 5300006197 | 40 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-02-27 | [5 empty] | 40 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 203813 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCEEHA | 2024-05-16 | 2024-03-14 | 2024-03-14 | Released/Pre-costed/Object created/Ready For Scheduling/Goods movement posted/Job In Process/Material shortage/Settlement rule created | Proactive Maintenance (AM02)
No Stock at Base | 4500002301/00050 - Due Date 45396 | No Req or Processed |  | IP REVIEW 19.03: AT RISK Not delivered Yet | 24MCEEHA | DU50 | 200129010 | 4Y Inspect EEHA Group 3 GRC (200129010) | Released | 2024-01-29 | 2024-04-30 | 2024-03-14 | 2024-05-16 | 70002207 | 70002207 (CMP, IP WASHER, 25MM, WHITE NYLONG, 2MM) | 5 | 10 | 20 | 0 | 0 | POPO-4500002301_00050 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300006197 | 1000002102 | 10 | 4500002301 | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 2024-03-18 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: AT RISK Not delivered Yet | N | Execution (07) | Main Work Started (Order) (0070) | EEHA Inspection Campaign Phase 2 (0020) | Gas Dehydration (DU50.MA.GCD.20) | 0000203813 | 10 |  |  | 0050 | 1130 |  | 2024-02-07 | 50 | 0 | 0 | 10 | 2024-03-05 | 2024-03-05 | 2024-04-11 |  |  | 2024-03-08 |  |  | 2024-04-16 | 0 |  |  | 2024-02-27 | 2024-03-07 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90001863 | WorkPackLink | 2024-02-27 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CMP, IP WASHER, 25MM, WHITE NYLONG, 2MM | 2024-02-27 | Supply for Order 200129010, Item 10 cannot be changed 90001863 item 50 already exists |  |  |  | 0020 | ESRV | EEHA Inspection Campaign Phase 2 |  |  | 90001863_0050 |  |  | 20 | 20 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90001863 | 2024-02-07 |  | 20 | EA | 2024-03-08 | 10 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000203208 | S001 |  |  |  | 5300006197 | 50 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-02-27 | [5 empty] | 50 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 203813 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCEEHA | 2024-05-16 | 2024-03-14 | 2024-03-14 | Released/Pre-costed/Object created/Ready For Scheduling/Goods movement posted/Job In Process/Material shortage/Settlement rule created | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 5001 Refurb x1 |  | DU50 | 100068545 | P5(9) Re-instating PSV-42027A/B with DBB (100068545) | Released | 2024-01-01 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 11175195 | 11175195 (VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT) | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | REFURB |  | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | P5(9) Re-instating PSV-42027A/B with DBB (0010) | DBNGP Sales Gas Metering Skid (DU50.MA.GSG.60.ME001) | 0000208827 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-21 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | P5(9) Re-instating PSV-42027A/B with DBB | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000208211 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | Material committed/Goods movement posted/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 100068545 | P5(9) Re-instating PSV-42027A/B with DBB (100068545) | Released | 2024-01-01 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 11175195 | 11175195 (VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT) | 30 | 30 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | P5(9) Re-instating PSV-42027A/B with DBB (0010) | DBNGP Sales Gas Metering Skid (DU50.MA.GSG.60.ME001) | 0000208827 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-21 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | P5(9) Re-instating PSV-42027A/B with DBB | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 | 4900028190_2024 | 5400000033 | 10 | 1 |  |  | 1000208211 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | Material committed/Goods movement posted/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | AT MAC | 24MCSGA | DU50 | 100068591 | SGC-A Replace On-Crank Solenoid Valve (100068591) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 10504787 | 10504787 (VALVE,SOL,SOLATURB 1027484101) | 20 | 20 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | SGC-A Replace On-Crank Solenoid Valve (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000208873 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SOL,SOLATURB 1027484101 | [5 empty] | 0010 | INT | SGC-A Replace On-Crank Solenoid Valve |  |  |  |  | 11-03-01-05A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000208257 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-05-01 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink | 24MCSGA | DU50 | 100069556 | SGC-A Replace Antisurge controller (100069556) | Released | 2024-01-02 | 2024-05-01 | 2024-04-30 | 2024-05-01 | 10992866 | 10992866 (CARD,CTRL,COMPCONT 10500010007) | 30 | 30 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | change UIC-34100 AS controller (0010) | Sales Gas Comp A Module (DU50.MA.GSG.10.ME001) | 0000209854 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-04-30 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | CARD,CTRL,COMPCONT 10500010007 | [5 empty] | 0010 | INT | change UIC-34100 AS controller | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000209229 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-05-01 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
No Stock at Base | 4500002830/00010 - Due Date 45419 | No Req or Processed |  | WM TO ACTION 03.04; Reschedule ETA 07.05 | 24MCSGA | DU50 | 100072775 | Replace filter socks E12 SGC-A (100072775) | Released | 2024-02-12 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 70002506 | 70002506 (ELEMENT,FLTR,AIR,CYL,SOCK) | 30 | 30 | 80 | 0 | 0 | IDPO-0180011288 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver in-full | 5300006482 | 1000002413 | 4 | 4500002830 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-07 | 2024-09-19 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not Delivered Yet - On track | N | Preparation (05) | In Preparation (Order) (0055) | Replace filter socks E12 SGC-A (0010) | COMPRESSOR, GENERAL (DU50.MA.GSG.10.CM001-COGE) | 0000219415 | 4 |  |  | 0010 | 1130 |  | 2024-02-12 | 10 | 75 | 0 | 0 | 2024-07-03 | 2024-07-13 | 2024-05-01 |  |  | 2024-07-06 |  |  | 2025-02-01 | 0 |  |  | 2024-07-08 | 2024-07-15 |  |  | 0 | 2 | 3 | 0 | 0 | 0 | 180011288 |  | 0 | EXW | 1 | L |  | 0 |  |  | 0 |  | 180011288 |  | 90002758 | WorkPackLink | 2024-07-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ELEMENT,FLTR,AIR,CYL,SOCK | 2024-07-08 | Supply for Order 100072775, Item 4 cannot be changed 90002758 item 10 already exists |  |  |  | 0010 | INT | Replace filter socks E12 SGC-A |  |  | 90002758_0010 |  |  | 120 | 120 |  | 80 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002758 | 2024-02-26 |  | 80 | EA | 2024-07-06 | 4 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000217270 | S001 |  |  |  | 5300006482 | 10 |  |  | 0 | 80 | EA | 0 | 2001 | DU01 |  | 2024-07-08 | [5 empty] | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-08 | 219415 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCSGA | 2024-05-01 | 2024-05-01 | 2024-05-01 | Pre-costed/Settlement rule created/Released/Material shortage/Order Approved/Object created | Reactive Maintenance (AM01)
No Stock at Base | 4500002830/00020 - Due Date 45419 | No Req or Processed |  | WM TO ACTION 03.04; Reschedule ETA 07.05 | 24MCSGA | DU50 | 100072775 | Replace filter socks E12 SGC-A (100072775) | Released | 2024-02-12 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 70002507 | 70002507 (CABLE TIE W X 48 IN,NYLON) | 30 | 30 | 80 | 0 | 0 | IDPO-0180011288 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | No Issue identified | 5300006482 | 1000002413 | 6 | 4500002830 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-07 | 2024-09-19 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not Delivered Yet - On track | N | Preparation (05) | In Preparation (Order) (0055) | Replace filter socks E12 SGC-A (0010) | COMPRESSOR, GENERAL (DU50.MA.GSG.10.CM001-COGE) | 0000219415 | 6 |  |  | 0020 | 1130 |  | 2024-02-12 | 20 | 75 | 0 | 0 | 2024-07-03 | 2024-07-13 | 2024-05-01 |  |  | 2024-07-06 |  |  | 2025-02-01 | 0 |  |  | 2024-07-08 | 2024-07-15 |  |  | 0 | 2 | 3 | 0 | 0 | 0 | 180011288 |  | 0 | EXW | 3 | L |  | 0 |  |  | 0 |  | 180011288 |  | 90002758 | WorkPackLink | 2024-07-08 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CABLE TIE W X 48 IN,NYLON | 2024-07-08 | Supply for Order 100072775, Item 6 cannot be changed 90002758 item 20 already exists |  |  |  | 0010 | INT | Replace filter socks E12 SGC-A |  |  | 90002758_0020 |  |  | 120 | 120 |  | 80 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002758 | 2024-02-26 |  | 80 | EA | 2024-07-06 | 6 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000217270 | S001 |  |  |  | 5300006482 | 20 |  |  | 0 | 80 | EA | 0 | 2001 | DU01 |  | 2024-07-08 | [5 empty] | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-08 | 219415 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCSGA | 2024-05-01 | 2024-05-01 | 2024-05-01 | Pre-costed/Settlement rule created/Released/Material shortage/Order Approved/Object created | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | AT MAC |  | DU50 | 200129018 | 1Y Insp & Svce Nitrogen Generator (200129018) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-05-02 | 10507328 | 10507328 (FILTER ELEMENT,CB,AIRPNETH 13368F0002) | 20 | 20 | 2 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Inspect & Service N2 Generator Skid (0010) | Nitrogen Generation Skid (DU50.MA.UIG.10.ME001) | 0000203921 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-01 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,CB,AIRPNETH 13368F0002 | [5 empty] | 0010 | INT | Inspect & Service N2 Generator Skid | 6 |  |  |  | 11-03-04-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203216 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-02 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | AT MAC |  | DU50 | 200129018 | 1Y Insp & Svce Nitrogen Generator (200129018) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-05-02 | 10504707 | 10504707 (FILTER ELEMENT,AIRPNETH 13368F0001) | 20 | 20 | 2 | 4 | 2 |  |  | Stock at Base and Remote (SP11) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Inspect & Service N2 Generator Skid (0010) | Nitrogen Generation Skid (DU50.MA.UIG.10.ME001) | 0000203921 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-01 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,AIRPNETH 13368F0001 | [5 empty] | 0010 | INT | Inspect & Service N2 Generator Skid | 6 |  |  |  | 11-03-04-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203216 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-02 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02)
Remote Pick - Low Stock | No PO | - |  | 04.04 SOH at DU50 1001 x3, Del 80003438 01.04 MONITOR |  | DU50 | 200129018 | 1Y Insp & Svce Nitrogen Generator (200129018) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-05-02 | 11120477 | 11120477 (O-RING,HSG,FILT,AIRPNETH 13368F0000A) | 20 | 20 | 4 | 3 | 6 |  |  | Stock at Base and Remote (SP11) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Replace O2 Sensor (0020) | Nitrogen Generation Skid (DU50.MA.UIG.10.ME001) | 0000203921 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-01 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,HSG,FILT,AIRPNETH 13368F0000A | [5 empty] | 0020 | INT | Replace O2 Sensor | 0 |  |  |  | 11-01-04-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203216 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-02 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200131708 | 5Y Cft MO-PSV-31019 GRC (200131708) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-26 | 11174908 | 11174908 (VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35) | 5 | 10 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | PSV 310V302AB SLG CATCH PSV-31019 (DU50.GSE.MO-PSV-31019) | 0000206504 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-06-26 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000205868 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Material shortage | Proactive Maintenance (AM02)
Remote Pick - Low Stock | No PO | - |  | IP REVIEW 29.02: Not Delivered Yet ETA 15.04 REP Callidus K 4500000313 |  | DU50 | 200131708 | 5Y Cft MO-PSV-31019 GRC (200131708) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-26 | 11174908 | 11174908 (VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35) | 5 | 10 | 1 | 0 | 1 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | IP REVIEW 29.02: Not Delivered Yet ETA 15.04 REP Callidus K 4500000313 | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | PSV 310V302AB SLG CATCH PSV-31019 (DU50.GSE.MO-PSV-31019) | 0000206504 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-06-26 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000205868 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Material shortage | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | AT MAC - MLC Checking PSV numbers |  | DU50 | 200132827 | SD 5Y Cft MO-PSV-34022A (200132827) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-27 | 11175236 | 11175236 (VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT) | 20 | 20 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | AT MAC - MLC Checking PSV numbers | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Barrier Seal Gas Common Sys (DU50.MA.GSG.40.ME001) | 0000207670 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  | 10-03-06-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207045 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Estimated costs/Material committed | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132827 | SD 5Y Cft MO-PSV-34022A (200132827) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-27 | 11175236 | 11175236 (VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Barrier Seal Gas Common Sys (DU50.MA.GSG.40.ME001) | 0000207670 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207045 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Estimated costs/Material committed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | AT MAC - MLC Checking PSV numbers |  | DU50 | 200132828 | SD 5Y Cft MO-PSV-34022B (200132828) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-27 | 11175236 | 11175236 (VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT) | 20 | 20 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | AT MAC - MLC Checking PSV numbers | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Barrier Seal Gas Common Sys (DU50.MA.GSG.40.ME001) | 0000207671 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  | 10-03-06-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207046 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Estimated costs/Material committed/Object created | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132828 | SD 5Y Cft MO-PSV-34022B (200132828) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-27 | 11175236 | 11175236 (VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Barrier Seal Gas Common Sys (DU50.MA.GSG.40.ME001) | 0000207671 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207046 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Estimated costs/Material committed/Object created | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132834 | SD 5Y Cft MO-PSV-52010 (200132834) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-27 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Nitrogen Accumulator (DU50.MA.UIG.10.VP002) | 0000207677 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207052 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Delivered Pre S/4 |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-01 | 2024-05-01 | Released/Pre-costed/Object created/Material committed/Estimated costs/Settlement rule created | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132881 | 5Y Cft MO-PSV-33027C (200132881) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-26 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Gas Dehyd Adsorber C (DU50.MA.GCD.20.VP003) | 0000207724 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207059 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Delivered Pre S/4 |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Goods movement posted | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132881 | 5Y Cft MO-PSV-33027C (200132881) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-26 | 11175229 | 11175229 (VALVE,SAFETY,25*E*50,CONVENTIONAL,DIRECT) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Gas Dehyd Adsorber C (DU50.MA.GCD.20.VP003) | 0000207724 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,25*E*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0 | EA |  | 0 | 0 |  | 0 | 4900034344_2024/4900034346_2024 | 5400000106 | 10 | 1 |  |  | 1000207059 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Goods movement posted | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132882 | 5Y Cft MO-PSV-33027D (200132882) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-26 | 11175229 | 11175229 (VALVE,SAFETY,25*E*50,CONVENTIONAL,DIRECT) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Gas Dehyd Adsorber D (DU50.MA.GCD.20.VP004) | 0000207725 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,25*E*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0 | EA |  | 0 | 0 |  | 0 | 4900034345_2024/4900034349_2024 | 5400000107 | 10 | 1 |  |  | 1000207060 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 1 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Released/Pre-costed/Object created/Material committed/Settlement rule created/Goods movement posted | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 200132882 | 5Y Cft MO-PSV-33027D (200132882) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-26 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Gas Dehyd Adsorber D (DU50.MA.GCD.20.VP004) | 0000207725 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207060 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Delivered Pre S/4 |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Released/Pre-costed/Object created/Material committed/Settlement rule created/Goods movement posted | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132885 | 5Y Cft MO-PSV-33028C (200132885) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-26 | 11175229 | 11175229 (VALVE,SAFETY,25*E*50,CONVENTIONAL,DIRECT) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Gas Dehyd Adsorber C (DU50.MA.GCD.20.VP003) | 0000207728 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,25*E*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207143 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Material committed/Object created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | AT MAC |  | DU50 | 200132885 | 5Y Cft MO-PSV-33028C (200132885) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-26 | 11175229 | 11175229 (VALVE,SAFETY,25*E*50,CONVENTIONAL,DIRECT) | 20 | 20 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | REFURB | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Gas Dehyd Adsorber C (DU50.MA.GCD.20.VP003) | 0000207728 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,25*E*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207143 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Material committed/Object created | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132899 | SD 5Y Cft MO-PSV-36003 GRC (200132899) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-27 | 11175236 | 11175236 (VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT) | 5 | 10 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Replace Pressure Relief Device (0010) | PSV 360VH301 BLK START HTR PSV-36003 (DU50.UFS.MO-PSV-36003) | 0000207802 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-06-25 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207157 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Partially confirmed/Material committed/Estimated costs | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | AT MAC |  | DU50 | 200132899 | SD 5Y Cft MO-PSV-36003 GRC (200132899) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-06-27 | 11175236 | 11175236 (VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT) | 5 | 10 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | AT MAC | N | Execution (07) | Main Work Started (Order) (0070) | Replace Pressure Relief Device (0010) | PSV 360VH301 BLK START HTR PSV-36003 (DU50.UFS.MO-PSV-36003) | 0000207802 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-06-25 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,40*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  | 10-03-06-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207157 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  | 2024-01-08 | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Object created/Partially confirmed/Material committed/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | 4500007704/00010 - Due Date 45401 | No Req or Processed |  | IP REVIEW 03.04: Monitor PDC movements Not delivered Yet |  | DU50 | 100074644 | Renew Louver connector bolts. (100074644) | Released | 2024-03-18 | 2024-05-01 | 2024-04-09 | 2024-05-02 | 70004110 | 70004110 (B2LNWA4006025 BOLT/2FW/2LN SS316 6X25MM) | 20 | 20 | 1 | 0 | 0 | POPO-4500007704_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300007992 | 1000005832 | 2 | 4500007704 | J BLACKWOOD AND SON LTD (30000394) | 2024-04-19 | 2024-05-09 | AUS Operations (106) |  | DU01 | WM TO ACTION 25.03: Reschedule | N | Scheduling (06) | Ready to Schedule (Order) (0060) | Renew Louver connector bolts. (0020) | EXCH REGEN GAS COOLER 330-H-311 (DU50.GCD.MO-330-H-311) | 0000226677 | 2 |  |  | 0010 | 1130 |  | 2024-03-18 | 10 | 0 | 0 | 21 | 2024-04-15 | 2024-04-06 | 2024-05-01 |  |  | 2024-04-18 |  |  | 2024-09-09 | 0 |  |  | 2024-03-28 | 2024-04-08 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90005904 | WorkPackLink | 2024-03-28 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | B2LNWA4006025 BOLT/2FW/2LN SS316 6X25MM | 2024-03-28 | Supply for Order 100074644, Item 2 cannot be changed 90005904 item 10 already exists |  |  |  | 0020 | INT | Renew Louver connector bolts. |  |  | 90005904_0010 |  |  | 21 | 21 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90005904 | 2024-03-18 |  | 1 | EA | 2024-04-18 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000224088 | S001 |  |  |  | 5300007992 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-03-28 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-15 | 226677 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-05-02 | 2024-04-09 | 2024-04-09 | Ready For Scheduling/Pre-costed/Material shortage/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01)
Remote Pick - Low Stock | No PO | - |  | WM TO ACTION 18.03: Reschedule ATN PURCHASING 12.03: PR 1000005388 TO PO |  | DU50 | 200126686 | 5Y Cft MO-CRV-02517B GRC (200126686) | Released | 2024-03-11 | 2024-05-01 | 2024-05-01 | 2024-06-26 | 11271657 | 11271657 (VALVE,PRESS REG,DN25,BKBPUMP CRV0251796M) | 5 | 10 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | WM TO ACTION 18.03: Reschedule ATN PURCHASING 12.03: PR TO PO | N | Preparation (05) | In Preparation (Order) (0055) | Replace Min Flow Device (0010) | Pump Fire Water A (DU50.MA.UFP.20.PU001) | 0000201502 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-27 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,PRESS REG,DN25,BKBPUMP CRV0251796M | [5 empty] | 0010 | INT | Replace Min Flow Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200865 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-26 | 2024-05-01 | 2024-05-01 | Pre-costed/Released/Material shortage/Settlement rule created/Object created | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500002969/00010 - Due Date | - |  | 03.04 - SOH at DU01 - Del 80005725 17.04 |  | DU50 | 200129018 | 1Y Insp & Svce Nitrogen Generator (200129018) | Released | 2024-01-02 | 2024-05-01 | 2024-05-01 | 2024-05-02 | 11120471 | 11120471 (DETECTOR,GAS,ELECTROCHEMICAL SENSOR,O2,2) | 20 | 20 | 2 | 0 | 2 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | Not Delivered Yet ETA 22.03 Prochem Pipeline 4500002969 | N | Preparation (05) | In Preparation (Order) (0055) | Replace O2 Sensor (0020) | Nitrogen Generation Skid (DU50.MA.UIG.10.ME001) | 0000203921 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-01 | [5 empty] | 2024-05-01 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DETECTOR,GAS,ELECTROCHEMICAL SENSOR,O2,2 | [5 empty] | 0020 | INT | Replace O2 Sensor | 0 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203216 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-02 | 2024-05-01 | 2024-05-01 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200128793 | 5Y Cft MO-PSV-54024 (200128793) | Released | 2024-01-02 | 2024-05-02 | 2024-05-02 | 2024-06-27 | 10893131 | 10893131 (VALVE,SAFETY,1/2 X 1IN,2.5BAR,1500PSI,-2) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Accumulator Potable Water (DU50.MA.UWS.20.VP003) | 0000203596 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-02 | [5 empty] | 2024-06-15 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,1/2 X 1IN,2.5BAR,1500PSI,-2 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000202971 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | B513596972/00010 - Due Date 45013 | - |  | 03.04 - Expediting in progress, new buy PO B513596972 Callidus |  | DU50 | 200128793 | 5Y Cft MO-PSV-54024 (200128793) | Released | 2024-01-02 | 2024-05-02 | 2024-05-02 | 2024-06-27 | 10893131 | 10893131 (VALVE,SAFETY,1/2 X 1IN,2.5BAR,1500PSI,-2) | 20 | 20 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | IP REVIEW 29.02: ETA 28.03 REP PO B513596972 Callidus | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Accumulator Potable Water (DU50.MA.UWS.20.VP003) | 0000203596 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-02 | [5 empty] | 2024-06-15 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,1/2 X 1IN,2.5BAR,1500PSI,-2 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000202971 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-06-27 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500007917/00010 - Due Date 45383 | - |  | 03.04 - Expediting in progress, PO 4500007917 SMC - ETA 01.04.24 |  | DU50 | 100073278 | Replace flare valve XV-38020 regulator (100073278) | Released | 2024-02-16 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 11279741 | 11279741 (REGULATOR,PRESS,SMCPNEU AW20N02BCG2B) | 99 | 255 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | PO 4500007917 SMC - ETA 01.04.24 | N | Preparation (05) | In Preparation (Order) (0055) | Replace flare valve XV-38020 regulator (0010) | 7204-SWITCHING VALVE (DU50.VFL.MO-XV-38020) | 0000222430 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2026-01-09 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | REGULATOR,PRESS,SMCPNEU AW20N02BCG2B | [5 empty] | 0010 | INT | Replace flare valve XV-38020 regulator | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000220114 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-16 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-06 | 2024-05-06 | 2024-05-06 | Material shortage/Order Approved/Object created/Pre-costed/Released/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | B513596465/00010 - Due Date 45391 | No Req or Processed |  | IP REVIEW 13.03: Not Delivered Yet ETA 09.04 B513596465 Ex Engineering | 24MCUPS1 | DU50 | 100067898 | Replace AC UPS Bank A Batteries (100067898) | Released | 2024-01-02 | 2024-05-06 | 2024-05-06 | 2024-05-10 | 10618978 | 10618978 (M01100G31, Absolyte GP 2V Cell, Bank D) | 30 | 30 | 30 | 0 | 0 | PRPO-1000000191_00004 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000191 | 4 |  |  |  | 2024-03-29 |  |  |  | IP REVIEW 13.03: Not Delivered Yet ETA 09.04 B513596465 Ex Engineering | N | Preparation (05) | In Preparation (Order) (0055) | Scope & prepare batt lifter & pallets (0010) | Power Supply AC UPS A (DU50.MA.UEP.40.PW033) | 0000208156 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-27 |  | 2024-05-06 | [5 empty] | 2024-07-22 | 0 |  |  |  |  | MO-610-EUP-6 |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | M01100G31, Absolyte GP 2V Cell, Bank D | [5 empty] | 0010 | INT | Scope & prepare batt lifter & pallets | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-22 |  | 30 | EA | 2024-03-29 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207571 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | OPS |  | 1 |  |  | CC11874501 | 24MCUPS1 | 2024-05-10 | 2024-05-06 | 2024-05-06 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596462/00010 - Due Date 45391 | No Req or Processed |  | IP REVIEW 13.03: Not Delivered Yet ETA 09.04 B513596462 Ex Engineering | 24MCUPS1 | DU50 | 100067898 | Replace AC UPS Bank A Batteries (100067898) | Released | 2024-01-02 | 2024-05-06 | 2024-05-06 | 2024-05-10 | 10618975 | 10618975 (M01100G31, Absolyte GP 2V Cell, Bank A) | 30 | 30 | 30 | 0 | 0 | PRPO-1000000191_00001 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000191 | 1 |  |  |  | 2024-03-29 |  |  |  | IP REVIEW 13.03: Not Delivered Yet ETA 09.04 B513596462 Ex Engineering | N | Preparation (05) | In Preparation (Order) (0055) | Scope & prepare batt lifter & pallets (0010) | Power Supply AC UPS A (DU50.MA.UEP.40.PW033) | 0000208156 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-27 |  | 2024-05-06 | [5 empty] | 2024-07-22 | 0 |  |  |  |  | MO-610-EUP-6 |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | M01100G31, Absolyte GP 2V Cell, Bank A | [5 empty] | 0010 | INT | Scope & prepare batt lifter & pallets | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-22 |  | 30 | EA | 2024-03-29 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207571 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | OPS |  | 1 |  |  | CC11874501 | 24MCUPS1 | 2024-05-10 | 2024-05-06 | 2024-05-06 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596464/00010 - Due Date 45391 | No Req or Processed |  | IP REVIEW 13.03: Not Delivered Yet ETA 09.04 B513596464 Ex Engineering | 24MCUPS1 | DU50 | 100067898 | Replace AC UPS Bank A Batteries (100067898) | Released | 2024-01-02 | 2024-05-06 | 2024-05-06 | 2024-05-10 | 10618977 | 10618977 (M01100G31, Absolyte GP 2V Cell, Bank C) | 30 | 30 | 30 | 0 | 0 | PRPO-1000000191_00003 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000191 | 3 |  |  |  | 2024-03-29 |  |  |  | IP REVIEW 13.03: Not Delivered Yet ETA 09.04 B513596464 Ex Engineering | N | Preparation (05) | In Preparation (Order) (0055) | Scope & prepare batt lifter & pallets (0010) | Power Supply AC UPS A (DU50.MA.UEP.40.PW033) | 0000208156 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-27 |  | 2024-05-06 | [5 empty] | 2024-07-22 | 0 |  |  |  |  | MO-610-EUP-6 |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | M01100G31, Absolyte GP 2V Cell, Bank C | [5 empty] | 0010 | INT | Scope & prepare batt lifter & pallets | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-22 |  | 30 | EA | 2024-03-29 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207571 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | OPS |  | 1 |  |  | CC11874501 | 24MCUPS1 | 2024-05-10 | 2024-05-06 | 2024-05-06 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596463/00010 - Due Date 45391 | No Req or Processed |  | IP REVIEW 13.03: Not Delivered Yet ETA 09.04 b513596463 Ex Engineering | 24MCUPS1 | DU50 | 100067898 | Replace AC UPS Bank A Batteries (100067898) | Released | 2024-01-02 | 2024-05-06 | 2024-05-06 | 2024-05-10 | 10618976 | 10618976 (M01100G31, Absolyte GP 2V Cell, Bank B) | 30 | 30 | 30 | 0 | 0 | PRPO-1000000191_00002 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000191 | 2 |  |  |  | 2024-03-29 |  |  |  | IP REVIEW 13.03: Not Delivered Yet ETA 09.04 b513596463 Ex Engineering | N | Preparation (05) | In Preparation (Order) (0055) | Scope & prepare batt lifter & pallets (0010) | Power Supply AC UPS A (DU50.MA.UEP.40.PW033) | 0000208156 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 | 2024-03-27 |  | 2024-05-06 | [5 empty] | 2024-07-22 | 0 |  |  |  |  | MO-610-EUP-6 |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | M01100G31, Absolyte GP 2V Cell, Bank B | [5 empty] | 0010 | INT | Scope & prepare batt lifter & pallets | [5 empty] | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-01-22 |  | 30 | EA | 2024-03-29 | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207571 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | OPS |  | 1 |  |  | CC11874501 | 24MCUPS1 | 2024-05-10 | 2024-05-06 | 2024-05-06 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | 4500007335/00020 - Due Date 45385 | No Req or Processed |  | IP REVIEW 19.03: Not delivered Yet |  | DU50 | 100074595 | Eye wash nozzles require changing. (100074595) | Released | 2024-03-15 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 70004025 | 70004025 (Aerator Screen and Cap Assembly) | 30 | 30 | 4 | 0 | 0 | IDPO-0180014309 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | No Issue identified | 5300007925 | 1000005710 | 4 | 4500007335 | PBA SAFETY PTY LTD (30002257) | 2024-04-03 | 2024-04-26 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Eye wash nozzles require changing. (0010) | BUILDING WORKSHOP/WAREHOUSE 810-Q-802 (DU50.FBD.MO-810-Q-802) | 0000226983 | 4 |  |  | 0020 | 1130 |  | 2024-03-15 | 20 | 0 | 0 | 0 | 2024-04-23 | 2024-05-04 | 2024-05-06 |  |  | 2024-04-26 |  |  | 2025-03-02 | 0 |  |  | 2024-04-29 | 2024-05-06 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 | 180014309 |  | 0 | CPT | 3 | L |  | 0 |  |  | 0 |  | 180014309 |  |  | WorkPackLink | 2024-04-29 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Aerator Screen and Cap Assembly | 2024-04-29 |  |  |  |  | 0010 | INT | Eye wash nozzles require changing. | [5 empty] | 14 | 14 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 4 | PAC | 2024-04-26 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000224362 | S001 |  |  |  | 5300007925 | 20 |  |  | 0 | 4 | PAC | 0 | 2001 | DU01 |  | 2024-04-29 | Mac Store |  |  |  |  | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-15 | 226983 | 0 | BUILD |  | 3 |  |  | CC11874501 |  | 2024-05-06 | 2024-05-06 | 2024-05-06 | Material shortage/Released/Order Approved/Pre-costed/Object created/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500007335/00010 - Due Date 45385 | No Req or Processed |  | IP REVIEW 19.03: Not delivered Yet |  | DU50 | 100074595 | Eye wash nozzles require changing. (100074595) | Released | 2024-03-15 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 70004024 | 70004024 (Shroud Repair Kit (Yellow Plastic Parts)) | 30 | 30 | 4 | 0 | 0 | IDPO-0180014309 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | No Issue identified | 5300007925 | 1000005710 | 3 | 4500007335 | PBA SAFETY PTY LTD (30002257) | 2024-04-03 | 2024-04-26 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Eye wash nozzles require changing. (0010) | BUILDING WORKSHOP/WAREHOUSE 810-Q-802 (DU50.FBD.MO-810-Q-802) | 0000226983 | 3 |  |  | 0010 | 1130 |  | 2024-03-15 | 10 | 0 | 0 | 0 | 2024-04-23 | 2024-05-04 | 2024-05-06 |  |  | 2024-04-26 |  |  | 2025-03-02 | 0 |  |  | 2024-04-29 | 2024-05-06 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 | 180014309 |  | 0 | CPT | 3 | L |  | 0 |  |  | 0 |  | 180014309 |  |  | WorkPackLink | 2024-04-29 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Shroud Repair Kit (Yellow Plastic Parts) | 2024-04-29 |  |  |  |  | 0010 | INT | Eye wash nozzles require changing. | [5 empty] | 14 | 14 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 4 | EA | 2024-04-26 | 3 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000224362 | S001 |  |  |  | 5300007925 | 10 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 |  | 2024-04-29 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-15 | 226983 | 0 | BUILD |  | 3 |  |  | CC11874501 |  | 2024-05-06 | 2024-05-06 | 2024-05-06 | Material shortage/Released/Order Approved/Pre-costed/Object created/Settlement rule created | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCGC1 | DU50 | 200129019 | 1Y Inst Svce Gas Chromatograph Anlyser A (200129019) | Released | 2024-03-15 | 2024-05-06 | 2024-05-06 | 2024-05-13 | 10232295 | 10232295 (REPAIR KIT,VLV,EMERSON 244000179) | 20 | 20 | 10 | 25 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Chromatograph Anlyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203922 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-04-16 | 0 |  |  |  |  | Mac Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | REPAIR KIT,VLV,EMERSON 244000179 | [5 empty] | 0010 | ESRV | Service Gas Chromatograph Anlyser |  |  |  |  | 11-03-03-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 10 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203217 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Mac Store |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCGC1 | 2024-05-13 | 2024-05-06 | 2024-05-06 | Pre-costed/Released/Settlement rule created/Material shortage/Object created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCGC1 | DU50 | 200129019 | 1Y Inst Svce Gas Chromatograph Anlyser A (200129019) | Released | 2024-03-15 | 2024-05-06 | 2024-05-06 | 2024-05-13 | 11213720 | 11213720 (DIAPHRAGM KIT,10 PORT,EMERSON GCW9A00097) | 20 | 20 | 4 | 11 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Chromatograph Anlyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203922 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-04-16 | 0 |  |  |  |  | Mac Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DIAPHRAGM KIT,10 PORT,EMERSON GCW9A00097 | [5 empty] | 0010 | ESRV | Service Gas Chromatograph Anlyser |  |  |  |  | 11-03-03-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203217 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Mac Store |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCGC1 | 2024-05-13 | 2024-05-06 | 2024-05-06 | Pre-costed/Released/Settlement rule created/Material shortage/Object created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCGC1 | DU50 | 200129019 | 1Y Inst Svce Gas Chromatograph Anlyser A (200129019) | Released | 2024-03-15 | 2024-05-06 | 2024-05-06 | 2024-05-13 | 10503002 | 10503002 (DIAPHRAGM KIT,6 PORT,EMERSON GCW9A00096G) | 20 | 20 | 10 | 12 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Chromatograph Anlyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203922 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-04-16 | 0 |  |  |  |  | Mac Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DIAPHRAGM KIT,6 PORT,EMERSON GCW9A00096G | [5 empty] | 0010 | ESRV | Service Gas Chromatograph Anlyser |  |  |  |  | 11-03-03-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 10 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000203217 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Mac Store |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCGC1 | 2024-05-13 | 2024-05-06 | 2024-05-06 | Pre-costed/Released/Settlement rule created/Material shortage/Object created | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed |  | IP REVIEW 27.03: Expediting REP Callidus K 4500000315 |  | DU50 | 200129144 | 4Y Cft MO-PSV-36017 (200129144) | Released | 2024-01-01 | 2024-05-06 | 2024-05-06 | 2024-07-01 | 11175256 | 11175256 (VALVE,SAFETY,50*H*80,PILOT OPER,CS SA352) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | NEW |  | IP REVIEW 27.03: Expediting REP Callidus K 4500000315 | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Exch Fuel Gas Super Heater (DU50.MA.UFS.30.HX001) | 0000203927 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-07-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,50*H*80,PILOT OPER,CS SA352 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203322 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-07-01 | 2024-05-06 | 2024-05-06 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 1001 x51 |  | DU50 | 200129144 | 4Y Cft MO-PSV-36017 (200129144) | Released | 2024-01-01 | 2024-05-06 | 2024-05-06 | 2024-07-01 | 10015044 | 10015044 (GASKET,SPW,CRIR,CL 300/600,50MM NB,SS316) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Exch Fuel Gas Super Heater (DU50.MA.UFS.30.HX001) | 0000203927 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-07-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 300/600,50MM NB,SS316 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203322 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-07-01 | 2024-05-06 | 2024-05-06 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 1001 x11 5001 x3 |  | DU50 | 200129144 | 4Y Cft MO-PSV-36017 (200129144) | Released | 2024-01-01 | 2024-05-06 | 2024-05-06 | 2024-07-01 | 10015058 | 10015058 (GASKET,SPW,METAFLEX,SG/IR,CL 300/600,80M) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Exch Fuel Gas Super Heater (DU50.MA.UFS.30.HX001) | 0000203927 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-07-02 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,METAFLEX,SG/IR,CL 300/600,80M | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203322 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-07-01 | 2024-05-06 | 2024-05-06 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200129144 | 4Y Cft MO-PSV-36017 (200129144) | Released | 2024-01-01 | 2024-05-06 | 2024-05-06 | 2024-07-01 | 11175256 | 11175256 (VALVE,SAFETY,50*H*80,PILOT OPER,CS SA352) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Exch Fuel Gas Super Heater (DU50.MA.UFS.30.HX001) | 0000203927 | 4 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-07-02 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,50*H*80,PILOT OPER,CS SA352 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203322 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-07-01 | 2024-05-06 | 2024-05-06 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
Remote Pick - Low Stock | No PO | - |  | Material Consumed | 24MCAC1 | DU50 | 200132666 | 12M Svce HVAC 810-M-803 (200132666) | Released | 2024-01-01 | 2024-05-06 | 2024-05-06 | 2024-05-07 | 11066136 | 11066136 (FILTER,AIR,ELECTROSTATIC,MEDIA MAXIMISIN) | 20 | 20 | 8 | 1 | 0 |  | Material Consumed | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Service HVAC - CEB D1 (0010) | Building Central Equipment (DU50.MA.FBD.04.BG001) | 0000207482 | 4 |  |  | X |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-04-22 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER,AIR,ELECTROSTATIC,MEDIA MAXIMISIN | [5 empty] | 0010 | INT | Service HVAC - CEB D1 |  |  |  |  | 10-03-02-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 0 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206846 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 8 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCAC1 | 2024-05-07 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Ready For Scheduling/Material committed/Estimated costs/Job In Process/Object created/Goods movement posted | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink | 24MCAC1 | DU50 | 200132666 | 12M Svce HVAC 810-M-803 (200132666) | Released | 2024-01-01 | 2024-05-06 | 2024-05-06 | 2024-05-07 |  |  | 20 | 20 | 8 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Service HVAC - CEB D1 (0010) | Building Central Equipment (DU50.MA.FBD.04.BG001) | 0000207482 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-04-22 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Service HVAC - CEB D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 8 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206846 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCAC1 | 2024-05-07 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Ready For Scheduling/Material committed/Estimated costs/Job In Process/Object created/Goods movement posted | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink | 24MCAC1 | DU50 | 200132666 | 12M Svce HVAC 810-M-803 (200132666) | Released | 2024-01-01 | 2024-05-06 | 2024-05-06 | 2024-05-07 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Service HVAC - CEB D1 (0010) | Building Central Equipment (DU50.MA.FBD.04.BG001) | 0000207482 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-04-22 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Service HVAC - CEB D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206846 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCAC1 | 2024-05-07 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Ready For Scheduling/Material committed/Estimated costs/Job In Process/Object created/Goods movement posted | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink | 24MCAC1 | DU50 | 200132666 | 12M Svce HVAC 810-M-803 (200132666) | Released | 2024-01-01 | 2024-05-06 | 2024-05-06 | 2024-05-07 |  |  | 20 | 20 | 6 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Execution (07) | Main Work Started (Order) (0070) | Service HVAC - CEB D1 (0010) | Building Central Equipment (DU50.MA.FBD.04.BG001) | 0000207482 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-06 | [5 empty] | 2024-04-22 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Service HVAC - CEB D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 6 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206846 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCAC1 | 2024-05-07 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Ready For Scheduling/Material committed/Estimated costs/Job In Process/Object created/Goods movement posted | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed | 03.04 - Expedite email sent 03/04 - Prochem | WM TO ACTION 25.03: Reschedule ETA 01.06 - Aaron looking into | 24MCGC1 | DU50 | 200129019 | 1Y Inst Svce Gas Chromatograph Anlyser A (200129019) | Released | 2024-03-15 | 2024-05-06 | 2024-05-06 | 2024-05-13 | 70004229 | 70004229 (O-RING VITON STANDARD) | 20 | 20 | 20 | 0 | 0 | POPO-4500007699_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300008086 | 1000006124 | 5 | 4500007699 | PROCHEM PIPELINE PRODUCTS PTY LTD (30000271) | 2024-06-01 | 2024-08-17 | AUS Operations (106) |  | DU01 | WM TO ACTION 25.03: Reschedule | N | Preparation (05) | In Preparation (Order) (0055) | Service Gas Chromatograph Anlyser (0010) | Sales Gas Metering Plant (DU50.MA.GSG.50) | 0000203922 | 5 |  |  | 0040 | 1130 |  | 2024-03-19 | 10 | 0 | 0 | 71 | 2024-06-04 | 2024-04-07 | 2024-05-06 |  |  | 2024-06-07 |  |  | 2024-04-16 | 0 |  |  | 2024-03-28 | 2024-04-09 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  | 90005968 | WorkPackLink | 2024-03-28 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING VITON STANDARD | 2024-03-28 | Supply for Order 200129019, Item 5 cannot be changed 90005968 item 10 already exists |  |  |  | 0010 | ESRV | Service Gas Chromatograph Anlyser |  |  | 90005968_0010 |  |  | 70 | 70 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90005968 | 2024-03-19 |  | 20 | EA | 2024-06-07 | 5 | 0 |  | 0 |  |  | 0 | 0 | MN | AU1153 | 1000203217 | S001 |  |  |  | 5300008086 | 10 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-03-28 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 203922 | 0 | MECH |  | 1 |  |  | CC11874501 | 24MCGC1 | 2024-05-13 | 2024-05-06 | 2024-05-06 | Pre-costed/Released/Settlement rule created/Material shortage/Object created | Proactive Maintenance (AM02)
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002501 | 70002501 (LED PANEL LIGHT 30W 240V OPAL WHT) | 99 | 255 | 2 | 0 | 2 | ODST-0090002757_0050 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 10 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 10 |  |  | 0050 | 1130 |  | 2024-02-12 | 50 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 |  |  | 2026-01-28 | 0 |  | 5000042694_2024_0001 | 2024-03-22 | 2024-03-21 |  |  | 0 | 2 | 3 | 0 | 2 | 0 | /180007840 |  | 0 | CPT | 3 | L |  | 0 | 5000042694 |  | 0 | 2024 | /018000784 |  | 90002757 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | LED PANEL LIGHT 30W 240V OPAL WHT | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 90002757_0050 |  |  | 28 | 28 |  | 2 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 2 | EA | 2024-04-29 | 10 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 |  |  |  | 5300006467 | 50 |  |  | 0 | 2 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 50 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01)
Onsite - Sloc 5001 | - | - |  | SIT |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002498 | 70002498 (EMER LED PANEL 30W OPAL WHT 295X1195IP20) | 99 | 255 | 8 | 8 | 0 | GRST-5000046939_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 4 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | SIT | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 4 | 2024-03-27 | 2024-03-09 | 0020 | 1130 | 070324 MACEDON | 2024-02-12 | 20 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000016815 | 1010 | 2026-01-28 | 8 | 4900035398_2024_0001 | 5000030591_2024_0001/5000030566_2024_0001 | 2024-03-07 | 2024-03-06 |  | 5000047052_2024_0001/5000046939_2024_0001 | 0 | 2 | 3 | 8 | 8 | 4 | /180007849 | 180009475 | 0 | CPT | 3 | L | 4900035398 | 2024 | 5000030591 | 5000046939 | 2024 | 2024 | /018000784 | 180009475 | 9000456 | 00000101000000022707 | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 | 2024-03-22 |  | 101000000022708 |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9000456_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 8 | EA | 2024-04-29 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 | 101000000023047 | 2024-03-22 |  | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01) |  | DU01-DU50-MACEDON
Onsite - Sloc 5001 | - | - |  | SIT |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002498 | 70002498 (EMER LED PANEL 30W OPAL WHT 295X1195IP20) | 99 | 255 | 8 | 8 | 0 | GRST-5000046939_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 4 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | SIT | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 4 | 2024-03-27 | 2024-03-09 | 0020 | 1130 |  | 2024-02-12 | 20 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000016815 | 1010 | 2026-01-28 | 8 | 4900035398_2024_0001 | 5000030591_2024_0001/5000030566_2024_0001 | 2024-03-07 | 2024-03-06 |  | 5000047052_2024_0001/5000046939_2024_0001 | 0 | 2 | 3 | 8 | 8 | 4 | /180007849 | 180009475 | 0 | CPT | 3 | L | 4900035398 | 2024 | 5000030591 | 5000046939 | 2024 | 2024 | /018000784 | 180009475 | 9000456 | 00000101000000022707 | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9000456_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 8 | EA | 2024-04-29 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 | 101000000022707 | 2024-03-22 |  | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01) |  | 10-07-03-01A
Onsite - Sloc 5001 | - | - |  | SIT |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002498 | 70002498 (EMER LED PANEL 30W OPAL WHT 295X1195IP20) | 99 | 255 | 8 | 8 | 0 | GRST-5000046939_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 4 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | SIT | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 4 | 2024-03-27 | 2024-03-09 | 0020 | 1130 | 070324 MACEDON | 2024-02-12 | 20 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000016815 | 1010 | 2026-01-28 | 8 | 4900035398_2024_0001 | 5000030591_2024_0001/5000030566_2024_0001 | 2024-03-07 | 2024-03-06 |  | 5000047052_2024_0001/5000046939_2024_0001 | 0 | 2 | 3 | 8 | 8 | 4 | /180007849 | 180009475 | 0 | CPT | 3 | L | 4900035398 | 2024 | 5000030591 | 5000046939 | 2024 | 2024 | /018000784 | 180009475 | 9000456 | 00000101000000022707 | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 | 2024-03-22 |  | 101000000022708 |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9000456_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 8 | EA | 2024-04-29 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 | 101000000023047 | 2024-03-22 |  | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01) |  | 10-07-03-01A
Onsite - Sloc 5001 | - | - |  | SIT |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002498 | 70002498 (EMER LED PANEL 30W OPAL WHT 295X1195IP20) | 99 | 255 | 8 | 8 | 0 | GRST-5000047052_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 4 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | SIT | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 4 | 2024-03-27 | 2024-03-09 | 0020 | 1130 | 070324 MACEDON | 2024-02-12 | 20 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000016815 | 1010 | 2026-01-28 | 8 | 4900035398_2024_0001 | 5000030591_2024_0001/5000030566_2024_0001 | 2024-03-07 | 2024-03-06 |  | 5000047052_2024_0001/5000046939_2024_0001 | 0 | 2 | 3 | 8 | 8 | 4 | /180007849 | 180009475 | 0 | CPT | 3 | L | 4900035398 | 2024 | 5000030591 | 5000047052 | 2024 | 2024 | /018000784 | 180009475 | 9000456 | 00000101000000022707 | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 | 2024-03-22 |  | 101000000022708 |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9000456_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 8 | EA | 2024-04-29 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 | 101000000023047 | 2024-03-22 |  | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01) |  | DU01-DU50-MACEDON
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002502 | 70002502 (SOCKET SURFACE RC 1G 10A 250V 3PIN 1P WH) | 99 | 255 | 30 | 0 | 30 | ODST-0090002757_0060 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 12 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 12 |  |  | 0060 | 1130 |  | 2024-02-12 | 60 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 |  |  | 2026-01-28 | 0 |  | 5000042574_2024_0001/5000042568_2024_0001/5000042534_2024_0001 | 2024-03-22 | 2024-03-21 |  |  | 0 | 2 | 3 | 0 | 30 | 0 | /180007840 |  | 0 | CPT | 3 | L |  | 0 | 5000042574 |  | 0 | 2024 | /018000784 |  | 90002757 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SOCKET SURFACE RC 1G 10A 250V 3PIN 1P WH | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 90002757_0060 |  |  | 28 | 28 |  | 30 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 30 | EA | 2024-04-29 | 12 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 |  |  |  | 5300006467 | 60 |  |  | 0 | 30 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 60 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01)
In Transit via Road | - | - |  |  |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002497 | 70002497 (EMER LED PANEL 18W OPAL WHT 295X595IP20) | 99 | 255 | 2 | 0 | 0 | GIST-4900041139_2024 | Material In-Transit on-01-Road | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 2 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 2 |  | 2024-03-30 | 0010 | 1130 |  | 2024-02-12 | 10 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000042873 | 1010 | 2026-01-28 | 2 | 4900041139_2024_0001 | 5000042613_2024_0001/5000042608_2024_0001 | 2024-03-28 | 2024-03-21 |  |  | 0 | 2 | 3 | 0 | 2 | 1 | /180007840 | 180014233 | 0 | CPT | 3 | L | 4900041139 | 2024 | 5000042613 |  | 0 | 2024 | /018000784 | 180014233 | 9001037 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 18W OPAL WHT 295X595IP20 | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9001037_0010 |  |  | 28 | 28 |  | 2 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 2 | EA | 2024-04-29 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 10 |  |  | 0 | 2 | EA | 2 | 2001 | DU01 | 101000000027632 | 2024-03-22 |  | EA |  |  | 2024-03-28 | 10 | AU00 | 3-In Transit |  | 20000631 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01)
In Transit via Road | - | - |  |  |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002497 | 70002497 (EMER LED PANEL 18W OPAL WHT 295X595IP20) | 99 | 255 | 2 | 0 | 0 | GIST-4900041139_2024 | Material In-Transit on-01-Road | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 2 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 2 |  | 2024-03-30 | 0010 | 1130 |  | 2024-02-12 | 10 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000042873 | 1010 | 2026-01-28 | 2 | 4900041139_2024_0001 | 5000042613_2024_0001/5000042608_2024_0001 | 2024-03-28 | 2024-03-21 |  |  | 0 | 2 | 3 | 0 | 2 | 1 | /180007840 | 180014233 | 0 | CPT | 3 | L | 4900041139 | 2024 | 5000042613 |  | 0 | 2024 | /018000784 | 180014233 | 9001037 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 18W OPAL WHT 295X595IP20 | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9001037_0010 |  |  | 28 | 28 |  | 2 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 2 | EA | 2024-04-29 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 10 |  |  | 0 | 2 | EA | 2 | 2001 | DU01 | 101000000027630 | 2024-03-22 |  | EA |  |  | 2024-03-28 | 10 | AU00 | 3-In Transit |  | 20000631 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01)
Onsite - Sloc 5001 | - | - |  | SIT |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002498 | 70002498 (EMER LED PANEL 30W OPAL WHT 295X1195IP20) | 99 | 255 | 8 | 8 | 0 | GRST-5000046939_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 4 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | SIT | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 4 | 2024-03-27 | 2024-03-09 | 0020 | 1130 |  | 2024-02-12 | 20 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000016815 | 1010 | 2026-01-28 | 8 | 4900035398_2024_0001 | 5000030591_2024_0001/5000030566_2024_0001 | 2024-03-07 | 2024-03-06 |  | 5000047052_2024_0001/5000046939_2024_0001 | 0 | 2 | 3 | 8 | 8 | 4 | /180007849 | 180009475 | 0 | CPT | 3 | L | 4900035398 | 2024 | 5000030591 | 5000046939 | 2024 | 2024 | /018000784 | 180009475 | 9000456 | 00000101000000022707 | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9000456_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 8 | EA | 2024-04-29 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 | 101000000022707 | 2024-03-22 |  | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01) |  | DU01-DU50-MACEDON
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002503 | 70002503 (FLAT TWIN & EARTH 2C+E 7/0.5 1.5MM PVC W) | 99 | 255 | 1 | 0 | 1 | ODST-0090002757_0070 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 14 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 14 |  |  | 0070 | 1130 |  | 2024-02-12 | 70 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 |  |  | 2026-01-28 | 0 |  | 5000042661_2024_0001 | 2024-03-22 | 2024-03-21 |  |  | 0 | 2 | 3 | 0 | 1 | 0 | /180007840 |  | 0 | CPT | 3 | L |  | 0 | 5000042661 |  | 0 | 2024 | /018000784 |  | 90002757 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FLAT TWIN & EARTH 2C+E 7/0.5 1.5MM PVC W | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 90002757_0070 |  |  | 28 | 28 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 1 | EA | 2024-04-29 | 14 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 |  |  |  | 5300006467 | 70 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 70 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01)
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002500 | 70002500 (LED PANEL 30W 240V NON DIM OPAL WHT) | 99 | 255 | 4 | 0 | 4 | ODST-0090002757_0040 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 8 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 8 |  |  | 0040 | 1130 |  | 2024-02-12 | 40 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 |  |  | 2026-01-28 | 0 |  | 5000042660_2024_0001 | 2024-03-22 | 2024-03-21 |  |  | 0 | 2 | 3 | 0 | 4 | 0 | /180007840 |  | 0 | CPT | 3 | L |  | 0 | 5000042660 |  | 0 | 2024 | /018000784 |  | 90002757 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | LED PANEL 30W 240V NON DIM OPAL WHT | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 90002757_0040 |  |  | 28 | 28 |  | 4 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 4 | EA | 2024-04-29 | 8 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 |  |  |  | 5300006467 | 40 |  |  | 0 | 4 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 40 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01)
Onsite - Sloc 5001 | - | - |  | SIT |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002498 | 70002498 (EMER LED PANEL 30W OPAL WHT 295X1195IP20) | 99 | 255 | 8 | 8 | 0 | GRST-5000047052_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 4 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | SIT | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 4 | 2024-03-27 | 2024-03-09 | 0020 | 1130 | 070324 MACEDON | 2024-02-12 | 20 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000016815 | 1010 | 2026-01-28 | 8 | 4900035398_2024_0001 | 5000030591_2024_0001/5000030566_2024_0001 | 2024-03-07 | 2024-03-06 |  | 5000047052_2024_0001/5000046939_2024_0001 | 0 | 2 | 3 | 8 | 8 | 4 | /180007849 | 180009475 | 0 | CPT | 3 | L | 4900035398 | 2024 | 5000030591 | 5000047052 | 2024 | 2024 | /018000784 | 180009475 | 9000456 | 00000101000000022707 | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 | 2024-03-22 |  | 101000000022708 |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9000456_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 8 | EA | 2024-04-29 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 | 101000000023047 | 2024-03-22 |  | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01) |  | 10-07-03-01A
Onsite - Sloc 5001 | - | - |  | SIT |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002498 | 70002498 (EMER LED PANEL 30W OPAL WHT 295X1195IP20) | 99 | 255 | 8 | 8 | 0 | GRST-5000047052_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 4 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | SIT | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 4 | 2024-03-27 | 2024-03-09 | 0020 | 1130 |  | 2024-02-12 | 20 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000016815 | 1010 | 2026-01-28 | 8 | 4900035398_2024_0001 | 5000030591_2024_0001/5000030566_2024_0001 | 2024-03-07 | 2024-03-06 |  | 5000047052_2024_0001/5000046939_2024_0001 | 0 | 2 | 3 | 8 | 8 | 4 | /180007849 | 180009475 | 0 | CPT | 3 | L | 4900035398 | 2024 | 5000030591 | 5000047052 | 2024 | 2024 | /018000784 | 180009475 | 9000456 | 00000101000000022707 | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9000456_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 8 | EA | 2024-04-29 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 | 101000000022707 | 2024-03-22 |  | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01) |  | DU01-DU50-MACEDON
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002499 | 70002499 (LED PANEL 18W 240V NON DIM OPAL WHT) | 99 | 255 | 18 | 0 | 18 | ODST-0090002757_0030 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 6 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 6 |  |  | 0030 | 1130 |  | 2024-02-12 | 30 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 |  |  | 2026-01-28 | 0 |  | 5000042673_2024_0001/5000042664_2024_0001/5000042651_2024_0001/5000042616_2024_0001 | 2024-03-22 | 2024-03-21 |  |  | 0 | 2 | 3 | 0 | 18 | 0 | /180007840 |  | 0 | CPT | 3 | L |  | 0 | 5000042673 |  | 0 | 2024 | /018000784 |  | 90002757 | WorkPackLink | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | LED PANEL 18W 240V NON DIM OPAL WHT | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 90002757_0030 |  |  | 28 | 28 |  | 18 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 18 | EA | 2024-04-29 | 6 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 |  |  |  | 5300006467 | 30 |  |  | 0 | 18 | EA | 0 | 2001 | DU01 |  | 2024-03-22 | [5 empty] | 30 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01)
Onsite - Sloc 5001 | - | - |  | SIT |  | DU50 | 100073030 | Replace Lights in CCR (100073030) | Released | 2024-02-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 70002498 | 70002498 (EMER LED PANEL 30W OPAL WHT 295X1195IP20) | 99 | 255 | 8 | 8 | 0 | GRST-5000047052_2024 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | No Issue identified | 5300006467 | 1000002377 | 4 | 4500002717 | EX ENGINEERING PTY LTD (30000025) | 2024-03-15 | 2024-06-06 | AUS Operations (106) |  | DU01 | SIT | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in CCR D1 (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000220483 | 4 | 2024-03-27 | 2024-03-09 | 0020 | 1130 |  | 2024-02-12 | 20 | 0 | 0 | 38 | 2024-04-26 | 2024-04-01 | 2024-05-09 |  |  | 2024-04-29 | 100000016815 | 1010 | 2026-01-28 | 8 | 4900035398_2024_0001 | 5000030591_2024_0001/5000030566_2024_0001 | 2024-03-07 | 2024-03-06 |  | 5000047052_2024_0001/5000046939_2024_0001 | 0 | 2 | 3 | 8 | 8 | 4 | /180007849 | 180009475 | 0 | CPT | 3 | L | 4900035398 | 2024 | 5000030591 | 5000047052 | 2024 | 2024 | /018000784 | 180009475 | 9000456 | 00000101000000022707 | 2024-03-22 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 | 2024-03-22 |  |  |  |  | 0010 | INT | Replace Lights in CCR D1 |  |  | 9000456_0020 |  |  | 28 | 28 |  | 8 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002757 | 2024-03-21 |  | 8 | EA | 2024-04-29 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000218193 | S001 | 01-Road |  |  | 5300006467 | 20 |  |  | 0 | 8 | EA | 0 | 2001 | DU01 | 101000000022707 | 2024-03-22 |  | EA |  |  | 2024-03-07 | 20 | AU00 | 5-Completed |  | 20000369 | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-12 | 220483 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-10 | 2024-05-09 | 2024-05-09 | Material shortage/Pre-costed/Object created/Settlement rule created/Released/Order Approved | Reactive Maintenance (AM01) |  | 10-07-03-01A
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10243119 | 10243119 (ELEMENT KIT,FILT,SOLATURB 10647281) | 5 | 10 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 15 |  |  | 0150 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ELEMENT KIT,FILT,SOLATURB 10647281 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 10-03-05-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10185741 | 10185741 (DETERGENT,GP,CLEANER,CORROSION INHIBITOR) | 5 | 10 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 17 |  |  | 0170 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DETERGENT,GP,CLEANER,CORROSION INHIBITOR | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 21-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10191045 | 10191045 (GASKET,0.77IN ID,MTL,SOLATURB 903315C1) | 5 | 10 | 2 | 56 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 18 |  |  | 0180 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,0.77IN ID,MTL,SOLATURB 903315C1 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-01-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10229014 | 10229014 (GASKET,SPW,CL 150,RF,6IN ID,SS304,GRAPHI) | 5 | 10 | 1 | 12 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 19 |  |  | 0190 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CL 150,RF,6IN ID,SS304,GRAPHI | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 10-05-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10229980 | 10229980 (GASKET,BLEED AIR,2.82IN ID,5.63IN OD,0.0) | 5 | 10 | 2 | 13 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 20 |  |  | 0200 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,BLEED AIR,2.82IN ID,5.63IN OD,0.0 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-03-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10202018 | 10202018 (WATER,PURIFIED,DEMINERALISED,IBC/1000KG) | 5 | 10 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 21 |  |  | 0210 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WATER,PURIFIED,DEMINERALISED,IBC/1000KG | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 21-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10898330 | 10898330 (DISC,SAFETY,SOLATURB 999887C1) | 5 | 10 | 2 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DISC,SAFETY,SOLATURB 999887C1 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-03-08A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10231011 | 10231011 (O-RING,VITON V757,MIL-R-83248,SAE 225,TY) | 5 | 10 | 2 | 27 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,VITON V757,MIL-R-83248,SAE 225,TY | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-02-02-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10231207 | 10231207 (GASKET,TUBE,3/4IN NB,MTL,PACK/4 EACH) | 5 | 10 | 1 | 11 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 14 |  |  | 0140 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,TUBE,3/4IN NB,MTL,PACK/4 EACH | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-04-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10002572 | 10002572 (O-RING,3.234IN ID,0,139IN ESPESOR,NITRIL) | 5 | 10 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 13 |  |  | 0130 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,3.234IN ID,0,139IN ESPESOR,NITRIL | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-02-09A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11032438 | 11032438 (FILTER,ELEMENT,DRESRAND 80994353) | 5 | 10 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 12 |  |  | 0120 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER,ELEMENT,DRESRAND 80994353 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-02-09A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10502979 | 10502979 (FILTER ELEMENT,PARKER 10F10025) | 5 | 10 | 2 | 5 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 11 |  |  | 0110 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,PARKER 10F10025 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-03-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10274901 | 10274901 (ELEMENT,BARRIER,SOLATURB 10890343) | 5 | 10 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 10 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ELEMENT,BARRIER,SOLATURB 10890343 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-02-06A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10504518 | 10504518 (GASKET,4.27IN ID,SOLATURB 1995151) | 5 | 10 | 8 | 39 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,4.27IN ID,SOLATURB 1995151 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-04-08A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 8 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10251212 | 10251212 (GASKET,0.344IN ID,SOLATURB 1007799) | 5 | 10 | 4 | 27 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,0.344IN ID,SOLATURB 1007799 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-03-06A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10251214 | 10251214 (GASKET,SPW,1.25IN,SOLATURB 1017891) | 5 | 10 | 2 | 8 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 9 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,1.25IN,SOLATURB 1017891 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-01-09A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10243123 | 10243123 (ELEMENT KIT,FILT,SOLATURB 186280600) | 5 | 10 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 8 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ELEMENT KIT,FILT,SOLATURB 186280600 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 10-08-01-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10231204 | 10231204 (GASKET,EB,TORCH,SOLATURB 1739421) | 5 | 10 | 2 | 14 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 6 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,EB,TORCH,SOLATURB 1739421 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-03-05A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10243108 | 10243108 (FILTER ELEMENT,CART,SOLATURB 106081710) | 5 | 10 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 7 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,CART,SOLATURB 106081710 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 10-04-05-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500003180/00030 - Due Date | - |  | IP REVIEW 12.03: Not Delivered Yet ETA 22.03 PO 4500003180 Klinger | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10015056 | 10015056 (GASKET,SPW,CRIR,CL 300/600,25MM NB,SS316) | 5 | 10 | 2 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | IP REVIEW 12.03: Not Delivered Yet ETA 22.03 PO 4500003180 Klinger | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 24 |  |  | 0240 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 300/600,25MM NB,SS316 | [5 empty] | 0160 | INT | Mech Service Package D6 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 12 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10265076 | 10265076 (WASHER,FLAT,1/2IN ID,17-7PH,HARDENED) | 5 | 10 | 8 | 92 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 43 |  |  | 0430 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WASHER,FLAT,1/2IN ID,17-7PH,HARDENED | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-02-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 8 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10196866 | 10196866 (BOLT,HEX,0.50-13 SIZE,SOLATURB 1731012) | 5 | 10 | 8 | 80 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 42 |  |  | 0420 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BOLT,HEX,0.50-13 SIZE,SOLATURB 1731012 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-02-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 8 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10230665 | 10230665 (VALVE,CHECK,SWING,1IN NB,NPTF) | 5 | 10 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 41 |  |  | 0410 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,CHECK,SWING,1IN NB,NPTF | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-01-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10502980 | 10502980 (FILTER ELEMENT,PARKER 6F10025) | 5 | 10 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 40 |  |  | 0400 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,PARKER 6F10025 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-04-05A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11041999 | 11041999 (O-RING,BUNA-N,SAE 143,SOLATURB 1094051) | 5 | 10 | 1 | 11 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 39 |  |  | 0390 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,BUNA-N,SAE 143,SOLATURB 1094051 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-03-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10228388 | 10228388 (FILTER ELEMENT,AIR,SOLATURB 10874913) | 5 | 10 | 1 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 38 |  |  | 0380 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,AIR,SOLATURB 10874913 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-01-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10144284 | 10144284 (BATTERY,SERIES B,AB 1756BA2) | 5 | 10 | 1 | 5 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 37 |  |  | 0370 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BATTERY,SERIES B,AB 1756BA2 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-02-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10504692 | 10504692 (ELEMENT KIT,GAS FUEL,SOLATURB 105636930) | 5 | 10 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 36 |  |  | 0360 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ELEMENT KIT,GAS FUEL,SOLATURB 105636930 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 10-03-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11093550 | 11093550 (O-RING,169.3MM ID X 5.7MM,CRANE 89150084) | 5 | 10 | 1 | 1 | 1 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 35 |  |  | 0350 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,169.3MM ID X 5.7MM,CRANE 89150084 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-01-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11086322 | 11086322 (BELT,V,2000MM LG P,12MM W,8MM P,SYNC,RD) | 5 | 10 | 2 | 7 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 34 |  |  | 0340 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BELT,V,2000MM LG P,12MM W,8MM P,SYNC,RD | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-02-01-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11079030 | 11079030 (FILTER ELEMENT,H2O,SOLATURB 602205C1) | 5 | 10 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 33 |  |  | 0330 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,H2O,SOLATURB 602205C1 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-01-09A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11092315 | 11092315 (RING,BACK-UP,CRANE 89114673) | 5 | 10 | 2 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 32 |  |  | 0320 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | RING,BACK-UP,CRANE 89114673 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-03-08A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11092270 | 11092270 (FILTER ELEMENT,SS,CRANE 89460717) | 5 | 10 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 31 |  |  | 0310 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,SS,CRANE 89460717 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-02-01-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11093552 | 11093552 (O-RING,179.3MM X 5.7MM,CRANE 87461607) | 5 | 10 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 30 |  |  | 0300 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,179.3MM X 5.7MM,CRANE 87461607 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-01-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10371643 | 10371643 (PARTS KIT,VLV,SOLATURB 997396C1) | 5 | 10 | 1 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 28 |  |  | 0280 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | PARTS KIT,VLV,SOLATURB 997396C1 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-01-04A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | No PO | - |  | 03.04 - ATN Purchasing PR 2000049129 to PO, (77 SOH at Du50) | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11359230 | 11359230 (FILTER ELEMENT,AIR,CYL,SOLATURB 603346C1) | 5 | 10 | 80 | 77 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,AIR,CYL,SOLATURB 603346C1 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 10-04-02-05A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 80 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10229789 | 10229789 (BREATHER,CONDUIT,SOLATURB 70301431) | 5 | 10 | 2 | 5 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 27 |  |  | 0270 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BREATHER,CONDUIT,SOLATURB 70301431 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-04-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10189853 | 10189853 (IGNITER,SPARK,GAS TURB,PLUG,TORCH,IRIDIU) | 5 | 10 | 1 | 8 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 26 |  |  | 0260 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | IGNITER,SPARK,GAS TURB,PLUG,TORCH,IRIDIU | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-01-05A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10015027 | 10015027 (GASKET,SPW,CRIR,CL 300/600,15MM NB,SS316) | 5 | 10 | 2 | 16 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 25 |  |  | 0250 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 300/600,15MM NB,SS316 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-03-01-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10015055 | 10015055 (GASKET,SPW,CRIR,CL 150,25MM NB,SS316 INN) | 5 | 10 | 2 | 29 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 23 |  |  | 0230 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 150,25MM NB,SS316 INN | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 10-05-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 10251213 | 10251213 (GASKET,0.938IN ID,SOLATURB 1008726) | 5 | 10 | 3 | 20 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 22 |  |  | 0220 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,0.938IN ID,SOLATURB 1008726 | [5 empty] | 0160 | INT | Mech Service Package D6 |  |  |  |  | 11-01-03-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
No Stock at Base | 4500003445/00010 - Due Date 45383 | PDC - MAC NG (DU01)1000007452 / 00097 - Due Date 30/04/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-05-10 | 2024-04-16 | 2024-04-16 | 70002669 | 70002669 (Sample Cell matched pair 1cm P/N KH2001) | 30 | 30 | 1 | 0 | 0 | PRPO-1000007452_00097 | PR approved; PO not issued | Directs (Inventory) (SP14) | No Issue identified | 5300006839 | 1000007452 | 97 |  |  |  | 2024-05-02 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 97 |  |  | 0470 | 1130 |  | 2024-02-19 | 390 | 0 | 0 | 0 | 2024-04-30 | 2024-05-08 | 2024-04-16 |  |  | 2024-05-02 |  |  | 2025-02-10 | 0 |  |  | 2024-05-02 | 2024-05-10 | Macedon Lab |  | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-05-02 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Sample Cell matched pair 1cm P/N KH2001 | 2024-05-02 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 7 | 7 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-16 |  | 1 | EA | 2024-05-02 | 97 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 390 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-05-02 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007452 / 00095 - Due Date 14/05/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-05-10 | 2024-04-16 | 2024-04-16 | 70005165 | 70005165 (MEDIA MODIFIED POSTGATES (MPB) GROWTH IN) | 30 | 30 | 2 | 0 | 0 | PRPO-1000007452_00095 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007452 | 95 |  |  |  | 2024-06-01 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 95 |  |  | 0460 | 1130 |  | 2024-02-19 | 380 | 0 | 0 | 15 | 2024-05-14 | 2024-05-08 | 2024-04-16 |  |  | 2024-05-17 |  |  | 2025-02-10 | 0 |  |  | 2024-05-02 | 2024-05-10 | Macedon Lab |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-05-02 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MEDIA MODIFIED POSTGATES (MPB) GROWTH IN | 2024-05-02 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 35 | 35 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 2 | PAC | 2024-05-17 | 95 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 380 |  |  | 0 | 2 | PAC | 0 | 2001 | DU01 |  | 2024-05-02 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007452 / 00093 - Due Date 14/05/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-05-10 | 2024-04-16 | 2024-04-16 | 70005164 | 70005164 (MEDIA, PHENOL RED DEXTROSE (PRD) FOR DET) | 30 | 30 | 2 | 0 | 0 | PRPO-1000007452_00093 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007452 | 93 |  |  |  | 2024-06-01 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 93 |  |  | 0450 | 1130 |  | 2024-02-19 | 370 | 0 | 0 | 15 | 2024-05-14 | 2024-05-08 | 2024-04-16 |  |  | 2024-05-17 |  |  | 2025-02-10 | 0 |  |  | 2024-05-02 | 2024-05-10 | Macedon Lab |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-05-02 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MEDIA, PHENOL RED DEXTROSE (PRD) FOR DET | 2024-05-02 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 35 | 35 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 2 | PAC | 2024-05-17 | 93 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 370 |  |  | 0 | 2 | PAC | 0 | 2001 | DU01 |  | 2024-05-02 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Remote Pick - Low Stock | 4500002064/00030 - Due Date | - |  | 03.04 - SOH at DU01 - monitor STO 5200004830 10.04 del date | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11093583 | 11093583 (RING,BACK-UP,CRANE 87480284) | 5 | 10 | 1 | 0 | 2 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | IP REVIEW 12.03: On track at DU01 awaiting SIT | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 29 |  |  | 0290 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | RING,BACK-UP,CRANE 87480284 | [5 empty] | 0160 | INT | Mech Service Package D6 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500002064/00010 - Due Date | - |  | 03.04 - SOH at DU01 - monitor STO 5200004829 10.04 del date | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-10 | 2024-04-30 | 2024-06-12 | 11092272 | 11092272 (O-RING,3.109IN X 0.139IN,CRANE 87460999) | 5 | 10 | 2 | 0 | 4 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | P REVIEW 12.03: On track at DU01 awaiting SIT | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D6 (0160) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 16 |  |  | 0160 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-10 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,3.109IN X 0.139IN,CRANE 87460999 | [5 empty] | 0160 | INT | Mech Service Package D6 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 100073295 | Emergency Lighting Repairs Required (100073295) | Released | 2024-02-16 | 2024-05-13 | 2024-05-13 | 2024-05-13 | 70002778 | 70002778 (STAHL 6V/7Ah BATTERY FOR 6009/6409) | 99 | 255 | 11 | 0 | 11 | ODST-0090002761_0010 | Workpack awaiting Shipment @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006728 | 1000002849 | 2 | 4500003384 | EX ENGINEERING PTY LTD (30000025) | 2024-04-10 | 2024-05-04 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Emergency Lighting Repairs Required (0010) | Electrical LV Distribution (DU50.MA.UEP.40) | 0000222507 | 2 |  |  | 0010 | 1130 |  | 2024-02-16 | 10 | 0 | 0 | 0 | 2024-05-01 | 2024-05-11 | 2024-05-13 |  |  | 2024-05-04 |  |  | 2026-02-01 | 0 |  | 5000048660_2024_0001/5000048622_2024_0001 | 2024-05-06 | 2024-03-30 |  |  | 0 | 2 | 3 | 0 | 11 | 3 | /180013441 |  | 0 | CPT | 3 | L |  | 0 | 5000048660 |  | 0 | 2024 | /018001344 |  | 90002761 | WorkPackLink | 2024-05-06 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | STAHL 6V/7Ah BATTERY FOR 6009/6409 | 2024-05-06 |  | 101000000030317 |  |  | 0010 | INT | Emergency Lighting Repairs Required |  |  | 90002761_0010 |  |  | 56 | 56 |  | 11 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002761 | 2024-02-27 |  | 11 | EA | 2024-05-04 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220193 | S001 |  |  |  | 5300006728 | 10 |  |  | 0 | 11 | EA | 0 | 2001 | DU01 | 101000000030319 | 2024-05-06 |  | EA |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-16 | 222507 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-13 | 2024-05-13 | 2024-05-13 | Settlement rule created/Order Approved/Pre-costed/Released/Object created/Material shortage | Reactive Maintenance (AM01) |  | DU01-DU50-MACEDON
Stock Available at Base | - | - |  | Not Delivered Yet |  | DU50 | 100073295 | Emergency Lighting Repairs Required (100073295) | Released | 2024-02-16 | 2024-05-13 | 2024-05-13 | 2024-05-13 | 70002778 | 70002778 (STAHL 6V/7Ah BATTERY FOR 6009/6409) | 99 | 255 | 11 | 0 | 11 | ODST-0090002761_0010 | Workpack awaiting Shipment @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300006728 | 1000002849 | 2 | 4500003384 | EX ENGINEERING PTY LTD (30000025) | 2024-04-10 | 2024-05-04 | AUS Operations (106) |  | DU01 | Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Emergency Lighting Repairs Required (0010) | Electrical LV Distribution (DU50.MA.UEP.40) | 0000222507 | 2 |  |  | 0010 | 1130 |  | 2024-02-16 | 10 | 0 | 0 | 0 | 2024-05-01 | 2024-05-11 | 2024-05-13 |  |  | 2024-05-04 |  |  | 2026-02-01 | 0 |  | 5000048660_2024_0001/5000048622_2024_0001 | 2024-05-06 | 2024-03-30 |  |  | 0 | 2 | 3 | 0 | 11 | 8 | /180013441 |  | 0 | CPT | 3 | L |  | 0 | 5000048660 |  | 0 | 2024 | /018001344 |  | 90002761 | WorkPackLink | 2024-05-06 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | STAHL 6V/7Ah BATTERY FOR 6009/6409 | 2024-05-06 |  | 101000000030316 |  |  | 0010 | INT | Emergency Lighting Repairs Required |  |  | 90002761_0010 |  |  | 56 | 56 |  | 11 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002761 | 2024-02-27 |  | 11 | EA | 2024-05-04 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220193 | S001 |  |  |  | 5300006728 | 10 |  |  | 0 | 11 | EA | 0 | 2001 | DU01 | 101000000030318 | 2024-05-06 |  | EA |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-16 | 222507 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-13 | 2024-05-13 | 2024-05-13 | Settlement rule created/Order Approved/Pre-costed/Released/Object created/Material shortage | Reactive Maintenance (AM01) |  | DU01-DU50-MACEDON
Stock Available at Base | - | - |  | IP REVIEW 19.03: Not Delivered Yet |  | DU50 | 100074581 | Replace Admin Building Down Lights (100074581) | Released | 2024-03-14 | 2024-05-13 | 2024-05-13 | 2024-05-14 | 70004011 | 70004011 (Phillips DN029BL12CCT150 LED Downlight) | 99 | 255 | 45 | 0 | 45 | GRPO-5000045622_2024 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300007893 | 1000005536 | 2 | 4500006895 | EX ENGINEERING PTY LTD (30000025) | 2024-03-21 | 2024-05-04 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: Not Delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Admin Building Down Lights (0010) | ADMIN BUILDING MAIN DB (DU50.FBD.MO-620-EDB-6412) | 0000226558 | 2 |  |  | 0010 | 1130 |  | 2024-03-14 | 10 | 0 | 0 | 0 | 2024-05-01 | 2024-05-11 | 2024-05-13 |  |  | 2024-05-04 |  |  | 2026-02-02 | 0 |  | 5000045622_2024_0001/5000045601_2024_0001/5000045584_2024_0001/5000045577_2024_0001/5000045548_2024_0001/5000045540_2024_0001/5000045527_2024_0001/5000045476_2024_0001 | 2024-05-06 | 2024-03-26 | Mac Store |  | 0 | 2 | 3 | 0 | 45 | 0 | 180012404/ |  | 0 | CPT | 3 | L |  | 0 | 5000045622 |  | 0 | 2024 | 180012404 |  |  | WorkPackLink | 2024-05-06 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Phillips DN029BL12CCT150 LED Downlight | 2024-05-06 |  |  |  |  | 0010 | INT | Replace Admin Building Down Lights | [5 empty] | 7 | 7 |  | 45 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-17 |  | 45 | EA | 2024-05-04 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000224101 | S001 |  |  |  | 5300007893 | 10 |  |  | 0 | 45 | EA | 0 | 2001 | DU01 |  | 2024-05-06 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-14 | 226558 | 0 | INLEC |  | 3 |  |  | CC11874501 |  | 2024-05-14 | 2024-05-13 | 2024-05-13 | Settlement rule created/Pre-costed/Released/Order Approved/Material shortage/Object created | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-13 | 2024-04-30 | 2024-06-12 | 11391404 | 11391404 (ELEMENT,DEPTH MEDIA,N15,HYDAC N15DM002) | 5 | 10 | 1 | 6 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Svc D9-Repl Vnsh Fltr&Insp DGS Line (0250) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 44 |  |  | 0440 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-13 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ELEMENT,DEPTH MEDIA,N15,HYDAC N15DM002 | [5 empty] | 0250 | INT | Mech Svc D9-Repl Vnsh Fltr&Insp DGS Line |  |  |  |  | 10-05-01-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink | 24MCSGA | DU50 | 200126975 | 2Y Mech & Elec Svce SGC-A (200126975) | Released | 2024-01-02 | 2024-05-13 | 2024-04-30 | 2024-06-12 | 11391365 | 11391365 (O-RING,FILTER HOUSING SEAL,VARNISH REMOV) | 5 | 10 | 1 | 7 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Svc D9-Repl Vnsh Fltr&Insp DGS Line (0250) | Sales Gas Train A (DU50.MA.GSG.10) | 0000201758 | 45 |  |  | 0450 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-13 | [5 empty] | 2024-07-16 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,FILTER HOUSING SEAL,VARNISH REMOV | [5 empty] | 0250 | INT | Mech Svc D9-Repl Vnsh Fltr&Insp DGS Line |  |  |  |  | 11-03-01-09A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000201153 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 | 24MCSGA | 2024-06-12 | 2024-04-30 | 2024-04-30 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Stock Available at Base | - | - |  | UserCommentLink |  | DU50 | 100072011 | GTG-D Replace oil level indicator (100072011) | Released | 2024-01-29 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 70001096 | 70001096 (GAGE,LEVEL,FLOAT) | 30 | 30 | 1 | 0 | 1 | ODST-0090002756_0010 | Material is received @DU01 | Directs (Inventory) (SP14) | No Issue identified | 5300005677 | 1000001401 | 2 | 4500001227 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-02-07 | 2024-05-25 | AUS Operations (106) |  | DU01 | UserCommentLink | N | Scheduling (06) | Ready to Schedule (Order) (0060) | GTG-D Replace oil level indicator (0010) | Turbine Driven Generator Pkg D (DU50.MA.UEP.10.PG006) | 0000216541 | 2 |  |  | 0010 | 1130 |  | 2024-01-29 | 10 | 0 | 0 | 20 | 2024-05-02 | 2024-04-20 | 2024-05-15 |  |  | 2024-05-05 |  |  | 2024-12-24 | 0 |  | 5000027021_2024_0001 | 2024-04-15 | 2024-02-28 | Mac Store |  | 0 | 2 | 3 | 0 | 1 | 0 | 180006615 |  | 0 | EXW | 3 | L |  | 0 | 5000027021 |  | 0 | 2024 | 180006615 |  | 90002756 | WorkPackLink | 2024-04-15 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GAGE,LEVEL,FLOAT | 2024-04-15 |  |  |  |  | 0010 | INT | GTG-D Replace oil level indicator |  |  | 90002756_0010 |  |  | 84 | 84 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002756 | 2024-02-01 |  | 1 | EA | 2024-05-05 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000214698 | S001 |  |  |  | 5300005677 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-15 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-01-23 | 216541 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-16 | 2024-05-15 | 2024-05-15 | Material shortage/Settlement rule created/Order Approved/Object created/Ready For Scheduling/Released/Pre-costed | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | AT MAC |  | DU50 | 200127094 | 24M Replace Flare PLC Battery (200127094) | Released | 2024-01-02 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 10144284 | 10144284 (BATTERY,SERIES B,AB 1756BA2) | 20 | 20 | 1 | 5 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Replace Flare PLC Battery (0010) | Flare Pilot & Ignition Skid (DU50.MA.VFL.30.ME002) | 0000201890 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-15 | [5 empty] | 2024-05-15 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BATTERY,SERIES B,AB 1756BA2 | [5 empty] | 0010 | INT | Replace Flare PLC Battery |  |  |  |  | 11-03-02-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000201273 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | AT MAC |  | DU50 | 200127095 | 2Y Replace VESDA Filter (200127095) | Released | 2024-01-02 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 10059698 | 10059698 (FILTER,CARTRIDGE,WORMALD VSP005) | 20 | 20 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Replace Filter Cartridge & Reset Timer (0010) | DBNGP Instrument Gas Common (DU50.MA.GSG.60.PS001) | 0000201891 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-15 | [5 empty] | 2024-05-15 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER,CARTRIDGE,WORMALD VSP005 | [5 empty] | 0010 | INT | Replace Filter Cartridge & Reset Timer |  |  |  |  | 11-03-04-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000201274 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Pre-costed/Object created/Estimated costs/Material shortage/Settlement rule created | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200129142 | 4Y Cft MO-PSV-36014 (200129142) | Released | 2024-01-01 | 2024-05-16 | 2024-05-16 | 2024-07-11 | 11175295 | 11175295 (VALVE,SAFETY,40*G*80,PILOT OPER,SA352 LC) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Exch Fuel Gas Super Heater (DU50.MA.UFS.30.HX001) | 0000203925 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-16 | [5 empty] | 2024-07-25 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,40*G*80,PILOT OPER,SA352 LC | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203220 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-07-11 | 2024-05-16 | 2024-05-16 | Released/Settlement rule created/Pre-costed/Object created/Estimated costs/Material shortage | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed |  | IP REVIEW 27.03: Expediting REP Callidus K 4500000314 |  | DU50 | 200129142 | 4Y Cft MO-PSV-36014 (200129142) | Released | 2024-01-01 | 2024-05-16 | 2024-05-16 | 2024-07-11 | 11175295 | 11175295 (VALVE,SAFETY,40*G*80,PILOT OPER,SA352 LC) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | NEW |  | IP REVIEW 27.03: Expediting REP Callidus K 4500000314 | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Exch Fuel Gas Super Heater (DU50.MA.UFS.30.HX001) | 0000203925 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-16 | [5 empty] | 2024-07-25 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,40*G*80,PILOT OPER,SA352 LC | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203220 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-07-11 | 2024-05-16 | 2024-05-16 | Released/Settlement rule created/Pre-costed/Object created/Estimated costs/Material shortage | Proactive Maintenance (AM02)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007452 / 00103 - Due Date 24/05/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-05-17 | 2024-04-16 | 2024-04-16 | 70005168 | 70005168 (GAS, CALIBRATION 8AL - 58L - 5 ppm BENZE) | 30 | 30 | 2 | 0 | 0 | PRPO-1000007452_00103 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007452 | 103 |  |  |  | 2024-06-14 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 103 |  |  | 0500 | 1130 |  | 2024-02-19 | 420 | 0 | 0 | 18 | 2024-05-24 | 2024-05-15 | 2024-04-16 |  |  | 2024-05-27 |  |  | 2025-02-10 | 0 |  |  | 2024-05-09 | 2024-05-17 | Macedon Lab |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-05-09 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GAS, CALIBRATION 8AL - 58L - 5 ppm BENZE | 2024-05-09 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 45 | 45 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 2 | EA | 2024-05-27 | 103 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 420 |  |  | 0 | 2 | EA | 0 | 2001 | DU01 |  | 2024-05-09 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
No Stock at Base | No PO | PDC - MAC NG (DU01)1000007452 / 00105 - Due Date 24/05/2024 |  | UserCommentLink |  | DU50 | 500003979 | MACEDON OPS - CONSUMABLES 2024 (500003979) | Released | 2024-02-19 | 2024-05-17 | 2024-04-16 | 2024-04-16 | 70005122 | 70005122 (GAS, CALIBRATION 6DM - 58L - 50% METHANE) | 30 | 30 | 2 | 0 | 0 | PRPO-1000007452_00105 | PR approved; PO not issued | Directs (Inventory) (SP14) | PR due for release | 5300006839 | 1000007452 | 105 |  |  |  | 2024-06-14 |  |  | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | PROCUREMENT OF MOZZIE MATS - CONSUMABLES (0010) | Workshop/Warehouse Building (DU50.MA.FBD.06) | 0000222511 | 105 |  |  | 0510 | 1130 |  | 2024-02-19 | 430 | 0 | 0 | 18 | 2024-05-24 | 2024-05-15 | 2024-04-16 |  |  | 2024-05-27 |  |  | 2025-02-10 | 0 |  |  | 2024-05-09 | 2024-05-17 | Macedon Lab |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-05-09 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GAS, CALIBRATION 6DM - 58L - 50% METHANE | 2024-05-09 |  |  |  |  | 0010 | INT | PROCUREMENT OF MOZZIE MATS - CONSUMABLES | [5 empty] | 45 | 45 |  | 0 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-02 |  | 2 | EA | 2024-05-27 | 105 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000220196 | S001 |  |  |  | 5300006839 | 430 |  |  | 0 | 2 | EA | 0 | 2001 | DU01 |  | 2024-05-09 | Macedon Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GSJ | 2024-02-16 | 222511 | 0 | WARE |  | 1 |  |  | CC11874501 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | Settlement rule created/Pre-costed/Object created/Goods movement posted/Released/Material shortage | Non-Execution (AM05)
Remote Pick - Low Stock | 4500007710/00010 - Due Date 45392 | - | 03.04 - Expedite email sent 03/04 - Atom | 03.04 PURCHASING Expediting PO 4500007710 Atom Supply - ETA 10.04 |  | DU50 | 100074627 | GEA batteries require replacement (100074627) | Released | 2024-03-14 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 11027363 | 11027363 (BATTERY,STORAGE,12V,MAINT FREE,600CCA,15) | 20 | 20 | 2 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | PO 4500007710 Atom Supply - ETA 10.04.24 | N | Preparation (05) | In Preparation (Order) (0055) | GEA batteries require replacement (0010) | Gas Eng Alternator (DU50.MA.UEP.10.PG002) | 0000226699 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-20 | [5 empty] | 2024-08-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BATTERY,STORAGE,12V,MAINT FREE,600CCA,15 | [5 empty] | 0010 | INT | GEA batteries require replacement | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000224076 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-14 | 0 | 0 | INLEC |  | 4 |  |  | CC11874501 |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | Pre-costed/Material shortage/Object created/Released/Settlement rule created/Order Approved | Reactive Maintenance (AM01)
Remote Pick - Low Stock | No PO | - |  | 03.04 - SOH at DT01 - should be DU01 - PDC to check date |  | DU50 | 200132257 | 5Y Cft MO-PSV-53004 (200132257) | Released | 2024-01-02 | 2024-05-20 | 2024-05-20 | 2024-07-15 | 11175259 | 11175259 (VALVE,SAFETY,40*G*80,CONVENTIONAL,DIRECT) | 20 | 20 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Filter Diesel (DU50.MA.UFS.20.VP001) | 0000207073 | 3 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-20 | [5 empty] | 2024-05-13 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,40*G*80,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000206456 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-15 | 2024-05-20 | 2024-05-20 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02)
No Stock at Base | 4500002830/00020 - Due Date 45419 | No Req or Processed |  | IP REVIEW 13.03: Not Delivered Yet ETA 26.03 4500002830 Solar Turbines |  | DU50 | 100072777 | Replace filter socks E12 SGC-B (100072777) | Released | 2024-03-11 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 70002507 | 70002507 (CABLE TIE W X 48 IN,NYLON) | 30 | 30 | 80 | 0 | 0 | POPO-4500006309_00020 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300007740 | 1000005026 | 2 | 4500006309 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-03-26 | 2024-11-09 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not Delivered Yet ETA 26.03 4500002830 Solar Turbines | N | Preparation (05) | In Preparation (Order) (0055) | Replace filter socks E12 SGC-B (0010) | SALES GAS COMPRESSORS COMMON 340-PSSY02 (DU50.GSG.MO-340-PSSY02) | 0000219417 | 2 |  |  | 0020 | 1130 |  | 2024-03-11 | 20 | 0 | 0 | 113 | 2024-07-16 | 2024-04-06 | 2024-05-21 |  |  | 2024-07-19 |  |  | 2025-02-01 | 0 |  |  | 2024-03-28 | 2024-04-08 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | EXW | 1 | L |  | 0 |  |  | 0 |  |  |  | 90004495 | WorkPackLink | 2024-03-28 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | CABLE TIE W X 48 IN,NYLON | 2024-03-28 | Supply for Order 100072777, Item 2 cannot be changed 90004495 item 20 already exists |  |  |  | 0010 | INT | Replace filter socks E12 SGC-B |  |  | 90004495_0020 |  |  | 120 | 120 |  | 80 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90004495 | 2024-03-11 |  | 80 | EA | 2024-07-19 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000217272 | S001 |  |  |  | 5300007740 | 20 |  |  | 0 | 80 | EA | 0 | 2001 | DU01 |  | 2024-03-28 | [5 empty] | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-08 | 219417 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | Object created/Settlement rule created/Pre-costed/Released/Order Approved/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500002830/00010 - Due Date 45419 | No Req or Processed |  | IP REVIEW 13.03: Not Delivered Yet ETA 07.05 4500002830 Solar Turbines |  | DU50 | 100072777 | Replace filter socks E12 SGC-B (100072777) | Released | 2024-03-11 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 70002506 | 70002506 (ELEMENT,FLTR,AIR,CYL,SOCK) | 30 | 30 | 80 | 0 | 0 | POPO-4500006309_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300007740 | 1000005026 | 1 | 4500006309 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-07 | 2024-11-09 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not Delivered Yet ETA 07.05 4500002830 Solar Turbines | N | Preparation (05) | In Preparation (Order) (0055) | Replace filter socks E12 SGC-B (0010) | SALES GAS COMPRESSORS COMMON 340-PSSY02 (DU50.GSG.MO-340-PSSY02) | 0000219417 | 1 |  |  | 0010 | 1130 |  | 2024-03-11 | 10 | 0 | 0 | 113 | 2024-07-16 | 2024-04-06 | 2024-05-21 |  |  | 2024-07-19 |  |  | 2025-02-01 | 0 |  |  | 2024-03-28 | 2024-04-08 |  |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | EXW | 1 | L |  | 0 |  |  | 0 |  |  |  | 90004495 | WorkPackLink | 2024-03-28 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ELEMENT,FLTR,AIR,CYL,SOCK | 2024-03-28 | Supply for Order 100072777, Item 1 cannot be changed 90004495 item 10 already exists |  |  |  | 0010 | INT | Replace filter socks E12 SGC-B |  |  | 90004495_0010 |  |  | 120 | 120 |  | 80 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90004495 | 2024-03-11 |  | 80 | EA | 2024-07-19 | 1 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000217272 | S001 |  |  |  | 5300007740 | 10 |  |  | 0 | 80 | EA | 0 | 2001 | DU01 |  | 2024-03-28 | [5 empty] | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GLS | 2024-02-08 | 219417 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | Object created/Settlement rule created/Pre-costed/Released/Order Approved/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500007336/00010 - Due Date 45385 | No Req or Processed |  | IP REVIEW 19.03: Not delivered Yet |  | DU50 | 100074626 | Replace Lights in Workshop and warehouse (100074626) | Released | 2024-03-14 | 2024-05-22 | 2024-05-22 | 2024-05-23 | 70003988 | 70003988 (Pierlite ECOHB200LSE5G7 ECO HIGHBAY 200W) | 99 | 255 | 20 | 0 | 0 | IDPO-/018001357 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver in-full | 5300007913 | 1000005604 | 3 | 4500007336 | EX ENGINEERING PTY LTD (30000025) | 2024-04-03 | 2024-05-12 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in Workshop and warehouse (0010) | BUILDING WORKSHOP/WAREHOUSE 810-Q-802 (DU50.FBD.MO-810-Q-802) | 0000226698 | 3 |  |  | 0010 | 1130 |  | 2024-03-14 | 10 | 0 | 0 | 0 | 2024-05-09 | 2024-05-20 | 2024-05-22 |  |  | 2024-05-12 |  |  | 2026-02-10 | 0 |  |  | 2024-05-14 | 2024-05-22 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 | /180013576 |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  | /018001357 |  |  | WorkPackLink | 2024-05-14 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Pierlite ECOHB200LSE5G7 ECO HIGHBAY 200W | 2024-05-14 |  |  |  |  | 0010 | INT | Replace Lights in Workshop and warehouse | [5 empty] | 14 | 14 |  | 20 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-17 |  | 20 | EA | 2024-05-12 | 3 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000224075 | S001 |  |  |  | 5300007913 | 10 |  |  | 0 | 20 | EA | 0 | 2001 | DU01 |  | 2024-05-14 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-14 | 226698 | 0 | BUILD |  | 1 |  |  | CC11874501 |  | 2024-05-23 | 2024-05-22 | 2024-05-22 | Order Approved/Released/Object created/Material shortage/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500007336/00020 - Due Date 45385 | No Req or Processed |  | IP REVIEW 19.03: Not delivered Yet |  | DU50 | 100074626 | Replace Lights in Workshop and warehouse (100074626) | Released | 2024-03-14 | 2024-05-22 | 2024-05-22 | 2024-05-23 | 70003989 | 70003989 (Socket Surface RC 2G 10A 250V 3 Pin 1P) | 99 | 255 | 10 | 0 | 0 | IDPO-/018001357 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver in-full | 5300007913 | 1000005604 | 4 | 4500007336 | EX ENGINEERING PTY LTD (30000025) | 2024-04-03 | 2024-05-12 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lights in Workshop and warehouse (0010) | BUILDING WORKSHOP/WAREHOUSE 810-Q-802 (DU50.FBD.MO-810-Q-802) | 0000226698 | 4 |  |  | 0020 | 1130 |  | 2024-03-14 | 20 | 0 | 0 | 0 | 2024-05-09 | 2024-05-20 | 2024-05-22 |  |  | 2024-05-12 |  |  | 2026-02-10 | 0 |  |  | 2024-05-14 | 2024-05-22 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 | /180013576 |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  | /018001357 |  |  | WorkPackLink | 2024-05-14 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Socket Surface RC 2G 10A 250V 3 Pin 1P | 2024-05-14 |  |  |  |  | 0010 | INT | Replace Lights in Workshop and warehouse | [5 empty] | 14 | 14 |  | 10 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-17 |  | 10 | EA | 2024-05-12 | 4 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000224075 | S001 |  |  |  | 5300007913 | 20 |  |  | 0 | 10 | EA | 0 | 2001 | DU01 |  | 2024-05-14 | Mac Store |  |  |  |  | 20 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-14 | 226698 | 0 | BUILD |  | 1 |  |  | CC11874501 |  | 2024-05-23 | 2024-05-22 | 2024-05-22 | Order Approved/Released/Object created/Material shortage/Pre-costed/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500007088/00030 - Due Date 45643 | No Req or Processed |  | IP REVIEW 13.03: Not Delivered Yet ETA 01.05, B513592043 Solar Turbines |  | DU50 | 100068055 | Replace Lube oil pump on RGB - GTG D (100068055) | Released | 2024-03-11 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 10617159 | 10617159 (MQ0032611-1635418-100-KIT,RETROFIT,L/O P) | 30 | 30 | 1 | 0 | 0 | STST-5300007738_00010 | STO raised (through orchestration) | Stock at Base (SP12) | No Issue identified | 5300007738 |  | 0 |  |  |  | 2024-05-24 |  |  | DU01 | IP REVIEW 13.03: Not Delivered Yet ETA 01.05, B513592043 Solar Turbines | N | Preparation (05) | In Preparation (Order) (0055) | Replace Lube oil pump on RGB - GTG D (0010) | Turbine Driven Generator Pkg D (DU50.MA.UEP.10.PG006) | 0000208337 | 1 |  |  | 0010 | 1130 |  | 2024-03-11 | 10 | 0 | 0 | 0 |  | 2024-05-22 | 2024-05-24 | [5 empty] | 2024-08-02 | 0 |  |  | 2024-05-16 | 2024-05-24 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-05-16 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MQ0032611-1635418-100-KIT,RETROFIT,L/O P | 2024-05-16 |  |  |  |  | 0010 | INT | Replace Lube oil pump on RGB - GTG D | [5 empty] | 0 | 60 |  | 0 | [5 empty] | 0 | AUS Operations (106) | AU00 |  | DU50 |  |  |  | 1 | EA |  | 1 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207741 | S001 |  | 30 | 30 | 5300007738 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-05-16 | [5 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208337 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | Pre-costed/Object created/Order Approved/Released/Material shortage/Settlement rule created | Reactive Maintenance (AM01)
No Stock at Base | 4500007088/00030 - Due Date 45643 | No Req or Processed |  | IP REVIEW 14.03: Not Delivered Yet ETA 01.05 B513592043 Solar Turbines |  | DU50 | 100068674 | GTG-B Replace Main LO Pump (100068674) | Released | 2024-01-02 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 10617159 | 10617159 (MQ0032611-1635418-100-KIT,RETROFIT,L/O P) | 30 | 30 | 1 | 0 | 0 | PRPO-1000000219_00001 | PR approved; PO not issued | Direct to Remote (SP96) | PR due for release |  | 1000000219 | 1 |  |  |  | 2024-05-15 |  |  |  | IP REVIEW 14.03: Not Delivered Yet ETA 01.05 B513592043 Solar Turbines | N | Preparation (05) | In Preparation (Order) (0055) | Mech - GTG-B Replace Main LO Pump (0010) | Turbine Driven Generator Pkg B (DU50.MA.UEP.10.PG004) | 0000208952 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 | 2024-05-13 |  | 2024-05-25 | [5 empty] | 2024-08-13 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 2 | 0 | 0 | 0 |  |  | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | MQ0032611-1635418-100-KIT,RETROFIT,L/O P | [5 empty] | 0010 | INT | Mech - GTG-B Replace Main LO Pump | 5 |  |  |  |  | 60 | 0 |  | 0 |  | Release Completed (05) | X |  |  | 0 |  |  | 5 | DU50 |  | 2024-03-09 |  | 1 | EA | 2024-05-15 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000208367 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-05-25 | 2024-05-25 | 2024-05-25 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material shortage | Reactive Maintenance (AM01)
No Stock at Base | 4500008632/00010 - Due Date 45392 | No Req or Processed |  | 04.04 Not Delivered Yet ETA 10.04 |  | DU50 | 100074643 | MO-025-L-601 Replace fire hose nozzle (100074643) | Released | 2024-03-22 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 70004707 | 70004707 (Nozzle Branch 65mm BIC brass with rubber) | 20 | 20 | 1 | 0 | 0 | POPO-4500008632_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300008212 | 1000006570 | 2 | 4500008632 | WORMALD AUSTRALIA PTY LTD (30000072) | 2024-04-10 | 2024-06-06 | AUS Operations (106) |  | DU01 | IP REVIEW 27.03: SOH at DU01 del 80003434 17.04 | N | Preparation (05) | In Preparation (Order) (0055) | MO-025-L-601 Replace fire hose nozzle (0010) | Safety Systems Fire Water (DU50.MA.UFP.20.SF001) | 0000226676 | 2 |  |  | 0010 | 1130 |  | 2024-03-22 | 10 | 0 | 0 | 19 | 2024-05-15 | 2024-05-04 | 2024-05-26 |  |  | 2024-05-18 |  |  | 2024-09-07 | 0 |  |  | 2024-04-29 | 2024-05-06 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-04-29 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Nozzle Branch 65mm BIC brass with rubber | 2024-04-29 |  |  |  |  | 0010 | INT | MO-025-L-601 Replace fire hose nozzle | [5 empty] | 14 | 14 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-04-23 |  | 1 | EA | 2024-05-18 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000224087 | S001 |  |  |  | 5300008212 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-04-29 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-15 | 226676 | 0 | HSE |  | 1 |  |  | CC11874501 |  | 2024-05-26 | 2024-05-26 | 2024-05-26 | Settlement rule created/Pre-costed/Order Approved/Material shortage/Released/Object created | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 1001 x4 2001 x2 |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 | 11358241 | 11358241 (HOSE ASSY,FLEX,1.5IN ID,SOLATURB 1046489) | 20 | 20 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | AT MAC | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | 00000127000000000012 |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | HOSE ASSY,FLEX,1.5IN ID,SOLATURB 1046489 | [5 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01) |  | 10-07-03-02A
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 11 |  |  | 0110 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 12 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 10 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 12 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 9 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 8 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 7 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 6 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100069554 | GTG-A Replace Package FHAs (100069554) | Released | 2024-01-01 | 2024-05-27 | 2024-05-27 | 2024-05-28 |  |  | 20 | 20 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace GTG-A Package FHAs D1 (0020) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000209852 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-27 | [5 empty] | 2024-05-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | Replace GTG-A Package FHAs D1 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209227 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Estimated costs/Material committed | Reactive Maintenance (AM01)
Remote Pick - Low Stock | 4500008679/00010 - Due Date 45418 | - |  | 03.04 - SOH at DU01 - monitor STO 5200004435 01.05 del date |  | DU50 | 200126545 | 6M Mech Insp 510-U-502A (200126545) | Released | 2024-01-02 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 10504687 | 10504687 (FILTER ELEMENT,AIR,COMPAIR 100006374) | 20 | 20 | 1 | 0 | 3 |  |  | Stock at Base and Remote (SP11) |  |  |  | 0 | [6 empty] | DU01 | SOH at DU01 - STO 5200004435 | N | Preparation (05) | In Preparation (Order) (0055) | Inspect Air Compressor Minor (0010) | Compressed Air Unit A (DU50.MA.UCA.10.CM001) | 0000201328 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-28 | [5 empty] | 2024-05-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,AIR,COMPAIR 100006374 | [5 empty] | 0010 | INT | Inspect Air Compressor Minor | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200723 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | Released/Settlement rule created/Pre-costed/Object created/Material shortage/Estimated costs | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500008679/00010 - Due Date 45418 | - |  | 03.04 - SOH at DU01 - monitor STO 5200004435 01.05 del date |  | DU50 | 200126546 | 6M Mech Insp 510-U-502B (200126546) | Released | 2024-01-02 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 10504687 | 10504687 (FILTER ELEMENT,AIR,COMPAIR 100006374) | 20 | 20 | 1 | 0 | 3 |  |  | Stock at Base and Remote (SP11) |  |  |  | 0 | [6 empty] | DU01 | SOH at DU01 - STO 5200004435 | N | Preparation (05) | In Preparation (Order) (0055) | Inspect Air Compressor Minor (0010) | Compressed Air Unit B (DU50.MA.UCA.10.CM002) | 0000201329 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-28 | [5 empty] | 2024-05-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,AIR,COMPAIR 100006374 | [5 empty] | 0010 | INT | Inspect Air Compressor Minor | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200724 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500008679/00010 - Due Date 45418 | - |  | 03.04 - SOH at DU01 - monitor STO 5200004435 01.05 del date |  | DU50 | 200126547 | 6M Mech Insp 510-U-502C (200126547) | Released | 2024-01-02 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 10504687 | 10504687 (FILTER ELEMENT,AIR,COMPAIR 100006374) | 20 | 20 | 1 | 0 | 3 |  |  | Stock at Base and Remote (SP11) |  |  |  | 0 | [6 empty] | DU01 | SOH at DU01 - STO 5200004435 | N | Preparation (05) | In Preparation (Order) (0055) | Inspect Air Compressor Minor (0010) | Compressed Air Unit C (DU50.MA.UCA.10.CM003) | 0000201330 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-28 | [5 empty] | 2024-05-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,AIR,COMPAIR 100006374 | [5 empty] | 0010 | INT | Inspect Air Compressor Minor | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200725 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | Settlement rule created/Pre-costed/Object created/Estimated costs/Material shortage/Released | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126545 | 6M Mech Insp 510-U-502A (200126545) | Released | 2024-01-02 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 10283437 | 10283437 (FILTER,CART,OIL,COMPAIR A04425274) | 20 | 20 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Inspect Air Compressor Minor (0010) | Compressed Air Unit A (DU50.MA.UCA.10.CM001) | 0000201328 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-28 | [5 empty] | 2024-05-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER,CART,OIL,COMPAIR A04425274 | [5 empty] | 0010 | INT | Inspect Air Compressor Minor |  |  |  |  | 10-03-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200723 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | Released/Settlement rule created/Pre-costed/Object created/Material shortage/Estimated costs | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126546 | 6M Mech Insp 510-U-502B (200126546) | Released | 2024-01-02 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 10283437 | 10283437 (FILTER,CART,OIL,COMPAIR A04425274) | 20 | 20 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Inspect Air Compressor Minor (0010) | Compressed Air Unit B (DU50.MA.UCA.10.CM002) | 0000201329 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-28 | [5 empty] | 2024-05-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER,CART,OIL,COMPAIR A04425274 | [5 empty] | 0010 | INT | Inspect Air Compressor Minor |  |  |  |  | 10-03-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200724 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126547 | 6M Mech Insp 510-U-502C (200126547) | Released | 2024-01-02 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 10283437 | 10283437 (FILTER,CART,OIL,COMPAIR A04425274) | 20 | 20 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Inspect Air Compressor Minor (0010) | Compressed Air Unit C (DU50.MA.UCA.10.CM003) | 0000201330 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-28 | [5 empty] | 2024-05-28 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER,CART,OIL,COMPAIR A04425274 | [5 empty] | 0010 | INT | Inspect Air Compressor Minor |  |  |  |  | 10-03-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200725 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | Settlement rule created/Pre-costed/Object created/Estimated costs/Material shortage/Released | Proactive Maintenance (AM02)
Stock Available at Base | - | - |  | 03.04 - SOH at DU01 - monitor Del 90002756 13.05 del date |  | DU50 | 100074733 | Replace level indicator (100074733) | Released | 2024-03-18 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 70001096 | 70001096 (GAGE,LEVEL,FLOAT) | 99 | 255 | 1 | 0 | 1 | POPO-4500007337_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Vendor del date will not meet planned Work-packing | 5300008019 | 1000005918 | 2 | 4500007337 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-01 | 2024-07-20 | AUS Operations (106) |  | DU01 | IP REVIEW 19.03: Not delivered Yet | N | Preparation (05) | In Preparation (Order) (0055) | Replace level indicator (0010) | TURBINE DRIVEN GENERATOR PKG D 630-U-901 (DU50.UEP.MO-630-U-901) | 0000227433 | 2 |  |  | 0010 | 1130 |  | 2024-03-18 | 10 | 0 | 0 | 30 | 2024-06-17 | 2024-05-27 | 2024-05-29 |  |  | 2024-06-20 |  |  | 2026-02-18 | 0 |  |  | 2024-05-21 | 2024-05-29 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | EXW | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-05-21 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GAGE,LEVEL,FLOAT | 2024-05-21 |  |  |  |  | 0010 | INT | Replace level indicator | [5 empty] | 84 | 84 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-03-18 |  | 1 | EA | 2024-06-20 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000224459 | S001 |  |  |  | 5300008019 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-05-21 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | WA0GRY | 2024-03-18 | 227433 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | Order Approved/Material shortage/Settlement rule created/Object created/Pre-costed/Released | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200132897 | 5Y Cft MO-PSV-33067A (200132897) | Released | 2024-01-01 | 2024-05-31 | 2024-05-31 | 2024-07-26 | 11175225 | 11175225 (VALVE,SAFETY,25*D*50,CONVENTIONAL,DIRECT) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Silica Bed Coalescer Regen Gas A (DU50.MA.GCD.10.VP004) | 0000207740 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-31 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,25*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207155 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-07-26 | 2024-05-31 | 2024-05-31 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
No Stock at Base | No PO | No Req or Processed |  | 03.04 - ETA 05.04 Callidus Karratha PO B513595638 |  | DU50 | 200132897 | 5Y Cft MO-PSV-33067A (200132897) | Released | 2024-01-01 | 2024-05-31 | 2024-05-31 | 2024-07-26 | 11175225 | 11175225 (VALVE,SAFETY,25*D*50,CONVENTIONAL,DIRECT) | 20 | 20 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | NEW |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Vessel Silica Bed Coalescer Regen Gas A (DU50.MA.GCD.10.VP004) | 0000207740 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-05-31 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,25*D*50,CONVENTIONAL,DIRECT | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000207155 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-07-26 | 2024-05-31 | 2024-05-31 | Settlement rule created/Pre-costed/Object created/Material shortage/Released/Estimated costs | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | AT MAC 27.03 |  | DU50 | 200133946 | 4Y CERT PSV (200133946) | Released | 2024-01-19 | 2024-06-05 | 2024-06-05 | 2024-07-31 | 11175245 | 11175245 (VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35) | 5 | 10 | 1 | 1 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | AT MAC 27.03 | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | PSV SALES GAS SUCT SCRB PSV-34207 (DU50.GSG.MO-PSV-34207) | 0000214633 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-05 | [5 empty] | 2024-06-05 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,80*J*100,PILOT OPER,CS SA35 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  | 10-03-06-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000213070 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | IP1020240119 | 2024-01-19 | 0 | 0 | OPS |  | 4 | W01 |  | CC11874501 |  | 2024-07-31 | 2024-06-05 | 2024-06-05 | Settlement rule created/Pre-costed/Object created/Material committed/Released | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200133947 | 4Y CERT PSV (200133947) | Released | 2024-01-19 | 2024-06-05 | 2024-06-05 | 2024-07-31 | 11175200 | 11175200 (VALVE,SAFETY,100*L*150,PILOT OPER,CS SA3) | 5 | 10 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | PSV SALES GAS CMPR PROTECTION PSV-34209 (DU50.GSG.MO-PSV-34209) | 0000214634 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-05 | [5 empty] | 2024-06-05 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,100*L*150,PILOT OPER,CS SA3 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  | 10-03-06-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000213071 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | IP1020240119 | 2024-01-19 | 0 | 0 | OPS |  | 4 | W01 |  | CC11874501 |  | 2024-07-31 | 2024-06-05 | 2024-06-05 | Released/Settlement rule created/Pre-costed/Object created/Material committed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200127139 | 4Y Cft MO-PSV-37016 GRC (200127139) | Released | 2024-01-02 | 2024-06-09 | 2024-06-09 | 2024-08-04 | 11175266 | 11175266 (VALVE,SAFETY,150*Q*200,PILOT OPER,CS SA2) | 5 | 10 | 1 | 1 | 0 |  |  | Stock at Base and Remote (SP11) |  |  |  | 0 | [5 empty] | NEW | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | PSV 370V301 H/OIL EXPANSION PSV-37016 (DU50.UHT.MO-PSV-37016) | 0000201982 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-09 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,150*Q*200,PILOT OPER,CS SA2 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  | 10-03-05-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000201337 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-08-04 | 2024-06-09 | 2024-06-09 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200127139 | 4Y Cft MO-PSV-37016 GRC (200127139) | Released | 2024-01-02 | 2024-06-09 | 2024-06-09 | 2024-08-04 | 11175266 | 11175266 (VALVE,SAFETY,150*Q*200,PILOT OPER,CS SA2) | 5 | 10 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | PSV 370V301 H/OIL EXPANSION PSV-37016 (DU50.UHT.MO-PSV-37016) | 0000201982 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-09 | [5 empty] | 2024-08-04 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,150*Q*200,PILOT OPER,CS SA2 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000201337 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-08-04 | 2024-06-09 | 2024-06-09 | Released/Settlement rule created/Pre-costed/Estimated costs/Material shortage/Object created | Proactive Maintenance (AM02)
No Stock at Base | 4500006461/00010 - Due Date 45509 | No Req or Processed |  | WM TO ACTION 03.04: Reschedule ETA 05.08 |  | DU50 | 100068291 | Replace magnetic level indicator LG39022 (100068291) | Released | 2024-03-11 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 70001148 | 70001148 (Orion Level + Flag Indicator) | 30 | 30 | 1 | 0 | 0 | POPO-4500006461_00010 | Vendor PO raised | Directs (Inventory) (SP14) | Planned delivery after Reqmt Date | 5300007739 | 1000005018 | 3 | 4500006461 | HINCO INSTRUMENTS HINCO GROUP PTY LTD (30000235) | 2024-08-05 | 2024-10-16 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not Delivered Yet - On track | N | Preparation (05) | In Preparation (Order) (0055) | Replace magnetic level indicator LG39022 (0010) | Corrosion Inhibitor (DU50.MA.NCI.05) | 0000208589 | 3 |  |  | 0010 | 1130 |  | 2024-03-11 | 10 | 0 | 0 | 69 | 2024-08-05 | 2024-06-08 | 2024-06-10 |  |  | 2024-08-08 |  |  | 2024-06-12 | 0 |  |  | 2024-05-31 | 2024-06-10 | Mac Store |  | 0 | 2 | 3 | 0 | 0 | 0 |  |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink | 2024-05-31 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | Orion Level + Flag Indicator | 2024-05-31 |  |  |  |  | 0010 | INT | Replace magnetic level indicator LG39022 | [5 empty] | 140 | 140 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 |  | 2024-03-11 |  | 1 | EA | 2024-08-08 | 3 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207984 | S001 |  |  |  | 5300007739 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-05-31 | Mac Store |  |  |  |  | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208589 | 0 | OPS |  | 1 |  |  | CC11874501 |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | Order Approved/Released/Material shortage/Settlement rule created/Pre-costed/Object created | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 x16 1001 and 5001 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504497 | 10504497 (O-RING,DRESRAND 002272151) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 18 |  |  | 0180 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002272151 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 x7 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10507280 | 10507280 (O-RING,2.612IN ID,SAE 146) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 19 |  |  | 0190 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,2.612IN ID,SAE 146 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504517 | 10504517 (O-RING,BU,3.01IN ID,SOLATURB 1056982) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 20 |  |  | 0200 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,BU,3.01IN ID,SOLATURB 1056982 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504550 | 10504550 (SEAL,MECH,5.687IN,DRY GAS,CRANE 89746807) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | NEW |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 32 |  |  | 0320 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL,MECH,5.687IN,DRY GAS,CRANE 89746807 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 - 5001 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504549 | 10504549 (SEAL,MECH,5.687IN,DRY GAS,CRANE 89746806) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | NEW |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 31 |  |  | 0310 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL,MECH,5.687IN,DRY GAS,CRANE 89746806 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | ATN PURCHASING 18.03: Uplift PO ETA 23.05 B513592778 John Crane | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 11053284 | 11053284 (SEAL,SEPARATION,CRANE 89429470) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | NEW |  | IP REVIEW 18.03: ETA 23.05 B513592778 John Crane ATN PURCHASING: Uplift PO | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 25 |  |  | 0250 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL,SEPARATION,CRANE 89429470 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596555/00030 - Due Date | No Req or Processed |  | 03.04 - ATN purchasing has this been expedited? ETA was 16.02 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10273946 | 10273946 (O-RING,DRESRAND 002272219) | 5 | 10 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 7 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002272219 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596555/00040 - Due Date | No Req or Processed |  | 03.04 - ATN purchasing has this been expedited? ETA was 16.02 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10273947 | 10273947 (O-RING,DRESRAND 002272228) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 8 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002272228 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596555/00010 - Due Date | No Req or Processed |  | 03.04 - ATN purchasing has this been expedited? ETA was 16.02 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504496 | 10504496 (O-RING,DRESRAND 002272149) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 9 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002272149 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596555/00060 - Due Date | No Req or Processed |  | 03.04 - ATN purchasing has this been expedited? ETA was 16.02 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504504 | 10504504 (O-RING,DRESRAND 002285273) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 12 |  |  | 0120 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002285273 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596555/00020 - Due Date | No Req or Processed |  | 03.04 - ATN purchasing has this been expedited? ETA was 16.02 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504509 | 10504509 (O-RING,DRESRAND 002272214) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 14 |  |  | 0140 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002272214 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513596555/00050 - Due Date | No Req or Processed |  | 03.04 - ATN purchasing has this been expedited? ETA was 16.02 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504510 | 10504510 (O-RING,DRESRAND 002276256) | 5 | 10 | 4 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 15 |  |  | 0150 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002276256 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | B513597129/00010 - Due Date 45300 | No Req or Processed |  | 03.04 - ATN purchasing has this been expedited? ETA was 09.01 Solar Turbines | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504560 | 10504560 (GASKET,NON-MTL,SOLATURB 11006491) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 16 |  |  | 0160 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,NON-MTL,SOLATURB 11006491 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504550 | 10504550 (SEAL,MECH,5.687IN,DRY GAS,CRANE 89746807) | 5 | 10 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 35 |  |  | 0321 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | SEAL,MECH,5.687IN,DRY GAS,CRANE 89746807 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504549 | 10504549 (SEAL,MECH,5.687IN,DRY GAS,CRANE 89746806) | 5 | 10 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 34 |  |  | 0311 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | SEAL,MECH,5.687IN,DRY GAS,CRANE 89746806 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 11053284 | 11053284 (SEAL,SEPARATION,CRANE 89429470) | 5 | 10 | -2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 33 |  |  | 0251 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | SEAL,SEPARATION,CRANE 89429470 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 1001 x8 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10229182 | 10229182 (SEAL,SOLATURB 000049374) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 30 |  |  | 0300 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL,SOLATURB 000049374 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 1001 x1 5001 x1 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504766 | 10504766 (VALVE,SOL,0.25IN,SOLATURB 604876C1) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 29 |  |  | 0290 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SOL,0.25IN,SOLATURB 604876C1 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 2001 x2 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10231413 | 10231413 (O-RING,VITON,SOLATURB 952876C1) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 28 |  |  | 0280 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | 00000127000000000040 |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,VITON,SOLATURB 952876C1 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01) |  | 10-07-02-02B
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 1001 x1 5001 x1 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504516 | 10504516 (O-RING,BU,VITON,SOLATURB 1056596) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 21 |  |  | 0210 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,BU,VITON,SOLATURB 1056596 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  | AT MAC - SOH at DU50 1001 x4 5001 x1 | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504498 | 10504498 (O-RING,DRESRAND 002272146) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 27 |  |  | 0270 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002272146 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504908 | 10504908 (RING,BU,DRESRAND 423749048) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 26 |  |  | 0260 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | RING,BU,DRESRAND 423749048 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | PDC - MAC NG (DU01)2000015936 / 00010 - Due Date 13/04/2024 |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10274029 | 10274029 (COMPOUND,DRESRAND 099010023) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 24 |  |  | 0240 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | COMPOUND,DRESRAND 099010023 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10005488 | 10005488 (GASKET COMPOUND,LOCTITE 515,FLEX,FLANGE) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 23 |  |  | 0230 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET COMPOUND,LOCTITE 515,FLEX,FLANGE | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10015055 | 10015055 (GASKET,SPW,CRIR,CL 150,25MM NB,SS316 INN) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 22 |  |  | 0220 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 150,25MM NB,SS316 INN | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504908 | 10504908 (RING,BU,DRESRAND 423749048) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | RING,BU,DRESRAND 423749048 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10015043 | 10015043 (GASKET,SPW,CRIR,CL 150,50MM NB,SS316 INN) | 5 | 10 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 150,50MM NB,SS316 INN | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10015046 | 10015046 (GASKET,SPW,CRIR,CL 150,80MM NB,SS316 INN) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 150,80MM NB,SS316 INN | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10015054 | 10015054 (GASKET,SPW,CRIR,CL 150,20MM NB,SS316 INN) | 5 | 10 | 5 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 150,20MM NB,SS316 INN | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 5 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10015057 | 10015057 (GASKET,SPIRAL,CRIR,CL 150,40MM NB,SS316) | 5 | 10 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPIRAL,CRIR,CL 150,40MM NB,SS316 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10261962 | 10261962 (GASKET,RING TYPE JOINT,R16,50.8MM ID,7.9) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 6 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,RING TYPE JOINT,R16,50.8MM ID,7.9 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504499 | 10504499 (O-RING,DRESRAND 002272254) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 10 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002272254 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504500 | 10504500 (O-RING,DRESRAND 002272225) | 5 | 10 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 11 |  |  | 0110 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,DRESRAND 002272225 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10504508 | 10504508 (O-RING,CORDAGE,DRESRAND 090094002) | 5 | 10 | 2 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 13 |  |  | 0130 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,CORDAGE,DRESRAND 090094002 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
No Stock at Base | No PO | No Req or Processed |  |  | 24MCSGBS | DU50 | 100067883 | SGC-B DE Sep Gas Seal Issue (100067883) | Released | 2024-01-01 | 2024-06-11 | 2024-06-10 | 2024-07-19 | 10844283 | 10844283 (SEAL,ROTASOLU 000129489) | 5 | 10 | 8 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Assist RS seal change D1 (0060) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000208141 | 17 |  |  | 0170 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-07-31 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL,ROTASOLU 000129489 | [5 empty] | 0060 | INT | Assist RS seal change D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 8 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207416 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCSGBS | 2024-07-19 | 2024-06-10 | 2024-06-10 | Material shortage/Estimated costs/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Refurb Return | - | - |  | UserCommentLink |  | DU50 | 200129146 | 4Y Cft MO-PSV-37015 (200129146) | Released | 2024-01-02 | 2024-06-11 | 2024-06-11 | 2024-08-06 | 11175260 | 11175260 (VALVE,SAFETY,25*E*50,PILOT OPER,CS SA216) | 20 | 20 | -1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [5 empty] | DAMAGED |  | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Filter Hot Oil Sidestream (DU50.MA.UHT.10.FR001) | 0000203929 | 2 |  |  | 0011 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-08-06 | 0 |  |  |  |  | Supply |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 4001 | VALVE,SAFETY,25*E*50,PILOT OPER,CS SA216 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203324 |  |  | 30 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Warehouse |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-08-06 | 2024-06-11 | 2024-06-11 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | No PO | - | 03.04 - RFQ 6000003038 with Callidus - ETA TBA |  |  | DU50 | 200129146 | 4Y Cft MO-PSV-37015 (200129146) | Released | 2024-01-02 | 2024-06-11 | 2024-06-11 | 2024-08-06 | 11175260 | 11175260 (VALVE,SAFETY,25*E*50,PILOT OPER,CS SA216) | 20 | 20 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [5 empty] | NEW | DU01 | ATN PURCHASING 13.03: PR to PO 1000005381 New buy | N | Preparation (05) | In Preparation (Order) (0055) | Replace Pressure Relief Device (0010) | Filter Hot Oil Sidestream (DU50.MA.UHT.10.FR001) | 0000203929 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-11 | [5 empty] | 2024-08-06 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | VALVE,SAFETY,25*E*50,PILOT OPER,CS SA216 | [5 empty] | 0010 | INT | Replace Pressure Relief Device | 6 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000203324 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-08-06 | 2024-06-11 | 2024-06-11 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10228388 | 10228388 (FILTER ELEMENT,AIR,SOLATURB 10874913) | 20 | 20 | 1 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 33 |  |  | 0330 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,AIR,SOLATURB 10874913 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-01-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10228884 | 10228884 (KIT,ELEMENT,FILT,SOLATURB 16891251) | 20 | 20 | 1 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 32 |  |  | 0320 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | KIT,ELEMENT,FILT,SOLATURB 16891251 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 10-03-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10371643 | 10371643 (PARTS KIT,VLV,SOLATURB 997396C1) | 20 | 20 | 2 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 31 |  |  | 0310 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | PARTS KIT,VLV,SOLATURB 997396C1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-01-04A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10231008 | 10231008 (GASKET,GRAFOIL,SOLATURB 1368451) | 20 | 20 | 2 | 14 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 30 |  |  | 0300 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,GRAFOIL,SOLATURB 1368451 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-01-04A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10231209 | 10231209 (GASKET,3/8IN ID,MTL) | 20 | 20 | 1 | 7 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 29 |  |  | 0290 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,3/8IN ID,MTL | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-01-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10239252 | 10239252 (O-RING,VITON,SOLATURB 102661420) | 20 | 20 | 1 | 5 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 28 |  |  | 0280 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,VITON,SOLATURB 102661420 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-01-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10248256 | 10248256 (O-RING,3-1/2IN ID,1/8IN,VITON,SAE 235,BL) | 20 | 20 | 1 | 10 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 27 |  |  | 0270 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,3-1/2IN ID,1/8IN,VITON,SAE 235,BL | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-03-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10249534 | 10249534 (GASKET,1.79IN ID,SOLATURB 1737411) | 20 | 20 | 2 | 18 | 3 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 26 |  |  | 0260 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,1.79IN ID,SOLATURB 1737411 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-02-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10250413 | 10250413 (SEAL,LIP,SOLATURB 3005731) | 20 | 20 | 4 | 15 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 25 |  |  | 0250 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL,LIP,SOLATURB 3005731 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-03-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10250423 | 10250423 (SEAL,CB,SOLATURB 447891) | 20 | 20 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 24 |  |  | 0240 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SEAL,CB,SOLATURB 447891 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-03-06A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10281327 | 10281327 (O-RING,VITON,SAE 146,SOLATURB 999949C1) | 20 | 20 | 1 | 2 | 4 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 23 |  |  | 0230 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,VITON,SAE 146,SOLATURB 999949C1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-01-06A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 41 | 41 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10507498 | 10507498 (FILTER ELEMENT,GAS FUEL,SIMPLEX,CYLDC) | 20 | 20 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 22 |  |  | 0220 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,GAS FUEL,SIMPLEX,CYLDC | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 10-03-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 11041999 | 11041999 (O-RING,BUNA-N,SAE 143,SOLATURB 1094051) | 20 | 20 | 1 | 11 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 21 |  |  | 0210 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,BUNA-N,SAE 143,SOLATURB 1094051 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-03-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 11079030 | 11079030 (FILTER ELEMENT,H2O,SOLATURB 602205C1) | 20 | 20 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 20 |  |  | 0200 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,H2O,SOLATURB 602205C1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-01-09A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | No PO | - | 03.04 - New PR required for balance (only QTY 3 ay DU50) | PR to PO |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10509341 | 10509341 (FILTER ELEMENT,SPIDER WEB XP,324MM RD X) | 20 | 20 | 9 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 18 |  |  | 0180 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,SPIDER WEB XP,324MM RD X | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 10-02-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 9 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10144284 | 10144284 (BATTERY,SERIES B,AB 1756BA2) | 20 | 20 | 1 | 5 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 17 |  |  | 0170 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BATTERY,SERIES B,AB 1756BA2 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-02-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10507280 | 10507280 (O-RING,2.612IN ID,SAE 146) | 20 | 20 | 2 | 7 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 16 |  |  | 0160 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,2.612IN ID,SAE 146 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-04-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10015053 | 10015053 (GASKET,SPW,CRIR,CL 150,15MM NB,SS316 INN) | 20 | 20 | 1 | 7 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 15 |  |  | 0150 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 150,15MM NB,SS316 INN | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 10-05-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10015055 | 10015055 (GASKET,SPW,CRIR,CL 150,25MM NB,SS316 INN) | 20 | 20 | 2 | 29 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 14 |  |  | 0140 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 150,25MM NB,SS316 INN | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 10-05-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10898330 | 10898330 (DISC,SAFETY,SOLATURB 999887C1) | 20 | 20 | 2 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 13 |  |  | 0130 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DISC,SAFETY,SOLATURB 999887C1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-03-08A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 11365784 | 11365784 (DECONTAMINATING AGENT,DECON A,LIQUID,COL) | 20 | 20 | 1 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 12 |  |  | 0120 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DECONTAMINATING AGENT,DECON A,LIQUID,COL | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 21-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10211074 | 10211074 (BOLT,0.5IN-13,1.75IN LG,GDE 5,HEX) | 20 | 20 | 4 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 11 |  |  | 0110 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BOLT,0.5IN-13,1.75IN LG,GDE 5,HEX | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-02-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10240681 | 10240681 (WASHER,LOCK,SPLIT,0.5IN ID,STL,ZP,PK/25) | 20 | 20 | 4 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 10 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WASHER,LOCK,SPLIT,0.5IN ID,STL,ZP,PK/25 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-02-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10248659 | 10248659 (WASHER,FLAT,0.5IN,1.062IN OD,STL,ZP,HARD) | 20 | 20 | 4 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 9 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WASHER,FLAT,0.5IN,1.062IN OD,STL,ZP,HARD | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-02-11A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10249525 | 10249525 (GASKET,4.65IN SQUARE,SOLATURB 1725111) | 20 | 20 | 1 | 10 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 8 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,4.65IN SQUARE,SOLATURB 1725111 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-02-07A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10248101 | 10248101 (WASHER,EB,SOLATURB 905271C1) | 20 | 20 | 1 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 7 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | WASHER,EB,SOLATURB 905271C1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-03-04A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10231205 | 10231205 (O-RING,VITON V75,MIL-R-83248,SAE 173,TYP) | 20 | 20 | 1 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 5 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,VITON V75,MIL-R-83248,SAE 173,TYP | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-03-06A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10229481 | 10229481 (ACTUATOR,LINEAR,PNEU,SOLATURB 70301081) | 20 | 20 | 2 | 2 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 4 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ACTUATOR,LINEAR,PNEU,SOLATURB 70301081 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-02-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10504629 | 10504629 (GASKET,SPW,SS304,SOLATURB 10691442) | 20 | 20 | 2 | 4 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 3 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,SS304,SOLATURB 10691442 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 10-05-02-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10191045 | 10191045 (GASKET,0.77IN ID,MTL,SOLATURB 903315C1) | 20 | 20 | 1 | 56 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,0.77IN ID,MTL,SOLATURB 903315C1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-01-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10265242 | 10265242 (LOCKWASHER,SPLIT,SOLATURB 623083R1) | 20 | 20 | 6 | 44 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | LOCKWASHER,SPLIT,SOLATURB 623083R1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-02-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 6 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10212109 | 10212109 (O-RING,VITON,SAE 219) | 20 | 20 | 1 | 18 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 34 |  |  | 0340 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,VITON,SAE 219 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-04-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10189853 | 10189853 (IGNITER,SPARK,GAS TURB,PLUG,TORCH,IRIDIU) | 20 | 20 | 1 | 8 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 35 |  |  | 0350 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | IGNITER,SPARK,GAS TURB,PLUG,TORCH,IRIDIU | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-01-05A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10185741 | 10185741 (DETERGENT,GP,CLEANER,CORROSION INHIBITOR) | 20 | 20 | 1 | 3 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 36 |  |  | 0360 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DETERGENT,GP,CLEANER,CORROSION INHIBITOR | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 21-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10248401 | 10248401 (BOLT,0.312IN-18,0.75IN LG,B7,HEX) | 20 | 20 | 2 | 48 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 37 |  |  | 0370 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | BOLT,0.312IN-18,0.75IN LG,B7,HEX | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-01-01-01A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 2 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 11041998 | 11041998 (SCREW,HEX SKT,SOLATURB 970256C1) | 20 | 20 | 4 | 11 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 38 |  |  | 0380 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | SCREW,HEX SKT,SOLATURB 970256C1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  | 11-03-02-10A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500007088/00020 - Due Date 45426 | - |  | IP REVIEW 20.03: Not Delivered Yet ETA 14.05 4500007088 Solar Turbines |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10248102 | 10248102 (LOCKPLATE,SOLATURB 905272C1) | 20 | 20 | 1 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | IP REVIEW 20.03: Not Delivered Yet ETA 14.05 4500007088 Solar Turbines | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 6 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | LOCKPLATE,SOLATURB 905272C1 | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Pick - Low Stock | 4500001712/00030 - Due Date 45436 | - |  | IP REVIEW 13.03: Not Delivered Yet ETA 24.05 Solar T 4500001712 |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-16 | 2024-05-27 | 2024-07-17 | 10385132 | 10385132 (FILTER ELEMENT,SPIDER WEB XP,324MM DIA X) | 20 | 20 | 9 | 0 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | IP REVIEW 13.03: Not Delivered Yet ETA 24.05 Solar T 4500001712 | N | Preparation (05) | In Preparation (Order) (0055) | Mech Service Package D4 (0140) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 19 |  |  | 0190 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | FILTER ELEMENT,SPIDER WEB XP,324MM DIA X | [5 empty] | 0140 | INT | Mech Service Package D4 | 5 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 9 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002740 | SGCB Varnish Removal System (600002740) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCB Varnish Removal System D1 (0010) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000207483 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCB Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206847 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002740 | SGCB Varnish Removal System (600002740) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCB Varnish Removal System D1 (0010) | Sales Gas Comp B (DU50.MA.GSG.20.CM001) | 0000207483 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCB Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206847 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002741 | SGCC Varnish Removal System (600002741) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCC Varnish Removal System D1 (0010) | Sales Gas Comp C (DU50.MA.GSG.30.CM001) | 0000207484 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2025-01-11 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCC Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206848 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002741 | SGCC Varnish Removal System (600002741) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCC Varnish Removal System D1 (0010) | Sales Gas Comp C (DU50.MA.GSG.30.CM001) | 0000207484 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2025-01-11 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCC Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000206848 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCA Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCA Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 3 |  |  | 0150 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCA Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 4 |  |  | 0160 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCA Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 5 |  |  | 0170 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCA Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-16 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 1 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D1 (0010) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 6 |  |  | 0180 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-16 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | SGCA Varnish Removal System D1 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Service-PR required |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
No Stock at Base | 4500003481/00010 - Due Date 45442 | No Req or Processed |  | IP REVIEW 13.03: Not Delivered Yet |  | DU50 | 100067857 | EDG DP switch PDSH-62051 replacement (100067857) | Released | 2024-02-20 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 70002885 | 70002885 (DANFOSS PRESSURE SWITCH) | 30 | 30 | 1 | 0 | 0 | IDPO-/018001409 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | Vendor Not able to deliver in-full | 5300006877 | 1000002976 | 2 | 4500003481 | HINCO INSTRUMENTS HINCO GROUP PTY LTD (30000235) | 2024-05-30 | 2024-06-08 | AUS Operations (106) |  | DU01 | IP REVIEW 13.03: Not Delivered Yet - On track | N | Preparation (05) | In Preparation (Order) (0055) | EDG DP switch PDSH-62051 replacement (0010) | Emerg Diesel Driven Generator (DU50.MA.UEP.10.PG001) | 0000208112 | 2 |  |  | 0010 | 1130 |  | 2024-02-20 | 10 | 0 | 0 | 0 | 2024-06-05 | 2024-06-15 | 2024-06-17 |  |  | 2024-06-08 |  |  | 2024-06-30 | 0 |  |  | 2024-06-10 | 2024-06-17 |  |  | 0 | 2 | 3 | 0 | 0 | 0 | /180014097 |  | 0 | CPT | 1 | L |  | 0 |  |  | 0 |  | /018001409 |  | 90002765 | WorkPackLink | 2024-06-10 |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | DANFOSS PRESSURE SWITCH | 2024-06-10 |  |  |  |  | 0010 | INT | EDG DP switch PDSH-62051 replacement |  |  | 90002765_0010 |  |  | 98 | 98 |  | 1 |  | Release Completed (05) | X |  |  | 0 | AUS Operations (106) | AU00 | 5 | DU50 | 90002765 | 2024-02-21 |  | 1 | EA | 2024-06-08 | 2 | 0 |  | 0 |  |  | 0 | 0 |  | AU1153 | 1000207495 | S001 |  |  |  | 5300006877 | 10 |  |  | 0 | 1 | EA | 0 | 2001 | DU01 |  | 2024-06-10 | [5 empty] | 10 | AU00 |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 208112 | 0 | MECH |  | 1 |  |  | CC11874501 |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | Material shortage/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 20 |  |  | 0210 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 22 |  |  | 0230 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 21 |  |  | 0220 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 7 |  |  | 0030 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 11 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 19 |  |  | 0190 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 11 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 39 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 18 |  |  | 0140 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 39 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 21 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 17 |  |  | 0130 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 21 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 72 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 16 |  |  | 0120 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 72 | M |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 15 |  |  | 0110 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 6 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 14 |  |  | 0100 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 6 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 13 |  |  | 0090 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 6 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 12 |  |  | 0080 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 6 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 11 |  |  | 0070 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 10 |  |  | 0060 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Pre-costed/Object created/Material committed/Estimated costs/Released/Settlement rule created | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 15 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 9 |  |  | 0050 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 15 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
ECC6 Material | - | - |  | UserCommentLink | 24MCVRN | DU50 | 600002813 | SGCA Varnish Removal System (600002813) | Released | 2024-01-02 | 2024-06-17 | 2024-06-16 | 2024-06-19 |  |  | 30 | 30 | 3 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | SGCA Varnish Removal System D2 (0020) | Sales Gas Comp A (DU50.MA.GSG.10.CM001) | 0000207765 | 8 |  |  | 0040 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-17 | [5 empty] | 2024-06-16 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0020 | INT | SGCA Varnish Removal System D2 | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 3 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 | MN |  | 1000207128 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 | 24MCVRN | 2024-06-19 | 2024-06-16 | 2024-06-16 | Released/Settlement rule created/Pre-costed/Object created/Material committed/Estimated costs | Capital (AM06)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-18 | 2024-05-27 | 2024-07-17 | 11391404 | 11391404 (ELEMENT,DEPTH MEDIA,N15,HYDAC N15DM002) | 20 | 20 | 1 | 6 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Svce Pkg D6-Repl Vrnsh Rmv Skd Fltr (0210) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 40 |  |  | 0400 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-18 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | ELEMENT,DEPTH MEDIA,N15,HYDAC N15DM002 | [5 empty] | 0210 | INT | Mech Svce Pkg D6-Repl Vrnsh Rmv Skd Fltr | 5 |  |  |  | 10-05-01-02A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200126445 | 3Y Mech & Elec Svce GTG-A (200126445) | Released | 2024-01-02 | 2024-06-18 | 2024-05-27 | 2024-07-17 | 11391365 | 11391365 (O-RING,FILTER HOUSING SEAL,VARNISH REMOV) | 20 | 20 | 1 | 7 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech Svce Pkg D6-Repl Vrnsh Rmv Skd Fltr (0210) | Turbine Driven Generator Pkg A (DU50.MA.UEP.10.PG003) | 0000201208 | 39 |  |  | 0390 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-18 | [5 empty] | 2024-07-18 | 0 |  |  |  |  | Pyr Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | O-RING,FILTER HOUSING SEAL,VARNISH REMOV | [5 empty] | 0210 | INT | Mech Svce Pkg D6-Repl Vrnsh Rmv Skd Fltr | 5 |  |  |  | 11-03-01-09A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 1 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000200623 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Pyrenees Venture FPSO |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 4 |  |  | CC11874501 |  | 2024-07-17 | 2024-05-27 | 2024-05-27 | Released/Settlement rule created/Object created/Estimated costs/Material shortage/Pre-costed | Proactive Maintenance (AM02)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100070306 | @Nitrogen Package- Replace N2 Membranes (100070306) | Released | 2024-01-01 | 2024-06-19 | 2024-06-19 | 2024-06-20 |  |  | 30 | 30 | 8 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech -Isolate 1XN2 train&replace element (0010) | Nitrogen Generation Skid (DU50.MA.UIG.10.ME001) | 0000210555 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-19 | [5 empty] | 2024-07-25 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Mech -Isolate 1XN2 train&replace element | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 8 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209938 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-20 | 2024-06-19 | 2024-06-19 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
ECC6 Material | - | - |  | UserCommentLink |  | DU50 | 100070306 | @Nitrogen Package- Replace N2 Membranes (100070306) | Released | 2024-01-01 | 2024-06-19 | 2024-06-19 | 2024-06-20 |  |  | 30 | 30 | 4 | 0 | 0 |  |  |  | No Issue identified |  |  | 0 | [7 empty] | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Mech -Isolate 1XN2 train&replace element (0010) | Nitrogen Generation Skid (DU50.MA.UIG.10.ME001) | 0000210555 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-19 | [5 empty] | 2024-07-25 | 0 |  |  |  |  | MAC Store |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | [7 empty] | 0010 | INT | Mech -Isolate 1XN2 train&replace element | [5 empty] | 0 | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000209938 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  |  |  | Macedon Gas Plant Warehou |  |  |  |  | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | W73974 | 2023-12-30 | 0 | 0 | MECH |  | 3 |  |  | CC11874501 |  | 2024-06-20 | 2024-06-19 | 2024-06-19 | Estimated costs/Material committed/Order Approved/Object created/Pre-costed/Settlement rule created/Released | Reactive Maintenance (AM01)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200133945 | 1Y Mech Svce Flare Drum Pumps (200133945) | Released | 2024-01-19 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 10171618 | 10171618 (GASKET,SPW,TYPE CG/IR,CL 150,100MM NB,SS) | 20 | 20 | 4 | 25 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service 380-P-302A (0010) | Flares High Pressure (DU50.MA.VFL.10) | 0000214632 | 2 |  |  | 0020 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-25 | [5 empty] | 2024-06-25 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,TYPE CG/IR,CL 150,100MM NB,SS | [5 empty] | 0010 | INT | Service 380-P-302A |  |  |  |  | 10-05-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 4 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000213069 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | IP1020240119 | 2024-01-19 | 0 | 0 | OPS |  | 4 | W01 |  | CC11874501 |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | Released/Pre-costed/Object created/Material committed/Settlement rule created | Proactive Maintenance (AM02)
Remote Stock - Stock Available | - | - |  | UserCommentLink |  | DU50 | 200133945 | 1Y Mech Svce Flare Drum Pumps (200133945) | Released | 2024-01-19 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 10015055 | 10015055 (GASKET,SPW,CRIR,CL 150,25MM NB,SS316 INN) | 20 | 20 | 8 | 29 | 0 |  |  | Stock at Remote (SP13) |  |  |  | 0 | [6 empty] | DU01 | UserCommentLink | N | Preparation (05) | In Preparation (Order) (0055) | Service 380-P-302A (0010) | Flares High Pressure (DU50.MA.VFL.10) | 0000214632 | 1 |  |  | 0010 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2024-06-25 | [5 empty] | 2024-06-25 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 4 | L |  | 0 |  |  | 0 |  |  |  |  | WorkPackLink |  |  | Macedon - MAC NG (DU50) | Macedon - MAC NG (DU50) | 5001 | GASKET,SPW,CRIR,CL 150,25MM NB,SS316 INN | [5 empty] | 0010 | INT | Service 380-P-302A |  |  |  |  | 10-05-02-03A | 0 | 0 |  | 0 | [5 empty] | 0 |  |  |  | DU50 |  |  |  | 8 | EA |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 1000213069 |  |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 1270 | 0 |  |  | WE Global Pty Ltd (1130) | W001 | IP1020240119 | 2024-01-19 | 0 | 0 | OPS |  | 4 | W01 |  | CC11874501 |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | Released/Pre-costed/Object created/Material committed/Settlement rule created | Proactive Maintenance (AM02)
ECC6 Material | - | -
ECC6 Material | - | -
ECC6 Material | - | -
ECC6 Material | - | -
ECC6 Material | - | -
ECC6 Material | - | -
ECC6 Material | - | -
ECC6 Material | - | -
ECC6 Material | - | -
ECC6 Material | - | -

## PO
Purchase Order | Item | Material | Supplier | Next Delivery Date | Next Delivery Quantity | Order Quantity | Net Order Value | Quantity to be Delivered | Value to be Invoiced | Formula - No Delete or Edit
4500000229 | 00040 | Capacitor ¦ 8MFD ¦ 450V ¦ Mk450.8 (70000150) | OCEANIA ENGINEERING SERVICES PTY LTD (30000034) |  | 0 | 10 | 218 | 0 | 0 | 70000150) | 70000150 | 4500000229/00040 - Due Date
4500000396 | 00010 | HELIUM,TECH,336150,SIZE G CYL,GDE 5,99.9 (10509368) | COREGAS PTY LTD (30001686) |  | 0 | 7 | 3129.56 | 0 | 0 | 10509368) | 10509368 | 4500000396/00010 - Due Date
4500000674 | 00020 | UNION ELBOW 3/4" TUBE (70001004) | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) |  | 0 | 12 | 1747.8 | 0 | 1747.8 | 70001004) | 70001004 | 4500000674/00020 - Due Date
4500000674 | 00030 | 40 SERIES BALL VALVE 3/4" TUBE ENDS (70001005) | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) |  | 0 | 4 | 2386.4 | 0 | 2386.4 | 70001005) | 70001005 | 4500000674/00030 - Due Date
4500000674 | 00040 | 60 SERIES BALL VALVE 3/4" FNPT ENDS (70001006) | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) |  | 0 | 4 | 3615.2 | 0 | 3615.2 | 70001006) | 70001006 | 4500000674/00040 - Due Date
4500000674 | 00050 | HEX NIPPLE 3/4" MNPT (70001007) | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) |  | 0 | 4 | 198.8 | 0 | 198.8 | 70001007) | 70001007 | 4500000674/00050 - Due Date
4500000674 | 00060 | MALE CONNECTOR 3/4" TUBE x 3/4" NPT (70001008) | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) |  | 0 | 12 | 768.6 | 0 | 768.6 | 70001008) | 70001008 | 4500000674/00060 - Due Date
4500000674 | 00070 | UNION 3/4" TUBE (70001009) | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) |  | 0 | 20 | 1947 | 0 | 1947 | 70001009) | 70001009 | 4500000674/00070 - Due Date
4500000674 | 00080 | 3/4` CUSHIONED CLAMP TUBE SUPPORT (70001078) | SWAGELOK AUSTRALIA FLUID SYSTEM TECHNOLOGIES ES PL (30000241) |  | 0 | 20 | 241 | 0 | 241 | 70001078) | 70001078 | 4500000674/00080 - Due Date
4500000773 | 00010 | FLANGE-THRD 3"X1" NPT 600 RF/BLIND FLG D (70000879) | AUSTRALASIAN FITTINGS AND FLANGES (30000390) |  | 0 | 3 | 1788 | 0 | 0 | 70000879) | 70000879 | 4500000773/00010 - Due Date
4500000773 | 00020 | Additional Charges (70001020) | AUSTRALASIAN FITTINGS AND FLANGES (30000390) |  | 0 | 1 | 40 | 0 | 0 | 70001020) | 70001020 | 4500000773/00020 - Due Date
4500000905 | 00010 | KTEK LMT200 Magnetostrictive Transmitter (70001171) | PROCHEM PIPELINE PRODUCTS PTY LTD (30000271) | 2024-03-27 | 1 | 1 | 9740 | 1 | 9740 | 70001171) | 70001171 | 4500000905/00010 - Due Date 45378
4500000998 | 00010 | 15-20A Single phase test lead adapter (70001197) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 1 | 145 | 0 | 0 | 70001197) | 70001197 | 4500000998/00010 - Due Date
4500001105 | 00010 | Sqwincher Qwik Stiks Mixed Pack Pack of (70000305) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 10 | 420.9 | 0 | 420.9 | 70000305) | 70000305 | 4500001105/00010 - Due Date
4500001116 | 00010 | TAPE,SENSING,330FT LG,ENVEENGI 330133XS (10232273) | ANALYTICAL CONTROL PTY LTD (30000230) |  | 0 | 8 | 2120 | 0 | 0 | 10232273) | 10232273 | 4500001116/00010 - Due Date
4500001191 | 00010 | MAINTENANCE KIT,SERVICE,48 MONTH,RE-SET (11163196) | GARDNER DENVER INDUSTRIES PTY LTD (30000270) | 2024-04-01 | 1 | 1 | 4392.41 | 1 | 0 | 11163196) | 11163196 | 4500001191/00010 - Due Date 45383
4500001191 | 00020 | MAINTENANCE KIT,SERVICE,48 MONTH,RE-SET (11163196) | GARDNER DENVER INDUSTRIES PTY LTD (30000270) | 2024-04-01 | 1 | 1 | 4392.41 | 1 | 0 | 11163196) | 11163196 | 4500001191/00020 - Due Date 45383
4500001227 | 00010 | GAGE,LEVEL,FLOAT (70001096) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) |  | 0 | 1 | 251.66 | 0 | 0 | 70001096) | 70001096 | 4500001227/00010 - Due Date
4500001712 | 00010 | HOSE,MTL,FLEX,1-1/4N ID X 42-1/2IN LG (10243314) | SOLAR TURBINES INCORPORATED (30000090) | 2024-05-20 | 1 | 1 | 958.73 | 1 | 958.73 | 10243314) | 10243314 | 4500001712/00010 - Due Date 45432
4500001712 | 00020 | HOSE ASSY,FLEX,MTL,SOLATURB 945061C1 (10243340) | SOLAR TURBINES INCORPORATED (30000090) | 2024-04-29 | 1 | 1 | 876.26 | 1 | 876.26 | 10243340) | 10243340 | 4500001712/00020 - Due Date 45411
4500001712 | 00030 | FILTER ELEMENT,SPIDER WEB XP,324MM DIA X (10385132) | SOLAR TURBINES INCORPORATED (30000090) | 2024-05-24 | 9 | 9 | 1888.38 | 9 | 1888.38 | 10385132) | 10385132 | 4500001712/00030 - Due Date 45436
4500001712 | 00040 | FILTER ELEMENT,SPIDER WEB XP,324MM DIA X (10385132) | SOLAR TURBINES INCORPORATED (30000090) | 2024-06-21 | 12 | 12 | 2517.84 | 12 | 2517.84 | 10385132) | 10385132 | 4500001712/00040 - Due Date 45464
4500001712 | 00050 | DISC,SAFETY,SOLATURB 999887C1 (10898330) | SOLAR TURBINES INCORPORATED (30000090) | 2024-06-18 | 2 | 2 | 451.3 | 2 | 451.3 | 10898330) | 10898330 | 4500001712/00050 - Due Date 45461
4500001712 | 00060 | DISC,SAFETY,SOLATURB 999887C1 (10898330) | SOLAR TURBINES INCORPORATED (30000090) | 2024-06-21 | 2 | 2 | 451.3 | 2 | 451.3 | 10898330) | 10898330 | 4500001712/00060 - Due Date 45464
4500002032 | 00010 | DETECTOR,METHANE GAS,SOLATURB 107832527 (11311235) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) |  | 0 | 2 | 7629.16 | 0 | 0 | 11311235) | 11311235 | 4500002032/00010 - Due Date
4500002064 | 00010 | O-RING,3.109IN X 0.139IN,CRANE 87460999 (11092272) | JOHN CRANE AUSTRALIA PTY LTD (30000329) |  | 0 | 2 | 642.61 | 0 | 0 | 11092272) | 11092272 | 4500002064/00010 - Due Date
4500002064 | 00020 | O-RING,3.109IN X 0.139IN,CRANE 87460999 (11092272) | JOHN CRANE AUSTRALIA PTY LTD (30000329) |  | 0 | 2 | 642.61 | 0 | 0 | 11092272) | 11092272 | 4500002064/00020 - Due Date
4500002064 | 00030 | RING,BACK-UP,CRANE 87480284 (11093583) | JOHN CRANE AUSTRALIA PTY LTD (30000329) |  | 0 | 1 | 575.07 | 0 | 0 | 11093583) | 11093583 | 4500002064/00030 - Due Date
4500002064 | 00040 | O-RING,179.3MM X 5.7MM,CRANE 87461607 (11093552) | JOHN CRANE AUSTRALIA PTY LTD (30000329) | 2024-04-19 | 1 | 1 | 411.87 | 1 | 411.87 | 11093552) | 11093552 | 4500002064/00040 - Due Date 45401
4500002068 | 00020 | WATER BOTTLE,15L,BLKWOODS 01029558DS (11229501) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 32 | 329.28 | 0 | 0 | 11229501) | 11229501 | 4500002068/00020 - Due Date
4500002301 | 00010 | CMP, CABLE GLAND, 20'S (M20) T3CDS IP66 (70002200) | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 20 | 20 | 1256 | 20 | 1256 | 70002200) | 70002200 | 4500002301/00010 - Due Date 45396
4500002301 | 00020 | Band-IT KE0128 Type 316 SS 4.6x200mm (70002202) | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 5 | 5 | 494.35 | 5 | 494.35 | 70002202) | 70002202 | 4500002301/00020 - Due Date 45396
4500002301 | 00030 | CMP, ADAPTER, M25 MALE TO M20 FEMALE (70002203) | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 20 | 20 | 724 | 20 | 724 | 70002203) | 70002203 | 4500002301/00030 - Due Date 45396
4500002301 | 00040 | SEALING WASHER M20 X 2MM WHYITE NYLON (70002206) | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 20 | 20 | 42 | 20 | 42 | 70002206) | 70002206 | 4500002301/00040 - Due Date 45396
4500002301 | 00050 | CMP, IP WASHER, 25MM, WHITE NYLONG, 2MM (70002207) | SKN ELECTRICAL SERVICES LIMITED (30000497) | 2024-04-14 | 20 | 20 | 62 | 20 | 62 | 70002207) | 70002207 | 4500002301/00050 - Due Date 45396
4500002532 | 00010 | TAPE,SENSING,330FT LG,ENVEENGI 330133XS (10232273) | ANALYTICAL CONTROL PTY LTD (30000230) |  | 0 | 8 | 2120 | 0 | 0 | 10232273) | 10232273 | 4500002532/00010 - Due Date
4500002641 | 00010 | VALVE,DRAIN,1/2IN,16BAR,230V (11172514) | GARDNER DENVER INDUSTRIES PTY LTD (30000270) |  | 0 | 5 | 1691.5 | 0 | 0 | 11172514) | 11172514 | 4500002641/00010 - Due Date
4500002717 | 00010 | EMER LED PANEL 18W OPAL WHT 295X595IP20 (70002497) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 2 | 519.54 | 0 | 0 | 70002497) | 70002497 | 4500002717/00010 - Due Date
4500002717 | 00020 | EMER LED PANEL 30W OPAL WHT 295X1195IP20 (70002498) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 8 | 2309.12 | 0 | 0 | 70002498) | 70002498 | 4500002717/00020 - Due Date
4500002717 | 00030 | LED PANEL 18W 240V NON DIM OPAL WHT (70002499) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 18 | 1784.7 | 0 | 0 | 70002499) | 70002499 | 4500002717/00030 - Due Date
4500002717 | 00040 | LED PANEL 30W 240V NON DIM OPAL WHT (70002500) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 4 | 404.6 | 0 | 0 | 70002500) | 70002500 | 4500002717/00040 - Due Date
4500002717 | 00050 | LED PANEL LIGHT 30W 240V OPAL WHT (70002501) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 2 | 206.58 | 0 | 0 | 70002501) | 70002501 | 4500002717/00050 - Due Date
4500002717 | 00060 | SOCKET SURFACE RC 1G 10A 250V 3PIN 1P WH (70002502) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 30 | 134.1 | 0 | 0 | 70002502) | 70002502 | 4500002717/00060 - Due Date
4500002717 | 00070 | FLAT TWIN & EARTH 2C+E 7/0.5 1.5MM PVC W (70002503) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 1 | 245.1 | 0 | 0 | 70002503) | 70002503 | 4500002717/00070 - Due Date
4500002741 | 00010 | J Burrows A4 Premium Copy Paper 80gsm Wh (70002463) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 5 | 210.85 | 0 | 0 | 70002463) | 70002463 | 4500002741/00010 - Due Date
4500002741 | 00030 | Sqwincher Qwik Stiks Mixed Pack Pack of (70000305) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 5 | 210.45 | 0 | 0 | 70000305) | 70000305 | 4500002741/00030 - Due Date
4500002761 | 00010 | POLYFLEX HOSE -16JICF/1" NPT MALE 316SS (70001858) | ENZED WELSHPOOL BELTRAMO BUSINESS TRUST (30000896) |  | 0 | 2 | 13108.9 | 0 | 0 | 70001858) | 70001858 | 4500002761/00010 - Due Date
4500002761 | 00020 | 124224 1" NPT 316 SS NIPPLE (70001859) | ENZED WELSHPOOL BELTRAMO BUSINESS TRUST (30000896) |  | 0 | 4 | 287.64 | 0 | 0 | 70001859) | 70001859 | 4500002761/00020 - Due Date
4500002761 | 00030 | 1" NPT PLUG 316SS (70002290) | ENZED WELSHPOOL BELTRAMO BUSINESS TRUST (30000896) |  | 0 | 4 | 232.28 | 0 | 0 | 70002290) | 70002290 | 4500002761/00030 - Due Date
4500002761 | 00040 | MATERIAL CERT (70002265) | ENZED WELSHPOOL BELTRAMO BUSINESS TRUST (30000896) |  | 0 | 2 | 30 | 0 | 0 | 70002265) | 70002265 | 4500002761/00040 - Due Date
4500002830 | 00010 | ELEMENT,FLTR,AIR,CYL,SOCK (70002506) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-07 | 80 | 80 | 4182.4 | 80 | 52.28 | 70002506) | 70002506 | 4500002830/00010 - Due Date 45419
4500002830 | 00020 | CABLE TIE W X 48 IN,NYLON (70002507) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-07 | 80 | 80 | 623.2 | 80 | 0 | 70002507) | 70002507 | 4500002830/00020 - Due Date 45419
4500002830 | 00030 | ELEMENT,FLTR,AIR,CYL,SOCK (70002506) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-07 | 80 | 80 | 4182.4 | 80 | 0 | 70002506) | 70002506 | 4500002830/00030 - Due Date 45419
4500002830 | 00040 | CABLE TIE W X 48 IN,NYLON (70002507) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-07 | 80 | 80 | 623.2 | 80 | 0 | 70002507) | 70002507 | 4500002830/00040 - Due Date 45419
4500002969 | 00010 | DETECTOR,GAS,ELECTROCHEMICAL SENSOR,O2,2 (11120471) | PROCHEM PIPELINE PRODUCTS PTY LTD (30000271) |  | 0 | 2 | 1940 | 0 | 0 | 11120471) | 11120471 | 4500002969/00010 - Due Date
4500003059 | 00010 | 25NPT FEMALE FULL ORE BALL VALVE HOKE (70002738) | PROCHEM PIPELINE PRODUCTS PTY LTD (30000271) |  | 0 | 4 | 415.28 | 0 | 0 | 70002738) | 70002738 | 4500003059/00010 - Due Date
4500003180 | 00020 | GASKET,SPW,TYPE CRIR,600LB,DN80,101MM ID (10509404) | KLINGER LIMITED (30000403) |  | 0 | 4 | 104.16 | 0 | 104.16 | 10509404) | 10509404 | 4500003180/00020 - Due Date
4500003180 | 00030 | GASKET,SPW,CRIR,CL 300/600,25MM NB,SS316 (10015056) | KLINGER LIMITED (30000403) |  | 0 | 12 | 128.64 | 0 | 128.64 | 10015056) | 10015056 | 4500003180/00030 - Due Date
4500003282 | 00010 | WATER,DRINKING,BOTTLED,STILL WATER,CTN/2 (10276570) | ATOM SUPPLY (30000407) |  | 0 | 57 | 1303.02 | 0 | 1303.02 | 10276570) | 10276570 | 4500003282/00010 - Due Date
4500003342 | 00020 | Bullivants Ratchet Assembly J Hook 35mm (70002829) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 25 | 514.75 | 0 | 0 | 70002829) | 70002829 | 4500003342/00020 - Due Date
4500003342 | 00030 | Sqwincher Frozen Squeeze Pops Pack of 10 (70001767) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-04 | 20 | 20 | 110.6 | 20 | 110.6 | 70001767) | 70001767 | 4500003342/00030 - Due Date 45386
4500003342 | 00040 | CRC 2016 CO Contact Cleaner Clear 350 gr (70000847) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 18 | 306.18 | 0 | 0 | 70000847) | 70000847 | 4500003342/00040 - Due Date
4500003342 | 00050 | Cabac 40HDMI1 4MM10 Male Male Cable HDMI (70002893) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 10 | 850.9 | 0 | 0 | 70002893) | 70002893 | 4500003342/00050 - Due Date
4500003342 | 00060 | Hamilton 7242 Sunscreen Lotion Sensitive (70002850) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 20 | 372.8 | 0 | 0 | 70002850) | 70002850 | 4500003342/00060 - Due Date
4500003342 | 00070 | CRC 5005 5 56 Multi Purpose Lubricant 40 (70002839) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 18 | 133.92 | 0 | 0 | 70002839) | 70002839 | 4500003342/00070 - Due Date
4500003380 | 00010 | Antibacterial Wipes 'MAXX-PACK' 4 X 1200 (70002894) | ATOM SUPPLY (30000407) |  | 0 | 1 | 255.47 | 0 | 255.47 | 70002894) | 70002894 | 4500003380/00010 - Due Date
4500003380 | 00020 | Bucket Plastic Dispenser Empty For WOW W (70002895) | ATOM SUPPLY (30000407) |  | 0 | 5 | 139.55 | 0 | 139.55 | 70002895) | 70002895 | 4500003380/00020 - Due Date
4500003384 | 00010 | STAHL 6V/7Ah BATTERY FOR 6009/6409 (70002778) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 11 | 9037.82 | 0 | 0 | 70002778) | 70002778 | 4500003384/00010 - Due Date
4500003399 | 00010 | REGULATOR; 1/2" BSP Black Nylon Flow (70002853) | TRINKOR PTY LTD (30001954) | 2024-03-22 | 8 | 8 | 4764.08 | 8 | 4764.08 | 70002853) | 70002853 | 4500003399/00010 - Due Date 45373
4500003399 | 00020 | VALVE; Ball 1/2 inch BSP Female/Female 3 (70002854) | TRINKOR PTY LTD (30001954) | 2024-03-22 | 8 | 8 | 886.16 | 8 | 886.16 | 70002854) | 70002854 | 4500003399/00020 - Due Date 45373
4500003399 | 00030 | ASSEMBLY; Push down plate & Valve leaver (70002855) | TRINKOR PTY LTD (30001954) | 2024-03-22 | 8 | 8 | 1658.24 | 8 | 1658.24 | 70002855) | 70002855 | 4500003399/00030 - Due Date 45373
4500003399 | 00040 | PLATE; Baffle 316L (70002879) | TRINKOR PTY LTD (30001954) | 2024-03-22 | 8 | 8 | 584.96 | 8 | 584.96 | 70002879) | 70002879 | 4500003399/00040 - Due Date 45373
4500003399 | 00050 | BOWL; 316 S/Steel Eyewash (70002900) | TRINKOR PTY LTD (30001954) | 2024-03-22 | 4 | 4 | 1375.52 | 4 | 1375.52 | 70002900) | 70002900 | 4500003399/00050 - Due Date 45373
4500003399 | 00060 | ASSEMBLY; Ball Valve (70002901) | TRINKOR PTY LTD (30001954) | 2024-03-22 | 8 | 8 | 1992.16 | 8 | 1992.16 | 70002901) | 70002901 | 4500003399/00060 - Due Date 45373
4500003399 | 00070 | ROD; Pull Assy (70002902) | TRINKOR PTY LTD (30001954) | 2024-03-22 | 4 | 4 | 831.08 | 4 | 831.08 | 70002902) | 70002902 | 4500003399/00070 - Due Date 45373
4500003399 | 00080 | ROSE; Shower SS (70002903) | TRINKOR PTY LTD (30001954) | 2024-03-22 | 4 | 4 | 871.88 | 4 | 871.88 | 70002903) | 70002903 | 4500003399/00080 - Due Date 45373
4500003445 | 00010 | Sample Cell matched pair 1cm P/N KH2001 (70002669) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-01 | 1 | 1 | 756.57 | 1 | 756.57 | 70002669) | 70002669 | 4500003445/00010 - Due Date 45383
4500003445 | 00020 | Thermometer -10/110 degrees P/N GT4750 (70002905) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-01 | 1 | 1 | 15.84 | 1 | 15.84 | 70002905) | 70002905 | 4500003445/00020 - Due Date 45383
4500003481 | 00010 | DANFOSS PRESSURE SWITCH (70002885) | HINCO INSTRUMENTS HINCO GROUP PTY LTD (30000235) | 2024-05-30 | 1 | 1 | 2229 | 1 | 2229 | 70002885) | 70002885 | 4500003481/00010 - Due Date 45442
4500003488 | 00010 | Perfecto HT 5 Heat transfer oil 205l (70002906) | CASTROL PERFORMANCE LUBRICANTS CASTROL AUSTRALIA PTY LIMITED (30001101) |  | 0 | 4 | 3990.2 | 0 | 0 | 70002906) | 70002906 | 4500003488/00010 - Due Date
4500003501 | 00010 | Sqwincher Qwik Stiks Mixed Pack Pack of (70000305) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 10 | 420.9 | 0 | 0 | 70000305) | 70000305 | 4500003501/00010 - Due Date
4500005313 | 00010 | Bolle 1614401 Safety Spectacles Prism Me (70003600) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 30 | 230.1 | 0 | 0 | 70003600) | 70003600 | 4500005313/00010 - Due Date
4500005313 | 00020 | Bolle 1614402 Safety Spectacles Prism Me (70003601) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 30 | 230.1 | 0 | 0 | 70003601) | 70003601 | 4500005313/00020 - Due Date
4500005313 | 00030 | Ansell HyFlex 11 618 General Purpose Glo (70000866) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 50 | 327 | 0 | 0 | 70000866) | 70000866 | 4500005313/00030 - Due Date
4500005313 | 00040 | Ansell HyFlex 11 618 General Purpose Glo (70000864) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 50 | 327 | 0 | 0 | 70000864) | 70000864 | 4500005313/00040 - Due Date
4500005313 | 00050 | Ansell HyFlex 11 618 General Purpose Glo (70000865) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 25 | 140 | 0 | 0 | 70000865) | 70000865 | 4500005313/00050 - Due Date
4500005313 | 00060 | J Burrows A4 Premium Copy Paper 80gsm Wh (70002463) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 5 | 210.85 | 0 | 0 | 70002463) | 70002463 | 4500005313/00060 - Due Date
4500005313 | 00070 | New Balance Contour MIDCNTR2E Men Safety (70003602) | J BLACKWOOD AND SON LTD (30000394) | 2024-03-21 | 1 | 1 | 189.09 | 1 | 189.09 | 70003602) | 70003602 | 4500005313/00070 - Due Date 45372
4500005313 | 00080 | Energizer EN92 Battery Industrial Alkali (70003603) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 60 | 33.6 | 0 | 0 | 70003603) | 70003603 | 4500005313/00080 - Due Date
4500005556 | 00010 | Oliver Safety Boots Lace Up Zip 55 332Z (70000954) | J BLACKWOOD AND SON LTD (30000394) | 2024-03-22 | 1 | 1 | 208 | 1 | 208 | 70000954) | 70000954 | 4500005556/00010 - Due Date 45373
4500005556 | 00020 | 3M S76SP AT010657586 Spectacles Whim Cre (70003591) | J BLACKWOOD AND SON LTD (30000394) |  | 0 | 5 | 151.85 | 0 | 0 | 70003591) | 70003591 | 4500005556/00020 - Due Date
4500005556 | 00030 | InvisibleZinc 103699 Mineral Sunscreen S (70000890) | J BLACKWOOD AND SON LTD (30000394) | 2024-03-22 | 20 | 20 | 616 | 20 | 616 | 70000890) | 70000890 | 4500005556/00030 - Due Date 45373
4500005556 | 00040 | JBS Industrial Storage Cupboards Flat To (70003609) | J BLACKWOOD AND SON LTD (30000394) | 2024-03-22 | 1 | 1 | 1016.79 | 1 | 1016.79 | 70003609) | 70003609 | 4500005556/00040 - Due Date 45373
4500006100 | 00010 | SCHELL VALVE / URINAL ROUGH IN KIT (70003681) | ROTATION SOLUTIONS ROTATION SOLUTIONS PTY LTD (30000246) | 2024-04-01 | 2 | 2 | 3690 | 2 | 3690 | 70003681) | 70003681 | 4500006100/00010 - Due Date 45383
4500006100 | 00020 | Procurement and Del to Centurion (70003682) | ROTATION SOLUTIONS ROTATION SOLUTIONS PTY LTD (30000246) | 2024-04-01 | 1 | 1 | 805 | 1 | 805 | 70003682) | 70003682 | 4500006100/00020 - Due Date 45383
4500006309 | 00010 | ELEMENT,FLTR,AIR,CYL,SOCK (70002506) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-07 | 80 | 80 | 4182.4 | 80 | 4182.4 | 70002506) | 70002506 | 4500006309/00010 - Due Date 45419
4500006309 | 00020 | CABLE TIE W X 48 IN,NYLON (70002507) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-03-26 | 80 | 80 | 623.2 | 80 | 623.2 | 70002507) | 70002507 | 4500006309/00020 - Due Date 45377
4500006460 | 00010 | HYDROGEN,TECH,320150,SIZE G CYLINDER,GDE (10509369) | COREGAS PTY LTD (30001686) |  | 0 | 6 | 854.82 | 0 | 0 | 10509369) | 10509369 | 4500006460/00010 - Due Date
4500006461 | 00010 | Orion Level + Flag Indicator (70001148) | HINCO INSTRUMENTS HINCO GROUP PTY LTD (30000235) | 2024-08-05 | 1 | 1 | 7875 | 1 | 7875 | 70001148) | 70001148 | 4500006461/00010 - Due Date 45509
4500006472 | 00010 | TESTING FLUID,ABLEWEST WC475MV20 (11153850) | ABLE WESTCHEM BORVEK PTY. LTD. (30001235) | 2024-03-27 | 1 | 1 | 475.5 | 1 | 475.5 | 11153850) | 11153850 | 4500006472/00010 - Due Date 45378
4500006895 | 00010 | Phillips DN029BL12CCT150 LED Downlight (70004011) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 45 | 3244.05 | 0 | 0 | 70004011) | 70004011 | 4500006895/00010 - Due Date
4500007088 | 00020 | LOCKPLATE,SOLATURB 905272C1 (10248102) | SOLAR TURBINES INCORPORATED (30000090) | 2024-05-14 | 1 | 1 | 52.39 | 1 | 52.39 | 10248102) | 10248102 | 4500007088/00020 - Due Date 45426
4500007088 | 00030 | MQ0032611-1635418-100-KIT,RETROFIT,L/O P (10617159) | SOLAR TURBINES INCORPORATED (30000090) | 2024-12-17 | 1 | 1 | 20542 | 1 | 20542 | 10617159) | 10617159 | 4500007088/00030 - Due Date 45643
4500007335 | 00010 | Shroud Repair Kit (Yellow Plastic Parts) (70004024) | PBA SAFETY PTY LTD (30002257) | 2024-04-03 | 4 | 4 | 256 | 4 | 256 | 70004024) | 70004024 | 4500007335/00010 - Due Date 45385
4500007335 | 00020 | Aerator Screen and Cap Assembly (70004025) | PBA SAFETY PTY LTD (30002257) | 2024-04-03 | 4 | 4 | 472 | 4 | 472 | 70004025) | 70004025 | 4500007335/00020 - Due Date 45385
4500007336 | 00010 | Pierlite ECOHB200LSE5G7 ECO HIGHBAY 200W (70003988) | EX ENGINEERING PTY LTD (30000025) | 2024-04-03 | 20 | 20 | 5330 | 20 | 5330 | 70003988) | 70003988 | 4500007336/00010 - Due Date 45385
4500007336 | 00020 | Socket Surface RC 2G 10A 250V 3 Pin 1P (70003989) | EX ENGINEERING PTY LTD (30000025) | 2024-04-03 | 10 | 10 | 216.2 | 10 | 216.2 | 70003989) | 70003989 | 4500007336/00020 - Due Date 45385
4500007337 | 00010 | GAGE,LEVEL,FLOAT (70001096) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-05-01 | 1 | 1 | 251.65 | 1 | 251.65 | 70001096) | 70001096 | 4500007337/00010 - Due Date 45413
4500007339 | 00010 | CHLORINE FREE "SWIFTEST" REAGENT DISPENS (70004042) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-03-22 | 1 | 1 | 229.3 | 1 | 229.3 | 70004042) | 70004042 | 4500007339/00010 - Due Date 45373
4500007339 | 00020 | ALKALINITY KIT 50-500ppm (K-9815) (70004051) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-23 | 1 | 1 | 159 | 1 | 159 | 70004051) | 70004051 | 4500007339/00020 - Due Date 45405
4500007699 | 00010 | O-RING VITON STANDARD (70004229) | PROCHEM PIPELINE PRODUCTS PTY LTD (30000271) | 2024-06-01 | 20 | 20 | 124 | 20 | 124 | 70004229) | 70004229 | 4500007699/00010 - Due Date 45444
4500007704 | 00010 | B2LNWA4006025 BOLT/2FW/2LN SS316 6X25MM (70004110) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-19 | 1 | 1 | 25.69 | 1 | 25.69 | 70004110) | 70004110 | 4500007704/00010 - Due Date 45401
4500007710 | 00010 | BATTERY,STORAGE,12V,MAINT FREE,600CCA,15 (11027363) | ATOM SUPPLY (30000407) | 2024-04-10 | 2 | 2 | 467.64 | 2 | 467.64 | 11027363) | 11027363 | 4500007710/00010 - Due Date 45392
4500007868 | 00010 | FOAM,ARC,FIREPROT FS12132201 (11052391) | MERCURY FIRESAFETY PTY LTD (30001728) | 2024-05-09 | 6 | 6 | 3690 | 6 | 3690 | 11052391) | 11052391 | 4500007868/00010 - Due Date 45421
4500007890 | 00010 | DIAPHRAGM KIT,6 PORT,EMERSON GCW9A00096G (10503002) | EMERSON PROCESS MANAGEMENT AUSTRALIA PTY LTD (30000401) | 2024-05-03 | 10 | 10 | 1500 | 10 | 1500 | 10503002) | 10503002 | 4500007890/00010 - Due Date 45415
4500007917 | 00010 | REGULATOR,PRESS,SMCPNEU AW20N02BCG2B (11279741) | SMC CORPORATION AUSTRALIA PTY LTD SMC PNEUMATICS AUSTRALIA PTY LTD (30001916) | 2024-04-01 | 1 | 1 | 165.9 | 1 | 165.9 | 11279741) | 11279741 | 4500007917/00010 - Due Date 45383
4500008163 | 00010 | FILTER ELEMENT,HEADLINE 125770C (10231706) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-08 | 2 | 2 | 170 | 2 | 170 | 10231706) | 10231706 | 4500008163/00010 - Due Date 45390
4500008163 | 00020 | TRAP,AIR,DRAIN,MOISTURE,18IN LG X 2-3/8I (11074919) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-08 | 1 | 1 | 1150 | 1 | 1150 | 11074919) | 11074919 | 4500008163/00020 - Due Date 45390
4500008163 | 00030 | WINDOW,REAR,ENVEENGI 330077 (10231999) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-08 | 2 | 2 | 300 | 2 | 300 | 10231999) | 10231999 | 4500008163/00030 - Due Date 45390
4500008163 | 00040 | O-RING,H/T,KALREZ,EMERSON MC0945 (10232005) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-08 | 4 | 4 | 408 | 4 | 408 | 10232005) | 10232005 | 4500008163/00040 - Due Date 45390
4500008163 | 00050 | O-RING KIT,CELL,AMETEK 76152TE (10504538) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-08 | 1 | 1 | 205 | 1 | 205 | 10504538) | 10504538 | 4500008163/00050 - Due Date 45390
4500008163 | 00060 | GASKET,REAR WINDOW,ENVEENGI 330078 (10231709) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-08 | 2 | 2 | 112 | 2 | 112 | 10231709) | 10231709 | 4500008163/00060 - Due Date 45390
4500008163 | 00070 | ACETIC ACID,UN2789,EMERSON C00082 (10231997) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-08 | 9 | 9 | 1098 | 9 | 1098 | 10231997) | 10231997 | 4500008163/00070 - Due Date 45390
4500008163 | 00080 | TUBE,QUARTZ,13IN LG,ENVEENGI 330423 (10232001) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-08 | 2 | 2 | 1250 | 2 | 1250 | 10232001) | 10232001 | 4500008163/00080 - Due Date 45390
4500008632 | 00010 | Nozzle Branch 65mm BIC brass with rubber (70004707) | WORMALD AUSTRALIA PTY LTD (30000072) | 2024-04-10 | 1 | 1 | 525.72 | 1 | 525.72 | 70004707) | 70004707 | 4500008632/00010 - Due Date 45392
4500008673 | 00010 | TAPE,SENSING,330FT LG,ENVEENGI 330133XS (10232273) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-11 | 5 | 5 | 1325 | 5 | 1325 | 10232273) | 10232273 | 4500008673/00010 - Due Date 45393
4500008673 | 00020 | TAPE,SENSING,330FT LG,ENVEENGI 330133XS (10232273) | ANALYTICAL CONTROL PTY LTD (30000230) | 2024-04-11 | 1 | 1 | 265 | 1 | 265 | 10232273) | 10232273 | 4500008673/00020 - Due Date 45393
4500008679 | 00010 | FILTER ELEMENT,AIR,COMPAIR 100006374 (10504687) | GARDNER DENVER INDUSTRIES PTY LTD (30000270) | 2024-05-06 | 3 | 3 | 1780.89 | 3 | 1780.89 | 10504687) | 10504687 | 4500008679/00010 - Due Date 45418
4500009332 | 00010 | GAS,CAL,50PPM H20,COREGAS 380122ESIZE (11316075) | COREGAS PTY LTD (30001686) | 2024-05-13 | 2 | 2 | 5814.2 | 2 | 5814.2 | 11316075) | 11316075 | 4500009332/00010 - Due Date 45425
4500009332 | 00020 | GAS,CAL,5PPM H2S,COREGAS 380122E (11316098) | COREGAS PTY LTD (30001686) | 2024-05-27 | 2 | 2 | 8430.48 | 2 | 8430.48 | 11316098) | 11316098 | 4500009332/00020 - Due Date 45439
4500009332 | 00030 | CALIBRATING GAS,380145,SIZE G 1081 CYLIN (10509372) | COREGAS PTY LTD (30001686) | 2024-05-20 | 2 | 2 | 13817 | 2 | 13817 | 10509372) | 10509372 | 4500009332/00030 - Due Date 45432
4500009333 | 00010 | WATER,PURIFIED,DEMINERALISED,IBC/1000KG (10202018) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-05-01 | 1 | 1 | 829.8 | 1 | 829.8 | 10202018) | 10202018 | 4500009333/00010 - Due Date 45413
4500009334 | 00020 | BELT,POS DRV,224T,FALCON PD,SYNC,HNBR,8M (10507326) | APPLIED INDUSTRIAL TECHNOLOGIES PTY LTD (30000076) | 2024-05-01 | 2 | 2 | 689.96 | 2 | 689.96 | 10507326) | 10507326 | 4500009334/00020 - Due Date 45413
4500009340 | 00010 | Panduit Pan Ty PLT3S C0 Locking Cable Ti (70004974) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 15 | 15 | 151.2 | 15 | 151.2 | 70004974) | 70004974 | 4500009340/00010 - Due Date 45405
4500009340 | 00020 | Bullivants Polypropylene Cable Haul Rope (70004975) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 1 | 1 | 76.36 | 1 | 76.36 | 70004975) | 70004975 | 4500009340/00020 - Due Date 45405
4500009340 | 00030 | CRC 2016 CO Contact Cleaner Clear 350 gr (70000847) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 12 | 12 | 204.12 | 12 | 204.12 | 70000847) | 70000847 | 4500009340/00030 - Due Date 45405
4500009340 | 00040 | Jamec Pem Air Blow Gun Pistol Grip Brass (70004976) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 2 | 2 | 32.14 | 2 | 32.14 | 70004976) | 70004976 | 4500009340/00040 - Due Date 45405
4500009340 | 00050 | Tesa Tape PVC Ducting Rubber Based Silve (70004980) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 30 | 30 | 110.7 | 30 | 110.7 | 70004980) | 70004980 | 4500009340/00050 - Due Date 45405
4500009340 | 00060 | Loctite 2783777 LB 8009 Heavy Duty Anti (70004981) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 10 | 10 | 377.7 | 10 | 377.7 | 70004981) | 70004981 | 4500009340/00060 - Due Date 45405
4500009340 | 00070 | Ansell Earth HyFlex 11 618 General Purpo (70005171) | J BLACKWOOD AND SON LTD (30000394) | 2024-04-23 | 50 | 50 | 327 | 50 | 327 | 70005171) | 70005171 | 4500009340/00070 - Due Date 45405
B513592043 | 00010 | MQ0032611-1635418-100-KIT,RETROFIT,L/O P (10617159) | SOLAR TURBINES INCORPORATED (30000090) | 2024-05-01 | 1 | 1 | 13079.7 | 1 | 13079.7 | 10617159) | 10617159 | B513592043/00010 - Due Date 45413
B513594607 | 00010 | CARD,CTRL,COMPCONT 10500010007 (10992866) | COMPRESSOR CONTROLS PTY LTD (30000168) | 2024-02-12 | 1 | 1 | 41257.4 | 1 | 0 | 10992866) | 10992866 | B513594607/00010 - Due Date 45334
B513596251 | 00020 | VALVE,JORDVALV MK6363D025S6PTZZZZ15JLSE0 (11392820) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-03-01 | 2 | 2 | 27045.22 | 2 | 27045.22 | 11392820) | 11392820 | B513596251/00020 - Due Date 45352
B513596462 | 00010 | M01100G31, Absolyte GP 2V Cell, Bank A (10618975) | EX ENGINEERING PTY LTD (30000025) | 2024-04-09 | 30 | 30 | 59220 | 30 | 59220 | 10618975) | 10618975 | B513596462/00010 - Due Date 45391
B513596463 | 00010 | M01100G31, Absolyte GP 2V Cell, Bank B (10618976) | EX ENGINEERING PTY LTD (30000025) | 2024-04-09 | 30 | 30 | 59220 | 30 | 59220 | 10618976) | 10618976 | B513596463/00010 - Due Date 45391
B513596464 | 00010 | M01100G31, Absolyte GP 2V Cell, Bank C (10618977) | EX ENGINEERING PTY LTD (30000025) | 2024-04-09 | 30 | 30 | 59220 | 30 | 59220 | 10618977) | 10618977 | B513596464/00010 - Due Date 45391
B513596465 | 00010 | M01100G31, Absolyte GP 2V Cell, Bank D (10618978) | EX ENGINEERING PTY LTD (30000025) | 2024-04-09 | 30 | 30 | 59220 | 30 | 59220 | 10618978) | 10618978 | B513596465/00010 - Due Date 45391
B513596527 | 00010 | C3000- HD PTZ Camera Station with integr (10618966) | WESTERN ADVANCE PTY LTD (30000287) |  | 0 | 2 | 35900 | 0 | 0 | 10618966) | 10618966 | B513596527/00010 - Due Date
B513596527 | 00020 | 2-port industrial 10/100/1000BaseT to 10 (10618967) | WESTERN ADVANCE PTY LTD (30000287) |  | 0 | 2 | 790 | 0 | 0 | 10618967) | 10618967 | B513596527/00020 - Due Date
B513596527 | 00030 | singlemode or multimode fibers 1000Base- (10618968) | WESTERN ADVANCE PTY LTD (30000287) |  | 0 | 2 | 150 | 0 | 0 | 10618968) | 10618968 | B513596527/00030 - Due Date
B513596527 | 00040 | 2M 10GBE ULTRA THIN CAT 6A UTPPATCH CABL (10618969) | WESTERN ADVANCE PTY LTD (30000287) |  | 0 | 2 | 20 | 0 | 0 | 10618969) | 10618969 | B513596527/00040 - Due Date
B513596527 | 00050 | LC to SC SM Duplex 1 metre lead (10618970) | WESTERN ADVANCE PTY LTD (30000287) |  | 0 | 2 | 68 | 0 | 0 | 10618970) | 10618970 | B513596527/00050 - Due Date
B513596555 | 00010 | O-RING,DRESRAND 002272149 (10504496) | SIEMENS ENERGY PTY LTD (30000222) |  | 0 | 5 | 972.61 | 0 | 0 | 10504496) | 10504496 | B513596555/00010 - Due Date
B513596555 | 00020 | O-RING,DRESRAND 002272214 (10504509) | SIEMENS ENERGY PTY LTD (30000222) |  | 0 | 6 | 53.62 | 0 | 0 | 10504509) | 10504509 | B513596555/00020 - Due Date
B513596555 | 00030 | O-RING,DRESRAND 002272219 (10273946) | SIEMENS ENERGY PTY LTD (30000222) |  | 0 | 6 | 66.69 | 0 | 0 | 10273946) | 10273946 | B513596555/00030 - Due Date
B513596555 | 00040 | O-RING,DRESRAND 002272228 (10273947) | SIEMENS ENERGY PTY LTD (30000222) |  | 0 | 6 | 96.77 | 0 | 0 | 10273947) | 10273947 | B513596555/00040 - Due Date
B513596555 | 00050 | O-RING,DRESRAND 002276256 (10504510) | SIEMENS ENERGY PTY LTD (30000222) |  | 0 | 5 | 221.84 | 0 | 0 | 10504510) | 10504510 | B513596555/00050 - Due Date
B513596555 | 00060 | O-RING,DRESRAND 002285273 (10504504) | SIEMENS ENERGY PTY LTD (30000222) |  | 0 | 4 | 962.1 | 0 | 0 | 10504504) | 10504504 | B513596555/00060 - Due Date
B513596833 | 00060 | Exide, Absolyte GP 2V Cell, Std. Casing (10618979) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 60 | 44745 | 0 | 0 | 10618979) | 10618979 | B513596833/00060 - Due Date
B513596833 | 00070 | Exide, Absolyte GP 2V Cell, Std. Casing (10355271) | EX ENGINEERING PTY LTD (30000025) |  | 0 | 60 | 44745 | 0 | 0 | 10355271) | 10355271 | B513596833/00070 - Due Date
B513596972 | 00010 | VALVE,SAFETY,1/2 X 1IN,2.5BAR,1500PSI,-2 (10893131) | CALLIDUS PROCESS SOLUTIONS (30001274) | 2023-03-28 | 1 | 1 | 4670 | 1 | 4670 | 10893131) | 10893131 | B513596972/00010 - Due Date 45013
B513597129 | 00010 | GASKET,NON-MTL,SOLATURB 11006491 (10504560) | SOLAR TURBINES INCORPORATED (30000090) | 2024-01-09 | 1 | 1 | 16.5 | 1 | 0 | 10504560) | 10504560 | B513597129/00010 - Due Date 45300
B513597960 | 00010 | CALIBRATING GAS,2 X 34L AL CYL,40PPM H2S (10232596) | THERMO FISHER SCIENTIFIC THERMO FISHER SCIENTIFIC AUSTRALIA (30000313) | 2024-01-12 | 2 | 2 | 1168 | 2 | 1168 | 10232596) | 10232596 | B513597960/00010 - Due Date 45303
B513598052 | 00010 | WATER,DRINKING,BOTTLED,STILL WATER,CTN/2 (10276570) | ATOM SUPPLY (30000407) |  | 0 | 57 | 1177.62 | 0 | 1177.62

## PR
Purchase Requisition Item | Material | Plant | Desired Supplier | Quantity | Valuation Price | Total Value | Delivery Date |  |  | Formula - Do Not Delete or Edit
1000005381 / 00010 | VALVE,SAFETY,25*E*50,PILOT OPER,CS SA216 (11175260) | PDC - MAC NG (DU01) | WESTERN PROCESS CONTROLS PTY LTD (30000278) | 1.000 EA | 1.00 AUD | 1.00 AUD | 13/06/2024 | 11175260) | 11175260 | PDC - MAC NG (DU01)1000005381 / 00010 - Due Date 13/06/2024
1000005388 / 00010 | VALVE,PRESS REG,DN25,BKBPUMP CRV0251796M (11271657) | PDC - MAC NG (DU01) |  | 2.000 EA | 1.00 AUD | 2.00 AUD | 15/05/2024 | 11271657) | 11271657 | PDC - MAC NG (DU01)1000005388 / 00010 - Due Date 15/05/2024
1000007397 / 00112 | Markrite Notebook Spiral Bound all weath (70005182) | PDC - MAC NG (DU01) |  | 20.000 EA | 14.68 AUD | 293.60 AUD | 30/04/2024 | 70005182) | 70005182 | PDC - MAC NG (DU01)1000007397 / 00112 - Due Date 30/04/2024
1000007397 / 00113 | Spirax Notebook Top Opening Black 112x77 (70005183) | PDC - MAC NG (DU01) |  | 20.000 EA | 0.72 AUD | 14.40 AUD | 30/04/2024 | 70005183) | 70005183 | PDC - MAC NG (DU01)1000007397 / 00113 - Due Date 30/04/2024
1000007397 / 00115 | BIC Pen 4 Colour Medium Tip 32mm Box of (70005184) | PDC - MAC NG (DU01) |  | 3.000 BOX | 27.64 AUD | 82.92 AUD | 30/04/2024 | 70005184) | 70005184 | PDC - MAC NG (DU01)1000007397 / 00115 - Due Date 30/04/2024
1000007398 / 00111 | Sqwincher Qwik Stiks Mixed Pack Pack of (70000305) | Macedon - MAC NG (DU50) |  | 5.000 PAC | 42.09 AUD | 210.45 AUD | 14/04/2024 | 70000305) | 70000305 | Macedon - MAC NG (DU50)1000007398 / 00111 - Due Date 14/04/2024
1000007398 / 00114 | Sharpie Permanent Marker Fine Tip Black (70000312) | Macedon - MAC NG (DU50) |  | 4.000 BOX | 16.03 AUD | 64.12 AUD | 14/04/2024 | 70000312) | 70000312 | Macedon - MAC NG (DU50)1000007398 / 00114 - Due Date 14/04/2024
1000007399 / 00111 | Sqwincher Qwik Stiks Mixed Pack Pack of (70000305) | Macedon - MAC NG (DU50) |  | 5.000 PAC | 42.09 AUD | 210.45 AUD | 14/04/2024 | 70000305) | 70000305 | Macedon - MAC NG (DU50)1000007399 / 00111 - Due Date 14/04/2024
1000007452 / 00093 | MEDIA, PHENOL RED DEXTROSE (PRD) FOR DET (70005164) | PDC - MAC NG (DU01) |  | 2.000 PAC | 143.72 AUD | 287.44 AUD | 14/05/2024 | 70005164) | 70005164 | PDC - MAC NG (DU01)1000007452 / 00093 - Due Date 14/05/2024
1000007452 / 00095 | MEDIA MODIFIED POSTGATES (MPB) GROWTH IN (70005165) | PDC - MAC NG (DU01) |  | 2.000 PAC | 143.72 AUD | 287.44 AUD | 14/05/2024 | 70005165) | 70005165 | PDC - MAC NG (DU01)1000007452 / 00095 - Due Date 14/05/2024
1000007452 / 00097 | Sample Cell matched pair 1cm P/N KH2001 (70002669) | PDC - MAC NG (DU01) |  | 1.000 EA | 637.34 AUD | 637.34 AUD | 30/04/2024 | 70002669) | 70002669 | PDC - MAC NG (DU01)1000007452 / 00097 - Due Date 30/04/2024
1000007452 / 00099 | DISTILLED (DEMIN.) WATER IN NATURAL HDPE (70005166) | PDC - MAC NG (DU01) |  | 1.000 EA | 36.63 AUD | 36.63 AUD | 22/04/2024 | 70005166) | 70005166 | PDC - MAC NG (DU01)1000007452 / 00099 - Due Date 22/04/2024
1000007452 / 00101 | DRAGER TUBE HYDROGEN SULFIDE 0.2-5ppm (8 (70005167) | PDC - MAC NG (DU01) |  | 1.000 EA | 191.34 AUD | 191.34 AUD | 16/04/2024 | 70005167) | 70005167 | PDC - MAC NG (DU01)1000007452 / 00101 - Due Date 16/04/2024
1000007452 / 00103 | GAS, CALIBRATION 8AL - 58L - 5 ppm BENZE (70005168) | PDC - MAC NG (DU01) |  | 2.000 EA | 1,444.00 AUD | 2,888.00 AUD | 24/05/2024 | 70005168) | 70005168 | PDC - MAC NG (DU01)1000007452 / 00103 - Due Date 24/05/2024
1000007452 / 00105 | GAS, CALIBRATION 6DM - 58L - 50% METHANE (70005122) | PDC - MAC NG (DU01) |  | 2.000 EA | 465.00 AUD | 930.00 AUD | 24/05/2024 | 70005122) | 70005122 | PDC - MAC NG (DU01)1000007452 / 00105 - Due Date 24/05/2024
1000007456 / 00117 | Thread Sealing Tapes Stainless Steel Sil (70000255) | Macedon - MAC NG (DU50) |  | 30.000 EA | 10.67 AUD | 320.10 AUD | 19/04/2024 | 70000255) | 70000255 | Macedon - MAC NG (DU50)1000007456 / 00117 - Due Date 19/04/2024
2000012385 / 00010 | DISC,SAFETY,SOLATURB 999887C1 (10898330) | Macedon - MAC NG (DU50) |  | 2.000 EA | 1.00 AUD | 2.00 AUD | 27/06/2024 | 10898330) | 10898330 | Macedon - MAC NG (DU50)2000012385 / 00010 - Due Date 27/06/2024
2000012396 / 00010 | FILTER ELEMENT,SPIDER WEB XP,324MM DIA X (10385132) | Macedon - MAC NG (DU50) |  | 9.000 EA | 209.82 AUD | 1,888.38 AUD | 2024-02-06 | 10385132) | 10385132 | Macedon - MAC NG (DU50)2000012396 / 00010 - Due Date 45328
2000012433 / 00010 | LOCKPLATE,SOLATURB 905272C1 (10248102) | Macedon - MAC NG (DU50) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 2024-02-06 | 10248102) | 10248102 | Macedon - MAC NG (DU50)2000012433 / 00010 - Due Date 45328
2000012447 / 00010 | VALVE,PRESS REG,DN25,BKBPUMP CRV0251796M (11271657) | Macedon - MAC NG (DU50) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 28/06/2024 | 11271657) | 11271657 | Macedon - MAC NG (DU50)2000012447 / 00010 - Due Date 28/06/2024
2000012664 / 00010 | BOTTLE,OIL SAMPLE,1L,SGS SK165 (11086135) | PDC - MAC NG (DU01) |  | 11.000 EA | 2.00 AUD | 22.00 AUD | 2024-04-04 | 11086135) | 11086135 | PDC - MAC NG (DU01)2000012664 / 00010 - Due Date 45386
2000015936 / 00010 | COMPOUND,DRESRAND 099010023 (10274029) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 13/04/2024 | 10274029) | 10274029 | PDC - MAC NG (DU01)2000015936 / 00010 - Due Date 13/04/2024
2000016991 / 00010 | FILTER,AIR,ELECTROSTATIC,MEDIA MAXIMISIN (11066136) | PDC - MAC NG (DU01) |  | 9.000 EA | 1.00 AUD | 9.00 AUD | 15/04/2024 | 11066136) | 11066136 | PDC - MAC NG (DU01)2000016991 / 00010 - Due Date 15/04/2024
2000036637 / 00010 | VALVE,PRESS REG,DN25,BKBPUMP CRV0251796M (11271657) | Macedon - MAC NG (DU50) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/04/2024 | 11271657) | 11271657 | Macedon - MAC NG (DU50)2000036637 / 00010 - Due Date 29/04/2024
2000037965 / 00010 | DISC,SAFETY,SOLATURB 999887C1 (10898330) | Macedon - MAC NG (DU50) |  | 2.000 EA | 1.00 AUD | 2.00 AUD | 18/06/2024 | 10898330) | 10898330 | Macedon - MAC NG (DU50)2000037965 / 00010 - Due Date 18/06/2024
2000037967 / 00010 | FILTER ELEMENT,SPIDER WEB XP,324MM DIA X (10385132) | Macedon - MAC NG (DU50) |  | 12.000 EA | 209.82 AUD | 2,517.84 AUD | 18/06/2024 | 10385132) | 10385132 | Macedon - MAC NG (DU50)2000037967 / 00010 - Due Date 18/06/2024
2000037973 / 00010 | O-RING,169.3MM ID X 5.7MM,CRANE 89150084 (11093550) | Macedon - MAC NG (DU50) |  | 1.000 EA | 612.44 AUD | 612.44 AUD | 18/06/2024 | 11093550) | 11093550 | Macedon - MAC NG (DU50)2000037973 / 00010 - Due Date 18/06/2024
2000037974 / 00010 | O-RING,179.3MM X 5.7MM,CRANE 87461607 (11093552) | Macedon - MAC NG (DU50) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 18/06/2024 | 11093552) | 11093552 | Macedon - MAC NG (DU50)2000037974 / 00010 - Due Date 18/06/2024
2000042823 / 00010 | O-RING,BRANLUEBBE BL152228 (10504623) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/05/2024 | 10504623) | 10504623 | PDC - MAC NG (DU01)2000042823 / 00010 - Due Date 29/05/2024
2000042824 / 00010 | O-RING,BRANLUEBBE BL051041 (10504617) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/05/2024 | 10504617) | 10504617 | PDC - MAC NG (DU01)2000042824 / 00010 - Due Date 29/05/2024
2000042825 / 00010 | O-RING,HARDNESS,BRANLUEBBE BL152197 (10504619) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/05/2024 | 10504619) | 10504619 | PDC - MAC NG (DU01)2000042825 / 00010 - Due Date 29/05/2024
2000042826 / 00010 | SEAL RING,BRANLUEBBE BL051043 (10504620) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/05/2024 | 10504620) | 10504620 | PDC - MAC NG (DU01)2000042826 / 00010 - Due Date 29/05/2024
2000042827 / 00010 | O-RING,BRANLUEBBE BL152072 (10504622) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/05/2024 | 10504622) | 10504622 | PDC - MAC NG (DU01)2000042827 / 00010 - Due Date 29/05/2024
2000042828 / 00010 | SEAL RING,GRV,PE,BRANLUEBBE BL369637 (10504618) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/05/2024 | 10504618) | 10504618 | PDC - MAC NG (DU01)2000042828 / 00010 - Due Date 29/05/2024
2000042829 / 00010 | O-RING,BRANLUEBBE BL090105 (10504621) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/05/2024 | 10504621) | 10504621 | PDC - MAC NG (DU01)2000042829 / 00010 - Due Date 29/05/2024
2000042830 / 00010 | VALVE,30MM FEEDER,BRANLUEBBE BL051757 (10384751) | PDC - MAC NG (DU01) |  | 3.000 EA | 1.00 AUD | 3.00 AUD | 29/05/2024 | 10384751) | 10384751 | PDC - MAC NG (DU01)2000042830 / 00010 - Due Date 29/05/2024
2000042831 / 00010 | RING,BU,SUPPORT,BRANLUEBBE BL150466 (10504731) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 29/05/2024 | 10504731) | 10504731 | PDC - MAC NG (DU01)2000042831 / 00010 - Due Date 29/05/2024
2000043590 / 00010 | CLEANING COMPOUND,SOLVENT,SIMPLE GREEN,D (10016991) | PDC - MAC NG (DU01) |  | 3.000 EA | 160.77 AUD | 482.31 AUD | 29/05/2024 | 10016991) | 10016991 | PDC - MAC NG (DU01)2000043590 / 00010 - Due Date 29/05/2024
2000043593 / 00010 | GREASE,SPECIAL,CLIMAX 1034MT,SYNTHETIC P (11165576) | PDC - MAC NG (DU01) |  | 5.000 EA | 54.97 AUD | 274.85 AUD | 29/05/2024 | 11165576) | 11165576 | PDC - MAC NG (DU01)2000043593 / 00010 - Due Date 29/05/2024
2000043594 / 00010 | CALIBRATING GAS,2 X 34L AL CYL,40PPM H2S (10232596) | PDC - MAC NG (DU01) |  | 1.000 EA | 554.00 AUD | 554.00 AUD | 29/05/2024 | 10232596) | 10232596 | PDC - MAC NG (DU01)2000043594 / 00010 - Due Date 29/05/2024
2000043595 / 00010 | HYDRAULIC FLUID,TRANS,ATF HD,MINERAL OIL (10324023) | PDC - MAC NG (DU01) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 2024-03-05 | 10324023) | 10324023 | PDC - MAC NG (DU01)2000043595 / 00010 - Due Date 45356
2000045191 / 00010 | SODIUM HYPOCHLORITE SOLUTION,12.5%,20L (10355695) | PDC - MAC NG (DU01) |  | 1.000 DR | 1.00 AUD | 1.00 AUD | 31/05/2024 | 10355695) | 10355695 | PDC - MAC NG (DU01)2000045191 / 00010 - Due Date 31/05/2024
2000045800 / 00010 | BATTERY,STORAGE,12V,MAINT FREE,600CCA,15 (11027363) | Macedon - MAC NG (DU50) |  | 2.000 EA | 1.00 AUD | 2.00 AUD | 2024-06-05 | 11027363) | 11027363 | Macedon - MAC NG (DU50)2000045800 / 00010 - Due Date 45448
2000045801 / 00010 | REGULATOR,PRESS,SMCPNEU AW20N02BCG2B (11279741) | Macedon - MAC NG (DU50) |  | 1.000 EA | 1.00 AUD | 1.00 AUD | 2024-04-05 | 11279741) | 11279741 | Macedon - MAC NG (DU50)2000045801 / 00010 - Due Date 45387
2000046587 / 00010 | FILTER ELEMENT,AIR,CYL,SOLATURB 603346C1 (11359230) | PDC - MAC NG (DU01) |  | 12.000 EA | 1.00 AUD | 12.00 AUD | 2024-03-09 | 11359230) | 11359230 | PDC - MAC NG (DU01)2000046587 / 00010 - Due Date 45360
2000047261 / 00010 | GREASE,GP,PREMIUM H/D,LITHIUM COMPLEX BA (10888808) | PDC - MAC NG (DU01) |  | 12.000 EA | 1.00 AUD | 12.00 AUD | 2024-04-06 | 10888808) | 10888808 | PDC - MAC NG (DU01)2000047261 / 00010 - Due Date 45388
2000047579 / 00010 | WATER,DRINKING,BOTTLED,STILL WATER,CTN/2 (10276570) | PDC - MAC NG (DU01) |  | 57.000 EA | 22.86 AUD | 1,303.02 AUD | 16/04/2024 | 10276570) | 10276570 | PDC - MAC NG (DU01)2000047579 / 00010 - Due Date 16/04/2024
2000047715 / 00010 | FILTER ELEMENT,DUST,COMPAIR CE0258NBE (10504691) | PDC - MAC NG (DU01) |  | 2.000 EA | 1.00 AUD | 2.00 AUD | 2024-04-06 | 10504691) | 10504691 | PDC - MAC NG (DU01)2000047715 / 00010 - Due Date 45388
2000047716 / 00010 | FILTER ELEMENT,DUST,COMPAIR CE0258ND (10912588) | PDC - MAC NG (DU01) |  | 2.000 EA | 1.00 AUD | 2.00 AUD | 2024-04-06 | 10912588) | 10912588 | PDC - MAC NG (DU01)2000047716 / 00010 - Due Date 45388
2000047717 / 00010 | WATER BOTTLE,15L,BLKWOODS 01029558DS (11229501) | PDC - MAC NG (DU01) |  | 32.000 EA | 9.90 AUD | 316.80 AUD | 30/04/2024 | 11229501) | 11229501 | PDC - MAC NG (DU01)2000047717 / 00010 - Due Date 30/04/2024
2000047718 / 00010 | MUFFLER,8.75 LG,ALLIEDWIT M10 (10042306) | PDC - MAC NG (DU01) |  | 12.000 EA | 114.80 AUD | 1,377.60 AUD | 2024-04-06 | 10042306) | 10042306 | PDC - MAC NG (DU01)2000047718 / 00010 - Due Date 45388
2000048044 / 00010 | SWITCH,PRESS,N2,SOLATURB 997425C1 (10283476) | Macedon - MAC NG (DU50) |  | 2.000 EA | 1.00 AUD | 2.00 AUD | 16/04/2024 | 10283476) | 10283476 | Macedon - MAC NG (DU50)2000048044 / 00010 - Due Date 16/04/2024
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date
- Due Date