## COP Raw.1
Unique | wo+mat+qty+batch | mat+batch | Release id (" "=rel., X=not yet,1=never) | MO Revision | MO Status | MO Actual Release date | Requirement date (MO component) | Material Staging date (STO) | MO basic Start date | MO basic Finish date | MO Main work centre | MO number | Oper/Act number of Reservation | BOM item number | MO Description | Description | Functional location | Description | Procurement plant | Req Priority for Material/Component | Alert / Exception | Material / Component | Material Description | Requirement quantity | Remaining quanity | Withdrawn quantity | balance | Requirement UOM | Stock on-hand @ Base | Stock In-Transit into Remote | Stock on-hand @ Remote | HU Quantity | UoM of HU | Expediting Note / User Comment | Message log(Orchestration / Derivation) | Supply status | Supply Process | Supply Process (Desc.) | Planned Deliver Time (in days) (PR) | Supplying Plant (STO) | Current STO | Current STO Item | Incoterms | Planned Delivery Time (in days) (STO) | Purchase Requisition | Purchase Requisition Item | Vendor | Name of Supplier | Vendor PO | Vendor PO item | PO qty | Requirement UOM | Delivery date (PO) | Batch/Valuation type(from MO component) | Inbound Delivery (PO) | Latest Inbound Delivery (STO) | Latest Outbound Delivery STO | Process Phase | Short Description | Reservation | Reservation Item | Reservation item deletion indicator | UoM of HU | Nested HU Lvl 2 | Nested HU Lvl 3 | Top HU | Shipping Type | Voyage type | Voyage status | Container-ID | Linked Work-pack/HU | Workpack bin | Unloading Point | Incompletion indic. (Y/N) | Return STO | Return STO Item | Return STO Qty | Return STO UOM | Arrival (actual) | Arrival (plan) | Campaign (Y/N) | Company Code (STO) | Creation Date (STO) | Current document | Current STO Item has deletion code? | Delay @ Demand plant | Delay @ Procument plant | Delay @ Supply plant | Delivery date (PR) | Delivery date (STO) | Demand Plant | Early start date (MO) | Equipment | Description | ETA @ Demand plant | ETA @ Procument plant | ETA @ Supply plant | EWM task for GI (STO) | EWM Warehouse for GI (STO) | Final Due Date | GI qty (OBD for STO) | Good Receipt (PO) | Goods Issue date (STO) | Goods Issue Document (STO) | Goods Receipt End date (STO) | Goods Recipient | GR IBD Document (STO) | GR processing time | GR Processing time Demand plant (STO) | GR Processing time Supply plant (PR) | Ref Latest Outbound Delivery (STO) | GR qty (IBD for STO) | GR qty (PO) | Inbound Delivery (STO) | Internal alert code | Is PR Item Deleted? | Is Reservation Item Deleted(hard)? | isMessageThresholdBreached | Item category (BOM) | Latest GI (STO) | Latest GI STO Year | Latest GR (PO) | Latest GR IBD (STO) | Latest GR IBD Year(STO) | Latest GR PO Year | Latest IBD (PO) | Loading Date (STO) | Maint. Operation Exec. Stage Code | Maintenance Planning Plant | Name 1 | Maintenance Plant | Plant Name | Maintenance Storage Location | Material / Component description | Material Description | Message Text Date | Message Type | Oper. Phase Status | Operation / Activity | Operation description | Operation Control key | Operation description | Operation System Condition | Order Phase Status | Outbound Delivery (STO) | Person responsible | Picking bin | Plant Section | PO item deletion indic | Position | PR Processing State | Short Description | PR Release Indicator | Priority Type | Priority Type Text | Process Subphase | Subphase Description | Profile Status | Project stock | Purchasing Group | Purchasing Grp. Name | Purchasing group (STO) | Purchasing Grp. Name | Purchasing Organisation (STO) | Purchasing Processing time(PR) | Receiving Plant (STO) | Release date (PR) | Req Urgency for Material/Component | Request for Quotation | Requirements date (PR) | Reservation Item (reverse link) | Reservation Special Stock Ind. | Responsible Buyer (for PO) | Return doc (MvT 262) | Revision | Revision Type | Voyage-id | Route (STO) | Routing number (of MO Operation) | Shipping Point (STO) | Status of Material (Demand Plant) | Status of Material (Supplying Plant) | STO (Supplying) - 1st STO | STO (Supplying) - 1st STO Item | STO Committed date (STO) | STO for SP97 (2nd STO) | STO for SP97 2ndS STO Item | STO quantity (STO) | STO quantity UoM (STO) | Storage Location (STO) based on MO | Supplying Plant | Transportation Planning date (STO) | User Responsible | User-status | Vehicle departure date | Vendor PO Pur Org | Warehouse | MO Actual Finish date | MO Actual Start date | MO Company Code | Company Name | MO Controlling Area | MO created by | MO creation date | MO from PR (reverse link) | MO item number | Stock on-hand @ Procurement Plant | MO Overall Status | Warehouse Number(STO) | MO overall status code | MO Planner Group | Planner Group Name | MO Priority | Priority Text | MO Responsible Cost Center | MO Scheduled Finish date | MO Scheduled Release date | MO Scheduled Start date | MO System Status | MO type | Order Type Name | MO WBS element
100436876000028620000216479ta0220121 | 600002862100436874 | 10043687 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0220 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10043687 | TEE:EQUAL,50mm,BW,CS,A234-WPB,SCH 40 | 4 | 0 | 0 | 4 | EA | 0 | 0 | 4 | 4 | EA | 05.10 - HU 101000000096674 to AA02 | Supply for Order 600002862, Item 121 cannot be changed 180085341 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085341 | 9017825 | 07 | Execution | 0000216479 | 121 | 0 | EA |  |  | 102000000021854 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255291_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000037301 | 1020 | 2024-12-31 | 4 |  | 2024-10-24 | 4900158479_2024_0001 | 2024-10-07 |  | 5000255291_2024_0001 | 0 | 2 | 0 | 90020228 | 4 | 0 | 180085341 | 2 | 0 | 0 | X | L | 4900158479 | 2024 |  | 5000255291 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10043687 | TEE:EQUAL,50mm,BW,CS,A234-WPB,SCH 40 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017825_0050 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 121 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 1130 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100484696000028620000216479ta0100109 | 600002862100484691 | 10048469 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2025-03-17 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0100 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10048469 | FLANGE,BLIND;450MM,CL150,RF,CS,A105N | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 14.10 - HU 101000000099504 TO AA02 | Supply for Order 600002862, Item 109 cannot be changed 180081148 item 10 already exists | Material work-packed @AA53 | SP97 | Direct Multi-base | 3 | AA02 | 5300006667 | 1010 | CPT | 7 | 1000018366 | 109 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500027121 | 90 | 1 | EA | 2024-10-07 |  | /180079843 | 180081280 | 90021679 | 07 | Execution | 0000216479 | 109 | 0 | EA |  |  | 101000000099504 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000242364_2024 | 0 | 0 | 0 | 0 | 2025-02-28 | 2025-03-20 | AA53 | 2024-11-22 |  |  | 2024-10-13 | 2025-03-02 | 2024-10-13 | 100000034938 | 1020 | 2024-12-31 | 1 | 5000240525_2024_0001 | 2024-10-13 | 4900151617_2024_0001 | 2024-10-11 |  | 5000242364_2024_0001 | 0 | 2 | 2 | 90021679 | 1 | 1 | 180081280 | 2 | 0 | 0 | X | L | 4900151617 | 2024 | 5000240525 | 5000242364 | 2024 | 2024 | /018007984 | 2025-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10048469 | FLANGE,BLIND;450MM,CL150,RF,CS,A105N | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90021679_0010 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-18 | 30 |  | 2025-03-02 | 109 |  | 0 |  | 24SDLN2C | MJ | 1000003675 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1010 |  | 5300014053 | 50 | 1 | EA | 2001 | AA02 | 2025-03-17 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100484896000028620000216479ta0200119 | 600002862100484894 | 10048489 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0200 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Shipped qty below requirement qty | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 4 | 1 | 0 | 4 | EA | 0 | 0 | 3 | 2 | EA | 10.10 - Del 80018247/000070 for picking | Supply for Order 600002862, Item 119 cannot be changed 180080833 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085321 | 9017445 | 07 | Execution | 0000216479 | 119 | 0 | EA |  |  | 102000000021789 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255250_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000036571 | 1020 | 2024-12-31 | 3 |  | 2024-10-24 | 4900158458_2024_0003/4900150844_2024_0001 | 2024-10-07 |  | 5000255250_2024_0002/5000241125_2024_0001 | 0 | 2 | 0 | 90020228 | 3 | 0 | 180085321/180080833 | 1 | 0 | 0 | X | L | 4900158458 | 2024 |  | 5000255250 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020228_0030/9017445_0030/9016340_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 119 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1110 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100484896000028620000216479ta0200119 | 600002862100484894 | 10048489 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0200 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Shipped qty below requirement qty | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 4 | 1 | 0 | 4 | EA | 0 | 0 | 3 | 1 | EA | 10.10 - Del 80018247/000070 for picking | Supply for Order 600002862, Item 119 cannot be changed 180080833 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085321 | 9017445 | 07 | Execution | 0000216479 | 119 | 0 | EA |  |  | 102000000020573 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255250_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000036571 | 1020 | 2024-12-31 | 3 |  | 2024-10-24 | 4900158458_2024_0003/4900150844_2024_0001 | 2024-10-07 |  | 5000255250_2024_0002/5000241125_2024_0001 | 0 | 2 | 0 | 90020228 | 3 | 0 | 180085321/180080833 | 1 | 0 | 0 | X | L | 4900158458 | 2024 |  | 5000255250 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020228_0030/9017445_0030/9016340_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 119 |  | 0 |  | 24SDLN2C | MJ | 1000003648 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1110 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-16 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100485286000028620000216479ta00101 | 600002862100485281 | 10048528 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-01 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0010 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10048528 | FLANGE,BLIND;150MM,CL300,RF,LTCS | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 06.03 - ETA 17.04.24 PO 4500005010 x 1 Australasian Fittings | Supply for Order 600002862, Item 1 cannot be changed 9019562 item 370 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096189 | 9019562 | 07 | Execution | 0000216479 | 1 | 1 | EA |  |  | 102000000024278 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-02-16 | GRST-5000288015_2024 | 0 | 0 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000042070 | 1020 | 2024-12-31 | 1 |  | 2024-11-21 | 4900176329_2024_0001 | 2024-11-01 |  | 5000288015_2024_0001 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180096189 | 1 | 0 | 0 | X | L | 4900176329 | 2024 |  | 5000288015 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048528 | FLANGE,BLIND;150MM,CL300,RF,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9019562_0370 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 24SDLN2C | MJ | 1000004156 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 370 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-11-22 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100485526000028620000216479ta00202 | 600002862100485521 | 10048552 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0020 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10048552 | FLANGE,BLIND;600MM,CL600,RF,LTCS | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 03.10 - HU 101000000060519 to AA02 | Supply for Order 600002862, Item 2 cannot be changed 180078362 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 2 | 0 | EA |  |  | 102000000020024 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000233767_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0001 | 2024-11-01 |  | 5000233767_2024_0001 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048552 | FLANGE,BLIND;600MM,CL600,RF,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0380 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 24SDLN2C | MJ | 1000003650 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 380 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100485926000028620000216479ta0320138 | 600002862100485922 | 10048592 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0320 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2 | 0 | 0 | 2 | EA | 6 | 0 | 2 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 138 cannot be changed 9019098 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096302 | 9019098 | 07 | Execution | 0000216479 | 138 | 0 | EA |  |  | 102000000024339 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000288422_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042336 | 1020 | 2024-12-31 | 2 |  | 2024-11-21 | 4900176518_2024_0001 | 2024-11-24 |  | 5000288422_2024_0001 | 0 | 2 | 0 | 90024832 | 2 | 0 | 180096302/180096308 | 2 | 0 | 0 |  | L | 4900176518 | 2024 |  | 5000288422 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019098_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 138 |  | 0 |  | 24SDLN2C | MJ | 1000004156 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1280 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-22 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100485926000028620000216479ta0300136 | 600002862100485922 | 10048592 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0300 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2 | 0 | 2 | 0 | EA | 6 | 0 | 2 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 136 cannot be changed 9019874 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180095953 | 9019874 | 07 | Execution | 0000216479 | 136 | 0 | EA |  |  | 102000000024297 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 40 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042154 | 1020 | 2024-12-31 | 2 |  | 2024-11-20 | 4900176014_2024_0001 | 2024-11-24 |  | 5000287051_2024_0001 | 0 | 2 | 0 | 90024831 | 2 | 0 | 180095953 | 2 | 0 | 0 |  | L | 4900176014 | 2024 |  | 5000287051 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019874_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 136 |  | 0 |  | 24SDLN2C | MJ | 1000004183 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1260 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-21 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100485936000028620000216479ta00303 | 600002862100485931 | 10048593 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0030 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10048593 | FLANGE,BLIND,150MM,CL150,RF,CS,SH40,GALV | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 03.10 - GR ZONE @ AA02 | Supply for Order 600002862, Item 3 cannot be changed 180083185 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 3 | 0 | EA | 101000000093418 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0003 | 2024-11-01 |  | 5000248569_2024_0002 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048593 | FLANGE,BLIND,150MM,CL150,RF,CS,SH40,GALV | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0390 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 390 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100485946000028620000216479ta00404 | 600002862100485947 | 10048594 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0040 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10048594 | FLANGE,BLIND;200MM,CL150,RF,CS,SH30,GALV | 7 | 0 | 7 | 0 | EA | 0 | 0 | 0 | 7 | EA | 03.10 - HU 101000000052150 to AA02 | Supply for Order 600002862, Item 4 cannot be changed 180078362 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 4 | 0 | EA |  |  | 102000000020023 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 7 |  | 2024-10-06 | 4900146921_2024_0003 | 2024-11-01 |  | 5000233767_2024_0002 | 0 | 2 | 0 | 90006343 | 7 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048594 | FLANGE,BLIND;200MM,CL150,RF,CS,SH30,GALV | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0400 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 400 |  |  | 0 | 7 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100485966000028620000216479ta00505 | 600002862100485965 | 10048596 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0050 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10048596 | FLANGE,BLIND;300MM,CL150,RF,CS,SH30,GALV | 5 | 0 | 5 | 0 | EA | 0 | 0 | 0 | 5 | EA | 01.10 - HU 101000000052151 TO AA02 OLS5307169 | Supply for Order 600002862, Item 5 cannot be changed 180078362 item 30 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 5 | 0 | EA |  |  | 102000000020020 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 5 |  | 2024-10-06 | 4900146921_2024_0005 | 2024-11-01 |  | 5000233767_2024_0003 | 0 | 2 | 0 | 90006343 | 5 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048596 | FLANGE,BLIND;300MM,CL150,RF,CS,SH30,GALV | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0410 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 5 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 410 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100492896000028620000216479ta00606 | 600002862100492892 | 10049289 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0060 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Shipped qty below requirement qty | 10049289 | FLANGE,BLIND;50MM,CL300,RF,SS316 | 2 | 1 | 0 | 2 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000093006 TO AA02 | Supply for Order 600002862, Item 6 cannot be changed 180083185 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 6 | 0 | EA | 101000000093006 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0005 | 2024-11-01 |  | 5000248569_2024_0003 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 1 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049289 | FLANGE,BLIND;50MM,CL300,RF,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0420/9016679_0420 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 6 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 420 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100492956000028620000216479ta081081 | 600002862100492951 | 10049295 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0810 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10049295 | FLANGE,BLIND;300MM,CL300,RF,SS316 | 1 | 0 | 1 | 0 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000076282 TO AA02 | Supply for Order 600002862, Item 81 cannot be changed 180078362 item 60 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 81 | 0 | EA |  |  | 102000000020026 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0011 | 2024-11-01 |  | 5000233767_2024_0006 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049295 | FLANGE,BLIND;300MM,CL300,RF,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0820 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 81 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 820 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100493106000028620000216479ta077077 | 600002862100493101 | 10049310 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0770 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10049310 | FLANGE,BLIND;80MM,CL600,RF,SS316 | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000093021 TO AA02 | Supply for Order 600002862, Item 77 cannot be changed 180083185 item 160 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 77 | 0 | EA | 101000000093021 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0031 | 2024-11-01 |  | 5000248569_2024_0016 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049310 | FLANGE,BLIND;80MM,CL600,RF,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0780 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 77 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 780 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100526706000028620000216479ta0110110 | 600002862100526701 | 10052670 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0110 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 |  | 30 | Maintenance Order material has been deleted | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 02.10 - ETA 17.12.24 PO 4500029495 AUS FITTINGS @AA02 | Supply for Order 600002862, Item 110 cannot be changed – 4500029495 already exists | Shipping notification from Vendor received | SP14 | Directs (Inventory) | 48 | AA02 | 5300006667 | 1020 | CPT | 7 | 1000018365 | 110 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500029495 | 10 | 1 | EA | 2024-10-28 |  | /180085785 |  |  | 07 | Execution | 0000216479 | 110 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-02-16 | IDPO-/018008578 | 1 | 35 | 0 | 35 | 2024-11-12 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-19 |  | 2024-11-14 |  |  | 2024-12-31 | 0 |  | 2024-10-10 |  | 2024-10-15 |  |  | 0 | 2 | 2 |  | 0 | 0 |  | 1 | 1 | 0 | X | L |  | 0 |  |  | 0 | 0 | /018008578 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 | L |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-20 | 30 |  | 2024-11-14 | 110 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1020 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100526706000028620000216479ta03100 | 600002862100526701 | 10052670 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0310 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 1 | 0 | 0 | 1 | EA | 0 | 1 | 0 | 1 | EA | UserCommentLink | Supply for Order 600002862, Item 137 cannot be changed 90024752 item 10 already exists | Material In-Transit on-01-Road | SP97 | Direct Multi-base | 48 | AA01 | 5300014053 | 150 | CPT | 48 | 1000023553 | 137 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500029495 | 20 | 1 | EA | 2024-11-29 |  | 180095811 | 180096725 | 90024752 | 07 | Execution | 0000216479 | 137 | 0 | EA |  |  | 101000000113674 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  | 2024-11-23 | Y | 1001 | 2024-08-13 | IDST-0180096725 | 0 | 108 | 57 | 68 | 2025-01-13 | 2024-11-17 | AA53 | 2024-11-22 |  |  | 2025-03-12 | 2025-01-15 | 2025-01-26 | 100000234894 | 1010 | 2024-12-31 | 1 | 5000286236_2024_0001 | 2024-11-22 | 4900177044_2024_0001 | 2024-11-20 |  |  | 0 | 2 | 2 | 90024752 | 0 | 1 | 180096725 | 2 | 0 | 0 |  | L | 4900177044 | 2024 | 5000286236 |  | 0 | 2024 | 180095811 | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90024752_0010 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-11-19 | 30 |  | 2025-01-15 | 0 |  | 0 |  | 24SDLN2C | MJ | 20003646 | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1270 |  | 5300014053 | 150 | 1 | EA | 1001 | AA02 | 2024-11-19 |  |  | 2024-11-21 | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100526756000028620000216479ta0050104 | 600002862100526751 | 10052675 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0050 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10052675 | SPADE BLIND,350MM,CL300,RF,A516-60 | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 104 cannot be changed 90020227 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 960 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020227 | 07 | Execution | 0000216479 | 104 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090020227_0030 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-10 |  | 2024-10-15 |  |  | 0 | 2 | 0 | 90020227 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052675 | SPADE BLIND,350MM,CL300,RF,A516-60 | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020227_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 104 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 960 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100526766000028620000216479ta00707 | 600002862100526764 | 10052676 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0070 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 4 | 4 | 0 | 4 | EA | 0 | 0 | 0 | 0 |  | 24.10 - ETA 05.12.24 PO 4500029844 MRC | Supply for Order 600002862, Item 7 cannot be changed 90006343 item 430 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006343 | 07 | Execution | 0000216479 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090006343_0430 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-29 |  | 2024-11-01 |  |  | 0 | 2 | 0 | 90006343 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0430 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 7 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 430 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100526766000028620000216479ta0190118 | 600002862100526764 | 10052676 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0190 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 4 | 0 | 4 | 0 | EA | 0 | 0 | 0 | 4 | EA | 03.10 - HU 101000000094431 to AA02 | Supply for Order 600002862, Item 118 cannot be changed 180078363 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078363 | 9015653 | 07 | Execution | 0000216479 | 118 | 0 | EA |  |  | 102000000020021 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000033541 | 1020 | 2024-12-31 | 4 |  | 2024-10-06 | 4900146945_2024_0001 | 2024-10-07 |  | 5000233793_2024_0001 | 0 | 2 | 0 | 90020228 | 4 | 0 | 180078363 | 2 | 0 | 0 | X | L | 4900146945 | 2024 |  | 5000233793 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015653_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 118 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 1100 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100526856000028620000216479ta075075 | 600002862100526851 | 10052685 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0750 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10052685 | SPADE BLIND,600MM,CL600,RF,LTCS | 1 | 0 | 1 | 0 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000060720 TO AA02 | Supply for Order 600002862, Item 75 cannot be changed 180078362 item 50 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 75 | 0 | EA |  |  | 102000000020029 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0009 | 2024-11-01 |  | 5000233767_2024_0005 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052685 | SPADE BLIND,600MM,CL600,RF,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0760 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 75 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 760 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100526966000028620000216479ta078078 | 600002862100526961 | 10052696 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0780 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10052696 | SPADE BLIND,150MM,CL150,CS,A285 GR.C | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000093390 TO AA02 | Supply for Order 600002862, Item 78 cannot be changed 180083185 item 170 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 78 | 0 | EA | 101000000093390 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0033 | 2024-11-01 |  | 5000248569_2024_0017 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052696 | SPADE BLIND,150MM,CL150,CS,A285 GR.C | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0790 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 78 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 790 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100530116000028620000216479ta89 | 600002862100530111 | 10053011 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 |  | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(11.03.2024) | 10053011 | SPADE BLIND,150MM,CL300,SS316 | 1 | 0 | 1 | 0 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000094436 TO AA02 | Supply for Order 600002862, Item 89 cannot be changed 180078362 item 100 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 89 | 0 | EA |  |  | 102000000020022 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0019 | 2024-11-01 |  | 5000233767_2024_0010 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10053011 | SPADE BLIND,150MM,CL300,SS316 | 2024-03-11 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0870 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 89 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 870 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100530146000028620000216479ta88 | 600002862100530141 | 10053014 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 |  | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(11.03.2024) | 10053014 | SPADE BLIND,300MM,CL300,SS316 | 1 | 0 | 1 | 0 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000094436 TO AA02 | Supply for Order 600002862, Item 88 cannot be changed 180078362 item 90 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 88 | 0 | EA |  |  | 102000000020022 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0017 | 2024-11-01 |  | 5000233767_2024_0009 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10053014 | SPADE BLIND,300MM,CL300,SS316 | 2024-03-11 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0860 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 88 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 860 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100530936000028620000216479ta00808 | 600002862100530931 | 10053093 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0080 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10053093 | SPADE BLIND,150MM,CL300,SS,TP316L | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 16.10 - 180082367 4500005381, 103 ERRORS | Supply for Order 600002862, Item 8 cannot be changed 180085320 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 8 | 0 | EA |  |  | 102000000021853 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0005 | 2024-11-01 |  | 5000255235_2024_0003 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10053093 | SPADE BLIND,150MM,CL300,SS,TP316L | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0440 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 8 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 440 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582016000028620000216479ta00909 | 6000028621005820116 | 10058201 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0090 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058201 | STUDBOLT;0.625" X 100MM,A193 B8M CL2 | 16 | 0 | 0 | 16 | EA | 24 | 0 | 120 | 16 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 9 cannot be changed 180017143 item 310 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 9 | 0 | EA | 102000000004373 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 16 |  | 2024-04-11 | 4900045283_2024_0061 | 2024-11-01 |  | 5000058191_2024_0031 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058201 | STUDBOLT;0.625" X 100MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0450 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 9 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 450 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582026000028620000216479ta010010 | 6000028621005820220 | 10058202 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0100 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10058202 | STUDBOLT;0.625" X 110MM,A193 B8M CL2 | 20 | 0 | 20 | 0 | EA | 21 | 0 | 0 | 20 | EA | 21.09 - MW2R11C02G @ KSF | Supply for Order 600002862, Item 10 cannot be changed 180017143 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 10 | 0 | EA | 102000000003646 | 102000000003612 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 20 |  | 2024-04-11 | 4900045283_2024_0001 | 2024-11-01 |  | 5000058191_2024_0001 | 0 | 2 | 0 | 90006343 | 20 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058202 | STUDBOLT;0.625" X 110MM,A193 B8M CL2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 10 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 20 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582036000028620000216479ta011011 | 600002862100582038 | 10058203 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0110 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 8 | 0 | 0 | 8 | EA | 10 | 8 | 8 | 5 | EA | 01.10 - HU 101000000092978, 93001 TO AA02 | Supply for Order 600002862, Item 11 cannot be changed 180083185 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 11 | 0 | EA | 101000000092978 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 8 |  | 2024-10-18 | 4900154759_2024_0007 | 2024-11-01 |  | 5000248569_2024_0004 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0460 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 11 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 460 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582036000028620000216479ta011011 | 600002862100582038 | 10058203 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0110 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 8 | 0 | 0 | 8 | EA | 10 | 8 | 8 | 3 | EA | 01.10 - HU 101000000092978, 93001 TO AA02 | Supply for Order 600002862, Item 11 cannot be changed 180083185 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 11 | 0 | EA | 101000000093001 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 8 |  | 2024-10-18 | 4900154759_2024_0007 | 2024-11-01 |  | 5000248569_2024_0004 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0460 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 11 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 460 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582056000028620000216479ta012012 | 600002862100582058 | 10058205 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0120 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10058205 | STUDBOLT;0.625" X 130MM,A193 B8M CL2 | 8 | 0 | 8 | 0 | EA | 44 | 0 | 0 | 8 | EA | 22.09 - IN GREY TUB / MW2R11C03G @ KSF | Supply for Order 600002862, Item 12 cannot be changed 180017143 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 12 | 0 | EA | 102000000003646 | 102000000003613 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0003 | 2024-11-01 |  | 5000058191_2024_0002 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058205 | STUDBOLT;0.625" X 130MM,A193 B8M CL2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 12 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 30 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582226000028620000216479ta013013 | 6000028621005822228 | 10058222 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0130 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 28 | 15 | 13 | 15 | EA | 4 | 0 | 3 | 3 | EA | 03.10 - Del 90009764/90009765 15-05-10-03CB @ AA01 | Supply for Order 600002862, Item 13 cannot be changed 180017143 item 320 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085779 | 9017334 | 07 | Execution | 0000216479 | 13 | 0 | EA |  |  | 101000000100284 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037409 | 1020 | 2024-12-31 | 16 |  | 2024-10-25 | 4900159071_2024_0001/4900045283_2024_0063 | 2024-11-01 |  | 5000256709_2024_0001/5000058191_2024_0032 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180085779/180017143 | 2 | 0 | 0 | X | L | 4900159071 | 2024 |  | 5000256709 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0470/9017334_0470/9002109_0470 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 13 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 470 |  |  | 0 | 28 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582226000028620000216479ta013013 | 6000028621005822228 | 10058222 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0130 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 28 | 15 | 13 | 15 | EA | 4 | 0 | 3 | 13 | EA | 03.10 - Del 90009764/90009765 15-05-10-03CB @ AA01 | Supply for Order 600002862, Item 13 cannot be changed 180017143 item 320 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085779 | 9017334 | 07 | Execution | 0000216479 | 13 | 0 | EA | 102000000004373 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037409 | 1020 | 2024-12-31 | 16 |  | 2024-10-25 | 4900159071_2024_0001/4900045283_2024_0063 | 2024-11-01 |  | 5000256709_2024_0001/5000058191_2024_0032 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180085779/180017143 | 2 | 0 | 0 | X | L | 4900159071 | 2024 |  | 5000256709 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0470/9017334_0470/9002109_0470 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 13 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 470 |  |  | 0 | 28 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582496000028620000216479ta014014 | 6000028621005824912 | 10058249 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0140 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 12 | 8 | 4 | 8 | EA | 4 | 0 | 8 | 4 | EA | 01.10 - HU 101000000094405 TO AA02 | Supply for Order 600002862, Item 14 cannot be changed 180083185 item 50 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085865 | 9017454 | 07 | Execution | 0000216479 | 14 | 0 | EA |  |  | 102000000022071 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037615 | 1020 | 2024-12-31 | 12 |  | 2024-10-25 | 4900159231_2024_0001/4900154759_2024_0009 | 2024-11-01 |  | 5000257049_2024_0001/5000248569_2024_0005 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180085865/180083185 | 2 | 0 | 0 | X | L | 4900159231 | 2024 |  | 5000257049 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017454_0480/9016679_0480 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 14 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 480 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582496000028620000216479ta014014 | 6000028621005824912 | 10058249 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0140 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 12 | 8 | 4 | 8 | EA | 4 | 0 | 8 | 8 | EA | 01.10 - HU 101000000094405 TO AA02 | Supply for Order 600002862, Item 14 cannot be changed 180083185 item 50 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085865 | 9017454 | 07 | Execution | 0000216479 | 14 | 0 | EA | 101000000094405 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037615 | 1020 | 2024-12-31 | 12 |  | 2024-10-25 | 4900159231_2024_0001/4900154759_2024_0009 | 2024-11-01 |  | 5000257049_2024_0001/5000248569_2024_0005 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180085865/180083185 | 2 | 0 | 0 | X | L | 4900159231 | 2024 |  | 5000257049 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017454_0480/9016679_0480 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 14 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 480 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582526000028620000216479ta015015 | 6000028621005825216 | 10058252 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0150 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 16 | 8 | 8 | 8 | EA | 0 | 0 | 8 | 8 | EA | 03.10 - Del 80018277/000010 for picking | Supply for Order 600002862, Item 15 cannot be changed 180085320 item 40 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085865 | 9017454 | 07 | Execution | 0000216479 | 15 | 0 | EA |  |  | 102000000022070 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037615 | 1020 | 2024-12-31 | 16 |  | 2024-10-25 | 4900159231_2024_0003/4900158497_2024_0007 | 2024-11-01 |  | 5000257049_2024_0002/5000255235_2024_0004 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180085865/180085320 | 2 | 0 | 0 | X | L | 4900159231 | 2024 |  | 5000257049 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017454_0490/9017444_0490 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 15 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 490 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582526000028620000216479ta015015 | 6000028621005825216 | 10058252 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0150 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 16 | 8 | 8 | 8 | EA | 0 | 0 | 8 | 8 | EA | 03.10 - Del 80018277/000010 for picking | Supply for Order 600002862, Item 15 cannot be changed 180085320 item 40 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085865 | 9017454 | 07 | Execution | 0000216479 | 15 | 0 | EA | 101000000097561 |  | 102000000021787 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037615 | 1020 | 2024-12-31 | 16 |  | 2024-10-25 | 4900159231_2024_0003/4900158497_2024_0007 | 2024-11-01 |  | 5000257049_2024_0002/5000255235_2024_0004 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180085865/180085320 | 2 | 0 | 0 | X | L | 4900159231 | 2024 |  | 5000257049 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017454_0490/9017444_0490 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 15 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 490 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100582626000028620000216479ta016016 | 6000028621005826216 | 10058262 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0160 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10058262 | BLT STUD:1.125in,190mm,316 SS,2,UN HEAVY | 16 | 0 | 16 | 0 | EA | 4 | 0 | 0 | 16 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 16 cannot be changed 180017143 item 30 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 16 | 0 | EA | 102000000003619 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 16 |  | 2024-04-11 | 4900045283_2024_0005 | 2024-11-01 |  | 5000058191_2024_0003 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058262 | BLT STUD:1.125in,190mm,316 SS,2,UN HEAVY | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0040 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 16 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 40 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100588286000028620000216479ta073073 | 6000028621005882824 | 10058828 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0730 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 24 | 22 | 2 | 22 | EA | 2 | 0 | 26 | 2 | EA | 01.10 - HU 101000000094101 - 08 TO AA02 | Supply for Order 600002862, Item 73 cannot be changed 180083185 item 150 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 73 | 0 | EA | 102000000018977 |  | 107000000000076 |  |  |  | STATIC-CAGE | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 24 |  | 2024-10-18 | 4900154759_2024_0029/4900143400_2024_0001/4900045283_2024_0069 | 2024-11-01 |  | 5000248569_2024_0015/5000227725_2024_0001/5000058191_2024_0035 | 0 | 2 | 0 | 90006343 | 24 | 0 | 180076528/180083185/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0740/9014976_0740/9002109_0740 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 73 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 740 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100588286000028620000216479ta073073 | 6000028621005882824 | 10058828 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0730 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 24 | 22 | 2 | 22 | EA | 2 | 0 | 26 | 2 | EA | 01.10 - HU 101000000094101 - 08 TO AA02 | Supply for Order 600002862, Item 73 cannot be changed 180083185 item 150 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 73 | 0 | EA | 102000000003618 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 24 |  | 2024-10-18 | 4900154759_2024_0029/4900143400_2024_0001/4900045283_2024_0069 | 2024-11-01 |  | 5000248569_2024_0015/5000227725_2024_0001/5000058191_2024_0035 | 0 | 2 | 0 | 90006343 | 24 | 0 | 180076528/180083185/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0740/9014976_0740/9002109_0740 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 73 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 740 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100588286000028620000216479ta073073 | 6000028621005882824 | 10058828 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0730 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 24 | 22 | 2 | 22 | EA | 2 | 0 | 26 | 20 | EA | 01.10 - HU 101000000094101 - 08 TO AA02 | Supply for Order 600002862, Item 73 cannot be changed 180083185 item 150 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 73 | 0 | EA | 102000000019834 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 24 |  | 2024-10-18 | 4900154759_2024_0029/4900143400_2024_0001/4900045283_2024_0069 | 2024-11-01 |  | 5000248569_2024_0015/5000227725_2024_0001/5000058191_2024_0035 | 0 | 2 | 0 | 90006343 | 24 | 0 | 180076528/180083185/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0740/9014976_0740/9002109_0740 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 73 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 740 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100599686000028620000216479ta017017 | 600002862100599682 | 10059968 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0170 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10059968 | GASKET;CNAF,50MM,CL150,TANG INTN,1.6MM | 2 | 0 | 2 | 0 | EA | 4 | 0 | 0 | 2 | EA | 22.09 - IN GREY TUB / MW2R05F11H @ KSF | Supply for Order 600002862, Item 17 cannot be changed 180017143 item 40 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 17 | 0 | EA | 102000000003646 | 102000000003620 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0007 | 2024-11-01 |  | 5000058191_2024_0004 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059968 | GASKET;CNAF,50MM,CL150,TANG INTN,1.6MM | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0050 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 17 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100599716000028620000216479ta018018 | 600002862100599711 | 10059971 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0180 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10059971 | GASKET;CNAF,150MM,CL150,TANG INTN,1.6MM | 1 | 1 | 0 | 1 | EA | 1 | 0 | 2 | 0 |  | 01.10 - HU 101000000092373 TO AA02 | Supply for Order 600002862, Item 18 cannot be changed 90006343 item 500 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006343 | 07 | Execution | 0000216479 | 18 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090006343_0500 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-29 |  | 2024-11-01 |  |  | 0 | 2 | 0 | 90006343 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059971 | GASKET;CNAF,150MM,CL150,TANG INTN,1.6MM | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0500 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 18 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 500 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100599726000028620000216479ta019019 | 600002862100599728 | 10059972 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0190 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10059972 | GASKET;CNAF,200MM,CL150,TANG INTN,1.5MM | 8 | 0 | 8 | 0 | EA | 4 | 0 | 0 | 8 | EA | X1 LOOSE | Supply for Order 600002862, Item 19 cannot be changed 180017143 item 50 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 19 | 0 | EA | 102000000003665 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0009 | 2024-11-01 |  | 5000058191_2024_0005 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059972 | GASKET;CNAF,200MM,CL150,TANG INTN,1.5MM | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 19 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 60 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100608856000028620000216479ta020020 | 600002862100608852 | 10060885 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0200 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 | 2 | 0 | 0 | 2 | EA | 106 | 1 | 102 | 2 | EA | 03.10 - KSF-PACK-REV-SML for picking | Supply for Order 600002862, Item 20 cannot be changed 180085320 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 20 | 0 | EA |  |  | 102000000021841 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0009 | 2024-11-01 |  | 5000255235_2024_0005 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0510 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 20 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 510 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100608866000028620000216479ta021021 | 600002862100608864 | 10060886 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0210 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 4 | 0 | 4 | 0 | EA | 36 | 10 | 60 | 4 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 21 cannot be changed 180059148 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180059148 | 9010626 | 07 | Execution | 0000216479 | 21 | 0 | EA | 102000000013914 |  | 102000000005501 |  |  |  | LP-SD-14 | WorkPackLink | KSF-KGP P07P08 SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000024047 | 1020 | 2024-12-31 | 4 |  | 2024-08-19 | 4900113231_2024_0001 | 2024-11-01 |  | 5000213867_2024_0001 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180059148 | 2 | 0 | 0 | X | L | 4900113231 | 2024 |  | 5000213867 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9010626_0520 |  |  | LN2 |  | A3 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 21 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 520 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100608876000028620000216479ta022022 | 600002862100608872 | 10060887 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0220 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 2 | 0 | 0 | 2 | EA | 35 | 11 | 86 | 2 | EA | 21.09 - MW2R03C03J @ KSF | Supply for Order 600002862, Item 22 cannot be changed 180085320 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 22 | 0 | EA |  |  | 102000000021788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0001 | 2024-11-01 |  | 5000255235_2024_0001 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0070 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 22 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 70 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100608886000028620000216479ta023023 | 600002862100608884 | 10060888 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0230 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10060888 | GASKET;SWCI,150MM,CL150,316L/GR/316 | 4 | 0 | 0 | 4 | EA | 0 | 0 | 12 | 4 | EA | 01.10 - HU 101000000093005 TO AA02 | Supply for Order 600002862, Item 23 cannot be changed 180083185 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 23 | 0 | EA | 101000000093005 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 4 |  | 2024-10-18 | 4900154759_2024_0011 | 2024-11-01 |  | 5000248569_2024_0006 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET;SWCI,150MM,CL150,316L/GR/316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0530 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 23 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 530 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100608926000028620000216479ta024024 | 600002862100608922 | 10060892 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0240 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060892 | GASKET;SWCI,350MM,CL150,316L/GR/316 | 2 | 0 | 0 | 2 | EA | 4 | 0 | 7 | 2 | EA | 03.10 - SW3R03E02B @ AA02 | Supply for Order 600002862, Item 24 cannot be changed 180085320 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 24 | 0 | EA | 102000000021786 |  | 107000000000076 |  |  |  | STATIC-CAGE | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0003 | 2024-11-01 |  | 5000255235_2024_0002 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060892 | GASKET;SWCI,350MM,CL150,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0080 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 24 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100608946000028620000216479ta025025 | 600002862100608942 | 10060894 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0250 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060894 | GASKET;SWCI,450MM,CL150,316L/GR/316 | 2 | 0 | 0 | 2 | EA | 10 | 0 | 3 | 2 | EA | 22.09 - X1 LOOSE / MW2R04J02B @ KSF | Supply for Order 600002862, Item 25 cannot be changed 180017143 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 25 | 0 | EA | 102000000003633 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0011 | 2024-11-01 |  | 5000058191_2024_0006 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060894 | GASKET;SWCI,450MM,CL150,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0090 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 25 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 90 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609016000028620000216479ta026026 | 600002862100609012 | 10060901 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-30 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0260 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060901 | GASKET;SWCI,100MM,CL300,SS316L/GR/316 | 2 | 0 | 0 | 2 | EA | 38 | 6 | 38 | 2 | EA | 21.09 - MW2R03A02A @ KSF | Supply for Order 600002862, Item 26 cannot be changed 180017143 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 26 | 0 | EA | 102000000003646 | 102000000003635 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0013 | 2024-11-01 |  | 5000058191_2024_0007 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060901 | GASKET;SWCI,100MM,CL300,SS316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0100 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 26 |  | 0 |  | 24SDLN2C | MJ | 1000001236 |  | 1000214854 | S002 | 30 | 30 | 5300006667 | 100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-30 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609026000028620000216479ta027027 | 600002862100609024 | 10060902 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0270 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10060902 | GASKET;SWCI,150MM,CL300,316L/GR/316 | 4 | 0 | 4 | 0 | EA | 4 | 12 | 2 | 4 | EA | 22.09 - IN GREY TUB / MW2R04F02A @ KSF | Supply for Order 600002862, Item 27 cannot be changed 180017143 item 330 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 27 | 0 | EA | 102000000003646 | 102000000003684 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045283_2024_0065 | 2024-11-01 |  | 5000058191_2024_0033 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET;SWCI,150MM,CL300,316L/GR/316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0540 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 27 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 540 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609046000028620000216479ta028028 | 600002862100609042 | 10060904 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0280 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060904 | GASKET;SWCI,250MM,CL300,316L/GR/316 | 2 | 0 | 0 | 2 | EA | 13 | 8 | 13 | 2 | EA | 22.09 - X1 LOOSE / MW2R03A03E @ KSF | Supply for Order 600002862, Item 28 cannot be changed 180017143 item 80 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 28 | 0 | EA | 102000000003632 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0015 | 2024-11-01 |  | 5000058191_2024_0008 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060904 | GASKET;SWCI,250MM,CL300,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0110 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 28 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 110 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609056000028620000216479ta029029 | 600002862100609051 | 10060905 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0290 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060905 | GASKET;SWCI,300MM,CL300,316L/GR/316 | 1 | 0 | 0 | 1 | EA | 3 | 0 | 10 | 1 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 29 cannot be changed 180017143 item 90 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 29 | 0 | EA | 102000000003625 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 1 |  | 2024-04-11 | 4900045283_2024_0017 | 2024-11-01 |  | 5000058191_2024_0009 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060905 | GASKET;SWCI,300MM,CL300,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0120 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 29 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609066000028620000216479ta0900130 | 600002862100609064 | 10060906 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0900 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(04.10.2024) | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 4 | 0 | 4 | 0 | EA | 11 | 0 | 8 | 4 | EA | UserCommentLink | Supply for Order 600002862, Item 130 cannot be changed 180083292 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083292 | 90021285 | 07 | Execution | 0000216479 | 130 | 0 | EA | 102000000021301 |  | 107000000000076 |  |  |  | STATIC-CAGE | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-10-21 |  |  | 2024-10-15 |  |  | 100000035929 | 1020 | 2024-12-31 | 4 |  | 2024-10-18 | 4900154888_2024_0001 | 2024-10-15 |  | 5000248724_2024_0001 | 0 | 2 | 0 | 90021285 | 4 | 0 | 180083292 | 2 | 0 | 0 | X | L | 4900154888 | 2024 |  | 5000248724 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 2024-10-04 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90021285_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 130 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1210 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609066000028620000216479ta030030 | 600002862100609064 | 10060906 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0300 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 4 | 0 | 0 | 4 | EA | 11 | 0 | 8 | 4 | EA | 22.09 - X1 LOOSE / MW2R04J03D @ KSF | Supply for Order 600002862, Item 30 cannot be changed 180017143 item 100 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 30 | 1 | EA | 102000000003634 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045283_2024_0019 | 2024-11-01 |  | 5000058191_2024_0010 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180017143 | 1 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0130 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 30 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 130 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609076000028620000216479ta031031 | 600002862100609078 | 10060907 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0310 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060907 | GASKET;SWCI,400MM,CL300,SS316L/GR/316 | 8 | 0 | 0 | 8 | EA | 7 | 0 | 12 | 8 | EA | 22.09 - X1 LOOSE / MW2R05E07D @ KSF | Supply for Order 600002862, Item 31 cannot be changed 180017143 item 110 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 31 | 0 | EA | 102000000003637 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0021 | 2024-11-01 |  | 5000058191_2024_0011 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060907 | GASKET;SWCI,400MM,CL300,SS316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0140 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 31 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 140 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609196000028620000216479ta032032 | 6000028621006091912 | 10060919 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0320 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 12 | 0 | 0 | 12 | EA | 223 | 20 | 534 | 12 | EA | 22.09 - IN GREY TUB / MW2R03B03A @ KSF | Supply for Order 600002862, Item 32 cannot be changed 180017143 item 120 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 32 | 0 | EA | 102000000003646 | 102000000003636 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 12 |  | 2024-04-11 | 4900045283_2024_0023 | 2024-11-01 |  | 5000058191_2024_0012 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0150 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 32 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 150 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609206000028620000216479ta033033 | 600002862100609204 | 10060920 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-01 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10060920 | GASKET:RF,80mm,4.5mm,316L,CL300,SWCI,GR | 4 | 0 | 0 | 4 | EA | 0 | 3 | 8 | 4 | EA | 21.09 - 10-16-11-02B @ PDC X 3 | Supply for Order 600002862, Item 33 cannot be changed 180017143 item 130 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 33 | 1 | EA | 102000000003646 | 102000000003622 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 0 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045283_2024_0025 | 2024-11-01 |  | 5000058191_2024_0013 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180017143 | 1 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060920 | GASKET:RF,80mm,4.5mm,316L,CL300,SWCI,GR | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0160 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 33 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 74 | 74 | 5300006667 | 160 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609326000028620000216479ta034034 | 600002862100609324 | 10060932 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0340 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 4 | 0 | 0 | 4 | EA | 102 | 0 | 83 | 4 | EA | 22.09 - IN GREY TUB / MW2R03A02C @ KSF | Supply for Order 600002862, Item 34 cannot be changed 180017143 item 140 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 34 | 0 | EA | 102000000003646 | 102000000003624 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045283_2024_0027 | 2024-11-01 |  | 5000058191_2024_0014 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0170 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 34 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 170 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609326000028620000216479ta0290134 | 600002862100609326 | 10060932 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-22 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0290 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.10.2024) | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 6 | 6 | 0 | 6 | EA | 102 | 0 | 83 | 0 |  | UserCommentLink | Supply for Order 600002862, Item 134 cannot be changed 90025334 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025334 | 07 | Execution | 0000216479 | 134 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090025334_0010 | 0 | 5 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-27 |  |  |  |  | 2024-12-31 | 0 |  | 2024-11-22 |  | 2024-11-27 |  |  | 0 | 2 | 0 | 90025334 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2024-10-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90025334_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 134 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1240 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-11-22 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
100609346000028620000216479ta035035 | 600002862100609342 | 10060934 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0350 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 2 | 0 | 2 | 0 | EA | 5 | 8 | 0 | 2 | EA | 22.09 - IN GREY TUB / MW2R04J02D @KSF | Supply for Order 600002862, Item 35 cannot be changed 180017143 item 150 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 35 | 0 | EA | 102000000003646 | 102000000003629 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0029 | 2024-11-01 |  | 5000058191_2024_0015 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0180 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 35 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 180 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609396000028620000216479ta071071 | 6000028621006093912 | 10060939 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0710 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060939 | GASKET;SWCI,450MM,CL600,316L/GR/316 | 12 | 0 | 12 | 0 | EA | 6 | 0 | 0 | 12 | EA | 22.09 - X4 FLAT PACKS / 4 SOH @ KSF /180071538 75KG 18.09.24 PO 4500024711 | Supply for Order 600002862, Item 71 cannot be changed 180017143 item 290 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 71 | 0 | EA | 102000000003628 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 12 |  | 2024-04-11 | 4900045283_2024_0057 | 2024-11-01 |  | 5000058191_2024_0029 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060939 | GASKET;SWCI,450MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0330 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 71 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 330 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609416000028620000216479ta072072 | 600002862100609416 | 10060941 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0720 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 6 | 0 | 0 | 6 | EA | 29 | 0 | 9 | 6 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 72 cannot be changed 180017143 item 300 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 72 | 0 | EA | 102000000003627 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 6 |  | 2024-04-11 | 4900045283_2024_0059 | 2024-11-01 |  | 5000058191_2024_0030 | 0 | 2 | 0 | 90006343 | 6 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0340 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 72 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 340 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100609416000028620000216479ta036036 | 600002862100609411 | 10060941 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0360 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 1 | 0 | 0 | 1 | EA | 29 | 0 | 9 | 1 | EA | 21.09 - MW2R04H04A @ KSF / X1 FLAT PACK | Supply for Order 600002862, Item 36 cannot be changed 180017143 item 160 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 36 | 0 | EA | 102000000003626 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 1 |  | 2024-04-11 | 4900045283_2024_0031 | 2024-11-01 |  | 5000058191_2024_0016 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0190 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 36 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100610036000028620000216479ta037037 | 600002862100610032 | 10061003 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0370 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10061003 | GASKET;SWCI,1050MM,CL150,316L/GR/316 | 2 | 0 | 2 | 0 | EA | 4 | 0 | 0 | 2 | EA | X1 PALLET | Supply for Order 600002862, Item 37 cannot be changed 180017143 item 170 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 37 | 0 | EA |  |  | 102000000003630 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0033 | 2024-11-01 |  | 5000058191_2024_0017 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061003 | GASKET;SWCI,1050MM,CL150,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0200 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 37 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 200 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
100629856000028620000216479taX128 | 600002862100629852 | 10062985 |  | 24SDLN2C | Released | 2024-02-29 | 2025-03-17 | 2025-03-17 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | X | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 |  | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(03.10.2024) | 10062985 | AIR,MEDICAL,DRY,COMPRESSED,SIZE G CYL | 2 | 0 | 0 | 2 | CYL | 0 | 0 | 2 | 2 | CYL | 14.10 - ETA 18.10.24 PO 4500031439 BOC | Supply for Order 600002862, Item 128 cannot be changed 9016849 item 40 already exists | Material work-packed @AA53 | SP14 | Directs (Inventory) | 2 | AA02 | 5300006667 | 1190 | CPT | 14 | 1000020500 | 128 | 30000395 | BOC LIMITED | 4500031439 | 10 | 2 | CYL | 2024-10-18 |  | 180083823/180083823/ | 180083825 | 9016849 | 07 | Execution | 0000216479 | 128 | 0 | CYL |  |  | 102000000021412 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000249608_2024 | 0 | 5 | 0 | 0 | 2025-03-15 | 2025-03-20 | AA53 | 2024-11-22 |  |  | 2025-03-22 |  | 2025-03-17 | 100000036129 | 1020 | 2024-12-31 | 2 | 5000249607_2024_0001 | 2024-10-19 | 4900155774_2024_0001 | 2024-10-19 |  | 5000249608_2024_0001 | 0 | 2 | 2 | 90022091 | 2 | 2 | 180083825 | 2 | 0 | 0 | X | L | 4900155774 | 2024 | 5000249607 | 5000249608 | 2024 | 2024 | 180083823 | 2025-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062985 | AIR,MEDICAL,DRY,COMPRESSED,SIZE G CYL | 2024-10-03 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9016849_0040 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-08 | 30 |  | 2025-03-17 | 128 |  | 31522 |  | 24SDLN2C | MJ | 1000003773 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1190 |  |  | 0 | 2 | CYL | 2001 | AA02 | 2025-03-17 |  |  | 2024-10-24 | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023236000028620000216479ta070070 | 600002862102023236 | 10202323 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0700 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 6 | 0 | 0 | 6 | M | 0 | 0 | 24 | 6 | M | 14.10 - HU 101000000056226 TO AA02 | Supply for Order 600002862, Item 70 cannot be changed 180082338 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  | 180082338 | 9016520 | 07 | Execution | 0000216479 | 70 | 0 | M |  |  | 101000000056226 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000245960_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035353 | 1020 | 2024-12-31 | 6 |  | 2024-10-16 | 4900153435_2024_0001 | 2024-11-01 |  | 5000245960_2024_0001 | 0 | 2 | 0 | 90006343 | 6 | 0 | 180082338 | 2 | 0 | 0 | X | L | 4900153435 | 2024 |  | 5000245960 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016520_0320 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 70 |  | 0 |  | 24SDLN2C | MJ | 1000003713 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 320 |  |  | 0 | 6 | M | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-19 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102023236000028620000216479ta0210120 | 600002862102023236 | 10202323 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0210 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 6 | 0 | 0 | 6 | M | 0 | 0 | 24 | 6 | M | 14.10 - HU 101000000099762 TO AA02 | Supply for Order 600002862, Item 120 cannot be changed 180082339 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1120 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  | 180082339 | 9016521 | 07 | Execution | 0000216479 | 120 | 0 | M |  |  | 101000000099762 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000245932_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000035354 | 1020 | 2024-12-31 | 6 |  | 2024-10-16 | 4900153423_2024_0001 | 2024-10-07 |  | 5000245932_2024_0001 | 0 | 2 | 0 | 90020228 | 6 | 0 | 180082339 | 2 | 0 | 0 | X | L | 4900153423 | 2024 |  | 5000245932 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9016521_0040 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 120 |  | 0 |  | 24SDLN2C | MJ | 1000003724 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1120 |  |  | 0 | 6 | M | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-19 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023296000028620000216479ta0330139 | 6000028621020232910 | 10202329 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | 0 | 0 | 10 | EA | 0 | 0 | 11 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 0 | EA |  |  | 101000000114001 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 139 |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023296000028620000216479ta0330139 | 6000028621020232910 | 10202329 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | 0 | 0 | 10 | EA | 0 | 0 | 11 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 0 | EA |  |  | 101000000114000 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 139 |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023296000028620000216479ta0330139 | 6000028621020232910 | 10202329 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | 0 | 0 | 10 | EA | 0 | 0 | 11 | 1 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 0 | EA |  |  | 101000000113698 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 139 |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023296000028620000216479ta0330139 | 6000028621020232910 | 10202329 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | 0 | 0 | 10 | EA | 0 | 0 | 11 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 0 | EA |  |  | 101000000113971 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 139 |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023296000028620000216479ta0330139 | 6000028621020232910 | 10202329 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | 0 | 0 | 10 | EA | 0 | 0 | 11 | 1 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 0 | EA |  |  | 101000000113529 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 139 |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023296000028620000216479ta0330139 | 6000028621020232910 | 10202329 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | 0 | 0 | 10 | EA | 0 | 0 | 11 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 0 | EA |  |  | 101000000113788 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 139 |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023346000028620000216479ta0120111 | 600002862102023341 | 10202334 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0120 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10202334 | FLANGE,BLIND;350MM,CL150,RF,CS,A105N | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 05.10 - HU 101000000096902 to AA02 | Supply for Order 600002862, Item 111 cannot be changed 180078491 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1030 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078491 | 9015168 | 07 | Execution | 0000216479 | 111 | 0 | EA | 101000000096802 |  | 107000000000418 |  |  |  | P07YRDBY11 | WorkPackLink | P07YRDBY11 | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000234665_2024 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  | 100000033635 | 1020 | 2024-12-31 | 1 |  | 2024-10-07 | 4900147491_2024_0005 | 2024-10-15 |  | 5000234665_2024_0001 | 0 | 2 | 0 | 90020227 | 1 | 0 | 180078491 | 2 | 0 | 0 | X | L | 4900147491 | 2024 |  | 5000234665 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202334 | FLANGE,BLIND;350MM,CL150,RF,CS,A105N | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015168_0090 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 111 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 1030 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023436000028620000216479ta0180117 | 600002862102023434 | 10202343 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0180 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 4 | 0 | 0 | 4 | EA | 0 | 0 | 8 | 4 | EA | 05.10 - Del 80019284 for picking | Supply for Order 600002862, Item 117 cannot be changed 180085321 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1090 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085321 | 9017445 | 07 | Execution | 0000216479 | 117 | 0 | EA | 101000000097682 |  | 102000000021840 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255250_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000036571 | 1020 | 2024-12-31 | 4 |  | 2024-10-24 | 4900158458_2024_0001 | 2024-10-07 |  | 5000255250_2024_0001 | 0 | 2 | 0 | 90020228 | 4 | 0 | 180085321 | 2 | 0 | 0 | X | L | 4900158458 | 2024 |  | 5000255250 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017445_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 117 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1090 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102023436000028620000216479ta068068 | 600002862102023434 | 10202343 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0680 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 4 | 0 | 0 | 4 | EA | 0 | 0 | 8 | 4 | EA | 03.10 - GR ZONE @ AA02 | Supply for Order 600002862, Item 68 cannot be changed 180083185 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 68 | 0 | EA | 101000000094149 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 4 |  | 2024-10-18 | 4900154759_2024_0001 | 2024-11-01 |  | 5000248569_2024_0001 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0350 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 68 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 350 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102023526000028620000216479ta076076 | 600002862102023521 | 10202352 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0760 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 24.10 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 76 cannot be changed 90006343 item 770 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006343 | 07 | Execution | 0000216479 | 76 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090006343_0770 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-29 |  | 2024-11-01 |  |  | 0 | 2 | 0 | 90006343 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0770 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 76 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 770 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102023526000028620000216479ta0090108 | 600002862102023521 | 10202352 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0090 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 1 | 0 | 1 | 0 | EA | 0 | 0 | 0 | 1 | EA | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 108 cannot be changed 180078364 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1000 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078364 | 9015654 | 07 | Execution | 0000216479 | 108 | 0 | EA |  |  | 102000000020025 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  | 100000033542 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146886_2024_0001 | 2024-10-15 |  | 5000233769_2024_0001 | 0 | 2 | 0 | 90020227 | 1 | 0 | 180078364 | 2 | 0 | 0 | X | L | 4900146886 | 2024 |  | 5000233769 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015654_0070 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 108 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 1000 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102186136000028620000216479ta038038 | 6000028621021861312 | 10218613 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0380 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218613 | STUDBOLT;0.625" X 110MM,L7,ZN+XYLAN | 12 | 0 | 0 | 12 | EA | 44 | 0 | 21 | 12 | EA | 22.09 - X2 boxes / SOH @ AA01 | Supply for Order 600002862, Item 38 cannot be changed 180017143 item 180 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 38 | 0 | EA | 102000000003638 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 12 |  | 2024-04-11 | 4900045283_2024_0035 | 2024-11-01 |  | 5000058191_2024_0018 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218613 | STUDBOLT;0.625" X 110MM,L7,ZN+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0210 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 38 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 210 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186176000028620000216479ta039039 | 6000028621021861748 | 10218617 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0390 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218617 | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN | 48 | 0 | 48 | 0 | EA | 4 | 0 | 40 | 48 | EA | 22.09 - X1 BOX / SOH @ PDC | Supply for Order 600002862, Item 39 cannot be changed 180017143 item 190 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 39 | 0 | EA | 102000000003639 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 48 |  | 2024-04-11 | 4900045283_2024_0037 | 2024-11-01 |  | 5000058191_2024_0019 | 0 | 2 | 0 | 90006343 | 48 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218617 | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0220 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 39 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 220 |  |  | 0 | 48 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186256000028620000216479ta040040 | 600002862102186258 | 10218625 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0400 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218625 | STUDBOLT;0.750"X110MM,L7,CAD+XYLAN | 8 | 0 | 0 | 8 | EA | 72 | 8 | 8 | 8 | EA | 22.09 - X1 BOX / MW3R15B08B @ KSF | Supply for Order 600002862, Item 40 cannot be changed 180017143 item 200 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 40 | 0 | EA | 102000000003640 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0039 | 2024-11-01 |  | 5000058191_2024_0020 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218625 | STUDBOLT;0.750"X110MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0230 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 40 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 230 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186266000028620000216479ta041041 | 6000028621021862648 | 10218626 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0410 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218626 | STUDBOLT;0.750"X120MM,L7,CAD+XYLAN | 48 | 0 | 0 | 48 | EA | 100 | 12 | 20 | 48 | EA | 22.09 - X3 BOX / 24 Stocked @ PDC, 12 @ KSF | Supply for Order 600002862, Item 41 cannot be changed 180017143 item 210 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 41 | 0 | EA | 102000000003641 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 48 |  | 2024-04-11 | 4900045283_2024_0041 | 2024-11-01 |  | 5000058191_2024_0021 | 0 | 2 | 0 | 90006343 | 48 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218626 | STUDBOLT;0.750"X120MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0240 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 41 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 240 |  |  | 0 | 48 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186276000028620000216479ta042042 | 6000028621021862732 | 10218627 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0420 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218627 | STUDBOLT;0.750"X130MM,L7,CAD+XYLAN | 32 | 0 | 0 | 32 | EA | 0 | 0 | 96 | 32 | EA | 22.09 - X1 BOX/ 20 SOH @ AA01 | Supply for Order 600002862, Item 42 cannot be changed 180017143 item 220 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 42 | 0 | EA | 102000000003642 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 32 |  | 2024-04-11 | 4900045283_2024_0043 | 2024-11-01 |  | 5000058191_2024_0022 | 0 | 2 | 0 | 90006343 | 32 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218627 | STUDBOLT;0.750"X130MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0250 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 42 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 250 |  |  | 0 | 32 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186286000028620000216479ta043043 | 6000028621021862820 | 10218628 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0430 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218628 | STUDBOLT;0.750"X140MM,L7,CAD+XYLAN | 20 | 0 | 0 | 20 | EA | 20 | 24 | 32 | 20 | EA | X1 BOX | Supply for Order 600002862, Item 43 cannot be changed 180017143 item 230 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 43 | 0 | EA | 102000000003643 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 20 |  | 2024-04-11 | 4900045283_2024_0045 | 2024-11-01 |  | 5000058191_2024_0023 | 0 | 2 | 0 | 90006343 | 20 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218628 | STUDBOLT;0.750"X140MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0260 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 43 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 260 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186326000028620000216479ta044044 | 6000028621021863260 | 10218632 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0440 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 60 | 0 | 0 | 60 | EA | 60 | 0 | 48 | 12 | EA | 01.10 - HU 101000000094408 TO AA02 | Supply for Order 600002862, Item 44 cannot be changed 180083185 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 44 | 0 | EA | 102000000003617 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 60 |  | 2024-10-18 | 4900154759_2024_0013/4900138157_2024_0001/4900045283_2024_0067 | 2024-11-01 |  | 5000248569_2024_0007/5000218662_2024_0001/5000058191_2024_0034 | 0 | 2 | 0 | 90006343 | 60 | 0 | 180073289/180083185/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0550/9013491_0550/9002109_0550 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 44 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 550 |  |  | 0 | 60 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186326000028620000216479ta044044 | 6000028621021863260 | 10218632 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0440 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 60 | 0 | 0 | 60 | EA | 60 | 0 | 48 | 24 | EA | 01.10 - HU 101000000094408 TO AA02 | Supply for Order 600002862, Item 44 cannot be changed 180083185 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 44 | 0 | EA |  |  | 102000000016304 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 60 |  | 2024-10-18 | 4900154759_2024_0013/4900138157_2024_0001/4900045283_2024_0067 | 2024-11-01 |  | 5000248569_2024_0007/5000218662_2024_0001/5000058191_2024_0034 | 0 | 2 | 0 | 90006343 | 60 | 0 | 180073289/180083185/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0550/9013491_0550/9002109_0550 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 44 |  | 0 |  | 24SDLN2C | MJ | 1000003470 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 550 |  |  | 0 | 60 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186326000028620000216479ta044044 | 6000028621021863260 | 10218632 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0440 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 60 | 0 | 0 | 60 | EA | 60 | 0 | 48 | 24 | EA | 01.10 - HU 101000000094408 TO AA02 | Supply for Order 600002862, Item 44 cannot be changed 180083185 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 44 | 0 | EA | 101000000094408 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 60 |  | 2024-10-18 | 4900154759_2024_0013/4900138157_2024_0001/4900045283_2024_0067 | 2024-11-01 |  | 5000248569_2024_0007/5000218662_2024_0001/5000058191_2024_0034 | 0 | 2 | 0 | 90006343 | 60 | 0 | 180073289/180083185/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0550/9013491_0550/9002109_0550 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 44 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 550 |  |  | 0 | 60 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186366000028620000216479ta045045 | 600002862102186368 | 10218636 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-30 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0450 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218636 | STUDBOLT;0.875"X180MM,L7,CAD+XYLAN | 8 | 0 | 0 | 8 | EA | 12 | 0 | 12 | 8 | EA | 03.10 - GR ZONE @ AA02 | Supply for Order 600002862, Item 45 cannot be changed 180083185 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 45 | 0 | EA | 101000000094430 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 8 |  | 2024-10-18 | 4900154759_2024_0015 | 2024-11-01 |  | 5000248569_2024_0008 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218636 | STUDBOLT;0.875"X180MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0560 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 45 |  | 0 |  | 24SDLN2C | MJ | 1000003732 |  | 1000214854 | S002 | 30 | 30 | 5300006667 | 560 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-30 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186526000028620000216479ta046046 | 6000028621021865216 | 10218652 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0460 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218652 | STUDBOLT;1.125"X190MM,L7,CAD+XYLAN | 16 | 0 | 0 | 16 | EA | 0 | 0 | 16 | 16 | EA | 01.10 - HU 101000000094366 TO AA02 | Supply for Order 600002862, Item 46 cannot be changed 180083185 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 46 | 0 | EA | 101000000094366 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 16 |  | 2024-10-18 | 4900154759_2024_0017 | 2024-11-01 |  | 5000248569_2024_0009 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218652 | STUDBOLT;1.125"X190MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0570 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 46 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 570 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102186576000028620000216479ta047047 | 6000028621021865740 | 10218657 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0470 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218657 | STUDBOLT;1.125"X230MM,L7,CAD+XYLAN | 40 | 0 | 40 | 0 | EA | 100 | 0 | 0 | 40 | EA | 22.09 - X2 BOXES / MW3R12D05A @ KSF | Supply for Order 600002862, Item 47 cannot be changed 180017143 item 240 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 47 | 0 | EA | 102000000003614 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 40 |  | 2024-04-11 | 4900045283_2024_0047 | 2024-11-01 |  | 5000058191_2024_0024 | 0 | 2 | 0 | 90006343 | 40 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218657 | STUDBOLT;1.125"X230MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0270 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 47 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 270 |  |  | 0 | 40 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102195266000028620000216479ta048048 | 600002862102195268 | 10219526 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0480 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10219526 | STUDBOLT;0.750"X160MM,L7,CAD+XYLAN | 8 | 0 | 0 | 8 | EA | 52 | 0 | 8 | 8 | EA | 01.10 - HU 101000000093107 TO AA02 | Supply for Order 600002862, Item 48 cannot be changed 180083185 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 48 | 0 | EA | 101000000093107 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 8 |  | 2024-10-18 | 4900154759_2024_0019 | 2024-11-01 |  | 5000248569_2024_0010 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219526 | STUDBOLT;0.750"X160MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0580 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 48 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 580 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102195386000028620000216479ta049049 | 6000028621021953880 | 10219538 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0490 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10219538 | STUDBOLT;1.250"X250MM,L7,CAD+XYLAN | 80 | 0 | 0 | 80 | EA | 0 | 0 | 80 | 80 | EA | 01.10 - HU 101...93499, 93530,43,45 TO AA02 | Supply for Order 600002862, Item 49 cannot be changed 180083185 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 49 | 0 | EA | 102000000019719 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 80 |  | 2024-10-18 | 4900154759_2024_0021 | 2024-11-01 |  | 5000248569_2024_0011 | 0 | 2 | 0 | 90006343 | 80 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219538 | STUDBOLT;1.250"X250MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0590 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 49 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 590 |  |  | 0 | 80 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102198856000028620000216479ta050050 | 6000028621021988512 | 10219885 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0500 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10219885 | STUDBOLT;1.125"X240MM,L7,CAD+XYLAN | 12 | 12 | 0 | 12 | EA | 0 | 0 | 0 | 0 |  | 10.10 - Del 80018302/000010 for picking | Supply for Order 600002862, Item 50 cannot be changed 90006343 item 600 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006343 | 07 | Execution | 0000216479 | 50 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090006343_0600 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-29 |  | 2024-11-01 |  |  | 0 | 2 | 0 | 90006343 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219885 | STUDBOLT;1.125"X240MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0600 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 50 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 600 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102199766000028620000216479ta0910133 | 6000028621021997624 | 10219976 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-21 | 2024-10-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0910 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(26.10.2024) | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 24 | 0 | 0 | 24 | EA | 60 | 0 | 24 | 24 | EA | MRF 241026-6712278 processed to 5001 HU 1020-22091 P-99 | Supply for Order 600002862, Item 133 cannot be changed 90022810 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180086211 | 90022810 | 07 | Execution | 0000216479 | 133 | 0 | EA |  |  | 102000000022091 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000258272_2024 | 0 | 11 | 0 | 0 |  | 2024-10-19 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037359 | 1020 | 2024-12-31 | 24 |  | 2024-10-27 | 4900160002_2024_0001 | 2024-11-01 |  | 5000258272_2024_0001 | 0 | 2 | 0 | 90022810 | 24 | 0 | 180086211 | 2 | 0 | 0 | X | L | 4900160002 | 2024 |  | 5000258272 | 2024 | 0 |  | 2024-10-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 2024-10-26 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90022810_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 133 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1230 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102199766000028620000216479ta051051 | 6000028621021997624 | 10219976 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0510 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 24 | 0 | 24 | 0 | EA | 60 | 0 | 24 | 24 | EA | X1 CRATE | Supply for Order 600002862, Item 51 cannot be changed 180017143 item 250 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 51 | 0 | EA |  |  | 102000000003644 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 24 |  | 2024-04-11 | 4900045283_2024_0049 | 2024-11-01 |  | 5000058191_2024_0025 | 0 | 2 | 0 | 90006343 | 24 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0280 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 51 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 280 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102204556000028620000216479ta052052 | 600002862102204558 | 10220455 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0520 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10220455 | STUDBOLT;0.875" X 180MM,A193 B8M CL2 | 8 | 0 | 8 | 0 | EA | 16 | 0 | 0 | 8 | EA | 22.09 - X1 BOX / MW3R15F09A @ KSF | Supply for Order 600002862, Item 52 cannot be changed 180017143 item 260 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 52 | 0 | EA | 102000000003615 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0051 | 2024-11-01 |  | 5000058191_2024_0026 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10220455 | STUDBOLT;0.875" X 180MM,A193 B8M CL2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0290 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 52 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 290 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102229536000028620000216479ta053053 | 600002862102229536 | 10222953 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0530 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10222953 | SPADE BLIND,50MM,CL300,RF,A516-60/70 | 6 | 0 | 0 | 6 | EA | 0 | 0 | 6 | 6 | EA | 01.10 - HU 101000000093007 TO AA02 | Supply for Order 600002862, Item 53 cannot be changed 180083185 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 53 | 0 | EA | 101000000093007 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 6 |  | 2024-10-18 | 4900154759_2024_0023 | 2024-11-01 |  | 5000248569_2024_0012 | 0 | 2 | 0 | 90006343 | 6 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10222953 | SPADE BLIND,50MM,CL300,RF,A516-60/70 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0610 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 53 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 610 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102233746000028620000216479ta054054 | 6000028621022337420 | 10223374 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0540 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10223374 | STUDBOLT;0.750"X140MM,A193 B8M,CL2 | 20 | 0 | 20 | 0 | EA | 32 | 4 | 24 | 20 | EA | 22.09 - IN GREY TUB / MW2R03A02A @ KSF | Supply for Order 600002862, Item 54 cannot be changed 180017143 item 270 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 54 | 0 | EA | 102000000003646 | 102000000003616 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 20 |  | 2024-04-11 | 4900045283_2024_0053 | 2024-11-01 |  | 5000058191_2024_0027 | 0 | 2 | 0 | 90006343 | 20 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223374 | STUDBOLT;0.750"X140MM,A193 B8M,CL2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0300 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 54 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 300 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102299386000028620000216479ta055055 | 600002862102299381 | 10229938 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0550 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10229938 | SPADE BLIND,80MM,CL150,SS316 | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 16.10 - 180082367 4500005381, 103 ERRORS | Supply for Order 600002862, Item 55 cannot be changed 180085320 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 620 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 55 | 0 | EA | 101000000101564 |  | 102000000021842 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0011 | 2024-11-01 |  | 5000255235_2024_0006 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229938 | SPADE BLIND,80MM,CL150,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0620 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 55 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 620 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102299416000028620000216479ta079079 | 600002862102299411 | 10229941 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0790 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10229941 | SPADE BLIND,50MM,CL600,SS316 | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000092975 TO AA02 | Supply for Order 600002862, Item 79 cannot be changed 180083185 item 180 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 79 | 0 | EA | 101000000092975 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0035 | 2024-11-01 |  | 5000248569_2024_0018 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229941 | SPADE BLIND,50MM,CL600,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0800 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 79 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 800 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102299426000028620000216479ta080080 | 600002862102299421 | 10229942 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0800 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10229942 | SPADE BLIND,100MM,CL600,SS316 | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 16.10 - 180082367 4500005381, 103 ERRORS | Supply for Order 600002862, Item 80 cannot be changed 180085320 item 160 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 80 | 0 | EA | 101000000101537 |  | 102000000021852 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0031 | 2024-11-01 |  | 5000255235_2024_0016 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229942 | SPADE BLIND,100MM,CL600,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0810 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 80 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 810 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102516546000028620000216479ta0230122 | 600002862102516546 | 10251654 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0230 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 6 | 0 | 6 | 0 | EA | 0 | 0 | 5 | 4 | EA | 03.10 - HU 101000000093112 to AA02 | Supply for Order 600002862, Item 122 cannot be changed 180085864 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085878 | 9017455 | 07 | Execution | 0000216479 | 122 | 0 | EA |  |  | 102000000022072 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000037617 | 1020 | 2024-12-31 | 6 |  | 2024-10-25 | 4900159260_2024_0001/4900159250_2024_0001 | 2024-10-07 |  | 5000257063_2024_0001/5000257056_2024_0001 | 0 | 2 | 0 | 90020228 | 6 | 0 | 180085864/180085878 | 2 | 0 | 0 | X | L | 4900159260 | 2024 |  | 5000257056 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017455_0060/9017453_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 122 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-02 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102516546000028620000216479ta09000 | 600002862102516540 | 10251654 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 |  | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0900 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 |  | 30 | Maintenance Order material has been deleted | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 99 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | AA53 | 2024-10-21 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 |  |  |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter | [5 empty] | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 24SDLN2C | MJ |  |  | 1000214854 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102516546000028620000216479ta069069 | 600002862102516544 | 10251654 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-01 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0690 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 4 | 0 | 0 | 4 | EA | 0 | 0 | 5 | 1 | EA | 06.03 - ETA 17.04.24 PO 4500004781 x 3 Australasian, ETA 16.02.24 PO W451781228 | Supply for Order 600002862, Item 69 cannot be changed 9018326 item 360 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180090422 | 9018456 | 07 | Execution | 0000216479 | 69 | 1 | EA | 102000000022419 |  | 107000000000391 |  |  |  | P07 - BENCH | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-02-16 | GRST-5000271136_2024 | 0 | 0 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000039296 | 1020 | 2024-12-31 | 4 |  | 2024-11-07 | 4900167013_2024_0001/4900162552_2024_0001 | 2024-11-01 |  | 5000271136_2024_0001/5000263690_2024_0001 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180090422/180088335 | 1 | 0 | 0 | X | L | 4900167013 | 2024 |  | 5000271136 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9018456_0360/9018326_0360 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 69 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 360 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102516546000028620000216479ta0230122 | 600002862102516546 | 10251654 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0230 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 6 | 0 | 6 | 0 | EA | 0 | 0 | 5 | 1 | EA | 03.10 - HU 101000000093112 to AA02 | Supply for Order 600002862, Item 122 cannot be changed 180085864 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085878 | 9017455 | 07 | Execution | 0000216479 | 122 | 0 | EA |  |  | 102000000022018 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000037617 | 1020 | 2024-12-31 | 6 |  | 2024-10-25 | 4900159260_2024_0001/4900159250_2024_0001 | 2024-10-07 |  | 5000257063_2024_0001/5000257056_2024_0001 | 0 | 2 | 0 | 90020228 | 6 | 0 | 180085864/180085878 | 2 | 0 | 0 | X | L | 4900159260 | 2024 |  | 5000257056 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017455_0060/9017453_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 122 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-02 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102516546000028620000216479ta0230122 | 600002862102516546 | 10251654 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0230 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 6 | 0 | 6 | 0 | EA | 0 | 0 | 5 | 1 | EA | 03.10 - HU 101000000093112 to AA02 | Supply for Order 600002862, Item 122 cannot be changed 180085864 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085878 | 9017455 | 07 | Execution | 0000216479 | 122 | 0 | EA |  |  | 102000000022019 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000037617 | 1020 | 2024-12-31 | 6 |  | 2024-10-25 | 4900159260_2024_0001/4900159250_2024_0001 | 2024-10-07 |  | 5000257063_2024_0001/5000257056_2024_0001 | 0 | 2 | 0 | 90020228 | 6 | 0 | 180085864/180085878 | 2 | 0 | 0 | X | L | 4900159260 | 2024 |  | 5000257056 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017455_0060/9017453_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 122 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-02 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102516546000028620000216479ta069069 | 600002862102516544 | 10251654 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-01 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0690 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 4 | 0 | 0 | 4 | EA | 0 | 0 | 5 | 3 | EA | 06.03 - ETA 17.04.24 PO 4500004781 x 3 Australasian, ETA 16.02.24 PO W451781228 | Supply for Order 600002862, Item 69 cannot be changed 9018326 item 360 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180090422 | 9018456 | 07 | Execution | 0000216479 | 69 | 1 | EA | 102000000023066 |  | 107000000000076 |  |  |  | STATIC-CAGE | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-02-16 | GRST-5000271136_2024 | 0 | 0 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000039296 | 1020 | 2024-12-31 | 4 |  | 2024-11-07 | 4900167013_2024_0001/4900162552_2024_0001 | 2024-11-01 |  | 5000271136_2024_0001/5000263690_2024_0001 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180090422/180088335 | 1 | 0 | 0 | X | L | 4900167013 | 2024 |  | 5000271136 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9018456_0360/9018326_0360 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 69 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 360 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102548706000028620000216479ta056056 | 600002862102548701 | 10254870 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0560 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254870 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN50C> | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 56 cannot be changed 180085320 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 56 | 0 | EA | 101000000101568 |  | 102000000021843 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0013 | 2024-11-01 |  | 5000255235_2024_0007 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254870 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN50C> | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0630 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 56 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 630 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102548716000028620000216479ta057057 | 600002862102548711 | 10254871 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0570 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254871 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN80C> | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 57 cannot be changed 180085320 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 57 | 0 | EA | 101000000101620 |  | 102000000021844 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0015 | 2024-11-01 |  | 5000255235_2024_0008 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254871 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN80C> | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0640 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 57 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 640 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102548756000028620000216479ta058058 | 600002862102548751 | 10254875 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0580 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254875 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN100> | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 58 cannot be changed 180085320 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 58 | 0 | EA | 101000000101567 |  | 102000000021845 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0017 | 2024-11-01 |  | 5000255235_2024_0009 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254875 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN100> | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0650 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 58 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 650 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102549746000028620000216479ta059059 | 600002862102549741 | 10254974 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0590 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254974 | SPADE,BLIND;CAMCO 7666720DN50CL3008MM | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 59 cannot be changed 180085320 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 59 | 0 | EA | 101000000101569 |  | 102000000021846 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0019 | 2024-11-01 |  | 5000255235_2024_0010 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254974 | SPADE,BLIND;CAMCO 7666720DN50CL3008MM | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0660 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 59 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 660 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102549796000028620000216479ta060060 | 600002862102549792 | 10254979 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0600 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254979 | SPADE,BLIND,80MM,CL600,15MM,SS304 | 2 | 0 | 0 | 2 | EA | 0 | 0 | 2 | 2 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 60 cannot be changed 180085320 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 60 | 0 | EA | 101000000101535 |  | 102000000021847 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0021 | 2024-11-01 |  | 5000255235_2024_0011 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254979 | SPADE,BLIND,80MM,CL600,15MM,SS304 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0670 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 60 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 670 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102550086000028620000216479ta00400 | 600002862102550081 | 10255008 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2025-03-05 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0040 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10255008 | SPADE,BLIND,1050MM,CL150,55MM,SS304 | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALIAN FITTINGS | Supply for Order 600002862, Item 103 cannot be changed – 4500027121 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300014053 | 40 | CPT | 7 | 1000018366 | 103 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500027121 | 40 | 1 | EA | 2024-11-24 |  |  |  |  | 07 | Execution | 0000216479 | 103 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-08-13 | POPO-4500027121_00040 | 0 | 158 | 0 | 0 | 2025-02-28 | 2025-03-15 | AA53 | 2024-11-22 |  |  | 2025-08-27 | 2025-03-02 | 2025-03-17 |  |  | 2024-12-31 | 0 |  | 2025-03-05 |  | 2025-03-17 |  |  | 0 | 2 | 2 |  | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255008 | SPADE,BLIND,1050MM,CL150,55MM,SS304 | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-01-03 | 30 |  | 2025-03-02 | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 950 |  | 5300014053 | 40 | 1 | EA | 1001 | AA02 | 2025-03-05 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
102582136000028620000216479ta085085 | 6000028621025821310 | 10258213 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0850 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(15.02.2024) | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 10 | 0 | 0 | 10 | SHT | 0 | 0 | 13 | 2 | SHT | 01.10 - HU 101000000068823 TO AA02 | Supply for Order 600002862, Item 85 cannot be changed 180078327 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  | 180081721 | 9016389 | 07 | Execution | 0000216479 | 85 | 0 | SHT |  |  | 102000000020802 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000243856_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035211 | 1020 | 2024-12-31 | 10 |  | 2024-10-14 | 4900152515_2024_0001/4900146823_2024_0001/4900138179_2024_0001 | 2024-11-01 |  | 5000243856_2024_0001/5000233678_2024_0001/5000218684_2024_0001 | 0 | 2 | 0 | 90006343 | 10 | 0 | 180073288/180078327/180081721 | 2 | 0 | 0 | X | L | 4900152515 | 2024 |  | 5000243856 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 2024-02-15 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016389_0010/9015483_0010/9013490_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 85 |  | 0 |  | 24SDLN2C | MJ | 1000003654 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 10 |  |  | 0 | 10 | SHT | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-15 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102582136000028620000216479ta085085 | 6000028621025821310 | 10258213 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0850 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(15.02.2024) | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 10 | 0 | 0 | 10 | SHT | 0 | 0 | 13 | 3 | SHT | 01.10 - HU 101000000068823 TO AA02 | Supply for Order 600002862, Item 85 cannot be changed 180078327 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  | 180081721 | 9016389 | 07 | Execution | 0000216479 | 85 | 0 | SHT | 102000000016228 |  | 107000000000418 |  |  |  | P07YRDBY11 | WorkPackLink | P07YRDBY11 |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000243856_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035211 | 1020 | 2024-12-31 | 10 |  | 2024-10-14 | 4900152515_2024_0001/4900146823_2024_0001/4900138179_2024_0001 | 2024-11-01 |  | 5000243856_2024_0001/5000233678_2024_0001/5000218684_2024_0001 | 0 | 2 | 0 | 90006343 | 10 | 0 | 180073288/180078327/180081721 | 2 | 0 | 0 | X | L | 4900152515 | 2024 |  | 5000243856 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 2024-02-15 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016389_0010/9015483_0010/9013490_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 85 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 10 |  |  | 0 | 10 | SHT | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102582136000028620000216479ta085085 | 6000028621025821310 | 10258213 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0850 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(15.02.2024) | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 10 | 0 | 0 | 10 | SHT | 0 | 0 | 13 | 5 | SHT | 01.10 - HU 101000000068823 TO AA02 | Supply for Order 600002862, Item 85 cannot be changed 180078327 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  | 180081721 | 9016389 | 07 | Execution | 0000216479 | 85 | 0 | SHT |  |  | 102000000019866 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000243856_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035211 | 1020 | 2024-12-31 | 10 |  | 2024-10-14 | 4900152515_2024_0001/4900146823_2024_0001/4900138179_2024_0001 | 2024-11-01 |  | 5000243856_2024_0001/5000233678_2024_0001/5000218684_2024_0001 | 0 | 2 | 0 | 90006343 | 10 | 0 | 180073288/180078327/180081721 | 2 | 0 | 0 | X | L | 4900152515 | 2024 |  | 5000243856 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 2024-02-15 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016389_0010/9015483_0010/9013490_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 85 |  | 0 |  | 24SDLN2C | MJ | 1000003650 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 10 |  |  | 0 | 10 | SHT | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
102917726000028620000216479ta0080107 | 600002862102917721 | 10291772 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0080 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10291772 | FLANGE,BLIND;200MM,CL150,RF,CS,A105M | 1 | 0 | 0 | 1 | EA | 1 | 1 | 12 | 1 | EA | 05.10 - HU 101000000096902 to AA02 | Supply for Order 600002862, Item 107 cannot be changed 180078491 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078491 | 9015168 | 07 | Execution | 0000216479 | 107 | 0 | EA | 101000000096789 |  | 107000000000418 |  |  |  | P07YRDBY11 | WorkPackLink | P07YRDBY11 | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000234684_2024 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  | 100000033635 | 1020 | 2024-12-31 | 1 |  | 2024-10-07 | 4900147491_2024_0003 | 2024-10-15 |  | 5000234684_2024_0001 | 0 | 2 | 0 | 90020227 | 1 | 0 | 180078491 | 2 | 0 | 0 | X | L | 4900147491 | 2024 |  | 5000234684 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10291772 | FLANGE,BLIND;200MM,CL150,RF,CS,A105M | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015168_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 107 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 990 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
103057446000028620000216479ta90 | 600002862103057444 | 10305744 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 |  | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(25.03.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 4 | 0 | 0 | 4 | EA | 47 | 15 | 37 | 4 | EA | 22.09 - IN GRAY TUB / MW2R03B03E @ KSF | Supply for Order 600002862, Item 90 cannot be changed 180017111 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017111 | 90006609 | 07 | Execution | 0000216479 | 90 | 0 | EA | 102000000003646 | 102000000003685 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058173_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045279_2024_0001 | 2024-11-01 |  | 5000058173_2024_0001 | 0 | 2 | 0 | 90006609 | 4 | 0 | 180017111 | 2 | 0 | 0 | X | L | 4900045279 | 2024 |  | 5000058173 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-03-25 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006609_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 90 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 880 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
103067246000028620000216479ta061061 | 600002862103067248 | 10306724 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0610 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10306724 | GASKET;SWC,80MM,CL300/600,31>WSE10508041 | 8 | 0 | 0 | 8 | EA | 6 | 0 | 8 | 8 | EA | 22.09 - IN GREY TUB / 4 SOH @ AA02 | Supply for Order 600002862, Item 61 cannot be changed 180017143 item 280 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 61 | 0 | EA | 102000000003646 | 102000000003631 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0055 | 2024-11-01 |  | 5000058191_2024_0028 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10306724 | GASKET;SWC,80MM,CL300/600,31>WSE10508041 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0310 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 61 |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 70 | 5300006667 | 310 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
103128546000028620000216479taX129 | 600002862103128541 | 10312854 |  | 24SDLN2C | Released | 2024-02-29 | 2025-03-17 | 2025-03-17 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | X | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 |  | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(03.10.2024) | 10312854 | AIR;MEDICAL DRY,25PPM,BOC 470MAN15 | 1 | 0 | 0 | 1 | PAC | 0 | 0 | 1 | 1 | PAC | 24.10 - ETA 24.10.24 PO 4500031439 BOC | Supply for Order 600002862, Item 129 cannot be changed 9017564 item 50 already exists | Material work-packed @AA53 | SP14 | Directs (Inventory) | 10 | AA02 | 5300006667 | 1200 | CPT | 14 | 1000020500 | 129 | 30000395 | BOC LIMITED | 4500031439 | 20 | 1 | PAC | 2024-10-28 |  | /180086442/180086442 | 180086443 | 9017564 | 07 | Execution | 0000216479 | 129 | 0 | PAC |  |  | 102000000022162 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000259599_2024 | 0 | 5 | 0 | 0 | 2025-03-15 | 2025-03-20 | AA53 | 2024-11-22 |  |  | 2025-03-22 |  | 2025-03-17 | 100000037748 | 1020 | 2024-12-31 | 1 | 5000259612_2024_0001 | 2024-10-28 | 4900160481_2024_0001 | 2024-10-28 |  | 5000259599_2024_0001 | 0 | 2 | 2 | 90022091 | 1 | 1 | 180086443 | 2 | 0 | 0 | X | L | 4900160481 | 2024 | 5000259612 | 5000259599 | 2024 | 2024 | /018008644 | 2025-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10312854 | AIR;MEDICAL DRY,25PPM,BOC 470MAN15 | 2024-10-03 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017564_0050 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-08 | 30 |  | 2025-03-17 | 129 |  | 31522 |  | 24SDLN2C | MJ | 1000003911 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1200 |  |  | 0 | 1 | PAC | 2001 | AA02 | 2025-03-17 |  |  | 2024-10-31 | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
103400866000028620000216479ta0060105 | 600002862103400861 | 10340086 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0060 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10340086 | FLANGE,BLIND;350MM,CL300,RF,CS,A105N | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 05.10 - HU 101000000096902 to AA02 | Supply for Order 600002862, Item 105 cannot be changed 180078491 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078491 | 9015168 | 07 | Execution | 0000216479 | 105 | 0 | EA | 101000000096787 |  | 107000000000418 |  |  |  | P07YRDBY11 | WorkPackLink | P07YRDBY11 | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000234700_2024 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  | 100000033635 | 1020 | 2024-12-31 | 1 |  | 2024-10-07 | 4900147491_2024_0001 | 2024-10-15 |  | 5000234700_2024_0001 | 0 | 2 | 0 | 90020227 | 1 | 0 | 180078491 | 2 | 0 | 0 | X | L | 4900147491 | 2024 |  | 5000234700 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10340086 | FLANGE,BLIND;350MM,CL300,RF,CS,A105N | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015168_0040 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 105 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 970 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
103401066000028620000216479ta0030102 | 600002862103401061 | 10340106 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0030 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10340106 | SPADE BLIND,50MM,CL150,CS,A285,GDE C | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 102 cannot be changed 90020227 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 940 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020227 | 07 | Execution | 0000216479 | 102 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090020227_0020 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-10 |  | 2024-10-15 |  |  | 0 | 2 | 0 | 90020227 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10340106 | SPADE BLIND,50MM,CL150,CS,A285,GDE C | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020227_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 102 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 940 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
104413786000028620000216479ta062062 | 600002862104413781 | 10441378 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0620 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10441378 | SPADE BLIND,100MM,CL600,CS | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 16.10 - 180082367 4500005381, 103 ERRORS | Supply for Order 600002862, Item 62 cannot be changed 180085320 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 62 | 0 | EA | 101000000101627 |  | 102000000021848 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0023 | 2024-11-01 |  | 5000255235_2024_0012 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441378 | SPADE BLIND,100MM,CL600,CS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0680 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 62 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 680 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
104413796000028620000216479ta0020101 | 600002862104413791 | 10441379 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0020 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10441379 | SPADE BLIND,150MM,CL600,CS | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 101 cannot be changed 90020227 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 930 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020227 | 07 | Execution | 0000216479 | 101 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090020227_0010 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-10 |  | 2024-10-15 |  |  | 0 | 2 | 0 | 90020227 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441379 | SPADE BLIND,150MM,CL600,CS | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020227_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 101 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 930 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
104872446000028620000216479ta063063 | 600002862104872442 | 10487244 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0630 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10487244 | SPADE,BLIND,80MM,CL300,LTCS | 2 | 0 | 0 | 2 | EA | 0 | 0 | 2 | 2 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 63 cannot be changed 180085320 item 130 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 63 | 0 | EA | 101000000101539 |  | 102000000021849 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0025 | 2024-11-01 |  | 5000255235_2024_0013 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10487244 | SPADE,BLIND,80MM,CL300,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0690 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 63 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 690 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
104872456000028620000216479ta064064 | 600002862104872451 | 10487245 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0640 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10487245 | SPADE,BLIND,100MM,CL300,LTCS | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 64 cannot be changed 180085320 item 140 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 700 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 64 | 0 | EA | 101000000101565 |  | 102000000021850 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0027 | 2024-11-01 |  | 5000255235_2024_0014 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10487245 | SPADE,BLIND,100MM,CL300,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0700 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 64 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 700 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
104880486000028620000216479ta065065 | 600002862104880481 | 10488048 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0650 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10488048 | FLANGE,BLIND,150MM,CL300,RF,SS | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000093024 TO AA02 | Supply for Order 600002862, Item 65 cannot be changed 180083185 item 130 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 710 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 65 | 0 | EA | 101000000093024 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0025 | 2024-11-01 |  | 5000248569_2024_0013 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10488048 | FLANGE,BLIND,150MM,CL300,RF,SS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0710 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 65 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 710 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
104881346000028620000216479ta00100 | 600002862104881341 | 10488134 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2025-03-05 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0010 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10488134 | SPADE,BLIND,250MM,CL300,SS | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALIAN FITTINGS | Supply for Order 600002862, Item 100 cannot be changed – 4500027121 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300014053 | 30 | CPT | 7 | 1000018366 | 100 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500027121 | 10 | 1 | EA | 2024-11-24 |  |  |  |  | 07 | Execution | 0000216479 | 100 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-08-13 | POPO-4500027121_00010 | 0 | 158 | 0 | 0 | 2025-02-28 | 2025-03-15 | AA53 | 2024-11-22 |  |  | 2025-08-27 | 2025-03-02 | 2025-03-17 |  |  | 2024-12-31 | 0 |  | 2025-03-05 |  | 2025-03-17 |  |  | 0 | 2 | 2 |  | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10488134 | SPADE,BLIND,250MM,CL300,SS | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-01-03 | 30 |  | 2025-03-02 | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 920 |  | 5300014053 | 30 | 1 | EA | 1001 | AA02 | 2025-03-05 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
104889406000028620000216479ta066066 | 600002862104889401 | 10488940 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0660 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10488940 | SPADE,BLIND,80MM,CL600,LTCS | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 66 cannot be changed 180085320 item 150 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 66 | 0 | EA | 101000000101566 |  | 102000000021851 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0029 | 2024-11-01 |  | 5000255235_2024_0015 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10488940 | SPADE,BLIND,80MM,CL600,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0720 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 66 |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 720 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
104929796000028620000216479ta074074 | 6000028621049297948 | 10492979 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0740 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10492979 | STUDBOLT;1.875" X 470MM,L7,ZN+XYLAN | 48 | 0 | 0 | 48 | EA | 0 | 0 | 48 | 48 | EA | 01.10 - HU 101000000080184 TO AA02 | Supply for Order 600002862, Item 74 cannot be changed 180078362 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 74 | 0 | EA | 102000000020030 |  | 107000000000278 |  |  |  |  | WorkPackLink | P07YRDBY12 |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000233767_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 48 |  | 2024-10-06 | 4900146921_2024_0007 | 2024-11-01 |  | 5000233767_2024_0004 | 0 | 2 | 0 | 90006343 | 48 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10492979 | STUDBOLT;1.875" X 470MM,L7,ZN+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0750 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 74 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 750 |  |  | 0 | 48 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
105905966000028620000216479ta067067 | 600002862105905966 | 10590596 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0670 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10590596 | GASKET;RF,GR,300MM,CL150,KLINGER 154756 | 6 | 0 | 0 | 6 | EA | 0 | 0 | 6 | 6 | EA | 01.10 - HU 101000000093397 TO AA02 | Supply for Order 600002862, Item 67 cannot be changed 180083185 item 140 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 67 | 0 | EA | 101000000093397 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 6 |  | 2024-10-18 | 4900154759_2024_0027 | 2024-11-01 |  | 5000248569_2024_0014 | 0 | 2 | 0 | 90006343 | 6 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10590596 | GASKET;RF,GR,300MM,CL150,KLINGER 154756 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0730 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 67 |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 730 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
105925096000028620000216479ta0010135 | 6000028621059250950 | 10592509 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-22 | 2024-11-11 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0001 | 0010 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(11.11.2024) | 10592509 | BLADE,SAW;RECIP,CB,8TPI,1",230MM | 50 | 0 | 50 | 0 | EA | 53 | 5 | 0 | 50 | EA | UserCommentLink | Supply for Order 600002862, Item 135 cannot be changed 90024081 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180092179 | 90024081 | 07 | Execution | 0000216479 | 135 | 0 | EA |  |  | 102000000023606 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 KGP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 25 | 0 | 0 |  | 2024-10-20 | AA53 | 2024-10-22 |  |  | 2024-11-16 |  |  | 100000040495 | 1020 | 2024-12-31 | 50 |  | 2024-11-12 | 4900170153_2024_0001 | 2024-11-16 | LNG2 COP | 5000276086_2024_0001 | 0 | 2 | 0 | 90024081 | 50 | 0 | 180092179 | 2 | 0 | 0 | X | L | 4900170153 | 2024 |  | 5000276086 | 2024 | 0 |  | 2024-11-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10592509 | BLADE,SAW;RECIP,CB,8TPI,1",230MM | 2024-11-11 | W |  | 0001 | Supervisors | ENON | Supervisors |  |  | 90024081_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 135 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1250 |  |  | 0 | 50 | EA | 2001 | AA02 | 2024-11-11 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Pre-costed/Object created/Ready For Scheduling/Settlement rule created/Goods movement posted/Released/Material shortage/Date set by external system/Partially confirmed | AM06 | Capital | R0-010051-02-01-EX
106136396000028620000216479ta084084 | 600002862106136391 | 10613639 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0840 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10613639 | SPADE BLIND 150MM CL150 FF A516 GR70 | 1 | 0 | 0 | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 84 cannot be changed 180084380 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180084380 | 9017420 | 07 | Execution | 0000216479 | 84 | 0 | EA |  |  | 102000000021568 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | GRST-5000252447_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036544 | 1020 | 2024-12-31 | 1 |  | 2024-10-22 | 4900156964_2024_0001 | 2024-11-01 |  | 5000252447_2024_0001 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180084380 | 2 | 0 | 0 | X | L | 4900156964 | 2024 |  | 5000252447 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613639 | SPADE BLIND 150MM CL150 FF A516 GR70 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017420_0830 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 84 |  | 0 |  | 24SDLN2C | MJ | 1000003766 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 830 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-23 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
106136426000028620000216479ta0070106 | 600002862106136421 | 10613642 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 |  | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0070 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10613642 | SPADE BLIND 200MM CL150 FF A516 GR70 | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - NEED PURCHSING |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 980 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 106 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-02-16 | STST-5300006667_00980 | 1 | 0 | 0 | 0 |  |  | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  |  |  | 2024-12-31 | 0 | [6 empty] | 0 | 2 | 0 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613642 | SPADE BLIND 200MM CL150 FF A516 GR70 |  |  |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 106 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 980 |  |  | 0 | 0 | EA | 2001 | AA02 | [5 empty] | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114008056000028620000216479ta086086 | 600002862114008051 | 11400805 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0860 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(05.03.2024) | 11400805 | SPADE,BLIND,200MM,CL600,LTCS | 1 | 0 | 1 | 0 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000040351 TO AA02 | Supply for Order 600002862, Item 86 cannot be changed 180078362 item 70 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 840 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 86 | 0 | EA |  |  | 102000000020027 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0013 | 2024-11-01 |  | 5000233767_2024_0007 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400805 | SPADE,BLIND,200MM,CL600,LTCS | 2024-03-05 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0840 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 86 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 840 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
114008086000028620000216479ta087087 | 600002862114008081 | 11400808 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0870 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(05.03.2024) | 11400808 | SPADE BLIND,350MM,CL150,SS316 | 1 | 0 | 1 | 0 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000085146 TO AA02 | Supply for Order 600002862, Item 87 cannot be changed 180078362 item 80 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 850 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 87 | 0 | EA |  |  | 102000000020028 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0015 | 2024-11-01 |  | 5000233767_2024_0008 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400808 | SPADE BLIND,350MM,CL150,SS316 | 2024-03-05 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0850 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  | 87 |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 850 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
114047756000028620000216479ta01400 | 600002862114047756 | 11404775 |  | 24SDLN2C | Released | 2024-02-29 | 2025-03-22 |  | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0140 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404775 | CONTRACTOR;100-250V,ABB 1SFL547002R3322 | 6 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Supplying document 5300006667 1050 could not be updated on RESB due to locks |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 113 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404775 | CONTRACTOR;100-250V,ABB 1SFL547002R3322 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 24SDLN2C | MJ |  |  | 1000214854 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114049096000028620000216479ta01300 | 6000028621140490910 | 11404909 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-09-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0130 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 10 | 10 | 0 | 10 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Linked STO 5300014053 change failed for Order 600002862 Item 112 |  | SP97 | Direct Multi-base | 0 | AA01 | 5300014053 | 60 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020245 | 07 | Execution | 0000216479 | 112 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-08-13 |  | 0 | 0 | 0 | 0 |  | 2024-10-08 | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 |  | 2024-09-27 |  | 2024-10-10 |  |  | 0 | 2 | 0 | 90020245 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-09-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020245_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA02 |  | 30 |  |  | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1040 |  | 5300014053 | 60 | 10 | EA | 1001 | AA02 | 2024-09-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114049096000028620000216479ta0240123 | 6000028621140490910 | 11404909 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0240 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.09.2024) | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 10 | 10 | 0 | 10 | EA | 0 | 0 | 10 | 0 |  | At KGP 19/10/24 | Supply for Order 600002862, Item 123 cannot be changed 180082361 item 10 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300006667 | 1150 | EXW | 7 | 1000019709 | 123 | 30003000 | PIPESERV GARDINER INVESTMENTS QLD PTY LTD | 4500029623 | 10 | 10 | EA | 2024-11-18 |  | 180078395 |  | 90020249 | 07 | Execution | 0000216479 | 123 | 0 | [8 empty] | 00000107000000000580 | P07-WAREHOUSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090020249_0010 | 0 | 60 | 54 | 60 | 2024-11-18 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-14 | 2024-11-20 | 2024-12-09 |  |  | 2024-12-31 | 0 | 5000234489_2024_0001 | 2024-10-10 |  | 2024-10-07 |  |  | 0 | 2 | 2 | 90020249 | 0 | 10 |  | 2 | 0 | 0 | X | L |  | 0 | 5000234489 |  | 0 | 2024 | 180078395 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 2024-09-21 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020249_0010 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-24 | 30 |  | 2024-11-20 | 123 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1150 |  | 5300014053 | 100 | 10 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114049256000028620000216479ta01700 | 600002862114049256 | 11404925 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-09-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0170 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | 6 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Linked STO 5300014053 change failed for Order 600002862 Item 116 |  | SP97 | Direct Multi-base | 0 | AA01 | 5300014053 | 90 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020245 | 07 | Execution | 0000216479 | 116 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-08-13 |  | 0 | 0 | 0 | 0 |  | 2024-10-08 | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 |  | 2024-09-27 |  | 2024-10-10 |  |  | 0 | 2 | 0 | 90020245 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-09-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020245_0040 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA02 |  | 30 |  |  | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1080 |  | 5300014053 | 90 | 6 | EA | 1001 | AA02 | 2024-09-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114049256000028620000216479ta0270127 | 600002862114049256 | 11404925 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0270 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.09.2024) | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | 6 | 6 | 0 | 6 | EA | 0 | 0 | 6 | 0 |  | At KGP 19/10/24 | Supply for Order 600002862, Item 127 cannot be changed 180082361 item 40 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300006667 | 1180 | EXW | 7 | 1000019709 | 127 | 30003000 | PIPESERV GARDINER INVESTMENTS QLD PTY LTD | 4500029623 | 40 | 6 | EA | 2024-11-18 |  | 180078395 |  | 90020249 | 07 | Execution | 0000216479 | 127 | 0 | [8 empty] | 00000107000000000580 | P07-WAREHOUSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090020249_0040 | 0 | 60 | 54 | 60 | 2024-11-18 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-14 | 2024-11-20 | 2024-12-09 |  |  | 2024-12-31 | 0 | 5000234520_2024_0001 | 2024-10-10 |  | 2024-10-07 |  |  | 0 | 2 | 2 | 90020249 | 0 | 6 |  | 2 | 0 | 0 | X | L |  | 0 | 5000234520 |  | 0 | 2024 | 180078395 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | 2024-09-21 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020249_0040 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-24 | 30 |  | 2024-11-20 | 127 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1180 |  | 5300014053 | 130 | 6 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114049266000028620000216479ta01500 | 600002862114049266 | 11404926 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-09-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0150 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | 6 | 6 | 0 | 6 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Linked STO 5300014053 change failed for Order 600002862 Item 114 |  | SP97 | Direct Multi-base | 0 | AA01 | 5300014053 | 70 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020245 | 07 | Execution | 0000216479 | 114 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-08-13 |  | 0 | 0 | 0 | 0 |  | 2024-10-08 | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 |  | 2024-09-27 |  | 2024-10-10 |  |  | 0 | 2 | 0 | 90020245 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-09-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020245_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA02 |  | 30 |  |  | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1060 |  | 5300014053 | 70 | 6 | EA | 1001 | AA02 | 2024-09-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114049266000028620000216479ta0250125 | 600002862114049266 | 11404926 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0250 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.09.2024) | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | 6 | 6 | 0 | 6 | EA | 0 | 0 | 6 | 0 |  | At KGP 19/10/24 | Supply for Order 600002862, Item 125 cannot be changed 180082361 item 20 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300006667 | 1160 | EXW | 7 | 1000019709 | 125 | 30003000 | PIPESERV GARDINER INVESTMENTS QLD PTY LTD | 4500029623 | 20 | 6 | EA | 2024-11-18 |  | 180078395 |  | 90020249 | 07 | Execution | 0000216479 | 125 | 0 | [8 empty] | 00000107000000000580 | P07-WAREHOUSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090020249_0020 | 0 | 60 | 54 | 60 | 2024-11-18 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-14 | 2024-11-20 | 2024-12-09 |  |  | 2024-12-31 | 0 | 5000234502_2024_0001 | 2024-10-10 |  | 2024-10-07 |  |  | 0 | 2 | 2 | 90020249 | 0 | 6 |  | 2 | 0 | 0 | X | L |  | 0 | 5000234502 |  | 0 | 2024 | 180078395 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | 2024-09-21 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020249_0020 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-24 | 30 |  | 2024-11-20 | 125 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1160 |  | 5300014053 | 110 | 6 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114049296000028620000216479ta01600 | 6000028621140492910 | 11404929 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-09-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0160 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | 10 | 10 | 0 | 10 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Linked STO 5300014053 change failed for Order 600002862 Item 115 |  | SP97 | Direct Multi-base | 0 | AA01 | 5300014053 | 80 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020245 | 07 | Execution | 0000216479 | 115 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  |  | 1001 | 2024-08-13 |  | 0 | 0 | 0 | 0 |  | 2024-10-08 | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 |  | 2024-09-27 |  | 2024-10-10 |  |  | 0 | 2 | 0 | 90020245 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-09-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020245_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA02 |  | 30 |  |  | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1070 |  | 5300014053 | 80 | 10 | EA | 1001 | AA02 | 2024-09-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
114049296000028620000216479ta0260126 | 6000028621140492910 | 11404929 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0260 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.09.2024) | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | 10 | 10 | 0 | 10 | EA | 0 | 0 | 10 | 0 |  | At KGP 19/10/24 | Supply for Order 600002862, Item 126 cannot be changed 180082361 item 30 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300006667 | 1170 | EXW | 7 | 1000019709 | 126 | 30003000 | PIPESERV GARDINER INVESTMENTS QLD PTY LTD | 4500029623 | 30 | 10 | EA | 2024-11-18 |  | 180078395 |  | 90020249 | 07 | Execution | 0000216479 | 126 | 0 | [8 empty] | 00000107000000000580 | P07-WAREHOUSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-02-16 | ODST-0090020249_0030 | 0 | 60 | 54 | 60 | 2024-11-18 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-14 | 2024-11-20 | 2024-12-09 |  |  | 2024-12-31 | 0 | 5000234504_2024_0001 | 2024-10-10 |  | 2024-10-07 |  |  | 0 | 2 | 2 | 90020249 | 0 | 10 |  | 2 | 0 | 0 | X | L |  | 0 | 5000234504 |  | 0 | 2024 | 180078395 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | 2024-09-21 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020249_0030 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-24 | 30 |  | 2024-11-20 | 126 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1170 |  | 5300014053 | 120 | 10 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
700110106000028620000216479taX0 | 600002862700110101 | 70011010 |  | 24SDLN2C | Released | 2024-02-29 | 2024-11-01 |  | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | X | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 70011010 | Restriction Orifice Plate 41RO20 | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - SOH @ AA01 | Supplying document 5300006667 890 could not be updated on RESB due to locks |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 92 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | AA53 | 2024-10-21 | [7 empty] | 2024-12-31 | 0 |  |  |  |  | LNG2 COP |  | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70011010 | Restriction Orifice Plate 41RO20 | 2024-08-12 | E |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter | [5 empty] | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 24SDLN2C | MJ |  |  | 1000214854 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
700110106000028620000216479ta08800 | 600002862700110101 | 70011010 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-22 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0880 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(12.08.2024) | 70011010 | Restriction Orifice Plate 41RO20 | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | SPT Error TOP HU 102000000019832 - 2nd HU 101000000094259 | Supply for Order 600002862, Item 96 cannot be changed 90022126 item 10 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300014053 | 10 | CPT | 21 | 1000017114 | 96 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500026367 | 10 | 1 | EA | 2024-09-27 |  | /180068765 |  | 90022126 | 07 | Execution | 0000216479 | 96 | 0 | [8 empty] | 00000102000000019832 | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-08-13 | ODST-0090022126_0010 | 0 | 3 | 0 | 0 | 2024-10-17 | 2024-10-26 | AA53 | 2024-10-21 |  |  | 2024-10-21 | 2024-10-20 | 2024-10-29 |  |  | 2024-12-31 | 0 | 5000214213_2024_0001 | 2024-10-22 |  | 2024-09-19 |  |  | 0 | 3 | 3 | 90022126 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000214213 |  | 0 | 2024 | /018006876 | 2024-10-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70011010 | Restriction Orifice Plate 41RO20 | 2024-08-12 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90022126_0010 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-09-18 | 30 |  | 2024-10-20 | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 |  |  | 5300006667 | 900 |  | 5300014053 | 10 | 1 | EA | 1001 | AA02 | 2024-10-22 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
700110146000028620000216479ta08900 | 600002862700110141 | 70011014 |  | 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-22 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0890 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(12.08.2024) | 70011014 | Restriction Orifice Plate 41RO21 | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | SPT Error TOP HU 102000000019832 - 2nd HU 101000000094290 | Supply for Order 600002862, Item 98 cannot be changed 90022126 item 20 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300014053 | 20 | CPT | 21 | 1000017114 | 98 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500026367 | 20 | 1 | EA | 2024-09-27 |  | /180068765 |  | 90022126 | 07 | Execution | 0000216479 | 98 | 0 | [8 empty] | 00000102000000019832 | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-08-13 | ODST-0090022126_0020 | 0 | 3 | 0 | 0 | 2024-10-17 | 2024-10-26 | AA53 | 2024-10-21 |  |  | 2024-10-21 | 2024-10-20 | 2024-10-29 |  |  | 2024-12-31 | 0 | 5000214221_2024_0001 | 2024-10-22 |  | 2024-09-19 |  |  | 0 | 3 | 3 | 90022126 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000214221 |  | 0 | 2024 | /018006876 | 2024-10-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70011014 | Restriction Orifice Plate 41RO21 | 2024-08-12 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90022126_0020 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-09-18 | 30 |  | 2024-10-20 | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 |  |  | 5300006667 | 910 |  | 5300014053 | 20 | 1 | EA | 1001 | AA02 | 2024-10-22 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
700138606000028620000216479ta02800 | 600002862700138601 | 70013860 |  | 24SDLN2C | Released | 2024-02-29 | 2025-02-25 | 2025-02-25 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0280 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue detected, please check message in derivation or orchestration log | 70013860 | SPADE BLIND 200MM CL150 FF A516 GR70 | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0 |  | ISSUE WITH MOZZIE NUMBER | Linked STO 5300014053 change failed for Order 600002862 Item 132 | PR approved; PO not issued | SP97 | Direct Multi-base | 20 | AA01 | 5300014053 | 140 |  | 20 | 1000020613 | 132 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 132 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  |  |  | Y | 1001 | 2024-08-13 | PRPO-1000020613_00132 | 0 | 25 | 0 | 25 | 2025-02-17 | 2025-03-08 | AA53 | 2024-11-22 |  |  | 2025-03-22 | 2025-02-23 | 2025-03-14 |  |  | 2024-12-31 | 0 |  | 2025-02-25 |  | 2025-03-14 |  |  | 0 | 6 | 6 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70013860 | SPADE BLIND 200MM CL150 FF A516 GR70 | 2024-10-04 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-01-20 | 30 |  | 2025-02-23 | 0 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 |  |  | 5300006667 | 1220 |  | 5300014053 | 140 | 1 | EA | 1001 | AA02 | 2025-02-25 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX

## Raw.2
Release id (" "=rel., X=not yet,1=never) | MO Revision | MO Status | MO Actual Release date | Requirement date (MO component) | Material Staging date (STO) | MO basic Start date | MO basic Finish date | MO Main work centre | MO number | Oper/Act number of Reservation | BOM item number | MO Description | Description | Functional location | Description | Procurement plant | Req Priority for Material/Component | Alert / Exception | Material / Component | Material Description | Requirement quantity | Requirement UOM | Stock on-hand @ Base | Stock In-Transit into Remote | Stock on-hand @ Remote | HU Quantity | UoM of HU | Expediting Note / User Comment | Message log(Orchestration / Derivation) | Supply status | Supply Process | Supply Process (Desc.) | Planned Deliver Time (in days) (PR) | Supplying Plant (STO) | Current STO | Current STO Item | Incoterms | Planned Delivery Time (in days) (STO) | Purchase Requisition | Purchase Requisition Item | Vendor | Name of Supplier | Vendor PO | Vendor PO item | PO qty | Requirement UOM | Delivery date (PO) | Batch/Valuation type(from MO component) | Inbound Delivery (PO) | Latest Inbound Delivery (STO) | Latest Outbound Delivery STO | Process Phase | Short Description | Reservation | Reservation Item | Reservation Item (reverse link) | Reservation item deletion indicator | UoM of HU | Nested HU Lvl 2 | Nested HU Lvl 3 | Top HU | Shipping Type | Voyage type | Voyage status | Container-ID | Linked Work-pack/HU | Workpack bin | Unloading Point | Incompletion indic. (Y/N) | Return STO | Return STO Item | Return STO Qty | Return STO UOM | Withdrawn quantity | Remaining quanity | Arrival (actual) | Arrival (plan) | Campaign (Y/N) | Company Code (STO) | Creation Date (STO) | Current document | Current STO Item has deletion code? | Delay @ Demand plant | Delay @ Procument plant | Delay @ Supply plant | Delivery date (PR) | Delivery date (STO) | Demand Plant | Early start date (MO) | Equipment | Description | ETA @ Demand plant | ETA @ Procument plant | ETA @ Supply plant | EWM task for GI (STO) | EWM Warehouse for GI (STO) | Final Due Date | GI qty (OBD for STO) | Good Receipt (PO) | Goods Issue date (STO) | Goods Issue Document (STO) | Goods Receipt End date (STO) | Goods Recipient | GR IBD Document (STO) | GR processing time | GR Processing time Demand plant (STO) | GR Processing time Supply plant (PR) | Ref Latest Outbound Delivery (STO) | GR qty (IBD for STO) | GR qty (PO) | Inbound Delivery (STO) | Internal alert code | Is PR Item Deleted? | Is Reservation Item Deleted(hard)? | isMessageThresholdBreached | Item category (BOM) | Latest GI (STO) | Latest GI STO Year | Latest GR (PO) | Latest GR IBD (STO) | Latest GR IBD Year(STO) | Latest GR PO Year | Latest IBD (PO) | Loading Date (STO) | Maint. Operation Exec. Stage Code | Maintenance Planning Plant | Name 1 | Maintenance Plant | Plant Name | Maintenance Storage Location | Material / Component description | Material Description | Message Text Date | Message Type | Oper. Phase Status | Operation / Activity | Operation description | Operation Control key | Operation description | Operation System Condition | Order Phase Status | Outbound Delivery (STO) | Person responsible | Picking bin | Plant Section | PO item deletion indic | Position | PR Processing State | Short Description | PR Release Indicator | Priority Type | Priority Type Text | Process Subphase | Subphase Description | Profile Status | Project stock | Purchasing Group | Purchasing Grp. Name | Purchasing group (STO) | Purchasing Grp. Name | Purchasing Organisation (STO) | Purchasing Processing time(PR) | Receiving Plant (STO) | Release date (PR) | Req Urgency for Material/Component | Request for Quotation | Requirements date (PR) | Reservation Special Stock Ind. | Responsible Buyer (for PO) | Return doc (MvT 262) | Revision | Revision Type | Voyage-id | Route (STO) | Routing number (of MO Operation) | Shipping Point (STO) | Status of Material (Demand Plant) | Status of Material (Supplying Plant) | STO (Supplying) - 1st STO | STO (Supplying) - 1st STO Item | STO Committed date (STO) | STO for SP97 (2nd STO) | STO for SP97 2ndS STO Item | STO quantity (STO) | STO quantity UoM (STO) | Storage Location (STO) based on MO | Supplying Plant | Transportation Planning date (STO) | User Responsible | User-status | Vehicle departure date | Vendor PO Pur Org | Warehouse | MO Actual Finish date | MO Actual Start date | MO Company Code | Company Name | MO Controlling Area | MO created by | MO creation date | MO from PR (reverse link) | MO item number | Stock on-hand @ Procurement Plant | MO Overall Status | Warehouse Number(STO) | MO overall status code | MO Planner Group | Planner Group Name | MO Priority | Priority Text | MO Responsible Cost Center | MO Scheduled Finish date | MO Scheduled Release date | MO Scheduled Start date | MO System Status | MO type | Order Type Name | MO WBS element
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0220 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10043687 | TEE:EQUAL,50mm,BW,CS,A234-WPB,SCH 40 | 4 | EA | 0 | 0 | 4 | 4 | EA | 05.10 - HU 101000000096674 to AA02 | Supply for Order 600002862, Item 121 cannot be changed 180085341 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085341 | 9017825 | 07 | Execution | 0000216479 | 121 | 121 | 0 | EA |  |  | 102000000021854 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255291_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000037301 | 1020 | 2024-12-31 | 4 |  | 2024-10-24 | 4900158479_2024_0001 | 2024-10-07 |  | 5000255291_2024_0001 | 0 | 2 | 0 | 90020228 | 4 | 0 | 180085341 | 2 | 0 | 0 | X | L | 4900158479 | 2024 |  | 5000255291 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10043687 | TEE:EQUAL,50mm,BW,CS,A234-WPB,SCH 40 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017825_0050 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 1130 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2025-03-17 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0100 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10048469 | FLANGE,BLIND;450MM,CL150,RF,CS,A105N | 1 | EA | 0 | 0 | 1 | 1 | EA | 14.10 - HU 101000000099504 TO AA02 | Supply for Order 600002862, Item 109 cannot be changed 180081148 item 10 already exists | Material work-packed @AA53 | SP97 | Direct Multi-base | 3 | AA02 | 5300006667 | 1010 | CPT | 7 | 1000018366 | 109 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500027121 | 90 | 1 | EA | 2024-10-07 |  | /180079843 | 180081280 | 90021679 | 07 | Execution | 0000216479 | 109 | 109 | 0 | EA |  |  | 101000000099504 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000242364_2024 | 0 | 0 | 0 | 0 | 2025-02-28 | 2025-03-20 | AA53 | 2024-11-22 |  |  | 2024-10-13 | 2025-03-02 | 2024-10-13 | 100000034938 | 1020 | 2024-12-31 | 1 | 5000240525_2024_0001 | 2024-10-13 | 4900151617_2024_0001 | 2024-10-11 |  | 5000242364_2024_0001 | 0 | 2 | 2 | 90021679 | 1 | 1 | 180081280 | 2 | 0 | 0 | X | L | 4900151617 | 2024 | 5000240525 | 5000242364 | 2024 | 2024 | /018007984 | 2025-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10048469 | FLANGE,BLIND;450MM,CL150,RF,CS,A105N | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90021679_0010 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-18 | 30 |  | 2025-03-02 |  | 0 |  | 24SDLN2C | MJ | 1000003675 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1010 |  | 5300014053 | 50 | 1 | EA | 2001 | AA02 | 2025-03-17 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0200 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Shipped qty below requirement qty | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 4 | EA | 0 | 0 | 3 | 1 | EA | 10.10 - Del 80018247/000070 for picking | Supply for Order 600002862, Item 119 cannot be changed 180080833 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085321 | 9017445 | 07 | Execution | 0000216479 | 119 | 119 | 0 | EA |  |  | 102000000020573 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255250_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000036571 | 1020 | 2024-12-31 | 3 |  | 2024-10-24 | 4900158458_2024_0003/4900150844_2024_0001 | 2024-10-07 |  | 5000255250_2024_0002/5000241125_2024_0001 | 0 | 2 | 0 | 90020228 | 3 | 0 | 180085321/180080833 | 1 | 0 | 0 | X | L | 4900158458 | 2024 |  | 5000255250 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020228_0030/9017445_0030/9016340_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003648 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1110 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-16 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0200 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Shipped qty below requirement qty | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 4 | EA | 0 | 0 | 3 | 2 | EA | 10.10 - Del 80018247/000070 for picking | Supply for Order 600002862, Item 119 cannot be changed 180080833 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085321 | 9017445 | 07 | Execution | 0000216479 | 119 | 119 | 0 | EA |  |  | 102000000021789 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255250_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000036571 | 1020 | 2024-12-31 | 3 |  | 2024-10-24 | 4900158458_2024_0003/4900150844_2024_0001 | 2024-10-07 |  | 5000255250_2024_0002/5000241125_2024_0001 | 0 | 2 | 0 | 90020228 | 3 | 0 | 180085321/180080833 | 1 | 0 | 0 | X | L | 4900158458 | 2024 |  | 5000255250 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020228_0030/9017445_0030/9016340_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1110 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-01 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0010 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10048528 | FLANGE,BLIND;150MM,CL300,RF,LTCS | 1 | EA | 0 | 0 | 1 | 1 | EA | 06.03 - ETA 17.04.24 PO 4500005010 x 1 Australasian Fittings | Supply for Order 600002862, Item 1 cannot be changed 9019562 item 370 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096189 | 9019562 | 07 | Execution | 0000216479 | 1 | 1 | 1 | EA |  |  | 102000000024278 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 1001 | 2024-02-16 | GRST-5000288015_2024 | 0 | 0 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000042070 | 1020 | 2024-12-31 | 1 |  | 2024-11-21 | 4900176329_2024_0001 | 2024-11-01 |  | 5000288015_2024_0001 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180096189 | 1 | 0 | 0 | X | L | 4900176329 | 2024 |  | 5000288015 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048528 | FLANGE,BLIND;150MM,CL300,RF,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9019562_0370 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004156 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 370 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-11-22 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0020 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10048552 | FLANGE,BLIND;600MM,CL600,RF,LTCS | 1 | EA | 0 | 0 | 1 | 1 | EA | 03.10 - HU 101000000060519 to AA02 | Supply for Order 600002862, Item 2 cannot be changed 180078362 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 2 | 2 | 0 | EA |  |  | 102000000020024 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000233767_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0001 | 2024-11-01 |  | 5000233767_2024_0001 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048552 | FLANGE,BLIND;600MM,CL600,RF,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0380 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003650 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 380 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0300 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2 | EA | 6 | 0 | 2 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 136 cannot be changed 9019874 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180095953 | 9019874 | 07 | Execution | 0000216479 | 136 | 136 | 0 | EA |  |  | 102000000024297 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 40 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042154 | 1020 | 2024-12-31 | 2 |  | 2024-11-20 | 4900176014_2024_0001 | 2024-11-24 |  | 5000287051_2024_0001 | 0 | 2 | 0 | 90024831 | 2 | 0 | 180095953 | 2 | 0 | 0 |  | L | 4900176014 | 2024 |  | 5000287051 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019874_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004183 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1260 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-21 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0320 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2 | EA | 6 | 0 | 2 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 138 cannot be changed 9019098 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096302 | 9019098 | 07 | Execution | 0000216479 | 138 | 138 | 0 | EA |  |  | 102000000024339 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000288422_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042336 | 1020 | 2024-12-31 | 2 |  | 2024-11-21 | 4900176518_2024_0001 | 2024-11-24 |  | 5000288422_2024_0001 | 0 | 2 | 0 | 90024832 | 2 | 0 | 180096302/180096308 | 2 | 0 | 0 |  | L | 4900176518 | 2024 |  | 5000288422 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019098_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004156 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1280 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-22 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0030 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10048593 | FLANGE,BLIND,150MM,CL150,RF,CS,SH40,GALV | 1 | EA | 0 | 0 | 1 | 1 | EA | 03.10 - GR ZONE @ AA02 | Supply for Order 600002862, Item 3 cannot be changed 180083185 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 3 | 3 | 0 | EA | 101000000093418 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0003 | 2024-11-01 |  | 5000248569_2024_0002 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048593 | FLANGE,BLIND,150MM,CL150,RF,CS,SH40,GALV | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0390 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 390 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0040 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10048594 | FLANGE,BLIND;200MM,CL150,RF,CS,SH30,GALV | 7 | EA | 0 | 0 | 0 | 7 | EA | 03.10 - HU 101000000052150 to AA02 | Supply for Order 600002862, Item 4 cannot be changed 180078362 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 4 | 4 | 0 | EA |  |  | 102000000020023 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 7 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 7 |  | 2024-10-06 | 4900146921_2024_0003 | 2024-11-01 |  | 5000233767_2024_0002 | 0 | 2 | 0 | 90006343 | 7 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048594 | FLANGE,BLIND;200MM,CL150,RF,CS,SH30,GALV | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0400 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 400 |  |  | 0 | 7 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0050 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10048596 | FLANGE,BLIND;300MM,CL150,RF,CS,SH30,GALV | 5 | EA | 0 | 0 | 0 | 5 | EA | 01.10 - HU 101000000052151 TO AA02 OLS5307169 | Supply for Order 600002862, Item 5 cannot be changed 180078362 item 30 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 5 | 5 | 0 | EA |  |  | 102000000020020 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 5 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 5 |  | 2024-10-06 | 4900146921_2024_0005 | 2024-11-01 |  | 5000233767_2024_0003 | 0 | 2 | 0 | 90006343 | 5 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048596 | FLANGE,BLIND;300MM,CL150,RF,CS,SH30,GALV | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0410 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 410 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0060 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Shipped qty below requirement qty | 10049289 | FLANGE,BLIND;50MM,CL300,RF,SS316 | 2 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000093006 TO AA02 | Supply for Order 600002862, Item 6 cannot be changed 180083185 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 6 | 6 | 0 | EA | 101000000093006 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0005 | 2024-11-01 |  | 5000248569_2024_0003 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 1 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049289 | FLANGE,BLIND;50MM,CL300,RF,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0420/9016679_0420 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 420 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0810 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10049295 | FLANGE,BLIND;300MM,CL300,RF,SS316 | 1 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000076282 TO AA02 | Supply for Order 600002862, Item 81 cannot be changed 180078362 item 60 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 81 | 81 | 0 | EA |  |  | 102000000020026 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0011 | 2024-11-01 |  | 5000233767_2024_0006 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049295 | FLANGE,BLIND;300MM,CL300,RF,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0820 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 820 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0770 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10049310 | FLANGE,BLIND;80MM,CL600,RF,SS316 | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000093021 TO AA02 | Supply for Order 600002862, Item 77 cannot be changed 180083185 item 160 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 77 | 77 | 0 | EA | 101000000093021 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0031 | 2024-11-01 |  | 5000248569_2024_0016 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049310 | FLANGE,BLIND;80MM,CL600,RF,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0780 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 780 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0110 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 |  | 30 | Maintenance Order material has been deleted | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 1 | EA | 0 | 0 | 0 | 0 |  | 02.10 - ETA 17.12.24 PO 4500029495 AUS FITTINGS @AA02 | Supply for Order 600002862, Item 110 cannot be changed – 4500029495 already exists | Shipping notification from Vendor received | SP14 | Directs (Inventory) | 48 | AA02 | 5300006667 | 1020 | CPT | 7 | 1000018365 | 110 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500029495 | 10 | 1 | EA | 2024-10-28 |  | /180085785 |  |  | 07 | Execution | 0000216479 | 110 | 110 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  |  | 1001 | 2024-02-16 | IDPO-/018008578 | 1 | 35 | 0 | 35 | 2024-11-12 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-19 |  | 2024-11-14 |  |  | 2024-12-31 | 0 |  | 2024-10-10 |  | 2024-10-15 |  |  | 0 | 2 | 2 |  | 0 | 0 |  | 1 | 1 | 0 | X | L |  | 0 |  |  | 0 | 0 | /018008578 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 | L |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-20 | 30 |  | 2024-11-14 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1020 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0310 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 1 | EA | 0 | 1 | 0 | 1 | EA | UserCommentLink | Supply for Order 600002862, Item 137 cannot be changed 90024752 item 10 already exists | Material In-Transit on-01-Road | SP97 | Direct Multi-base | 48 | AA01 | 5300014053 | 150 | CPT | 48 | 1000023553 | 137 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500029495 | 20 | 1 | EA | 2024-11-29 |  | 180095811 | 180096725 | 90024752 | 07 | Execution | 0000216479 | 137 | 0 | 0 | EA |  |  | 101000000113674 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  | 2024-11-23 | Y | 1001 | 2024-08-13 | IDST-0180096725 | 0 | 108 | 57 | 68 | 2025-01-13 | 2024-11-17 | AA53 | 2024-11-22 |  |  | 2025-03-12 | 2025-01-15 | 2025-01-26 | 100000234894 | 1010 | 2024-12-31 | 1 | 5000286236_2024_0001 | 2024-11-22 | 4900177044_2024_0001 | 2024-11-20 |  |  | 0 | 2 | 2 | 90024752 | 0 | 1 | 180096725 | 2 | 0 | 0 |  | L | 4900177044 | 2024 | 5000286236 |  | 0 | 2024 | 180095811 | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90024752_0010 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-11-19 | 30 |  | 2025-01-15 |  | 0 |  | 24SDLN2C | MJ | 20003646 | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1270 |  | 5300014053 | 150 | 1 | EA | 1001 | AA02 | 2024-11-19 |  |  | 2024-11-21 | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0050 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10052675 | SPADE BLIND,350MM,CL300,RF,A516-60 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 104 cannot be changed 90020227 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 960 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020227 | 07 | Execution | 0000216479 | 104 | 104 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | ODST-0090020227_0030 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-10 |  | 2024-10-15 |  |  | 0 | 2 | 0 | 90020227 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052675 | SPADE BLIND,350MM,CL300,RF,A516-60 | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020227_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 960 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0070 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 4 | EA | 0 | 0 | 0 | 0 |  | 24.10 - ETA 05.12.24 PO 4500029844 MRC | Supply for Order 600002862, Item 7 cannot be changed 90006343 item 430 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006343 | 07 | Execution | 0000216479 | 7 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-02-16 | ODST-0090006343_0430 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-29 |  | 2024-11-01 |  |  | 0 | 2 | 0 | 90006343 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0430 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 430 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0190 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 4 | EA | 0 | 0 | 0 | 4 | EA | 03.10 - HU 101000000094431 to AA02 | Supply for Order 600002862, Item 118 cannot be changed 180078363 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078363 | 9015653 | 07 | Execution | 0000216479 | 118 | 118 | 0 | EA |  |  | 102000000020021 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 4 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000033541 | 1020 | 2024-12-31 | 4 |  | 2024-10-06 | 4900146945_2024_0001 | 2024-10-07 |  | 5000233793_2024_0001 | 0 | 2 | 0 | 90020228 | 4 | 0 | 180078363 | 2 | 0 | 0 | X | L | 4900146945 | 2024 |  | 5000233793 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015653_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 1100 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0750 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10052685 | SPADE BLIND,600MM,CL600,RF,LTCS | 1 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000060720 TO AA02 | Supply for Order 600002862, Item 75 cannot be changed 180078362 item 50 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 75 | 75 | 0 | EA |  |  | 102000000020029 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0009 | 2024-11-01 |  | 5000233767_2024_0005 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052685 | SPADE BLIND,600MM,CL600,RF,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0760 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 760 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0780 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10052696 | SPADE BLIND,150MM,CL150,CS,A285 GR.C | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000093390 TO AA02 | Supply for Order 600002862, Item 78 cannot be changed 180083185 item 170 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 78 | 78 | 0 | EA | 101000000093390 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0033 | 2024-11-01 |  | 5000248569_2024_0017 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10052696 | SPADE BLIND,150MM,CL150,CS,A285 GR.C | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0790 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 790 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 |  | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(11.03.2024) | 10053011 | SPADE BLIND,150MM,CL300,SS316 | 1 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000094436 TO AA02 | Supply for Order 600002862, Item 89 cannot be changed 180078362 item 100 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 89 | 89 | 0 | EA |  |  | 102000000020022 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0019 | 2024-11-01 |  | 5000233767_2024_0010 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10053011 | SPADE BLIND,150MM,CL300,SS316 | 2024-03-11 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0870 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 870 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 |  | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(11.03.2024) | 10053014 | SPADE BLIND,300MM,CL300,SS316 | 1 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000094436 TO AA02 | Supply for Order 600002862, Item 88 cannot be changed 180078362 item 90 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 88 | 88 | 0 | EA |  |  | 102000000020022 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0017 | 2024-11-01 |  | 5000233767_2024_0009 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10053014 | SPADE BLIND,300MM,CL300,SS316 | 2024-03-11 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0860 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 860 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0080 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10053093 | SPADE BLIND,150MM,CL300,SS,TP316L | 1 | EA | 0 | 0 | 1 | 1 | EA | 16.10 - 180082367 4500005381, 103 ERRORS | Supply for Order 600002862, Item 8 cannot be changed 180085320 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 8 | 8 | 0 | EA |  |  | 102000000021853 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0005 | 2024-11-01 |  | 5000255235_2024_0003 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10053093 | SPADE BLIND,150MM,CL300,SS,TP316L | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0440 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 440 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0090 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058201 | STUDBOLT;0.625" X 100MM,A193 B8M CL2 | 16 | EA | 24 | 0 | 120 | 16 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 9 cannot be changed 180017143 item 310 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 9 | 9 | 0 | EA | 102000000004373 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 16 |  | 2024-04-11 | 4900045283_2024_0061 | 2024-11-01 |  | 5000058191_2024_0031 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058201 | STUDBOLT;0.625" X 100MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0450 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 450 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0100 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10058202 | STUDBOLT;0.625" X 110MM,A193 B8M CL2 | 20 | EA | 21 | 0 | 0 | 20 | EA | 21.09 - MW2R11C02G @ KSF | Supply for Order 600002862, Item 10 cannot be changed 180017143 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 10 | 10 | 0 | EA | 102000000003646 | 102000000003612 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 20 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 20 |  | 2024-04-11 | 4900045283_2024_0001 | 2024-11-01 |  | 5000058191_2024_0001 | 0 | 2 | 0 | 90006343 | 20 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058202 | STUDBOLT;0.625" X 110MM,A193 B8M CL2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 20 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0110 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 8 | EA | 10 | 8 | 8 | 5 | EA | 01.10 - HU 101000000092978, 93001 TO AA02 | Supply for Order 600002862, Item 11 cannot be changed 180083185 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 11 | 11 | 0 | EA | 101000000092978 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 8 |  | 2024-10-18 | 4900154759_2024_0007 | 2024-11-01 |  | 5000248569_2024_0004 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0460 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 460 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0110 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 8 | EA | 10 | 8 | 8 | 3 | EA | 01.10 - HU 101000000092978, 93001 TO AA02 | Supply for Order 600002862, Item 11 cannot be changed 180083185 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 11 | 11 | 0 | EA | 101000000093001 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 8 |  | 2024-10-18 | 4900154759_2024_0007 | 2024-11-01 |  | 5000248569_2024_0004 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0460 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 460 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0120 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10058205 | STUDBOLT;0.625" X 130MM,A193 B8M CL2 | 8 | EA | 44 | 0 | 0 | 8 | EA | 22.09 - IN GREY TUB / MW2R11C03G @ KSF | Supply for Order 600002862, Item 12 cannot be changed 180017143 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 12 | 12 | 0 | EA | 102000000003646 | 102000000003613 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 8 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0003 | 2024-11-01 |  | 5000058191_2024_0002 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058205 | STUDBOLT;0.625" X 130MM,A193 B8M CL2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 30 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0130 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 28 | EA | 4 | 0 | 3 | 13 | EA | 03.10 - Del 90009764/90009765 15-05-10-03CB @ AA01 | Supply for Order 600002862, Item 13 cannot be changed 180017143 item 320 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085779 | 9017334 | 07 | Execution | 0000216479 | 13 | 13 | 0 | EA | 102000000004373 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 13 | 15 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037409 | 1020 | 2024-12-31 | 16 |  | 2024-10-25 | 4900159071_2024_0001/4900045283_2024_0063 | 2024-11-01 |  | 5000256709_2024_0001/5000058191_2024_0032 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180085779/180017143 | 2 | 0 | 0 | X | L | 4900159071 | 2024 |  | 5000256709 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0470/9017334_0470/9002109_0470 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 470 |  |  | 0 | 28 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0130 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 28 | EA | 4 | 0 | 3 | 3 | EA | 03.10 - Del 90009764/90009765 15-05-10-03CB @ AA01 | Supply for Order 600002862, Item 13 cannot be changed 180017143 item 320 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085779 | 9017334 | 07 | Execution | 0000216479 | 13 | 13 | 0 | EA |  |  | 101000000100284 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 13 | 15 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037409 | 1020 | 2024-12-31 | 16 |  | 2024-10-25 | 4900159071_2024_0001/4900045283_2024_0063 | 2024-11-01 |  | 5000256709_2024_0001/5000058191_2024_0032 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180085779/180017143 | 2 | 0 | 0 | X | L | 4900159071 | 2024 |  | 5000256709 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0470/9017334_0470/9002109_0470 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 470 |  |  | 0 | 28 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0140 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 12 | EA | 4 | 0 | 8 | 8 | EA | 01.10 - HU 101000000094405 TO AA02 | Supply for Order 600002862, Item 14 cannot be changed 180083185 item 50 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085865 | 9017454 | 07 | Execution | 0000216479 | 14 | 14 | 0 | EA | 101000000094405 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 4 | 8 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037615 | 1020 | 2024-12-31 | 12 |  | 2024-10-25 | 4900159231_2024_0001/4900154759_2024_0009 | 2024-11-01 |  | 5000257049_2024_0001/5000248569_2024_0005 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180083185/180085865 | 2 | 0 | 0 | X | L | 4900159231 | 2024 |  | 5000257049 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017454_0480/9016679_0480 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 480 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0140 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 12 | EA | 4 | 0 | 8 | 4 | EA | 01.10 - HU 101000000094405 TO AA02 | Supply for Order 600002862, Item 14 cannot be changed 180083185 item 50 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085865 | 9017454 | 07 | Execution | 0000216479 | 14 | 14 | 0 | EA |  |  | 102000000022071 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  | 4 | 8 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037615 | 1020 | 2024-12-31 | 12 |  | 2024-10-25 | 4900159231_2024_0001/4900154759_2024_0009 | 2024-11-01 |  | 5000257049_2024_0001/5000248569_2024_0005 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180083185/180085865 | 2 | 0 | 0 | X | L | 4900159231 | 2024 |  | 5000257049 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017454_0480/9016679_0480 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 480 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0150 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 16 | EA | 0 | 0 | 8 | 8 | EA | 03.10 - Del 80018277/000010 for picking | Supply for Order 600002862, Item 15 cannot be changed 180085320 item 40 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085865 | 9017454 | 07 | Execution | 0000216479 | 15 | 15 | 0 | EA | 101000000097561 |  | 102000000021787 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 8 | 8 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037615 | 1020 | 2024-12-31 | 16 |  | 2024-10-25 | 4900159231_2024_0003/4900158497_2024_0007 | 2024-11-01 |  | 5000257049_2024_0002/5000255235_2024_0004 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180085320/180085865 | 2 | 0 | 0 | X | L | 4900159231 | 2024 |  | 5000257049 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017454_0490/9017444_0490 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 490 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0150 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 16 | EA | 0 | 0 | 8 | 8 | EA | 03.10 - Del 80018277/000010 for picking | Supply for Order 600002862, Item 15 cannot be changed 180085320 item 40 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085865 | 9017454 | 07 | Execution | 0000216479 | 15 | 15 | 0 | EA |  |  | 102000000022070 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  | 8 | 8 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037615 | 1020 | 2024-12-31 | 16 |  | 2024-10-25 | 4900159231_2024_0003/4900158497_2024_0007 | 2024-11-01 |  | 5000257049_2024_0002/5000255235_2024_0004 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180085320/180085865 | 2 | 0 | 0 | X | L | 4900159231 | 2024 |  | 5000257049 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017454_0490/9017444_0490 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 490 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0160 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10058262 | BLT STUD:1.125in,190mm,316 SS,2,UN HEAVY | 16 | EA | 4 | 0 | 0 | 16 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 16 cannot be changed 180017143 item 30 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 16 | 16 | 0 | EA | 102000000003619 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 16 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 16 |  | 2024-04-11 | 4900045283_2024_0005 | 2024-11-01 |  | 5000058191_2024_0003 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058262 | BLT STUD:1.125in,190mm,316 SS,2,UN HEAVY | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0040 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 40 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0730 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 24 | EA | 2 | 0 | 26 | 20 | EA | 01.10 - HU 101000000094101 - 08 TO AA02 | Supply for Order 600002862, Item 73 cannot be changed 180083185 item 150 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 73 | 73 | 0 | EA | 102000000019834 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 2 | 22 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 24 |  | 2024-10-18 | 4900154759_2024_0029/4900143400_2024_0001/4900045283_2024_0069 | 2024-11-01 |  | 5000248569_2024_0015/5000227725_2024_0001/5000058191_2024_0035 | 0 | 2 | 0 | 90006343 | 24 | 0 | 180083185/180076528/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0740/9014976_0740/9002109_0740 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 740 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0730 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 24 | EA | 2 | 0 | 26 | 2 | EA | 01.10 - HU 101000000094101 - 08 TO AA02 | Supply for Order 600002862, Item 73 cannot be changed 180083185 item 150 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 73 | 73 | 0 | EA | 102000000018977 |  | 107000000000076 |  |  |  | STATIC-CAGE | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 2 | 22 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 24 |  | 2024-10-18 | 4900154759_2024_0029/4900143400_2024_0001/4900045283_2024_0069 | 2024-11-01 |  | 5000248569_2024_0015/5000227725_2024_0001/5000058191_2024_0035 | 0 | 2 | 0 | 90006343 | 24 | 0 | 180083185/180076528/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0740/9014976_0740/9002109_0740 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 740 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0730 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 24 | EA | 2 | 0 | 26 | 2 | EA | 01.10 - HU 101000000094101 - 08 TO AA02 | Supply for Order 600002862, Item 73 cannot be changed 180083185 item 150 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 73 | 73 | 0 | EA | 102000000003618 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 2 | 22 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 24 |  | 2024-10-18 | 4900154759_2024_0029/4900143400_2024_0001/4900045283_2024_0069 | 2024-11-01 |  | 5000248569_2024_0015/5000227725_2024_0001/5000058191_2024_0035 | 0 | 2 | 0 | 90006343 | 24 | 0 | 180083185/180076528/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0740/9014976_0740/9002109_0740 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 740 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0170 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10059968 | GASKET;CNAF,50MM,CL150,TANG INTN,1.6MM | 2 | EA | 4 | 0 | 0 | 2 | EA | 22.09 - IN GREY TUB / MW2R05F11H @ KSF | Supply for Order 600002862, Item 17 cannot be changed 180017143 item 40 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 17 | 17 | 0 | EA | 102000000003646 | 102000000003620 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0007 | 2024-11-01 |  | 5000058191_2024_0004 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059968 | GASKET;CNAF,50MM,CL150,TANG INTN,1.6MM | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0050 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0180 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10059971 | GASKET;CNAF,150MM,CL150,TANG INTN,1.6MM | 1 | EA | 1 | 0 | 2 | 0 |  | 01.10 - HU 101000000092373 TO AA02 | Supply for Order 600002862, Item 18 cannot be changed 90006343 item 500 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006343 | 07 | Execution | 0000216479 | 18 | 18 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | ODST-0090006343_0500 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-29 |  | 2024-11-01 |  |  | 0 | 2 | 0 | 90006343 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059971 | GASKET;CNAF,150MM,CL150,TANG INTN,1.6MM | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0500 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 500 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0190 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10059972 | GASKET;CNAF,200MM,CL150,TANG INTN,1.5MM | 8 | EA | 4 | 0 | 0 | 8 | EA | X1 LOOSE | Supply for Order 600002862, Item 19 cannot be changed 180017143 item 50 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 19 | 19 | 0 | EA | 102000000003665 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 8 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0009 | 2024-11-01 |  | 5000058191_2024_0005 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059972 | GASKET;CNAF,200MM,CL150,TANG INTN,1.5MM | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 60 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0200 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 | 2 | EA | 106 | 1 | 102 | 2 | EA | 03.10 - KSF-PACK-REV-SML for picking | Supply for Order 600002862, Item 20 cannot be changed 180085320 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 20 | 20 | 0 | EA |  |  | 102000000021841 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0009 | 2024-11-01 |  | 5000255235_2024_0005 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0510 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 510 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0210 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 4 | EA | 36 | 10 | 60 | 4 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 21 cannot be changed 180059148 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180059148 | 9010626 | 07 | Execution | 0000216479 | 21 | 21 | 0 | EA | 102000000013914 |  | 102000000005501 |  |  |  | LP-SD-14 | WorkPackLink | KSF-KGP P07P08 SML |  | 0 |  | 0 | 0 |  | 4 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000024047 | 1020 | 2024-12-31 | 4 |  | 2024-08-19 | 4900113231_2024_0001 | 2024-11-01 |  | 5000213867_2024_0001 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180059148 | 2 | 0 | 0 | X | L | 4900113231 | 2024 |  | 5000213867 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9010626_0520 |  |  | LN2 |  | A3 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 520 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0220 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 2 | EA | 35 | 11 | 86 | 2 | EA | 21.09 - MW2R03C03J @ KSF | Supply for Order 600002862, Item 22 cannot be changed 180085320 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 22 | 22 | 0 | EA |  |  | 102000000021788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0001 | 2024-11-01 |  | 5000255235_2024_0001 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0070 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 70 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0230 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10060888 | GASKET;SWCI,150MM,CL150,316L/GR/316 | 4 | EA | 0 | 0 | 12 | 4 | EA | 01.10 - HU 101000000093005 TO AA02 | Supply for Order 600002862, Item 23 cannot be changed 180083185 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 23 | 23 | 0 | EA | 101000000093005 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 4 |  | 2024-10-18 | 4900154759_2024_0011 | 2024-11-01 |  | 5000248569_2024_0006 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET;SWCI,150MM,CL150,316L/GR/316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0530 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 530 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0240 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060892 | GASKET;SWCI,350MM,CL150,316L/GR/316 | 2 | EA | 4 | 0 | 7 | 2 | EA | 03.10 - SW3R03E02B @ AA02 | Supply for Order 600002862, Item 24 cannot be changed 180085320 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 24 | 24 | 0 | EA | 102000000021786 |  | 107000000000076 |  |  |  | STATIC-CAGE | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0003 | 2024-11-01 |  | 5000255235_2024_0002 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060892 | GASKET;SWCI,350MM,CL150,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0080 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0250 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060894 | GASKET;SWCI,450MM,CL150,316L/GR/316 | 2 | EA | 10 | 0 | 3 | 2 | EA | 22.09 - X1 LOOSE / MW2R04J02B @ KSF | Supply for Order 600002862, Item 25 cannot be changed 180017143 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 25 | 25 | 0 | EA | 102000000003633 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0011 | 2024-11-01 |  | 5000058191_2024_0006 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060894 | GASKET;SWCI,450MM,CL150,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0090 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 90 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-30 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0260 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060901 | GASKET;SWCI,100MM,CL300,SS316L/GR/316 | 2 | EA | 38 | 6 | 38 | 2 | EA | 21.09 - MW2R03A02A @ KSF | Supply for Order 600002862, Item 26 cannot be changed 180017143 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 26 | 26 | 0 | EA | 102000000003646 | 102000000003635 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0013 | 2024-11-01 |  | 5000058191_2024_0007 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060901 | GASKET;SWCI,100MM,CL300,SS316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0100 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 |  | 1000214854 | S002 | 30 | 30 | 5300006667 | 100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-30 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0270 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10060902 | GASKET;SWCI,150MM,CL300,316L/GR/316 | 4 | EA | 4 | 12 | 2 | 4 | EA | 22.09 - IN GREY TUB / MW2R04F02A @ KSF | Supply for Order 600002862, Item 27 cannot be changed 180017143 item 330 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 27 | 27 | 0 | EA | 102000000003646 | 102000000003684 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 4 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045283_2024_0065 | 2024-11-01 |  | 5000058191_2024_0033 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET;SWCI,150MM,CL300,316L/GR/316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0540 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 540 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0280 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060904 | GASKET;SWCI,250MM,CL300,316L/GR/316 | 2 | EA | 13 | 8 | 13 | 2 | EA | 22.09 - X1 LOOSE / MW2R03A03E @ KSF | Supply for Order 600002862, Item 28 cannot be changed 180017143 item 80 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 28 | 28 | 0 | EA | 102000000003632 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0015 | 2024-11-01 |  | 5000058191_2024_0008 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060904 | GASKET;SWCI,250MM,CL300,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0110 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 110 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0290 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060905 | GASKET;SWCI,300MM,CL300,316L/GR/316 | 1 | EA | 3 | 0 | 10 | 1 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 29 cannot be changed 180017143 item 90 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 29 | 29 | 0 | EA | 102000000003625 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 1 |  | 2024-04-11 | 4900045283_2024_0017 | 2024-11-01 |  | 5000058191_2024_0009 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060905 | GASKET;SWCI,300MM,CL300,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0120 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0300 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 4 | EA | 11 | 0 | 8 | 4 | EA | 22.09 - X1 LOOSE / MW2R04J03D @ KSF | Supply for Order 600002862, Item 30 cannot be changed 180017143 item 100 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 30 | 30 | 1 | EA | 102000000003634 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045283_2024_0019 | 2024-11-01 |  | 5000058191_2024_0010 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180017143 | 1 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0130 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 130 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0900 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(04.10.2024) | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 4 | EA | 11 | 0 | 8 | 4 | EA | UserCommentLink | Supply for Order 600002862, Item 130 cannot be changed 180083292 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083292 | 90021285 | 07 | Execution | 0000216479 | 130 | 130 | 0 | EA | 102000000021301 |  | 107000000000076 |  |  |  | STATIC-CAGE | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 4 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-10-21 |  |  | 2024-10-15 |  |  | 100000035929 | 1020 | 2024-12-31 | 4 |  | 2024-10-18 | 4900154888_2024_0001 | 2024-10-15 |  | 5000248724_2024_0001 | 0 | 2 | 0 | 90021285 | 4 | 0 | 180083292 | 2 | 0 | 0 | X | L | 4900154888 | 2024 |  | 5000248724 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 2024-10-04 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90021285_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1210 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0310 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060907 | GASKET;SWCI,400MM,CL300,SS316L/GR/316 | 8 | EA | 7 | 0 | 12 | 8 | EA | 22.09 - X1 LOOSE / MW2R05E07D @ KSF | Supply for Order 600002862, Item 31 cannot be changed 180017143 item 110 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 31 | 31 | 0 | EA | 102000000003637 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0021 | 2024-11-01 |  | 5000058191_2024_0011 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060907 | GASKET;SWCI,400MM,CL300,SS316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0140 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 140 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0320 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 12 | EA | 223 | 20 | 534 | 12 | EA | 22.09 - IN GREY TUB / MW2R03B03A @ KSF | Supply for Order 600002862, Item 32 cannot be changed 180017143 item 120 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 32 | 32 | 0 | EA | 102000000003646 | 102000000003636 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 12 |  | 2024-04-11 | 4900045283_2024_0023 | 2024-11-01 |  | 5000058191_2024_0012 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0150 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 150 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-01 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10060920 | GASKET:RF,80mm,4.5mm,316L,CL300,SWCI,GR | 4 | EA | 0 | 3 | 8 | 4 | EA | 21.09 - 10-16-11-02B @ PDC X 3 | Supply for Order 600002862, Item 33 cannot be changed 180017143 item 130 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 33 | 33 | 1 | EA | 102000000003646 | 102000000003622 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 0 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045283_2024_0025 | 2024-11-01 |  | 5000058191_2024_0013 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180017143 | 1 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060920 | GASKET:RF,80mm,4.5mm,316L,CL300,SWCI,GR | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0160 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 74 | 74 | 5300006667 | 160 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-22 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0290 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.10.2024) | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 6 | EA | 102 | 0 | 83 | 0 |  | UserCommentLink | Supply for Order 600002862, Item 134 cannot be changed 90025334 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025334 | 07 | Execution | 0000216479 | 134 | 134 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-02-16 | ODST-0090025334_0010 | 0 | 5 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-27 |  |  |  |  | 2024-12-31 | 0 |  | 2024-11-22 |  | 2024-11-27 |  |  | 0 | 2 | 0 | 90025334 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2024-10-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90025334_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1240 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-11-22 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0340 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 4 | EA | 102 | 0 | 83 | 4 | EA | 22.09 - IN GREY TUB / MW2R03A02C @ KSF | Supply for Order 600002862, Item 34 cannot be changed 180017143 item 140 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 34 | 34 | 0 | EA | 102000000003646 | 102000000003624 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045283_2024_0027 | 2024-11-01 |  | 5000058191_2024_0014 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0170 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 170 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0350 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 2 | EA | 5 | 8 | 0 | 2 | EA | 22.09 - IN GREY TUB / MW2R04J02D @KSF | Supply for Order 600002862, Item 35 cannot be changed 180017143 item 150 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 35 | 35 | 0 | EA | 102000000003646 | 102000000003629 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0029 | 2024-11-01 |  | 5000058191_2024_0015 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0180 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 180 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0710 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060939 | GASKET;SWCI,450MM,CL600,316L/GR/316 | 12 | EA | 6 | 0 | 0 | 12 | EA | 22.09 - X4 FLAT PACKS / 4 SOH @ KSF /180071538 75KG 18.09.24 PO 4500024711 | Supply for Order 600002862, Item 71 cannot be changed 180017143 item 290 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 71 | 71 | 0 | EA | 102000000003628 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 12 |  | 2024-04-11 | 4900045283_2024_0057 | 2024-11-01 |  | 5000058191_2024_0029 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060939 | GASKET;SWCI,450MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0330 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 330 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0360 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 1 | EA | 29 | 0 | 9 | 1 | EA | 21.09 - MW2R04H04A @ KSF / X1 FLAT PACK | Supply for Order 600002862, Item 36 cannot be changed 180017143 item 160 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 36 | 36 | 0 | EA | 102000000003626 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 1 |  | 2024-04-11 | 4900045283_2024_0031 | 2024-11-01 |  | 5000058191_2024_0016 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0190 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0720 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 6 | EA | 29 | 0 | 9 | 6 | EA | 25.09 - At KGP | Supply for Order 600002862, Item 72 cannot be changed 180017143 item 300 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 72 | 72 | 0 | EA | 102000000003627 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 6 |  | 2024-04-11 | 4900045283_2024_0059 | 2024-11-01 |  | 5000058191_2024_0030 | 0 | 2 | 0 | 90006343 | 6 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0340 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 340 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0370 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10061003 | GASKET;SWCI,1050MM,CL150,316L/GR/316 | 2 | EA | 4 | 0 | 0 | 2 | EA | X1 PALLET | Supply for Order 600002862, Item 37 cannot be changed 180017143 item 170 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 37 | 37 | 0 | EA |  |  | 102000000003630 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 2 |  | 2024-04-11 | 4900045283_2024_0033 | 2024-11-01 |  | 5000058191_2024_0017 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061003 | GASKET;SWCI,1050MM,CL150,316L/GR/316 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0200 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 200 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2025-03-17 | 2025-03-17 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | X | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 |  | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(03.10.2024) | 10062985 | AIR,MEDICAL,DRY,COMPRESSED,SIZE G CYL | 2 | CYL | 0 | 0 | 2 | 2 | CYL | 14.10 - ETA 18.10.24 PO 4500031439 BOC | Supply for Order 600002862, Item 128 cannot be changed 9016849 item 40 already exists | Material work-packed @AA53 | SP14 | Directs (Inventory) | 2 | AA02 | 5300006667 | 1190 | CPT | 14 | 1000020500 | 128 | 30000395 | BOC LIMITED | 4500031439 | 10 | 2 | CYL | 2024-10-18 |  | 180083823/180083823/ | 180083825 | 9016849 | 07 | Execution | 0000216479 | 128 | 128 | 0 | CYL |  |  | 102000000021412 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000249608_2024 | 0 | 5 | 0 | 0 | 2025-03-15 | 2025-03-20 | AA53 | 2024-11-22 |  |  | 2025-03-22 |  | 2025-03-17 | 100000036129 | 1020 | 2024-12-31 | 2 | 5000249607_2024_0001 | 2024-10-19 | 4900155774_2024_0001 | 2024-10-19 |  | 5000249608_2024_0001 | 0 | 2 | 2 | 90022091 | 2 | 2 | 180083825 | 2 | 0 | 0 | X | L | 4900155774 | 2024 | 5000249607 | 5000249608 | 2024 | 2024 | 180083823 | 2025-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062985 | AIR,MEDICAL,DRY,COMPRESSED,SIZE G CYL | 2024-10-03 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9016849_0040 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-08 | 30 |  | 2025-03-17 |  | 31522 |  | 24SDLN2C | MJ | 1000003773 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1190 |  |  | 0 | 2 | CYL | 2001 | AA02 | 2025-03-17 |  |  | 2024-10-24 | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0700 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 6 | M | 0 | 0 | 24 | 6 | M | 14.10 - HU 101000000056226 TO AA02 | Supply for Order 600002862, Item 70 cannot be changed 180082338 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  | 180082338 | 9016520 | 07 | Execution | 0000216479 | 70 | 70 | 0 | M |  |  | 101000000056226 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000245960_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035353 | 1020 | 2024-12-31 | 6 |  | 2024-10-16 | 4900153435_2024_0001 | 2024-11-01 |  | 5000245960_2024_0001 | 0 | 2 | 0 | 90006343 | 6 | 0 | 180082338 | 2 | 0 | 0 | X | L | 4900153435 | 2024 |  | 5000245960 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016520_0320 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003713 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 320 |  |  | 0 | 6 | M | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-19 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0210 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 6 | M | 0 | 0 | 24 | 6 | M | 14.10 - HU 101000000099762 TO AA02 | Supply for Order 600002862, Item 120 cannot be changed 180082339 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1120 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  | 180082339 | 9016521 | 07 | Execution | 0000216479 | 120 | 120 | 0 | M |  |  | 101000000099762 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000245932_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000035354 | 1020 | 2024-12-31 | 6 |  | 2024-10-16 | 4900153423_2024_0001 | 2024-10-07 |  | 5000245932_2024_0001 | 0 | 2 | 0 | 90020228 | 6 | 0 | 180082339 | 2 | 0 | 0 | X | L | 4900153423 | 2024 |  | 5000245932 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9016521_0040 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003724 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1120 |  |  | 0 | 6 | M | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-19 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | EA | 0 | 0 | 11 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 139 | 0 | EA |  |  | 101000000114000 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | EA | 0 | 0 | 11 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 139 | 0 | EA |  |  | 101000000113788 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | EA | 0 | 0 | 11 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 139 | 0 | EA |  |  | 101000000113971 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | EA | 0 | 0 | 11 | 2 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 139 | 0 | EA |  |  | 101000000114001 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | EA | 0 | 0 | 11 | 1 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 139 | 0 | EA |  |  | 101000000113529 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-22 | 2024-11-19 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0330 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 10 | EA | 0 | 0 | 11 | 1 | EA | UserCommentLink | Supply for Order 600002862, Item 139 cannot be changed 9019099 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096309 | 9019099 | 07 | Execution | 0000216479 | 139 | 139 | 0 | EA |  |  | 101000000113698 | 06-Air Passenger |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 | 2024-11-21 | 2024-11-21 | Y | 1001 | 2024-02-16 | GRST-5000288419_2024 | 0 | 2 | 0 | 0 |  | 2024-11-20 | AA53 | 2024-11-22 |  |  | 2024-11-24 |  |  | 100000042344 | 1020 | 2024-12-31 | 10 |  | 2024-11-21 | 4900176570_2024_0001 | 2024-11-24 |  | 5000288419_2024_0001 | 0 | 2 | 0 | 90024832 | 10 | 0 | 180096308/180096309 | 2 | 0 | 0 |  | L | 4900176570 | 2024 |  | 5000288419 | 2024 | 0 |  | 2024-11-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-11-19 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9019099_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000004175 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1290 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-19 |  |  | 2024-11-20 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0120 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10202334 | FLANGE,BLIND;350MM,CL150,RF,CS,A105N | 1 | EA | 0 | 0 | 1 | 1 | EA | 05.10 - HU 101000000096902 to AA02 | Supply for Order 600002862, Item 111 cannot be changed 180078491 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1030 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078491 | 9015168 | 07 | Execution | 0000216479 | 111 | 111 | 0 | EA | 101000000096802 |  | 107000000000418 |  |  |  | P07YRDBY11 | WorkPackLink | P07YRDBY11 | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000234665_2024 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  | 100000033635 | 1020 | 2024-12-31 | 1 |  | 2024-10-07 | 4900147491_2024_0005 | 2024-10-15 |  | 5000234665_2024_0001 | 0 | 2 | 0 | 90020227 | 1 | 0 | 180078491 | 2 | 0 | 0 | X | L | 4900147491 | 2024 |  | 5000234665 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202334 | FLANGE,BLIND;350MM,CL150,RF,CS,A105N | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015168_0090 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 1030 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0680 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 4 | EA | 0 | 0 | 8 | 4 | EA | 03.10 - GR ZONE @ AA02 | Supply for Order 600002862, Item 68 cannot be changed 180083185 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 68 | 68 | 0 | EA | 101000000094149 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 4 |  | 2024-10-18 | 4900154759_2024_0001 | 2024-11-01 |  | 5000248569_2024_0001 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0350 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 350 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0180 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 4 | EA | 0 | 0 | 8 | 4 | EA | 05.10 - Del 80019284 for picking | Supply for Order 600002862, Item 117 cannot be changed 180085321 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1090 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085321 | 9017445 | 07 | Execution | 0000216479 | 117 | 117 | 0 | EA | 101000000097682 |  | 102000000021840 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255250_2024 | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000036571 | 1020 | 2024-12-31 | 4 |  | 2024-10-24 | 4900158458_2024_0001 | 2024-10-07 |  | 5000255250_2024_0001 | 0 | 2 | 0 | 90020228 | 4 | 0 | 180085321 | 2 | 0 | 0 | X | L | 4900158458 | 2024 |  | 5000255250 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017445_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1090 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-02 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0090 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 1 | EA | 0 | 0 | 0 | 1 | EA | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 108 cannot be changed 180078364 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1000 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078364 | 9015654 | 07 | Execution | 0000216479 | 108 | 108 | 0 | EA |  |  | 102000000020025 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  | 100000033542 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146886_2024_0001 | 2024-10-15 |  | 5000233769_2024_0001 | 0 | 2 | 0 | 90020227 | 1 | 0 | 180078364 | 2 | 0 | 0 | X | L | 4900146886 | 2024 |  | 5000233769 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015654_0070 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 1000 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0760 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 1 | EA | 0 | 0 | 0 | 0 |  | 24.10 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 76 cannot be changed 90006343 item 770 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006343 | 07 | Execution | 0000216479 | 76 | 76 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | ODST-0090006343_0770 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-29 |  | 2024-11-01 |  |  | 0 | 2 | 0 | 90006343 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0770 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 770 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0380 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218613 | STUDBOLT;0.625" X 110MM,L7,ZN+XYLAN | 12 | EA | 44 | 0 | 21 | 12 | EA | 22.09 - X2 boxes / SOH @ AA01 | Supply for Order 600002862, Item 38 cannot be changed 180017143 item 180 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 38 | 38 | 0 | EA | 102000000003638 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 12 |  | 2024-04-11 | 4900045283_2024_0035 | 2024-11-01 |  | 5000058191_2024_0018 | 0 | 2 | 0 | 90006343 | 12 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218613 | STUDBOLT;0.625" X 110MM,L7,ZN+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0210 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 210 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0390 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218617 | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN | 48 | EA | 4 | 0 | 40 | 48 | EA | 22.09 - X1 BOX / SOH @ PDC | Supply for Order 600002862, Item 39 cannot be changed 180017143 item 190 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 39 | 39 | 0 | EA | 102000000003639 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 48 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 48 |  | 2024-04-11 | 4900045283_2024_0037 | 2024-11-01 |  | 5000058191_2024_0019 | 0 | 2 | 0 | 90006343 | 48 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218617 | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0220 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 220 |  |  | 0 | 48 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0400 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218625 | STUDBOLT;0.750"X110MM,L7,CAD+XYLAN | 8 | EA | 72 | 8 | 8 | 8 | EA | 22.09 - X1 BOX / MW3R15B08B @ KSF | Supply for Order 600002862, Item 40 cannot be changed 180017143 item 200 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 40 | 40 | 0 | EA | 102000000003640 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0039 | 2024-11-01 |  | 5000058191_2024_0020 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218625 | STUDBOLT;0.750"X110MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0230 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 230 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0410 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218626 | STUDBOLT;0.750"X120MM,L7,CAD+XYLAN | 48 | EA | 100 | 12 | 20 | 48 | EA | 22.09 - X3 BOX / 24 Stocked @ PDC, 12 @ KSF | Supply for Order 600002862, Item 41 cannot be changed 180017143 item 210 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 41 | 41 | 0 | EA | 102000000003641 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 48 |  | 2024-04-11 | 4900045283_2024_0041 | 2024-11-01 |  | 5000058191_2024_0021 | 0 | 2 | 0 | 90006343 | 48 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218626 | STUDBOLT;0.750"X120MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0240 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 240 |  |  | 0 | 48 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0420 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218627 | STUDBOLT;0.750"X130MM,L7,CAD+XYLAN | 32 | EA | 0 | 0 | 96 | 32 | EA | 22.09 - X1 BOX/ 20 SOH @ AA01 | Supply for Order 600002862, Item 42 cannot be changed 180017143 item 220 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 42 | 42 | 0 | EA | 102000000003642 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 32 |  | 2024-04-11 | 4900045283_2024_0043 | 2024-11-01 |  | 5000058191_2024_0022 | 0 | 2 | 0 | 90006343 | 32 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218627 | STUDBOLT;0.750"X130MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0250 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 250 |  |  | 0 | 32 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0430 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218628 | STUDBOLT;0.750"X140MM,L7,CAD+XYLAN | 20 | EA | 20 | 24 | 32 | 20 | EA | X1 BOX | Supply for Order 600002862, Item 43 cannot be changed 180017143 item 230 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 43 | 43 | 0 | EA | 102000000003643 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 20 |  | 2024-04-11 | 4900045283_2024_0045 | 2024-11-01 |  | 5000058191_2024_0023 | 0 | 2 | 0 | 90006343 | 20 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218628 | STUDBOLT;0.750"X140MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0260 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 260 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0440 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 60 | EA | 60 | 0 | 48 | 12 | EA | 01.10 - HU 101000000094408 TO AA02 | Supply for Order 600002862, Item 44 cannot be changed 180083185 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 44 | 44 | 0 | EA | 102000000003617 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 60 |  | 2024-10-18 | 4900154759_2024_0013/4900138157_2024_0001/4900045283_2024_0067 | 2024-11-01 |  | 5000248569_2024_0007/5000218662_2024_0001/5000058191_2024_0034 | 0 | 2 | 0 | 90006343 | 60 | 0 | 180083185/180073289/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0550/9013491_0550/9002109_0550 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 550 |  |  | 0 | 60 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0440 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 60 | EA | 60 | 0 | 48 | 24 | EA | 01.10 - HU 101000000094408 TO AA02 | Supply for Order 600002862, Item 44 cannot be changed 180083185 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 44 | 44 | 0 | EA | 101000000094408 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 60 |  | 2024-10-18 | 4900154759_2024_0013/4900138157_2024_0001/4900045283_2024_0067 | 2024-11-01 |  | 5000248569_2024_0007/5000218662_2024_0001/5000058191_2024_0034 | 0 | 2 | 0 | 90006343 | 60 | 0 | 180083185/180073289/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0550/9013491_0550/9002109_0550 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 550 |  |  | 0 | 60 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0440 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 60 | EA | 60 | 0 | 48 | 24 | EA | 01.10 - HU 101000000094408 TO AA02 | Supply for Order 600002862, Item 44 cannot be changed 180083185 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 44 | 44 | 0 | EA |  |  | 102000000016304 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 60 |  | 2024-10-18 | 4900154759_2024_0013/4900138157_2024_0001/4900045283_2024_0067 | 2024-11-01 |  | 5000248569_2024_0007/5000218662_2024_0001/5000058191_2024_0034 | 0 | 2 | 0 | 90006343 | 60 | 0 | 180083185/180073289/180017143 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0550/9013491_0550/9002109_0550 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003470 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 550 |  |  | 0 | 60 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-30 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0450 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218636 | STUDBOLT;0.875"X180MM,L7,CAD+XYLAN | 8 | EA | 12 | 0 | 12 | 8 | EA | 03.10 - GR ZONE @ AA02 | Supply for Order 600002862, Item 45 cannot be changed 180083185 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 45 | 45 | 0 | EA | 101000000094430 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 8 |  | 2024-10-18 | 4900154759_2024_0015 | 2024-11-01 |  | 5000248569_2024_0008 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218636 | STUDBOLT;0.875"X180MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0560 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 |  | 1000214854 | S002 | 30 | 30 | 5300006667 | 560 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-30 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0460 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10218652 | STUDBOLT;1.125"X190MM,L7,CAD+XYLAN | 16 | EA | 0 | 0 | 16 | 16 | EA | 01.10 - HU 101000000094366 TO AA02 | Supply for Order 600002862, Item 46 cannot be changed 180083185 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 46 | 46 | 0 | EA | 101000000094366 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 16 |  | 2024-10-18 | 4900154759_2024_0017 | 2024-11-01 |  | 5000248569_2024_0009 | 0 | 2 | 0 | 90006343 | 16 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218652 | STUDBOLT;1.125"X190MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0570 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 570 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0470 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10218657 | STUDBOLT;1.125"X230MM,L7,CAD+XYLAN | 40 | EA | 100 | 0 | 0 | 40 | EA | 22.09 - X2 BOXES / MW3R12D05A @ KSF | Supply for Order 600002862, Item 47 cannot be changed 180017143 item 240 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 47 | 47 | 0 | EA | 102000000003614 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 40 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 40 |  | 2024-04-11 | 4900045283_2024_0047 | 2024-11-01 |  | 5000058191_2024_0024 | 0 | 2 | 0 | 90006343 | 40 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218657 | STUDBOLT;1.125"X230MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0270 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 270 |  |  | 0 | 40 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0480 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10219526 | STUDBOLT;0.750"X160MM,L7,CAD+XYLAN | 8 | EA | 52 | 0 | 8 | 8 | EA | 01.10 - HU 101000000093107 TO AA02 | Supply for Order 600002862, Item 48 cannot be changed 180083185 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 48 | 48 | 0 | EA | 101000000093107 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 8 |  | 2024-10-18 | 4900154759_2024_0019 | 2024-11-01 |  | 5000248569_2024_0010 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219526 | STUDBOLT;0.750"X160MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0580 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 580 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0490 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10219538 | STUDBOLT;1.250"X250MM,L7,CAD+XYLAN | 80 | EA | 0 | 0 | 80 | 80 | EA | 01.10 - HU 101...93499, 93530,43,45 TO AA02 | Supply for Order 600002862, Item 49 cannot be changed 180083185 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 49 | 49 | 0 | EA | 102000000019719 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 80 |  | 2024-10-18 | 4900154759_2024_0021 | 2024-11-01 |  | 5000248569_2024_0011 | 0 | 2 | 0 | 90006343 | 80 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219538 | STUDBOLT;1.250"X250MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0590 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 590 |  |  | 0 | 80 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0500 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10219885 | STUDBOLT;1.125"X240MM,L7,CAD+XYLAN | 12 | EA | 0 | 0 | 0 | 0 |  | 10.10 - Del 80018302/000010 for picking | Supply for Order 600002862, Item 50 cannot be changed 90006343 item 600 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006343 | 07 | Execution | 0000216479 | 50 | 50 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-02-16 | ODST-0090006343_0600 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-29 |  | 2024-11-01 |  |  | 0 | 2 | 0 | 90006343 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219885 | STUDBOLT;1.125"X240MM,L7,CAD+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006343_0600 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 600 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-21 | 2024-10-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0910 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(26.10.2024) | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 24 | EA | 60 | 0 | 24 | 24 | EA | MRF 241026-6712278 processed to 5001 HU 1020-22091 P-99 | Supply for Order 600002862, Item 133 cannot be changed 90022810 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180086211 | 90022810 | 07 | Execution | 0000216479 | 133 | 133 | 0 | EA |  |  | 102000000022091 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000258272_2024 | 0 | 11 | 0 | 0 |  | 2024-10-19 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000037359 | 1020 | 2024-12-31 | 24 |  | 2024-10-27 | 4900160002_2024_0001 | 2024-11-01 |  | 5000258272_2024_0001 | 0 | 2 | 0 | 90022810 | 24 | 0 | 180086211 | 2 | 0 | 0 | X | L | 4900160002 | 2024 |  | 5000258272 | 2024 | 0 |  | 2024-10-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 2024-10-26 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90022810_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1230 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0510 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 24 | EA | 60 | 0 | 24 | 24 | EA | X1 CRATE | Supply for Order 600002862, Item 51 cannot be changed 180017143 item 250 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 51 | 51 | 0 | EA |  |  | 102000000003644 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 24 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 24 |  | 2024-04-11 | 4900045283_2024_0049 | 2024-11-01 |  | 5000058191_2024_0025 | 0 | 2 | 0 | 90006343 | 24 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0280 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 280 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0520 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10220455 | STUDBOLT;0.875" X 180MM,A193 B8M CL2 | 8 | EA | 16 | 0 | 0 | 8 | EA | 22.09 - X1 BOX / MW3R15F09A @ KSF | Supply for Order 600002862, Item 52 cannot be changed 180017143 item 260 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 52 | 52 | 0 | EA | 102000000003615 |  | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 8 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0051 | 2024-11-01 |  | 5000058191_2024_0026 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10220455 | STUDBOLT;0.875" X 180MM,A193 B8M CL2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0290 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 290 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0530 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10222953 | SPADE BLIND,50MM,CL300,RF,A516-60/70 | 6 | EA | 0 | 0 | 6 | 6 | EA | 01.10 - HU 101000000093007 TO AA02 | Supply for Order 600002862, Item 53 cannot be changed 180083185 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 53 | 53 | 0 | EA | 101000000093007 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 6 |  | 2024-10-18 | 4900154759_2024_0023 | 2024-11-01 |  | 5000248569_2024_0012 | 0 | 2 | 0 | 90006343 | 6 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10222953 | SPADE BLIND,50MM,CL300,RF,A516-60/70 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0610 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 610 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0540 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10223374 | STUDBOLT;0.750"X140MM,A193 B8M,CL2 | 20 | EA | 32 | 4 | 24 | 20 | EA | 22.09 - IN GREY TUB / MW2R03A02A @ KSF | Supply for Order 600002862, Item 54 cannot be changed 180017143 item 270 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 54 | 54 | 0 | EA | 102000000003646 | 102000000003616 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 20 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 20 |  | 2024-04-11 | 4900045283_2024_0053 | 2024-11-01 |  | 5000058191_2024_0027 | 0 | 2 | 0 | 90006343 | 20 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223374 | STUDBOLT;0.750"X140MM,A193 B8M,CL2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0300 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 300 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0550 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10229938 | SPADE BLIND,80MM,CL150,SS316 | 1 | EA | 0 | 0 | 1 | 1 | EA | 16.10 - 180082367 4500005381, 103 ERRORS | Supply for Order 600002862, Item 55 cannot be changed 180085320 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 620 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 55 | 55 | 0 | EA | 101000000101564 |  | 102000000021842 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0011 | 2024-11-01 |  | 5000255235_2024_0006 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229938 | SPADE BLIND,80MM,CL150,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0620 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 620 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0790 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10229941 | SPADE BLIND,50MM,CL600,SS316 | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000092975 TO AA02 | Supply for Order 600002862, Item 79 cannot be changed 180083185 item 180 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 79 | 79 | 0 | EA | 101000000092975 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0035 | 2024-11-01 |  | 5000248569_2024_0018 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229941 | SPADE BLIND,50MM,CL600,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0800 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 800 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0800 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10229942 | SPADE BLIND,100MM,CL600,SS316 | 1 | EA | 0 | 0 | 1 | 1 | EA | 16.10 - 180082367 4500005381, 103 ERRORS | Supply for Order 600002862, Item 80 cannot be changed 180085320 item 160 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 80 | 80 | 0 | EA | 101000000101537 |  | 102000000021852 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0031 | 2024-11-01 |  | 5000255235_2024_0016 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229942 | SPADE BLIND,100MM,CL600,SS316 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0810 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 810 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-01 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0690 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 4 | EA | 0 | 0 | 5 | 1 | EA | 06.03 - ETA 17.04.24 PO 4500004781 x 3 Australasian, ETA 16.02.24 PO W451781228 | Supply for Order 600002862, Item 69 cannot be changed 9018326 item 360 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180090422 | 9018456 | 07 | Execution | 0000216479 | 69 | 69 | 1 | EA | 102000000022419 |  | 107000000000391 |  |  |  | P07 - BENCH | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 1001 | 2024-02-16 | GRST-5000271136_2024 | 0 | 0 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000039296 | 1020 | 2024-12-31 | 4 |  | 2024-11-07 | 4900167013_2024_0001/4900162552_2024_0001 | 2024-11-01 |  | 5000271136_2024_0001/5000263690_2024_0001 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180090422/180088335 | 1 | 0 | 0 | X | L | 4900167013 | 2024 |  | 5000271136 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9018456_0360/9018326_0360 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 360 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0230 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 6 | EA | 0 | 0 | 5 | 4 | EA | 03.10 - HU 101000000093112 to AA02 | Supply for Order 600002862, Item 122 cannot be changed 180085864 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085878 | 9017455 | 07 | Execution | 0000216479 | 122 | 122 | 0 | EA |  |  | 102000000022072 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 6 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000037617 | 1020 | 2024-12-31 | 6 |  | 2024-10-25 | 4900159260_2024_0001/4900159250_2024_0001 | 2024-10-07 |  | 5000257063_2024_0001/5000257056_2024_0001 | 0 | 2 | 0 | 90020228 | 6 | 0 | 180085864/180085878 | 2 | 0 | 0 | X | L | 4900159260 | 2024 |  | 5000257056 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017455_0060/9017453_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-02 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0230 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 6 | EA | 0 | 0 | 5 | 1 | EA | 03.10 - HU 101000000093112 to AA02 | Supply for Order 600002862, Item 122 cannot be changed 180085864 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085878 | 9017455 | 07 | Execution | 0000216479 | 122 | 122 | 0 | EA |  |  | 102000000022018 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 6 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000037617 | 1020 | 2024-12-31 | 6 |  | 2024-10-25 | 4900159260_2024_0001/4900159250_2024_0001 | 2024-10-07 |  | 5000257063_2024_0001/5000257056_2024_0001 | 0 | 2 | 0 | 90020228 | 6 | 0 | 180085864/180085878 | 2 | 0 | 0 | X | L | 4900159260 | 2024 |  | 5000257056 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017455_0060/9017453_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-02 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-07 | 2024-10-02 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0230 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(20.09.2024) | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 6 | EA | 0 | 0 | 5 | 1 | EA | 03.10 - HU 101000000093112 to AA02 | Supply for Order 600002862, Item 122 cannot be changed 180085864 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085878 | 9017455 | 07 | Execution | 0000216479 | 122 | 122 | 0 | EA |  |  | 102000000022019 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 6 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 0 | 0 | 0 |  | 2024-10-05 | AA53 | 2024-11-22 |  |  | 2024-10-07 |  |  | 100000037617 | 1020 | 2024-12-31 | 6 |  | 2024-10-25 | 4900159260_2024_0001/4900159250_2024_0001 | 2024-10-07 |  | 5000257063_2024_0001/5000257056_2024_0001 | 0 | 2 | 0 | 90020228 | 6 | 0 | 180085864/180085878 | 2 | 0 | 0 | X | L | 4900159260 | 2024 |  | 5000257056 | 2024 | 0 |  | 2024-10-02 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-09-20 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017455_0060/9017453_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-02 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-01 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0690 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 4 | EA | 0 | 0 | 5 | 3 | EA | 06.03 - ETA 17.04.24 PO 4500004781 x 3 Australasian, ETA 16.02.24 PO W451781228 | Supply for Order 600002862, Item 69 cannot be changed 9018326 item 360 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180090422 | 9018456 | 07 | Execution | 0000216479 | 69 | 69 | 1 | EA | 102000000023066 |  | 107000000000076 |  |  |  | STATIC-CAGE | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 1001 | 2024-02-16 | GRST-5000271136_2024 | 0 | 0 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000039296 | 1020 | 2024-12-31 | 4 |  | 2024-11-07 | 4900167013_2024_0001/4900162552_2024_0001 | 2024-11-01 |  | 5000271136_2024_0001/5000263690_2024_0001 | 0 | 2 | 0 | 90006343 | 4 | 0 | 180090422/180088335 | 1 | 0 | 0 | X | L | 4900167013 | 2024 |  | 5000271136 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9018456_0360/9018326_0360 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 360 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 |  | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0900 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 |  | 30 | Maintenance Order material has been deleted | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 0 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 99 | 0 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  |  | AA53 | 2024-10-21 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 |  |  |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter | [5 empty] | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  |  | 1000214854 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0560 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254870 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN50C> | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 56 cannot be changed 180085320 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 56 | 56 | 0 | EA | 101000000101568 |  | 102000000021843 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0013 | 2024-11-01 |  | 5000255235_2024_0007 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254870 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN50C> | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0630 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 630 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0570 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254871 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN80C> | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 57 cannot be changed 180085320 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 57 | 57 | 0 | EA | 101000000101620 |  | 102000000021844 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0015 | 2024-11-01 |  | 5000255235_2024_0008 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254871 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN80C> | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0640 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 640 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0580 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254875 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN100> | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 58 cannot be changed 180085320 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 58 | 58 | 0 | EA | 101000000101567 |  | 102000000021845 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0017 | 2024-11-01 |  | 5000255235_2024_0009 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254875 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN100> | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0650 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 650 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0590 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254974 | SPADE,BLIND;CAMCO 7666720DN50CL3008MM | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 59 cannot be changed 180085320 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 59 | 59 | 0 | EA | 101000000101569 |  | 102000000021846 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0019 | 2024-11-01 |  | 5000255235_2024_0010 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254974 | SPADE,BLIND;CAMCO 7666720DN50CL3008MM | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0660 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 660 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0600 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10254979 | SPADE,BLIND,80MM,CL600,15MM,SS304 | 2 | EA | 0 | 0 | 2 | 2 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 60 cannot be changed 180085320 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 60 | 60 | 0 | EA | 101000000101535 |  | 102000000021847 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0021 | 2024-11-01 |  | 5000255235_2024_0011 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254979 | SPADE,BLIND,80MM,CL600,15MM,SS304 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0670 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 670 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2025-03-05 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0040 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10255008 | SPADE,BLIND,1050MM,CL150,55MM,SS304 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALIAN FITTINGS | Supply for Order 600002862, Item 103 cannot be changed – 4500027121 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300014053 | 40 | CPT | 7 | 1000018366 | 103 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500027121 | 40 | 1 | EA | 2024-11-24 |  |  |  |  | 07 | Execution | 0000216479 | 103 | 0 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | POPO-4500027121_00040 | 0 | 158 | 0 | 0 | 2025-02-28 | 2025-03-15 | AA53 | 2024-11-22 |  |  | 2025-08-27 | 2025-03-02 | 2025-03-17 |  |  | 2024-12-31 | 0 |  | 2025-03-05 |  | 2025-03-17 |  |  | 0 | 2 | 2 |  | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255008 | SPADE,BLIND,1050MM,CL150,55MM,SS304 | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-01-03 | 30 |  | 2025-03-02 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 950 |  | 5300014053 | 40 | 1 | EA | 1001 | AA02 | 2025-03-05 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0850 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(15.02.2024) | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 10 | SHT | 0 | 0 | 13 | 3 | SHT | 01.10 - HU 101000000068823 TO AA02 | Supply for Order 600002862, Item 85 cannot be changed 180078327 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  | 180081721 | 9016389 | 07 | Execution | 0000216479 | 85 | 85 | 0 | SHT | 102000000016228 |  | 107000000000418 |  |  |  | P07YRDBY11 | WorkPackLink | P07YRDBY11 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000243856_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035211 | 1020 | 2024-12-31 | 10 |  | 2024-10-14 | 4900152515_2024_0001/4900146823_2024_0001/4900138179_2024_0001 | 2024-11-01 |  | 5000243856_2024_0001/5000233678_2024_0001/5000218684_2024_0001 | 0 | 2 | 0 | 90006343 | 10 | 0 | 180073288/180078327/180081721 | 2 | 0 | 0 | X | L | 4900152515 | 2024 |  | 5000243856 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 2024-02-15 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016389_0010/9015483_0010/9013490_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 10 |  |  | 0 | 10 | SHT | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0850 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(15.02.2024) | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 10 | SHT | 0 | 0 | 13 | 2 | SHT | 01.10 - HU 101000000068823 TO AA02 | Supply for Order 600002862, Item 85 cannot be changed 180078327 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  | 180081721 | 9016389 | 07 | Execution | 0000216479 | 85 | 85 | 0 | SHT |  |  | 102000000020802 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000243856_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035211 | 1020 | 2024-12-31 | 10 |  | 2024-10-14 | 4900152515_2024_0001/4900146823_2024_0001/4900138179_2024_0001 | 2024-11-01 |  | 5000243856_2024_0001/5000233678_2024_0001/5000218684_2024_0001 | 0 | 2 | 0 | 90006343 | 10 | 0 | 180073288/180078327/180081721 | 2 | 0 | 0 | X | L | 4900152515 | 2024 |  | 5000243856 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 2024-02-15 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016389_0010/9015483_0010/9013490_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003654 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 10 |  |  | 0 | 10 | SHT | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-15 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0850 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(15.02.2024) | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 10 | SHT | 0 | 0 | 13 | 5 | SHT | 01.10 - HU 101000000068823 TO AA02 | Supply for Order 600002862, Item 85 cannot be changed 180078327 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  | 180081721 | 9016389 | 07 | Execution | 0000216479 | 85 | 85 | 0 | SHT |  |  | 102000000019866 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000243856_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035211 | 1020 | 2024-12-31 | 10 |  | 2024-10-14 | 4900152515_2024_0001/4900146823_2024_0001/4900138179_2024_0001 | 2024-11-01 |  | 5000243856_2024_0001/5000233678_2024_0001/5000218684_2024_0001 | 0 | 2 | 0 | 90006343 | 10 | 0 | 180073288/180078327/180081721 | 2 | 0 | 0 | X | L | 4900152515 | 2024 |  | 5000243856 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 2024-02-15 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016389_0010/9015483_0010/9013490_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003650 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 10 |  |  | 0 | 10 | SHT | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0080 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10291772 | FLANGE,BLIND;200MM,CL150,RF,CS,A105M | 1 | EA | 1 | 1 | 12 | 1 | EA | 05.10 - HU 101000000096902 to AA02 | Supply for Order 600002862, Item 107 cannot be changed 180078491 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078491 | 9015168 | 07 | Execution | 0000216479 | 107 | 107 | 0 | EA | 101000000096789 |  | 107000000000418 |  |  |  | P07YRDBY11 | WorkPackLink | P07YRDBY11 | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000234684_2024 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  | 100000033635 | 1020 | 2024-12-31 | 1 |  | 2024-10-07 | 4900147491_2024_0003 | 2024-10-15 |  | 5000234684_2024_0001 | 0 | 2 | 0 | 90020227 | 1 | 0 | 180078491 | 2 | 0 | 0 | X | L | 4900147491 | 2024 |  | 5000234684 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10291772 | FLANGE,BLIND;200MM,CL150,RF,CS,A105M | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015168_0060 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 990 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 |  | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(25.03.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 4 | EA | 47 | 15 | 37 | 4 | EA | 22.09 - IN GRAY TUB / MW2R03B03E @ KSF | Supply for Order 600002862, Item 90 cannot be changed 180017111 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017111 | 90006609 | 07 | Execution | 0000216479 | 90 | 90 | 0 | EA | 102000000003646 | 102000000003685 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058173_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 4 |  | 2024-04-11 | 4900045279_2024_0001 | 2024-11-01 |  | 5000058173_2024_0001 | 0 | 2 | 0 | 90006609 | 4 | 0 | 180017111 | 2 | 0 | 0 | X | L | 4900045279 | 2024 |  | 5000058173 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-03-25 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90006609_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 880 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0610 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.02.2024) | 10306724 | GASKET;SWC,80MM,CL300/600,31>WSE10508041 | 8 | EA | 6 | 0 | 8 | 8 | EA | 22.09 - IN GREY TUB / 4 SOH @ AA02 | Supply for Order 600002862, Item 61 cannot be changed 180017143 item 280 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017143 | 9002109 | 07 | Execution | 0000216479 | 61 | 61 | 0 | EA | 102000000003646 | 102000000003631 | 102000000003666 | 01-Road |  | 3-In Transit | 24SDLN2C - CAGED PALLET | WorkPackLink | P07WH-R2FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000058191_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000005808 | 1020 | 2024-12-31 | 8 |  | 2024-04-11 | 4900045283_2024_0055 | 2024-11-01 |  | 5000058191_2024_0028 | 0 | 2 | 0 | 90006343 | 8 | 0 | 180017143 | 2 | 0 | 0 | X | L | 4900045283 | 2024 |  | 5000058191 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10306724 | GASKET;SWC,80MM,CL300/600,31>WSE10508041 | 2024-02-29 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9002109_0310 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000001236 | AU1072 | 1000214854 | S002 | 30 | 70 | 5300006667 | 310 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2025-03-17 | 2025-03-17 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | X | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 |  | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(03.10.2024) | 10312854 | AIR;MEDICAL DRY,25PPM,BOC 470MAN15 | 1 | PAC | 0 | 0 | 1 | 1 | PAC | 24.10 - ETA 24.10.24 PO 4500031439 BOC | Supply for Order 600002862, Item 129 cannot be changed 9017564 item 50 already exists | Material work-packed @AA53 | SP14 | Directs (Inventory) | 10 | AA02 | 5300006667 | 1200 | CPT | 14 | 1000020500 | 129 | 30000395 | BOC LIMITED | 4500031439 | 20 | 1 | PAC | 2024-10-28 |  | 180086442//180086442 | 180086443 | 9017564 | 07 | Execution | 0000216479 | 129 | 129 | 0 | PAC |  |  | 102000000022162 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000259599_2024 | 0 | 5 | 0 | 0 | 2025-03-15 | 2025-03-20 | AA53 | 2024-11-22 |  |  | 2025-03-22 |  | 2025-03-17 | 100000037748 | 1020 | 2024-12-31 | 1 | 5000259612_2024_0001 | 2024-10-28 | 4900160481_2024_0001 | 2024-10-28 |  | 5000259599_2024_0001 | 0 | 2 | 2 | 90022091 | 1 | 1 | 180086443 | 2 | 0 | 0 | X | L | 4900160481 | 2024 | 5000259612 | 5000259599 | 2024 | 2024 | 180086442 | 2025-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10312854 | AIR;MEDICAL DRY,25PPM,BOC 470MAN15 | 2024-10-03 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9017564_0050 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-08 | 30 |  | 2025-03-17 |  | 31522 |  | 24SDLN2C | MJ | 1000003911 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1200 |  |  | 0 | 1 | PAC | 2001 | AA02 | 2025-03-17 |  |  | 2024-10-31 | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0060 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10340086 | FLANGE,BLIND;350MM,CL300,RF,CS,A105N | 1 | EA | 0 | 0 | 1 | 1 | EA | 05.10 - HU 101000000096902 to AA02 | Supply for Order 600002862, Item 105 cannot be changed 180078491 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078491 | 9015168 | 07 | Execution | 0000216479 | 105 | 105 | 0 | EA | 101000000096787 |  | 107000000000418 |  |  |  | P07YRDBY11 | WorkPackLink | P07YRDBY11 | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000234700_2024 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  | 100000033635 | 1020 | 2024-12-31 | 1 |  | 2024-10-07 | 4900147491_2024_0001 | 2024-10-15 |  | 5000234700_2024_0001 | 0 | 2 | 0 | 90020227 | 1 | 0 | 180078491 | 2 | 0 | 0 | X | L | 4900147491 | 2024 |  | 5000234700 | 2024 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10340086 | FLANGE,BLIND;350MM,CL300,RF,CS,A105N | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 9015168_0040 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 970 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0030 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10340106 | SPADE BLIND,50MM,CL150,CS,A285,GDE C | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 102 cannot be changed 90020227 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 940 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020227 | 07 | Execution | 0000216479 | 102 | 102 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | ODST-0090020227_0020 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-10 |  | 2024-10-15 |  |  | 0 | 2 | 0 | 90020227 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10340106 | SPADE BLIND,50MM,CL150,CS,A285,GDE C | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020227_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  | 30 | 5300006667 | 940 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0620 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10441378 | SPADE BLIND,100MM,CL600,CS | 1 | EA | 0 | 0 | 1 | 1 | EA | 16.10 - 180082367 4500005381, 103 ERRORS | Supply for Order 600002862, Item 62 cannot be changed 180085320 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 62 | 62 | 0 | EA | 101000000101627 |  | 102000000021848 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0023 | 2024-11-01 |  | 5000255235_2024_0012 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441378 | SPADE BLIND,100MM,CL600,CS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0680 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 680 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0020 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10441379 | SPADE BLIND,150MM,CL600,CS | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | Supply for Order 600002862, Item 101 cannot be changed 90020227 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 930 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020227 | 07 | Execution | 0000216479 | 101 | 101 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | ODST-0090020227_0010 | 0 | 0 | 0 | 0 |  | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  |  |  | 2024-12-31 | 0 |  | 2024-10-10 |  | 2024-10-15 |  |  | 0 | 2 | 0 | 90020227 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441379 | SPADE BLIND,150MM,CL600,CS | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020227_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 930 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0630 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10487244 | SPADE,BLIND,80MM,CL300,LTCS | 2 | EA | 0 | 0 | 2 | 2 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 63 cannot be changed 180085320 item 130 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 63 | 63 | 0 | EA | 101000000101539 |  | 102000000021849 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 2 |  | 2024-10-24 | 4900158497_2024_0025 | 2024-11-01 |  | 5000255235_2024_0013 | 0 | 2 | 0 | 90006343 | 2 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10487244 | SPADE,BLIND,80MM,CL300,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0690 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 690 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0640 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10487245 | SPADE,BLIND,100MM,CL300,LTCS | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 64 cannot be changed 180085320 item 140 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 700 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 64 | 64 | 0 | EA | 101000000101565 |  | 102000000021850 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0027 | 2024-11-01 |  | 5000255235_2024_0014 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10487245 | SPADE,BLIND,100MM,CL300,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0700 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 700 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0650 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10488048 | FLANGE,BLIND,150MM,CL300,RF,SS | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.10 - HU 101000000093024 TO AA02 | Supply for Order 600002862, Item 65 cannot be changed 180083185 item 130 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 710 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 65 | 65 | 0 | EA | 101000000093024 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 1 |  | 2024-10-18 | 4900154759_2024_0025 | 2024-11-01 |  | 5000248569_2024_0013 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10488048 | FLANGE,BLIND,150MM,CL300,RF,SS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0710 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 710 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2025-03-05 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0010 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.08.2024) | 10488134 | SPADE,BLIND,250MM,CL300,SS | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALIAN FITTINGS | Supply for Order 600002862, Item 100 cannot be changed – 4500027121 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300014053 | 30 | CPT | 7 | 1000018366 | 100 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500027121 | 10 | 1 | EA | 2024-11-24 |  |  |  |  | 07 | Execution | 0000216479 | 100 | 0 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | POPO-4500027121_00010 | 0 | 158 | 0 | 0 | 2025-02-28 | 2025-03-15 | AA53 | 2024-11-22 |  |  | 2025-08-27 | 2025-03-02 | 2025-03-17 |  |  | 2024-12-31 | 0 |  | 2025-03-05 |  | 2025-03-17 |  |  | 0 | 2 | 2 |  | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10488134 | SPADE,BLIND,250MM,CL300,SS | 2024-08-31 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-01-03 | 30 |  | 2025-03-02 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 920 |  | 5300014053 | 30 | 1 | EA | 1001 | AA02 | 2025-03-05 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0660 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10488940 | SPADE,BLIND,80MM,CL600,LTCS | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 66 cannot be changed 180085320 item 150 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180085320 | 9017444 | 07 | Execution | 0000216479 | 66 | 66 | 0 | EA | 101000000101566 |  | 102000000021851 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000255235_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036570 | 1020 | 2024-12-31 | 1 |  | 2024-10-24 | 4900158497_2024_0029 | 2024-11-01 |  | 5000255235_2024_0015 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180085320 | 2 | 0 | 0 | X | L | 4900158497 | 2024 |  | 5000255235 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10488940 | SPADE,BLIND,80MM,CL600,LTCS | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017444_0720 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003809 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 720 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-25 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0740 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10492979 | STUDBOLT;1.875" X 470MM,L7,ZN+XYLAN | 48 | EA | 0 | 0 | 48 | 48 | EA | 01.10 - HU 101000000080184 TO AA02 | Supply for Order 600002862, Item 74 cannot be changed 180078362 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 74 | 74 | 0 | EA | 102000000020030 |  | 107000000000278 |  |  |  |  | WorkPackLink | P07YRDBY12 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000233767_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 48 |  | 2024-10-06 | 4900146921_2024_0007 | 2024-11-01 |  | 5000233767_2024_0004 | 0 | 2 | 0 | 90006343 | 48 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10492979 | STUDBOLT;1.875" X 470MM,L7,ZN+XYLAN | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0750 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 750 |  |  | 0 | 48 | EA | 2001 | AA02 | 2024-10-29 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0670 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10590596 | GASKET;RF,GR,300MM,CL150,KLINGER 154756 | 6 | EA | 0 | 0 | 6 | 6 | EA | 01.10 - HU 101000000093397 TO AA02 | Supply for Order 600002862, Item 67 cannot be changed 180083185 item 140 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083185 | 9016679 | 07 | Execution | 0000216479 | 67 | 67 | 0 | EA | 101000000093397 |  | 102000000019832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000248569_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000035922 | 1020 | 2024-12-31 | 6 |  | 2024-10-18 | 4900154759_2024_0027 | 2024-11-01 |  | 5000248569_2024_0014 | 0 | 2 | 0 | 90006343 | 6 | 0 | 180083185 | 2 | 0 | 0 | X | L | 4900154759 | 2024 |  | 5000248569 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10590596 | GASKET;RF,GR,300MM,CL150,KLINGER 154756 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9016679_0730 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003732 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 730 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-18 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-22 | 2024-11-11 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0001 | 0010 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(11.11.2024) | 10592509 | BLADE,SAW;RECIP,CB,8TPI,1",230MM | 50 | EA | 53 | 5 | 0 | 50 | EA | UserCommentLink | Supply for Order 600002862, Item 135 cannot be changed 90024081 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 1250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180092179 | 90024081 | 07 | Execution | 0000216479 | 135 | 135 | 0 | EA |  |  | 102000000023606 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 KGP | 0 |  | 0 | 0 |  | 50 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 25 | 0 | 0 |  | 2024-10-20 | AA53 | 2024-10-22 |  |  | 2024-11-16 |  |  | 100000040495 | 1020 | 2024-12-31 | 50 |  | 2024-11-12 | 4900170153_2024_0001 | 2024-11-16 | LNG2 COP | 5000276086_2024_0001 | 0 | 2 | 0 | 90024081 | 50 | 0 | 180092179 | 2 | 0 | 0 | X | L | 4900170153 | 2024 |  | 5000276086 | 2024 | 0 |  | 2024-11-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10592509 | BLADE,SAW;RECIP,CB,8TPI,1",230MM | 2024-11-11 | W |  | 0001 | Supervisors | ENON | Supervisors |  |  | 90024081_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1250 |  |  | 0 | 50 | EA | 2001 | AA02 | 2024-11-11 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Pre-costed/Object created/Ready For Scheduling/Settlement rule created/Goods movement posted/Released/Material shortage/Date set by external system/Partially confirmed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0840 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.03.2024) | 10613639 | SPADE BLIND 150MM CL150 FF A516 GR70 | 1 | EA | 0 | 0 | 1 | 1 | EA | In Transit voyage 20003452 | Supply for Order 600002862, Item 84 cannot be changed 180084380 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180084380 | 9017420 | 07 | Execution | 0000216479 | 84 | 84 | 0 | EA |  |  | 102000000021568 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-16 | GRST-5000252447_2024 | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000036544 | 1020 | 2024-12-31 | 1 |  | 2024-10-22 | 4900156964_2024_0001 | 2024-11-01 |  | 5000252447_2024_0001 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180084380 | 2 | 0 | 0 | X | L | 4900156964 | 2024 |  | 5000252447 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613639 | SPADE BLIND 150MM CL150 FF A516 GR70 | 2024-03-01 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9017420_0830 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003766 | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 830 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-23 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 |  | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0070 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 10613642 | SPADE BLIND 200MM CL150 FF A516 GR70 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - NEED PURCHSING |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 980 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 106 | 106 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  |  | 1001 | 2024-02-16 | STST-5300006667_00980 | 1 | 0 | 0 | 0 |  |  | AA53 | 2024-11-22 |  |  | 2024-10-15 |  |  |  |  | 2024-12-31 | 0 | [6 empty] | 0 | 2 | 0 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613642 | SPADE BLIND 200MM CL150 FF A516 GR70 |  |  |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 |  |  | 5300006667 | 980 |  |  | 0 | 0 | EA | 2001 | AA02 | [5 empty] | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0860 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(05.03.2024) | 11400805 | SPADE,BLIND,200MM,CL600,LTCS | 1 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000040351 TO AA02 | Supply for Order 600002862, Item 86 cannot be changed 180078362 item 70 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 840 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 86 | 86 | 0 | EA |  |  | 102000000020027 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0013 | 2024-11-01 |  | 5000233767_2024_0007 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400805 | SPADE,BLIND,200MM,CL600,LTCS | 2024-03-05 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0840 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 840 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-29 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0870 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(05.03.2024) | 11400808 | SPADE BLIND,350MM,CL150,SS316 | 1 | EA | 0 | 0 | 0 | 1 | EA | 01.10 - HU 101000000085146 TO AA02 | Supply for Order 600002862, Item 87 cannot be changed 180078362 item 80 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006667 | 850 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180078362 | 9015652 | 07 | Execution | 0000216479 | 87 | 87 | 0 | EA |  |  | 102000000020028 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 LRG |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-16 |  | 0 | 17 | 0 | 0 |  | 2024-10-30 | AA53 | 2024-10-21 |  |  | 2024-11-01 |  |  | 100000033540 | 1020 | 2024-12-31 | 1 |  | 2024-10-06 | 4900146921_2024_0015 | 2024-11-01 |  | 5000233767_2024_0008 | 0 | 2 | 0 | 90006343 | 1 | 0 | 180078362 | 2 | 0 | 0 | X | L | 4900146921 | 2024 |  | 5000233767 | 2024 | 0 |  | 2024-10-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400808 | SPADE BLIND,350MM,CL150,SS316 | 2024-03-05 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 9015652_0850 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ | 1000003519 | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 850 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-29 |  |  | 2024-10-10 |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2025-03-22 |  | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0140 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404775 | CONTRACTOR;100-250V,ABB 1SFL547002R3322 | 6 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Supplying document 5300006667 1050 could not be updated on RESB due to locks |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 113 | 0 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 6 | [6 empty] | 0 | 0 | 0 | 0 |  |  | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404775 | CONTRACTOR;100-250V,ABB 1SFL547002R3322 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  |  | 1000214854 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-09-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0130 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 10 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Linked STO 5300014053 change failed for Order 600002862 Item 112 |  | SP97 | Direct Multi-base | 0 | AA01 | 5300014053 | 60 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020245 | 07 | Execution | 0000216479 | 112 | 0 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 10 |  |  |  | 1001 | 2024-08-13 |  | 0 | 0 | 0 | 0 |  | 2024-10-08 | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 |  | 2024-09-27 |  | 2024-10-10 |  |  | 0 | 2 | 0 | 90020245 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-09-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020245_0010 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA02 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1040 |  | 5300014053 | 60 | 10 | EA | 1001 | AA02 | 2024-09-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0240 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.09.2024) | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 10 | EA | 0 | 0 | 10 | 0 |  | At KGP 19/10/24 | Supply for Order 600002862, Item 123 cannot be changed 180082361 item 10 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300006667 | 1150 | EXW | 7 | 1000019709 | 123 | 30003000 | PIPESERV GARDINER INVESTMENTS QLD PTY LTD | 4500029623 | 10 | 10 | EA | 2024-11-18 |  | 180078395 |  | 90020249 | 07 | Execution | 0000216479 | 123 | 123 | 0 | [8 empty] | 00000107000000000580 | P07-WAREHOUSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-02-16 | ODST-0090020249_0010 | 0 | 60 | 54 | 60 | 2024-11-18 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-14 | 2024-11-20 | 2024-12-09 |  |  | 2024-12-31 | 0 | 5000234489_2024_0001 | 2024-10-10 |  | 2024-10-07 |  |  | 0 | 2 | 2 | 90020249 | 0 | 10 |  | 2 | 0 | 0 | X | L |  | 0 | 5000234489 |  | 0 | 2024 | 180078395 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 2024-09-21 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020249_0010 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-24 | 30 |  | 2024-11-20 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1150 |  | 5300014053 | 100 | 10 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-09-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0170 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | 6 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Linked STO 5300014053 change failed for Order 600002862 Item 116 |  | SP97 | Direct Multi-base | 0 | AA01 | 5300014053 | 90 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020245 | 07 | Execution | 0000216479 | 116 | 0 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 6 |  |  |  | 1001 | 2024-08-13 |  | 0 | 0 | 0 | 0 |  | 2024-10-08 | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 |  | 2024-09-27 |  | 2024-10-10 |  |  | 0 | 2 | 0 | 90020245 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-09-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020245_0040 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA02 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1080 |  | 5300014053 | 90 | 6 | EA | 1001 | AA02 | 2024-09-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0270 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.09.2024) | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | 6 | EA | 0 | 0 | 6 | 0 |  | At KGP 19/10/24 | Supply for Order 600002862, Item 127 cannot be changed 180082361 item 40 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300006667 | 1180 | EXW | 7 | 1000019709 | 127 | 30003000 | PIPESERV GARDINER INVESTMENTS QLD PTY LTD | 4500029623 | 40 | 6 | EA | 2024-11-18 |  | 180078395 |  | 90020249 | 07 | Execution | 0000216479 | 127 | 127 | 0 | [8 empty] | 00000107000000000580 | P07-WAREHOUSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-02-16 | ODST-0090020249_0040 | 0 | 60 | 54 | 60 | 2024-11-18 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-14 | 2024-11-20 | 2024-12-09 |  |  | 2024-12-31 | 0 | 5000234520_2024_0001 | 2024-10-10 |  | 2024-10-07 |  |  | 0 | 2 | 2 | 90020249 | 0 | 6 |  | 2 | 0 | 0 | X | L |  | 0 | 5000234520 |  | 0 | 2024 | 180078395 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | 2024-09-21 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020249_0040 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-24 | 30 |  | 2024-11-20 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1180 |  | 5300014053 | 130 | 6 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-09-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0150 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | 6 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Linked STO 5300014053 change failed for Order 600002862 Item 114 |  | SP97 | Direct Multi-base | 0 | AA01 | 5300014053 | 70 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020245 | 07 | Execution | 0000216479 | 114 | 0 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 6 |  |  |  | 1001 | 2024-08-13 |  | 0 | 0 | 0 | 0 |  | 2024-10-08 | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 |  | 2024-09-27 |  | 2024-10-10 |  |  | 0 | 2 | 0 | 90020245 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-09-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020245_0020 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA02 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1060 |  | 5300014053 | 70 | 6 | EA | 1001 | AA02 | 2024-09-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0250 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.09.2024) | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | 6 | EA | 0 | 0 | 6 | 0 |  | At KGP 19/10/24 | Supply for Order 600002862, Item 125 cannot be changed 180082361 item 20 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300006667 | 1160 | EXW | 7 | 1000019709 | 125 | 30003000 | PIPESERV GARDINER INVESTMENTS QLD PTY LTD | 4500029623 | 20 | 6 | EA | 2024-11-18 |  | 180078395 |  | 90020249 | 07 | Execution | 0000216479 | 125 | 125 | 0 | [8 empty] | 00000107000000000580 | P07-WAREHOUSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-02-16 | ODST-0090020249_0020 | 0 | 60 | 54 | 60 | 2024-11-18 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-14 | 2024-11-20 | 2024-12-09 |  |  | 2024-12-31 | 0 | 5000234502_2024_0001 | 2024-10-10 |  | 2024-10-07 |  |  | 0 | 2 | 2 | 90020249 | 0 | 6 |  | 2 | 0 | 0 | X | L |  | 0 | 5000234502 |  | 0 | 2024 | 180078395 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | 2024-09-21 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020249_0020 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-24 | 30 |  | 2024-11-20 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1160 |  | 5300014053 | 110 | 6 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-09-27 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0160 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | 10 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Linked STO 5300014053 change failed for Order 600002862 Item 115 |  | SP97 | Direct Multi-base | 0 | AA01 | 5300014053 | 80 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90020245 | 07 | Execution | 0000216479 | 115 | 0 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 10 |  |  |  | 1001 | 2024-08-13 |  | 0 | 0 | 0 | 0 |  | 2024-10-08 | AA53 | 2024-11-22 | [7 empty] | 2024-12-31 | 0 |  | 2024-09-27 |  | 2024-10-10 |  |  | 0 | 2 | 0 | 90020245 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-09-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | 2024-08-31 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020245_0030 |  |  | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA02 |  | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 | 30 | 30 | 5300006667 | 1070 |  | 5300014053 | 80 | 10 | EA | 1001 | AA02 | 2024-09-27 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-10 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0260 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.09.2024) | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | 10 | EA | 0 | 0 | 10 | 0 |  | At KGP 19/10/24 | Supply for Order 600002862, Item 126 cannot be changed 180082361 item 30 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300006667 | 1170 | EXW | 7 | 1000019709 | 126 | 30003000 | PIPESERV GARDINER INVESTMENTS QLD PTY LTD | 4500029623 | 30 | 10 | EA | 2024-11-18 |  | 180078395 |  | 90020249 | 07 | Execution | 0000216479 | 126 | 126 | 0 | [8 empty] | 00000107000000000580 | P07-WAREHOUSE | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-02-16 | ODST-0090020249_0030 | 0 | 60 | 54 | 60 | 2024-11-18 | 2024-10-13 | AA53 | 2024-11-22 |  |  | 2024-12-14 | 2024-11-20 | 2024-12-09 |  |  | 2024-12-31 | 0 | 5000234504_2024_0001 | 2024-10-10 |  | 2024-10-07 |  |  | 0 | 2 | 2 | 90020249 | 0 | 10 |  | 2 | 0 | 0 | X | L |  | 0 | 5000234504 |  | 0 | 2024 | 180078395 | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | 2024-09-21 | W |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade |  |  | 90020249_0030 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-24 | 30 |  | 2024-11-20 |  | 0 |  | 24SDLN2C | MJ |  | AU1072 | 1000214854 | S002 | 30 | 30 | 5300006667 | 1170 |  | 5300014053 | 120 | 10 | EA | 2001 | AA02 | 2024-10-10 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 216479 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-11-01 |  | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | X | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Maintenance Order material has been deleted | 70011010 | Restriction Orifice Plate 41RO20 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.09 - SOH @ AA01 | Supplying document 5300006667 890 could not be updated on RESB due to locks |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 92 | 0 | 1 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 |  |  | AA53 | 2024-10-21 | [7 empty] | 2024-12-31 | 0 |  |  |  |  | LNG2 COP |  | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70011010 | Restriction Orifice Plate 41RO20 | 2024-08-12 | E |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter | [5 empty] | LN2 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 30 |  |  |  | 0 |  | 24SDLN2C | MJ |  |  | 1000214854 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-22 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0880 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(12.08.2024) | 70011010 | Restriction Orifice Plate 41RO20 | 1 | EA | 0 | 0 | 0 | 0 |  | SPT Error TOP HU 102000000019832 - 2nd HU 101000000094259 | Supply for Order 600002862, Item 96 cannot be changed 90022126 item 10 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300014053 | 10 | CPT | 21 | 1000017114 | 96 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500026367 | 10 | 1 | EA | 2024-09-27 |  | /180068765 |  | 90022126 | 07 | Execution | 0000216479 | 96 | 0 | 0 | [8 empty] | 00000102000000019832 | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090022126_0010 | 0 | 3 | 0 | 0 | 2024-10-17 | 2024-10-26 | AA53 | 2024-10-21 |  |  | 2024-10-21 | 2024-10-20 | 2024-10-29 |  |  | 2024-12-31 | 0 | 5000214213_2024_0001 | 2024-10-22 |  | 2024-09-19 |  |  | 0 | 3 | 3 | 90022126 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000214213 |  | 0 | 2024 | /018006876 | 2024-10-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70011010 | Restriction Orifice Plate 41RO20 | 2024-08-12 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90022126_0010 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-09-18 | 30 |  | 2024-10-20 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 |  |  | 5300006667 | 900 |  | 5300014053 | 10 | 1 | EA | 1001 | AA02 | 2024-10-22 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2024-10-15 | 2024-10-22 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0010 | 0890 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(12.08.2024) | 70011014 | Restriction Orifice Plate 41RO21 | 1 | EA | 0 | 0 | 0 | 0 |  | SPT Error TOP HU 102000000019832 - 2nd HU 101000000094290 | Supply for Order 600002862, Item 98 cannot be changed 90022126 item 20 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300014053 | 20 | CPT | 21 | 1000017114 | 98 | 30000390 | AUSTRALASIAN FITTINGS AND FLANGES | 4500026367 | 20 | 1 | EA | 2024-09-27 |  | /180068765 |  | 90022126 | 07 | Execution | 0000216479 | 98 | 0 | 0 | [8 empty] | 00000102000000019832 | KSF-P07-SD-LRG | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090022126_0020 | 0 | 3 | 0 | 0 | 2024-10-17 | 2024-10-26 | AA53 | 2024-10-21 |  |  | 2024-10-21 | 2024-10-20 | 2024-10-29 |  |  | 2024-12-31 | 0 | 5000214221_2024_0001 | 2024-10-22 |  | 2024-09-19 |  |  | 0 | 3 | 3 | 90022126 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000214221 |  | 0 | 2024 | /018006876 | 2024-10-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70011014 | Restriction Orifice Plate 41RO21 | 2024-08-12 | W |  | 0010 | IC Mech Fitter | INT | IC Mech Fitter |  |  | 90022126_0020 |  |  | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-09-18 | 30 |  | 2024-10-20 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 |  |  | 5300006667 | 910 |  | 5300014053 | 20 | 1 | EA | 1001 | AA02 | 2024-10-22 |  |  |  | AU00 | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Date set by external system/Partially confirmed/Released/Material shortage/Settlement rule created/Goods movement posted/Object created/Ready For Scheduling/Pre-costed | AM06 | Capital | R0-010051-02-01-EX
| 24SDLN2C | Released | 2024-02-29 | 2025-02-25 | 2025-02-25 | 2024-10-20 | 2025-05-10 | MECH | 600002862 | 0081 | 0280 | 600002862 | LNG2 COP 2024 – Execution | AA53.LN2.B0252 | GAS LIQUEFACTION TRAIN 2 | AA01 | 30 | Issue detected, please check message in derivation or orchestration log | 70013860 | SPADE BLIND 200MM CL150 FF A516 GR70 | 1 | EA | 0 | 0 | 0 | 0 |  | ISSUE WITH MOZZIE NUMBER | Linked STO 5300014053 change failed for Order 600002862 Item 132 | PR approved; PO not issued | SP97 | Direct Multi-base | 20 | AA01 | 5300014053 | 140 |  | 20 | 1000020613 | 132 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000216479 | 132 | 0 | 0 | [8 empty] | WorkPackLink |  | P07 - LNG2 COP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | PRPO-1000020613_00132 | 0 | 25 | 0 | 25 | 2025-02-17 | 2025-03-08 | AA53 | 2024-11-22 |  |  | 2025-03-22 | 2025-02-23 | 2025-03-14 |  |  | 2024-12-31 | 0 |  | 2025-02-25 |  | 2025-03-14 |  |  | 0 | 6 | 6 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70013860 | SPADE BLIND 200MM CL150 FF A516 GR70 | 2024-10-04 | E |  | 0081 | 2C1101 Spade | INT | 2C1101 Spade | [5 empty] | LN2 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-01-20 | 30 |  | 2025-02-23 |  | 0 |  | 24SDLN2C | MJ |  | AU1009 | 1000214854 | S001 |  |  | 5300006667 | 1220 |  | 5300014053 | 140 | 1 | EA | 1001 | AA02 | 2025-02-25 |  |  |  |  | 1070 |  | 2024-10-20 | 1001 | Woodside Energy Ltd | W001 | WOP2ZH | 2024-01-23 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00064002 | 2025-05-10 | 2024-10-20 | 2024-10-20 | Partially confirmed/Material shortage/Goods movement posted/Ready For Scheduling/Pre-costed/Object created/Settlement rule created/Released/Date set by external system | AM06 | Capital | R0-010051-02-01-EX

## Pivot
Release id (" "=rel., X=not yet,1=never) | MO Revision | MO number | Description | Oper/Act number of Reservation | BOM item number | Material / Component | Material Description | Expediting Note / User Comment | Reservation Item | Reservation | Average of Requirement quantity | Sum of HU Quantity | Average of Remaining quanity | Sum of Withdrawn quantity
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0001 | 0010 | 10592509 | BLADE,SAW;RECIP,CB,8TPI,1",230MM | UserCommentLink | 135 | 0000216479 | 50 | 50 | 0 | 50
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | X | 70011010 | Restriction Orifice Plate 41RO20 | 21.09 - SOH @ AA01 | 92 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0010 | 10048528 | FLANGE,BLIND;150MM,CL300,RF,LTCS | 06.03 - ETA 17.04.24 PO 4500005010 x 1 Australasian Fittings | 1 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0020 | 10048552 | FLANGE,BLIND;600MM,CL600,RF,LTCS | 03.10 - HU 101000000060519 to AA02 | 2 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0030 | 10048593 | FLANGE,BLIND,150MM,CL150,RF,CS,SH40,GALV | 03.10 - GR ZONE @ AA02 | 3 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0040 | 10048594 | FLANGE,BLIND;200MM,CL150,RF,CS,SH30,GALV | 03.10 - HU 101000000052150 to AA02 | 4 | 0000216479 | 7 | 7 | 0 | 7
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0050 | 10048596 | FLANGE,BLIND;300MM,CL150,RF,CS,SH30,GALV | 01.10 - HU 101000000052151 TO AA02 OLS5307169 | 5 | 0000216479 | 5 | 5 | 0 | 5
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0060 | 10049289 | FLANGE,BLIND;50MM,CL300,RF,SS316 | 01.10 - HU 101000000093006 TO AA02 | 6 | 0000216479 | 2 | 1 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0070 | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 24.10 - ETA 05.12.24 PO 4500029844 MRC | 7 | 0000216479 | 4 | 0 | 4 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0080 | 10053093 | SPADE BLIND,150MM,CL300,SS,TP316L | 16.10 - 180082367 4500005381, 103 ERRORS | 8 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0090 | 10058201 | STUDBOLT;0.625" X 100MM,A193 B8M CL2 | 25.09 - At KGP | 9 | 0000216479 | 16 | 16 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0100 | 10058202 | STUDBOLT;0.625" X 110MM,A193 B8M CL2 | 21.09 - MW2R11C02G @ KSF | 10 | 0000216479 | 20 | 20 | 0 | 20
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0110 | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 01.10 - HU 101000000092978, 93001 TO AA02 | 11 | 0000216479 | 8 | 8 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0120 | 10058205 | STUDBOLT;0.625" X 130MM,A193 B8M CL2 | 22.09 - IN GREY TUB / MW2R11C03G @ KSF | 12 | 0000216479 | 8 | 8 | 0 | 8
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0130 | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 03.10 - Del 90009764/90009765 15-05-10-03CB @ AA01 | 13 | 0000216479 | 28 | 16 | 15 | 26
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0140 | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 01.10 - HU 101000000094405 TO AA02 | 14 | 0000216479 | 12 | 12 | 8 | 8
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0150 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 03.10 - Del 80018277/000010 for picking | 15 | 0000216479 | 16 | 16 | 8 | 16
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0160 | 10058262 | BLT STUD:1.125in,190mm,316 SS,2,UN HEAVY | 25.09 - At KGP | 16 | 0000216479 | 16 | 16 | 0 | 16
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0170 | 10059968 | GASKET;CNAF,50MM,CL150,TANG INTN,1.6MM | 22.09 - IN GREY TUB / MW2R05F11H @ KSF | 17 | 0000216479 | 2 | 2 | 0 | 2
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0180 | 10059971 | GASKET;CNAF,150MM,CL150,TANG INTN,1.6MM | 01.10 - HU 101000000092373 TO AA02 | 18 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0190 | 10059972 | GASKET;CNAF,200MM,CL150,TANG INTN,1.5MM | X1 LOOSE | 19 | 0000216479 | 8 | 8 | 0 | 8
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0200 | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 | 03.10 - KSF-PACK-REV-SML for picking | 20 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0210 | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 25.09 - At KGP | 21 | 0000216479 | 4 | 4 | 0 | 4
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0220 | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 21.09 - MW2R03C03J @ KSF | 22 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0230 | 10060888 | GASKET;SWCI,150MM,CL150,316L/GR/316 | 01.10 - HU 101000000093005 TO AA02 | 23 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0240 | 10060892 | GASKET;SWCI,350MM,CL150,316L/GR/316 | 03.10 - SW3R03E02B @ AA02 | 24 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0250 | 10060894 | GASKET;SWCI,450MM,CL150,316L/GR/316 | 22.09 - X1 LOOSE / MW2R04J02B @ KSF | 25 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0260 | 10060901 | GASKET;SWCI,100MM,CL300,SS316L/GR/316 | 21.09 - MW2R03A02A @ KSF | 26 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0270 | 10060902 | GASKET;SWCI,150MM,CL300,316L/GR/316 | 22.09 - IN GREY TUB / MW2R04F02A @ KSF | 27 | 0000216479 | 4 | 4 | 0 | 4
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0280 | 10060904 | GASKET;SWCI,250MM,CL300,316L/GR/316 | 22.09 - X1 LOOSE / MW2R03A03E @ KSF | 28 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0290 | 10060905 | GASKET;SWCI,300MM,CL300,316L/GR/316 | 25.09 - At KGP | 29 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0300 | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 22.09 - X1 LOOSE / MW2R04J03D @ KSF | 30 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0310 | 10060907 | GASKET;SWCI,400MM,CL300,SS316L/GR/316 | 22.09 - X1 LOOSE / MW2R05E07D @ KSF | 31 | 0000216479 | 8 | 8 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0320 | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 22.09 - IN GREY TUB / MW2R03B03A @ KSF | 32 | 0000216479 | 12 | 12 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0330 | 10060920 | GASKET:RF,80mm,4.5mm,316L,CL300,SWCI,GR | 21.09 - 10-16-11-02B @ PDC X 3 | 33 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0340 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 22.09 - IN GREY TUB / MW2R03A02C @ KSF | 34 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0350 | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 22.09 - IN GREY TUB / MW2R04J02D @KSF | 35 | 0000216479 | 2 | 2 | 0 | 2
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0360 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 21.09 - MW2R04H04A @ KSF / X1 FLAT PACK | 36 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0370 | 10061003 | GASKET;SWCI,1050MM,CL150,316L/GR/316 | X1 PALLET | 37 | 0000216479 | 2 | 2 | 0 | 2
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0380 | 10218613 | STUDBOLT;0.625" X 110MM,L7,ZN+XYLAN | 22.09 - X2 boxes / SOH @ AA01 | 38 | 0000216479 | 12 | 12 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0390 | 10218617 | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN | 22.09 - X1 BOX / SOH @ PDC | 39 | 0000216479 | 48 | 48 | 0 | 48
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0400 | 10218625 | STUDBOLT;0.750"X110MM,L7,CAD+XYLAN | 22.09 - X1 BOX / MW3R15B08B @ KSF | 40 | 0000216479 | 8 | 8 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0410 | 10218626 | STUDBOLT;0.750"X120MM,L7,CAD+XYLAN | 22.09 - X3 BOX / 24 Stocked @ PDC, 12 @ KSF | 41 | 0000216479 | 48 | 48 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0420 | 10218627 | STUDBOLT;0.750"X130MM,L7,CAD+XYLAN | 22.09 - X1 BOX/ 20 SOH @ AA01 | 42 | 0000216479 | 32 | 32 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0430 | 10218628 | STUDBOLT;0.750"X140MM,L7,CAD+XYLAN | X1 BOX | 43 | 0000216479 | 20 | 20 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0440 | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 01.10 - HU 101000000094408 TO AA02 | 44 | 0000216479 | 60 | 60 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0450 | 10218636 | STUDBOLT;0.875"X180MM,L7,CAD+XYLAN | 03.10 - GR ZONE @ AA02 | 45 | 0000216479 | 8 | 8 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0460 | 10218652 | STUDBOLT;1.125"X190MM,L7,CAD+XYLAN | 01.10 - HU 101000000094366 TO AA02 | 46 | 0000216479 | 16 | 16 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0470 | 10218657 | STUDBOLT;1.125"X230MM,L7,CAD+XYLAN | 22.09 - X2 BOXES / MW3R12D05A @ KSF | 47 | 0000216479 | 40 | 40 | 0 | 40
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0480 | 10219526 | STUDBOLT;0.750"X160MM,L7,CAD+XYLAN | 01.10 - HU 101000000093107 TO AA02 | 48 | 0000216479 | 8 | 8 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0490 | 10219538 | STUDBOLT;1.250"X250MM,L7,CAD+XYLAN | 01.10 - HU 101...93499, 93530,43,45 TO AA02 | 49 | 0000216479 | 80 | 80 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0500 | 10219885 | STUDBOLT;1.125"X240MM,L7,CAD+XYLAN | 10.10 - Del 80018302/000010 for picking | 50 | 0000216479 | 12 | 0 | 12 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0510 | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | X1 CRATE | 51 | 0000216479 | 24 | 24 | 0 | 24
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0520 | 10220455 | STUDBOLT;0.875" X 180MM,A193 B8M CL2 | 22.09 - X1 BOX / MW3R15F09A @ KSF | 52 | 0000216479 | 8 | 8 | 0 | 8
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0530 | 10222953 | SPADE BLIND,50MM,CL300,RF,A516-60/70 | 01.10 - HU 101000000093007 TO AA02 | 53 | 0000216479 | 6 | 6 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0540 | 10223374 | STUDBOLT;0.750"X140MM,A193 B8M,CL2 | 22.09 - IN GREY TUB / MW2R03A02A @ KSF | 54 | 0000216479 | 20 | 20 | 0 | 20
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0550 | 10229938 | SPADE BLIND,80MM,CL150,SS316 | 16.10 - 180082367 4500005381, 103 ERRORS | 55 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0560 | 10254870 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN50C> | In Transit voyage 20003452 | 56 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0570 | 10254871 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN80C> | In Transit voyage 20003452 | 57 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0580 | 10254875 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN100> | In Transit voyage 20003452 | 58 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0590 | 10254974 | SPADE,BLIND;CAMCO 7666720DN50CL3008MM | In Transit voyage 20003452 | 59 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0600 | 10254979 | SPADE,BLIND,80MM,CL600,15MM,SS304 | In Transit voyage 20003452 | 60 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0610 | 10306724 | GASKET;SWC,80MM,CL300/600,31>WSE10508041 | 22.09 - IN GREY TUB / 4 SOH @ AA02 | 61 | 0000216479 | 8 | 8 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0620 | 10441378 | SPADE BLIND,100MM,CL600,CS | 16.10 - 180082367 4500005381, 103 ERRORS | 62 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0630 | 10487244 | SPADE,BLIND,80MM,CL300,LTCS | In Transit voyage 20003452 | 63 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0640 | 10487245 | SPADE,BLIND,100MM,CL300,LTCS | In Transit voyage 20003452 | 64 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0650 | 10488048 | FLANGE,BLIND,150MM,CL300,RF,SS | 01.10 - HU 101000000093024 TO AA02 | 65 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0660 | 10488940 | SPADE,BLIND,80MM,CL600,LTCS | In Transit voyage 20003452 | 66 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0670 | 10590596 | GASKET;RF,GR,300MM,CL150,KLINGER 154756 | 01.10 - HU 101000000093397 TO AA02 | 67 | 0000216479 | 6 | 6 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0680 | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 03.10 - GR ZONE @ AA02 | 68 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0690 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 06.03 - ETA 17.04.24 PO 4500004781 x 3 Australasian, ETA 16.02.24 PO W451781228 | 69 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0700 | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 14.10 - HU 101000000056226 TO AA02 | 70 | 0000216479 | 6 | 6 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0710 | 10060939 | GASKET;SWCI,450MM,CL600,316L/GR/316 | 22.09 - X4 FLAT PACKS / 4 SOH @ KSF /180071538 75KG 18.09.24 PO 4500024711 | 71 | 0000216479 | 12 | 12 | 0 | 12
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0720 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 25.09 - At KGP | 72 | 0000216479 | 6 | 6 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0730 | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 01.10 - HU 101000000094101 - 08 TO AA02 | 73 | 0000216479 | 24 | 24 | 22 | 6
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0740 | 10492979 | STUDBOLT;1.875" X 470MM,L7,ZN+XYLAN | 01.10 - HU 101000000080184 TO AA02 | 74 | 0000216479 | 48 | 48 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0750 | 10052685 | SPADE BLIND,600MM,CL600,RF,LTCS | 01.10 - HU 101000000060720 TO AA02 | 75 | 0000216479 | 1 | 1 | 0 | 1
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0760 | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 24.10 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 76 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0770 | 10049310 | FLANGE,BLIND;80MM,CL600,RF,SS316 | 01.10 - HU 101000000093021 TO AA02 | 77 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0780 | 10052696 | SPADE BLIND,150MM,CL150,CS,A285 GR.C | 01.10 - HU 101000000093390 TO AA02 | 78 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0790 | 10229941 | SPADE BLIND,50MM,CL600,SS316 | 01.10 - HU 101000000092975 TO AA02 | 79 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0800 | 10229942 | SPADE BLIND,100MM,CL600,SS316 | 16.10 - 180082367 4500005381, 103 ERRORS | 80 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0810 | 10049295 | FLANGE,BLIND;300MM,CL300,RF,SS316 | 01.10 - HU 101000000076282 TO AA02 | 81 | 0000216479 | 1 | 1 | 0 | 1
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0840 | 10613639 | SPADE BLIND 150MM CL150 FF A516 GR70 | In Transit voyage 20003452 | 84 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0850 | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 01.10 - HU 101000000068823 TO AA02 | 85 | 0000216479 | 10 | 10 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0860 | 11400805 | SPADE,BLIND,200MM,CL600,LTCS | 01.10 - HU 101000000040351 TO AA02 | 86 | 0000216479 | 1 | 1 | 0 | 1
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0870 | 11400808 | SPADE BLIND,350MM,CL150,SS316 | 01.10 - HU 101000000085146 TO AA02 | 87 | 0000216479 | 1 | 1 | 0 | 1
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0880 | 70011010 | Restriction Orifice Plate 41RO20 | SPT Error TOP HU 102000000019832 - 2nd HU 101000000094259 | 96 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0890 | 70011014 | Restriction Orifice Plate 41RO21 | SPT Error TOP HU 102000000019832 - 2nd HU 101000000094290 | 98 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0900 | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | UserCommentLink | 130 | 0000216479 | 4 | 4 | 0 | 4
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0900 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | UserCommentLink | 99 | 0000216479 | 0 | 0 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0910 | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | MRF 241026-6712278 processed to 5001 HU 1020-22091 P-99 | 133 | 0000216479 | 24 | 24 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | (blank) | 10053011 | SPADE BLIND,150MM,CL300,SS316 | 01.10 - HU 101000000094436 TO AA02 | 89 | 0000216479 | 1 | 1 | 0 | 1
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | (blank) | 10053014 | SPADE BLIND,300MM,CL300,SS316 | 01.10 - HU 101000000094436 TO AA02 | 88 | 0000216479 | 1 | 1 | 0 | 1
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | (blank) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 22.09 - IN GRAY TUB / MW2R03B03E @ KSF | 90 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | X | 10062985 | AIR,MEDICAL,DRY,COMPRESSED,SIZE G CYL | 14.10 - ETA 18.10.24 PO 4500031439 BOC | 128 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | X | 10312854 | AIR;MEDICAL DRY,25PPM,BOC 470MAN15 | 24.10 - ETA 24.10.24 PO 4500031439 BOC | 129 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0010 | 10488134 | SPADE,BLIND,250MM,CL300,SS | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALIAN FITTINGS | 100 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0020 | 10441379 | SPADE BLIND,150MM,CL600,CS | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 101 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0030 | 10340106 | SPADE BLIND,50MM,CL150,CS,A285,GDE C | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 102 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0040 | 10255008 | SPADE,BLIND,1050MM,CL150,55MM,SS304 | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALIAN FITTINGS | 103 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0050 | 10052675 | SPADE BLIND,350MM,CL300,RF,A516-60 | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 104 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0060 | 10340086 | FLANGE,BLIND;350MM,CL300,RF,CS,A105N | 05.10 - HU 101000000096902 to AA02 | 105 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0070 | 10613642 | SPADE BLIND 200MM CL150 FF A516 GR70 | 21.09 - NEED PURCHSING | 106 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0080 | 10291772 | FLANGE,BLIND;200MM,CL150,RF,CS,A105M | 05.10 - HU 101000000096902 to AA02 | 107 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0090 | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 108 | 0000216479 | 1 | 1 | 0 | 1
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0100 | 10048469 | FLANGE,BLIND;450MM,CL150,RF,CS,A105N | 14.10 - HU 101000000099504 TO AA02 | 109 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0110 | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 02.10 - ETA 17.12.24 PO 4500029495 AUS FITTINGS @AA02 | 110 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0120 | 10202334 | FLANGE,BLIND;350MM,CL150,RF,CS,A105N | 05.10 - HU 101000000096902 to AA02 | 111 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0130 | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | UserCommentLink | 112 | 0000216479 | 10 | 0 | 10 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0140 | 11404775 | CONTRACTOR;100-250V,ABB 1SFL547002R3322 | UserCommentLink | 113 | 0000216479 | 6 | 0 | 6 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0150 | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | UserCommentLink | 114 | 0000216479 | 6 | 0 | 6 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0160 | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | UserCommentLink | 115 | 0000216479 | 10 | 0 | 10 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0170 | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | UserCommentLink | 116 | 0000216479 | 6 | 0 | 6 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0180 | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 05.10 - Del 80019284 for picking | 117 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0190 | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 03.10 - HU 101000000094431 to AA02 | 118 | 0000216479 | 4 | 4 | 0 | 4
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0200 | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 10.10 - Del 80018247/000070 for picking | 119 | 0000216479 | 4 | 3 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0210 | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 14.10 - HU 101000000099762 TO AA02 | 120 | 0000216479 | 6 | 6 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0220 | 10043687 | TEE:EQUAL,50mm,BW,CS,A234-WPB,SCH 40 | 05.10 - HU 101000000096674 to AA02 | 121 | 0000216479 | 4 | 4 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0230 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 03.10 - HU 101000000093112 to AA02 | 122 | 0000216479 | 6 | 6 | 0 | 18
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0240 | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | At KGP 19/10/24 | 123 | 0000216479 | 10 | 0 | 10 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0250 | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | At KGP 19/10/24 | 125 | 0000216479 | 6 | 0 | 6 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0260 | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | At KGP 19/10/24 | 126 | 0000216479 | 10 | 0 | 10 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0270 | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | At KGP 19/10/24 | 127 | 0000216479 | 6 | 0 | 6 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0280 | 70013860 | SPADE BLIND 200MM CL150 FF A516 GR70 | ISSUE WITH MOZZIE NUMBER | 132 | 0000216479 | 1 | 0 | 1 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0290 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | UserCommentLink | 134 | 0000216479 | 6 | 0 | 6 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0300 | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | UserCommentLink | 136 | 0000216479 | 2 | 2 | 0 | 2
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0310 | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | UserCommentLink | 137 | 0000216479 | 1 | 1 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0320 | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | UserCommentLink | 138 | 0000216479 | 2 | 2 | 0 | 0
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0330 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | UserCommentLink | 139 | 0000216479 | 10 | 10 | 0 | 0
Grand Total | [10 empty] | 9.1544 | 923 | 1.5839 | 371

## WSheet
Release id (" "=rel., X=not yet,1=never) | MO Revision | MO number | Description | Oper/Act number of Reservation | BOM item number | Material | Material Description | Expediting Note / User Comment | Reservation Item | Reservation | Requirement QTY | HU QTY | Remaining QTY | Withdrawn QTY | Unique | Issued to WO MB51 Issued QTY | Issued to WO MB51 $ | Unit Price MM60 | Requirement $ | Withdrawn $ | Remaining $ | AA53 SOH 5001 | AA53 SOH In Transit | AA53 SOH 2001 | Enough to consume | All Work Order Demand | Issue All | SLOC & Material | SLOC
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0001 | 0010 | 10592509 | BLADE,SAW;RECIP,CB,8TPI,1",230MM | UserCommentLink | 135 | 0000216479 | 50 | 50 | 0 | 50 | 10592509600002862 | 50 | 1631.5 | 32.63 | 1631.5 | 1631.5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 105925095001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | X | 70011010 | Restriction Orifice Plate 41RO20 | 21.09 - SOH @ AA01 | 92 | 0000216479 | 1 | 0 | 1 | 0 | 70011010600002862 |  |  | 560 | 560 | 0 | 560 | 0 |  | 1 | -1 | 2 | -2 | 700110105001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0010 | 10048528 | FLANGE,BLIND;150MM,CL300,RF,LTCS | 06.03 - ETA 17.04.24 PO 4500005010 x 1 Australasian Fittings | 1 | 0000216479 | 1 | 1 | 0 | 0 | 10048528600002862 |  |  | 198 | 198 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100485285001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0020 | 10048552 | FLANGE,BLIND;600MM,CL600,RF,LTCS | 03.10 - HU 101000000060519 to AA02 | 2 | 0000216479 | 1 | 1 | 0 | 0 | 10048552600002862 |  |  | 6356.26 | 6356.26 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100485525001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0030 | 10048593 | FLANGE,BLIND,150MM,CL150,RF,CS,SH40,GALV | 03.10 - GR ZONE @ AA02 | 3 | 0000216479 | 1 | 1 | 0 | 0 | 10048593600002862 |  |  | 238.38 | 238.38 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100485935001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0040 | 10048594 | FLANGE,BLIND;200MM,CL150,RF,CS,SH30,GALV | 03.10 - HU 101000000052150 to AA02 | 4 | 0000216479 | 7 | 7 | 0 | 7 | 10048594600002862 | 7 | 1966.3 | 280.9 | 1966.3 | 1966.3 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100485945001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0050 | 10048596 | FLANGE,BLIND;300MM,CL150,RF,CS,SH30,GALV | 01.10 - HU 101000000052151 TO AA02 OLS5307169 | 5 | 0000216479 | 5 | 5 | 0 | 5 | 10048596600002862 | 5 | 2751 | 550.2 | 2751 | 2751 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100485965001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0060 | 10049289 | FLANGE,BLIND;50MM,CL300,RF,SS316 | 01.10 - HU 101000000093006 TO AA02 | 6 | 0000216479 | 2 | 1 | 1 | 0 | 10049289600002862 |  |  | 82.46 | 164.92 | 0 | 82.46 | 0 |  | 1 | -1 | 1 | -1 | 100492895001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0070 | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 24.10 - ETA 05.12.24 PO 4500029844 MRC | 7 | 0000216479 | 4 | 0 | 4 | 0 | 10052676600002862 | 4 | 10297.84 | 2574.46 | 10297.84 | 0 | 10297.84 | 0 |  | 0 | -4 | 4 | -4 | 100526765001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0080 | 10053093 | SPADE BLIND,150MM,CL300,SS,TP316L | 16.10 - 180082367 4500005381, 103 ERRORS | 8 | 0000216479 | 1 | 1 | 0 | 0 | 10053093600002862 |  |  | 819.5 | 819.5 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100530935001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0090 | 10058201 | STUDBOLT;0.625" X 100MM,A193 B8M CL2 | 25.09 - At KGP | 9 | 0000216479 | 16 | 16 | 0 | 0 | 10058201600002862 |  |  | 5.95 | 95.2 | 0 | 0 | 120 |  | 0 | 120 | 0 | 120 | 100582015001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0100 | 10058202 | STUDBOLT;0.625" X 110MM,A193 B8M CL2 | 21.09 - MW2R11C02G @ KSF | 10 | 0000216479 | 20 | 20 | 0 | 20 | 10058202600002862 | 20 | 35 | 1.75 | 35 | 35 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100582025001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0110 | 10058203 | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 01.10 - HU 101000000092978, 93001 TO AA02 | 11 | 0000216479 | 8 | 8 | 0 | 0 | 10058203600002862 |  |  | 5.7 | 45.6 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 100582035001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0120 | 10058205 | STUDBOLT;0.625" X 130MM,A193 B8M CL2 | 22.09 - IN GREY TUB / MW2R11C03G @ KSF | 12 | 0000216479 | 8 | 8 | 0 | 8 | 10058205600002862 | 8 | 47.36 | 5.92 | 47.36 | 47.36 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100582055001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0130 | 10058222 | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 03.10 - Del 90009764/90009765 15-05-10-03CB @ AA01 | 13 | 0000216479 | 28 | 16 | 15 | 26 | 10058222600002862 | 13 | 143.54 | 12.48 | 349.44 | 324.48 | 187.2 | 0 |  | 3 | -15 | 15 | -15 | 100582225001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0140 | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 01.10 - HU 101000000094405 TO AA02 | 14 | 0000216479 | 12 | 12 | 8 | 8 | 10058249600002862 | 4 | 77.44 | 19.36 | 232.32 | 154.88 | 154.88 | 0 |  | 8 | -8 | 8 | -8 | 100582495001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0150 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 03.10 - Del 80018277/000010 for picking | 15 | 0000216479 | 16 | 16 | 8 | 16 | 10058252600002862 | 8 | 179.12 | 22.39 | 358.24 | 358.24 | 179.12 | 0 |  | 8 | -8 | 8 | -8 | 100582525001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0160 | 10058262 | BLT STUD:1.125in,190mm,316 SS,2,UN HEAVY | 25.09 - At KGP | 16 | 0000216479 | 16 | 16 | 0 | 16 | 10058262600002862 | 16 | 441.28 | 27.58 | 441.28 | 441.28 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100582625001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0170 | 10059968 | GASKET;CNAF,50MM,CL150,TANG INTN,1.6MM | 22.09 - IN GREY TUB / MW2R05F11H @ KSF | 17 | 0000216479 | 2 | 2 | 0 | 2 | 10059968600002862 | 2 | 7.83 | 3.92 | 7.84 | 7.84 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100599685001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0180 | 10059971 | GASKET;CNAF,150MM,CL150,TANG INTN,1.6MM | 01.10 - HU 101000000092373 TO AA02 | 18 | 0000216479 | 1 | 0 | 1 | 0 | 10059971600002862 |  |  | 14.25 | 14.25 | 0 | 14.25 | 2 |  | 0 | 1 | 1 | 1 | 100599715001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0190 | 10059972 | GASKET;CNAF,200MM,CL150,TANG INTN,1.5MM | X1 LOOSE | 19 | 0000216479 | 8 | 8 | 0 | 8 | 10059972600002862 | 8 | 224.14 | 32.64 | 261.12 | 261.12 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100599725001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0200 | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 | 03.10 - KSF-PACK-REV-SML for picking | 20 | 0000216479 | 2 | 2 | 0 | 0 | 10060885600002862 |  |  | 4.78 | 9.56 | 0 | 0 | 81 |  | 21 | 81 | 0 | 81 | 100608855001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0210 | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 25.09 - At KGP | 21 | 0000216479 | 4 | 4 | 0 | 4 | 10060886600002862 | 4 | 27.3 | 6.82 | 27.28 | 27.28 | 0 | 15 |  | 45 | 15 | 0 | 15 | 100608865001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0220 | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 21.09 - MW2R03C03J @ KSF | 22 | 0000216479 | 2 | 2 | 0 | 0 | 10060887600002862 |  |  | 10.29 | 20.58 | 0 | 0 | 5 |  | 81 | 5 | 0 | 5 | 100608875001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0230 | 10060888 | GASKET;SWCI,150MM,CL150,316L/GR/316 | 01.10 - HU 101000000093005 TO AA02 | 23 | 0000216479 | 4 | 4 | 0 | 0 | 10060888600002862 |  |  | 10.45 | 41.8 | 0 | 0 | 5 |  | 7 | 5 | 0 | 5 | 100608885001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0240 | 10060892 | GASKET;SWCI,350MM,CL150,316L/GR/316 | 03.10 - SW3R03E02B @ AA02 | 24 | 0000216479 | 2 | 2 | 0 | 0 | 10060892600002862 |  |  | 31.4 | 62.8 | 0 | 0 | 3 |  | 4 | 3 | 0 | 3 | 100608925001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0250 | 10060894 | GASKET;SWCI,450MM,CL150,316L/GR/316 | 22.09 - X1 LOOSE / MW2R04J02B @ KSF | 25 | 0000216479 | 2 | 2 | 0 | 0 | 10060894600002862 |  |  | 64.65 | 129.3 | 0 | 0 | 3 |  | 0 | 3 | 0 | 3 | 100608945001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0260 | 10060901 | GASKET;SWCI,100MM,CL300,SS316L/GR/316 | 21.09 - MW2R03A02A @ KSF | 26 | 0000216479 | 2 | 2 | 0 | 0 | 10060901600002862 |  |  | 11.72 | 23.44 | 0 | 0 | 23 |  | 15 | 23 | 0 | 23 | 100609015001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0270 | 10060902 | GASKET;SWCI,150MM,CL300,316L/GR/316 | 22.09 - IN GREY TUB / MW2R04F02A @ KSF | 27 | 0000216479 | 4 | 4 | 0 | 4 | 10060902600002862 | 4 | 65.61 | 16.7 | 66.8 | 66.8 | 0 | 1 |  | 1 | 1 | 0 | 1 | 100609025001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0280 | 10060904 | GASKET;SWCI,250MM,CL300,316L/GR/316 | 22.09 - X1 LOOSE / MW2R03A03E @ KSF | 28 | 0000216479 | 2 | 2 | 0 | 0 | 10060904600002862 |  |  | 25.01 | 50.02 | 0 | 0 | 13 |  | 0 | 13 | 0 | 13 | 100609045001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0290 | 10060905 | GASKET;SWCI,300MM,CL300,316L/GR/316 | 25.09 - At KGP | 29 | 0000216479 | 1 | 1 | 0 | 0 | 10060905600002862 |  |  | 31.67 | 31.67 | 0 | 0 | 6 |  | 4 | 6 | 0 | 6 | 100609055001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0300 | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | 22.09 - X1 LOOSE / MW2R04J03D @ KSF | 30 | 0000216479 | 4 | 4 | 0 | 0 | 10060906600002862 | 4 | 161.04 | 40.26 | 161.04 | 0 | 0 | 4 |  | 4 | 4 | 0 | 4 | 100609065001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0310 | 10060907 | GASKET;SWCI,400MM,CL300,SS316L/GR/316 | 22.09 - X1 LOOSE / MW2R05E07D @ KSF | 31 | 0000216479 | 8 | 8 | 0 | 0 | 10060907600002862 |  |  | 45.74 | 365.92 | 0 | 0 | 12 |  | 0 | 12 | 0 | 12 | 100609075001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0320 | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 22.09 - IN GREY TUB / MW2R03B03A @ KSF | 32 | 0000216479 | 12 | 12 | 0 | 0 | 10060919600002862 |  |  | 5.5 | 66 | 0 | 0 | 217 |  | 317 | 217 | 0 | 217 | 100609195001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0330 | 10060920 | GASKET:RF,80mm,4.5mm,316L,CL300,SWCI,GR | 21.09 - 10-16-11-02B @ PDC X 3 | 33 | 0000216479 | 4 | 4 | 0 | 0 | 10060920600002862 |  |  | 13.4 | 53.6 | 0 | 0 | 4 |  | 4 | 4 | 0 | 4 | 100609205001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0340 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 22.09 - IN GREY TUB / MW2R03A02C @ KSF | 34 | 0000216479 | 4 | 4 | 0 | 0 | 10060932600002862 |  |  | 14.54 | 58.16 | 0 | 0 | 11 |  | 72 | 11 | 6 | 5 | 100609325001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0350 | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 22.09 - IN GREY TUB / MW2R04J02D @KSF | 35 | 0000216479 | 2 | 2 | 0 | 2 | 10060934600002862 | 2 | 48.48 | 24.17 | 48.34 | 48.34 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100609345001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0360 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 21.09 - MW2R04H04A @ KSF / X1 FLAT PACK | 36 | 0000216479 | 1 | 1 | 0 | 0 | 10060941600002862 |  |  | 92.14 | 92.14 | 0 | 0 | 0 |  | 9 | 0 | 0 | 0 | 100609415001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0370 | 10061003 | GASKET;SWCI,1050MM,CL150,316L/GR/316 | X1 PALLET | 37 | 0000216479 | 2 | 2 | 0 | 2 | 10061003600002862 | 2 | 562.26 | 281.13 | 562.26 | 562.26 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100610035001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0380 | 10218613 | STUDBOLT;0.625" X 110MM,L7,ZN+XYLAN | 22.09 - X2 boxes / SOH @ AA01 | 38 | 0000216479 | 12 | 12 | 0 | 0 | 10218613600002862 |  |  | 3.1 | 37.2 | 0 | 0 | 4 |  | 17 | 4 | 0 | 4 | 102186135001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0390 | 10218617 | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN | 22.09 - X1 BOX / SOH @ PDC | 39 | 0000216479 | 48 | 48 | 0 | 48 | 10218617600002862 | 48 | 95.25 | 1.98 | 95.04 | 95.04 | 0 | 0 |  | 40 | 0 | 0 | 0 | 102186175001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0400 | 10218625 | STUDBOLT;0.750"X110MM,L7,CAD+XYLAN | 22.09 - X1 BOX / MW3R15B08B @ KSF | 40 | 0000216479 | 8 | 8 | 0 | 0 | 10218625600002862 |  |  | 6.88 | 55.04 | 0 | 0 | 8 |  | 0 | 8 | 0 | 8 | 102186255001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0410 | 10218626 | STUDBOLT;0.750"X120MM,L7,CAD+XYLAN | 22.09 - X3 BOX / 24 Stocked @ PDC, 12 @ KSF | 41 | 0000216479 | 48 | 48 | 0 | 0 | 10218626600002862 |  |  | 5.18 | 248.64 | 0 | 0 | 0 |  | 20 | 0 | 0 | 0 | 102186265001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0420 | 10218627 | STUDBOLT;0.750"X130MM,L7,CAD+XYLAN | 22.09 - X1 BOX/ 20 SOH @ AA01 | 42 | 0000216479 | 32 | 32 | 0 | 0 | 10218627600002862 |  |  | 7.62 | 243.84 | 0 | 0 | 64 |  | 32 | 64 | 0 | 64 | 102186275001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0430 | 10218628 | STUDBOLT;0.750"X140MM,L7,CAD+XYLAN | X1 BOX | 43 | 0000216479 | 20 | 20 | 0 | 0 | 10218628600002862 |  |  | 7.97 | 159.4 | 0 | 0 | 32 |  | 0 | 32 | 0 | 32 | 102186285001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0440 | 10218632 | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 01.10 - HU 101000000094408 TO AA02 | 44 | 0000216479 | 60 | 60 | 0 | 0 | 10218632600002862 |  |  | 6.89 | 413.4 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 102186325001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0450 | 10218636 | STUDBOLT;0.875"X180MM,L7,CAD+XYLAN | 03.10 - GR ZONE @ AA02 | 45 | 0000216479 | 8 | 8 | 0 | 0 | 10218636600002862 |  |  | 7.5 | 60 | 0 | 0 | 0 |  | 12 | 0 | 0 | 0 | 102186365001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0460 | 10218652 | STUDBOLT;1.125"X190MM,L7,CAD+XYLAN | 01.10 - HU 101000000094366 TO AA02 | 46 | 0000216479 | 16 | 16 | 0 | 0 | 10218652600002862 |  |  | 12.59 | 201.44 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 102186525001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0470 | 10218657 | STUDBOLT;1.125"X230MM,L7,CAD+XYLAN | 22.09 - X2 BOXES / MW3R12D05A @ KSF | 47 | 0000216479 | 40 | 40 | 0 | 40 | 10218657600002862 | 40 | 966.8 | 24.17 | 966.8 | 966.8 | 0 | 0 |  | 0 | 0 | 0 | 0 | 102186575001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0480 | 10219526 | STUDBOLT;0.750"X160MM,L7,CAD+XYLAN | 01.10 - HU 101000000093107 TO AA02 | 48 | 0000216479 | 8 | 8 | 0 | 0 | 10219526600002862 |  |  | 4.69 | 37.52 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 102195265001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0490 | 10219538 | STUDBOLT;1.250"X250MM,L7,CAD+XYLAN | 01.10 - HU 101...93499, 93530,43,45 TO AA02 | 49 | 0000216479 | 80 | 80 | 0 | 0 | 10219538600002862 |  |  | 19.11 | 1528.8 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 102195385001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0500 | 10219885 | STUDBOLT;1.125"X240MM,L7,CAD+XYLAN | 10.10 - Del 80018302/000010 for picking | 50 | 0000216479 | 12 | 0 | 12 | 0 | 10219885600002862 |  |  | 14.65 | 175.8 | 0 | 175.8 | 0 |  | 0 | -12 | 12 | -12 | 102198855001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0510 | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | X1 CRATE | 51 | 0000216479 | 24 | 24 | 0 | 24 | 10219976600002862 | 24 | 24 | 1 | 24 | 24 | 0 | 24 |  | 0 | 24 | 0 | 24 | 102199765001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0520 | 10220455 | STUDBOLT;0.875" X 180MM,A193 B8M CL2 | 22.09 - X1 BOX / MW3R15F09A @ KSF | 52 | 0000216479 | 8 | 8 | 0 | 8 | 10220455600002862 | 8 | 146.8 | 18.35 | 146.8 | 146.8 | 0 | 0 |  | 0 | 0 | 0 | 0 | 102204555001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0530 | 10222953 | SPADE BLIND,50MM,CL300,RF,A516-60/70 | 01.10 - HU 101000000093007 TO AA02 | 53 | 0000216479 | 6 | 6 | 0 | 0 | 10222953600002862 |  |  | 242.24 | 1453.44 | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 102229535001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0540 | 10223374 | STUDBOLT;0.750"X140MM,A193 B8M,CL2 | 22.09 - IN GREY TUB / MW2R03A02A @ KSF | 54 | 0000216479 | 20 | 20 | 0 | 20 | 10223374600002862 | 20 | 203 | 10.15 | 203 | 203 | 0 | 0 |  | 24 | 0 | 0 | 0 | 102233745001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0550 | 10229938 | SPADE BLIND,80MM,CL150,SS316 | 16.10 - 180082367 4500005381, 103 ERRORS | 55 | 0000216479 | 1 | 1 | 0 | 0 | 10229938600002862 |  |  | 367.23 | 367.23 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 102299385001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0560 | 10254870 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN50C> | In Transit voyage 20003452 | 56 | 0000216479 | 1 | 1 | 0 | 0 | 10254870600002862 |  |  | 283.48 | 283.48 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 102548705001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0570 | 10254871 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN80C> | In Transit voyage 20003452 | 57 | 0000216479 | 1 | 1 | 0 | 0 | 10254871600002862 |  |  | 367.23 | 367.23 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 102548715001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0580 | 10254875 | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN100> | In Transit voyage 20003452 | 58 | 0000216479 | 1 | 1 | 0 | 0 | 10254875600002862 |  |  | 373.68 | 373.68 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 102548755001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0590 | 10254974 | SPADE,BLIND;CAMCO 7666720DN50CL3008MM | In Transit voyage 20003452 | 59 | 0000216479 | 1 | 1 | 0 | 0 | 10254974600002862 |  |  | 521.85 | 521.85 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 102549745001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0600 | 10254979 | SPADE,BLIND,80MM,CL600,15MM,SS304 | In Transit voyage 20003452 | 60 | 0000216479 | 2 | 2 | 0 | 0 | 10254979600002862 |  |  | 543.76 | 1087.52 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 102549795001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0610 | 10306724 | GASKET;SWC,80MM,CL300/600,31>WSE10508041 | 22.09 - IN GREY TUB / 4 SOH @ AA02 | 61 | 0000216479 | 8 | 8 | 0 | 0 | 10306724600002862 |  |  | 16.98 | 135.84 | 0 | 0 | 8 |  | 0 | 8 | 0 | 8 | 103067245001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0620 | 10441378 | SPADE BLIND,100MM,CL600,CS | 16.10 - 180082367 4500005381, 103 ERRORS | 62 | 0000216479 | 1 | 1 | 0 | 0 | 10441378600002862 |  |  | 476.75 | 476.75 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 104413785001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0630 | 10487244 | SPADE,BLIND,80MM,CL300,LTCS | In Transit voyage 20003452 | 63 | 0000216479 | 2 | 2 | 0 | 0 | 10487244600002862 |  |  | 309.25 | 618.5 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 104872445001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0640 | 10487245 | SPADE,BLIND,100MM,CL300,LTCS | In Transit voyage 20003452 | 64 | 0000216479 | 1 | 1 | 0 | 0 | 10487245600002862 |  |  | 454.85 | 454.85 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 104872455001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0650 | 10488048 | FLANGE,BLIND,150MM,CL300,RF,SS | 01.10 - HU 101000000093024 TO AA02 | 65 | 0000216479 | 1 | 1 | 0 | 0 | 10488048600002862 |  |  | 372.39 | 372.39 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 104880485001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0660 | 10488940 | SPADE,BLIND,80MM,CL600,LTCS | In Transit voyage 20003452 | 66 | 0000216479 | 1 | 1 | 0 | 0 | 10488940600002862 |  |  | 360.79 | 360.79 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 104889405001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0670 | 10590596 | GASKET;RF,GR,300MM,CL150,KLINGER 154756 | 01.10 - HU 101000000093397 TO AA02 | 67 | 0000216479 | 6 | 6 | 0 | 0 | 10590596600002862 |  |  | 53.36 | 320.16 | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 105905965001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0680 | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 03.10 - GR ZONE @ AA02 | 68 | 0000216479 | 4 | 4 | 0 | 0 | 10202343600002862 |  |  | 35 | 140 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 102023435001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0690 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 06.03 - ETA 17.04.24 PO 4500004781 x 3 Australasian, ETA 16.02.24 PO W451781228 | 69 | 0000216479 | 4 | 4 | 0 | 0 | 10251654600002862 | 6 | 54 | 9 | 36 | 0 | 0 | 1 |  | 4 | 1 | 0 | 1 | 102516545001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0700 | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 14.10 - HU 101000000056226 TO AA02 | 70 | 0000216479 | 6 | 6 | 0 | 0 | 10202323600002862 |  |  | 27.25 | 163.5 | 0 | 0 | 12 |  | 12 | 12 | 0 | 12 | 102023235001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0710 | 10060939 | GASKET;SWCI,450MM,CL600,316L/GR/316 | 22.09 - X4 FLAT PACKS / 4 SOH @ KSF /180071538 75KG 18.09.24 PO 4500024711 | 71 | 0000216479 | 12 | 12 | 0 | 12 | 10060939600002862 | 12 | 903 | 75.25 | 903 | 903 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100609395001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0720 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 25.09 - At KGP | 72 | 0000216479 | 6 | 6 | 0 | 0 | 10060941600002862 |  |  | 92.14 | 552.84 | 0 | 0 | 0 |  | 9 | 0 | 0 | 0 | 100609415001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0730 | 10058828 | STUDBOLT;1.625" X 360MM,L7,BLK | 01.10 - HU 101000000094101 - 08 TO AA02 | 73 | 0000216479 | 24 | 24 | 22 | 6 | 10058828600002862 | 2 | 61 | 30.63 | 735.12 | 183.78 | 673.86 | 4 |  | 22 | -18 | 22 | -18 | 100588285001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0740 | 10492979 | STUDBOLT;1.875" X 470MM,L7,ZN+XYLAN | 01.10 - HU 101000000080184 TO AA02 | 74 | 0000216479 | 48 | 48 | 0 | 0 | 10492979600002862 |  |  | 163.35 | 7840.8 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 104929795001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0750 | 10052685 | SPADE BLIND,600MM,CL600,RF,LTCS | 01.10 - HU 101000000060720 TO AA02 | 75 | 0000216479 | 1 | 1 | 0 | 1 | 10052685600002862 | 1 | 5952.95 | 5952.95 | 5952.95 | 5952.95 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100526855001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0760 | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 24.10 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 76 | 0000216479 | 1 | 0 | 1 | 0 | 10202352600002862 | 1 | 2046.16 | 2046.16 | 2046.16 | 0 | 2046.16 | 0 |  | 0 | -1 | 1 | -1 | 102023525001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0770 | 10049310 | FLANGE,BLIND;80MM,CL600,RF,SS316 | 01.10 - HU 101000000093021 TO AA02 | 77 | 0000216479 | 1 | 1 | 0 | 0 | 10049310600002862 |  |  | 235.8 | 235.8 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100493105001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0780 | 10052696 | SPADE BLIND,150MM,CL150,CS,A285 GR.C | 01.10 - HU 101000000093390 TO AA02 | 78 | 0000216479 | 1 | 1 | 0 | 0 | 10052696600002862 |  |  | 693.5 | 693.5 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100526965001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0790 | 10229941 | SPADE BLIND,50MM,CL600,SS316 | 01.10 - HU 101000000092975 TO AA02 | 79 | 0000216479 | 1 | 1 | 0 | 0 | 10229941600002862 |  |  | 385 | 385 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 102299415001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0800 | 10229942 | SPADE BLIND,100MM,CL600,SS316 | 16.10 - 180082367 4500005381, 103 ERRORS | 80 | 0000216479 | 1 | 1 | 0 | 0 | 10229942600002862 |  |  | 747.34 | 747.34 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 102299425001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0810 | 10049295 | FLANGE,BLIND;300MM,CL300,RF,SS316 | 01.10 - HU 101000000076282 TO AA02 | 81 | 0000216479 | 1 | 1 | 0 | 1 | 10049295600002862 | 1 | 2574.46 | 2574.46 | 2574.46 | 2574.46 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100492955001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0840 | 10613639 | SPADE BLIND 150MM CL150 FF A516 GR70 | In Transit voyage 20003452 | 84 | 0000216479 | 1 | 1 | 0 | 0 | 10613639600002862 |  |  | 440.68 | 440.68 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 106136395001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0850 | 10258213 | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 01.10 - HU 101000000068823 TO AA02 | 85 | 0000216479 | 10 | 10 | 0 | 0 | 10258213600002862 |  |  | 836.94 | 8369.4 | 0 | 0 | 0 |  | 13 | 0 | 0 | 0 | 102582135001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0860 | 11400805 | SPADE,BLIND,200MM,CL600,LTCS | 01.10 - HU 101000000040351 TO AA02 | 86 | 0000216479 | 1 | 1 | 0 | 1 | 11400805600002862 | 1 | 961 | 961 | 961 | 961 | 0 | 0 |  | 0 | 0 | 0 | 0 | 114008055001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0870 | 11400808 | SPADE BLIND,350MM,CL150,SS316 | 01.10 - HU 101000000085146 TO AA02 | 87 | 0000216479 | 1 | 1 | 0 | 1 | 11400808600002862 | 1 | 2278 | 2278 | 2278 | 2278 | 0 | 0 |  | 0 | 0 | 0 | 0 | 114008085001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0880 | 70011010 | Restriction Orifice Plate 41RO20 | SPT Error TOP HU 102000000019832 - 2nd HU 101000000094259 | 96 | 0000216479 | 1 | 0 | 1 | 0 | 70011010600002862 |  |  | 560 | 560 | 0 | 560 | 0 |  | 1 | -1 | 2 | -2 | 700110105001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0890 | 70011014 | Restriction Orifice Plate 41RO21 | SPT Error TOP HU 102000000019832 - 2nd HU 101000000094290 | 98 | 0000216479 | 1 | 0 | 1 | 0 | 70011014600002862 |  |  | 560 | 560 | 0 | 560 | 0 |  | 1 | -1 | 1 | -1 | 700110145001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0900 | 10060906 | GASKET;SWCI,350MM,CL300,316L/GR/316 | UserCommentLink | 130 | 0000216479 | 4 | 4 | 0 | 4 | 10060906600002862 | 4 | 161.04 | 40.26 | 161.04 | 161.04 | 0 | 4 |  | 4 | 4 | 0 | 4 | 100609065001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0900 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | UserCommentLink | 99 | 0000216479 | 0 | 0 | 0 | 0 | 10251654600002862 | 6 | 54 | 9 | 0 | 0 | 0 | 1 |  | 4 | 1 | 0 | 1 | 102516545001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | 0910 | 10219976 | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | MRF 241026-6712278 processed to 5001 HU 1020-22091 P-99 | 133 | 0000216479 | 24 | 24 | 0 | 0 | 10219976600002862 | 24 | 24 | 1 | 24 | 0 | 0 | 24 |  | 0 | 24 | 0 | 24 | 102199765001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | (blank) | 10053011 | SPADE BLIND,150MM,CL300,SS316 | 01.10 - HU 101000000094436 TO AA02 | 89 | 0000216479 | 1 | 1 | 0 | 1 | 10053011600002862 | 1 | 541.03 | 541.03 | 541.03 | 541.03 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100530115001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | (blank) | 10053014 | SPADE BLIND,300MM,CL300,SS316 | 01.10 - HU 101000000094436 TO AA02 | 88 | 0000216479 | 1 | 1 | 0 | 1 | 10053014600002862 | 1 | 2367.78 | 2367.78 | 2367.78 | 2367.78 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100530145001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0010 | (blank) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 22.09 - IN GRAY TUB / MW2R03B03E @ KSF | 90 | 0000216479 | 4 | 4 | 0 | 0 | 10305744600002862 |  |  | 9.27 | 37.08 | 0 | 0 | 29 |  | 8 | 29 | 0 | 29 | 103057445001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | X | 10062985 | AIR,MEDICAL,DRY,COMPRESSED,SIZE G CYL | 14.10 - ETA 18.10.24 PO 4500031439 BOC | 128 | 0000216479 | 2 | 2 | 0 | 0 | 10062985600002862 |  |  | 45.52 | 91.04 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 100629855001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | X | 10312854 | AIR;MEDICAL DRY,25PPM,BOC 470MAN15 | 24.10 - ETA 24.10.24 PO 4500031439 BOC | 129 | 0000216479 | 1 | 1 | 0 | 0 | 10312854600002862 |  |  | 682.71 | 682.71 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 103128545001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0010 | 10488134 | SPADE,BLIND,250MM,CL300,SS | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALIAN FITTINGS | 100 | 0000216479 | 1 | 0 | 1 | 0 | 10488134600002862 |  |  | 1 | 1 | 0 | 1 | 0 |  | 0 | -1 | 1 | -1 | 104881345001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0020 | 10441379 | SPADE BLIND,150MM,CL600,CS | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 101 | 0000216479 | 1 | 0 | 1 | 0 | 10441379600002862 |  |  | 515.44 | 515.44 | 0 | 515.44 | 0 |  | 0 | -1 | 1 | -1 | 104413795001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0030 | 10340106 | SPADE BLIND,50MM,CL150,CS,A285,GDE C | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 102 | 0000216479 | 1 | 0 | 1 | 0 | 10340106600002862 |  |  | 542 | 542 | 0 | 542 | 0 |  | 0 | -1 | 1 | -1 | 103401065001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0040 | 10255008 | SPADE,BLIND,1050MM,CL150,55MM,SS304 | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALIAN FITTINGS | 103 | 0000216479 | 1 | 0 | 1 | 0 | 10255008600002862 |  |  | 4890.07 | 4890.07 | 0 | 4890.07 | 0 |  | 0 | -1 | 1 | -1 | 102550085001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0050 | 10052675 | SPADE BLIND,350MM,CL300,RF,A516-60 | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 104 | 0000216479 | 1 | 0 | 1 | 0 | 10052675600002862 |  |  | 1500 | 1500 | 0 | 1500 | 0 |  | 0 | -1 | 1 | -1 | 100526755001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0060 | 10340086 | FLANGE,BLIND;350MM,CL300,RF,CS,A105N | 05.10 - HU 101000000096902 to AA02 | 105 | 0000216479 | 1 | 1 | 0 | 0 | 10340086600002862 |  |  | 1459 | 1459 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 103400865001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0070 | 10613642 | SPADE BLIND 200MM CL150 FF A516 GR70 | 21.09 - NEED PURCHSING | 106 | 0000216479 | 1 | 0 | 1 | 0 | 10613642600002862 |  |  | 510 | 510 | 0 | 510 | 0 |  | 0 | -1 | 1 | -1 | 106136425001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0080 | 10291772 | FLANGE,BLIND;200MM,CL150,RF,CS,A105M | 05.10 - HU 101000000096902 to AA02 | 107 | 0000216479 | 1 | 1 | 0 | 0 | 10291772600002862 |  |  | 123.08 | 123.08 | 0 | 0 | 0 |  | 12 | 0 | 0 | 0 | 102917725001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0090 | 10202352 | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 21.09 - ETA 24.11.24 PO 4500027121 AUSTRALASIAN FITTINGS AND FLANGES | 108 | 0000216479 | 1 | 1 | 0 | 1 | 10202352600002862 | 1 | 2046.16 | 2046.16 | 2046.16 | 2046.16 | 0 | 0 |  | 0 | 0 | 1 | -1 | 102023525001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0100 | 10048469 | FLANGE,BLIND;450MM,CL150,RF,CS,A105N | 14.10 - HU 101000000099504 TO AA02 | 109 | 0000216479 | 1 | 1 | 0 | 0 | 10048469600002862 |  |  | 1445 | 1445 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100484695001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0110 | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | 02.10 - ETA 17.12.24 PO 4500029495 AUS FITTINGS @AA02 | 110 | 0000216479 | 1 | 0 | 1 | 0 | 10052670600002862 |  |  | 1 | 1 | 0 | 1 | 0 |  | 0 | -1 | 1 | -1 | 100526705001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0120 | 10202334 | FLANGE,BLIND;350MM,CL150,RF,CS,A105N | 05.10 - HU 101000000096902 to AA02 | 111 | 0000216479 | 1 | 1 | 0 | 0 | 10202334600002862 |  |  | 980 | 980 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 102023345001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0130 | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | UserCommentLink | 112 | 0000216479 | 10 | 0 | 10 | 0 | 11404909600002862 |  |  | 845 | 8450 | 0 | 8450 | 0 |  | 10 | -10 | 20 | -20 | 114049095001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0140 | 11404775 | CONTRACTOR;100-250V,ABB 1SFL547002R3322 | UserCommentLink | 113 | 0000216479 | 6 | 0 | 6 | 0 | 11404775600002862 |  |  | 4152 | 24912 | 0 | 24912 | 0 |  | 0 | -6 | 6 | -6 | 114047755001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0150 | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | UserCommentLink | 114 | 0000216479 | 6 | 0 | 6 | 0 | 11404926600002862 |  |  | 1285 | 7710 | 0 | 7710 | 0 |  | 6 | -6 | 12 | -12 | 114049265001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0160 | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | UserCommentLink | 115 | 0000216479 | 10 | 0 | 10 | 0 | 11404929600002862 |  |  | 665 | 6650 | 0 | 6650 | 0 |  | 10 | -10 | 20 | -20 | 114049295001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0170 | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | UserCommentLink | 116 | 0000216479 | 6 | 0 | 6 | 0 | 11404925600002862 |  |  | 895 | 5370 | 0 | 5370 | 0 |  | 6 | -6 | 12 | -12 | 114049255001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0180 | 10202343 | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 05.10 - Del 80019284 for picking | 117 | 0000216479 | 4 | 4 | 0 | 0 | 10202343600002862 |  |  | 35 | 140 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 102023435001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0190 | 10052676 | SPADE BLIND,400MM,CL300,RF,A516-60 | 03.10 - HU 101000000094431 to AA02 | 118 | 0000216479 | 4 | 4 | 0 | 4 | 10052676600002862 | 4 | 10297.84 | 2574.46 | 10297.84 | 10297.84 | 0 | 0 |  | 0 | 0 | 4 | -4 | 100526765001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0200 | 10048489 | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 10.10 - Del 80018247/000070 for picking | 119 | 0000216479 | 4 | 3 | 1 | 0 | 10048489600002862 |  |  | 46 | 184 | 0 | 46 | 0 |  | 3 | -1 | 1 | -1 | 100484895001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0210 | 10202323 | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 14.10 - HU 101000000099762 TO AA02 | 120 | 0000216479 | 6 | 6 | 0 | 0 | 10202323600002862 |  |  | 27.25 | 163.5 | 0 | 0 | 12 |  | 12 | 12 | 0 | 12 | 102023235001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0220 | 10043687 | TEE:EQUAL,50mm,BW,CS,A234-WPB,SCH 40 | 05.10 - HU 101000000096674 to AA02 | 121 | 0000216479 | 4 | 4 | 0 | 0 | 10043687600002862 |  |  | 22 | 88 | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 100436875001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0230 | 10251654 | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 03.10 - HU 101000000093112 to AA02 | 122 | 0000216479 | 6 | 6 | 0 | 18 | 10251654600002862 | 6 | 54 | 9 | 54 | 162 | 0 | 1 |  | 4 | 1 | 0 | 1 | 102516545001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0240 | 11404909 | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | At KGP 19/10/24 | 123 | 0000216479 | 10 | 0 | 10 | 0 | 11404909600002862 |  |  | 845 | 8450 | 0 | 8450 | 0 |  | 10 | -10 | 20 | -20 | 114049095001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0250 | 11404926 | FLANGE,FTG;3",CL150,LOKRING 9061370 | At KGP 19/10/24 | 125 | 0000216479 | 6 | 0 | 6 | 0 | 11404926600002862 |  |  | 1285 | 7710 | 0 | 7710 | 0 |  | 6 | -6 | 12 | -12 | 114049265001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0260 | 11404929 | FLANGE,FTG;1",CL150,LOKRING 9060429 | At KGP 19/10/24 | 126 | 0000216479 | 10 | 0 | 10 | 0 | 11404929600002862 |  |  | 665 | 6650 | 0 | 6650 | 0 |  | 10 | -10 | 20 | -20 | 114049295001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0270 | 11404925 | FLANGE,FTG;2",CL150,LOKRING 9060441 | At KGP 19/10/24 | 127 | 0000216479 | 6 | 0 | 6 | 0 | 11404925600002862 |  |  | 895 | 5370 | 0 | 5370 | 0 |  | 6 | -6 | 12 | -12 | 114049255001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0280 | 70013860 | SPADE BLIND 200MM CL150 FF A516 GR70 | ISSUE WITH MOZZIE NUMBER | 132 | 0000216479 | 1 | 0 | 1 | 0 | 70013860600002862 |  |  | 510 | 510 | 0 | 510 | 0 |  | 0 | -1 | 1 | -1 | 700138605001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0290 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | UserCommentLink | 134 | 0000216479 | 6 | 0 | 6 | 0 | 10060932600002862 |  |  | 14.54 | 87.24 | 0 | 87.24 | 11 |  | 72 | 5 | 6 | 5 | 100609325001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0300 | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | UserCommentLink | 136 | 0000216479 | 2 | 2 | 0 | 2 | 10048592600002862 | 2 | 139.75 | 73.91 | 147.82 | 147.82 | 0 | 0 |  | 2 | 0 | 0 | 0 | 100485925001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0310 | 10052670 | SPADE BLIND,350MM,CL150,RF,A516-60 | UserCommentLink | 137 | 0000216479 | 1 | 1 | 0 | 0 | 10052670600002862 |  |  | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 1 | -1 | 100526705001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0320 | 10048592 | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | UserCommentLink | 138 | 0000216479 | 2 | 2 | 0 | 0 | 10048592600002862 | 2 | 139.75 | 73.91 | 147.82 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 100485925001 | 5001
(blank) | 24SDLN2C | 600002862 | LNG2 COP 2024 – Execution | 0081 | 0330 | 10202329 | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | UserCommentLink | 139 | 0000216479 | 10 | 10 | 0 | 0 | 10202329600002862 |  |  | 49.59 | 495.9 | 0 | 0 | 1 |  | 10 | 1 | 0 | 1 | 102023295001 | 5001

## SOH 2001
Material | Storage location | Currency | Sum of Transit and Transfer | Sum of Unrestricted
10043687 | 2001 | AUD | 0 | 4
10048469 | 2001 | AUD | 0 | 1
10048489 | 2001 | AUD | 0 | 3
10048528 | 2001 | AUD | 0 | 1
10048552 | 2001 | AUD | 0 | 1
10048592 | 2001 | AUD | 0 | 2
10048593 | 2001 | AUD | 0 | 1
10049289 | 2001 | AUD | 0 | 1
10049310 | 2001 | AUD | 0 | 1
10052696 | 2001 | AUD | 0 | 1
10053093 | 2001 | AUD | 0 | 1
10058203 | 2001 | AUD | 0 | 8
10058222 | 2001 | AUD | 0 | 3
10058249 | 2001 | AUD | 0 | 8
10058252 | 2001 | AUD | 0 | 8
10058828 | 2001 | AUD | 0 | 22
10060885 | 2001 | AUD | 0 | 21
10060886 | 2001 | AUD | 0 | 45
10060887 | 2001 | AUD | 0 | 81
10060888 | 2001 | AUD | 0 | 7
10060892 | 2001 | AUD | 0 | 4
10060901 | 2001 | AUD | 0 | 15
10060902 | 2001 | AUD | 0 | 1
10060905 | 2001 | AUD | 0 | 4
10060906 | 2001 | AUD | 0 | 4
10060919 | 2001 | AUD | 0 | 317
10060920 | 2001 | AUD | 0 | 4
10060932 | 2001 | AUD | 0 | 72
10060941 | 2001 | AUD | 0 | 9
10062985 | 2001 | AUD | 0 | 2
10202323 | 2001 | AUD | 0 | 12
10202329 | 2001 | AUD | 0 | 10
10202334 | 2001 | AUD | 0 | 1
10202343 | 2001 | AUD | 0 | 8
10218613 | 2001 | AUD | 0 | 17
10218617 | 2001 | AUD | 0 | 40
10218626 | 2001 | AUD | 0 | 20
10218627 | 2001 | AUD | 0 | 32
10218632 | 2001 | AUD | 0 | 48
10218636 | 2001 | AUD | 0 | 12
10218652 | 2001 | AUD | 0 | 16
10219526 | 2001 | AUD | 0 | 8
10219538 | 2001 | AUD | 0 | 80
10222953 | 2001 | AUD | 0 | 6
10223374 | 2001 | AUD | 0 | 24
10229938 | 2001 | AUD | 0 | 1
10229941 | 2001 | AUD | 0 | 1
10229942 | 2001 | AUD | 0 | 1
10251654 | 2001 | AUD | 0 | 4
10254870 | 2001 | AUD | 0 | 1
10254871 | 2001 | AUD | 0 | 1
10254875 | 2001 | AUD | 0 | 1
10254974 | 2001 | AUD | 0 | 1
10254979 | 2001 | AUD | 0 | 2
10258213 | 2001 | AUD | 0 | 13
10291772 | 2001 | AUD | 0 | 12
10305744 | 2001 | AUD | 0 | 8
10312854 | 2001 | AUD | 0 | 1
10340086 | 2001 | AUD | 0 | 1
10441378 | 2001 | AUD | 0 | 1
10487244 | 2001 | AUD | 0 | 2
10487245 | 2001 | AUD | 0 | 1
10488048 | 2001 | AUD | 0 | 1
10488940 | 2001 | AUD | 0 | 1
10492979 | 2001 | AUD | 0 | 48
10590596 | 2001 | AUD | 0 | 6
10613639 | 2001 | AUD | 0 | 1
11404909 | 2001 | AUD | 0 | 10
11404925 | 2001 | AUD | 0 | 6
11404926 | 2001 | AUD | 0 | 6
11404929 | 2001 | AUD | 0 | 10
70011010 | 2001 | AUD | 0 | 1
70011014 | 2001 | AUD | 0 | 1

## SOH 5001
Material | Storage location | Currency | Sum of Transit and Transfer | Sum of Unrestricted
10058201 | 5001 | AUD | 0 | 120
10058828 | 5001 | AUD | 0 | 4
10059971 | 5001 | AUD | 0 | 2
10060885 | 5001 | AUD | 0 | 81
10060886 | 5001 | AUD | 0 | 15
10060887 | 5001 | AUD | 0 | 5
10060888 | 5001 | AUD | 0 | 5
10060892 | 5001 | AUD | 0 | 3
10060894 | 5001 | AUD | 0 | 3
10060901 | 5001 | AUD | 0 | 23
10060902 | 5001 | AUD | 0 | 1
10060904 | 5001 | AUD | 0 | 13
10060905 | 5001 | AUD | 0 | 6
10060906 | 5001 | AUD | 0 | 4
10060907 | 5001 | AUD | 0 | 12
10060919 | 5001 | AUD | 0 | 217
10060920 | 5001 | AUD | 0 | 4
10060932 | 5001 | AUD | 0 | 11
10202323 | 5001 | AUD | 0 | 12
10202329 | 5001 | AUD | 0 | 1
10218613 | 5001 | AUD | 0 | 4
10218625 | 5001 | AUD | 0 | 8
10218627 | 5001 | AUD | 0 | 64
10218628 | 5001 | AUD | 0 | 32
10219976 | 5001 | AUD | 0 | 24
10251654 | 5001 | AUD | 0 | 1
10305744 | 5001 | AUD | 0 | 29
10306724 | 5001 | AUD | 0 | 8

## mm60
Material | Plant | Valuation Type | Material Description | Last Change | Material type | Material Group | Base Unit of Measure | Purchasing Group | ABC Indicator | MRP Type | Valuation Class | Price control | Price | Currency | Price unit | Created By
10043687 | AA53 |  | TEE:EQUAL,50mm,BW,CS,A234-WPB,SCH 40 | 2024-11-21 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 22 | AUD | 1 | W74432
10048469 | AA53 |  | FLANGE,BLIND;450MM,CL150,RF,CS,A105N | 2024-10-11 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 1445 | AUD | 1 | W52667
10048489 | AA53 |  | FLANGE,BLIND;50MM,CL300,RF,CS,A105N | 2024-07-02 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 46 | AUD | 1 | W74432
10048528 | AA53 |  | FLANGE,BLIND;150MM,CL300,RF,LTCS | 2024-06-11 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 198 | AUD | 1 | W74432
10048552 | AA53 |  | FLANGE,BLIND;600MM,CL600,RF,LTCS | 2024-07-04 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 6356.26 | AUD | 1 | W74432
10048592 | AA53 |  | FLANGE,BLIND,100MM,CL150,RF,CS,GALV | 2024-05-10 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 73.91 | AUD | 1 | W74432
10048593 | AA53 |  | FLANGE,BLIND,150MM,CL150,RF,CS,SH40,GALV | 2024-05-10 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 238.38 | AUD | 1 | W74432
10048594 | AA53 |  | FLANGE,BLIND;200MM,CL150,RF,CS,SH30,GALV | 2024-06-12 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 280.9 | AUD | 1 | W74432
10048596 | AA53 |  | FLANGE,BLIND;300MM,CL150,RF,CS,SH30,GALV | 2024-06-12 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 550.2 | AUD | 1 | W74432
10049289 | AA53 |  | FLANGE,BLIND;50MM,CL300,RF,SS316 | 2024-07-03 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 82.46 | AUD | 1 | W74432
10049295 | AA53 |  | FLANGE,BLIND;300MM,CL300,RF,SS316 | 2024-07-04 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 2574.46 | AUD | 1 | W74432
10049310 | AA53 |  | FLANGE,BLIND;80MM,CL600,RF,SS316 | 2024-07-03 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 235.8 | AUD | 1 | W74432
10052670 | AA53 |  | SPADE BLIND,350MM,CL150,RF,A516-60 | 2024-11-19 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 1 | AUD | 1 | W52667
10052675 | AA53 |  | SPADE BLIND,350MM,CL300,RF,A516-60 | 2024-06-07 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 1500 | AUD | 1 | W74432
10052676 | AA53 |  | SPADE BLIND,400MM,CL300,RF,A516-60 | 2024-07-04 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 2574.46 | AUD | 1 | W74432
10052685 | AA53 |  | SPADE BLIND,600MM,CL600,RF,LTCS | 2024-06-20 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 5952.95 | AUD | 1 | W74432
10052696 | AA53 |  | SPADE BLIND,150MM,CL150,CS,A285 GR.C | 2024-05-09 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 693.5 | AUD | 1 | W74432
10053011 | AA53 |  | SPADE BLIND,150MM,CL300,SS316 | 2024-09-03 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 541.03 | AUD | 1 | W74432
10053014 | AA53 |  | SPADE BLIND,300MM,CL300,SS316 | 2024-09-03 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 2367.78 | AUD | 1 | W74432
10053093 | AA53 |  | SPADE BLIND,150MM,CL300,SS,TP316L | 2024-07-05 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 819.5 | AUD | 1 | W74432
10058201 | AA53 |  | STUDBOLT;0.625" X 100MM,A193 B8M CL2 | 2024-06-11 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 5.95 | AUD | 1 | W74432
10058202 | AA53 |  | STUDBOLT;0.625" X 110MM,A193 B8M CL2 | 2024-06-11 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 1.75 | AUD | 1 | W74432
10058203 | AA53 |  | STUDBOLT;0.625" X 120MM,A193 B8M CL2 | 2024-06-11 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 5.7 | AUD | 1 | W74432
10058205 | AA53 |  | STUDBOLT;0.625" X 130MM,A193 B8M CL2 | 2024-06-11 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 5.92 | AUD | 1 | W74432
10058222 | AA53 |  | STUDBOLT;0.750" X 160MM,A193 B8M CL2 | 2024-06-11 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 12.48 | AUD | 1 | W74432
10058249 | AA53 |  | STUDBOLT;1.000"X170MM,B8M CL2 | 2024-06-11 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 19.36 | AUD | 1 | W74432
10058252 | AA53 |  | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 2024-06-11 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 22.39 | AUD | 1 | W74432
10058262 | AA53 |  | BLT STUD:1.125in,190mm,316 SS,2,UN HEAVY | 2024-11-22 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 27.58 | AUD | 1 | W74432
10058828 | AA53 |  | STUDBOLT;1.625" X 360MM,L7,BLK | 2024-06-11 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 30.63 | AUD | 1 | W74432
10059968 | AA53 |  | GASKET;CNAF,50MM,CL150,TANG INTN,1.6MM | 2024-07-19 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 3.92 | AUD | 1 | W74432
10059971 | AA53 |  | GASKET;CNAF,150MM,CL150,TANG INTN,1.6MM | 2024-10-03 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 14.25 | AUD | 1 | W74432
10059972 | AA53 |  | GASKET;CNAF,200MM,CL150,TANG INTN,1.5MM | 2024-07-19 | ZIBE | 31400000 | EA | 106 | C | ND | M121 | V | 32.64 | AUD | 1 | W74432
10060885 | AA53 |  | GASKET;SWCI,50MM,CL150,316L/GR/316 | 2024-11-18 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 4.78 | AUD | 1 | W74432
10060886 | AA53 |  | GASKET;SWCI,80MM,CL150,316L/GR/316 | 2024-06-14 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 6.82 | AUD | 1 | W74432
10060887 | AA53 |  | GASKET;SWCI,100MM,CL150,316L/GR/316 | 2024-06-18 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 10.29 | AUD | 1 | W74432
10060888 | AA53 |  | GASKET;SWCI,150MM,CL150,316L/GR/316 | 2024-07-09 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 10.45 | AUD | 1 | W74432
10060892 | AA53 |  | GASKET;SWCI,350MM,CL150,316L/GR/316 | 2024-09-03 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 31.4 | AUD | 1 | W74432
10060894 | AA53 |  | GASKET;SWCI,450MM,CL150,316L/GR/316 | 2024-07-19 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 64.65 | AUD | 1 | W74432
10060901 | AA53 |  | GASKET;SWCI,100MM,CL300,SS316L/GR/316 | 2024-11-18 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 11.72 | AUD | 1 | W74432
10060902 | AA53 |  | GASKET;SWCI,150MM,CL300,316L/GR/316 | 2024-06-11 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 16.7 | AUD | 1 | W74432
10060904 | AA53 |  | GASKET;SWCI,250MM,CL300,316L/GR/316 | 2024-07-19 | ZIBE | 31400000 | EA | 106 | C | ND | M121 | V | 25.01 | AUD | 1 | W74432
10060905 | AA53 |  | GASKET;SWCI,300MM,CL300,316L/GR/316 | 2024-07-19 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 31.67 | AUD | 1 | W74432
10060906 | AA53 |  | GASKET;SWCI,350MM,CL300,316L/GR/316 | 2024-07-19 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 40.26 | AUD | 1 | W74432
10060907 | AA53 |  | GASKET;SWCI,400MM,CL300,SS316L/GR/316 | 2024-07-19 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 45.74 | AUD | 1 | W74432
10060919 | AA53 |  | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 2024-08-30 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 5.5 | AUD | 1 | W74432
10060920 | AA53 |  | GASKET:RF,80mm,4.5mm,316L,CL300,SWCI,GR | 2024-11-21 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 13.4 | AUD | 1 | W74432
10060932 | AA53 |  | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2024-07-19 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 14.54 | AUD | 1 | W74432
10060934 | AA53 |  | GASKET;SWCI,200MM,CL600,316L/GR/316 | 2024-07-19 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 24.17 | AUD | 1 | W74432
10060939 | AA53 |  | GASKET;SWCI,450MM,CL600,316L/GR/316 | 2024-10-17 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 75.25 | AUD | 1 | W74432
10060941 | AA53 |  | GASKET;SWCI,600MM,CL600,316L/GR/316 | 2024-08-29 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 92.14 | AUD | 1 | W74432
10061003 | AA53 |  | GASKET;SWCI,1050MM,CL150,316L/GR/316 | 2024-07-19 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 281.13 | AUD | 1 | W74432
10062985 | AA53 |  | AIR,MEDICAL,DRY,COMPRESSED,SIZE G CYL | 2024-09-10 | ZIBE | 42190000 | CYL | 106 | B | ND | M109 | V | 45.52 | AUD | 1 | W74432
10202323 | AA53 |  | PIPE:SML,50mm,CS,A106 GR B,SCH40 | 2024-11-14 | ZIBE | 40170000 | M | 106 | B | ND | M121 | V | 27.25 | AUD | 1 | W74432
10202329 | AA53 |  | FLANGE,BLIND;100MM,CL150,RF,CS,A105N | 2024-06-11 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 49.59 | AUD | 1 | W74432
10202334 | AA53 |  | FLANGE,BLIND;350MM,CL150,RF,CS,A105N | 2024-06-11 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 980 | AUD | 1 | W74432
10202343 | AA53 |  | FLANGE,WN;50MM,CL300,RF,A105N,SCH 40 | 2024-10-08 | ZIBE | 40170000 | EA | 106 | A | ND | M121 | V | 35 | AUD | 1 | W74432
10202352 | AA53 |  | SPADE BLIND,450MM,CL150,CS,A285 GR.C | 2024-06-11 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 2046.16 | AUD | 1 | W74432
10218613 | AA53 |  | STUDBOLT;0.625" X 110MM,L7,ZN+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 3.1 | AUD | 1 | W74432
10218617 | AA53 |  | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 1.98 | AUD | 1 | W74432
10218625 | AA53 |  | STUDBOLT;0.750"X110MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 6.88 | AUD | 1 | W74432
10218626 | AA53 |  | STUDBOLT;0.750"X120MM,L7,CAD+XYLAN | 2024-07-08 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 5.18 | AUD | 1 | W74432
10218627 | AA53 |  | STUDBOLT;0.750"X130MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 7.62 | AUD | 1 | W74432
10218628 | AA53 |  | STUDBOLT;0.750"X140MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 7.97 | AUD | 1 | W74432
10218632 | AA53 |  | STUDBOLT;0.875"X130MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 6.89 | AUD | 1 | W74432
10218636 | AA53 |  | STUDBOLT;0.875"X180MM,L7,CAD+XYLAN | 2024-07-02 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 7.5 | AUD | 1 | W74432
10218652 | AA53 |  | STUDBOLT;1.125"X190MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 12.59 | AUD | 1 | W74432
10218657 | AA53 |  | STUDBOLT;1.125"X230MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 24.17 | AUD | 1 | W74432
10219526 | AA53 |  | STUDBOLT;0.750"X160MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 4.69 | AUD | 1 | W74432
10219538 | AA53 |  | STUDBOLT;1.250"X250MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 19.11 | AUD | 1 | W74432
10219885 | AA53 |  | STUDBOLT;1.125"X240MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 14.65 | AUD | 1 | W74432
10219976 | AA53 |  | STUDBOLT;1.875"X390MM,L7,CAD+XYLAN | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 1 | AUD | 1 | W74432
10220455 | AA53 |  | STUDBOLT;0.875" X 180MM,A193 B8M CL2 | 2024-06-11 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 18.35 | AUD | 1 | W74432
10222953 | AA53 |  | SPADE BLIND,50MM,CL300,RF,A516-60/70 | 2024-07-04 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 242.24 | AUD | 1 | W74432
10223374 | AA53 |  | STUDBOLT;0.750"X140MM,A193 B8M,CL2 | 2024-07-02 | ZIBE | 31160000 | EA | 106 | B | ND | M108 | V | 10.15 | AUD | 1 | W74432
10229938 | AA53 |  | SPADE BLIND,80MM,CL150,SS316 | 2024-07-05 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 367.23 | AUD | 1 | W74432
10229941 | AA53 |  | SPADE BLIND,50MM,CL600,SS316 | 2024-07-02 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 385 | AUD | 1 | W74432
10229942 | AA53 |  | SPADE BLIND,100MM,CL600,SS316 | 2024-07-05 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 747.34 | AUD | 1 | W74432
10251654 | AA53 |  | ELBOW:LONG RADIUS,50mm,BW,90deg,CS,40,A2 | 2024-11-21 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 9 | AUD | 1 | W74432
10254870 | AA53 |  | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN50C> | 2024-07-05 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 283.48 | AUD | 1 | W74432
10254871 | AA53 |  | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN80C> | 2024-07-05 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 367.23 | AUD | 1 | W74432
10254875 | AA53 |  | SPADE,BLIND,LOW TEMP;CAMCO 7664970DN100> | 2024-07-05 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 373.68 | AUD | 1 | W74432
10254974 | AA53 |  | SPADE,BLIND;CAMCO 7666720DN50CL3008MM | 2024-07-05 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 521.85 | AUD | 1 | W74432
10254979 | AA53 |  | SPADE,BLIND,80MM,CL600,15MM,SS304 | 2024-07-05 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 543.76 | AUD | 1 | W74432
10255008 | AA53 |  | SPADE,BLIND,1050MM,CL150,55MM,SS304 | 2024-10-08 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 4890.07 | AUD | 1 | W52667
10258213 | AA53 |  | SHEET,SS316,0.90MM X 1220 X 2440,PRF | 2024-07-26 | ZIBE | 30260000 | SHT | 106 | C | ND | M124 | V | 836.94 | AUD | 1 | W74432
10291772 | AA53 |  | FLANGE,BLIND;200MM,CL150,RF,CS,A105M | 2024-10-04 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 123.08 | AUD | 1 | W74432
10305744 | AA53 |  | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-06-11 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 9.27 | AUD | 1 | W74432
10306724 | AA53 |  | GASKET;SWC,80MM,CL300/600,31>WSE10508041 | 2024-06-11 | ZIBE | 31400000 | EA | 106 | B | ND | M121 | V | 16.98 | AUD | 1 | W74432
10312854 | AA53 |  | AIR;MEDICAL DRY,25PPM,BOC 470MAN15 | 2024-09-10 | ZIBE | 42190000 | PAC | 106 | B | ND | M109 | V | 682.71 | AUD | 1 | W74432
10340086 | AA53 |  | FLANGE,BLIND;350MM,CL300,RF,CS,A105N | 2024-10-04 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 1459 | AUD | 1 | W74432
10340106 | AA53 |  | SPADE BLIND,50MM,CL150,CS,A285,GDE C | 2024-06-07 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 542 | AUD | 1 | W74432
10441378 | AA53 |  | SPADE BLIND,100MM,CL600,CS | 2024-07-05 | ZIBE | 40170000 | EA | 106 | B | ND | M121 | V | 476.75 | AUD | 1 | W74432
10441379 | AA53 |  | SPADE BLIND,150MM,CL600,CS | 2024-05-10 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 515.44 | AUD | 1 | W74432
10487244 | AA53 |  | SPADE,BLIND,80MM,CL300,LTCS | 2024-07-05 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 309.25 | AUD | 1 | W74432
10487245 | AA53 |  | SPADE,BLIND,100MM,CL300,LTCS | 2024-07-05 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 454.85 | AUD | 1 | W74432
10488048 | AA53 |  | FLANGE,BLIND,150MM,CL300,RF,SS | 2024-07-03 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 372.39 | AUD | 1 | W74432
10488134 | AA53 |  | SPADE,BLIND,250MM,CL300,SS | 2024-08-30 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 1 | AUD | 1 | W52667
10488940 | AA53 |  | SPADE,BLIND,80MM,CL600,LTCS | 2024-07-05 | ZIBE | 40170000 | EA | 106 | C | ND | M121 | V | 360.79 | AUD | 1 | W74432
10492979 | AA53 |  | STUDBOLT;1.875" X 470MM,L7,ZN+XYLAN | 2024-08-20 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 163.35 | AUD | 1 | W74432
10590596 | AA53 |  | GASKET;RF,GR,300MM,CL150,KLINGER 154756 | 2024-01-19 | ZIBE | 31400000 | EA | 106 |  | ND | M121 | V | 53.36 | AUD | 1 | W74432
10592509 | AA53 |  | BLADE,SAW;RECIP,CB,8TPI,1",230MM | 2024-06-07 | ZIBE | 27110000 | EA | 106 |  | ND | M128 | V | 32.63 | AUD | 1 | W74432
10613639 | AA53 |  | SPADE BLIND 150MM CL150 FF A516 GR70 | 2024-08-21 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 440.68 | AUD | 1 | W74432
10613642 | AA53 |  | SPADE BLIND 200MM CL150 FF A516 GR70 | 2024-08-21 | ZIBE | 31160000 | EA | 106 |  | ND | M108 | V | 510 | AUD | 1 | W74432
11400805 | AA53 |  | SPADE,BLIND,200MM,CL600,LTCS | 2024-07-19 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 961 | AUD | 1 | W75230
11400808 | AA53 |  | SPADE BLIND,350MM,CL150,SS316 | 2024-07-19 | ZIBE | 40170000 | EA | 106 |  | ND | M121 | V | 2278 | AUD | 1 | W75230
11404775 | AA53 |  | CONTRACTOR;100-250V,ABB 1SFL547002R3322 | 2024-08-29 | ZIBE | 39120000 | EA | 106 |  | ND | M123 | V | 4152 | AUD | 1 | W79436
11404909 | AA53 |  | FLANGE,FTG;1.5",CL150,LOKRING 9060435 | 2024-10-07 | ZIBE | 40140000 | EA | 106 |  | ND | M122 | V | 845 | AUD | 1 | W53748
11404925 | AA53 |  | FLANGE,FTG;2",CL150,LOKRING 9060441 | 2024-10-07 | ZIBE | 40140000 | EA | 106 |  | ND | M122 | V | 895 | AUD | 1 | W53748
11404926 | AA53 |  | FLANGE,FTG;3",CL150,LOKRING 9061370 | 2024-10-07 | ZIBE | 40140000 | EA | 106 |  | ND | M122 | V | 1285 | AUD | 1 | W53748
11404929 | AA53 |  | FLANGE,FTG;1",CL150,LOKRING 9060429 | 2024-10-07 | ZIBE | 40140000 | EA | 106 |  | ND | M122 | V | 665 | AUD | 1 | W53748
70011010 | AA53 |  | Restriction Orifice Plate 41RO20 | 2024-08-12 | ZFRE | 40170000 | EA | 106 |  | ND | M108 | V | 560 | AUD | 1 | SAP_WFRT
70011014 | AA53 |  | Restriction Orifice Plate 41RO21 | 2024-08-12 | ZFRE | 40170000 | EA | 106 |  | ND | M108 | V | 560 | AUD | 1 | SAP_WFRT
70013860 | AA53 |  | SPADE BLIND 200MM CL150 FF A516 GR70 | 2024-10-04 | ZFRE | 40170000 | EA | 104 |  | ND | M108 | V | 510 | AUD | 1 | SAP_WFRT

## MB51
Material | Plant | Storage location | Movement type | Special Stock | Material Document | Material Doc.Item | Posting Date | Qty in unit of entry | Unit of Entry | Valuation Type | Amt.in Loc.Cur. | Batch | WBS Element | Cost Center | Order | Purchase order | Warehouse Number | Warehouse Document | Reservation | Unique
10060919 | AA53 | 5001 | 261 |  | 4900034050 | 4 | 2024-03-01 | -2 | EA |  | -10.64 |  |  |  | 600002183 |  |  |  | 85065 | 10060919600002183
10060902 | AA53 | 5001 | 261 |  | 4900047604 | 2 | 2024-04-18 | -1 | EA |  | -16.04 |  |  |  | 200082323 |  |  |  | 118184 | 10060902200082323
10060902 | AA53 | 5001 | 261 |  | 4900047982 | 1 | 2024-04-19 | -1 | EA |  | -16.04 |  |  |  | 200082323 |  |  |  | 118184 | 10060902200082323
10060919 | AA53 | 5001 | 261 |  | 4900049318 | 2 | 2024-04-23 | -2 | EA |  | -10.64 |  |  |  | 100074118 |  |  |  | 225371 | 10060919100074118
10060919 | AA53 | 5001 | 261 |  | 4900049208 | 1 | 2024-04-23 | -2 | EA |  | -10.64 |  |  |  | 100074118 |  |  |  | 225371 | 10060919100074118
10060919 | AA53 | 5001 | 261 |  | 4900049203 | 1 | 2024-04-23 | -8 | EA |  | -42.56 |  |  |  | 200082323 |  |  |  | 118184 | 10060919200082323
10060887 | AA53 | 5001 | 261 |  | 4900050021 | 1 | 2024-04-24 | -8 | EA |  | -82 |  |  |  | 200071239 |  |  |  | 105608 | 10060887200071239
10060887 | AA53 | 5001 | 261 |  | 4900050025 | 1 | 2024-04-24 | -8 | EA |  | -82 |  |  |  | 200054624 |  |  |  | 88933 | 10060887200054624
10060888 | AA53 | 5001 | 261 |  | 4900050012 | 1 | 2024-04-24 | -2 | EA |  | -20.9 |  |  |  | 100037462 |  |  |  | 135934 | 10060888100037462
10060902 | AA53 | 5001 | 261 |  | 4900050015 | 1 | 2024-04-24 | -3 | EA |  | -48.12 |  |  |  | 100040125 |  |  |  | 138626 | 10060902100040125
10060887 | AA53 | 5001 | 261 |  | 4900051662 | 1 | 2024-04-30 | -6 | EA |  | -61.5 |  |  |  | 200074552 |  |  |  | 108941 | 10060887200074552
10060887 | AA53 | 5001 | 261 |  | 4900051663 | 1 | 2024-04-30 | -2 | EA |  | -20.5 |  |  |  | 200074552 |  |  |  | 108941 | 10060887200074552
10202323 | AA53 | 5001 | 261 |  | 4900052033 | 5 | 2024-05-01 | -12 | M |  | -300 |  |  |  | 100072575 |  |  |  | 219261 | 10202323100072575
10202329 | AA53 | 5001 | 261 |  | 4900052033 | 3 | 2024-05-01 | -1 | EA |  | -65 |  |  |  | 100072575 |  |  |  | 219261 | 10202329100072575
10218625 | AA53 | 5001 | 261 |  | 4900052413 | 1 | 2024-05-02 | -16 | EA |  | -110.08 |  |  |  | 100037463 |  |  |  | 135935 | 10218625100037463
10218626 | AA53 | 5001 | 261 |  | 4900052657 | 2 | 2024-05-03 | -16 | EA |  | -142.56 |  |  |  | 100037464 |  |  |  | 135936 | 10218626100037464
10218626 | AA53 | 5001 | 261 |  | 4900052680 | 2 | 2024-05-03 | -16 | EA |  | -142.56 |  |  |  | 100037465 |  |  |  | 135937 | 10218626100037465
10251654 | AA53 | 5001 | 261 |  | 4900054425 | 1 | 2024-05-07 | -2 | EA |  | -18 |  |  |  | 100072575 |  |  |  | 219261 | 10251654100072575
10060887 | AA53 | 5001 | 261 |  | 4900061882 | 1 | 2024-05-18 | -2 | EA |  | -20.5 |  |  |  | 100039179 |  |  |  | 137691 | 10060887100039179
10060919 | AA53 | 5001 | 261 |  | 4900061902 | 4 | 2024-05-18 | -20 | EA |  | -106.4 |  |  |  | 100072016 |  |  |  | 216559 | 10060919100072016
10060887 | AA53 | 5001 | 261 |  | 4900061997 | 1 | 2024-05-19 | -1 | EA |  | -10.25 |  |  |  | 200089031 |  |  |  | 127309 | 10060887200089031
10060932 | AA53 | 5001 | 261 |  | 4900061994 | 1 | 2024-05-19 | -4 | EA |  | -56.48 |  |  |  | 200083164 |  |  |  | 120013 | 10060932200083164
10305744 | AA53 | 5001 | 261 |  | 4900064700 | 1 | 2024-05-23 | -4 | EA |  | -37.04 |  |  |  | 100071832 |  |  |  | 213988 | 10305744100071832
10060902 | AA53 | 5001 | 261 |  | 4900065112 | 3 | 2024-05-24 | -3 | EA |  | -48.12 |  |  |  | 200082323 |  |  |  | 118184 | 10060902200082323
10060902 | AA53 | 5001 | 261 |  | 4900065112 | 8 | 2024-05-24 | -3 | EA |  | -48.12 |  |  |  | 200082323 |  |  |  | 118184 | 10060902200082323
10060919 | AA53 | 5001 | 261 |  | 4900065070 | 1 | 2024-05-24 | -50 | EA |  | -266 |  |  |  | 100033847 |  |  |  | 132381 | 10060919100033847
10060919 | AA53 | 5001 | 261 |  | 4900065112 | 6 | 2024-05-24 | -1 | EA |  | -5.32 |  |  |  | 200082323 |  |  |  | 118184 | 10060919200082323
10218628 | AA53 | 5001 | 261 |  | 4900065112 | 5 | 2024-05-24 | -24 | EA |  | -191.28 |  |  |  | 200082323 |  |  |  | 118184 | 10218628200082323
10060919 | AA53 | 5001 | 261 |  | 4900066549 | 1 | 2024-05-28 | -2 | EA |  | -10.64 |  |  |  | 200090863 |  |  |  | 129152 | 10060919200090863
10060919 | AA53 | 5001 | 261 |  | 4900066549 | 5 | 2024-05-28 | -2 | EA |  | -10.64 |  |  |  | 200090863 |  |  |  | 129152 | 10060919200090863
10305744 | AA53 | 5001 | 261 |  | 4900066549 | 6 | 2024-05-28 | -8 | EA |  | -74.09 |  |  |  | 200090863 |  |  |  | 129152 | 10305744200090863
10305744 | AA53 | 5001 | 261 |  | 4900066549 | 2 | 2024-05-28 | -8 | EA |  | -74.09 |  |  |  | 200090863 |  |  |  | 129152 | 10305744200090863
10060902 | AA53 | 5001 | 261 |  | 4900068033 | 2 | 2024-05-31 | -2 | EA |  | -32.08 |  |  |  | 200061073 |  |  |  | 95422 | 10060902200061073
10060902 | AA53 | 5001 | 261 |  | 4900068033 | 9 | 2024-05-31 | -3 | EA |  | -48.12 |  |  |  | 200061073 |  |  |  | 95422 | 10060902200061073
10060919 | AA53 | 5001 | 261 |  | 4900068033 | 3 | 2024-05-31 | -1 | EA |  | -5.32 |  |  |  | 200061073 |  |  |  | 95422 | 10060919200061073
10060919 | AA53 | 5001 | 261 |  | 4900068288 | 1 | 2024-05-31 | -4 | EA |  | -21.28 |  |  |  | 100041985 |  |  |  | 140459 | 10060919100041985
10223374 | AA53 | 5001 | 261 |  | 4900067978 | 8 | 2024-05-31 | -16 | EA |  | -158.24 |  |  |  | 100045230 |  |  |  | 143731 | 10223374100045230
10305744 | AA53 | 5001 | 261 |  | 4900067978 | 7 | 2024-05-31 | -2 | EA |  | -18.52 |  |  |  | 100045230 |  |  |  | 143731 | 10305744100045230
10060887 | AA53 | 5001 | 261 |  | 4900069301 | 1 | 2024-06-04 | -1 | EA |  | -10.25 |  |  |  | 200089033 |  |  |  | 127311 | 10060887200089033
10060932 | AA53 | 5001 | 261 |  | 4900070378 | 1 | 2024-06-06 | -4 | EA |  | -56.48 |  |  |  | 200083165 |  |  |  | 120014 | 10060932200083165
10060885 | AA53 | 5001 | 261 |  | 4900072118 | 1 | 2024-06-10 | -1 | EA |  | -4.77 |  |  |  | 200087905 |  |  |  | 126139 | 10060885200087905
10060886 | AA53 | 5001 | 261 |  | 4900072115 | 1 | 2024-06-10 | -2 | EA |  | -12.56 |  |  |  | 200071730 |  |  |  | 106033 | 10060886200071730
10218617 | AA53 | 5001 | 261 |  | 4900072118 | 2 | 2024-06-10 | -16 | EA |  | -14.08 |  |  |  | 200087905 |  |  |  | 126139 | 10218617200087905
10060904 | AA53 | 5001 | 261 |  | 4900075417 | 1 | 2024-06-18 | -2 | EA |  | -51.44 |  |  |  | 100046911 |  |  |  | 145443 | 10060904100046911
10060919 | AA53 | 5001 | 261 |  | 4900076084 | 1 | 2024-06-19 | -6 | EA |  | -31.95 |  |  |  | 200089990 |  |  |  | 128264 | 10060919200089990
10218613 | AA53 | 5001 | 261 |  | 4900075804 | 27 | 2024-06-19 | -8 | EA |  | -8 |  |  |  | 600002061 |  |  |  | 84977 | 10218613600002061
10218627 | AA53 | 5001 | 261 |  | 4900075804 | 26 | 2024-06-19 | -16 | EA |  | -150.08 |  |  |  | 600002061 |  |  |  | 84977 | 10218627600002061
10060888 | AA53 | 5001 | 261 |  | 4900076606 | 1 | 2024-06-20 | -2 | EA |  | -20.9 |  |  |  | 100037463 |  |  |  | 135935 | 10060888100037463
10218625 | AA53 | 5001 | 261 |  | 4900076605 | 1 | 2024-06-20 | -8 | EA |  | -55.04 |  |  |  | 100037462 |  |  |  | 135934 | 10218625100037462
10060919 | AA53 | 5001 | 261 |  | 4900077438 | 1 | 2024-06-21 | -1 | EA |  | -5.33 |  |  |  | 200089470 |  |  |  | 127728 | 10060919200089470
10060932 | AA53 | 5001 | 261 |  | 4900091955 | 1 | 2024-07-15 | -20 | EA |  | -282.4 |  |  |  | 100080190 |  |  |  | 248086 | 10060932100080190
10059971 | AA53 | 5001 | 261 |  | 4900092763 | 2 | 2024-07-16 | -1 | EA |  | -14.25 |  |  |  | 100076762 |  |  |  | 234116 | 10059971100076762
10060919 | AA53 | 5001 | 261 |  | 4900092767 | 3 | 2024-07-16 | -6 | EA |  | -32.15 |  |  |  | 200069997 |  |  |  | 104331 | 10060919200069997
10218625 | AA53 | 5001 | 261 |  | 4900092763 | 3 | 2024-07-16 | -24 | EA |  | -165.12 |  |  |  | 100076762 |  |  |  | 234116 | 10218625100076762
10305744 | AA53 | 5001 | 261 |  | 4900092767 | 4 | 2024-07-16 | -2 | EA |  | -18.53 |  |  |  | 200069997 |  |  |  | 104331 | 10305744200069997
10060901 | AA53 | 5001 | 261 |  | 4900093609 | 1 | 2024-07-17 | -1 | EA |  | -11.64 |  |  |  | 200074034 |  |  |  | 108368 | 10060901200074034
10060901 | AA53 | 5001 | 261 |  | 4900093605 | 1 | 2024-07-17 | -1 | EA |  | -11.64 |  |  |  | 200070731 |  |  |  | 105000 | 10060901200070731
10060901 | AA53 | 5001 | 261 |  | 4900093601 | 1 | 2024-07-17 | -1 | EA |  | -11.64 |  |  |  | 200073637 |  |  |  | 107960 | 10060901200073637
10305744 | AA53 | 5001 | 261 |  | 4900093605 | 2 | 2024-07-17 | -1 | EA |  | -9.27 |  |  |  | 200070731 |  |  |  | 105000 | 10305744200070731
10305744 | AA53 | 5001 | 261 |  | 4900093601 | 2 | 2024-07-17 | -1 | EA |  | -9.27 |  |  |  | 200073637 |  |  |  | 107960 | 10305744200073637
10305744 | AA53 | 5001 | 261 |  | 4900093609 | 2 | 2024-07-17 | -1 | EA |  | -9.27 |  |  |  | 200074034 |  |  |  | 108368 | 10305744200074034
10218628 | AA53 | 5001 | 261 |  | 4900098485 | 1 | 2024-07-25 | -24 | EA |  | -191.28 |  |  |  | 100034900 |  |  |  | 133372 | 10218628100034900
10060934 | AA53 | 5001 | 261 |  | 4900099127 | 1 | 2024-07-26 | -2 | EA |  | -54.2 |  |  |  | 100032645 |  |  |  | 131143 | 10060934100032645
10060902 | AA53 | 5001 | 261 |  | 4900100348 | 1 | 2024-07-29 | -4 | EA |  | -64.16 |  |  |  | 100073112 |  |  |  | 220546 | 10060902100073112
10060919 | AA53 | 5001 | 261 |  | 4900100338 | 2 | 2024-07-29 | -1 | EA |  | -5.48 |  |  |  | 100043105 |  |  |  | 141629 | 10060919100043105
10060919 | AA53 | 5001 | 261 |  | 4900100347 | 1 | 2024-07-29 | -8 | EA |  | -43.87 |  |  |  | 100071546 |  |  |  | 212697 | 10060919100071546
10218636 | AA53 | 5001 | 261 |  | 4900100338 | 5 | 2024-07-29 | -12 | EA |  | -90.03 |  |  |  | 100043105 |  |  |  | 141629 | 10218636100043105
10060885 | AA53 | 5001 | 261 |  | 4900101254 | 1 | 2024-07-30 | -20 | EA |  | -95.41 |  |  |  | 100040863 |  |  |  | 139337 | 10060885100040863
10060887 | AA53 | 5001 | 261 |  | 4900101180 | 1 | 2024-07-30 | -2 | EA |  | -20.53 |  |  |  | 200068578 |  |  |  | 102967 | 10060887200068578
10060907 | AA53 | 5001 | 261 |  | 4900101150 | 1 | 2024-07-30 | -1 | EA |  | -45.21 |  |  |  | 200053721 |  |  |  | 87996 | 10060907200053721
10060907 | AA53 | 5001 | 261 |  | 4900101156 | 1 | 2024-07-30 | -1 | EA |  | -45.21 |  |  |  | 200054626 |  |  |  | 88935 | 10060907200054626
10218617 | AA53 | 5001 | 261 |  | 4900101180 | 2 | 2024-07-30 | -8 | EA |  | -12.32 |  |  |  | 200068578 |  |  |  | 102967 | 10218617200068578
10060919 | AA53 | 5001 | 261 |  | 4900105688 | 3 | 2024-08-07 | -3 | EA |  | -16.47 |  |  |  | 100078896 |  |  |  | 243419 | 10060919100078896
10218632 | AA53 | 5001 | 261 |  | 4900105680 | 1 | 2024-08-07 | -12 | EA |  | -117.39 |  |  |  | 100077847 |  |  |  | 238644 | 10218632100077847
10060886 | AA53 | 5001 | 261 |  | 4900110215 | 2 | 2024-08-14 | -1 | EA |  | -6.76 |  |  |  | 200073750 |  |  |  | 108085 | 10060886200073750
10060902 | AA53 | 5001 | 261 |  | 4900110384 | 1 | 2024-08-14 | -1 | EA |  | -16.04 |  |  |  | 200060898 |  |  |  | 95220 | 10060902200060898
10060919 | AA53 | 5001 | 261 |  | 4900110215 | 1 | 2024-08-14 | -1 | EA |  | -5.49 |  |  |  | 200073750 |  |  |  | 108085 | 10060919200073750
10060919 | AA53 | 5001 | 261 |  | 4900110225 | 2 | 2024-08-14 | -1 | EA |  | -5.49 |  |  |  | 200071054 |  |  |  | 105397 | 10060919200071054
10060919 | AA53 | 5001 | 261 |  | 4900110223 | 2 | 2024-08-14 | -1 | EA |  | -5.49 |  |  |  | 200071053 |  |  |  | 105395 | 10060919200071053
10060887 | AA53 | 5001 | 261 |  | 4900110748 | 2 | 2024-08-15 | -1 | EA |  | -10.27 |  |  |  | 200077413 |  |  |  | 111801 | 10060887200077413
10060887 | AA53 | 5001 | 261 |  | 4900110948 | 7 | 2024-08-15 | -8 | EA |  | -82.2 |  |  |  | 200069989 |  |  |  | 104323 | 10060887200069989
10060902 | AA53 | 5001 | 261 |  | 4900111082 | 1 | 2024-08-15 | -1 | EA |  | -16.04 |  |  |  | 200059447 |  |  |  | 93716 | 10060902200059447
10060902 | AA53 | 5001 | 261 |  | 4900111080 | 1 | 2024-08-15 | -1 | EA |  | -16.04 |  |  |  | 200059448 |  |  |  | 93717 | 10060902200059448
10060919 | AA53 | 5001 | 261 |  | 4900110958 | 2 | 2024-08-15 | -2 | EA |  | -10.98 |  |  |  | 200079164 |  |  |  | 113459 | 10060919200079164
10060919 | AA53 | 5001 | 261 |  | 4900110948 | 4 | 2024-08-15 | -6 | EA |  | -32.93 |  |  |  | 200069989 |  |  |  | 104323 | 10060919200069989
10060919 | AA53 | 5001 | 261 |  | 4900110958 | 7 | 2024-08-15 | -3 | EA |  | -16.47 |  |  |  | 200079164 |  |  |  | 113459 | 10060919200079164
10218613 | AA53 | 5001 | 261 |  | 4900110884 | 1 | 2024-08-15 | -4 | EA |  | -9.34 |  |  |  | 200079602 |  |  |  | 113878 | 10218613200079602
10218617 | AA53 | 5001 | 261 |  | 4900110958 | 4 | 2024-08-15 | -8 | EA |  | -12.97 |  |  |  | 200079164 |  |  |  | 113459 | 10218617200079164
10218626 | AA53 | 5001 | 261 |  | 4900110958 | 1 | 2024-08-15 | -8 | EA |  | -66.83 |  |  |  | 200079164 |  |  |  | 113459 | 10218626200079164
10218627 | AA53 | 5001 | 261 |  | 4900110958 | 6 | 2024-08-15 | -8 | EA |  | -69.07 |  |  |  | 200079164 |  |  |  | 113459 | 10218627200079164
10305744 | AA53 | 5001 | 261 |  | 4900110958 | 11 | 2024-08-15 | -3 | EA |  | -27.8 |  |  |  | 200079164 |  |  |  | 113459 | 10305744200079164
10305744 | AA53 | 5001 | 261 |  | 4900110748 | 3 | 2024-08-15 | -1 | EA |  | -9.27 |  |  |  | 200077413 |  |  |  | 111801 | 10305744200077413
10305744 | AA53 | 5001 | 261 |  | 4900110948 | 5 | 2024-08-15 | -2 | EA |  | -18.53 |  |  |  | 200069989 |  |  |  | 104323 | 10305744200069989
10060901 | AA53 | 5001 | 261 |  | 4900112026 | 1 | 2024-08-16 | -1 | EA |  | -11.64 |  |  |  | 200059446 |  |  |  | 93715 | 10060901200059446
10060919 | AA53 | 5001 | 261 |  | 4900112028 | 2 | 2024-08-16 | -1 | EA |  | -5.49 |  |  |  | 200059444 |  |  |  | 93713 | 10060919200059444
10305744 | AA53 | 5001 | 261 |  | 4900112028 | 3 | 2024-08-16 | -1 | EA |  | -9.27 |  |  |  | 200059444 |  |  |  | 93713 | 10305744200059444
10305744 | AA53 | 5001 | 261 |  | 4900112026 | 2 | 2024-08-16 | -1 | EA |  | -9.27 |  |  |  | 200059446 |  |  |  | 93715 | 10305744200059446
10060885 | AA53 | 5001 | 261 |  | 4900113421 | 2 | 2024-08-19 | -1 | EA |  | -4.78 |  |  |  | 200073242 |  |  |  | 107545 | 10060885200073242
10060886 | AA53 | 5001 | 261 |  | 4900113277 | 1 | 2024-08-19 | -1 | EA |  | -6.78 |  |  |  | 200089470 |  |  |  | 127728 | 10060886200089470
10060888 | AA53 | 5001 | 261 |  | 4900113503 | 1 | 2024-08-19 | -1 | EA |  | -10.45 |  |  |  | 200070736 |  |  |  | 105064 | 10060888200070736
10060888 | AA53 | 5001 | 261 |  | 4900113372 | 2 | 2024-08-19 | -1 | EA |  | -10.45 |  |  |  | 200080012 |  |  |  | 114300 | 10060888200080012
10060901 | AA53 | 5001 | 261 |  | 4900113372 | 3 | 2024-08-19 | -1 | EA |  | -11.68 |  |  |  | 200080012 |  |  |  | 114300 | 10060901200080012
10060901 | AA53 | 5001 | 261 |  | 4900113523 | 1 | 2024-08-19 | -1 | EA |  | -11.69 |  |  |  | 200070292 |  |  |  | 104641 | 10060901200070292
10060901 | AA53 | 5001 | 261 |  | 4900113503 | 2 | 2024-08-19 | -1 | EA |  | -11.69 |  |  |  | 200070736 |  |  |  | 105064 | 10060901200070736
10062985 | AA53 | 5001 | 261 |  | 4900113244 | 2 | 2024-08-19 | -2 | CYL |  | -88.4 | 0000000216 |  |  | 200090973 |  |  |  | 129247 | 10062985200090973
10312854 | AA53 | 5001 | 261 |  | 4900113244 | 1 | 2024-08-19 | -2 | PAC |  | -1325.66 | 0000000215 |  |  | 200090973 |  |  |  | 129247 | 10312854200090973
10060886 | AA53 | 5001 | 261 |  | 4900114109 | 3 | 2024-08-20 | -15 | EA |  | -101.64 |  |  |  | 500003904 |  |  |  | 218430 | 10060886500003904
10060887 | AA53 | 5001 | 261 |  | 4900114109 | 4 | 2024-08-20 | -18 | EA |  | -185.02 |  |  |  | 500003904 |  |  |  | 218430 | 10060887500003904
10060902 | AA53 | 5001 | 261 |  | 4900114109 | 18 | 2024-08-20 | -56 | EA |  | -898.24 |  |  |  | 500003904 |  |  |  | 218430 | 10060902500003904
10060904 | AA53 | 5001 | 261 |  | 4900114109 | 20 | 2024-08-20 | -18 | EA |  | -454.74 |  |  |  | 500003904 |  |  |  | 218430 | 10060904500003904
10060906 | AA53 | 5001 | 261 |  | 4900114109 | 21 | 2024-08-20 | -19 | EA |  | -764.94 |  |  |  | 500003904 |  |  |  | 218430 | 10060906500003904
10060907 | AA53 | 5001 | 261 |  | 4900114109 | 22 | 2024-08-20 | -5 | EA |  | -227.38 |  |  |  | 500003904 |  |  |  | 218430 | 10060907500003904
10060919 | AA53 | 5001 | 261 |  | 4900114109 | 16 | 2024-08-20 | -141 | EA |  | -774.26 |  |  |  | 500003904 |  |  |  | 218430 | 10060919500003904
10060934 | AA53 | 5001 | 261 |  | 4900114214 | 1 | 2024-08-20 | -14 | EA |  | -342.25 |  |  |  | 500003904 |  |  |  | 218430 | 10060934500003904
10060941 | AA53 | 5001 | 261 |  | 4900114214 | 6 | 2024-08-20 | -24 | EA |  | -2178.31 |  |  |  | 500003904 |  |  |  | 218430 | 10060941500003904
10305744 | AA53 | 5001 | 261 |  | 4900114109 | 17 | 2024-08-20 | -16 | EA |  | -148.3 |  |  |  | 500003904 |  |  |  | 218430 | 10305744500003904
10060919 | AA53 | 5001 | 261 |  | 4900114565 | 2 | 2024-08-21 | -1 | EA |  | -5.49 |  |  |  | 200068988 |  |  |  | 103237 | 10060919200068988
10592509 | AA53 | 5001 | 261 |  | 4900114959 | 12 | 2024-08-21 | -12 | EA |  | -391.56 |  |  |  | 500003890 |  |  |  | 218321 | 10592509500003890
10592509 | AA53 | 5001 | 261 |  | 4900114959 | 10 | 2024-08-21 | -10 | EA |  | -326.3 |  |  |  | 500003890 |  |  |  | 218321 | 10592509500003890
10060892 | AA53 | 5001 | 261 |  | 4900115278 | 1 | 2024-08-22 | -42 | EA |  | -1301.09 |  |  |  | 500003904 |  |  |  | 218430 | 10060892500003904
10052685 | AA53 | 5001 | 261 |  | 4900116078 | 1 | 2024-08-23 | -1 | EA |  | -4232.06 |  |  |  | 200089248 |  |  |  | 127517 | 10052685200089248
10052685 | AA53 | 5001 | 261 |  | 4900116077 | 1 | 2024-08-23 | -1 | EA |  | -4232.07 |  |  |  | 200089249 |  |  |  | 127518 | 10052685200089249
10052685 | AA53 | 5001 | 261 |  | 4900116076 | 1 | 2024-08-23 | -1 | EA |  | -4232.07 |  |  |  | 200089247 |  |  |  | 127516 | 10052685200089247
10312854 | AA53 | 5001 | 261 |  | 4900116101 | 1 | 2024-08-23 | -1 | PAC |  | -662.83 | 0000005315 |  |  | 100042829 |  |  |  | 141361 | 10312854100042829
10060901 | AA53 | 5001 | 261 |  | 4900116910 | 1 | 2024-08-24 | -1 | EA |  | -11.69 |  |  |  | 200064351 |  |  |  | 98666 | 10060901200064351
10060902 | AA53 | 5001 | 261 |  | 4900116910 | 2 | 2024-08-24 | -1 | EA |  | -16.04 |  |  |  | 200064351 |  |  |  | 98666 | 10060902200064351
10060919 | AA53 | 5001 | 261 |  | 4900116906 | 2 | 2024-08-24 | -1 | EA |  | -5.49 |  |  |  | 200065331 |  |  |  | 99653 | 10060919200065331
10305744 | AA53 | 5001 | 261 |  | 4900117034 | 1 | 2024-08-24 | -1 | EA |  | -9.27 |  |  |  | 200064071 |  |  |  | 98353 | 10305744200064071
10305744 | AA53 | 5001 | 261 |  | 4900116969 | 1 | 2024-08-24 | -1 | EA |  | -9.27 |  |  |  | 200070179 |  |  |  | 104515 | 10305744200070179
10060888 | AA53 | 5001 | 261 |  | 4900118670 | 2 | 2024-08-27 | -4 | EA |  | -41.8 |  |  |  | 200133268 |  |  |  | 212702 | 10060888200133268
10060888 | AA53 | 5001 | 261 |  | 4900118670 | 1 | 2024-08-27 | -2 | EA |  | -20.9 |  |  |  | 200133268 |  |  |  | 212702 | 10060888200133268
10060888 | AA53 | 5001 | 261 |  | 4900118670 | 3 | 2024-08-27 | -4 | EA |  | -41.8 |  |  |  | 200133268 |  |  |  | 212702 | 10060888200133268
10060919 | AA53 | 5001 | 261 |  | 4900119219 | 1 | 2024-08-27 | -1 | EA |  | -5.49 |  |  |  | 200063817 |  |  |  | 98166 | 10060919200063817
10060919 | AA53 | 5001 | 261 |  | 4900119213 | 2 | 2024-08-27 | -1 | EA |  | -5.49 |  |  |  | 200063811 |  |  |  | 98080 | 10060919200063811
10305744 | AA53 | 5001 | 261 |  | 4900118672 | 1 | 2024-08-27 | -5 | EA |  | -46.35 |  |  |  | 500003904 |  |  |  | 218430 | 10305744500003904
10062985 | AA53 | 5001 | 261 |  | 4900120030 | 1 | 2024-08-28 | -2 | CYL |  | -88.4 | 0000005673 |  |  | 100042829 |  |  |  | 141361 | 10062985100042829
10060892 | AA53 | 5001 | 261 |  | 4900120895 | 8 | 2024-08-29 | -1 | EA |  | -31 |  |  |  | 100082579 |  |  |  | 256886 | 10060892100082579
10060901 | AA53 | 5001 | 261 |  | 4900120872 | 1 | 2024-08-29 | -1 | EA |  | -11.69 |  |  |  | 100031833 |  |  |  | 130234 | 10060901100031833
10258213 | AA53 | 5001 | 261 |  | 4900120875 | 1 | 2024-08-29 | -2 | SHT |  | -1780.37 |  |  |  | 100042711 |  |  |  | 141215 | 10258213100042711
10305744 | AA53 | 5001 | 261 |  | 4900120741 | 1 | 2024-08-29 | -5 | EA |  | -46.35 |  |  |  | 500003904 |  |  |  | 218430 | 10305744500003904
10060885 | AA53 | 5001 | 261 |  | 4900122572 | 39 | 2024-08-31 | -1 | EA |  | -4.78 |  |  |  | 200133269 |  |  |  | 212703 | 10060885200133269
10060885 | AA53 | 5001 | 261 |  | 4900122246 | 17 | 2024-08-31 | -1 | EA |  | -4.78 |  |  |  | 200133268 |  |  |  | 212702 | 10060885200133268
10060886 | AA53 | 5001 | 261 |  | 4900122420 | 14 | 2024-08-31 | -2 | EA |  | -13.58 |  |  |  | 200133268 |  |  |  | 212702 | 10060886200133268
10060886 | AA53 | 5001 | 261 |  | 4900122572 | 37 | 2024-08-31 | -2 | EA |  | -13.58 |  |  |  | 200133269 |  |  |  | 212703 | 10060886200133269
10060887 | AA53 | 5001 | 261 |  | 4900122323 | 22 | 2024-08-31 | -2 | EA |  | -20.56 |  |  |  | 200133268 |  |  |  | 212702 | 10060887200133268
10060887 | AA53 | 5001 | 261 |  | 4900122495 | 19 | 2024-08-31 | -2 | EA |  | -20.56 |  |  |  | 200133269 |  |  |  | 212703 | 10060887200133269
10060888 | AA53 | 5001 | 261 |  | 4900122572 | 44 | 2024-08-31 | -2 | EA |  | -20.9 |  |  |  | 200133269 |  |  |  | 212703 | 10060888200133269
10060888 | AA53 | 5001 | 261 |  | 4900122572 | 47 | 2024-08-31 | -4 | EA |  | -41.8 |  |  |  | 200133269 |  |  |  | 212703 | 10060888200133269
10060892 | AA53 | 5001 | 261 |  | 4900122495 | 7 | 2024-08-31 | -3 | EA |  | -92.99 |  |  |  | 200133269 |  |  |  | 212703 | 10060892200133269
10060892 | AA53 | 5001 | 261 |  | 4900122578 | 32 | 2024-08-31 | -1 | EA |  | -31 |  |  |  | 200133269 |  |  |  | 212703 | 10060892200133269
10060892 | AA53 | 5001 | 261 |  | 4900122424 | 22 | 2024-08-31 | -4 | EA |  | -123.98 |  |  |  | 200133268 |  |  |  | 212702 | 10060892200133268
10060901 | AA53 | 5001 | 261 |  | 4900122578 | 3 | 2024-08-31 | -10 | EA |  | -116.9 |  |  |  | 200133269 |  |  |  | 212703 | 10060901200133269
10060901 | AA53 | 5001 | 261 |  | 4900122242 | 16 | 2024-08-31 | -10 | EA |  | -116.9 |  |  |  | 200133268 |  |  |  | 212702 | 10060901200133268
10060919 | AA53 | 5001 | 261 |  | 4900122242 | 17 | 2024-08-31 | -20 | EA |  | -109.85 |  |  |  | 200133268 |  |  |  | 212702 | 10060919200133268
10060919 | AA53 | 5001 | 261 |  | 4900122578 | 4 | 2024-08-31 | -20 | EA |  | -109.85 |  |  |  | 200133269 |  |  |  | 212703 | 10060919200133269
10305744 | AA53 | 5001 | 261 |  | 4900123188 | 1 | 2024-09-01 | -5 | EA |  | -46.35 |  |  |  | 500003904 |  |  |  | 218430 | 10305744500003904
10060885 | AA53 | 5001 | 261 |  | 4900124546 | 1 | 2024-09-03 | -5 | EA |  | -23.88 |  |  |  | 100082579 |  |  |  | 256886 | 10060885100082579
10060887 | AA53 | 5001 | 261 |  | 4900124125 | 63 | 2024-09-03 | -2 | EA |  | -20.56 |  |  |  | 200090902 |  |  |  | 129020 | 10060887200090902
10060887 | AA53 | 5001 | 261 |  | 4900124125 | 60 | 2024-09-03 | -2 | EA |  | -20.56 |  |  |  | 200090902 |  |  |  | 129020 | 10060887200090902
10060932 | AA53 | 5001 | 261 |  | 4900123973 | 38 | 2024-09-03 | -8 | EA |  | -114.16 |  |  |  | 200090757 |  |  |  | 129015 | 10060932200090757
10060887 | AA53 | 5001 | 261 |  | 4900125247 | 1 | 2024-09-04 | -2 | EA |  | -20.56 |  |  |  | 200089073 |  |  |  | 127362 | 10060887200089073
10060888 | AA53 | 5001 | 261 |  | 4900125036 | 1 | 2024-09-04 | -5 | EA |  | -52.25 |  |  |  | 100039294 |  |  |  | 137795 | 10060888100039294
10060901 | AA53 | 5001 | 261 |  | 4900125327 | 1 | 2024-09-04 | -4 | EA |  | -46.76 |  |  |  | 200090916 |  |  |  | 129214 | 10060901200090916
10060885 | AA53 | 5001 | 261 |  | 4900125894 | 1 | 2024-09-05 | -321 | EA |  | -1533.12 |  |  |  | 500003904 |  |  |  | 218430 | 10060885500003904
10060888 | AA53 | 5001 | 261 |  | 4900125894 | 2 | 2024-09-05 | -8 | EA |  | -83.6 |  |  |  | 500003904 |  |  |  | 218430 | 10060888500003904
10060905 | AA53 | 5001 | 261 |  | 4900125894 | 5 | 2024-09-05 | -67 | EA |  | -2105.98 |  |  |  | 500003904 |  |  |  | 218430 | 10060905500003904
10305744 | AA53 | 5001 | 261 |  | 4900125894 | 12 | 2024-09-05 | -27 | EA |  | -250.27 |  |  |  | 500003904 |  |  |  | 218430 | 10305744500003904
10060888 | AA53 | 5001 | 261 |  | 4900126805 | 1 | 2024-09-06 | -1 | EA |  | -10.45 |  |  |  | 200074843 |  |  |  | 109145 | 10060888200074843
10060886 | AA53 | 5001 | 261 |  | 4900128302 | 1 | 2024-09-09 | -35 | EA |  | -237.58 |  |  |  | 500003904 |  |  |  | 218430 | 10060886500003904
10060902 | AA53 | 5001 | 261 |  | 4900128235 | 1 | 2024-09-09 | -1 | EA |  | -16.11 |  |  |  | 200063189 |  |  |  | 97458 | 10060902200063189
10060888 | AA53 | 5001 | 261 |  | 4900129150 | 1 | 2024-09-10 | -1 | EA |  | -10.45 |  |  |  | 200063052 |  |  |  | 97401 | 10060888200063052
10060901 | AA53 | 5001 | 261 |  | 4900129156 | 3 | 2024-09-10 | -1 | EA |  | -11.69 |  |  |  | 200063526 |  |  |  | 97861 | 10060901200063526
10060901 | AA53 | 5001 | 261 |  | 4900129150 | 2 | 2024-09-10 | -1 | EA |  | -11.69 |  |  |  | 200063052 |  |  |  | 97401 | 10060901200063052
10060901 | AA53 | 5001 | 261 |  | 4900129159 | 1 | 2024-09-10 | -1 | EA |  | -11.69 |  |  |  | 200063527 |  |  |  | 97862 | 10060901200063527
10060901 | AA53 | 5001 | 261 |  | 4900128880 | 1 | 2024-09-10 | -10 | EA |  | -116.9 |  |  |  | 500003904 |  |  |  | 218430 | 10060901500003904
10060902 | AA53 | 5001 | 261 |  | 4900129156 | 2 | 2024-09-10 | -1 | EA |  | -16.13 |  |  |  | 200063526 |  |  |  | 97861 | 10060902200063526
10060902 | AA53 | 5001 | 261 |  | 4900129159 | 2 | 2024-09-10 | -1 | EA |  | -16.13 |  |  |  | 200063527 |  |  |  | 97862 | 10060902200063527
10060919 | AA53 | 5001 | 261 |  | 4900129145 | 1 | 2024-09-10 | -1 | EA |  | -5.5 |  |  |  | 200063752 |  |  |  | 98054 | 10060919200063752
10060919 | AA53 | 5001 | 261 |  | 4900129147 | 1 | 2024-09-10 | -1 | EA |  | -5.5 |  |  |  | 200063753 |  |  |  | 98055 | 10060919200063753
10060932 | AA53 | 5001 | 261 |  | 4900129194 | 5 | 2024-09-10 | -4 | EA |  | -57.38 |  |  |  | 100044574 |  |  |  | 143078 | 10060932100044574
10218628 | AA53 | 5001 | 261 |  | 4900128732 | 1 | 2024-09-10 | -24 | EA |  | -191.28 |  |  |  | 200089478 |  |  |  | 127736 | 10218628200089478
10305744 | AA53 | 5001 | 261 |  | 4900129145 | 2 | 2024-09-10 | -1 | EA |  | -9.27 |  |  |  | 200063752 |  |  |  | 98054 | 10305744200063752
10305744 | AA53 | 5001 | 261 |  | 4900129147 | 2 | 2024-09-10 | -1 | EA |  | -9.27 |  |  |  | 200063753 |  |  |  | 98055 | 10305744200063753
10059971 | AA53 | 5001 | 261 |  | 4900129498 | 1 | 2024-09-11 | -3 | EA |  | -42.75 |  |  |  | 100043738 |  |  |  | 142239 | 10059971100043738
10060888 | AA53 | 5001 | 261 |  | 4900129514 | 2 | 2024-09-11 | -4 | EA |  | -41.8 |  |  |  | 100083717 |  |  |  | 260559 | 10060888100083717
10060888 | AA53 | 5001 | 261 |  | 4900129967 | 1 | 2024-09-11 | -1 | EA |  | -10.45 |  |  |  | 200062474 |  |  |  | 96802 | 10060888200062474
10060888 | AA53 | 5001 | 261 |  | 4900129963 | 1 | 2024-09-11 | -1 | EA |  | -10.45 |  |  |  | 200062471 |  |  |  | 96779 | 10060888200062471
10060901 | AA53 | 5001 | 261 |  | 4900129967 | 2 | 2024-09-11 | -1 | EA |  | -11.69 |  |  |  | 200062474 |  |  |  | 96802 | 10060901200062474
10060901 | AA53 | 5001 | 261 |  | 4900129959 | 1 | 2024-09-11 | -1 | EA |  | -11.69 |  |  |  | 200062018 |  |  |  | 96366 | 10060901200062018
10060901 | AA53 | 5001 | 261 |  | 4900129957 | 1 | 2024-09-11 | -1 | EA |  | -11.69 |  |  |  | 200061446 |  |  |  | 95748 | 10060901200061446
10060902 | AA53 | 5001 | 261 |  | 4900129514 | 1 | 2024-09-11 | -4 | EA |  | -64.53 |  |  |  | 100083717 |  |  |  | 260559 | 10060902100083717
10060902 | AA53 | 5001 | 261 |  | 4900129959 | 2 | 2024-09-11 | -1 | EA |  | -16.13 |  |  |  | 200062018 |  |  |  | 96366 | 10060902200062018
10060919 | AA53 | 5001 | 261 |  | 4900129496 | 1 | 2024-09-11 | -138 | EA |  | -758.59 |  |  |  | 500004232 |  |  |  | 252576 | 10060919500004232
10060932 | AA53 | 5001 | 261 |  | 4900129963 | 2 | 2024-09-11 | -1 | EA |  | -14.35 |  |  |  | 200062471 |  |  |  | 96779 | 10060932200062471
10305744 | AA53 | 5001 | 261 |  | 4900129957 | 2 | 2024-09-11 | -1 | EA |  | -9.27 |  |  |  | 200061446 |  |  |  | 95748 | 10305744200061446
10060902 | AA53 | 5001 | 261 |  | 4900130469 | 1 | 2024-09-12 | -4 | EA |  | -64.53 |  |  |  | 500003904 |  |  |  | 218430 | 10060902500003904
10060932 | AA53 | 5001 | 261 |  | 4900130801 | 1 | 2024-09-12 | -20 | EA |  | -286.9 |  |  |  | 500003904 |  |  |  | 218430 | 10060932500003904
10312854 | AA53 | 5001 | 261 |  | 4900130436 | 1 | 2024-09-12 | -1 | PAC |  | -662.83 | 0000005315 |  |  | 100042829 |  |  |  | 141361 | 10312854100042829
10058201 | AA53 | 5001 | 261 |  | 4900131790 | 9 | 2024-09-14 | -8 | EA |  | -41.6 |  |  |  | 100040723 |  |  |  | 139195 | 10058201100040723
10058201 | AA53 | 5001 | 261 |  | 4900131790 | 8 | 2024-09-14 | -8 | EA |  | -41.6 |  |  |  | 100040723 |  |  |  | 139195 | 10058201100040723
10058222 | AA53 | 5001 | 261 |  | 4900131790 | 10 | 2024-09-14 | -24 | EA |  | -265.01 |  |  |  | 100040723 |  |  |  | 139195 | 10058222100040723
10060901 | AA53 | 5001 | 261 |  | 4900131790 | 4 | 2024-09-14 | -2 | EA |  | -23.39 |  |  |  | 100040723 |  |  |  | 139195 | 10060901100040723
10060902 | AA53 | 5001 | 261 |  | 4900131790 | 6 | 2024-09-14 | -2 | EA |  | -32.27 |  |  |  | 100040723 |  |  |  | 139195 | 10060902100040723
10060919 | AA53 | 5001 | 261 |  | 4900131790 | 5 | 2024-09-14 | -2 | EA |  | -10.99 |  |  |  | 100040723 |  |  |  | 139195 | 10060919100040723
10060919 | AA53 | 5001 | 261 |  | 4900131790 | 7 | 2024-09-14 | -2 | EA |  | -10.99 |  |  |  | 100040723 |  |  |  | 139195 | 10060919100040723
10060885 | AA53 | 5001 | 261 |  | 4900132057 | 2 | 2024-09-15 | -3 | EA |  | -14.33 |  |  |  | 100082579 |  |  |  | 256886 | 10060885100082579
10060885 | AA53 | 5001 | 261 |  | 4900132058 | 4 | 2024-09-15 | -8 | EA |  | -38.21 |  |  |  | 100083191 |  |  |  | 258765 | 10060885100083191
10218626 | AA53 | 5001 | 261 |  | 4900131818 | 4 | 2024-09-15 | -8 | EA |  | -66.34 |  |  |  | 100042851 |  |  |  | 141335 | 10218626100042851
10218626 | AA53 | 5001 | 261 |  | 4900131818 | 5 | 2024-09-15 | -8 | EA |  | -66.34 |  |  |  | 100042851 |  |  |  | 141335 | 10218626100042851
10305744 | AA53 | 5001 | 261 |  | 4900131818 | 3 | 2024-09-15 | -2 | EA |  | -18.54 |  |  |  | 100042851 |  |  |  | 141335 | 10305744100042851
10060888 | AA53 | 5001 | 261 |  | 4900132697 | 1 | 2024-09-16 | -1 | EA |  | -10.45 |  |  |  | 200063050 |  |  |  | 97339 | 10060888200063050
10060901 | AA53 | 5001 | 261 |  | 4900132697 | 2 | 2024-09-16 | -1 | EA |  | -11.7 |  |  |  | 200063050 |  |  |  | 97339 | 10060901200063050
10060901 | AA53 | 5001 | 261 |  | 4900132689 | 1 | 2024-09-16 | -1 | EA |  | -11.7 |  |  |  | 100039241 |  |  |  | 137745 | 10060901100039241
10060902 | AA53 | 5001 | 261 |  | 4900132689 | 2 | 2024-09-16 | -1 | EA |  | -16.19 |  |  |  | 100039241 |  |  |  | 137745 | 10060902100039241
10060904 | AA53 | 5001 | 261 |  | 4900132691 | 2 | 2024-09-16 | -1 | EA |  | -25.09 |  |  |  | 200064721 |  |  |  | 99023 | 10060904200064721
10060904 | AA53 | 5001 | 261 |  | 4900132684 | 2 | 2024-09-16 | -1 | EA |  | -25.09 |  |  |  | 200062494 |  |  |  | 96843 | 10060904200062494
10060904 | AA53 | 5001 | 261 |  | 4900132694 | 2 | 2024-09-16 | -1 | EA |  | -25.09 |  |  |  | 200063250 |  |  |  | 97539 | 10060904200063250
10060904 | AA53 | 5001 | 261 |  | 4900132681 | 2 | 2024-09-16 | -1 | EA |  | -25.09 |  |  |  | 200062492 |  |  |  | 96841 | 10060904200062492
10060904 | AA53 | 5001 | 261 |  | 4900132669 | 2 | 2024-09-16 | -1 | EA |  | -25.09 |  |  |  | 200061444 |  |  |  | 95746 | 10060904200061444
10060932 | AA53 | 5001 | 261 |  | 4900132691 | 4 | 2024-09-16 | -5 | EA |  | -71.73 |  |  |  | 200064721 |  |  |  | 99023 | 10060932200064721
10060885 | AA53 | 5001 | 261 |  | 4900133481 | 1 | 2024-09-17 | -1 | EA |  | -4.78 |  |  |  | 600001640 |  |  |  | 84535 | 10060885600001640
10060885 | AA53 | 5001 | 261 |  | 4900133481 | 2 | 2024-09-17 | -1 | EA |  | -4.78 |  |  |  | 600001640 |  |  |  | 84535 | 10060885600001640
10060885 | AA53 | 5001 | 261 |  | 4900133481 | 3 | 2024-09-17 | -1 | EA |  | -4.78 |  |  |  | 600001640 |  |  |  | 84535 | 10060885600001640
10060886 | AA53 | 5001 | 261 |  | 4900133338 | 1 | 2024-09-17 | -10 | EA |  | -68.04 |  |  |  | 100083937 |  |  |  | 261312 | 10060886100083937
10060887 | AA53 | 5001 | 261 |  | 4900133089 | 1 | 2024-09-17 | -1 | EA |  | -10.28 |  |  |  | 200054623 |  |  |  | 88932 | 10060887200054623
10060888 | AA53 | 5001 | 261 |  | 4900133345 | 1 | 2024-09-17 | -1 | EA |  | -10.45 |  |  |  | 200133268 |  |  |  | 212702 | 10060888200133268
10060888 | AA53 | 5001 | 261 |  | 4900133342 | 1 | 2024-09-17 | -6 | EA |  | -62.7 |  |  |  | 200090617 |  |  |  | 128927 | 10060888200090617
10060888 | AA53 | 5001 | 261 |  | 4900133341 | 1 | 2024-09-17 | -6 | EA |  | -62.7 |  |  |  | 200090616 |  |  |  | 128926 | 10060888200090616
10060905 | AA53 | 5001 | 261 |  | 4900133224 | 1 | 2024-09-17 | -1 | EA |  | -31.43 |  |  |  | 500003904 |  |  |  | 218430 | 10060905500003904
10060906 | AA53 | 5001 | 261 |  | 4900133474 | 1 | 2024-09-17 | -71 | EA |  | -2858.46 |  |  |  | 500003904 |  |  |  | 218430 | 10060906500003904
10060919 | AA53 | 5001 | 261 |  | 4900133220 | 1 | 2024-09-17 | -829 | EA |  | -4557.07 |  |  |  | 500003904 |  |  |  | 218430 | 10060919500003904
10060919 | AA53 | 5001 | 261 |  | 4900133254 | 1 | 2024-09-17 | -100 | EA |  | -549.71 |  |  |  | 500003888 |  |  |  | 218319 | 10060919500003888
10060932 | AA53 | 5001 | 261 |  | 4900133308 | 1 | 2024-09-17 | -5 | EA |  | -71.72 |  |  |  | 500003904 |  |  |  | 218430 | 10060932500003904
10305744 | AA53 | 5001 | 261 |  | 4900133257 | 1 | 2024-09-17 | -24 | EA |  | -222.46 |  |  |  | 500003904 |  |  |  | 218430 | 10305744500003904
10305744 | AA53 | 5001 | 261 |  | 4900133257 | 2 | 2024-09-17 | -23 | EA |  | -213.2 |  |  |  | 500003904 |  |  |  | 218430 | 10305744500003904
10060885 | AA53 | 5001 | 261 |  | 4900135271 | 3 | 2024-09-19 | -159 | EA |  | -759.39 |  |  |  | 500003904 |  |  |  | 218430 | 10060885500003904
10060887 | AA53 | 5001 | 261 |  | 4900135271 | 4 | 2024-09-19 | -56 | EA |  | -575.65 |  |  |  | 500003904 |  |  |  | 218430 | 10060887500003904
10060888 | AA53 | 5001 | 261 |  | 4900135271 | 5 | 2024-09-19 | -102 | EA |  | -1065.9 |  |  |  | 500003904 |  |  |  | 218430 | 10060888500003904
10060892 | AA53 | 5001 | 261 |  | 4900134981 | 1 | 2024-09-19 | -2 | EA |  | -62.15 |  |  |  | 100082579 |  |  |  | 256886 | 10060892100082579
10060892 | AA53 | 5001 | 261 |  | 4900135271 | 6 | 2024-09-19 | -6 | EA |  | -186.45 |  |  |  | 500003904 |  |  |  | 218430 | 10060892500003904
10060904 | AA53 | 5001 | 261 |  | 4900134859 | 2 | 2024-09-19 | -62 | EA |  | -1555.75 |  |  |  | 500003904 |  |  |  | 218430 | 10060904500003904
10060907 | AA53 | 5001 | 261 |  | 4900134859 | 3 | 2024-09-19 | -25 | EA |  | -1142.58 |  |  |  | 500003904 |  |  |  | 218430 | 10060907500003904
10060934 | AA53 | 5001 | 261 |  | 4900135251 | 1 | 2024-09-19 | -106 | EA |  | -2569.35 |  |  |  | 500003904 |  |  |  | 218430 | 10060934500003904
10060941 | AA53 | 5001 | 261 |  | 4900135271 | 8 | 2024-09-19 | -54 | EA |  | -4975.52 |  |  |  | 500003904 |  |  |  | 218430 | 10060941500003904
10305744 | AA53 | 5001 | 261 |  | 4900135271 | 24 | 2024-09-19 | -95 | EA |  | -880.59 |  |  |  | 500003904 |  |  |  | 218430 | 10305744500003904
10305744 | AA53 | 5001 | 261 |  | 4900134800 | 2 | 2024-09-19 | -4 | EA |  | -37.08 |  |  |  | 200066310 |  |  |  | 100598 | 10305744200066310
10060887 | AA53 | 5001 | 261 |  | 4900137550 | 1 | 2024-09-23 | -1 | EA |  | -10.28 |  |  |  | 200061073 |  |  |  | 95422 | 10060887200061073
10060886 | AA53 | 5001 | 261 |  | 4900138693 | 1 | 2024-09-24 | -1 | EA |  | -6.8 |  |  |  | 600001880 |  |  |  | 84775 | 10060886600001880
10202323 | AA53 | 5001 | 261 |  | 4900138694 | 1 | 2024-09-24 | -6 | M |  | -173.42 |  |  |  | 600001880 |  |  |  | 84775 | 10202323600001880
10060885 | AA53 | 5001 | 261 |  | 4900139253 | 5 | 2024-09-25 | -1 | EA |  | -4.78 |  |  |  | 200089320 |  |  |  | 127538 | 10060885200089320
10060887 | AA53 | 5001 | 261 |  | 4900139058 | 2 | 2024-09-25 | -5 | EA |  | -51.4 |  |  |  | 200069997 |  |  |  | 104331 | 10060887200069997
10060919 | AA53 | 5001 | 261 |  | 4900139090 | 2 | 2024-09-25 | -1 | EA |  | -5.5 |  |  |  | 200058304 |  |  |  | 92572 | 10060919200058304
10218613 | AA53 | 5001 | 261 |  | 4900139240 | 9 | 2024-09-25 | -8 | EA |  | -24.83 |  |  |  | 200079602 |  |  |  | 113878 | 10218613200079602
10305744 | AA53 | 5001 | 261 |  | 4900139090 | 3 | 2024-09-25 | -1 | EA |  | -9.27 |  |  |  | 200058304 |  |  |  | 92572 | 10305744200058304
10060902 | AA53 | 5001 | 261 |  | 4900139843 | 1 | 2024-09-26 | -1 | EA |  | -16.33 |  |  |  | 200057697 |  |  |  | 92072 | 10060902200057697
10060902 | AA53 | 5001 | 261 |  | 4900139842 | 1 | 2024-09-26 | -1 | EA |  | -16.33 |  |  |  | 200057696 |  |  |  | 92071 | 10060902200057696
10060902 | AA53 | 5001 | 261 |  | 4900141242 | 1 | 2024-09-28 | -2 | EA |  | -32.66 |  |  |  | 200082542 |  |  |  | 118716 | 10060902200082542
10219526 | AA53 | 5001 | 261 |  | 4900141242 | 2 | 2024-09-28 | -12 | EA |  | -64.86 |  |  |  | 200082542 |  |  |  | 118716 | 10219526200082542
10060901 | AA53 | 5001 | 261 |  | 4900142336 | 20 | 2024-09-30 | -3 | EA |  | -35.15 |  |  |  | 600002062 |  |  |  | 84978 | 10060901600002062
10060901 | AA53 | 5001 | 261 |  | 4900142336 | 14 | 2024-09-30 | -3 | EA |  | -35.15 |  |  |  | 600002062 |  |  |  | 84978 | 10060901600002062
10060919 | AA53 | 5001 | 261 |  | 4900142526 | 6 | 2024-09-30 | -2 | EA |  | -11 |  |  |  | 100040769 |  |  |  | 139323 | 10060919100040769
10060919 | AA53 | 5001 | 261 |  | 4900142525 | 5 | 2024-09-30 | -2 | EA |  | -11 |  |  |  | 100040768 |  |  |  | 139322 | 10060919100040768
10060919 | AA53 | 5001 | 261 |  | 4900142336 | 16 | 2024-09-30 | -2 | EA |  | -11 |  |  |  | 600002062 |  |  |  | 84978 | 10060919600002062
10060919 | AA53 | 5001 | 261 |  | 4900142240 | 1 | 2024-09-30 | -30 | EA |  | -165.02 |  |  |  | 500003860 |  |  |  | 216545 | 10060919500003860
10060919 | AA53 | 5001 | 261 |  | 4900142240 | 3 | 2024-09-30 | -50 | EA |  | -275.03 |  |  |  | 500003860 |  |  |  | 216545 | 10060919500003860
10060919 | AA53 | 5001 | 261 |  | 4900142525 | 1 | 2024-09-30 | -2 | EA |  | -11 |  |  |  | 100040768 |  |  |  | 139322 | 10060919100040768
10060919 | AA53 | 5001 | 261 |  | 4900142526 | 1 | 2024-09-30 | -2 | EA |  | -11 |  |  |  | 100040769 |  |  |  | 139323 | 10060919100040769
10060932 | AA53 | 5001 | 261 |  | 4900142526 | 4 | 2024-09-30 | -2 | EA |  | -29.07 |  |  |  | 100040769 |  |  |  | 139323 | 10060932100040769
10060932 | AA53 | 5001 | 261 |  | 4900142526 | 3 | 2024-09-30 | -2 | EA |  | -29.07 |  |  |  | 100040769 |  |  |  | 139323 | 10060932100040769
10218617 | AA53 | 5001 | 261 |  | 4900142525 | 6 | 2024-09-30 | -8 | EA |  | -15.88 |  |  |  | 100040768 |  |  |  | 139322 | 10218617100040768
10218617 | AA53 | 5001 | 261 |  | 4900142526 | 2 | 2024-09-30 | -8 | EA |  | -15.88 |  |  |  | 100040769 |  |  |  | 139323 | 10218617100040769
10218627 | AA53 | 5001 | 261 |  | 4900142336 | 21 | 2024-09-30 | -16 | EA |  | -129.18 |  |  |  | 600002062 |  |  |  | 84978 | 10218627600002062
10060887 | AA53 | 5001 | 261 |  | 4900142877 | 3 | 2024-10-01 | -1 | EA |  | -10.28 |  |  |  | 200091443 |  |  |  | 129721 | 10060887200091443
10060887 | AA53 | 5001 | 261 |  | 4900142845 | 4 | 2024-10-01 | -6 | EA |  | -61.69 |  |  |  | 200091445 |  |  |  | 129723 | 10060887200091445
10060888 | AA53 | 5001 | 261 |  | 4900143246 | 1 | 2024-10-01 | -2 | EA |  | -20.9 |  |  |  | 200079507 |  |  |  | 113863 | 10060888200079507
10060888 | AA53 | 5001 | 261 |  | 4900143267 | 1 | 2024-10-01 | -3 | EA |  | -31.35 |  |  |  | 200088589 |  |  |  | 126838 | 10060888200088589
10060888 | AA53 | 5001 | 261 |  | 4900143266 | 1 | 2024-10-01 | -3 | EA |  | -31.35 |  |  |  | 200088515 |  |  |  | 126824 | 10060888200088515
10060901 | AA53 | 5001 | 261 |  | 4900142870 | 4 | 2024-10-01 | -4 | EA |  | -46.86 |  |  |  | 100084639 |  |  |  | 266681 | 10060901100084639
10060901 | AA53 | 5001 | 261 |  | 4900142869 | 2 | 2024-10-01 | -4 | EA |  | -46.86 |  |  |  | 100081087 |  |  |  | 252341 | 10060901100081087
10060902 | AA53 | 5001 | 261 |  | 4900142870 | 5 | 2024-10-01 | -4 | EA |  | -65.32 |  |  |  | 100084639 |  |  |  | 266681 | 10060902100084639
10060904 | AA53 | 5001 | 261 |  | 4900142870 | 8 | 2024-10-01 | -4 | EA |  | -100.26 |  |  |  | 100084639 |  |  |  | 266681 | 10060904100084639
10060919 | AA53 | 5001 | 261 |  | 4900142869 | 1 | 2024-10-01 | -4 | EA |  | -22 |  |  |  | 100081087 |  |  |  | 252341 | 10060919100081087
10060919 | AA53 | 5001 | 261 |  | 4900142864 | 1 | 2024-10-01 | -2 | EA |  | -11 |  |  |  | 100047694 |  |  |  | 146208 | 10060919100047694
10060919 | AA53 | 5001 | 261 |  | 4900143218 | 1 | 2024-10-01 | -4 | EA |  | -22 |  |  |  | 100074842 |  |  |  | 227541 | 10060919100074842
10060919 | AA53 | 5001 | 261 |  | 4900142870 | 3 | 2024-10-01 | -4 | EA |  | -22 |  |  |  | 100084639 |  |  |  | 266681 | 10060919100084639
10060919 | AA53 | 5001 | 261 |  | 4900142864 | 3 | 2024-10-01 | -2 | EA |  | -11 |  |  |  | 100047694 |  |  |  | 146208 | 10060919100047694
10060932 | AA53 | 5001 | 261 |  | 4900142863 | 2 | 2024-10-01 | -2 | EA |  | -29.07 |  |  |  | 100047693 |  |  |  | 146207 | 10060932100047693
10060932 | AA53 | 5001 | 261 |  | 4900142863 | 1 | 2024-10-01 | -2 | EA |  | -29.07 |  |  |  | 100047693 |  |  |  | 146207 | 10060932100047693
10218613 | AA53 | 5001 | 261 |  | 4900142847 | 21 | 2024-10-01 | -8 | EA |  | -24.82 |  |  |  | 600001725 |  |  |  | 84580 | 10218613600001725
10218617 | AA53 | 5001 | 261 |  | 4900142864 | 4 | 2024-10-01 | -8 | EA |  | -15.88 |  |  |  | 100047694 |  |  |  | 146208 | 10218617100047694
10218625 | AA53 | 5001 | 261 |  | 4900143135 | 1 | 2024-10-01 | -16 | EA |  | -110.08 |  |  |  | 100038054 |  |  |  | 136586 | 10218625100038054
10218625 | AA53 | 5001 | 261 |  | 4900143131 | 1 | 2024-10-01 | -16 | EA |  | -110.08 |  |  |  | 100037720 |  |  |  | 136244 | 10218625100037720
10218625 | AA53 | 5001 | 261 |  | 4900143079 | 1 | 2024-10-01 | -32 | EA |  | -220.16 |  |  |  | 100036312 |  |  |  | 134813 | 10218625100036312
10218626 | AA53 | 5001 | 261 |  | 4900143030 | 1 | 2024-10-01 | -8 | EA |  | -61.46 |  |  |  | 100033006 |  |  |  | 131510 | 10218626100033006
10218628 | AA53 | 5001 | 261 |  | 4900143030 | 2 | 2024-10-01 | -8 | EA |  | -63.76 |  |  |  | 100033006 |  |  |  | 131510 | 10218628100033006
10060886 | AA53 | 5001 | 261 |  | 4900143753 | 1 | 2024-10-02 | -20 | EA |  | -136.8 |  |  |  | 600001880 |  |  |  | 84775 | 10060886600001880
10592509 | AA53 | 5001 | 261 |  | 4900144431 | 44 | 2024-10-03 | -20 | EA |  | -652.6 |  |  |  | 600003189 |  |  |  | 248102 | 10592509600003189
10060885 | AA53 | 5001 | 261 |  | 4900148930 | 3 | 2024-10-08 | -50 | EA |  | -238.83 |  |  |  | 200054623 |  |  |  | 88932 | 10060885200054623
10060887 | AA53 | 5001 | 261 |  | 4900148931 | 1 | 2024-10-08 | -1 | EA |  | -10.28 |  |  |  | 200054623 |  |  |  | 88932 | 10060887200054623
10060887 | AA53 | 5001 | 261 |  | 4900148930 | 1 | 2024-10-08 | -1 | EA |  | -10.28 |  |  |  | 200054623 |  |  |  | 88932 | 10060887200054623
10060902 | AA53 | 5001 | 261 |  | 4900148380 | 1 | 2024-10-08 | -1 | EA |  | -16.33 |  |  |  | 200058585 |  |  |  | 92873 | 10060902200058585
10060902 | AA53 | 5001 | 261 |  | 4900148980 | 1 | 2024-10-08 | -1 | EA |  | -16.33 |  |  |  | 200089478 |  |  |  | 127736 | 10060902200089478
10060902 | AA53 | 5001 | 261 |  | 4900148979 | 6 | 2024-10-08 | -4 | EA |  | -65.32 |  |  |  | 200089478 |  |  |  | 127736 | 10060902200089478
10060901 | AA53 | 5001 | 261 |  | 4900149702 | 1 | 2024-10-09 | -4 | EA |  | -46.86 |  |  |  | 100078851 |  |  |  | 243481 | 10060901100078851
10060919 | AA53 | 5001 | 261 |  | 4900149416 | 1 | 2024-10-09 | -4 | EA |  | -22 |  |  |  | 100078851 |  |  |  | 243481 | 10060919100078851
10218617 | AA53 | 5001 | 261 |  | 4900149235 | 1 | 2024-10-09 | -8 | EA |  | -15.88 |  |  |  | 200089478 |  |  |  | 127736 | 10218617200089478
10058828 | AA53 | 5001 | 261 |  | 4900149697 | 1 | 2024-10-10 | -2 | EA |  | -58.39 |  |  |  | 100040131 |  |  |  | 138632 | 10058828100040131
10060887 | AA53 | 5001 | 261 |  | 4900150089 | 1 | 2024-10-10 | -1 | EA |  | -10.28 |  |  |  | 200056096 |  |  |  | 90445 | 10060887200056096
10305744 | AA53 | 5001 | 261 |  | 4900150089 | 2 | 2024-10-10 | -1 | EA |  | -9.27 |  |  |  | 200056096 |  |  |  | 90445 | 10305744200056096
10052676 | AA53 | 5001 | 261 |  | 4900156920 | 1 | 2024-10-22 | -4 | EA |  | -10297.84 |  |  |  | 600002862 |  |  |  | 216479 | 10052676600002862
10052685 | AA53 | 5001 | 261 |  | 4900157273 | 1 | 2024-10-22 | -1 | EA |  | -5952.95 |  |  |  | 600002862 |  |  |  | 216479 | 10052685600002862
10059968 | AA53 | 5001 | 261 |  | 4900157769 | 2 | 2024-10-22 | -2 | EA |  | -7.83 |  |  |  | 100073567 |  |  |  | 223483 | 10059968100073567
10059971 | AA53 | 5001 | 261 |  | 4900156786 | 1 | 2024-10-22 | -2 | EA |  | -28.5 |  |  |  | 100038054 |  |  |  | 136586 | 10059971100038054
10060887 | AA53 | 5001 | 261 |  | 4900157635 | 1 | 2024-10-22 | -1 | EA |  | -10.28 |  |  |  | 200086360 |  |  |  | 124578 | 10060887200086360
10060887 | AA53 | 5001 | 261 |  | 4900157634 | 1 | 2024-10-22 | -1 | EA |  | -10.28 |  |  |  | 200086361 |  |  |  | 124579 | 10060887200086361
10060919 | AA53 | 5001 | 261 |  | 4900157769 | 1 | 2024-10-22 | -2 | EA |  | -11 |  |  |  | 100073567 |  |  |  | 223483 | 10060919100073567
10305744 | AA53 | 5001 | 261 |  | 4900156983 | 1 | 2024-10-22 | -1 | EA |  | -9.27 |  |  |  | 200089031 |  |  |  | 127309 | 10305744200089031
10048594 | AA53 | 5001 | 261 |  | 4900157930 | 1 | 2024-10-23 | -7 | EA |  | -1966.3 |  |  |  | 600002862 |  |  |  | 216479 | 10048594600002862
10048596 | AA53 | 5001 | 261 |  | 4900157930 | 2 | 2024-10-23 | -5 | EA |  | -2751 |  |  |  | 600002862 |  |  |  | 216479 | 10048596600002862
10049295 | AA53 | 5001 | 261 |  | 4900157930 | 3 | 2024-10-23 | -1 | EA |  | -2574.46 |  |  |  | 600002862 |  |  |  | 216479 | 10049295600002862
10053011 | AA53 | 5001 | 261 |  | 4900157930 | 4 | 2024-10-23 | -1 | EA |  | -541.03 |  |  |  | 600002862 |  |  |  | 216479 | 10053011600002862
10053014 | AA53 | 5001 | 261 |  | 4900157930 | 5 | 2024-10-23 | -1 | EA |  | -2367.78 |  |  |  | 600002862 |  |  |  | 216479 | 10053014600002862
10058202 | AA53 | 5001 | 261 |  | 4900157930 | 6 | 2024-10-23 | -20 | EA |  | -35 |  |  |  | 600002862 |  |  |  | 216479 | 10058202600002862
10058205 | AA53 | 5001 | 261 |  | 4900157930 | 7 | 2024-10-23 | -8 | EA |  | -47.36 |  |  |  | 600002862 |  |  |  | 216479 | 10058205600002862
10058222 | AA53 | 5001 | 261 |  | 4900157930 | 8 | 2024-10-23 | -13 | EA |  | -143.54 |  |  |  | 600002862 |  |  |  | 216479 | 10058222600002862
10058262 | AA53 | 5001 | 261 |  | 4900157930 | 9 | 2024-10-23 | -16 | EA |  | -441.28 |  |  |  | 600002862 |  |  |  | 216479 | 10058262600002862
10058828 | AA53 | 5001 | 261 |  | 4900157930 | 10 | 2024-10-23 | -2 | EA |  | -61 |  |  |  | 600002862 |  |  |  | 216479 | 10058828600002862
10059968 | AA53 | 5001 | 261 |  | 4900157930 | 11 | 2024-10-23 | -2 | EA |  | -7.83 |  |  |  | 600002862 |  |  |  | 216479 | 10059968600002862
10059972 | AA53 | 5001 | 261 |  | 4900157930 | 12 | 2024-10-23 | -8 | EA |  | -224.14 |  |  |  | 600002862 |  |  |  | 216479 | 10059972600002862
10060902 | AA53 | 5001 | 261 |  | 4900158116 | 1 | 2024-10-23 | -1 | EA |  | -16.4 |  |  |  | 200089478 |  |  |  | 127736 | 10060902200089478
10060902 | AA53 | 5001 | 261 |  | 4900158118 | 1 | 2024-10-23 | -1 | EA |  | -16.41 |  |  |  | 200062018 |  |  |  | 0 | 10060902200062018
10060902 | AA53 | 5001 | 261 |  | 4900158117 | 3 | 2024-10-23 | -1 | EA |  | -16.4 |  |  |  | 200062016 |  |  |  | 96364 | 10060902200062016
10060902 | AA53 | 5001 | 261 |  | 4900158115 | 1 | 2024-10-23 | -4 | EA |  | -65.61 |  |  |  | 600002862 |  |  |  | 216479 | 10060902600002862
10060902 | AA53 | 5001 | 261 |  | 4900158117 | 2 | 2024-10-23 | -1 | EA |  | -16.41 |  |  |  | 200073749 |  |  |  | 108084 | 10060902200073749
10060902 | AA53 | 5001 | 261 |  | 4900158117 | 1 | 2024-10-23 | -1 | EA |  | -16.4 |  |  |  | 200074037 |  |  |  | 108372 | 10060902200074037
10060906 | AA53 | 5001 | 261 |  | 4900157930 | 13 | 2024-10-23 | -4 | EA |  | -161.04 |  |  |  | 600002862 |  |  |  | 216479 | 10060906600002862
10060919 | AA53 | 5001 | 261 |  | 4900157821 | 2 | 2024-10-23 | -1 | EA |  | -5.5 |  |  |  | 200091798 |  |  |  | 130087 | 10060919200091798
10060934 | AA53 | 5001 | 261 |  | 4900157930 | 14 | 2024-10-23 | -2 | EA |  | -48.48 |  |  |  | 600002862 |  |  |  | 216479 | 10060934600002862
10060939 | AA53 | 5001 | 261 |  | 4900157930 | 15 | 2024-10-23 | -12 | EA |  | -903 |  |  |  | 600002862 |  |  |  | 216479 | 10060939600002862
10061003 | AA53 | 5001 | 261 |  | 4900157930 | 16 | 2024-10-23 | -2 | EA |  | -562.26 |  |  |  | 600002862 |  |  |  | 216479 | 10061003600002862
10202329 | AA53 | 5001 | 261 |  | 4900158112 | 2 | 2024-10-23 | -1 | EA |  | -56.5 |  |  |  | 600001645 |  |  |  | 84540 | 10202329600001645
10202352 | AA53 | 5001 | 261 |  | 4900157930 | 17 | 2024-10-23 | -1 | EA |  | -2046.16 |  |  |  | 600002862 |  |  |  | 216479 | 10202352600002862
10218617 | AA53 | 5001 | 261 |  | 4900157930 | 18 | 2024-10-23 | -48 | EA |  | -95.25 |  |  |  | 600002862 |  |  |  | 216479 | 10218617600002862
10218657 | AA53 | 5001 | 261 |  | 4900157930 | 19 | 2024-10-23 | -40 | EA |  | -966.8 |  |  |  | 600002862 |  |  |  | 216479 | 10218657600002862
10219976 | AA53 | 5001 | 261 |  | 4900157930 | 20 | 2024-10-23 | -24 | EA |  | -24 |  |  |  | 600002862 |  |  |  | 216479 | 10219976600002862
10220455 | AA53 | 5001 | 261 |  | 4900157930 | 21 | 2024-10-23 | -8 | EA |  | -146.8 |  |  |  | 600002862 |  |  |  | 216479 | 10220455600002862
10223374 | AA53 | 5001 | 261 |  | 4900157930 | 22 | 2024-10-23 | -20 | EA |  | -203 |  |  |  | 600002862 |  |  |  | 216479 | 10223374600002862
10258213 | AA53 | 5001 | 261 |  | 4900158139 | 1 | 2024-10-23 | -2 | SHT |  | -1673.88 |  |  |  | 600002112 |  |  |  | 84994 | 10258213600002112
11400805 | AA53 | 5001 | 261 |  | 4900157930 | 23 | 2024-10-23 | -1 | EA |  | -961 |  |  |  | 600002862 |  |  |  | 216479 | 11400805600002862
11400808 | AA53 | 5001 | 261 |  | 4900157930 | 24 | 2024-10-23 | -1 | EA |  | -2278 |  |  |  | 600002862 |  |  |  | 216479 | 11400808600002862
10060901 | AA53 | 5001 | 261 |  | 4900159148 | 7 | 2024-10-25 | -8 | EA |  | -93.73 |  |  |  | 500003830 |  |  |  | 217346 | 10060901500003830
10060885 | AA53 | 5001 | 261 |  | 4900159925 | 1 | 2024-10-26 | -1 | EA |  | -4.78 |  |  |  | 100035140 |  |  |  | 133624 | 10060885100035140
10060885 | AA53 | 5001 | 261 |  | 4900159928 | 1 | 2024-10-26 | -1 | EA |  | -4.78 |  |  |  | 100035140 |  |  |  | 133624 | 10060885100035140
10219526 | AA53 | 5001 | 261 |  | 4900160229 | 1 | 2024-10-27 | -32 | EA |  | -173.57 |  |  |  | 200089478 |  |  |  | 127736 | 10219526200089478
10060904 | AA53 | 5001 | 261 |  | 4900160289 | 1 | 2024-10-28 | -4 | EA |  | -100.2 |  |  |  | 100081087 |  |  |  | 252341 | 10060904100081087
10060885 | AA53 | 5001 | 261 |  | 4900161818 | 1 | 2024-10-30 | -400 | EA |  | -1911.55 |  |  |  | 500004232 |  |  |  | 252576 | 10060885500004232
10060885 | AA53 | 5001 | 261 |  | 4900162574 | 1 | 2024-10-31 | -2 | EA |  | -9.56 |  |  |  | 100082798 |  |  |  | 258035 | 10060885100082798
10060885 | AA53 | 5001 | 261 |  | 4900162241 | 1 | 2024-10-31 | -2 | EA |  | -9.56 |  |  |  | 200079507 |  |  |  | 113863 | 10060885200079507
10060888 | AA53 | 5001 | 261 |  | 4900162245 | 1 | 2024-10-31 | -1 | EA |  | -10.45 |  |  |  | 100036312 |  |  |  | 134813 | 10060888100036312
10060888 | AA53 | 5001 | 261 |  | 4900162243 | 1 | 2024-10-31 | -3 | EA |  | -31.35 |  |  |  | 200088587 |  |  |  | 126836 | 10060888200088587
10060887 | AA53 | 5001 | 261 |  | 4900162801 | 24 | 2024-11-01 | -2 | EA |  | -20.57 |  |  |  | 100033645 |  |  |  | 132137 | 10060887100033645
10060888 | AA53 | 5001 | 261 |  | 4900162767 | 1 | 2024-11-01 | -1 | EA |  | -10.45 |  |  |  | 100031833 |  |  |  | 0 | 10060888100031833
10060892 | AA53 | 5001 | 261 |  | 4900162802 | 1 | 2024-11-01 | -4 | EA |  | -125.14 |  |  |  | 100033829 |  |  |  | 132330 | 10060892100033829
10218632 | AA53 | 5001 | 261 |  | 4900162801 | 8 | 2024-11-01 | -12 | EA |  | -81.52 |  |  |  | 100032559 |  |  |  | 131077 | 10218632100032559
10060888 | AA53 | 5001 | 261 |  | 4900166330 | 1 | 2024-11-06 | -2 | EA |  | -20.9 |  |  |  | 200088588 |  |  |  | 126837 | 10060888200088588
10060888 | AA53 | 5001 | 261 |  | 4900166305 | 1 | 2024-11-06 | -2 | EA |  | -20.9 |  |  |  | 100037720 |  |  |  | 136244 | 10060888100037720
10251654 | AA53 | 5001 | 261 |  | 4900166909 | 1 | 2024-11-07 | -4 | EA |  | -36 |  |  |  | 600001880 |  |  |  | 84775 | 10251654600001880
10058828 | AA53 | 5001 | 261 |  | 4900168470 | 1 | 2024-11-08 | -14 | EA |  | -428.41 |  |  |  | 100040131 |  |  |  | 138632 | 10058828100040131
10060885 | AA53 | 5001 | 261 |  | 4900168192 | 1 | 2024-11-08 | -1 | EA |  | -4.78 |  |  |  | 200089320 |  |  |  | 127538 | 10060885200089320
10060885 | AA53 | 5001 | 261 |  | 4900168240 | 1 | 2024-11-08 | -2 | EA |  | -9.56 |  |  |  | 200089320 |  |  |  | 127538 | 10060885200089320
10060885 | AA53 | 5001 | 261 |  | 4900168357 | 1 | 2024-11-08 | -30 | EA |  | -143.37 |  |  |  | 500003847 |  |  |  | 216567 | 10060885500003847
10060885 | AA53 | 5001 | 261 |  | 4900168190 | 1 | 2024-11-08 | -2 | EA |  | -9.56 |  |  |  | 500003860 |  |  |  | 216545 | 10060885500003860
10060902 | AA53 | 5001 | 261 |  | 4900170875 | 1 | 2024-11-12 | -4 | EA |  | -66.76 |  |  |  | 200082323 |  |  |  | 118184 | 10060902200082323
10060902 | AA53 | 5001 | 261 |  | 4900171853 | 1 | 2024-11-13 | -1 | EA |  | -16.69 |  |  |  | 200061073 |  |  |  | 95422 | 10060902200061073
10060934 | AA53 | 5001 | 261 |  | 4900171852 | 1 | 2024-11-13 | -2 | EA |  | -48.34 |  |  |  | 200156880 |  |  |  | 249626 | 10060934200156880
10058249 | AA53 | 5001 | 261 |  | 4900172231 | 7 | 2024-11-14 | -4 | EA |  | -77.44 |  |  |  | 600002862 |  |  |  | 216479 | 10058249600002862
10058252 | AA53 | 5001 | 261 |  | 4900172231 | 8 | 2024-11-14 | -8 | EA |  | -179.12 |  |  |  | 600002862 |  |  |  | 216479 | 10058252600002862
10060888 | AA53 | 5001 | 261 |  | 4900172291 | 1 | 2024-11-14 | -7 | EA |  | -73.15 |  |  |  | 200090298 |  |  |  | 128587 | 10060888200090298
10060919 | AA53 | 5001 | 261 |  | 4900172243 | 3 | 2024-11-14 | -2 | EA |  | -11 |  |  |  | 100074118 |  |  |  | 0 | 10060919100074118
10060919 | AA53 | 5001 | 261 |  | 4900172243 | 1 | 2024-11-14 | -2 | EA |  | -11 |  |  |  | 100074118 |  |  |  | 0 | 10060919100074118
10251654 | AA53 | 5001 | 261 |  | 4900172231 | 9 | 2024-11-14 | -6 | EA |  | -54 |  |  |  | 600002862 |  |  |  | 216479 | 10251654600002862
10592509 | AA53 | 5001 | 261 |  | 4900172231 | 10 | 2024-11-14 | -50 | EA |  | -1631.5 |  |  |  | 600002862 |  |  |  | 216479 | 10592509600002862
10060885 | AA53 | 5001 | 261 |  | 4900173092 | 2 | 2024-11-16 | -2 | EA |  | -9.56 |  |  |  | 100038677 |  |  |  | 137261 | 10060885100038677
10060885 | AA53 | 5001 | 261 |  | 4900173092 | 1 | 2024-11-16 | -2 | EA |  | -9.56 |  |  |  | 100038677 |  |  |  | 137261 | 10060885100038677
10060919 | AA53 | 5001 | 261 |  | 4900173880 | 3 | 2024-11-17 | -12 | EA |  | -66.03 |  |  |  | 100077012 |  |  |  | 235309 | 10060919100077012
10060932 | AA53 | 5001 | 261 |  | 4900173880 | 2 | 2024-11-17 | -4 | EA |  | -58.15 |  |  |  | 100077012 |  |  |  | 235309 | 10060932100077012
10060885 | AA53 | 5001 | 261 |  | 4900175405 | 2 | 2024-11-19 | -6 | EA |  | -28.67 |  |  |  | 100072575 |  |  |  | 219261 | 10060885100072575
10060885 | AA53 | 5001 | 261 |  | 4900175304 | 1 | 2024-11-19 | -4 | EA |  | -19.12 |  |  |  | 200091445 |  |  |  | 129723 | 10060885200091445
10060885 | AA53 | 5001 | 261 |  | 4900175266 | 1 | 2024-11-19 | -1 | EA |  | -4.78 |  |  |  | 200087905 |  |  |  | 0 | 10060885200087905
10060885 | AA53 | 5001 | 261 |  | 4900175263 | 1 | 2024-11-19 | -3 | EA |  | -14.34 |  |  |  | 100044332 |  |  |  | 142816 | 10060885100044332
10060902 | AA53 | 5001 | 261 |  | 4900175277 | 1 | 2024-11-19 | -4 | EA |  | -66.77 |  |  |  | 100078851 |  |  |  | 243481 | 10060902100078851
10060904 | AA53 | 5001 | 261 |  | 4900175301 | 1 | 2024-11-19 | -6 | EA |  | -150.09 |  |  |  | 100085531 |  |  |  | 269371 | 10060904100085531
10060904 | AA53 | 5001 | 261 |  | 4900175278 | 1 | 2024-11-19 | -4 | EA |  | -100.06 |  |  |  | 100078851 |  |  |  | 243481 | 10060904100078851
10060906 | AA53 | 5001 | 261 |  | 4900175300 | 2 | 2024-11-19 | -2 | EA |  | -80.52 |  |  |  | 100082798 |  |  |  | 258035 | 10060906100082798
10060934 | AA53 | 5001 | 261 |  | 4900175302 | 1 | 2024-11-19 | -6 | EA |  | -145.01 |  |  |  | 100085983 |  |  |  | 271629 | 10060934100085983
10060919 | AA53 | 5001 | 261 |  | 4900175925 | 2 | 2024-11-20 | -1 | EA |  | -5.5 |  |  |  | 100047153 |  |  |  | 145654 | 10060919100047153
10048592 | AA53 | 5001 | 261 |  | 4900176357 | 1 | 2024-11-21 | -2 | EA |  | -139.75 |  |  |  | 600002862 |  |  |  | 216479 | 10048592600002862
10059971 | AA53 | 5001 | 261 |  | 4900176888 | 2 | 2024-11-22 | -3 | EA |  | -42.75 |  |  |  | 100035120 |  |  |  | 133612 | 10059971100035120
10060885 | AA53 | 5001 | 261 |  | 4900176886 | 7 | 2024-11-22 | -4 | EA |  | -19.12 |  |  |  | 100034809 |  |  |  | 133330 | 10060885100034809
10060885 | AA53 | 5001 | 261 |  | 4900176886 | 3 | 2024-11-22 | -4 | EA |  | -19.12 |  |  |  | 100034809 |  |  |  | 133330 | 10060885100034809
10060885 | AA53 | 5001 | 261 |  | 4900176880 | 3 | 2024-11-22 | -6 | EA |  | -28.67 |  |  |  | 100033829 |  |  |  | 132330 | 10060885100033829
10060892 | AA53 | 5001 | 261 |  | 4900176886 | 9 | 2024-11-22 | -2 | EA |  | -62.8 |  |  |  | 100034809 |  |  |  | 133330 | 10060892100034809
10060894 | AA53 | 5001 | 261 |  | 4900176880 | 1 | 2024-11-22 | -4 | EA |  | -258.6 |  |  |  | 100033829 |  |  |  | 132330 | 10060894100033829
10060902 | AA53 | 5001 | 261 |  | 4900176926 | 3 | 2024-11-22 | -3 | EA |  | -50.09 |  |  |  | 100040125 |  |  |  | 138626 | 10060902100040125
10060905 | AA53 | 5001 | 261 |  | 4900176914 | 4 | 2024-11-22 | -2 | EA |  | -63.33 |  |  |  | 100038756 |  |  |  | 137290 | 10060905100038756
10060919 | AA53 | 5001 | 261 |  | 4900176858 | 1 | 2024-11-22 | -2 | EA |  | -11 |  |  |  | 100032858 |  |  |  | 131362 | 10060919100032858
10218625 | AA53 | 5001 | 261 |  | 4900176888 | 1 | 2024-11-22 | -24 | EA |  | -165.12 |  |  |  | 100035120 |  |  |  | 133612 | 10218625100035120
10218626 | AA53 | 5001 | 261 |  | 4900176928 | 1 | 2024-11-22 | -8 | EA |  | -41.41 |  |  |  | 100040128 |  |  |  | 138629 | 10218626100040128
10218626 | AA53 | 5001 | 261 |  | 4900176927 | 1 | 2024-11-22 | -8 | EA |  | -41.42 |  |  |  | 100040127 |  |  |  | 138628 | 10218626100040127
10218628 | AA53 | 5001 | 261 |  | 4900176926 | 2 | 2024-11-22 | -12 | EA |  | -95.64 |  |  |  | 100040125 |  |  |  | 138626 | 10218628100040125
10059972 | AA53 | 5001 | 261 |  | 4900177557 | 1 | 2024-11-23 | -6 | EA |  | -195.86 |  |  |  | 100042790 |  |  |  | 141311 | 10059972100042790
10060886 | AA53 | 5001 | 261 |  | 4900177516 | 1 | 2024-11-23 | -4 | EA |  | -27.3 |  |  |  | 600002862 |  |  |  | 216479 | 10060886600002862
10218626 | AA53 | 5001 | 261 |  | 4900177557 | 2 | 2024-11-23 | -20 | EA |  | -103.54 |  |  |  | 100042790 |  |  |  | 141311 | 10218626100042790
10218632 | AA53 | 5001 | 261 |  | 4900177554 | 1 | 2024-11-23 | -12 | EA |  | -82.65 |  |  |  | 100041903 |  |  |  | 140387 | 10218632100041903