| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10262746 | ADAPTOR,FLT;ARLON TXSL5ASLEEVE | 2 | EA | 3 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 330 cannot be changed 90028419 item 2570 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 330 | 0 | EA | 102000000030113 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2570 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262746 | ADAPTOR,FLT;ARLON TXSL5ASLEEVE | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2570 |  |  | DG1 |  | C5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 330 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2600 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2240 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10262747 | ELEMENT,FLT;OIL,GF,ARLON TXWL5AGDL03 | 2 | EA | 3 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 329 cannot be changed 90028419 item 2560 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 329 | 0 | EA | 102000000030090 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262747 | ELEMENT,FLT;OIL,GF,ARLON TXWL5AGDL03 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2560 |  |  | DG1 |  | C5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 329 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2590 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0120 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 1 | EA | 16 | 0 | 8 | 1 | EA | 19.02 - At KGP | Supply for Order 100039666, Item 9 cannot be changed 90024949 item 80 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122883 | 9026893 | 05 | Preparation | 0000138170 | 9 | 0 | EA | 102000000027394 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391260_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056487 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230018_2025_0005 | 2025-03-01 | 144PT60 | 5000391260_2025_0003 | 0 | 2 | 0 | 90024949 | 1 | 0 | 180122911/180122883 | 2 | 0 | 0 | X | L | 4900230018 | 2025 |  | 5000391260 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026893_0080 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 9 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0020 | 0150 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 1 | EA | 16 | 0 | 8 | 1 | EA | 19.02 - At KGP | Supply for Order 100039741, Item 10 cannot be changed 9026899 item 90 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122896 | 9026899 | 05 | Preparation | 0000138265 | 10 | 0 | EA | 102000000027395 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AU01P08-DG | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391272_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056493 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900229979_2025_0007 | 2025-03-01 | 344PT504 | 5000391272_2025_0004 | 0 | 2 | 0 | 90024952 | 1 | 0 | 180122896 | 2 | 0 | 0 | X | L | 4900229979 | 2025 |  | 5000391272 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 2024-01-01 | W |  | 0020 | Reconnect & Deisolate | INT | Reconnect & Deisolate |  | Management of Change | 9026899_0090 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 10 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 | 30 | 30 | 5300002054 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2024-03-01 | 2025-05-31 | 2025-06-01 | QMI | 100047965 | 0010 | 0030 | 100047965 | MOC-141289 Transmitter Replace 144FT84 | AA53.144FT84 | METER,DP FLOW,1V4450 OUTLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 1 | EA | 16 | 0 | 8 | 1 | EA | 19.02 - At KGP | Supply for Order 100047965, Item 3 cannot be changed 180009111 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300001827 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180009111 | 90001493 | 05 | Preparation | 0000146486 | 3 | 0 | EA |  |  | 102000000002681 | 01-Road |  | 3-In Transit |  | WorkPackLink | QMP08CAGE | KCM-LNG | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000030950_2024 | 0 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2025-05-31 |  |  | 2025-03-01 |  |  | 100000002887 | 1020 | 2024-12-30 | 1 |  | 2024-03-06 | 4900035070_2024_0005 | 2024-03-04 | 144FT84 | 5000030950_2024_0003 | 0 | 2 | 0 | 90001493 | 1 | 0 | 180009111 | 2 | 0 | 0 | X | L | 4900035070 | 2024 |  | 5000030950 | 2024 | 0 |  | 2024-03-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Engineering Query/Management of Change | 90001493_0030 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 | 4900193788_2024 | 25SDLN1 | MJ | 1000000809 | AU1072 | 1000145855 | S002 | 30 | 30 | 5300001827 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-03-01 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146486 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-06-01 | 2025-05-31 | 2025-05-31 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-05 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0090 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 16.12 - AT KGP | Supply for Order 100039665, Item 21 cannot be changed 180092338 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180092338 | 9019265 | 05 | Preparation | 0000138169 | 21 | 0 | EA | 102000000023625 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000276551_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000040088 | 1020 | 2024-03-07 | 1 |  | 2024-11-12 | 4900170489_2024_0003 | 2024-12-01 | 144PT504 | 5000276551_2024_0002 | 0 | 2 | 0 | 90023592 | 1 | 0 | 180092338/180122921 | 2 | 0 | 0 | X | L | 4900170489 | 2024 |  | 5000276551 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-11-05 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9019265_0060 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 21 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 | 30 | 30 | 5300017367 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-05 | 2024-12-01 | 2024-12-13 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0110 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 19.02 - At KGP | Supply for Order 100039665, Item 23 cannot be changed 90026772 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122905 | 90026772 | 05 | Preparation | 0000138169 | 23 | 0 | EA | 102000000029481 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000391271_2025 | 0 | 17 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-18 |  |  | 100000056497 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230035_2025_0001 | 2024-12-18 | 144PT504 | 5000391271_2025_0001 | 0 | 2 | 0 | 90026772 | 1 | 0 | 180122905 | 2 | 0 | 0 | X | L | 4900230035 | 2025 |  | 5000391271 | 2025 | 0 |  | 2024-12-13 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-12-13 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 90026772_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 23 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 | 30 | 30 | 5300017367 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-12-13 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0090 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 19.02 - At KGP | Supply for Order 100039666, Item 7 cannot be changed 90024949 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122883 | 9026893 | 05 | Preparation | 0000138170 | 7 | 0 | EA | 102000000027389 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391260_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056487 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230018_2025_0003 | 2025-03-01 | 144PT60 | 5000391260_2025_0002 | 0 | 2 | 0 | 90024949 | 1 | 0 | 180122911/180122883 | 2 | 0 | 0 | X | L | 4900230018 | 2025 |  | 5000391260 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026893_0060 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 7 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-07 | 2024-12-01 | 2024-12-13 | 2025-03-04 | 2025-03-08 | INLEC | 100039667 | 0010 | 0140 | 100039667 | MOC-141259 TX Replace 144PT059 | AA53.144PT059 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 19.02 - At KGP | Supply for Order 100039667, Item 14 cannot be changed 90026773 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017556 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122913 | 90026773 | 05 | Preparation | 0000138171 | 14 | 0 | EA | 102000000029482 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000391262_2025 | 0 | 17 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-04 |  |  | 2024-12-18 |  |  | 100000056800 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900229997_2025_0001 | 2024-12-18 | 144PT059 | 5000391262_2025_0001 | 0 | 2 | 0 | 90026773 | 1 | 0 | 180122913 | 2 | 0 | 0 | X | L | 4900229997 | 2025 |  | 5000391262 | 2025 | 0 |  | 2024-12-13 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-12-13 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 90026773_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 14 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137582 | S002 | 30 | 30 | 5300017556 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-12-13 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138171 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-08 | 2025-03-04 | 2025-03-04 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-04 | 2025-03-08 | INLEC | 100039667 | 0010 | 0120 | 100039667 | MOC-141259 TX Replace 144PT059 | AA53.144PT059 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | AT KGP | Supply for Order 100039667, Item 12 cannot be changed 180092339 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017556 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180092339 | 9019266 | 05 | Preparation | 0000138171 | 12 | 0 | EA | 102000000023622 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000276518_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-04 |  |  | 2024-12-01 |  |  | 100000040089 | 1020 | 2024-03-07 | 1 |  | 2024-11-12 | 4900170554_2024_0001 | 2024-12-01 | 144PT059 | 5000276518_2024_0001 | 0 | 2 | 0 | 90023934 | 1 | 0 | 180092339 | 2 | 0 | 0 | X | L | 4900170554 | 2024 |  | 5000276518 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9019266_0050 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 12 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137582 | S002 | 30 | 30 | 5300017556 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138171 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-08 | 2025-03-04 | 2025-03-04 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-21 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-03 | INLEC | 100039668 | 0030 | 0020 | 100039668 | MOC-141262 Transmitter Replace 244PT58 | AA53.244PT58 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 19.02 - At KGP | Supply for Order 100039668, Item 2 cannot be changed 90025183 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300018207 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122904 | 9027002 | 05 | Preparation | 0000138172 | 2 | 0 | EA | 102000000025831 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-21 | GRST-5000391251_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056496 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230023_2025_0001 | 2024-12-01 | 244PT58 | 5000391251_2025_0001 | 0 | 2 | 0 | 90025183 | 1 | 0 | 180122904/180122906 | 2 | 0 | 0 | X | L | 4900230023 | 2025 |  | 5000391251 | 2025 | 0 |  | 2024-11-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-11-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9027002_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137583 | S002 | 30 | 30 | 5300018207 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138172 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-21 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-04 | INLEC | 100039669 | 0030 | 0020 | 100039669 | MOC-146093 Pressure TX Replace 244PT501 | AA53.244PT501 | TX,PRESS K4401B-P2A/P2B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 19.02 - At KGP | Supply for Order 100039669, Item 2 cannot be changed 90025184 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300018206 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122898 | 9027000 | 05 | Preparation | 0000138173 | 2 | 0 | EA | 102000000025830 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-21 | GRST-5000391223_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056494 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230034_2025_0003 | 2024-12-01 | 244PT501 | 5000391223_2025_0002 | 0 | 2 | 0 | 90025184 | 1 | 0 | 180122898/180122901 | 2 | 0 | 0 | X | L | 4900230034 | 2025 |  | 5000391223 | 2025 | 0 |  | 2024-11-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-11-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9027000_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137584 | S002 | 30 | 30 | 5300018206 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138173 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0080 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 19.02 - At KGP | Supply for Order 100039671, Item 7 cannot be changed 9026894 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122884 | 9026894 | 05 | Preparation | 0000138175 | 7 | 0 | EA | 102000000027392 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391239_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056488 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230007_2025_0009 | 2025-03-01 | 244PT60 | 5000391239_2025_0005 | 0 | 2 | 0 | 90024950 | 1 | 0 | 180122884 | 2 | 0 | 0 | X | L | 4900230007 | 2025 |  | 5000391239 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 9026894_0060 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 7 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 | 30 | 30 | 5300002039 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0080 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 19.02 - At KGP | Supply for Order 100039740, Item 7 cannot be changed 9026897 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122888 | 9026897 | 05 | Preparation | 0000138264 | 7 | 0 | EA | 102000000027391 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391270_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056491 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230032_2025_0003 | 2025-03-01 | 344PT501 | 5000391270_2025_0002 | 0 | 2 | 0 | 90024951 | 1 | 0 | 180122920/180122888 | 2 | 0 | 0 | X | L | 4900230032 | 2025 |  | 5000391270 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026897_0060 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 7 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0010 | 0120 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 19.02 - At KGP | Supply for Order 100039741, Item 7 cannot be changed 9026899 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122896 | 9026899 | 05 | Preparation | 0000138265 | 7 | 0 | EA | 102000000027390 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391272_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056493 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900229979_2025_0005 | 2025-03-01 | 344PT504 | 5000391272_2025_0003 | 0 | 2 | 0 | 90024952 | 1 | 0 | 180122896 | 2 | 0 | 0 | X | L | 4900229979 | 2025 |  | 5000391272 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Management of Change | 9026899_0060 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 7 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 | 30 | 30 | 5300002054 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-07 | 2024-12-01 | 2024-12-13 | 2025-03-01 | 2025-03-01 | INLEC | 100047874 | 0010 | 0070 | 100047874 | MOC-124841 Transmitter Replace 114PT87 | AA53.114PIC87 | LOOP,CTRL PRESS TO E1409 SHELL OUTLET | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 100047874, Item 7 cannot be changed 90026774 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017557 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90026774 | 05 | Preparation | 0000146415 | 7 | 0 | EA | 102000000029480 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-07 | ODST-0090026774_0010 | 0 | 17 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-18 |  |  |  |  | 2022-11-30 | 0 |  | 2024-12-13 |  | 2024-12-18 | 114PT87 |  | 0 | 2 | 0 | 90026774 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-12-13 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-12-13 | W |  | 0010 | TX Pre Works | INT | TX Pre Works | 5 |  | 90026774_0010 |  |  | LN1 |  | C2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000145844 | S002 | 30 | 30 | 5300017557 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-12-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146415 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-01 | INLEC | 100047874 | 0010 | 0020 | 100047874 | MOC-124841 Transmitter Replace 114PT87 | AA53.114PIC87 | LOOP,CTRL PRESS TO E1409 SHELL OUTLET | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 4 | 1 | 14 | 1 | EA | AT KGP | Supply for Order 100047874, Item 2 cannot be changed 180092340 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017557 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180092340 | 9019267 | 05 | Preparation | 0000146415 | 2 | 0 | EA | 102000000023623 |  | 107000000000750 |  |  |  |  | WorkPackLink | P07-WAREHOUSE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000276495_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000040090 | 1020 | 2022-11-30 | 1 |  | 2024-11-12 | 4900170555_2024_0001 | 2024-12-01 | 114PT87 | 5000276495_2024_0001 | 0 | 2 | 0 | 90023935 | 1 | 0 | 180092340 | 2 | 0 | 0 | X | L | 4900170555 | 2024 |  | 5000276495 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works | 5 |  | 9019267_0020 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000145844 | S002 | 30 | 30 | 5300017557 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146415 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0080 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2 | EA | 4 | 1 | 14 | 2 | EA | 09.02 - SOH @ AA02 | Supply for Order 600001815, Item 14 cannot be changed 9027673 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180129282 | 9027673 | 07 | Execution | 0000084731 | 14 | 0 | EA |  |  | 102000000033736 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-03-13 | GRST-5000416512_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  | 100000058593 | 1020 | 2024-08-30 | 2 |  | 2025-02-25 | 4900248397_2025_0001 | 2025-03-01 | 37PT40/41 | 5000416512_2025_0001 | 0 | 2 | 0 | 90030415 | 2 | 0 | 180129282 | 2 | 0 | 0 | X | L | 4900248397 | 2025 |  | 5000416512 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 9027673_0060 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 14 |  | 0 |  | 25SDFLR | MJ | 1000005234 | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 90 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-25 |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-05-01 | 2025-05-02 | INLEC | 600001756 | 0010 | 0010 | 600001756 | MOC-119238 Replace Flare Flowmtr 37FQI41 | AA53.37FQI41 | LOOP,MASS FLOW TO FLARE A3711B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.03.2024) | 10263048 | VALVE,BALL;50MM,CL150,RF,SS,S1BEF | 4 | EA | 0 | 0 | 0 | 0 |  | 09.02 - SOH @ AA01 block stock | Supply for Order 600001756, Item 1 cannot be changed 90024972 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007842 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024972 | 07 | Execution | 0000084652 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-03-13 | ODST-0090024972_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-01 |  |  | 2025-03-01 |  |  |  |  | 2024-09-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024972 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263048 | VALVE,BALL;50MM,CL150,RF,SS,S1BEF | 2024-03-13 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90024972_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084066 | S002 | 30 | 30 | 5300007842 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84652 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-02 | 2025-05-01 | 2025-05-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0010 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.03.2024) | 10263048 | VALVE,BALL;50MM,CL150,RF,SS,S1BEF | 4 | EA | 0 | 0 | 0 | 0 |  | 09.02 - SOH @ AA01 block stock | Supply for Order 600001815, Item 1 cannot be changed 90024973 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024973 | 07 | Execution | 0000084731 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-03-13 | ODST-0090024973_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024973 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263048 | VALVE,BALL;50MM,CL150,RF,SS,S1BEF | 2024-03-13 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90024973_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SD4401 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 100035121 | 0020 | 0020 | 100035121 | Vibration Probe Replace 244XE505X | AA53.FAR7CM6 | PANEL,SYSTEM CABINET,CPMS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 1 | EA | 35 | 3 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 100035121, Item 2 cannot be changed 90025068 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016553 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025068 | 05 | Preparation | 0000133613 | 2 | 0 | EA | 102000000033918 |  | 102000000034357 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090025068_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-12-29 | 0 |  | 2025-02-24 |  | 2025-03-01 | K4401B |  | 0 | 2 | 0 | 90025068 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025068_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000133023 | S002 | 30 | 30 | 5300016553 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133613 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-03-12 | 2025-03-01 | 2024-07-19 | 2025-03-01 | 2025-03-01 | INLEC | 200065935 | 0010 | 0030 | 200065935 | 6Y Vib/Speed Probe Repl (7) 1K2420 | AA53.124GE026 | TXDCR,TRIP VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.03.2024) | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 8 | EA | 35 | 3 | 0 | 8 | EA | 25.09 - At KGP | Supply for Order 200065935, Item 3 cannot be changed 180066907 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300008306 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180066907 | 9012275 | 05 | Preparation | 0000100270 | 3 | 0 | EA |  |  | 102000000016375 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07-WAREHOUSE | AA53-TA-P07 | 0 | 5400001434 | 10 | 8 | EA | 0 | 0 |  |  | Y | 1001 | 2024-03-25 | GRST-5000198315_2024 | 0 | 0 | 0 | 0 |  | 2024-07-20 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000026858 | 1020 | 2025-07-31 | 8 |  | 2024-09-06 | 4900126643_2024_0001 | 2024-07-22 | 200065935 | 5000198315_2024_0001 | 0 | 2 | 0 | 90011040 | 8 | 0 | 180066907/180073889 | 2 | 0 | 0 | X | L | 4900126643 | 2024 |  | 5000198315 | 2024 | 0 |  | 2024-07-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 2024-03-25 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 9012275_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 | 4900162858_2024 | 25SD2420 | MJ | 1000003107 | AU1072 | 1000099654 | S002 | 30 | 30 | 5300008306 | 30 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-07-19 |  |  | 2024-09-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100270 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0020 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 18 | EA | 35 | 3 | 0 | 5 | EA | 02.10 - SOH @ AA01/AA02 | Supply for Order 200089806, Item 2 cannot be changed 90024958 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003900 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024958 | 05 | Preparation | 0000128060 | 2 | 0 | EA | 102000000031510 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024958_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024958 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 2024-01-02 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024958_0020 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127469 | S002 | 30 | 30 | 5300003900 | 20 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128060 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0020 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 18 | EA | 35 | 3 | 0 | 13 | EA | 02.10 - SOH @ AA01/AA02 | Supply for Order 200089806, Item 2 cannot be changed 90024958 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003900 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024958 | 05 | Preparation | 0000128060 | 2 | 0 | EA | 102000000029433 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024958_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024958 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 2024-01-02 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024958_0020 |  |  | FR1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127469 | S002 | 30 | 30 | 5300003900 | 20 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128060 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-16 | INLEC | 200089807 | 0010 | 0020 | 200089807 | 8Y Replace Vibration Probes (4) 1K1820 | AA53.118XT505A | TXDCR,1K1820 GEAR AXIAL DISPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 4 | EA | 35 | 3 | 0 | 2 | EA | 19.02 - SOH @AA02 | Supply for Order 200089807, Item 2 cannot be changed 90024959 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003901 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024959 | 05 | Preparation | 0000128101 | 2 | 0 | EA | 102000000033917 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024959_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024959 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 2024-10-14 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024959_0030 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127470 | S002 | 30 | 30 | 5300003901 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128101 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-16 | INLEC | 200089807 | 0010 | 0020 | 200089807 | 8Y Replace Vibration Probes (4) 1K1820 | AA53.118XT505A | TXDCR,1K1820 GEAR AXIAL DISPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 4 | EA | 35 | 3 | 0 | 2 | EA | 19.02 - SOH @AA02 | Supply for Order 200089807, Item 2 cannot be changed 90024959 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003901 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024959 | 05 | Preparation | 0000128101 | 2 | 0 | EA | 102000000031511 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024959_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024959 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 2024-10-14 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024959_0030 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127470 | S002 | 30 | 30 | 5300003901 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128101 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147116 | 0020 | 0060 | 200147116 | 3Y Vibration Probe Replace (7) 1KT2420 | AA53.124YE031 | TXDCR,ALARM VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 3 | EA | 35 | 3 | 0 | 3 | EA | 18.11 - SOH @ AA02 | Supply for Order 200147116, Item 6 cannot be changed 9027115 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017864 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027115 | 05 | Preparation | 0000235387 | 6 | 0 | EA | 102000000032160 | 102000000025915 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-14 | GIST-4900234130_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 3 |  | 2025-02-11 | 4900234130_2025_0005 | 2025-03-01 | 1K2420 |  | 0 | 2 | 0 | 90025108 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234130 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263215 | SENSOR,PROXIMITOR;BENTLEY 3301805005 | 2024-11-13 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027115_0040 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232430 | S002 | 30 | 30 | 5300017864 | 40 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235387 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091128 | 0060 | 0120 | 200091128 | 6Y Motor Bearing Insp - 1KM2301 | AA53.1KM2301 | MOTOR,HV,REGENERATION GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10263553 | OIL,LUB;TURBO,SHELL T46,209L | 1 | DR | 2 | 0 | 2 | 1 | DR | 03.10 - SOH @ AA02 | Supply for Order 200091128, Item 8 cannot be changed 90024963 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004360 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  | CUTOVER_S4 |  | 180129091 | 9027390 | 05 | Preparation | 0000129422 | 8 | 0 | DR | 102000000033674 |  | 107000000000120 |  |  |  | P07YRDBY34 | WorkPackLink | P07YRDBY34 | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000415892_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000058670 | 1020 | 2023-04-01 | 1 |  | 2025-02-25 | 4900247969_2025_0001 | 2025-03-01 | 200091128 | 5000415892_2025_0001 | 0 | 2 | 0 | 90024963 | 1 | 0 | 180129091 | 2 | 0 | 0 | X | L | 4900247969 | 2025 |  | 5000415892 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10263553 | OIL,LUB;TURBO,SHELL T46,209L | 2024-05-11 | W |  | 0060 | Inspect Motor NDE Bearing | ENON | Inspect Motor NDE Bearing | 5 |  | 9027390_0070 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128791 | S002 | 30 | 30 | 5300004360 | 70 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-12-23 | 2025-05-08 | 2025-01-27 | 2025-05-08 | 2025-05-09 | INLEC | 100089412 | 0010 | 0010 | 100089412 | OPSD 414HV851 Replace Reg / stroke | AA53.414HV851 | VALVE,MANUAL 4V1431 HC LIQ TO E1423 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.12.2024) | 10264473 | VALVE,CONTR;PRESS,INSERT DEAL R3027C | 1 | EA | 1 | 0 | 0 | 1 | EA | 10.03 - AT AA53 | Supply for Order 100089412, Item 1 cannot be changed 180110139 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300019450 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180110139 | 90027584 | 05 | Preparation | 0000285921 | 1 | 0 | EA |  |  | 102000000028650 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-P19-QMI-SML | P19 OPSD | 0 |  | 0 | 0 |  | 1 | 0 | 2025-01-01 |  | Y | 1001 | 2024-12-24 |  | 0 | 0 | 0 | 0 |  | 2025-01-30 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000049466 | 1020 | 2025-12-18 | 1 |  | 2024-12-29 | 4900199379_2024_0001 | 2025-02-01 | 414HV851 | 5000334976_2024_0001 | 0 | 2 | 0 | 90027584 | 1 | 0 | 180110139 | 2 | 0 | 0 | X | L | 4900199379 | 2024 |  | 5000334976 | 2024 | 0 |  | 2025-01-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10264473 | VALVE,CONTR;PRESS,INSERT DEAL R3027C | 2024-12-24 | W |  | 0010 | Replace air reg / Stroke cal valve | INT | Replace air reg / Stroke cal valve |  | Opportune Shutdown | 90027584_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ | 1000004577 | AU1072 | 1000280084 | S002 | 30 | 30 | 5300019450 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-01-27 |  | Opportune Shutdown | 2024-12-31 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPFN4 | 2024-12-23 | 285921 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-09 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Goods movement posted/Material shortage | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 100041806 | 0030 | 0020 | 100041806 | OPER-12982- Aux door seals Repl-4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10266027 | ADHESIVE;CONT GRIP;1LT,BOSTIK 30608496 | 1 | CON | 1 | 0 | 2 | 0 |  | 18.10 - SOH @ AA02 | Supply for Order 100041806, Item 2 cannot be changed 90025058 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016540 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  |  |  |  | 90025058 | 05 | Preparation | 0000140298 | 2 | 0 | [8 empty] | WorkPackLink |  | P08 - FL Mech | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025058_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-06-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2100337744 |  | 0 | 2 | 0 | 90025058 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10266027 | ADHESIVE;CONT GRIP;1LT,BOSTIK 30608496 | 2024-10-17 | W |  | 0030 | Remove & Replace Door Seals | INT | Remove & Replace Door Seals |  |  | 90025058_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139708 | S002 | 30 | 30 | 5300016540 | 20 |  |  | 0 | 1 | CON | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-10-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 100083725 | 0010 | 0030 | 100083725 | GT4009K1A - Vent Fan DE Bearing | AA53.GT4009K1A | FAN,TURBINE ACOUSTIC ENCL VENT,GT4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.10.2024) | 10266211 | BELT,SYNC;GATES 457814MGT2115 | 1 | EA | 5 | 0 | 0 | 0 |  | 28.10 - SOH @ AA02 | Supply for Order 100083725, Item 3 cannot be changed 90025083 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016986 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025083 | 05 | Preparation | 0000260566 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-28 | ODST-0090025083_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025083 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10266211 | BELT,SYNC;GATES 457814MGT2115 | 2024-10-27 | W |  | 0010 | GT4009K1A - Vent Fan DE Bearing | INT | GT4009K1A - Vent Fan DE Bearing |  |  | 90025083_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000256336 | S002 |  | 30 | 5300016986 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-09-02 | 260566 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | WORK | 200089335 | 0020 | 0060 | 200089335 | 10Y RECERTIFY PSV ROTABLE | AA53.408RV521 | PSV,CO2 DISCH LINE GT4008A CO2 |  | 10 | No issue identified | 10266469 | VALVE,REL,CROSBY 9611102A,PRESS 3100KPAG | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 07 | Execution | 0000127593 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10266469 | VALVE,REL,CROSBY 9611102A,PRESS 3100KPAG |  |  |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000127004 |  | 30 |  |  | 0 |  |  | 0 | 0 | [5 empty] | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-01-29 | 2025-02-07 | 2025-03-01 | 2025-03-01 | WORK | 200089335 | 0010 | 0010 | 200089335 | 10Y RECERTIFY PSV ROTABLE | AA53.408RV521 | PSV,CO2 DISCH LINE GT4008A CO2 |  | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.01.2024) | 10266469 | VALVE,REL,CROSBY 9611102A,PRESS 3100KPAG | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.01 - SOH @ AA03 | Supply for Order 200089335, Item 8 cannot be changed 90025124 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA03 | 5300005158 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  | 180115179 | 90025124 | 07 | Execution | 0000127593 | 8 | 0 | EA |  |  | 119000000001567 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08WHSFLR |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-01-17 |  | 0 | 31 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-01-29 |  |  | 2025-03-01 |  |  | 100000011833 | 1190 | 2025-07-31 | 1 |  | 2025-01-15 | 4900210923_2025_0001 | 2025-03-01 |  | 5000382267_2025_0001 | 0 | 2 | 0 | 90025124 | 1 | 0 | 180115179 | 2 | 0 | 0 | X | L | 4900210923 | 2025 |  | 5000382267 | 2025 | 0 |  | 2025-02-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10266469 | VALVE,REL,CROSBY 9611102A,PRESS 3100KPAG | 2024-01-17 | W |  | 0010 | Certify PSV | INT | Certify PSV | 5 | Ready for Release | 90025124_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDGT8 | MJ | 20004472 | AU1098 | 1000127004 | S003 | 30 | 30 | 5300005158 | 20 |  |  | 0 | 1 | EA | 2001 | AA03 | 2025-02-07 |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127593 | 0 | 0 |  | 1190 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1580 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10284664 | ROD,ROUND,BRASS,0.125" DIA,250MM LG | 4 | EA | 5 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 200 cannot be changed 90028419 item 1560 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 200 | 0 | EA | 102000000030498 | 102000000030718 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10284664 | ROD,ROUND,BRASS,0.125" DIA,250MM LG | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1560 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 200 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1590 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0780 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10285250 | ROD,SET SCR;NP SPR665131002 | 2 | EA | 0 | 0 | 0 | 1 | EA | 29.01 - Consumed | Supply for Order 200147980, Item 143 cannot be changed 9025301 item 520 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180116482 | 9025301 | 05 | Preparation | 0000236589 | 143 | 0 | EA |  |  | 101000000026211 |  |  |  |  | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-09-24 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053328 | 1020 | 2025-12-14 | 2 |  | 2025-01-20 | 4900214469_2025_0001 | 2025-03-01 |  | 5000365680_2025_0001 | 0 | 2 | 0 | 90028418 | 2 | 0 | 180116482 | 2 | 0 | 0 | X | L | 4900214469 | 2025 |  | 5000365680 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10285250 | ROD,SET SCR;NP SPR665131002 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 9025301_0520 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 143 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 550 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0780 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10285250 | ROD,SET SCR;NP SPR665131002 | 2 | EA | 0 | 0 | 0 | 1 | EA | 29.01 - Consumed | Supply for Order 200147980, Item 143 cannot be changed 9025301 item 520 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180116482 | 9025301 | 05 | Preparation | 0000236589 | 143 | 0 | EA |  |  | 101000000129334 |  |  |  |  | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-09-24 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053328 | 1020 | 2025-12-14 | 2 |  | 2025-01-20 | 4900214469_2025_0001 | 2025-03-01 |  | 5000365680_2025_0001 | 0 | 2 | 0 | 90028418 | 2 | 0 | 180116482 | 2 | 0 | 0 | X | L | 4900214469 | 2025 |  | 5000365680 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10285250 | ROD,SET SCR;NP SPR665131002 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 9025301_0520 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 143 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 550 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0140 | 0620 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10285327 | RING,INTER PKG;NP KHA405206901 | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 157 cannot be changed 90028418 item 650 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 157 | 0 | EA | 102000000030309 |  | 102000000034408 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0650 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10285327 | RING,INTER PKG;NP KHA405206901 | 2024-09-23 | W |  | 0140 | INTERMEDIATE PACKING BODY | INT | INTERMEDIATE PACKING BODY | 5 |  | 90028418_0650 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 157 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 680 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0930 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10287054 | DIAPH ACTUATOR | 1 | EA | 0 | 0 | 0 | 0 |  | 07.03 - SOH @ AA53 | Supply for Order 200147980, Item 93 cannot be changed 90028418 item 150 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 93 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10287054 | DIAPH ACTUATOR | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0150 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 93 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 71 | 71 | 5300015696 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-01-01 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100042125 | 0010 | 0020 | 100042125 | OPSD2-FL-S24G2 - MOC 95759 INSUM Gateway | AA53.S24G2 | SWBD,415V EMERG SUPPLY SUB 2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.07.2024) | 10287924 | GATEWAY,MODBUS RTU;ABB 1TGB302002R0005 | 2 | EA | 10 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 100042125, Item 3 cannot be changed 90024988 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300012347 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024988 | 06 | Scheduling | 0000140617 | 3 | 0 | EA | 102000000027408 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-03 | ODST-0090024988_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2024-07-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | S24G2 |  | 0 | 2 | 0 | 90024988 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10287924 | GATEWAY,MODBUS RTU;ABB 1TGB302002R0005 | 2024-07-03 | W |  | 0010 | Complete Isolations | INT | Complete Isolations | 3 |  | 90024988_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000140027 | S002 | 70 | 70 | 5300012347 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140617 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0060 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 12 cannot be changed 90028588 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 12 | 0 | KIT | 102000000031801 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177498 |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028588_0120 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 120 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0030 | 0020 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 2 cannot be changed 90028588 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 2 | 0 | KIT | 102000000031802 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 |  | 90028588_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0030 | 0020 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 2 cannot be changed 90028589 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 2 | 0 | KIT | 102000000031804 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 |  | 90028589_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0060 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 12 cannot be changed 90028589 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 12 | 0 | KIT | 102000000031803 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0120 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 120 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0030 | 0020 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | 15.01 - SOH @ AA02 | Supply for Order 200177720, Item 2 cannot be changed 90028590 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 2 | 0 | KIT | 102000000031800 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 | Ready for Release | 90028590_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0060 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | 15.01 - SOH @ AA02 | Supply for Order 200177720, Item 12 cannot be changed 90028590 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 12 | 0 | KIT | 102000000031799 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177720 |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 90028590_0120 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 120 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0020 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10290434 | PLUG,TUBE;8.3X7.6X76.2MM LG,TAP,STD,AL | 40 | EA | 9 | 0 | 0 | 0 |  | 07.03 - PR 2000282968 | Supply for Order 100090053, Item 2 cannot be changed 90032376 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 2 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0020 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10290434 | PLUG,TUBE;8.3X7.6X76.2MM LG,TAP,STD,AL | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0020 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 20 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0010 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10290467 | PLUG,TUBE;8.6X7.8X76.2MM LG,TAP,O/S,AL | 40 | EA | 10 | 0 | 0 | 0 |  | 07.03 - PR 2000282981 | Supply for Order 100090053, Item 1 cannot be changed 90032376 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 1 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0010 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10290467 | PLUG,TUBE;8.6X7.8X76.2MM LG,TAP,O/S,AL | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0010 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 10 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-07-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146424 | 0010 | 0020 | 200146424 | 5Y SVC 5KM2001 MOTOR MAJOR MATERIAL 2HF1 | AA53.5KM2001 | MOTOR,HV,MAIN,STABILIZER COMP,5K2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.07.2024) | 10290740 | KIT;ELEC MTR,BRG INS,SIEMENS DS912487 | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 02.10 - SOH @ AA02 | Supply for Order 200146424, Item 2 cannot be changed 90024989 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013117 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90024989 | 05 | Preparation | 0000234301 | 2 | 0 | KIT | 102000000031789 | 102000000027723 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-23 | ODST-0090024989_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-04 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024989 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10290740 | KIT;ELEC MTR,BRG INS,SIEMENS DS912487 | 2024-07-22 | W |  | 0010 | MOTOR MAJOR MATERIALS 2HF1 | INT | MOTOR MAJOR MATERIALS 2HF1 | 5 |  | 90024989_0010 |  |  | ST5 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231257 | S002 | 30 | 30 | 5300013117 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-22 | 234301 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0090 | 0110 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10290778 | O-RING;0.087X0.644",VIT,NP ISM101344139 | 2 | EA | 42 | 0 | 0 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 33 cannot be changed 90025036 item 280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 33 | 0 | EA | 102000000027588 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10290778 | O-RING;0.087X0.644",VIT,NP ISM101344139 | 2024-10-16 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 | Ready for Release | 90025036_0280 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 33 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 280 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0090 | 0020 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10290778 | O-RING;0.087X0.644",VIT,NP ISM101344139 | 2 | EA | 42 | 0 | 0 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 14 cannot be changed 90025043 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 14 | 0 | EA | 102000000027589 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10290778 | O-RING;0.087X0.644",VIT,NP ISM101344139 | 2024-10-17 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 | Ready for Release | 90025043_0130 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 14 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0090 | 0020 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10290778 | O-RING;0.087X0.644",VIT,NP ISM101344139 | 2 | EA | 42 | 0 | 0 | 2 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 14 cannot be changed 90025045 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 14 | 0 | EA | 102000000027590 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10290778 | O-RING;0.087X0.644",VIT,NP ISM101344139 | 2024-10-17 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 |  | 90025045_0130 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 14 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | ROTAT | 200088840 | 0060 | 0020 | 200088840 | 5Y P03 SD 5K2001 CRANKCASE RELIEF INSP | AA53.520RV502 | VALVE,CRANKCASE EXPLOSION 5K2001 | AA01 | 10 | No issue identified | 10293547 | O-RING;NTRL,5.7MM,314.5MMID,70,N7G315 | 1 | EA | 3 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015695 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025007 | 05 | Preparation | 0000127070 | 2 | 0 | EA | 102000000031886 | 102000000027572 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025007_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025007 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10293547 | O-RING;NTRL,5.7MM,314.5MMID,70,N7G315 |  |  |  | 0060 | REINSTALL 520RV502 | INT | REINSTALL 520RV502 |  |  | 90025007_0020 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126472 | S002 |  | 30 | 5300015695 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127070 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091128 | 0060 | 0050 | 200091128 | 6Y Motor Bearing Insp - 1KM2301 | AA53.1KM2301 | MOTOR,HV,REGENERATION GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10295185 | OIL,LUB;TURBO,SHELL T46,20L,300011701 | 2 | DR | 13 | 0 | 27 | 2 | DR | 03.10 - SOH @ AA02 | Supply for Order 200091128, Item 1 cannot be changed 9026405 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004360 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180120050 | 9026405 | 05 | Preparation | 0000129422 | 1 | 0 | DR |  |  | 102000000031941 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08YRDBAY4 | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000379599_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055182 | 1020 | 2023-04-01 | 2 |  | 2025-01-30 | 4900222747_2025_0001 | 2025-03-01 | 2200576286 | 5000379599_2025_0001 | 0 | 2 | 0 | 90024963 | 2 | 0 | 180120050 | 2 | 0 | 0 | X | L | 4900222747 | 2025 |  | 5000379599 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10295185 | OIL,LUB;TURBO,SHELL T46,20L,300011701 | 2024-01-02 | W |  | 0060 | Inspect Motor NDE Bearing | ENON | Inspect Motor NDE Bearing | 5 |  | 9026405_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SD2301 | MJ | 1000004928 | AU1072 | 1000128791 | S002 | 30 | 30 | 5300004360 | 10 |  |  | 0 | 2 | DR | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-03 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-04-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146423 | 0030 | 0010 | 200146423 | 1Y SVC 5KM2001 HV MOTOR OIL REPLACEMENT | AA53.5KM2001 | MOTOR,HV,MAIN,STABILIZER COMP,5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10295185 | OIL,LUB;TURBO,SHELL T46,20L,300011701 | 2 | DR | 13 | 0 | 27 | 2 | DR | 03.10 - SOH @ AA02 | Supply for Order 200146423, Item 1 cannot be changed 90025010 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015699 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  | CUTOVER_S4 |  | 180120053 | 90025010 | 05 | Preparation | 0000234120 | 1 | 0 | DR |  |  | 102000000031942 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08YRDBAY4 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-24 | GRST-5000379642_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055183 | 1020 | 2025-12-04 | 2 |  | 2025-01-30 | 4900222788_2025_0001 | 2025-03-01 |  | 5000379642_2025_0001 | 0 | 2 | 0 | 90025010 | 2 | 0 | 180120053 | 2 | 0 | 0 | X | L | 4900222788 | 2025 |  | 5000379642 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10295185 | OIL,LUB;TURBO,SHELL T46,20L,300011701 | 2024-09-23 | W |  | 0030 | Refill Oil of KM2001 NDE Bearing | INT | Refill Oil of KM2001 NDE Bearing | 3 |  | 90025010_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ | 1000004929 | AU1072 | 1000231256 | S002 | 30 | 30 | 5300015699 | 10 |  |  | 0 | 2 | DR | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-03 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-22 | 234120 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0220 | 0860 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10295185 | OIL,LUB;TURBO,SHELL T46,20L,300011701 | 1 | DR | 13 | 0 | 27 | 1 | DR | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 86 cannot be changed 90028418 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 86 | 0 | DR | 102000000030931 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10295185 | OIL,LUB;TURBO,SHELL T46,20L,300011701 | 2024-09-23 | W |  | 0220 | ELECTRIC MOTOR | INT | ELECTRIC MOTOR | 5 |  | 90028418_0090 |  |  | ST5 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 86 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 100 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD4401 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 100035121 | 0020 | 0030 | 100035121 | Vibration Probe Replace 244XE505X | AA53.FAR7CM6 | PANEL,SYSTEM CABINET,CPMS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10295309 | CABLE ASY;EXTN LEAD,BENTLY 3301300450005 | 1 | EA | 1 | 0 | 0 | 1 | EA | 21.02 - SOH @ AA02 | Supply for Order 100035121, Item 3 cannot be changed 90025068 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016553 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025068 | 05 | Preparation | 0000133613 | 3 | 0 | EA | 101000000146499 |  | 102000000034357 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090025068_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-12-29 | 0 |  | 2025-02-24 |  | 2025-03-01 | K4401B |  | 0 | 2 | 0 | 90025068 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10295309 | CABLE ASY;EXTN LEAD,BENTLY 3301300450005 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025068_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000133023 | S002 | 30 | 30 | 5300016553 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133613 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147450 | 0020 | 0040 | 200147450 | 2Y SVC GT4009 TURB VSV REPLACEMENT | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 96 | EA | 708 | 0 | 0 | 96 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147450, Item 4 cannot be changed 90025003 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015681 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025003 | 05 | Preparation | 0000235860 | 4 | 0 | EA | 102000000026469 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 96 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025003_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025003 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 2024-09-22 | W |  | 0020 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 3 |  | 90025003_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232866 | S002 | 30 | 30 | 5300015681 | 10 |  |  | 0 | 96 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235860 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0200 | 0230 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 24 | EA | 708 | 0 | 0 | 24 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 23 cannot be changed 90025036 item 200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 23 | 0 | EA | 102000000026467 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | VSV 3 4 |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 2024-10-16 | W |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 3 | Ready for Release | 90025036_0200 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 23 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 200 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0200 | 0040 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 24 | EA | 708 | 0 | 0 | 24 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 27 cannot be changed 90025043 item 250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 27 | 0 | EA | 102000000026468 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | VSV 3 4 |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 2024-10-17 | W |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 3 | Ready for Release | 90025043_0250 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 27 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 250 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147450 | 0020 | 0050 | 200147450 | 2Y SVC GT4009 TURB VSV REPLACEMENT | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 58 | EA | 236 | 0 | 0 | 58 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147450, Item 5 cannot be changed 90025003 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015681 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025003 | 05 | Preparation | 0000235860 | 5 | 0 | EA | 102000000026595 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 58 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025003_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025003 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 2024-09-22 | W |  | 0020 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 3 |  | 90025003_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232866 | S002 | 30 | 30 | 5300015681 | 20 |  |  | 0 | 58 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235860 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0200 | 0220 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 12 | EA | 236 | 0 | 0 | 12 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147548, Item 22 cannot be changed 90025036 item 190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 22 | 0 | EA | 102000000026593 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | VSV 5 |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 2024-10-16 | W |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 3 | Ready for Release | 90025036_0190 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 22 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 190 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0200 | 0030 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 12 | EA | 236 | 0 | 0 | 12 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147550, Item 26 cannot be changed 90025043 item 240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 26 | 0 | EA | 102000000026594 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | VSV 5 |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 2024-10-17 | W |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 3 | Ready for Release | 90025043_0240 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 26 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 240 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147450 | 0020 | 0060 | 200147450 | 2Y SVC GT4009 TURB VSV REPLACEMENT | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10297296 | WASHER,PLN;GE L44862P02 | 96 | EA | 386 | 0 | 0 | 96 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147450, Item 6 cannot be changed 90025003 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015681 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025003 | 05 | Preparation | 0000235860 | 6 | 0 | EA | 102000000027243 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 96 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025003_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025003 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 | 2024-09-22 | W |  | 0020 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 3 |  | 90025003_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232866 | S002 | 30 | 30 | 5300015681 | 30 |  |  | 0 | 96 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235860 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0200 | 0210 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10297296 | WASHER,PLN;GE L44862P02 | 24 | EA | 386 | 0 | 0 | 24 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 21 cannot be changed 90025036 item 180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 21 | 0 | EA | 102000000027241 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | VSV 3 4 |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 | 2024-10-16 | W |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 3 | Ready for Release | 90025036_0180 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 21 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 180 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0200 | 0020 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10297296 | WASHER,PLN;GE L44862P02 | 24 | EA | 386 | 0 | 0 | 24 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 25 cannot be changed 90025043 item 230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 25 | 0 | EA | 102000000027242 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | VSV 3 4 |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 | 2024-10-17 | W |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 3 | Ready for Release | 90025043_0230 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 25 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 230 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147450 | 0020 | 0070 | 200147450 | 2Y SVC GT4009 TURB VSV REPLACEMENT | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10297297 | WASHER,PLN;GE L44862P03 | 58 | EA | 138 | 0 | 58 | 58 | EA | 12.11 - SOH @ AA02 | Supply for Order 200147450, Item 7 cannot be changed 90025003 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015681 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025003 | 05 | Preparation | 0000235860 | 7 | 0 | EA | 102000000026698 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 58 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025003_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025003 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 | 2024-09-22 | W |  | 0020 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 3 |  | 90025003_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232866 | S002 | 30 | 30 | 5300015681 | 40 |  |  | 0 | 58 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235860 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0200 | 0200 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10297297 | WASHER,PLN;GE L44862P03 | 12 | EA | 138 | 0 | 58 | 12 | EA | 18.12 - SOH @ AA02 | Supply for Order 200147548, Item 20 cannot be changed 90025036 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 20 | 0 | EA | 102000000026696 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | VSV 5 |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 | 2024-10-16 | W |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 3 | Ready for Release | 90025036_0170 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 20 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 170 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0200 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10297297 | WASHER,PLN;GE L44862P03 | 12 | EA | 138 | 0 | 58 | 12 | EA | 18.12 - SOH @ AA02 | Supply for Order 200147550, Item 24 cannot be changed 90025043 item 220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 24 | 0 | EA | 102000000026697 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | VSV 5 |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 | 2024-10-17 | W |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 3 | Ready for Release | 90025043_0220 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 24 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 220 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147450 | 0020 | 0080 | 200147450 | 2Y SVC GT4009 TURB VSV REPLACEMENT | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10297384 | NUT,LK;0.250"X28UN,GE J574P02 | 54 | EA | 148 | 0 | 2 | 54 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147450, Item 8 cannot be changed 90025003 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015681 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025003 | 05 | Preparation | 0000235860 | 8 | 0 | EA | 102000000029428 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 54 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025003_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025003 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297384 | NUT,LK;0.250"X28UN,GE J574P02 | 2024-09-22 | W |  | 0020 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 3 |  | 90025003_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232866 | S002 |  | 30 | 5300015681 | 50 |  |  | 0 | 54 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235860 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0210 | 0270 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10297412 | PACKING,PF;GE M832481243 | 1 | EA | 18 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 27 cannot be changed 90025036 item 220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 27 | 0 | EA | 102000000029437 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297412 | PACKING,PF;GE M832481243 | 2024-10-16 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 | Ready for Release | 90025036_0220 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 27 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 220 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0210 | 0020 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10297412 | PACKING,PF;GE M832481243 | 1 | EA | 18 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 29 cannot be changed 90025043 item 270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 29 | 0 | EA | 102000000029438 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297412 | PACKING,PF;GE M832481243 | 2024-10-17 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 | Ready for Release | 90025043_0270 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 29 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 270 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0210 | 0020 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10297412 | PACKING,PF;GE M832481243 | 1 | EA | 18 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 25 cannot be changed 90025045 item 240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 25 | 0 | EA | 102000000029439 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297412 | PACKING,PF;GE M832481243 | 2024-10-17 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 |  | 90025045_0240 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 25 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 240 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0080 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10298351 | FILTER,AIR;MIDLAND 8BRESN102 | 1 | ASY | 0 | 0 | 0 | 0 |  | DEL: 80028774 | Supply for Order 100085072, Item 10 cannot be changed 90029953 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90029953 | 05 | Preparation | 0000267773 | 10 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029953_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10298351 | FILTER,AIR;MIDLAND 8BRESN102 | 2025-01-30 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029953_0050 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 | 30 | 30 | 5300019757 | 100 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0060 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10298352 | FLTR:AIR,316 SS,0.25in,NPT,MIDLAND,2BRES | 1 | ASY | 0 | 0 | 0 | 0 |  | 30.01 - ETA 03.02.25 PO 4500036368 ROTORK CPT | Supply for Order 100085072, Item 8 cannot be changed 90029953 item 40 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90029953 | 05 | Preparation | 0000267773 | 8 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029953_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10298352 | FLTR:AIR,316 SS,0.25in,NPT,MIDLAND,2BRES | 2025-01-30 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029953_0040 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 | 30 | 30 | 5300019757 | 80 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-09-19 | 2025-04-28 | 2024-08-16 | 2025-03-01 | 2025-03-01 | INLEC | 100079527 | 0010 | 0010 | 100079527 | OPSD Heat Det Cable/Loop Replace 1KT1410 | AA53.160TZ511A | LOOP,HEAT DETECT 1KT1410 TURBINE COMPART | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.07.2024) | 10299244 | CABLE,INSTR;1.5MM2,LAPP 0046313 | 50 | M | 150 | 0 | 0 | 50 | M | 29.01 - Consumed | Supply for Order 100079527, Item 1 cannot be changed 180080039 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300013318 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  | 180080039 | 90016433 | 06 | Scheduling | 0000246273 | 1 | 0 | M |  |  | 102000000020489 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-KGP-RUNNER-SML | AA53-P08-OPSD | 0 |  | 0 | 0 |  | 50 | 0 |  |  | Y | 1001 | 2024-07-29 |  | 0 | 0 | 0 | 0 |  | 2024-08-17 | AA53 | 2025-03-01 |  |  | 2025-04-28 |  |  | 100000034420 | 1020 | 2025-10-31 | 50 |  | 2024-10-09 | 4900149622_2024_0001 | 2024-08-19 | 160TZ511A | 5000238616_2024_0001 | 0 | 2 | 0 | 90016433 | 50 | 0 | 180080039 | 2 | 0 | 0 | X | L | 4900149622 | 2024 |  | 5000238616 | 2024 | 0 |  | 2024-08-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10299244 | CABLE,INSTR;1.5MM2,LAPP 0046313 | 2024-07-28 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  | Opportune Shutdown | 90016433_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ | 1000003626 | AU1072 | 1000242866 | S002 |  | 30 | 5300013318 | 10 |  |  | 0 | 50 | M | 2001 | AA02 | 2024-08-16 |  | Opportune Shutdown | 2024-10-10 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-24 | 246273 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2440 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10299959 | SCREW SET,AUX CPLG;NP IRG3386704 | 1 | SET | 1 | 0 | 0 | 1 | SET | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 356 cannot be changed 90028419 item 2760 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2790 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 356 | 0 | SET | 102000000030495 | 102000000030824 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2760 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10299959 | SCREW SET,AUX CPLG;NP IRG3386704 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2760 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 356 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2790 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-03-21 | 2024-03-01 | 2024-10-10 | 2025-03-01 | 2025-03-01 | INLEC | 100074555 | 0020 | 0010 | 100074555 | Replace internal HIMA card battery - GT4 | AA53.GT4007CO2 | SYSTEM,GT4007 CO2 FIRE SUPPRESSION | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(09.10.2024) | 10300675 | BATTERY,LI;RENATA CR2477N | 10 | EA | 4 | 0 | 10 | 4 | EA | 24.01 - ETA 28.02.25 PO 4500034659 MM | Supply for Order 100074555, Item 2 cannot be changed 90021633 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300008186 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90021633 | 07 | Execution | 0000226618 | 2 | 0 | EA | 101000000140746 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-03-21 | ODST-0090021633_0010 | 0 | 228 | 0 | 0 |  | 2024-02-28 | AA53 | 2025-03-01 |  |  | 2024-10-15 |  |  |  |  | 2026-03-03 | 0 |  | 2024-10-10 |  | 2024-10-15 | GT4007 |  | 0 | 2 | 0 | 90021633 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-10-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300675 | BATTERY,LI;RENATA CR2477N | 2024-10-09 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90021633_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000223997 | S002 |  | 30 | 5300008186 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-10-10 |  |  |  |  | 1070 |  | 2024-07-24 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-13 | 226618 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Partially confirmed/Job In Process/Material shortage | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2024-03-21 | 2025-03-01 | 2024-04-27 | 2025-03-01 | 2025-03-01 | INLEC | 100074555 | 0010 | 0010 | 100074555 | Replace internal HIMA card battery - GT4 | AA53.GT4007CO2 | SYSTEM,GT4007 CO2 FIRE SUPPRESSION | AA01 | 255 | Voyage arrived: too late to meet planned Reqmt Date | 10300675 | BATTERY,LI;RENATA CR2477N | 10 | EA | 4 | 0 | 10 | 10 | EA | 25.09 - At KGP | Supply for Order 100074555, Item 1 cannot be changed 180032271 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300008186 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180032271 | 90007254 | 07 | Execution | 0000226618 | 1 | 0 | EA | 101000000047216 | 101000000047214 | 101000000047416 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | P19 FL Inlec | 0 |  | 0 | 0 |  | 0 | 0 | 2024-06-11 | 2024-06-02 | Y | 1001 | 2024-03-21 | GRST-5000102748 | 0 | 0 | 0 | 0 |  | 2024-04-28 | AA53 | 2024-07-24 |  |  | 2025-03-01 |  |  | 100000011718 | 1020 | 2026-03-03 | 10 |  | 2024-06-06 | 4900070329_2024_0001 | 2024-04-30 |  | 5000102748_2024_0001 | 0 | 2 | 0 | 90007254 | 10 | 0 | 180032271 | 1 | 0 | 0 | X | L | 4900070329 | 2024 |  | 5000102748 | 2024 | 0 |  | 2024-04-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300675 | BATTERY,LI;RENATA CR2477N | 2024-03-21 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  |  | 90007254_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ | 20001452 | AU1072 | 1000223997 | S002 |  | 30 | 5300008186 | 10 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-27 |  |  | 2024-05-31 |  | 1070 |  | 2024-07-24 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-13 | 226618 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Partially confirmed/Job In Process/Material shortage | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0050 | 0010 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 4 | EA | 3 | 4 | 12 | 0 |  | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200089472, Item 1 cannot be changed 90028583 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 1 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028583_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0010 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 4 | EA | 3 | 4 | 12 | 1 | EA | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200089473, Item 12 cannot be changed 9027783 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180130045 | 9027783 | 05 | Preparation | 0000127731 | 12 | 0 | EA | 102000000033760 |  | 107000000000121 |  |  |  | P07YRDBY35 | WorkPackLink | P07YRDBY35 | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000419306_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000059129 | 1020 | 2024-09-06 | 4 |  | 2025-02-27 | 4900250603_2025_0001 | 2025-03-01 | 200089473 | 5000419306_2025_0001 | 0 | 2 | 0 | 90028584 | 4 | 0 | 180130045 | 2 | 0 | 0 | X | L | 4900250603 | 2025 |  | 5000419306 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 9027783_0120 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 120 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0010 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 4 | EA | 3 | 4 | 12 | 1 | EA | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200089473, Item 12 cannot be changed 9027783 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180130045 | 9027783 | 05 | Preparation | 0000127731 | 12 | 0 | EA | 102000000033764 |  | 107000000000121 |  |  |  | P07YRDBY35 | WorkPackLink | P07YRDBY35 | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000419306_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000059129 | 1020 | 2024-09-06 | 4 |  | 2025-02-27 | 4900250603_2025_0001 | 2025-03-01 | 200089473 | 5000419306_2025_0001 | 0 | 2 | 0 | 90028584 | 4 | 0 | 180130045 | 2 | 0 | 0 | X | L | 4900250603 | 2025 |  | 5000419306 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 9027783_0120 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 120 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0010 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 4 | EA | 3 | 4 | 12 | 1 | EA | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200089473, Item 12 cannot be changed 9027783 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180130045 | 9027783 | 05 | Preparation | 0000127731 | 12 | 0 | EA | 102000000033761 |  | 107000000000121 |  |  |  | P07YRDBY35 | WorkPackLink | P07YRDBY35 | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000419306_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000059129 | 1020 | 2024-09-06 | 4 |  | 2025-02-27 | 4900250603_2025_0001 | 2025-03-01 | 200089473 | 5000419306_2025_0001 | 0 | 2 | 0 | 90028584 | 4 | 0 | 180130045 | 2 | 0 | 0 | X | L | 4900250603 | 2025 |  | 5000419306 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 9027783_0120 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 120 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0010 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 4 | EA | 3 | 4 | 12 | 1 | EA | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200089473, Item 12 cannot be changed 9027783 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180130045 | 9027783 | 05 | Preparation | 0000127731 | 12 | 0 | EA | 102000000033762 |  | 107000000000121 |  |  |  | P07YRDBY35 | WorkPackLink | P07YRDBY35 | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000419306_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000059129 | 1020 | 2024-09-06 | 4 |  | 2025-02-27 | 4900250603_2025_0001 | 2025-03-01 | 200089473 | 5000419306_2025_0001 | 0 | 2 | 0 | 90028584 | 4 | 0 | 180130045 | 2 | 0 | 0 | X | L | 4900250603 | 2025 |  | 5000419306 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 9027783_0120 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 120 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0630 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 12 | EA | 3 | 4 | 12 | 0 |  | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200091505, Item 71 cannot be changed 90025019 item 690 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 71 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0690 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0690 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 71 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 690 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0070 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 3 | 4 | 12 | 0 |  | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200177498, Item 13 cannot be changed 90028588 item 130 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 13 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177498 |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028588_0130 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 | 30 | 30 | 5300020059 | 130 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0040 | 0060 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 3 | 4 | 12 | 0 |  | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200177498, Item 6 cannot be changed 90028588 item 60 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 |  | 90028588_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 | 30 | 30 | 5300020059 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0040 | 0060 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 3 | 4 | 12 | 0 |  | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200177499, Item 6 cannot be changed 90028589 item 60 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 |  | 90028589_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 | 30 | 30 | 5300020060 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0070 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 3 | 4 | 12 | 0 |  | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200177499, Item 13 cannot be changed 90028589 item 130 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 13 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0130 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 | 30 | 30 | 5300020060 | 130 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0070 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 3 | 4 | 12 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 200177720, Item 13 cannot be changed 90028590 item 130 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 13 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177720 |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 90028590_0130 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 | 30 | 30 | 5300020061 | 130 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0040 | 0060 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 3 | 4 | 12 | 0 |  | 24.02 - ETA 27.02.25 PO 4500043669 ATOM CPT | Supply for Order 200177720, Item 6 cannot be changed 90028590 item 60 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 | Ready for Release | 90028590_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 | 30 | 30 | 5300020061 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2400 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10302603 | O-RING;VITON,9.0MM,86.0MM ID,75 | 2 | EA | 10 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 532 cannot be changed 90028419 item 3860 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 532 | 0 | EA | 102000000030491 | 102000000030641 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3860 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10302603 | O-RING;VITON,9.0MM,86.0MM ID,75 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_3860 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 532 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3890 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086241 | 0020 | 0030 | 100086241 | Com Disch TC Replace (2) 1KT2420 | AA53.124TE36 | TXDCR,TEMP 1K2420 DISCH TEMP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10302610 | CABLE,INSTR;TEMPCONTR TCKGGB73SICCET | 500 | M | 1250 | 0 | 500 | 500 | M | 28.10 - SOH @ AA02 | Supply for Order 100086241, Item 3 cannot be changed 90025077 item 30 already exists | Material picked; currently at KSF-PACK-SD-SML/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300016829 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90025077 | 05 | Preparation | 0000272293 | 3 | 0 | M |  |  | 102000000032862 |  |  |  |  | WorkPackLink | KSF-PACK-SD-SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 500 |  |  | Y | 1001 | 2024-10-24 | ODST-0090025077_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124TE34/5 |  | 0 | 2 | 0 | 90025077 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10302610 | CABLE,INSTR;TEMPCONTR TCKGGB73SICCET | 2024-10-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025077_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267030 | S002 |  | 30 | 5300016829 | 30 |  |  | 0 | 500 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272293 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | INLEC | 200067823 | 0020 | 0020 | 200067823 | 6Y SIF Exhaust TC Replace (18) 1KT2420 | AA53.124TE301 | TXDCR,1KT2420 TURB EXH DUCT TEMP | AA01 | 10 | Shipped qty below requirement qty | 10302610 | CABLE,INSTR;TEMPCONTR TCKGGB73SICCET | 1250 | M | 1250 | 0 | 500 | 250 | M | 31.01 - SOH @ AA02 | Supply for Order 200067823, Item 2 cannot be changed 90025073 item 20 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016758 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  | 180117545 | 9026038 | 05 | Preparation | 0000102098 | 2 | 0 | M | 102000000032861 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 750 |  |  | Y | 1001 | 2024-10-23 | GRST-5000369507 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000054625 | 1020 | 2024-07-25 | 500 |  | 2025-01-22 | 4900216526_2025_0001 | 2025-03-01 | 124TE301-318 | 5000369507_2025_0001 | 0 | 2 | 0 | 90025073 | 500 | 0 | 180117545 | 1 | 0 | 0 | X | L | 4900216526 | 2025 |  | 5000369507 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10302610 | CABLE,INSTR;TEMPCONTR TCKGGB73SICCET | 2024-10-23 | W |  | 0020 | Complete Replacement of Cable & TC's | INT | Complete Replacement of Cable & TC's |  | Order Requires Replanning | 90025073_0020/9026038_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000101542 | S002 |  | 30 | 5300016758 | 20 |  |  | 0 | 750 | M | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 102098 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | INLEC | 200067823 | 0020 | 0020 | 200067823 | 6Y SIF Exhaust TC Replace (18) 1KT2420 | AA53.124TE301 | TXDCR,1KT2420 TURB EXH DUCT TEMP | AA01 | 10 | Shipped qty below requirement qty | 10302610 | CABLE,INSTR;TEMPCONTR TCKGGB73SICCET | 1250 | M | 1250 | 0 | 500 | 500 | M | 31.01 - SOH @ AA02 | Supply for Order 200067823, Item 2 cannot be changed 90025073 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016758 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  | 180117545 | 9026038 | 05 | Preparation | 0000102098 | 2 | 0 | M |  |  | 101000000135279 |  |  |  |  | WorkPackLink | INLEC-CAGE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 750 |  |  | Y | 1001 | 2024-10-23 | GRST-5000369507_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000054625 | 1020 | 2024-07-25 | 500 |  | 2025-01-22 | 4900216526_2025_0001 | 2025-03-01 | 124TE301-318 | 5000369507_2025_0001 | 0 | 2 | 0 | 90025073 | 500 | 0 | 180117545 | 1 | 0 | 0 | X | L | 4900216526 | 2025 |  | 5000369507 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10302610 | CABLE,INSTR;TEMPCONTR TCKGGB73SICCET | 2024-10-23 | W |  | 0020 | Complete Replacement of Cable & TC's | INT | Complete Replacement of Cable & TC's |  | Order Requires Replanning | 90025073_0020/9026038_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000101542 | S002 |  | 30 | 5300016758 | 20 |  |  | 0 | 750 | M | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 102098 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 100045383 | 0010 | 0010 | 100045383 | EEHA Cable Re-gland 123HZ019 | AA53.123HZ019 | SW,TRIP MANUAL CONT F/G 1F2301 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10303014 | WASHER,FLAT;M20,NYLON,RND,1.5MM | 1 | EA | 381 | 9 | 167 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 100045383, Item 1 cannot be changed 90025052 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016509 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025052 | 05 | Preparation | 0000143904 | 1 | 0 | EA | 102000000027245 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025052_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123HZ019 |  | 0 | 2 | 0 | 90025052 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10303014 | WASHER,FLAT;M20,NYLON,RND,1.5MM | 2024-10-17 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 2 |  | 90025052_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000143273 | S002 | 30 | 30 | 5300016509 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143904 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Material committed/Printed/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0200 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10303043 | TUBE,INSTR,PE,0.25" X150M RL,140PSI,BLK | 1 | ROL | 12 | 0 | 3 | 1 | ROL | 24.02 - SOH @ AA02 | Supply for Order 500005166, Item 40 cannot be changed 9028651 item 220 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132829 | 9028651 | 05 | Preparation | 0000294187 | 40 | 0 | ROL |  |  | 101000000147773 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000429492_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060148 | 1020 |  | 1 |  | 2025-03-06 | 4900259005_2025_0003 | 2025-04-01 | TA LAG_VORN | 5000429492_2025_0002 | 0 | 2 | 0 | 90031501 | 1 | 0 | 180132829 | 2 | 0 | 0 | X | L | 4900259005 | 2025 |  | 5000429492 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10303043 | TUBE,INSTR,PE,0.25" X150M RL,140PSI,BLK | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 9028651_0220 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 40 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 360 |  |  | 0 | 1 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2420 | Released | 2024-05-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100047394 | 0030 | 0040 | 100047394 | CV-OH 1" 600# 124PCV54 | AA53.124PCV54 | VALVE,CONT SEAL OIL BACK PRESS 1K2420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(19.09.2024) | 10303469 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 5 | 3 | 1 | 2 | EA | 13.01 - SOH @ AA02 | Supply for Order 100047394, Item 6 cannot be changed 90024986 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300011592 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024986 | 07 | Execution | 0000145926 | 6 | 0 | EA | 101000000121925 |  | 101000000121749 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  | 2024-12-14 | Y | 1001 | 2024-06-14 | ODST-0090024986_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2018-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100047394 |  | 0 | 2 | 0 | 90024986 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10303469 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 2024-09-19 | W |  | 0030 | Remove Valve 124PCV54 & Fit Blinds | INT | Remove Valve 124PCV54 & Fit Blinds | 5 |  | 90024986_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SD2420 | MJ | 20004133 | AU1072 | 1000145296 | S002 | 30 | 30 | 5300011592 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2024-12-12 |  | 1070 |  | 2024-05-23 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145926 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0110 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10303469 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 10 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10303469 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0380 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10303469 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 36 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10303469 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-06 | ROTAT | 100046308 | 0050 | 0030 | 100046308 | MOC-52386 - Tank Min Oil Replace - G4008 | AA53.G4008V1 | TANK,MINERAL OIL RESERVOIR G4008 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10304292 | GASKET;SWCI,200MM,CL150,3MM,316L/GR/316 | 2 | EA | 2 | 0 | 0 | 2 | EA | 06.01 - SOH @ AA02 | Supply for Order 100046308, Item 3 cannot be changed 90024955 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002735 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024955 | 05 | Preparation | 0000144829 | 3 | 0 | EA | 102000000029292 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024955_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-06-25 | 0 |  | 2025-02-24 |  | 2025-03-01 | MLO Gasket |  | 0 | 2 | 0 | 90024955 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10304292 | GASKET;SWCI,200MM,CL150,3MM,316L/GR/316 | 2024-01-02 | W |  | 0050 | Replace lube oil filters - 12 micron | INT | Replace lube oil filters - 12 micron | 5 |  | 90024955_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000144178 | S002 | 30 | 30 | 5300002735 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144829 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Estimated costs | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100032677 | 0020 | 0060 | 100032677 | CV-OH 3" 300# 118TCV501 | AA53.118TCV501 | VALVE,1K1820E1 L/O COOL BYPASS TEMP CTRL | AA01 | 20 | WO item has not been released yet | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2 | EA | 54 | 0 | 0 | 0 |  | 15.01 - PR Never line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131169 | 6 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032677 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130519 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-25 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039501 | 0020 | 0030 | 100039501 | Replace - Asbestos gaskets 1K1820V5 | AA53.1K1820V5 | TANK,EMERG LUBE OIL RUNDOWN 1K1820 | AA01 | 30 | WO item has not been released yet | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 1 | EA | 54 | 0 | 0 | 0 |  | 18.01 - At PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000137955 | 3 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-08-01 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  |  | 0020 | Remove & Replace Gaskets (x3) | INT | Remove & Replace Gaskets (x3) | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137357 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0300 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 40 | EA | 54 | 5 | 30 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 30 cannot be changed 90032376 item 280 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 30 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0280 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0280 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 30 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 300 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | WORK | 200059456 | 0030 | 0030 | 200059456 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.520RV02 | PSV,5P20040 FROM 5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 1 | EA | 54 | 5 | 30 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200059456, Item 3 cannot be changed 90024947 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300001576 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024947 | 05 | Preparation | 0000093805 | 3 | 0 | EA | 102000000031880 | 102000000026941 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024947_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024947 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-01-01 | W |  | 0030 | Remove / Install PSV | INT | Remove / Install PSV |  | Ready for Release | 90024947_0020 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000093175 | S002 | 30 | 30 | 5300001576 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  | 2025-01-15 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 93805 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed/Partially confirmed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0040 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | WO item has not been released yet | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 1 | EA | 54 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117838 | 4 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200082188 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000117251 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0120 | 0010 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2 | EA | 54 | 5 | 30 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089887, Item 3 cannot be changed 90025037 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 3 | 0 | EA | 102000000031990 | 101000000121087 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | FG Spading |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash | 5 | Ready for Release | 90025037_0030 |  |  | LN1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0160 | 0010 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 1 | EA | 54 | 5 | 30 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089887, Item 14 cannot be changed 90025037 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 14 | 0 | EA | 102000000032005 | 102000000029858 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | FG De-Spade |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-10-16 | W |  | 0160 | Remove Positive Isolations | INT | Remove Positive Isolations | 5 | Ready for Release | 90025037_0140 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0120 | 0010 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2 | EA | 54 | 5 | 30 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089887, Item 3 cannot be changed 90025037 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 3 | 0 | EA | 102000000031990 | 102000000029857 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | FG Spading |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash | 5 | Ready for Release | 90025037_0030 |  |  | LN1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0120 | 0080 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 3 | EA | 54 | 5 | 30 | 3 | EA | 17.10 - SOH @ AA01/AA02 | Supply for Order 200089888, Item 16 cannot be changed 90025038 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025038 | 05 | Preparation | 0000128157 | 16 | 0 | EA | 102000000032002 | 102000000029900 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025038_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025038 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025038_0100 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 100 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0120 | 0070 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 3 | EA | 54 | 5 | 30 | 3 | EA | 17.10 - SOH @ AA01/AA02 | Supply for Order 200089889, Item 16 cannot be changed 90025039 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 16 | 0 | EA | 102000000032028 | 102000000026939 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025039_0100 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 100 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0120 | 0010 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 3 | EA | 54 | 5 | 30 | 3 | EA | 18.12 - SOH @ AA02 | Supply for Order 200089890, Item 17 cannot be changed 90025059 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025059 | 05 | Preparation | 0000128159 | 17 | 0 | EA | 102000000032017 | 102000000027094 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025059_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025059 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025059_0020 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 30 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0120 | 0010 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 3 | EA | 54 | 5 | 30 | 3 | EA | 18.12 - SOH @ AA02 | Supply for Order 200089891, Item 11 cannot be changed 90025062 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025062 | 05 | Preparation | 0000128160 | 11 | 0 | EA | 102000000032020 | 102000000026940 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025062_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025062_0040 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 40 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2640 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 12 | EA | 54 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 391 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0060 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | WO item has not been released yet | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 1 | EA | 54 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235400 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232443 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-10-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200147137 | 0020 | 0020 | 200147137 | 10Y MV-RE 3" 300# 141CHV2043 | AA53.141CHV2043 | VALVE,CHECK 1E407 RE INJ VAPOURISER | AA01 | 10 | WO item has not been released yet | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2 | EA | 54 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235409 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  |  |  |  | 200147137 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  |  | 0020 | Remove & Replace NRV | INT | Remove & Replace NRV | 5 | Ready for Release |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232452 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0080 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 2 | EA | 54 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 26 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0070 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10307485 | VALVE;POPPET,PARKER N35461091 | 2 | EA | 0 | 1 | 3 | 0 |  | 13.02 - ETA 07.04.25 PO 4500034488 Score CPT | Supply for Order 100085072, Item 9 cannot be changed 90029880 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029880 | 05 | Preparation | 0000267773 | 9 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029880_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029880 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307485 | VALVE;POPPET,PARKER N35461091 | 2025-01-30 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029880_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 | 30 | 30 | 5300019757 | 90 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0040 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 1 | EA | 2 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 4 cannot be changed 90025036 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 4 | 0 | EA | 102000000027570 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Station face |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0020 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 1 | EA | 2 | 0 | 0 | 1 | EA | 24.10 - SOH @ AA02 | Supply for Order 200147550, Item 4 cannot be changed 90025043 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 4 | 0 | EA | 102000000027571 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Station face |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025043_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0020 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 1 | EA | 2 | 0 | 0 | 0 |  | 18.12 - SOH @ AA02 | Supply for Order 200147552, Item 4 cannot be changed 90025045 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Station face |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0130 | 0160 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10307736 | RING,PST;GE 1473M46P04 | 1 | EA | 5 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 16 cannot be changed 90025036 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 16 | 0 | EA | 102000000027578 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307736 | RING,PST;GE 1473M46P04 | 2024-10-16 | W |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 3 | Ready for Release | 90025036_0140 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 16 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0130 | 0020 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307736 | RING,PST;GE 1473M46P04 | 1 | EA | 5 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 21 cannot be changed 90025043 item 190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 21 | 0 | EA | 102000000027580 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307736 | RING,PST;GE 1473M46P04 | 2024-10-17 | W |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 3 | Ready for Release | 90025043_0190 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 21 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0130 | 0020 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307736 | RING,PST;GE 1473M46P04 | 1 | EA | 5 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 21 cannot be changed 90025045 item 200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 21 | 0 | EA | 102000000027581 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307736 | RING,PST;GE 1473M46P04 | 2024-10-17 | W |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 3 |  | 90025045_0200 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 21 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 200 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0120 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10307752 | RING;NP 9634M85P01 | 1 | EA | 2 | 0 | 2 | 1 | EA | 31.01 - SOH @ AA02 | Supply for Order 200147548, Item 37 cannot be changed 90025036 item 310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 37 | 0 | EA | 102000000032319 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Carbon ring |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307752 | RING;NP 9634M85P01 | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0310 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 37 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 310 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0090 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307752 | RING;NP 9634M85P01 | 1 | EA | 2 | 0 | 2 | 1 | EA | 18.12 - SOH @ AA02 | Supply for Order 200147550, Item 11 cannot be changed 90025043 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 11 | 0 | EA | 102000000032320 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Carbon ring |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307752 | RING;NP 9634M85P01 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025043_0100 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0090 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307752 | RING;NP 9634M85P01 | 1 | EA | 2 | 0 | 2 | 0 |  | 15.01 - ETA 04.09.25 PO 4500040063 BH expedite BHGE maybe in some in LM workshop | Supply for Order 200147552, Item 11 cannot be changed 90025045 item 100 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 11 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Carbon ring |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307752 | RING;NP 9634M85P01 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0100 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100076521 | 0020 | 0020 | 100076521 | Investigate Faulty T/C (1) GT4007 | AA53.407TE518B | TXDCR,TEMP HP COMP DISCH GT4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307832 | SENSOR;NP L47314P04 | 1 | EA | 1 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 100076521, Item 2 cannot be changed 90025057 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016535 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025057 | 05 | Preparation | 0000233040 | 2 | 0 | EA | 102000000027507 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025057_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-09-08 | 0 |  | 2025-02-24 |  | 2025-03-01 | 407TE518B |  | 0 | 2 | 0 | 90025057 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307832 | SENSOR;NP L47314P04 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025057_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000230205 | S002 | 30 | 30 | 5300016535 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-04-18 | 233040 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0180 | 0170 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10307833 | GASKET,SW;GE J219P03 | 1 | EA | 32 | 0 | 1 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 17 cannot be changed 90025036 item 150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 17 | 0 | EA | 102000000026590 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | VBV Rig |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307833 | GASKET,SW;GE J219P03 | 2024-10-16 | W |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 3 | Ready for Release | 90025036_0150 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 17 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0180 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307833 | GASKET,SW;GE J219P03 | 1 | EA | 32 | 0 | 1 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 22 cannot be changed 90025043 item 200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 22 | 0 | EA | 102000000026591 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | VBV Rig |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307833 | GASKET,SW;GE J219P03 | 2024-10-17 | W |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 3 | Ready for Release | 90025043_0200 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 22 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 200 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0180 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10307833 | GASKET,SW;GE J219P03 | 1 | EA | 32 | 0 | 1 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 22 cannot be changed 90025045 item 210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 22 | 0 | EA | 102000000026592 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | VBV Rig |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307833 | GASKET,SW;GE J219P03 | 2024-10-17 | W |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 3 |  | 90025045_0210 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 22 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 210 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDGT7 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0110 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | WO item has not been released yet | 10307865 | CLUTCH ASY,DRV;NP RJO06012 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235960 | 36 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | Clutch OnCon |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307865 | CLUTCH ASY,DRV;NP RJO06012 |  |  |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000232966 |  | 74 | 74 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT8 | Released | 2024-10-17 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0080 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | WO item has not been released yet | 10307865 | CLUTCH ASY,DRV;NP RJO06012 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235962 | 10 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  |  |  |  | Clutch OnCon |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307865 | CLUTCH ASY,DRV;NP RJO06012 |  |  |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000232968 |  | 74 | 74 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT9 | Released | 2024-10-17 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0080 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | WO item has not been released yet | 10307865 | CLUTCH ASY,DRV;NP RJO06012 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235964 | 10 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | Clutch OnCon |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307865 | CLUTCH ASY,DRV;NP RJO06012 |  |  |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000232970 |  | 74 | 74 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0080 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10307870 | PIPE,FLEX;NP RTO49543 | 1 | EA | 6 | 0 | 3 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 14 cannot be changed 9026831 item 140 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121407 | 9026831 | 05 | Preparation | 0000281227 | 14 | 0 | EA |  |  | 102000000032414 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R4FL | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000386099_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056298 | 1020 | 2026-06-30 | 1 |  | 2025-02-04 | 4900226464_2025_0001 | 2025-03-01 | 200177498 | 5000386099_2025_0001 | 0 | 2 | 0 | 90028588 | 1 | 0 | 180121407 | 2 | 0 | 0 | X | L | 4900226464 | 2025 |  | 5000386099 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307870 | PIPE,FLEX;NP RTO49543 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 9026831_0140 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDGT7 | MJ | 1000004989 | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0080 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10307870 | PIPE,FLEX;NP RTO49543 | 1 | EA | 6 | 0 | 3 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 14 cannot be changed 9026832 item 140 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121408 | 9026832 | 05 | Preparation | 0000281238 | 14 | 0 | EA |  |  | 102000000032415 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R4FL | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000386125_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056299 | 1020 | 2025-06-30 | 1 |  | 2025-02-04 | 4900226482_2025_0001 | 2025-03-01 | 200177499 | 5000386125_2025_0001 | 0 | 2 | 0 | 90028589 | 1 | 0 | 180121408 | 2 | 0 | 0 | X | L | 4900226482 | 2025 |  | 5000386125 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307870 | PIPE,FLEX;NP RTO49543 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 9026832_0140 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDGT8 | MJ | 1000004989 | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0080 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10307870 | PIPE,FLEX;NP RTO49543 | 1 | EA | 6 | 0 | 3 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177720, Item 14 cannot be changed 9026830 item 140 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121406 | 9026830 | 05 | Preparation | 0000281240 | 14 | 0 | EA |  |  | 102000000032413 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R4FL | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000386113_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056297 | 1020 | 2025-06-30 | 1 |  | 2025-02-04 | 4900226446_2025_0001 | 2025-03-01 | 200177720 | 5000386113_2025_0001 | 0 | 2 | 0 | 90028590 | 1 | 0 | 180121406 | 2 | 0 | 0 | X | L | 4900226446 | 2025 |  | 5000386113 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307870 | PIPE,FLEX;NP RTO49543 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 9026830_0140 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDGT9 | MJ | 1000004989 | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0010 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10308502 | PENETRANT;YIELD AERO,400GM,CHEMSEARCH | 12 | EA | 24 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 | Supply for Order 500004676, Item 1 cannot be changed 90031855 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 1 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0010 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10308502 | PENETRANT;YIELD AERO,400GM,CHEMSEARCH | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0010 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 |  | 30 | 5300021195 | 10 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2340 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10309092 | GASKET,C4430,209 X 223 X 2MM | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 313 cannot be changed 90028419 item 2450 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 313 | 0 | EA | 102000000030491 | 101000000135631 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10309092 | GASKET,C4430,209 X 223 X 2MM | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2450 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 313 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  |  | 5300013090 | 2480 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2350 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10309093 | GASKET,C4430,310 X 340 X 2MM,RF | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 314 cannot be changed 90028419 item 2460 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 314 | 0 | EA | 101000000135517 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10309093 | GASKET,C4430,310 X 340 X 2MM,RF | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2460 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 314 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  |  | 5300013090 | 2490 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2370 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10309094 | O-RING,VITON-A,4.00MM,30.00MM ID,70 | 2 | EA | 2 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 529 cannot be changed 90028419 item 3840 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 529 | 0 | EA | 102000000030491 | 102000000030377 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10309094 | O-RING,VITON-A,4.00MM,30.00MM ID,70 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_3840 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 529 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3870 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2360 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10309095 | SEAT,THOMASSEN M5002,VV,LUBE OIL,VITON | 4 | EA | 0 | 0 | 4 | 4 | EA | 21.0 - SOH @ AA01 | Supply for Order 200091513, Item 315 cannot be changed 9026997 item 2470 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180125808 | 9026997 | 05 | Preparation | 0000129822 | 315 | 0 | EA |  |  | 101000000142526 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000402890_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000057068 | 1020 | 2025-07-03 | 4 |  | 2025-02-16 | 4900238388_2025_0001 | 2025-03-01 |  | 5000402890_2025_0001 | 0 | 2 | 0 | 90028419 | 4 | 0 | 180125808 | 2 | 0 | 0 | X | L | 4900238388 | 2025 |  | 5000402890 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10309095 | SEAT,THOMASSEN M5002,VV,LUBE OIL,VITON | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 9026997_2470 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 315 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2500 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-11-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-05 | INLEC | 100033543 | 0020 | 0030 | 100033543 | GT4008 T48 Harness Changeout | AA53.408TE519F | TXDCR,TEMP GT4008 LP COMPR INLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10309519 | CABLE ASY;GE L44737P04 | 1 | ASY | 1 | 0 | 0 | 1 | ASY | 02.12 - SOH @ AA02 | Supply for Order 100033543, Item 3 cannot be changed 90028283 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018584 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90028283 | 05 | Preparation | 0000132064 | 3 | 0 | ASY | 102000000029942 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028283_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | AA53.408TE51 |  | 0 | 2 | 0 | 90028283 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10309519 | CABLE ASY;GE L44737P04 | 2024-11-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90028283_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000131433 | S002 |  |  | 5300018584 | 30 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132064 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0020 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10310267 | VALVE,GATE,50MM,CL300,RF,LTCS,L3GE | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 600001678, Item 1 cannot be changed 90024966 item 10 already exists | Material picked; currently at SW3R01C01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004588 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024966 | 05 | Preparation | 0000084596 | 1 | 0 | EA |  |  | 101000000070235 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R01C01B |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-09-22 | 2024-09-22 | Y | 1001 | 2024-01-02 | ODST-0090024966_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 |  | 2025-02-24 |  | 2025-03-01 | Critical |  | 0 | 2 | 0 | 90024966 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10310267 | VALVE,GATE,50MM,CL300,RF,LTCS,L3GE | 2024-01-02 | W |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify |  |  | 90024966_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ | 20003041 | AU1072 | 1000084000 | S002 | 30 | 30 | 5300004588 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2024-09-20 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84596 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 200144759 | 0010 | 0010 | 200144759 | 2Y Flame Eyes F/Test/Repl (8) 4KT1410 | AA53.414XE401 | DET,FLAME COMB CHAMB 3 PRIM ZNE 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10310366 | SENSOR,FLAME;REUTER-STOKES RSFS9004 | 8 | EA | 19 | 0 | 1 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200144759, Item 1 cannot be changed 90025040 item 10 already exists | Material picked; currently at WH2-PACK-SD-1B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300016476 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025040 | 05 | Preparation | 0000231909 | 1 | 0 | EA |  |  | 102000000027739 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1B | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025040_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-11-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | 4KT1410 |  | 0 | 2 | 0 | 90025040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10310366 | SENSOR,FLAME;REUTER-STOKES RSFS9004 | 2024-10-16 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90025040_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000229025 | S002 | 30 | 30 | 5300016476 | 10 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231909 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 200144760 | 0010 | 0010 | 200144760 | 2Y Flame Eyes F/Test/Repl (8) 4KT1430 | AA53.414XE501 | DET,FLAME COMB CHAMB 3 PRIM ZNE 4KT1430 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10310366 | SENSOR,FLAME;REUTER-STOKES RSFS9004 | 8 | EA | 19 | 0 | 1 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200144760, Item 1 cannot be changed 90025041 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016477 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025041 | 05 | Preparation | 0000231910 | 1 | 0 | EA | 102000000027740 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025041_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-11-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | 4KT1430 |  | 0 | 2 | 0 | 90025041 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10310366 | SENSOR,FLAME;REUTER-STOKES RSFS9004 | 2024-10-16 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90025041_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000229026 | S002 | 30 | 30 | 5300016477 | 10 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231910 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100042568 | 0010 | 0030 | 100042568 | Transmitter Replace 414PT016C | AA53.414PT016C | TX,PRESS INTERVALVE GAS FLOW 4KT1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10310370 | TX,PRESS;PIGNONE RTO507931821 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.10 - ETA 14.05.25 PO 4500031815 BH | Supply for Order 100042568, Item 3 cannot be changed 90025017 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015891 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025017 | 05 | Preparation | 0000141082 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025017_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2022-04-20 | 0 |  | 2025-02-24 |  | 2025-03-01 | 10310370 |  | 0 | 2 | 0 | 90025017 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10310370 | TX,PRESS;PIGNONE RTO507931821 | 2024-09-30 | W |  | 0010 | Complete Replacement | INT | Complete Replacement |  |  | 90025017_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000140484 | S002 | 30 | 70 | 5300015891 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141082 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-02-12 | 2025-03-03 | 2025-02-26 | 2025-05-19 | 2025-05-19 | INLEC | 100086261 | 0010 | 0010 | 100086261 | OPSD 3KT50 Flame det fault intermittent | AA53.360XE636A | DET,UV FLAME 3KT1450 TURBINE COMPART | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.02.2025) | 10310865 | DETECTOR,FLAME;UV,DET-TRONIC 006899040 | 1 | EA | 0 | 0 | 1 | 0 |  | 10.03 - PR 2000253778 RFQ | Supply for Order 100086261, Item 1 cannot be changed 90030601 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021081 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030601 | 05 | Preparation | 0000272260 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-P08-OPSD | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-10 | ODST-0090030601_0010 | 0 | 0 | 0 | 0 |  | 2025-03-01 | AA53 | 2025-05-19 |  |  | 2025-03-03 |  |  |  |  | 2027-06-30 | 0 |  | 2025-02-26 |  | 2025-03-03 | 360XE636A |  | 0 | 2 | 0 | 90030601 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10310865 | DETECTOR,FLAME;UV,DET-TRONIC 006899040 | 2025-02-10 | W |  | 0010 | OPSD 3KT50 Flame det fault intermittent | INT | OPSD 3KT50 Flame det fault intermittent |  | Opportune Shutdown | 90030601_0010 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000266940 | S002 | 30 | 30 | 5300021081 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-26 |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41088 | 2024-10-22 | 272260 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-19 | 2025-05-19 | 2025-05-19 | Pre-costed/Object created/Order Approved/Released/Settlement rule created/Material committed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10310868 | SENSOR,TEMP;DE1888K3,DTRONICS 003240221 | 3 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 588 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 160XE1216A-C |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10310868 | SENSOR,TEMP;DE1888K3,DTRONICS 003240221 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3070 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10310868 | SENSOR,TEMP;DE1888K3,DTRONICS 003240221 | 3 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 585 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 160XE1226A-C |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10310868 | SENSOR,TEMP;DE1888K3,DTRONICS 003240221 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-07 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-03 | VALVE | 100078477 | 0050 | 0040 | 100078477 | CV-OH 1" 600# 113LCV09 | AA53.113LCV09 | VALVE,1V1301 REGEN GAS WTR KO DRUM | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.10.2024) | 10312209 | BUSH ASY;SEAT RING,FISHER 25A6683X072 | 1 | EA | 1 | 0 | 0 | 1 | EA | 25.02 - SOH @ AA02 | Supply for Order 100078477, Item 6 cannot be changed 90025025 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016139 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025025 | 05 | Preparation | 0000241492 | 6 | 0 | EA | 101000000148357 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-07 | ODST-0090025025_0040 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2024-10-16 | 0 |  | 2025-03-26 |  | 2025-03-31 |  |  | 0 | 2 | 0 | 90025025 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10312209 | BUSH ASY;SEAT RING,FISHER 25A6683X072 | 2024-10-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90025025_0040 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000238214 | S002 | 30 | 30 | 5300016139 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-05-31 | 241492 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 100086204 | 0020 | 0010 | 100086204 | FGRV Solenoid Replace (20VG) 124XV13 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.10.2024) | 10312468 | VALVE,SLND;ASCO NFHTXB223A025V125DC22502 | 1 | EA | 1 | 1 | 2 | 1 | EA | 28.10 - SOH @ AA02 | Supply for Order 100086204, Item 1 cannot be changed 90025080 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016891 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124184 | 90025080 | 05 | Preparation | 0000272396 | 1 | 0 | EA | 102000000031666 | 102000000029407 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-25 | IDST-0180124184 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 1 |  | 2025-02-11 | 4900234067_2025_0001 | 2025-03-01 | 124XV13 |  | 0 | 2 | 0 | 90025080 | 0 | 0 | 180124184 | 2 | 0 | 0 | X | L | 4900234067 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10312468 | VALVE,SLND;ASCO NFHTXB223A025V125DC22502 | 2024-10-25 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025080_0010 |  |  | DG1 |  | A3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267095 | S002 | 30 | 30 | 5300016891 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272396 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2960 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10312468 | VALVE,SLND;ASCO NFHTXB223A025V125DC22502 | 2 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 574 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 20VG |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10312468 | VALVE,SLND;ASCO NFHTXB223A025V125DC22502 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 200088969 | 0020 | 0010 | 200088969 | 8Y ABB Motor Starter Insp S61D2A3R01 | AA53.S61D2A3R01 | START,1KT1450V4KM1 LUBE OIL MIST SEP | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(29.07.2024) | 10313057 | GREASE;ISOFLEX TOPAS,KLUBER A004179N | 2 | CQ | 5 | 5 | 4 | 2 | CAN | 02.10 - SOH @ AA01 | Supply for Order 200088969, Item 1 cannot be changed 90024990 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013337 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90024990 | 05 | Preparation | 0000127199 | 1 | 0 | CAN | 102000000027902 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | Sub 61 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-29 | ODST-0090024990_0090_0020/90024990_0090_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-11-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024990 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10313057 | GREASE;ISOFLEX TOPAS,KLUBER A004179N | 2024-07-29 | W |  | 0020 | Complete PRT | INT | Complete PRT |  |  | 90024990_0090_0020/90024990_0090_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000126681 | S002 | 30 | 30 | 5300013337 | 10 |  |  | 0 | 2 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127199 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 200088971 | 0020 | 0010 | 200088971 | 8Y LV MNS2 ABB MOTOR STARTER INSP S61D2B | AA53.S61D2B2R08 | START,1KT1420V4M1 LUBE OIL MIST SEP | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10313057 | GREASE;ISOFLEX TOPAS,KLUBER A004179N | 1 | CQ | 5 | 5 | 4 | 1 | CQ | 13.01 - SOH @ AA01 | Supply for Order 200088971, Item 1 cannot be changed 90025026 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016359 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90025026 | 05 | Preparation | 0000127261 | 1 | 0 | CQ | 102000000031497 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-14 | ODST-0090025026_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-11-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025026 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10313057 | GREASE;ISOFLEX TOPAS,KLUBER A004179N | 2024-10-14 | W |  | 0020 | Complete PRT | INT | Complete PRT |  |  | 90025026_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000126683 | S002 | 30 | 30 | 5300016359 | 10 |  |  | 0 | 1 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127261 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SD4403 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100031878 | 0030 | 0010 | 100031878 | Replace Flow Tx - 44FIT521 | AA53.44FIT521 | METER,FLOW K4403 SEALGAS PRIM VENT | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10313669 | FMTR;NP RJO01742 | 1 | EA | 0 | 0 | 2 | 0 |  | 18.11 - ETA 17.02.25 PO 4500035255 NP | Supply for Order 100031878, Item 1 cannot be changed 90025109 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017865 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025109 | 05 | Preparation | 0000130319 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025109_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-11-08 | 0 |  | 2025-02-24 |  | 2025-03-01 | 44FIT521 |  | 0 | 2 | 0 | 90025109 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10313669 | FMTR;NP RJO01742 | 2024-11-13 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 90025109_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SD4403 | MJ |  | AU1072 | 1000129688 | S002 |  | 30 | 5300017865 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 130319 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD4403 | Released | 2024-01-30 | 2025-03-01 | 2024-05-04 | 2024-05-07 | 2024-05-07 | INLEC | 100042451 | 0090 | 0010 | 100042451 | Replace Flow Tx - 44FIT520 | AA53.44FIT520 | METER,FLOW K4403 SEALGAS PRIM VENT | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.03.2024) | 10313669 | FMTR;NP RJO01742 | 1 | EA | 0 | 0 | 2 | 1 | EA | 25.09 - At KGP | Supply for Order 100042451, Item 3 cannot be changed 180068650 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300005745 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180068650 | 90007769 | 05 | Preparation | 0000140972 | 3 | 0 | EA | 102000000016984 |  | 107000000000064 |  |  |  |  | WorkPackLink | P07WHS-R9A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-30 | GRST-5000204072_2024 | 0 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2025-03-01 |  |  | 100000028213 | 1020 | 2021-12-26 | 1 |  | 2024-09-11 | 4900129554_2024_0001 | 2024-05-07 | 44FIT520 | 5000204072_2024_0001 | 0 | 2 | 0 | 90007769 | 1 | 0 | 180068650 | 2 | 0 | 0 | X | L | 4900129554 | 2024 |  | 5000204072 | 2024 | 0 |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10313669 | FMTR;NP RJO01742 | 2024-03-15 | W |  | 0090 | Replace Flow Meter | INT | Replace Flow Meter | 5 |  | 90007769_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SD4403 | MJ |  | AU1072 | 1000140401 | S002 |  | 30 | 5300005745 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140972 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1590 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10313775 | WASHER,THR;NP RRP40123 | 32 | EA | 32 | 0 | 0 | 32 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 201 cannot be changed 90028419 item 1570 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 201 | 0 | EA | 102000000030498 | 102000000030365 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1570 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10313775 | WASHER,THR;NP RRP40123 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1570 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 201 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1600 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0050 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue detected, please check message in derivation or orchestration log | 10314704 | METER;PROC,50X100X203MM,FLUKE FLUKE789 | 1 | EA | 2 | 0 | 2 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 500005166, Item 58 cannot be changed 90032306 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 58 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0040 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Locko |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10314704 | METER;PROC,50X100X203MM,FLUKE FLUKE789 | 2025-03-03 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0040 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 58 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 530 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0100 | 0130 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 1 | EA | 3 | 0 | 13 | 1 | EA | 10.01 - Picked @ KSF | Supply for Order 200147548, Item 13 cannot be changed 90025036 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 13 | 0 | EA | 102000000029362 | 101000000132298 | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE Sump gask |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 2024-10-16 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 | Ready for Release | 90025036_0110 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 13 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0100 | 0030 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 1 | EA | 3 | 0 | 13 | 1 | EA | 03.01 - SOH @ AA01 | Supply for Order 200147550, Item 18 cannot be changed 90025043 item 160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 18 | 0 | EA | 102000000029801 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE Sump gask |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 2024-10-17 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 | Ready for Release | 90025043_0160 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 18 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0100 | 0030 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 1 | EA | 3 | 0 | 13 | 1 | EA | 03.01 - SOH @ AA01 | Supply for Order 200147552, Item 18 cannot be changed 90025045 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 18 | 0 | EA | 102000000029802 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE Sump gask |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 2024-10-17 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 |  | 90025045_0170 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 18 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 170 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 3330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.10.2024) | 10317411 | COUPLING;ALLOY ST,THOMASSEN 65148401004 | 1 | EA | 0 | 0 | 0 | 0 |  | 14.10 - ETA 26.03.25 PO W451778948 HOWDEN | Supply for Order 200091513, Item 771 cannot be changed 90028419 item 4910 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4950 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90028419 | 05 | Preparation | 0000129822 | 771 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4910 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10317411 | COUPLING;ALLOY ST,THOMASSEN 65148401004 | 2024-10-02 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_4910 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 771 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4950 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2560 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | No issue identified | 10317411 | COUPLING;ALLOY ST,THOMASSEN 65148401004 | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000129822 | 748 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10317411 | COUPLING;ALLOY ST,THOMASSEN 65148401004 |  |  |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0060 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10317610 | O-RING;FR58/90,0.275",7.475"ID,95,BS443 | 6 | EA | 24 | 0 | 0 | 6 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 96 cannot be changed 90023534 item 480 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 96 | 0 | EA | 102000000030438 | 102000000031168 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0480 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10317610 | O-RING;FR58/90,0.275",7.475"ID,95,BS443 | 2024-05-11 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 90023534_0480 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 96 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 750 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0122 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10317610 | O-RING;FR58/90,0.275",7.475"ID,95,BS443 | 4 | EA | 24 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 23 cannot be changed 90023534 item 150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 23 | 0 | EA | 102000000030454 | 102000000031169 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10317610 | O-RING;FR58/90,0.275",7.475"ID,95,BS443 | 2024-01-02 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0150 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 23 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 220 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0070 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10317611 | O-RING;FR58/90,0.275",9.975"ID,95,BS449 | 6 | EA | 10 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 97 cannot be changed 90023534 item 490 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 97 | 0 | EA | 102000000030438 | 101000000142829 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10317611 | O-RING;FR58/90,0.275",9.975"ID,95,BS449 | 2024-05-11 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 90023534_0490 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 97 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 760 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0070 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10317611 | O-RING;FR58/90,0.275",9.975"ID,95,BS449 | 6 | EA | 10 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 97 cannot be changed 90023534 item 490 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 97 | 0 | EA | 102000000030438 | 102000000031171 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10317611 | O-RING;FR58/90,0.275",9.975"ID,95,BS449 | 2024-05-11 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 90023534_0490 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 97 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 760 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0132 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10317611 | O-RING;FR58/90,0.275",9.975"ID,95,BS449 | 4 | EA | 10 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 24 cannot be changed 90023534 item 160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 24 | 0 | EA | 102000000030454 | 102000000031170 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10317611 | O-RING;FR58/90,0.275",9.975"ID,95,BS449 | 2024-01-02 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0160 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 24 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 230 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-15 | 2025-03-01 | 2024-09-20 | 2025-03-01 | 2025-03-01 | VALVE | 100033225 | 0020 | 0010 | 100033225 | CV-RE 1" 300# 960UZ652 | AA53.960UZ652 | VALVE,GT4009V6 GAS TURB CO2 EXT DISCH | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.05.2024) | 10318870 | VALVE,DISCH;PISTA 450025060 | 1 | EA | 0 | 0 | 0 | 1 | EA | 22.11 - material consumed | Supply for Order 100033225, Item 1 cannot be changed 180088739 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300010228 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180088739 | 90016107 | 07 | Execution | 0000131737 | 1 | 0 | EA |  |  | 102000000022609 |  |  |  |  | WorkPackLink | P08C10L3 | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-05-15 |  | 0 | 0 | 0 | 0 |  | 2024-09-21 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000038362 | 1020 | 2025-04-28 | 1 |  | 2024-11-01 | 4900163094_2024_0001 | 2024-09-23 | 100033225 | 5000264675_2024_0001 | 0 | 2 | 0 | 90016107 | 1 | 0 | 180088739 | 2 | 0 | 0 | X | L | 4900163094 | 2024 |  | 5000264675 | 2024 | 0 |  | 2024-09-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10318870 | VALVE,DISCH;PISTA 450025060 | 2024-05-15 | W |  | 0020 | Punchlist & Closeout WP100033225MET001 | ENON | Punchlist & Closeout WP100033225MET001 |  |  | 90016107_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000131147 | S002 |  |  | 5300010228 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-09-20 |  |  |  |  | 1070 |  | 2024-10-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131737 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Partially confirmed/Job In Process/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-05-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100033225 | 0020 | 0040 | 100033225 | CV-RE 1" 300# 960UZ652 | AA53.960UZ652 | VALVE,GT4009V6 GAS TURB CO2 EXT DISCH | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10318870 | VALVE,DISCH;PISTA 450025060 | 1 | EA | 0 | 0 | 0 | 0 |  | 20.01 - ETA 24.04.25 PO 4500042120 PISTER FCA | Supply for Order 100033225, Item 4 cannot be changed 90028270 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300010228 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028270 | 07 | Execution | 0000131737 | 4 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-15 | ODST-0090028270_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100033225 |  | 0 | 2 | 0 | 90028270 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10318870 | VALVE,DISCH;PISTA 450025060 | 2024-12-13 | W |  | 0020 | Punchlist & Closeout WP100033225MET001 | ENON | Punchlist & Closeout WP100033225MET001 |  |  | 90028270_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000131147 | S002 |  |  | 5300010228 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2024-10-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131737 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Partially confirmed/Job In Process/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2024-10-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 200062886 | 0020 | 0010 | 200062886 | 8Y LV WESTERN FEEDER MODULE INSP | AA53.S15D1A6R03 | FEEDER,1KT2410E3 LUBE OIL HEATER | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.10.2024) | 10318973 | GREASE;KLUBER KR44102 | 1 | CAN | 5 | 0 | 7 | 1 | CAN | 17.10 - SOH @ AA02 | Supply for Order 200062886, Item 1 cannot be changed 90025027 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016390 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90025027 | 05 | Preparation | 0000097188 | 1 | 0 | CAN | 102000000028442 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-15 | ODST-0090025027_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-17 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025027 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10318973 | GREASE;KLUBER KR44102 | 2024-10-15 | W |  | 0020 | Complete PRT | INT | Complete PRT |  |  | 90025027_0010 |  |  | DG0 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000096605 | S002 | 30 | 30 | 5300016390 | 10 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 97188 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-11-01 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147513 | 0010 | 0010 | 200147513 | 8Y Inspection LV MNS3 Non-Insum Starter | AA53.S24D16B4MA | START,MOTOR G4008PM1A SUB 2 S24D16 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.11.2024) | 10318973 | GREASE;KLUBER KR44102 | 1 | CAN | 5 | 0 | 7 | 1 | CAN | 10.01 - Picked @ KSF | Supply for Order 200147513, Item 1 cannot be changed 90025093 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017222 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90025093 | 05 | Preparation | 0000235924 | 1 | 0 | CAN | 102000000028441 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-01 | ODST-0090025093_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-16 | 0 |  | 2025-02-24 |  | 2025-03-01 | S24D16B4 |  | 0 | 2 | 0 | 90025093 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10318973 | GREASE;KLUBER KR44102 | 2024-11-01 | W |  | 0010 | Complete PRT | INT | Complete PRT | 3 |  | 90025093_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232930 | S002 | 30 | 30 | 5300017222 | 10 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235924 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-11-01 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147521 | 0020 | 0010 | 200147521 | 8Y INSP LV S24D16 MNS3 NON-INSUM STARTER | AA53.S24D16A7AA | START,MOTOR GT4007PM2 SUB 2 S24D16 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.11.2024) | 10318973 | GREASE;KLUBER KR44102 | 1 | CAN | 5 | 0 | 7 | 1 | CAN | 10.01 - Picked @ KSF | Supply for Order 200147521, Item 3 cannot be changed 90025094 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017223 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90025094 | 05 | Preparation | 0000235932 | 3 | 0 | CAN | 102000000028443 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-01 | ODST-0090025094_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-16 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4007 |  | 0 | 2 | 0 | 90025094 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10318973 | GREASE;KLUBER KR44102 | 2024-11-01 | W |  | 0020 | Punchlist & Closeout WP200147521IET001 | ENON | Punchlist & Closeout WP200147521IET001 |  |  | 90025094_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232938 | S002 | 30 | 30 | 5300017223 | 10 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235932 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-11-26 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-01 | INLEC | 200147523 | 0010 | 0010 | 200147523 | 4Y LV MNS3 INSUM Starter Insp - S35D16 | AA53.S35D16A5HA | START,MOTOR G4009S2M1, B8342 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(26.11.2024) | 10318973 | GREASE;KLUBER KR44102 | 1 | CAN | 5 | 0 | 7 | 1 | CAN | 21.01 - SOH @ AA02 | Supply for Order 200147523, Item 1 cannot be changed 90028280 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018396 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90028280 | 05 | Preparation | 0000235934 | 1 | 0 | CAN | 102000000033028 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-26 | ODST-0090028280_0010 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2025-05-25 | 0 |  | 2025-03-26 |  | 2025-03-31 | S35D16A5HA |  | 0 | 2 | 0 | 90028280 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10318973 | GREASE;KLUBER KR44102 | 2024-11-26 | W |  | 0010 | Complete PRT | INT | Complete PRT | 2 |  | 90028280_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232940 | S002 | 30 | 30 | 5300018396 | 10 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235934 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | WO item has not been released yet | 10319055 | HOSE,HYD,1.00" X 700MM,RBR,HSHY001 | 1 | ASY | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000129822 | 439 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10319055 | HOSE,HYD,1.00" X 700MM,RBR,HSHY001 |  |  |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | WO item has not been released yet | 10319057 | HOSE,HYD,1.00" X 630MM,RBR,HSHY002 | 1 | ASY | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000129822 | 440 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10319057 | HOSE,HYD,1.00" X 630MM,RBR,HSHY002 |  |  |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | WO item has not been released yet | 10319059 | HOSE,HYD,1.25" X1400MM,RBR,HSHY003 | 1 | ASY | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000129822 | 441 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10319059 | HOSE,HYD,1.25" X1400MM,RBR,HSHY003 |  |  |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3060 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | WO item has not been released yet | 10319072 | HOSE,HYD,0.50" X 800MM,RBR,HSHY004 | 1 | ASY | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000129822 | 442 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10319072 | HOSE,HYD,0.50" X 800MM,RBR,HSHY004 |  |  |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3020 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | WO item has not been released yet | 10319073 | HOSE,HYD,1.50" X 800MM,RBR,HSHY005 | 1 | ASY | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000129822 | 438 | 0 | [8 empty] | WorkPackLink |  | AU01-P08-DG ZOIL | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10319073 | HOSE,HYD,1.50" X 800MM,RBR,HSHY005 |  |  |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT9 | Released | 2024-10-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 100083725 | 0010 | 0050 | 100083725 | GT4009K1A - Vent Fan DE Bearing | AA53.GT4009K1A | FAN,TURBINE ACOUSTIC ENCL VENT,GT4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.10.2024) | 10319176 | PULLEY,FENNER 56-14M-115-F | 1 | EA | 1 | 0 | 0 | 1 | EA | 28.10 - SOH @ AA02 | Supply for Order 100083725, Item 5 cannot be changed 90025083 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016986 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025083 | 05 | Preparation | 0000260566 | 5 | 0 | EA | 102000000028474 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-28 | ODST-0090025083_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025083 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10319176 | PULLEY,FENNER 56-14M-115-F | 2024-10-27 | W |  | 0010 | GT4009K1A - Vent Fan DE Bearing | INT | GT4009K1A - Vent Fan DE Bearing |  |  | 90025083_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000256336 | S002 | 30 | 30 | 5300016986 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-09-02 | 260566 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-10-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 100083725 | 0010 | 0060 | 100083725 | GT4009K1A - Vent Fan DE Bearing | AA53.GT4009K1A | FAN,TURBINE ACOUSTIC ENCL VENT,GT4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.10.2024) | 10319177 | PULLEY,FENNER,80-14M-115-F | 1 | EA | 1 | 0 | 0 | 1 | EA | 28.10 - SOH @ AA02 | Supply for Order 100083725, Item 6 cannot be changed 90025083 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016986 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025083 | 05 | Preparation | 0000260566 | 6 | 0 | EA | 102000000028473 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-28 | ODST-0090025083_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025083 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10319177 | PULLEY,FENNER,80-14M-115-F | 2024-10-27 | W |  | 0010 | GT4009K1A - Vent Fan DE Bearing | INT | GT4009K1A - Vent Fan DE Bearing |  |  | 90025083_0050 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000256336 | S002 | 30 | 30 | 5300016986 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-09-02 | 260566 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0010 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10333800 | SEAL,LABYTH;AL,NP SMS35111 | 1 | SET | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000129822 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10333800 | SEAL,LABYTH;AL,NP SMS35111 |  |  |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0130 | 0042 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10333856 | RING,SEALING;THOMASSEN 2770102900 | 1 | EA | 0 | 0 | 1 | 1 | EA | 29.01 - At KGP | Supply for Order 200091126, Item 140 cannot be changed 180116362 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180116362 | 9024799 | 05 | Preparation | 0000129360 | 140 | 0 | EA |  |  | 102000000030519 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WHS-R3B | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000363786_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053006 | 1020 | 2023-04-03 | 1 |  | 2025-01-18 | 4900213336_2025_0001 | 2025-03-01 |  | 5000363786_2025_0001/5000363778_2025_0001/5000363777_2025_0001 | 0 | 2 | 0 | 90023534 | 1 | 0 | 180116362 | 2 | 0 | 0 | X | L | 4900213336 | 2025 |  | 5000363786 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10333856 | RING,SEALING;THOMASSEN 2770102900 | 2024-05-11 | W |  | 0130 | PRIMARY, INTER & OIL SCRAPER SEALS | INT | PRIMARY, INTER & OIL SCRAPER SEALS |  |  | 9024799_0880 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 140 |  | 0 |  | 25SD2301 | MJ | 1000004850 | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1170 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-21 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0232 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10333857 | PIN,XHD,COMP;THOMASSEN 2239101400 | 2 | EA | 0 | 0 | 0 | 0 |  | 09.03 - ETA 19.03.25 PO 4500037854 ex Howden CPT | Supply for Order 200091126, Item 114 cannot be changed 90023534 item 640 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 920 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 114 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0640 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10333857 | PIN,XHD,COMP;THOMASSEN 2239101400 | 2024-05-11 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0640 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 114 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 920 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0460 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10333858 | SEAL ASY,COMP;THOMASSEN 2227144800 | 1 | EA | 0 | 0 | 0 | 0 |  | 09.12 - ETA 19.03.25 PO 4500038754 ex Howden | Supply for Order 200091108, Item 100 cannot be changed 90028420 item 660 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 100 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealAssy#6 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10333858 | SEAL ASY,COMP;THOMASSEN 2227144800 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 90028420_0660 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 100 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 690 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0200 | 3160 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10343771 | BUCKET,2ND STG;NP SMO1184304 | 1 | SET | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET |  | NEW |  |  |  | 05 | Preparation | 0000129822 | 753 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10343771 | BUCKET,2ND STG;NP SMO1184304 |  |  |  | 0200 | LP ROTOR ASSEMBLY | INT | LP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0200 | 3090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10343771 | BUCKET,2ND STG;NP SMO1184304 | 1 | SET | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET |  | NEW |  |  |  | 05 | Preparation | 0000129822 | 368 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10343771 | BUCKET,2ND STG;NP SMO1184304 |  |  |  | 0200 | LP ROTOR ASSEMBLY | INT | LP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | VALVE | 100079184 | 0050 | 0030 | 100079184 | CV-OH 1" 600# 124LCV26 | AA53.124LCV26 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 10345191 | ACTUATOR KIT,VV,CONTR;SAMSOM AK350 | 1 | KIT | 0 | 0 | 0 | 0 |  | 20.01 - ETA 25.03.25 PO 4500041815 SCORE CPT | Supply for Order 100079184, Item 7 cannot be changed 90028299 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019686 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028299 | 05 | Preparation | 0000244787 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028299_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079184 |  | 0 | 2 | 0 | 90028299 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10345191 | ACTUATOR KIT,VV,CONTR;SAMSOM AK350 | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028299_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 7 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241339 | S002 |  | 30 | 5300019686 | 30 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244787 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-30 | VALVE | 100079185 | 0050 | 0030 | 100079185 | CV-OH 1" 600# 124LCV27 | AA53.124LCV27 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 10345191 | ACTUATOR KIT,VV,CONTR;SAMSOM AK350 | 1 | KIT | 0 | 0 | 0 | 0 |  | 20.01 - ETA 25.03.25 PO 4500041815 SCORE CPT | Supply for Order 100079185, Item 3 cannot be changed 90028300 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019688 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028300 | 05 | Preparation | 0000244788 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028300_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079185 |  | 0 | 2 | 0 | 90028300 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10345191 | ACTUATOR KIT,VV,CONTR;SAMSOM AK350 | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028300_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241340 | S002 |  | 30 | 5300019688 | 30 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244788 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-30 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0100 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10347550 | O-RING;24.99X3.53MM,FKM,NP KHA024903501 | 1 | EA | 0 | 0 | 0 | 0 |  | 05.03 - ETA 05.04.25 PO 4500044464 BH; In Trans MOTtba GS5051853 1.7kg 22x22x15 | Supply for Order 200177498, Item 16 cannot be changed 90028588 item 160 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 16 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177498 |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10347550 | O-RING;24.99X3.53MM,FKM,NP KHA024903501 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028588_0160 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0100 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10347550 | O-RING;24.99X3.53MM,FKM,NP KHA024903501 | 1 | EA | 0 | 0 | 0 | 0 |  | 05.03 - ETA 05.04.25 PO 4500044464 BH; In Trans MOTtba GS5051853 1.7kg 22x22x15 | Supply for Order 200177499, Item 16 cannot be changed 90028589 item 160 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 16 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10347550 | O-RING;24.99X3.53MM,FKM,NP KHA024903501 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0160 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0100 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10347550 | O-RING;24.99X3.53MM,FKM,NP KHA024903501 | 1 | EA | 0 | 0 | 0 | 0 |  | 05.03 - ETA 05.04.25 PO 4500044464 BH; In Trans MOTtba GS5051853 1.7kg 22x22x15 | Supply for Order 200177720, Item 16 cannot be changed 90028590 item 160 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 16 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177720 |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10347550 | O-RING;24.99X3.53MM,FKM,NP KHA024903501 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 90028590_0160 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-06 | ROTAT | 100046308 | 0050 | 0040 | 100046308 | MOC-52386 - Tank Min Oil Replace - G4008 | AA53.G4008V1 | TANK,MINERAL OIL RESERVOIR G4008 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10349278 | GASKET;C4430,KLINGER 864432121 | 2 | KIT | 4 | 0 | 2 | 2 | KIT | 03.10 - SOH @ AA02 | Supply for Order 100046308, Item 4 cannot be changed 90024955 item 30 already exists | Material picked; currently at SW3R01D01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002735 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90024955 | 05 | Preparation | 0000144829 | 4 | 0 | KIT | 102000000027352 | 102000000027807 | 102000000029625 |  |  |  |  | WorkPackLink | SW3R01D01A | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024955_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-06-25 | 0 |  | 2025-02-24 |  | 2025-03-01 | MLO Gasket |  | 0 | 2 | 0 | 90024955 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10349278 | GASKET;C4430,KLINGER 864432121 | 2024-01-02 | W |  | 0050 | Replace lube oil filters - 12 micron | INT | Replace lube oil filters - 12 micron | 5 |  | 90024955_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000144178 | S002 | 30 | 30 | 5300002735 | 40 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144829 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Estimated costs | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0302 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10349371 | GASKET;CNAF,370 X 440 X 1.6MM,FF,C4430 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 126 cannot be changed 90023534 item 740 already exists | Material picked; currently at WH2-PACK-SD-1B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1030 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 126 | 0 | EA |  |  | 102000000030188 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1B | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10349371 | GASKET;CNAF,370 X 440 X 1.6MM,FF,C4430 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0740 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 126 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1030 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0092 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10349371 | GASKET;CNAF,370 X 440 X 1.6MM,FF,C4430 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 98 cannot be changed 90023534 item 500 already exists | Material picked; currently at WH2-PACK-SD-1B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 98 | 0 | EA |  |  | 102000000030187 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1B | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0500 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10349371 | GASKET;CNAF,370 X 440 X 1.6MM,FF,C4430 | 2024-05-11 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 90023534_0500 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 98 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 770 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0060 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10353453 | TAPE,MEASURE;5M,19MM,MTR | 5 | EA | 0 | 0 | 2 | 0 |  | 24.02 - ETA 27.03.25 PO 4500046941 BLACKWOODS CPT | Supply for Order 500005166, Item 7 cannot be changed 90031023 item 60 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031023 | 05 | Preparation | 0000294187 | 7 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031023_0060 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 | [5 empty] | 0 |  | 2025-03-06 |  | 2025-03-11 | TA LAG_VORN |  | 0 | 2 | 0 | 90031023 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10353453 | TAPE,MEASURE;5M,19MM,MTR | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0060 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 7 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 70 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD4403 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | INLEC | 100032350 | 0020 | 0020 | 100032350 | Vibration Probe Card Replace K4403 | AA53.44XT522 | TXDCR,K4403 COMPR ACCELEROMETER | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10401118 | MODULE,MON,SAF;BKV SM61021 | 1 | EA | 1 | 0 | 0 | 0 |  | 18.12 - qty 1 SOH at AA02 | Supply for Order 100032350, Item 2 cannot be changed 90025047 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016497 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  |  | 90025047 | 05 | Preparation | 0000130882 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025047_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-09-13 | 0 |  | 2025-02-24 |  | 2025-03-01 | FAR7 CM5 |  | 0 | 2 | 0 | 90025047 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10401118 | MODULE,MON,SAF;BKV SM61021 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025047_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SD4403 | MJ |  | AU1072 | 1000130232 | S002 |  | 30 | 5300016497 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 130882 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0030 | 0040 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10401794 | HEAD;REG,EXT,NP RPR22663 | 2 | EA | 11 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 4 cannot be changed 90028418 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 4 | 0 | EA | 102000000030534 | 102000000030226 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10401794 | HEAD;REG,EXT,NP RPR22663 | 2024-09-23 | W |  | 0030 | COMPRESSOR INSTRUMENTS | ENON | COMPRESSOR INSTRUMENTS | 5 |  | 90028418_0070 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0110 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10402782 | TAPE;LEAK TEST,33MX75MM | 20 | ROL | 0 | 0 | 40 | 20 | ROL | 20.02 - SOH @ AA02 | Supply for Order 500004676, Item 11 cannot be changed 9028889 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180134056 | 9028889 | 07 | Execution | 0000278102 | 11 | 0 | ROL |  |  | 102000000034438 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-12 | GRST-5000434885_2025 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060557 | 1020 | 2025-12-31 | 20 |  | 2025-03-10 | 4900263464_2025_0003 | 2025-04-01 | TA OPS/BAILS | 5000434885_2025_0002 | 0 | 2 | 0 | 90031855 | 20 | 0 | 180134056 | 2 | 0 | 0 | X | L | 4900263464 | 2025 |  | 5000434885 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10402782 | TAPE;LEAK TEST,33MX75MM | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 9028889_0100 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 11 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 110 |  |  | 0 | 20 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100074373 | 0020 | 0010 | 100074373 | Damaged Cable Replace AA53.414UV957 | AA53.414UV957 | VALVE,CTRL 4K1430 STG4 RECYCLE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10402910 | CABLE,INST;1.5MM2,OLEX WWC5502 | 25 | M | 195 | 0 | 0 | 25 | M | 18.10 - SOH @ AA02 | Supply for Order 100074373, Item 1 cannot be changed 90025053 item 10 already exists | Material picked; currently at SW3R06A01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016518 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90025053 | 05 | Preparation | 0000225767 | 1 | 0 | M |  |  | 102000000028698 |  |  |  |  | WorkPackLink | SW3R06A01A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 25 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025053_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414UV957 |  | 0 | 2 | 0 | 90025053 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10402910 | CABLE,INST;1.5MM2,OLEX WWC5502 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025053_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000223203 | S002 | 30 | 30 | 5300016518 | 10 |  |  | 0 | 25 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-08 | 225767 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0430 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10403727 | U-BOLT;GUIDE,BINDER 180006 | 7 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 41 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 7 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10403727 | U-BOLT;GUIDE,BINDER 180006 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0822 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE |  | 20 | No issue identified | 10404848 | COUPLING;KHI DRGZRC74B09 | -1 | SET | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET |  | DAMAGED |  |  |  | 05 | Preparation | 0000129754 | 96 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-06-05 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10404848 | COUPLING;KHI DRGZRC74B09 |  |  |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000129164 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0862 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10404848 | COUPLING;KHI DRGZRC74B09 | 1 | SET | 1 | 0 | 0 | 1 | SET | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 100 cannot be changed 90025019 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  | REFURB |  |  | 90025019 | 05 | Preparation | 0000129754 | 100 | 0 | SET | 102000000030046 |  | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | Coupling LS |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10404848 | COUPLING;KHI DRGZRC74B09 | 2024-09-30 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0030 |  |  | FR1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 100 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 30 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0560 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.02.2025) | 10405097 | IGV,PIGNONE MS3002,SET,(2 SEGMENTS/SET) | 1 | SET | 2 | 0 | 0 | 1 | SET | 03.02 - SOH @ AA02 | Supply for Order 200091513, Item 775 cannot be changed 90030042 item 10 already exists | Material picked; currently at 30-03-07-84A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4990 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90030042 | 05 | Preparation | 0000129822 | 775 | 0 | SET |  |  | 102000000034089 |  |  |  |  | WorkPackLink | 30-03-07-84A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090030042_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030042 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10405097 | IGV,PIGNONE MS3002,SET,(2 SEGMENTS/SET) | 2025-02-01 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90030042_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 775 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4990 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3340 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.10.2024) | 10405558 | CONVERTER,TORQUE,TWINDISC 4SG-1607-2 | 1 | EA | 1 | 0 | 0 | 0 |  | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 772 cannot be changed 90028419 item 4920 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4960 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90028419 | 05 | Preparation | 0000129822 | 772 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4920 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10405558 | CONVERTER,TORQUE,TWINDISC 4SG-1607-2 | 2024-10-02 | W |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  | 90028419_4920 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 772 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4960 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | No issue identified | 10405558 | CONVERTER,TORQUE,TWINDISC 4SG-1607-2 | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000129822 | 756 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10405558 | CONVERTER,TORQUE,TWINDISC 4SG-1607-2 |  |  |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-14 | 2025-04-01 | 2025-03-27 | 2025-02-28 | 2025-03-02 | MECH | 200147079 | 0030 | 0050 | 200147079 | 4Y INSP INT EXCHANGER 1KKT2420E3 | AA53.1KKT2420E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2420 | AA01 | 10 | No Issue identified | 10406162 | TUBE BUNDLE;EXCHANGER,TASOCS TB4782348U | 1 | EA | 2 | 0 | 0 | 0 |  | 10.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020191 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032434 | 05 | Preparation | 0000235350 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-20 | ODST-0090032434_0010 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-28 |  |  | 2025-04-01 |  |  |  |  | 2025-09-16 | 0 |  | 2025-03-27 |  | 2025-04-01 | 200147079 |  | 0 | 2 | 0 | 90032434 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10406162 | TUBE BUNDLE;EXCHANGER,TASOCS TB4782348U |  |  |  | 0030 | Remove Bonnet / Spools & Install Blinds | INT | Remove Bonnet / Spools & Install Blinds |  |  | 90032434_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232393 | S002 |  | 30 | 5300020191 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235350 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-03-07 | 2025-03-01 | 2025-03-01 | MECH | 200174926 | 0010 | 0010 | 200174926 | Replace Exchanger - 1KKT2430E3 | AA53.1KKT2430E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2430 | AA01 | 10 | No issue identified | 10406162 | TUBE BUNDLE;EXCHANGER,TASOCS TB4782348U | 1 | EA | 2 | 0 | 0 | 0 |  | 10.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020026 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032433 | 05 | Preparation | 0000277561 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090032433_0010 | 0 | 11 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-12 |  |  |  |  | 2026-07-09 | 0 |  | 2025-03-07 |  | 2025-03-12 | 200174926 |  | 0 | 2 | 0 | 90032433 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-07 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10406162 | TUBE BUNDLE;EXCHANGER,TASOCS TB4782348U |  |  |  | 0010 | Commisioning Inspection Bundle | ENON | Commisioning Inspection Bundle | 5 |  | 90032433_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000272048 | S002 |  | 30 | 5300020026 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277561 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1280 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10406549 | SHIELD,PIGNONE MS3002,OUTER HEAT,CASE | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 687 cannot be changed 90028419 item 4560 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 687 | 0 | EA |  |  | 102000000034183 |  |  |  |  | WorkPackLink | SW3R01B01B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10406549 | SHIELD,PIGNONE MS3002,OUTER HEAT,CASE | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_4560 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 687 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4600 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-08-19 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 200161965 | 0010 | 0080 | 200161965 | 4Y INSP EXP 1KM1310 PURGE UNIT | AA53.1KM1310PAP | PANEL,CTRL UNIT EEX P PURGE 1KM1310 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10407282 | SENSOR,PRESS;EXPO S0030588 | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200161965, Item 8 cannot be changed 90028297 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019288 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028297 | 07 | Execution | 0000257849 | 8 | 0 | EA | 101000000135200 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-18 | ODST-0090028297_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KM1310PAP |  | 0 | 2 | 0 | 90028297 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10407282 | SENSOR,PRESS;EXPO S0030588 | 2024-12-18 | W |  | 0010 | Carry out 4Y Exp Inspection | INT | Carry out 4Y Exp Inspection | 5 |  | 90028297_0080 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000253830 | S002 | 30 | 30 | 5300019288 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-19 | 257849 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0180 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Shipped qty below requirement qty | 10407516 | PADLOCK:KEYED ALIKE,MASTER LOCK COMPANY | 50 | EA | 0 | 0 | 20 | 20 | EA | 20.02 - ETA 04.04.25 PO 4500046416 HARTAC CPT | Supply for Order 500004676, Item 18 cannot be changed 90031855 item 170 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180133990 | 9028917 | 07 | Execution | 0000278102 | 18 | 0 | EA |  |  | 102000000034456 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2025-02-12 | GRST-5000434710_2025 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060634 | 1020 | 2025-12-31 | 20 |  | 2025-03-10 | 4900263288_2025_0005 | 2025-04-01 | TA OPS/BAILS | 5000434710_2025_0003 | 0 | 2 | 0 | 90031855 | 20 | 0 | 180133990 | 1 | 0 | 0 | X | L | 4900263288 | 2025 |  | 5000434710 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10407516 | PADLOCK:KEYED ALIKE,MASTER LOCK COMPANY | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0170/9028917_0170 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 18 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 180 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0140 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10407546 | PADLOCK:MASTER LOCK COMPANY,406KAYLW-6 | 50 | SET | 0 | 0 | 0 | 0 |  | 21.02 - ETA 04.04.25 PO 4500046416 HARTAC CPT | Supply for Order 500004676, Item 14 cannot be changed 90031855 item 130 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 14 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0130 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10407546 | PADLOCK:MASTER LOCK COMPANY,406KAYLW-6 | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0130 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 14 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 140 |  |  | 0 | 50 | SET | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0150 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10407552 | PADLOCK:KEYED LIKE,MASTER LOCK COMPANY,4 | 10 | SET | 5 | 0 | 0 | 0 |  | 21.02 - ETA 04.04.25 PO 4500046416 HARTAC CPT | Supply for Order 500004676, Item 15 cannot be changed 90031855 item 140 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 15 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0140 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10407552 | PADLOCK:KEYED LIKE,MASTER LOCK COMPANY,4 | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0140 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 150 |  |  | 0 | 10 | SET | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0160 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Shipped qty below requirement qty | 10407560 | PADLOCK;KEYED LIKE,M/LOCK 406KAYLW25 | 25 | SET | 0 | 0 | 5 | 5 | SET | 20.02 - ETA 04.04.25 PO 4500046416 HARTAC CPT | Supply for Order 500004676, Item 16 cannot be changed 90031855 item 150 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180133990 | 9028917 | 07 | Execution | 0000278102 | 16 | 0 | SET |  |  | 102000000034456 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-02-12 | GRST-5000434710_2025 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060634 | 1020 | 2025-12-31 | 5 |  | 2025-03-10 | 4900263288_2025_0003 | 2025-04-01 | TA OPS/BAILS | 5000434710_2025_0002 | 0 | 2 | 0 | 90031855 | 5 | 0 | 180133990 | 1 | 0 | 0 | X | L | 4900263288 | 2025 |  | 5000434710 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10407560 | PADLOCK;KEYED LIKE,M/LOCK 406KAYLW25 | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0150/9028917_0150 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 16 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 160 |  |  | 0 | 25 | SET | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0170 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10407565 | PADLOCK:MASTER LOCK COMPANY,406KAYLW-50 | 7 | SET | 2 | 0 | 0 | 0 |  | 20.02 - ETA 04.04.25 PO 4500046416 HARTAC CPT | Supply for Order 500004676, Item 17 cannot be changed 90031855 item 160 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 17 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 7 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0160 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10407565 | PADLOCK:MASTER LOCK COMPANY,406KAYLW-50 | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0160 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 17 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 170 |  |  | 0 | 7 | SET | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0030 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 1 | EA | 27 | 17 | 74 | 1 | EA | 19.02 - At KGP | Supply for Order 100039666, Item 2 cannot be changed 90024949 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122880 | 9026892 | 05 | Preparation | 0000138170 | 2 | 0 | EA | 102000000029820 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391253_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056486 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230015_2025_0001 | 2025-03-01 | 144PT60 | 5000391253_2025_0001 | 0 | 2 | 0 | 90024949 | 1 | 0 | 180122880/180122911 | 2 | 0 | 0 | X | L | 4900230015 | 2025 |  | 5000391253 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026892_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0110 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(31.01.2025) | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 1 | EA | 27 | 17 | 74 | 1 | EA | 03.02 - SOH @ AA02 | Supply for Order 100039671, Item 11 cannot be changed 90030039 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030039 | 05 | Preparation | 0000138175 | 11 | 0 | EA | 102000000034006 |  | 102000000034357 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030039_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-08 | 0 |  | 2025-02-24 |  | 2025-03-01 | 244PT60 |  | 0 | 2 | 0 | 90030039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 2025-01-31 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 90030039_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 11 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 | 30 | 30 | 5300002039 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0010 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 1 | EA | 27 | 17 | 74 | 1 | EA | 19.02 - At KGP | Supply for Order 100039740, Item 1 cannot be changed 9026895 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122885 | 9026895 | 05 | Preparation | 0000138264 | 1 | 0 | EA | 102000000029822 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391238_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056489 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900229989_2025_0001 | 2025-03-01 | 344PT501 | 5000391238_2025_0001 | 0 | 2 | 0 | 90024951 | 1 | 0 | 180122885/180122920 | 2 | 0 | 0 | X | L | 4900229989 | 2025 |  | 5000391238 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026895_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0010 | 0030 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 1 | EA | 27 | 17 | 74 | 1 | EA | 19.02 - At KGP | Supply for Order 100039741, Item 1 cannot be changed 9026898 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122893 | 9026898 | 05 | Preparation | 0000138265 | 1 | 0 | EA | 102000000029821 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391263_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056492 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230033_2025_0001 | 2025-03-01 | 344PT504 | 5000391263_2025_0001 | 0 | 2 | 0 | 90024952 | 1 | 0 | 180122893 | 2 | 0 | 0 | X | L | 4900230033 | 2025 |  | 5000391263 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Management of Change | 9026898_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 | 30 | 30 | 5300002054 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 100045383 | 0010 | 0030 | 100045383 | EEHA Cable Re-gland 123HZ019 | AA53.123HZ019 | SW,TRIP MANUAL CONT F/G 1F2301 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 1 | EA | 27 | 17 | 74 | 1 | EA | 09.01 - SOH @ AA02 | Supply for Order 100045383, Item 3 cannot be changed 90025052 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016509 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025052 | 05 | Preparation | 0000143904 | 3 | 0 | EA | 102000000029824 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025052_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123HZ019 |  | 0 | 2 | 0 | 90025052 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 2024-10-17 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 2 |  | 90025052_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000143273 | S002 | 30 | 30 | 5300016509 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143904 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Material committed/Printed/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0010 | 0040 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.02.2025) | 10409304 | TRANSMISSION UNIT,BTSKS-033-000-0790 | 1 | EA | 0 | 0 | 0 | 0 |  | 24.02 - ETA 15.04.25 PO 4500047259 JOHN CRANE CPT | Supply for Order 600001363, Item 10 cannot be changed 90030546 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030546 | 05 | Preparation | 0000084301 | 10 | 0 | [8 empty] | WorkPackLink |  | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-27 | ODST-0090030546_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Scott Kinloc |  | 0 | 2 | 0 | 90030546 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10409304 | TRANSMISSION UNIT,BTSKS-033-000-0790 | 2025-02-09 | W |  | 0010 | 5K2001 - Install Auxiliary Lube Oil Pump | INT | 5K2001 - Install Auxiliary Lube Oil Pump |  |  | 90030546_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 | 30 | 30 | 5300018438 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2940 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10412044 | TX,LVDT;SENTECH 75GV13500SR,EX | 1 | EA | 9 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 572 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 2SNLVDT |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10412044 | TX,LVDT;SENTECH 75GV13500SR,EX |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0130 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Shipped qty below requirement qty | 10412987 | PADLOCK:KEYED LIKE,MASTER LOCK COMPANY,4 | 30 | SET | 0 | 0 | 24 | 10 | SET | 21.02 - ETA 04.04.25 PO 4500046416 HARTAC CPT | Supply for Order 500004676, Item 13 cannot be changed 90031855 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180133990 | 9028917 | 07 | Execution | 0000278102 | 13 | 0 | SET |  |  | 102000000034456 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-02-12 | GRST-5000434710_2025 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060634 | 1020 | 2025-12-31 | 10 |  | 2025-03-10 | 4900263288_2025_0001 | 2025-04-01 | TA OPS/BAILS | 5000434710_2025_0001 | 0 | 2 | 0 | 90031855 | 10 | 0 | 180133990 | 1 | 0 | 0 | X | L | 4900263288 | 2025 |  | 5000434710 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10412987 | PADLOCK:KEYED LIKE,MASTER LOCK COMPANY,4 | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0120/9028917_0120 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 13 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 130 |  |  | 0 | 30 | SET | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0130 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10413219 | SHADE,SUN;300X200X125MM,316SS,AGCO 2S | 1 | EA | 1 | 0 | 2 | 1 | EA | 29.01 - At KGP | Supply for Order 100039666, Item 10 cannot be changed 9022060 item 90 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180104343 | 9022060 | 05 | Preparation | 0000138170 | 10 | 0 | EA | 101000000117304 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000316566_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000046220 | 1020 | 2024-03-07 | 1 |  | 2024-12-12 | 4900189818_2024_0001 | 2025-03-01 | 144PT60 | 5000316566_2024_0001 | 0 | 2 | 0 | 90024949 | 1 | 0 | 180104343/180122911 | 2 | 0 | 0 | X | L | 4900189818 | 2024 |  | 5000316566 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10413219 | SHADE,SUN;300X200X125MM,316SS,AGCO 2S | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9022060_0090 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 10 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | INLEC | 100087760 | 0010 | 0050 | 100087760 | Cyl Rod Drop Probes F/Test (4) 5K2001 | AA53.520XT11A | TXDCR,SENSOR PROX CYL 1 ROD DROP 5K2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10414223 | PROXIMITOR;COMP VIB,BENTLY 3307809005 | 4 | EA | 6 | 0 | 0 | 4 | EA | 02.12 - SOH @ AA02 | Supply for Order 100087760, Item 5 cannot be changed 90028435 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018538 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028435 | 05 | Preparation | 0000278368 | 5 | 0 | EA | 102000000031417 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-28 | ODST-0090028435_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5K2001 |  | 0 | 2 | 0 | 90028435 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10414223 | PROXIMITOR;COMP VIB,BENTLY 3307809005 | 2024-11-28 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's |  |  | 90028435_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272777 | S002 | 30 | 30 | 5300018538 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-11-20 | 278368 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0920 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10414426 | GASKET KIT;NP ISN316709308 | 1 | KIT | 3 | 0 | 0 | 1 | KIT | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 92 cannot be changed 90028418 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 92 | 0 | KIT | 102000000030539 | 102000000030292 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10414426 | GASKET KIT;NP ISN316709308 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0140 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 92 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 150 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0910 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10414428 | SEAL,MECH;NP ISN316709309 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 91 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10414428 | SEAL,MECH;NP ISN316709309 |  |  |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0900 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10414435 | GASKET KIT;NP IRR2735501 | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 90 cannot be changed 90028418 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 90 | 0 | KIT | 102000000030539 | 102000000030294 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10414435 | GASKET KIT;NP IRR2735501 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0130 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 90 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 140 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0890 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10414445 | ELEMENT,FLT;CART;NP RCO263580106 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 89 cannot be changed 90028418 item 120 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 89 | 0 | EA |  |  | 102000000030941 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10414445 | ELEMENT,FLT;CART;NP RCO263580106 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0120 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 89 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-10-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 200062886 | 0020 | 0020 | 200062886 | 8Y LV WESTERN FEEDER MODULE INSP | AA53.S15D1A6R03 | FEEDER,1KT2410E3 LUBE OIL HEATER | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.10.2024) | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 1 | CAN | 12 | 4 | 6 | 1 | CAN | 17.10 - SOH @ AA02 | Supply for Order 200062886, Item 2 cannot be changed 90025027 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016390 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90025027 | 05 | Preparation | 0000097188 | 2 | 0 | CAN | 102000000027901 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-15 | ODST-0090025027_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-17 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025027 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 2024-10-15 | W |  | 0020 | Complete PRT | INT | Complete PRT |  |  | 90025027_0020 |  |  | DG0 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000096605 | S002 | 30 | 30 | 5300016390 | 20 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 97188 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 200088969 | 0020 | 0020 | 200088969 | 8Y ABB Motor Starter Insp S61D2A3R01 | AA53.S61D2A3R01 | START,1KT1450V4KM1 LUBE OIL MIST SEP | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(29.07.2024) | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 2 | CAN | 12 | 4 | 6 | 2 | CAN | 02.10 - SOH @ AA02 | Supply for Order 200088969, Item 2 cannot be changed 90024990 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013337 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90024990 | 05 | Preparation | 0000127199 | 2 | 0 | CAN | 102000000027902 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | Sub 61 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-29 | ODST-0090024990_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-11-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024990 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 2024-07-29 | W |  | 0020 | Complete PRT | INT | Complete PRT |  |  | 90024990_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000126681 | S002 | 30 | 30 | 5300013337 | 20 |  |  | 0 | 2 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127199 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 200088971 | 0020 | 0020 | 200088971 | 8Y LV MNS2 ABB MOTOR STARTER INSP S61D2B | AA53.S61D2B2R08 | START,1KT1420V4M1 LUBE OIL MIST SEP | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 1 | CAN | 12 | 4 | 6 | 1 | CAN | 17.10 - SOH @ AA02 | Supply for Order 200088971, Item 2 cannot be changed 90025026 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016359 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90025026 | 05 | Preparation | 0000127261 | 2 | 0 | CAN | 102000000027869 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-14 | ODST-0090025026_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-11-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025026 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 2024-10-14 | W |  | 0020 | Complete PRT | INT | Complete PRT |  |  | 90025026_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000126683 | S002 | 30 | 30 | 5300016359 | 20 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127261 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-11-01 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147513 | 0010 | 0020 | 200147513 | 8Y Inspection LV MNS3 Non-Insum Starter | AA53.S24D16B4MA | START,MOTOR G4008PM1A SUB 2 S24D16 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.11.2024) | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 1 | CAN | 12 | 4 | 6 | 1 | CAN | 07.11 - SOH @ AA02 | Supply for Order 200147513, Item 2 cannot be changed 90025093 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017222 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90025093 | 05 | Preparation | 0000235924 | 2 | 0 | CAN | 102000000027900 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-01 | ODST-0090025093_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-16 | 0 |  | 2025-02-24 |  | 2025-03-01 | S24D16B4 |  | 0 | 2 | 0 | 90025093 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 2024-11-01 | W |  | 0010 | Complete PRT | INT | Complete PRT | 3 |  | 90025093_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232930 | S002 | 30 | 30 | 5300017222 | 20 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235924 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-11-01 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147521 | 0020 | 0020 | 200147521 | 8Y INSP LV S24D16 MNS3 NON-INSUM STARTER | AA53.S24D16A7AA | START,MOTOR GT4007PM2 SUB 2 S24D16 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.11.2024) | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 1 | CAN | 12 | 4 | 6 | 1 | CAN | 07.11 - SOH @ AA02 | Supply for Order 200147521, Item 4 cannot be changed 90025094 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017223 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90025094 | 05 | Preparation | 0000235932 | 4 | 0 | CAN | 102000000027903 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-01 | ODST-0090025094_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-16 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4007 |  | 0 | 2 | 0 | 90025094 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 2024-11-01 | W |  | 0020 | Punchlist & Closeout WP200147521IET001 | ENON | Punchlist & Closeout WP200147521IET001 |  |  | 90025094_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232938 | S002 | 30 | 30 | 5300017223 | 20 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235932 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-11-26 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-01 | INLEC | 200147523 | 0010 | 0020 | 200147523 | 4Y LV MNS3 INSUM Starter Insp - S35D16 | AA53.S35D16A5HA | START,MOTOR G4009S2M1, B8342 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(26.11.2024) | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 1 | CAN | 12 | 4 | 6 | 0 |  | 27.11 - SOH @ AA02 | Supply for Order 200147523, Item 2 cannot be changed 90028280 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018396 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90028280 | 05 | Preparation | 0000235934 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-26 | ODST-0090028280_0020 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2025-05-25 | 0 |  | 2025-03-26 |  | 2025-03-31 | S35D16A5HA |  | 0 | 2 | 0 | 90028280 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 2024-11-26 | W |  | 0010 | Complete PRT | INT | Complete PRT | 2 |  | 90028280_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232940 | S002 | 30 | 30 | 5300018396 | 20 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235934 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-16 | VALVE | 100032676 | 0010 | 0120 | 100032676 | CV-OH 2" 300# 118PCV507 | AA53.118PCV507 | VALVE,1K1820E1 L/O PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.12.2024) | 10418236 | DIAPHRAGM,ACT;FISHER 1F725102192 | 1 | EA | 1 | 0 | 0 | 1 | EA | 17.12 - ETA 04.03.25 PO 4500039296 SCORE CPT | Supply for Order 100032676, Item 12 cannot be changed 90028292 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019177 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028292 | 05 | Preparation | 0000131168 | 12 | 0 | EA | 102000000029953 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028292_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028292 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10418236 | DIAPHRAGM,ACT;FISHER 1F725102192 | 2024-12-15 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028292_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130518 | S002 | 30 | 30 | 5300019177 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131168 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-08-07 | 2025-03-01 | 2025-03-04 | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0040 | 0060 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10418650 | TIE,CABLE;679X4.6MM,SS316L,BANDIT KE0268 | 5 | PKT | 0 | 0 | 0 | 0 |  | 07.03 - ETA 09.04.25 PO 4500048417 MCLEAN CPT | Supply for Order 600001365, Item 13 cannot be changed 90032179 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013662 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | PKT |  |  |  |  | 90032179 | 05 | Preparation | 0000084303 | 13 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-08-06 | ODST-0090032179_0010 | 0 | 8 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-09 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-04 |  | 2025-03-09 | 1K2301 |  | 0 | 2 | 0 | 90032179 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10418650 | TIE,CABLE;679X4.6MM,SS316L,BANDIT KE0268 | 2025-03-04 | W |  | 0040 | Electrical Tie In | INT | Electrical Tie In |  | Order Requires Replanning | 90032179_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 13 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000083687 | S002 | 30 | 30 | 5300013662 | 70 |  |  | 0 | 5 | PKT | 2001 | AA02 | 2025-03-04 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84303 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-01 | INLEC | 100086263 | 0020 | 0010 | 100086263 | SRV, GCV, 2S Nozzle Overhaul 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10418747 | TX,LVDT;EX,SENTECH 75GV2500SR | 2 | EA | 2 | 2 | 0 | 2 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086263, Item 1 cannot be changed 90025090 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017085 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124188 | 90025090 | 05 | Preparation | 0000272422 | 1 | 0 | EA | 102000000032140 | 102000000029976 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-30 | IDST-0180124188 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 2 |  | 2025-02-11 | 4900234047_2025_0001 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025090 | 0 | 0 | 180124188 | 2 | 0 | 0 | X | L | 4900234047 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10418747 | TX,LVDT;EX,SENTECH 75GV2500SR | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025090_0010 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267122 | S002 |  | 30 | 5300017085 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10418747 | TX,LVDT;EX,SENTECH 75GV2500SR | 2 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 596 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | nozzcntrl |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10418747 | TX,LVDT;EX,SENTECH 75GV2500SR |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10419097 | HELICOIL;0.75",10UNC,NP N926BP00235 | 30 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 469 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10419097 | HELICOIL;0.75",10UNC,NP N926BP00235 |  |  |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0890 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10419097 | HELICOIL;0.75",10UNC,NP N926BP00235 | 30 | EA | 0 | 0 | 0 | 0 |  | 21.10 - ETA 29.01.25 PO 4500031675 BH | Supply for Order 200091513, Item 483 cannot be changed 90028419 item 3390 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 483 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3390 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10419097 | HELICOIL;0.75",10UNC,NP N926BP00235 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_3390 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 483 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3420 |  |  | 0 | 30 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-12-05 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100046238 | 0020 | 0030 | 100046238 | EEHA - Replace Glands - 414PDT608A | AA53.414PDT608A | TX,DIFF PRESS S/GAS REF 4K1450LP | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(10.02.2025) | 10419264 | PLUG,CDUIT;EX(DE),SCR,0.5" NPT M,SS316 | 6 | EA | 7 | 0 | 0 | 6 | EA | 24.02 - SOH @ AA02 | Supply for Order 100046238, Item 3 cannot be changed 90030598 item 30 already exists | Material picked; currently at SW3R01E02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021048 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030598 | 05 | Preparation | 0000144782 | 3 | 0 | EA |  |  | 102000000034495 |  |  |  |  | WorkPackLink | SW3R01E02A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-02-10 | ODST-0090030598_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2020-12-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414PDT608A |  | 0 | 2 | 0 | 90030598 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10419264 | PLUG,CDUIT;EX(DE),SCR,0.5" NPT M,SS316 | 2025-02-10 | W |  | 0020 | Replace Glands | INT | Replace Glands |  | Engineering Query | 90030598_0030 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000144153 | S002 | 30 | 30 | 5300021048 | 30 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144782 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-14 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0080 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue detected, please check message in derivation or orchestration log | 10420293 | GLAND CABLE | 50 | EA | 0 | 0 | 0 | 0 |  | 10.03 - NEEDS PURCHASE REQ | Linked PR creation failed for Order 62 Item |  | SP97 | Direct Multi-base | 0 | AA01 | 5300021228 | 50 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032104 | 05 | Preparation | 0000294187 | 62 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-02-13 |  | 0 | 0 | 0 | 0 |  | 2025-03-25 | AA53 | 2025-04-01 | [8 empty] | 0 |  | 2025-03-14 |  | 2025-03-27 | Inlec Contai |  | 0 | 2 | 0 | 90032104 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420293 | GLAND CABLE | 2025-03-03 | E |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032104_0010 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA02 |  | 99 |  |  | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 70 | 70 | 5300021227 | 560 |  | 5300021228 | 50 | 50 | EA | 1001 | AA02 | 2025-03-14 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0030 | 0030 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10420299 | GASKET,SW;50MM,65MM,KLINGER K016109162 | 5 | EA | 5 | 0 | 0 | 5 | EA | 23.01 - SOH @ AA02 | Supply for Order 200147980, Item 3 cannot be changed 90028418 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 3 | 0 | EA | 102000000030534 | 102000000030153 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420299 | GASKET,SW;50MM,65MM,KLINGER K016109162 | 2024-09-23 | W |  | 0030 | COMPRESSOR INSTRUMENTS | ENON | COMPRESSOR INSTRUMENTS | 5 |  | 90028418_0060 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 70 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0030 | 0030 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 1 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 3 cannot be changed 90028588 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 3 | 0 | EA | 102000000033452 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 |  | 90028588_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0090 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 1 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 15 cannot be changed 90028588 item 150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 15 | 0 | EA | 102000000033453 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177498 |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028588_0150 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0090 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 1 | 0 | 0 |  | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 15 cannot be changed 90028589 item 150 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 15 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0150 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0030 | 0030 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 1 | 0 | 0 |  | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 3 cannot be changed 90028589 item 30 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 |  | 90028589_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0090 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 1 | 0 | 1 | EA | 28.01 - ETA 20.02.25 PO 4500043563 ex Camfil | Supply for Order 200177720, Item 15 cannot be changed 180127677 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180127677 | 9027829 | 05 | Preparation | 0000281240 | 15 | 0 | EA | 102000000033451 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | IDST-0180127677 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 | 4900242979_2025_0003/4900242809_2025_0003 | 2025-03-01 | 200177720 |  | 0 | 2 | 0 | 90028590 | 0 | 0 | 180127677 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 9027829_0150 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0030 | 0030 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 1 | 0 | 1 | EA | 28.01 - ETA 20.02.25 PO 4500043563 ex Camfil | Supply for Order 200177720, Item 3 cannot be changed 180127677 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180127677 | 9027829 | 05 | Preparation | 0000281240 | 3 | 0 | EA | 102000000033450 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | IDST-0180127677 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 | 4900242979_2025_0001/4900242809_2025_0001 | 2025-03-01 |  |  | 0 | 2 | 0 | 90028590 | 0 | 0 | 180127677 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 | Ready for Release | 9027829_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-02 | MECH | 200147079 | 0030 | 0040 | 200147079 | 4Y INSP INT EXCHANGER 1KKT2420E3 | AA53.1KKT2420E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.01.2025) | 10422801 | SEAL;CPLG,RBR,100MM,VICTAULIC G00770114+ | 6 | EA | 12 | 6 | 0 | 6 | EA | 21.01 - SOH @ AA02 | Supply for Order 200147079, Item 4 cannot be changed 9027119 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300020191 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027119 | 05 | Preparation | 0000235350 | 4 | 0 | EA | 102000000032208 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-20 | GIST-4900234121_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-28 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-09-16 | 6 |  | 2025-02-11 | 4900234121_2025_0003 | 2025-03-01 | 200147079 |  | 0 | 2 | 0 | 90030058 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234121 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10422801 | SEAL;CPLG,RBR,100MM,VICTAULIC G00770114+ | 2025-01-20 | W |  | 0030 | Remove Bonnet / Spools & Install Blinds | INT | Remove Bonnet / Spools & Install Blinds |  |  | 9027119_0040 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232393 | S002 | 30 | 30 | 5300020191 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235350 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0700 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10423397 | PACKING,PIGNONE MS5352B,1ST NOZ,INCONEL | 50 | M | 254.2 | 0 | 0 | 50 | M | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 78 cannot be changed 90028419 item 610 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 620 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 78 | 0 | M | 102000000030502 | 102000000030116 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0610 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10423397 | PACKING,PIGNONE MS5352B,1ST NOZ,INCONEL | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0610 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 78 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 620 |  |  | 0 | 50 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0840 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10423397 | PACKING,PIGNONE MS5352B,1ST NOZ,INCONEL | 50 | M | 254.2 | 0 | 0 | 50 | M | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 97 cannot be changed 90028419 item 750 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 760 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 97 | 0 | M | 102000000030502 | 102000000030114 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10423397 | PACKING,PIGNONE MS5352B,1ST NOZ,INCONEL | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0750 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 97 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 760 |  |  | 0 | 50 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDLN1 | Released | 2024-11-11 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | VALVE | 100080816 | 0110 | 0020 | 100080816 | MOC-117208 Repl Accumulators (2) 1A1491 | AA53.1A1491 | PKG EQ,HYD PWR PACK |  | 10 | WO item has not been released yet | 10423729 | GAS COMPRESSED | 1 | SET | 6 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000251583 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 1A1491 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10423729 | GAS COMPRESSED |  |  |  | 0110 | refurbish exLNG2 accumulators pre shut | INT | refurbish exLNG2 accumulators pre shut | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000247849 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPR07 | 2024-07-19 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed | AM01 | Reactive Maintenance
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0150 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Shipped qty below requirement qty | 10425024 | RAIL | 2 | EA | 0 | 0 | 2 | 1 | EA | 07.03 - SOH @ AA53 | Supply for Order 600001815, Item 21 cannot be changed 90030415 item 130 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180129283 | 9027674 | 07 | Execution | 0000084731 | 21 | 0 | EA | 102000000033737 |  | 107000000000399 |  |  |  |  | WorkPackLink | INLEC-CAGE | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-13 | GRST-5000416521_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  | 100000058594 | 1020 | 2024-08-30 | 1 |  | 2025-02-25 | 4900248451_2025_0001 | 2025-03-01 | FAR12 | 5000416521_2025_0001 | 0 | 2 | 0 | 90030415 | 1 | 0 | 180129283 | 1 | 0 | 0 | X | L | 4900248451 | 2025 |  | 5000416521 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10425024 | RAIL | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030415_0130/9027674_0130 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 21 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 72 | 72 | 5300007843 | 160 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
1 | 25SD2420 | Released | 2024-11-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | INLEC | 100086242 | 0020 | 0020 | 100086242 | MOC-***** HYD Dump Vlve Repl (2) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | WO item has not been released yet | 10427179 | UNION;EX,ELEC BARRIER,20MM,TRIFLEX FB20 | 2 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000272294 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  |  |  |  | 1KT2420 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10427179 | UNION;EX,ELEC BARRIER,20MM,TRIFLEX FB20 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000267031 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-11-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | INLEC | 100086242 | 0020 | 0040 | 100086242 | MOC-***** HYD Dump Vlve Repl (2) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | WO item has not been released yet | 10427202 | CONDUIT;EX,RAMELEC FB25 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000272294 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  |  |  |  | 1KT2420 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10427202 | CONDUIT;EX,RAMELEC FB25 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000267031 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0090 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10430750 | BAG;COTTON,CALICO,,SIDE TIES,12X18" | 40 | EA | 40 | 0 | 0 | 40 | EA | 02.03 - SOH @ AA02 | Supply for Order 500004676, Item 9 cannot be changed 90031855 item 80 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 9 | 0 | EA | 101000000149761 |  | 101000000149860 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 40 |  | 2025-03-02 | Y | 1001 | 2025-02-12 | ODST-0090031855_0080 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10430750 | BAG;COTTON,CALICO,,SIDE TIES,12X18" | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0080 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 9 |  | 0 |  | 25SDENA1 | MJ | 20005413 | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 90 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-03-27 |  |  | 2025-02-28 |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDFR1 | Released | 2024-01-02 | 2025-01-01 | 2024-12-27 | 2025-03-01 | 2025-05-16 | INLEC | 600001530 | 0010 | 0080 | 600001530 | MOC-107654/88803 Pre SD Scope 118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10431354 | REDUCER,CDUIT;CLIPSAL CLI2643MGRY | 20 | EA | 34 | 6 | 159 | 1 | EA | 20.12 - SOH @ AA02 | Supply for Order 600001530, Item 3 cannot be changed 90024965 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004570 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024965 | 05 | Preparation | 0000084445 | 3 | 0 | EA | 102000000029375 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024965_0020 | 0 | 0 | 0 | 0 |  | 2024-12-30 | AA53 | 2025-03-01 |  |  | 2025-01-01 |  |  |  |  | 2025-07-31 | 0 |  | 2024-12-27 |  | 2025-01-01 | 118UCV112 |  | 0 | 2 | 0 | 90024965 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-12-27 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431354 | REDUCER,CDUIT;CLIPSAL CLI2643MGRY | 2024-01-02 | W |  | 0010 | MOC-88803 Frac 1 Pre Works | INT | MOC-88803 Frac 1 Pre Works | 0 |  | 90024965_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000083862 | S002 | 30 | 30 | 5300004570 | 20 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-12-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84445 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM06 | Capital
| 25SDFR1 | Released | 2024-01-02 | 2025-01-01 | 2024-12-27 | 2025-03-01 | 2025-05-16 | INLEC | 600001530 | 0010 | 0080 | 600001530 | MOC-107654/88803 Pre SD Scope 118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10431354 | REDUCER,CDUIT;CLIPSAL CLI2643MGRY | 20 | EA | 34 | 6 | 159 | 19 | EA | 20.12 - SOH @ AA02 | Supply for Order 600001530, Item 3 cannot be changed 90024965 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004570 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024965 | 05 | Preparation | 0000084445 | 3 | 0 | EA | 102000000025333 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024965_0020 | 0 | 0 | 0 | 0 |  | 2024-12-30 | AA53 | 2025-03-01 |  |  | 2025-01-01 |  |  |  |  | 2025-07-31 | 0 |  | 2024-12-27 |  | 2025-01-01 | 118UCV112 |  | 0 | 2 | 0 | 90024965 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-12-27 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431354 | REDUCER,CDUIT;CLIPSAL CLI2643MGRY | 2024-01-02 | W |  | 0010 | MOC-88803 Frac 1 Pre Works | INT | MOC-88803 Frac 1 Pre Works | 0 |  | 90024965_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000083862 | S002 | 30 | 30 | 5300004570 | 20 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-12-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84445 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM06 | Capital
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0290 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10431950 | INSLN BLANKET:2X50M,BIDIM A12 | 1 | ROL | 1 | 0 | 19 | 0 |  | 18.12 - qty 5 SOH @ AA01 | Supply for Order 100087648, Item 30 cannot be changed 90028417 item 280 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 30 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431950 | INSLN BLANKET:2X50M,BIDIM A12 | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0280 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 30 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 290 |  |  | 0 | 1 | ROL | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0380 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10431950 | INSLN BLANKET:2X50M,BIDIM A12 | 4 | ROL | 1 | 0 | 19 | 0 |  | 07.03 - ETA 23.03.25 PO 4500046941 BLACKWOODS CPT | Supply for Order 100090053, Item 38 cannot be changed 90032376 item 360 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 38 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0360 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431950 | INSLN BLANKET:2X50M,BIDIM A12 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0360 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 38 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 380 |  |  | 0 | 4 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0070 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Voyage arrived: too late to meet planned Reqmt Date | 10431950 | INSLN BLANKET:2X50M,BIDIM A12 | 1 | ROL | 1 | 0 | 19 | 1 | ROL | Workpacked at KGP | Supply for Order 200089373, Item 7 cannot be changed 9018854 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180092197 | 9018854 | 07 | Execution | 0000127667 | 7 | 0 | ROL |  |  | 102000000023720 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-P25-STONE-LRG | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 | 2024-11-12 |  | Y | 1001 | 2024-11-05 | GRST-5000276211_2024 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000040712 | 1020 | 2025-12-15 | 1 |  | 2024-11-12 | 4900170134_2024_0001 | 2024-11-10 | Troy Mac | 5000276211_2024_0001 | 0 | 2 | 0 | 90023594 | 1 | 0 | 180092197 | 1 | 0 | 0 | X | L | 4900170134 | 2024 |  | 5000276211 | 2024 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431950 | INSLN BLANKET:2X50M,BIDIM A12 | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9018854_0070 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDFR2 | MJ | 1000004055 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 70 |  |  | 0 | 1 | ROL | 2001 | AA02 | 2024-11-05 |  |  | 2024-11-13 |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0010 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10431950 | INSLN BLANKET:2X50M,BIDIM A12 | 10 | ROL | 1 | 0 | 19 | 0 |  | 24.02 - ETA 20.03.25 PO 4500046941 BLACKWOODS CPT | Supply for Order 500005166, Item 2 cannot be changed 90031023 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90031023 | 05 | Preparation | 0000294187 | 2 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031023_0010 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 | [5 empty] | 0 |  | 2025-03-06 |  | 2025-03-11 | TA LAG_VORN |  | 0 | 2 | 0 | 90031023 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431950 | INSLN BLANKET:2X50M,BIDIM A12 | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0010 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 20 |  |  | 0 | 10 | ROL | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN1 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 100033992 | 0020 | 0020 | 100033992 | Replace Faulty Gauge 114PG17 | AA53.114PG17 | GAUGE,DEFROST GAS TO P1402B | AA01 | 30 | No issue identified | 10433706 | GAUGE,PRESS;316SS,WIKA 2333016001600KPA | 1 | EA | 0 | 0 | 0 | 0 |  | 05.02 - ETA 28.03.25 PO 4500044916 WIKA CPT |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016547 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030141 | 05 | Preparation | 0000132524 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090030141_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 114PG17 |  | 0 | 2 | 0 | 90030141 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10433706 | GAUGE,PRESS;316SS,WIKA 2333016001600KPA |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90030141_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000131894 | S002 | 30 | 30 | 5300016547 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132524 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0070 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10433854 | TAPE,FOIL;TESA 7379,RL/50M | 50 | ROL | 0 | 4 | 206 | 0 |  | 07.03 - ETA 18.03.25 PO 4500046895 BLACKWOODS CPT | Supply for Order 100090053, Item 7 cannot be changed 90032376 item 70 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 7 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0070 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10433854 | TAPE,FOIL;TESA 7379,RL/50M | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0070 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 7 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 70 |  |  | 0 | 50 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0060 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Shipped qty below requirement qty | 10433854 | TAPE,FOIL;TESA 7379,RL/50M | 60 | ROL | 0 | 4 | 206 | 32 | ROL | 20.02 - ETA 18.03.25 PO 4500046895 BLACKWOODS CPT | Supply for Order 500005166, Item 26 cannot be changed 90031501 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132204 | 9028446 | 05 | Preparation | 0000294187 | 26 | 0 | ROL |  |  | 102000000033925 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427504_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060207 | 1020 |  | 52 |  | 2025-03-05 | 4900257428_2025_0001 | 2025-04-01 | TA LAG_VORN | 5000427504_2025_0001 | 0 | 2 | 0 | 90031501 | 52 | 0 | 180132204 | 1 | 0 | 0 | X | L | 4900257428 | 2025 |  | 5000427504 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10433854 | TAPE,FOIL;TESA 7379,RL/50M | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0080/9028446_0080 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 26 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 220 |  |  | 0 | 60 | ROL | 2001 | AA02 | 2025-03-27 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0060 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Shipped qty below requirement qty | 10433854 | TAPE,FOIL;TESA 7379,RL/50M | 60 | ROL | 0 | 4 | 206 | 20 | ROL | 20.02 - ETA 18.03.25 PO 4500046895 BLACKWOODS CPT | Supply for Order 500005166, Item 26 cannot be changed 90031501 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132204 | 9028446 | 05 | Preparation | 0000294187 | 26 | 0 | ROL |  |  | 102000000033926 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427504_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060207 | 1020 |  | 52 |  | 2025-03-05 | 4900257428_2025_0001 | 2025-04-01 | TA LAG_VORN | 5000427504_2025_0001 | 0 | 2 | 0 | 90031501 | 52 | 0 | 180132204 | 1 | 0 | 0 | X | L | 4900257428 | 2025 |  | 5000427504 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10433854 | TAPE,FOIL;TESA 7379,RL/50M | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0080/9028446_0080 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 26 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 220 |  |  | 0 | 60 | ROL | 2001 | AA02 | 2025-03-27 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0570 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10434236 | OIL,LUB;TURBO,SHELL T46,1000L | 3 | CON | 9 | 0 | 0 | 0 |  | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 65 cannot be changed 90025019 item 630 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 630 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 65 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0630 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | LubeOil |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10434236 | OIL,LUB;TURBO,SHELL T46,1000L | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0630 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 65 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 630 |  |  | 0 | 3 | CON | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0760 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10434236 | OIL,LUB;TURBO,SHELL T46,1000L | 2 | CON | 9 | 0 | 0 | 0 |  | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 82 cannot be changed 90025019 item 790 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 790 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 82 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0790 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | LubeOil |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10434236 | OIL,LUB;TURBO,SHELL T46,1000L | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0790 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 82 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 790 |  |  | 0 | 2 | CON | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147564 | 0010 | 0020 | 200147564 | 2Y SVC G4007 AIR SYSTEM FLT CHANGE OUT | AA53.G4007S2 | FILT,GENERATOR INLET AIR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10434976 | FILTER ELEM,AIR,DONALDSON P902840 | 32 | EA | 0 | 0 | 0 | 0 |  | 02.10 - ETA 10.04.25 PO 4500029446 ex Donaldson FCA | Supply for Order 200147564, Item 2 cannot be changed 90025005 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015683 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025005 | 05 | Preparation | 0000235976 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025005_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025005 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10434976 | FILTER ELEM,AIR,DONALDSON P902840 | 2024-09-22 | W |  | 0010 | Replace Generator Air Filters | INT | Replace Generator Air Filters | 3 | Ready for Release | 90025005_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232982 | S002 | 30 | 30 | 5300015683 | 20 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235976 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147564 | 0010 | 0030 | 200147564 | 2Y SVC G4007 AIR SYSTEM FLT CHANGE OUT | AA53.G4007S2 | FILT,GENERATOR INLET AIR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10435942 | ELEMENT,FLT;AIR,26",DONALD P902842 | 32 | EA | 0 | 0 | 0 | 0 |  | 06.01 - ETA 10.04.25 PO 4500029450 Donaldson FCA | Supply for Order 200147564, Item 3 cannot be changed 90025005 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015683 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025005 | 05 | Preparation | 0000235976 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025005_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025005 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10435942 | ELEMENT,FLT;AIR,26",DONALD P902842 | 2024-09-22 | W |  | 0010 | Replace Generator Air Filters | INT | Replace Generator Air Filters | 3 | Ready for Release | 90025005_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232982 | S002 | 30 | 30 | 5300015683 | 30 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235976 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0210 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 24 | ROL | 16 | 0 | 74 | 1 | ROL | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 21 cannot be changed 90032376 item 210 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180134141 | 9029112 | 05 | Preparation | 0000289018 | 21 | 0 | ROL |  |  | 101000000150988 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | P07 | 0 |  | 0 | 0 |  | 0 | 7 |  |  | Y | 1001 | 2025-03-04 | IDST-0180134141 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 17 |  | 2025-03-28 | 4900263779_2025_0001/4900263706_2025_0003 | 2025-04-02 | 3E1405/Vorn | 5000435555_2025_0001/5000435313_2025_0002 | 0 | 2 | 0 | 90032376 | 17 | 0 | 180134141/180134169 | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0210/9029112_0210/9028691_0210 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 21 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 210 |  |  | 0 | 24 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0210 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 24 | ROL | 16 | 0 | 74 | 16 | ROL | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 21 cannot be changed 90032376 item 210 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180134141 | 9029112 | 05 | Preparation | 0000289018 | 21 | 0 | ROL |  |  | 101000000150959 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | P07 | 0 |  | 0 | 0 |  | 0 | 7 |  |  | Y | 1001 | 2025-03-04 | IDST-0180134141 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 17 |  | 2025-03-28 | 4900263779_2025_0001/4900263706_2025_0003 | 2025-04-02 | 3E1405/Vorn | 5000435555_2025_0001/5000435313_2025_0002 | 0 | 2 | 0 | 90032376 | 17 | 0 | 180134141/180134169 | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0210/9029112_0210/9028691_0210 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 21 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 210 |  |  | 0 | 24 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0070 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 60 | ROL | 16 | 0 | 74 | 26 | ROL | 02.03 - SOH @ AA02 | Supply for Order 500005166, Item 27 cannot be changed 90031501 item 90 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180134139 | 9029110 | 05 | Preparation | 0000294187 | 27 | 0 | ROL |  |  | 102000000033924 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-02-13 | IDST-0180134139 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 57 |  | 2025-03-27 | 4900263804_2025_0001/4900263693_2025_0003/4900257428_2025_0003 | 2025-04-01 | TA LAG_VORN | 5000435533_2025_0001/5000435328_2025_0002/5000427504_2025_0002 | 0 | 2 | 0 | 90031501 | 57 | 0 | 180132204/180134139/180134168 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0090/9029110_0090/9028690_0090/9028446_0090 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 27 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 230 |  |  | 0 | 60 | ROL | 2001 | AA02 | 2025-03-27 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0070 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 60 | ROL | 16 | 0 | 74 | 15 | ROL | 02.03 - SOH @ AA02 | Supply for Order 500005166, Item 27 cannot be changed 90031501 item 90 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180134139 | 9029110 | 05 | Preparation | 0000294187 | 27 | 0 | ROL |  |  | 101000000150245 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-02-13 | IDST-0180134139 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 57 |  | 2025-03-27 | 4900263804_2025_0001/4900263693_2025_0003/4900257428_2025_0003 | 2025-04-01 | TA LAG_VORN | 5000435533_2025_0001/5000435328_2025_0002/5000427504_2025_0002 | 0 | 2 | 0 | 90031501 | 57 | 0 | 180132204/180134139/180134168 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0090/9029110_0090/9028690_0090/9028446_0090 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 27 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 230 |  |  | 0 | 60 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0070 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 60 | ROL | 16 | 0 | 74 | 16 | ROL | 02.03 - SOH @ AA02 | Supply for Order 500005166, Item 27 cannot be changed 90031501 item 90 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180134139 | 9029110 | 05 | Preparation | 0000294187 | 27 | 0 | ROL |  |  | 101000000150115 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-02-13 | IDST-0180134139 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 57 |  | 2025-03-27 | 4900263804_2025_0001/4900263693_2025_0003/4900257428_2025_0003 | 2025-04-01 | TA LAG_VORN | 5000435533_2025_0001/5000435328_2025_0002/5000427504_2025_0002 | 0 | 2 | 0 | 90031501 | 57 | 0 | 180132204/180134139/180134168 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0090/9029110_0090/9028690_0090/9028446_0090 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 27 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 230 |  |  | 0 | 60 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2024-03-01 | 2025-05-31 | 2025-06-01 | QMI | 100047965 | 0010 | 0040 | 100047965 | MOC-141289 Transmitter Replace 144FT84 | AA53.144FT84 | METER,DP FLOW,1V4450 OUTLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10441401 | BOX,JCT;EX,CCG 100201BC62 | 1 | EA | 52 | 5 | 0 | 1 | EA | 19.12 - Material Consumed | Supply for Order 100047965, Item 4 cannot be changed 180009111 item 40 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300001827 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180009111 | 90001493 | 05 | Preparation | 0000146486 | 4 | 0 | EA |  |  | 102000000002681 | 01-Road |  | 3-In Transit |  | WorkPackLink | QMP08CAGE | KCM-LNG | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2025-05-31 |  |  | 2025-03-01 |  |  | 100000002887 | 1020 | 2024-12-30 | 1 |  | 2024-03-06 | 4900035070_2024_0007 | 2024-03-04 | 144FT84 | 5000030950_2024_0004 | 0 | 2 | 0 | 90001493 | 1 | 0 | 180009111 | 2 | 0 | 0 | X | L | 4900035070 | 2024 |  | 5000030950 | 2024 | 0 |  | 2024-03-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441401 | BOX,JCT;EX,CCG 100201BC62 | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Engineering Query/Management of Change | 90001493_0040 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SDLN1 | MJ | 1000000809 | AU1072 | 1000145855 | S002 | 30 | 30 | 5300001827 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-03-01 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146486 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-06-01 | 2025-05-31 | 2025-05-31 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200090677 | 0110 | 0010 | 200090677 | 4Y INT INSP EXCHANGER 5P2002AE | AA53.5P2002AE | EXCH,SEAL OIL COOLER P2002A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(24.01.2025) | 10442861 | GASKET;FLU0ROELASTOMER,FLOWSV 568265GU | 1 | EA | 4 | 0 | 6 | 1 | EA | 28.01 - qty 4 SOH @ AA02 | Supply for Order 200090677, Item 10 cannot be changed 90030053 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019786 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030053 | 05 | Preparation | 0000128955 | 10 | 0 | EA | 102000000034331 |  | 102000000034305 |  |  |  |  | WorkPackLink | PACKING | P07 TA MET 2032 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-09 | ODST-0090030053_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090677 |  | 0 | 2 | 0 | 90030053 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10442861 | GASKET;FLU0ROELASTOMER,FLOWSV 568265GU | 2025-01-24 | W |  | 0110 | Replace Top cover /coil assembly | INT | Replace Top cover /coil assembly |  |  | 90030053_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128366 | S002 | 30 | 30 | 5300019786 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128955 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-02-25 | 2025-03-01 | MECH | 200090678 | 0090 | 0010 | 200090678 | 4Y INT INSP EXCHANGER 5P2002BE | AA53.5P2002BE | EXCH,SEAL OIL COOLER P2002B | AA01 | 10 | No issue identified | 10442861 | GASKET;FLU0ROELASTOMER,FLOWSV 568265GU | 1 | EA | 4 | 0 | 6 | 1 | EA | 28.01 - qty 4 SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019787 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030054 | 05 | Preparation | 0000128956 | 10 | 0 | EA | 102000000034330 |  | 102000000031905 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2032 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-09 | ODST-0090030054_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090678 |  | 0 | 2 | 0 | 90030054 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10442861 | GASKET;FLU0ROELASTOMER,FLOWSV 568265GU |  |  |  | 0090 | Replace Top cover /coil assembly | INT | Replace Top cover /coil assembly |  |  | 90030054_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128367 | S002 | 30 | 30 | 5300019787 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128956 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0230 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10443606 | TAPE:INS,FIBREGLASS,50X3MM,30M L | 3 | ROL | 3 | 0 | 4 | 3 | ROL | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 43 cannot be changed 9028446 item 250 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132204 | 9028446 | 05 | Preparation | 0000294187 | 43 | 0 | ROL |  |  | 102000000033935 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427504_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060207 | 1020 |  | 3 |  | 2025-03-05 | 4900257428_2025_0007 | 2025-04-01 | TA LAG_VORN | 5000427504_2025_0004 | 0 | 2 | 0 | 90031501 | 3 | 0 | 180132204 | 2 | 0 | 0 | X | L | 4900257428 | 2025 |  | 5000427504 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10443606 | TAPE:INS,FIBREGLASS,50X3MM,30M L | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 9028446_0250 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 43 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 390 |  |  | 0 | 3 | ROL | 2001 | AA02 | 2025-03-27 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-11 | 2025-04-01 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0040 | 0020 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2025) | 10446931 | GLASSES,SAF;PROTECTOR WHIMCREEKS76SP | 12 | PAA | 171 | 0 | 92 | 12 | PAA | MRF 250306-8038907 processed to 5001 awaiting Pickup WH2POPJOB bench 1 x Box | Supply for Order 500004676, Item 24 cannot be changed 90032393 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAA |  |  |  | 180133327 | 90032393 | 07 | Execution | 0000278102 | 24 | 0 | PAA |  |  | 102000000034306 |  |  |  |  | WorkPackLink | KSF-POP-JOB-BENCH |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-12 | GRST-5000431300_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060425 | 1020 | 2025-12-31 | 12 |  | 2025-03-07 | 4900260154_2025_0001 | 2025-04-01 | Sim/Teebs | 5000431300_2025_0001 | 0 | 2 | 0 | 90032393 | 12 | 0 | 180133327 | 2 | 0 | 0 |  | L | 4900260154 | 2025 |  | 5000431300 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10446931 | GLASSES,SAF;PROTECTOR WHIMCREEKS76SP | 2025-03-06 | W |  | 0040 | BLACKWOODS Consumables | NCNF | BLACKWOODS Consumables |  |  | 90032393_0010 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 24 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 230 |  |  | 0 | 12 | PAA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDGT9 | Released | 2025-03-06 | 2025-03-01 | 2025-03-07 | 2025-03-01 | 2025-03-07 | INLEC | 100038928 | 0020 | 0030 | 100038928 | MOC-151263 Repl Ammeter - S35D16A5BA | AA53.S35D16A5BA | START,MOTOR G4009KM1A, B8342 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2025) | 10447087 | METER:AMPERE;CROMPTON E242756AGLJLJC5 | 1 | EA | 0 | 0 | 0 | 0 |  | DEL: 90032385 | Supply for Order 100038928, Item 3 cannot be changed 90032385 item 10 already exists | PR approved; PO not issued | SP97 | Direct Multi-base | 50 | AA01 | 5300022219 | 10 |  | 7 | 1000031390 | 3 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032385 | 05 | Preparation | 0000137420 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-GT9-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  |  | 1001 | 2025-03-07 | PRPO-1000031390_00003 | 0 | 82 | 58 | 71 | 2025-05-02 | 2025-03-05 | AA53 | 2025-03-01 |  |  | 2025-06-02 | 2025-05-04 | 2025-05-17 |  |  | 2023-10-17 | 0 |  | 2025-03-07 |  | 2025-03-20 | S35D16A5BA |  | 0 | 2 | 2 | 90032385 | 0 | 0 |  | 2 | 1 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10447087 | METER:AMPERE;CROMPTON E242756AGLJLJC5 | 2025-03-06 | W |  | 0020 | Replace Ammeter | INT | Replace Ammeter |  |  | 90032385_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-07 | 30 |  | 2025-05-04 | 0 |  | 0 |  | 25SDGT9 | MJ |  | AU1009 | 1000136810 | S001 | 30 | 30 | 5300022218 | 10 |  | 5300022219 | 10 | 1 | EA | 2001 | AA02 | 2025-03-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 2 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0050 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10451053 | KNIFE;ROCKWOOL,300MM,H CS,MOULDED | 10 | EA | 12 | 0 | 0 | 10 | EA | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 6 cannot be changed 90031023 item 50 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031023 | 05 | Preparation | 0000294187 | 6 | 0 | EA |  |  | 102000000033155 |  |  |  |  | WorkPackLink | PACKING | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031023_0050 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 | [5 empty] | 0 |  | 2025-03-06 |  | 2025-03-11 | TA LAG_VORN |  | 0 | 2 | 0 | 90031023 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10451053 | KNIFE;ROCKWOOL,300MM,H CS,MOULDED | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0050 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 6 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 60 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0352 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10452588 | OIL,LUB;COMP,SHELL CORENA S2 P 150,1000L | 1 | CON | 2 | 0 | 0 | 1 | CON | 06.01 - SOH @ AA02 | Supply for Order 200091126, Item 74 cannot be changed 90023534 item 320 already exists | Material picked; currently at KSF-PACK-SD-LRG/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 570 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  | CUTOVER_S4 |  |  | 90023534 | 05 | Preparation | 0000129360 | 74 | 0 | CON |  |  | 101000000060321 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-PACK-SD-LRG | P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-07-06 | 2024-07-06 | Y | 1001 | 2024-01-02 | ODST-0090023534_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452588 | OIL,LUB;COMP,SHELL CORENA S2 P 150,1000L | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0320 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 74 |  | 0 |  | 25SD2301 | MJ | 20001726 | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 570 |  |  | 0 | 1 | CON | 2001 | AA02 | 2025-02-24 |  |  | 2024-07-04 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD4401 | Released | 2025-01-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100033160 | 0020 | 0010 | 100033160 | MOC-146133 - Replace Tx - 244LT511 | AA53.244LT511 | TX,LEVEL K4401B-E2 DEGASSING TANK | AA01 | 30 | No Issue identified | 10452625 | TX,DP;EX,RMOUNT 3051S1CD2A2F12A1KDA2DOK+ | 1 | EA | 3 | 3 | 6 | 1 | EA | 21.01 - SOH @ AA02 |  | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020235 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132198 | 9028443 | 05 | Preparation | 0000131681 | 1 | 0 | EA |  |  | 102000000033485 | 01-Road |  | 3-In Transit |  | WorkPackLink | INLEC-CAGE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-21 | GRST-5000427528_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060205 | 1020 | 2024-11-04 | 1 |  | 2025-03-05 | 4900257434_2025_0001 | 2025-03-01 | 244LT511 | 5000427528_2025_0001 | 0 | 2 | 0 | 90029003 | 1 | 0 | 180132198 | 3 | 0 | 0 |  | L | 4900257434 | 2025 |  | 5000427528 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452625 | TX,DP;EX,RMOUNT 3051S1CD2A2F12A1KDA2DOK+ |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 9028443_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SD4401 | MJ | 1000005306 | AU1072 | 1000131050 | S002 | 30 | 30 | 5300020235 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131681 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2024-03-01 | 2025-05-31 | 2025-06-01 | QMI | 100047965 | 0010 | 0050 | 100047965 | MOC-141289 Transmitter Replace 144FT84 | AA53.144FT84 | METER,DP FLOW,1V4450 OUTLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10452625 | TX,DP;EX,RMOUNT 3051S1CD2A2F12A1KDA2DOK+ | 1 | EA | 3 | 3 | 6 | 1 | EA | 19.12 - Material Consumed | Supply for Order 100047965, Item 5 cannot be changed 180009111 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300001827 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180009111 | 90001493 | 05 | Preparation | 0000146486 | 5 | 0 | EA |  |  | 102000000002680 | 01-Road |  | 3-In Transit |  | WorkPackLink | QMP08CAGE | KCM-LNG | 0 | 5400001855 | 10 | 1 | EA | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000030899_2024 | 0 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2025-05-31 |  |  | 2025-03-01 |  |  | 100000002887 | 1020 | 2024-12-30 | 1 |  | 2024-03-06 | 4900035070_2024_0009 | 2024-03-04 | 144FT84 | 5000030899_2024_0001 | 0 | 2 | 0 | 90001493 | 1 | 0 | 180009111 | 2 | 0 | 0 | X | L | 4900035070 | 2024 |  | 5000030899 | 2024 | 0 |  | 2024-03-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452625 | TX,DP;EX,RMOUNT 3051S1CD2A2F12A1KDA2DOK+ | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Engineering Query/Management of Change | 90001493_0050 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 5 |  | 0 | 4900193789_2024 | 25SDLN1 | MJ | 1000000809 | AU1072 | 1000145855 | S002 | 30 | 30 | 5300001827 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-03-01 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146486 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-06-01 | 2025-05-31 | 2025-05-31 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100085112 | 0020 | 0030 | 100085112 | MOC-150252: Flow TX's Repl (2) 44FT21L/H | AA53.44FT21L | TX,FLOW LP FUEL GAS TO HEADER | AA01 | 20 | No issue identified | 10452625 | TX,DP;EX,RMOUNT 3051S1CD2A2F12A1KDA2DOK+ | 1 | EA | 3 | 3 | 6 | 1 | EA | 09.02 - SOH @ AA01 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021006 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030534 | 05 | Preparation | 0000267756 | 3 | 0 | EA | 102000000033626 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-08 | ODST-0090030534_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 44FT21L |  | 0 | 2 | 0 | 90030534 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452625 | TX,DP;EX,RMOUNT 3051S1CD2A2F12A1KDA2DOK+ |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030534_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000262795 | S002 | 30 | 30 | 5300021006 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267756 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100085112 | 0020 | 0040 | 100085112 | MOC-150252: Flow TX's Repl (2) 44FT21L/H | AA53.44FT21L | TX,FLOW LP FUEL GAS TO HEADER | AA01 | 20 | No issue identified | 10452626 | TX,DP;RG3,SMART,EXIA,EMERSON 3051S1 | 1 | EA | 3 | 0 | 1 | 1 | EA | 09.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021006 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030534 | 05 | Preparation | 0000267756 | 4 | 0 | EA | 102000000033197 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-08 | ODST-0090030534_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 44FT21H |  | 0 | 2 | 0 | 90030534 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452626 | TX,DP;RG3,SMART,EXIA,EMERSON 3051S1 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030534_0040 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000262795 | S002 | 30 | 30 | 5300021006 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267756 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-05 | 2024-12-01 | 2024-11-05 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0080 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10452628 | TX,PRESS;3051S1CG4A2F12A1KDA2DOK7Y2L4M5+ | 1 | EA | 0 | 0 | 0 | 0 |  | 04.12 - ETA 22.04.25 PO 4500036111 EMERSON CPT | Supply for Order 100039665, Item 20 cannot be changed 90023593 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023593 | 05 | Preparation | 0000138169 | 20 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-05 | ODST-0090023593_0010 | 0 | 0 | 0 | 0 |  | 2024-10-01 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  |  |  | 2024-03-07 | 0 |  | 2024-11-05 |  | 2024-11-10 | 144PT504 |  | 0 | 2 | 0 | 90023593 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-05 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452628 | TX,PRESS;3051S1CG4A2F12A1KDA2DOK7Y2L4M5+ | 2024-11-05 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 90023593_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 20 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 | 30 | 30 | 5300017367 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-05 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-01 | INLEC | 100047874 | 0010 | 0010 | 100047874 | MOC-124841 Transmitter Replace 114PT87 | AA53.114PIC87 | LOOP,CTRL PRESS TO E1409 SHELL OUTLET | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10452628 | TX,PRESS;3051S1CG4A2F12A1KDA2DOK7Y2L4M5+ | 1 | EA | 0 | 0 | 0 | 0 |  | 04.12 - ETA 22.04.25 PO 4500036111 EMERSON CPT | Supply for Order 100047874, Item 1 cannot be changed 90023935 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017557 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023935 | 05 | Preparation | 0000146415 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-07 | ODST-0090023935_0010 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  |  |  | 2022-11-30 | 0 |  | 2024-11-26 |  | 2024-12-01 | 114PT87 |  | 0 | 2 | 0 | 90023935 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452628 | TX,PRESS;3051S1CG4A2F12A1KDA2DOK7Y2L4M5+ | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works | 5 |  | 90023935_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000145844 | S002 | 30 | 30 | 5300017557 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146415 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0110 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 1 | EA | 2 | 1 | 3 | 1 | EA | 19.02 - At KGP | Supply for Order 100039666, Item 8 cannot be changed 90024949 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122880 | 9026892 | 05 | Preparation | 0000138170 | 8 | 0 | EA | 102000000029847 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391253_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056486 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230015_2025_0005 | 2025-03-01 | 144PT60 | 5000391253_2025_0003 | 0 | 2 | 0 | 90024949 | 1 | 0 | 180122911/180122880 | 2 | 0 | 0 | X | L | 4900230015 | 2025 |  | 5000391253 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026892_0070 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 8 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-04 | 2025-03-08 | INLEC | 100039667 | 0010 | 0110 | 100039667 | MOC-141259 TX Replace 144PT059 | AA53.144PT059 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 1 | EA | 2 | 1 | 3 | 1 | EA | 29.01 - At KGP | Supply for Order 100039667, Item 11 cannot be changed 180100943 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017556 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100943 | 9021449 | 05 | Preparation | 0000138171 | 11 | 0 | EA | 102000000025677 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000305871_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-04 |  |  | 2024-12-01 |  |  | 100000044758 | 1020 | 2024-03-07 | 1 |  | 2024-12-04 | 4900185005_2024_0003 | 2024-12-01 | 144PT059 | 5000305871_2024_0002 | 0 | 2 | 0 | 90023934 | 1 | 0 | 180100943 | 2 | 0 | 0 | X | L | 4900185005 | 2024 |  | 5000305871 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9021449_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 11 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137582 | S002 | 30 | 30 | 5300017556 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138171 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-08 | 2025-03-04 | 2025-03-04 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-21 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-03 | INLEC | 100039668 | 0030 | 0010 | 100039668 | MOC-141262 Transmitter Replace 244PT58 | AA53.244PT58 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 1 | EA | 2 | 1 | 3 | 1 | EA | 29.01 - At KGP | Supply for Order 100039668, Item 1 cannot be changed 180100949 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300018207 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100949 | 9021454 | 05 | Preparation | 0000138172 | 1 | 0 | EA | 102000000025674 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-21 | GRST-5000305870_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000044764 | 1020 | 2024-03-08 | 1 |  | 2024-12-04 | 4900185008_2024_0001 | 2024-12-01 | 244PT58 | 5000305870_2024_0001 | 0 | 2 | 0 | 90025183 | 1 | 0 | 180100949/180122906 | 2 | 0 | 0 | X | L | 4900185008 | 2024 |  | 5000305870 | 2024 | 0 |  | 2024-11-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 2024-11-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9021454_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137583 | S002 | 30 | 30 | 5300018207 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138172 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0100 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 1 | EA | 2 | 1 | 3 | 0 |  | 25.02 - SOH @ AA02 | Supply for Order 100039671, Item 9 cannot be changed 90024950 item 80 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024950 | 05 | Preparation | 0000138175 | 9 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024950_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-08 | 0 |  | 2025-02-24 |  | 2025-03-01 | 244PT60 |  | 0 | 2 | 0 | 90024950 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 90024950_0080 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 9 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 | 30 | 30 | 5300002039 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0020 | 0140 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 1 | EA | 2 | 1 | 3 | 0 |  | 25.02 - SOH @ AA02 | Supply for Order 100039741, Item 9 cannot be changed 90024952 item 80 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024952 | 05 | Preparation | 0000138265 | 9 | 0 | [8 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024952_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-08 | 0 |  | 2025-02-24 |  | 2025-03-01 | 344PT504 |  | 0 | 2 | 0 | 90024952 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 2024-01-01 | W |  | 0020 | Reconnect & Deisolate | INT | Reconnect & Deisolate |  | Management of Change | 90024952_0080 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 9 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 | 30 | 30 | 5300002054 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0880 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10452837 | LUBRICANT OIL:HYD,SHELL MORLINA S2 B 220 | 3 | DR | 9 | 0 | 0 | 2 | DR | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 88 cannot be changed 90028418 item 900010 already exists | Material picked; currently at KSF-PACK-SD-LRG/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 88 | 0 | DR |  |  | 102000000030930 |  |  |  |  | WorkPackLink | KSF-PACK-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0110/90028418_0090_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452837 | LUBRICANT OIL:HYD,SHELL MORLINA S2 B 220 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0110/90028418_0090_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 88 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 120 |  |  | 0 | 3 | DR | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0010 | 0010 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10455660 | BOLT SET;JOHN CRANE 87117388 | 1 | SET | 6 | 0 | 0 | 1 | SET | 03.10 - SOH @ AA02 | Supply for Order 100033564, Item 1 cannot be changed 90025011 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015700 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025011 | 05 | Preparation | 0000132018 | 1 | 0 | SET | 102000000031894 | 102000000029540 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025011_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025011 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10455660 | BOLT SET;JOHN CRANE 87117388 | 2024-09-23 | W |  | 0010 | As Found Alignment Record | INT | As Found Alignment Record |  |  | 90025011_0010 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000131400 | S002 | 30 | 30 | 5300015700 | 10 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132018 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0010 | 0010 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10455660 | BOLT SET;JOHN CRANE 87117388 | 1 | SET | 6 | 0 | 0 | 1 | SET | 03.10 - SOH @ AA02 | Supply for Order 100033565, Item 1 cannot be changed 90025012 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015705 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025012 | 05 | Preparation | 0000132019 | 1 | 0 | SET | 102000000031895 | 102000000029429 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025012_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025012 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10455660 | BOLT SET;JOHN CRANE 87117388 | 2024-09-24 | W |  | 0010 | As Found Alignment Record | INT | As Found Alignment Record |  |  | 90025012_0010 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000131501 | S002 | 30 | 30 | 5300015705 | 10 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132019 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0010 | 0020 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10455662 | BOLT SET;JOHN CRANE 87379229 | 1 | SET | 6 | 0 | 0 | 1 | SET | 03.10 - SOH @ AA02 | Supply for Order 100033564, Item 2 cannot be changed 90025011 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015700 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025011 | 05 | Preparation | 0000132018 | 2 | 0 | SET | 102000000031894 | 102000000029543 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025011_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025011 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10455662 | BOLT SET;JOHN CRANE 87379229 | 2024-09-23 | W |  | 0010 | As Found Alignment Record | INT | As Found Alignment Record |  |  | 90025011_0020 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000131400 | S002 | 30 | 30 | 5300015700 | 20 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132018 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0010 | 0020 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10455662 | BOLT SET;JOHN CRANE 87379229 | 1 | SET | 6 | 0 | 0 | 1 | SET | 03.10 - SOH @ AA02 | Supply for Order 100033565, Item 2 cannot be changed 90025012 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015705 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025012 | 05 | Preparation | 0000132019 | 2 | 0 | SET | 102000000031895 | 102000000029542 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025012_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025012 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10455662 | BOLT SET;JOHN CRANE 87379229 | 2024-09-24 | W |  | 0010 | As Found Alignment Record | INT | As Found Alignment Record |  |  | 90025012_0020 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000131501 | S002 | 30 | 30 | 5300015705 | 20 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132019 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-21 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-04 | INLEC | 100039669 | 0030 | 0010 | 100039669 | MOC-146093 Pressure TX Replace 244PT501 | AA53.244PT501 | TX,PRESS K4401B-P2A/P2B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10456607 | TX,PRESS;R/MOUNT 3051S1CG3A2F12A1KDA2DO+ | 1 | ASY | 1 | 0 | 2 | 1 | ASY | 19.02 - At KGP | Supply for Order 100039669, Item 1 cannot be changed 90025184 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300018206 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180122898 | 9027000 | 05 | Preparation | 0000138173 | 1 | 0 | ASY | 102000000025822 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-21 | GRST-5000391223_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056494 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230034_2025_0001 | 2024-12-01 | 244PT501 | 5000391223_2025_0001 | 0 | 2 | 0 | 90025184 | 1 | 0 | 180122898/180122901 | 2 | 0 | 0 | X | L | 4900230034 | 2025 |  | 5000391223 | 2025 | 0 |  | 2024-11-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10456607 | TX,PRESS;R/MOUNT 3051S1CG3A2F12A1KDA2DO+ | 2024-11-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9027000_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137584 | S002 | 30 | 30 | 5300018206 | 10 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138173 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0110 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10456607 | TX,PRESS;R/MOUNT 3051S1CG3A2F12A1KDA2DO+ | 1 | ASY | 1 | 0 | 2 | 1 | ASY | 19.02 - At KGP | Supply for Order 100039740, Item 9 cannot be changed 9026896 item 80 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180122886 | 9026896 | 05 | Preparation | 0000138264 | 9 | 0 | ASY | 102000000029948 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391234_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056490 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230021_2025_0001 | 2025-03-01 | 344PT501 | 5000391234_2025_0001 | 0 | 2 | 0 | 90024951 | 1 | 0 | 180122920/180122886 | 2 | 0 | 0 | X | L | 4900230021 | 2025 |  | 5000391234 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10456607 | TX,PRESS;R/MOUNT 3051S1CG3A2F12A1KDA2DO+ | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026896_0080 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 9 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 80 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-01-01 | 2024-12-27 | 2025-03-01 | 2025-05-16 | INLEC | 600001530 | 0010 | 0010 | 600001530 | MOC-107654/88803 Pre SD Scope 118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10457600 | CABLE,INSTR;1.5MM2,450/750V,SCR,SWA,BLK | 150 | M | 150 | 0 | 0 | 150 | M | 02.02 - 16 SOH @ AA02 | Supply for Order 600001530, Item 1 cannot be changed 90024965 item 10 already exists | Material picked; currently at SW3R07E02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004570 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90024965 | 05 | Preparation | 0000084445 | 1 | 0 | M |  |  | 102000000027605 |  |  |  |  | WorkPackLink | SW3R07E02A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 150 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024965_0010 | 0 | 0 | 0 | 0 |  | 2024-12-30 | AA53 | 2025-03-01 |  |  | 2025-01-01 |  |  |  |  | 2025-07-31 | 0 |  | 2024-12-27 |  | 2025-01-01 | 118UCV112 |  | 0 | 2 | 0 | 90024965 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-12-27 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10457600 | CABLE,INSTR;1.5MM2,450/750V,SCR,SWA,BLK | 2024-01-02 | W |  | 0010 | MOC-88803 Frac 1 Pre Works | INT | MOC-88803 Frac 1 Pre Works | 0 |  | 90024965_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000083862 | S002 |  | 30 | 5300004570 | 10 |  |  | 0 | 150 | M | 2001 | AA02 | 2024-12-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84445 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM06 | Capital
| 25SDLN4 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100082289 | 0020 | 0010 | 100082289 | OPSD1 4KT1430 Purge Valve Inverse | AA53.414UZV50C | SOL,TRIP PURGE AIR INTER VLV VENT | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10460304 | VALVE,SLND;EX,0.5",THOMPSON Y013AA1V2SS | 1 | EA | 4 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 100082289, Item 1 cannot be changed 90025064 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016548 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025064 | 05 | Preparation | 0000255561 | 1 | 0 | EA | 102000000029529 | 101000000132027 | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090025064_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414UZV50C |  | 0 | 2 | 0 | 90025064 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460304 | VALVE,SLND;EX,0.5",THOMPSON Y013AA1V2SS | 2024-10-17 | W |  | 0020 | Fault Find & Repair | INT | Fault Find & Repair |  |  | 90025064_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000251533 | S002 | 30 | 30 | 5300016548 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2024-08-08 | 255561 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0870 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10460488 | TAG WARNING:ACS SWAN EXPRESS PRINT,WEL 1 | 25 | EA | 1092 | 0 | 550 | 25 | EA | 24.09 - SOH at AA02 | Supply for Order 200147980, Item 87 cannot be changed 90028418 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 87 | 0 | EA | 102000000030539 | 102000000030067 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 25 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460488 | TAG WARNING:ACS SWAN EXPRESS PRINT,WEL 1 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0100 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 87 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 110 |  |  | 0 | 25 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-14 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0400 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 70 | M | 0 | 0 | 0 | 0 |  | 24.02 - ETA 07.03.25 PO 4500046831 MM CPT | Supply for Order 600001815, Item 50 cannot be changed 90030856 item 30 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 48 | AA01 | 5300011702 | 180 | CPT | 48 | 1000030037 | 50 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500046831 | 50 | 70 | M | 2025-03-07 |  | /180130608 |  | 90030856 | 07 | Execution | 0000084731 | 50 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2024-06-18 | ODST-0090030856_0030 | 0 | 60 | 57 | 60 | 2025-04-10 | 2025-02-22 | AA53 | 2025-02-08 |  |  | 2025-04-30 | 2025-04-12 | 2025-04-25 |  |  | 2024-08-30 | 0 |  | 2025-02-14 |  | 2025-02-27 | 37FQI40/41 |  | 0 | 2 | 2 | 90030856 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | /018013060 | 2025-02-14 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 2025-02-14 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030856_0030 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-14 | 10 | 6000015504 | 2025-04-12 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 | 30 | 30 | 5300007843 | 340 |  | 5300011702 | 180 | 70 | M | 1001 | AA02 | 2025-02-14 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-14 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0420 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Vendor Not able to deliver in-full | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 330 | M | 0 | 0 | 0 | 0 |  | 24.02 - ETA 07.03.25 PO 4500046831 MM CPT | Supply for Order 600001815, Item 52 cannot be changed – 4500046831 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 48 | AA01 | 5300011702 | 200 | CPT | 48 | 1000030027 | 52 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500046831 | 10 | 330 | M | 2025-03-07 |  | /180130608 |  |  | 07 | Execution | 0000084731 | 52 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 330 |  |  | Y | 1001 | 2024-06-18 | IDPO-/018013060 | 1 | 60 | 57 | 60 | 2025-04-10 | 2025-02-22 | AA53 | 2025-02-08 |  |  | 2025-04-30 | 2025-04-12 | 2025-04-25 |  |  | 2024-08-30 | 0 |  | 2025-02-14 |  | 2025-02-27 | 37FQI40/41 |  | 0 | 2 | 2 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | /018013060 | 2025-02-14 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 2025-02-14 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour | [5 empty] | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-14 | 10 | 6000015504 | 2025-04-12 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 | 30 | 30 | 5300007843 | 360 |  | 5300011702 | 200 | 330 | M | 1001 | AA02 | 2025-02-14 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-14 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0390 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 330 | M | 0 | 0 | 0 | 0 |  | 21.02 - ETA 07.03.25 PO 4500046831 MM CPT | Supply for Order 600001815, Item 49 cannot be changed 90030856 item 20 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 48 | AA01 | 5300011702 | 170 | CPT | 48 | 1000030036 | 49 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500046831 | 40 | 330 | M | 2025-03-07 |  | /180132788 |  | 90030856 | 07 | Execution | 0000084731 | 49 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 330 |  |  | Y | 1001 | 2024-06-18 | ODST-0090030856_0020 | 0 | 60 | 57 | 60 | 2025-04-10 | 2025-02-22 | AA53 | 2025-02-08 |  |  | 2025-04-30 | 2025-04-12 | 2025-04-25 |  |  | 2024-08-30 | 0 |  | 2025-02-14 |  | 2025-02-27 | 37FQI40/41 |  | 0 | 2 | 2 | 90030856 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | /018013278 | 2025-02-14 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 2025-02-14 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030856_0020 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-14 | 10 | 6000015504 | 2025-04-12 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 | 30 | 30 | 5300007843 | 330 |  | 5300011702 | 170 | 330 | M | 1001 | AA02 | 2025-02-14 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-14 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0430 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 70 | M | 0 | 0 | 0 | 0 |  | 24.02 - ETA 07.03.25 PO 4500046831 MM CPT | Supply for Order 600001815, Item 53 cannot be changed 90030856 item 60 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 48 | AA01 | 5300011702 | 210 | CPT | 48 | 1000030027 | 53 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500046831 | 20 | 70 | M | 2025-03-07 |  | /180130608 |  | 90030856 | 07 | Execution | 0000084731 | 53 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2024-06-18 | ODST-0090030856_0060 | 0 | 60 | 57 | 60 | 2025-04-10 | 2025-02-22 | AA53 | 2025-02-08 |  |  | 2025-04-30 | 2025-04-12 | 2025-04-25 |  |  | 2024-08-30 | 0 |  | 2025-02-14 |  | 2025-02-27 | 37FQI40/41 |  | 0 | 2 | 2 | 90030856 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | /018013060 | 2025-02-14 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 2025-02-14 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030856_0060 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-14 | 10 | 6000015504 | 2025-04-12 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 | 30 | 30 | 5300007843 | 370 |  | 5300011702 | 210 | 70 | M | 1001 | AA02 | 2025-02-14 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-14 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0410 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Orchestrated PR Item has been deleted | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 330 | M | 0 | 0 | 0 | 0 |  | 24.02 - ETA 07.03.25 PO 4500046831 MM CPT | Supply for Order 600001815, Item 51 cannot be changed 90030856 item 40 already exists | PR approved; PO not issued | SP97 | Direct Multi-base | 48 | AA01 | 5300011702 | 190 |  | 48 | 1000030038 | 51 |  |  |  | 0 | 0 | M |  |  |  |  | 90030856 | 07 | Execution | 0000084731 | 51 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 330 |  |  |  | 1001 | 2024-06-18 | PRPO-1000030038_00051 | 0 | 60 | 57 | 60 | 2025-04-10 | 2025-02-22 | AA53 | 2025-02-08 |  |  | 2025-04-30 | 2025-04-12 | 2025-04-25 |  |  | 2024-08-30 | 0 |  | 2025-02-14 |  | 2025-02-27 | 37FQI40/41 |  | 0 | 2 | 2 | 90030856 | 0 | 0 |  | 1 | 1 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-14 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460844 | CABLE INSTRUMENTATION:2PR,1.5MM2,110V,SC | 2025-02-14 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030856_0040 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-14 | 10 |  | 2025-04-12 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 | 30 | 30 | 5300007843 | 350 |  | 5300011702 | 190 | 330 | M | 1001 | AA02 | 2025-02-14 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SD2420 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086119 | 0020 | 0010 | 100086119 | Pressure/Temp Gauge Function Test 1K2420 | AA53.124PG | GAUGE,PRESSURE UNIT 2400 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10460925 | GAUGE,PRESS;0-10000KPA,100MM,SS | 1 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 28.02.25 PO 4500038013 ex Wika | Supply for Order 100086119, Item 1 cannot be changed 90028281 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018528 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028281 | 05 | Preparation | 0000272240 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-28 | ODST-0090028281_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124PG43 |  | 0 | 2 | 0 | 90028281 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460925 | GAUGE,PRESS;0-10000KPA,100MM,SS | 2024-11-28 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90028281_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000266973 | S002 | 30 | 30 | 5300018528 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-11-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | INLEC | 100086242 | 0020 | 0030 | 100086242 | MOC-***** HYD Dump Vlve Repl (2) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | WO item has not been released yet | 10460997 | ADAPTOR,CDUIT;EX,90DEG,M/F,M20/M20 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000272294 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  |  |  |  | 1KT2420 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10460997 | ADAPTOR,CDUIT;EX,90DEG,M/F,M20/M20 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000267031 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-01-21 | 2025-05-08 | 2025-01-13 | 2025-05-08 | 2025-05-09 | INLEC | 100089986 | 0010 | 0010 | 100089986 | OPSD1 414UV955 SAS Replace Regulator | AA53.414PDCV955 | VALVE,CTRL PRESS 414UV955V1 IA RECEIVER | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(09.01.2025) | 10461277 | REGULATOR,PRESS;NORGREN 20AGX8GPH100 | 1 | EA | 0 | 0 | 8 | 0 |  | 10.03 - ETA 21.03.25 PO 4500042243 SCORE CPT | Supply for Order 100089986, Item 1 cannot be changed 90028219 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019850 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028219 | 05 | Preparation | 0000288837 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-P08-OPSD | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028219_0010 | 0 | 0 | 0 | 0 |  | 2025-01-16 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-07-05 | 0 |  | 2025-01-13 |  | 2025-01-18 | 100089986 |  | 0 | 2 | 0 | 90028219 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-01-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10461277 | REGULATOR,PRESS;NORGREN 20AGX8GPH100 | 2025-01-09 | W |  | 0010 | OPSD1 414UV955 SAS Replace Regulator | INT | OPSD1 414UV955 SAS Replace Regulator | 3 | Opportune Shutdown | 90028219_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000282901 | S002 | 30 | 30 | 5300019850 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-01-13 |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41088 | 2025-01-04 | 288837 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-09 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0220 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10461586 | PLUG,TUBE;BLANKING,PL,1.00",BLK | 2000 | EA | 1000 | 0 | 1152 | 0 |  | 07.03 - PR 2000283106 1500 IN STOCK | Supply for Order 100090053, Item 22 cannot be changed 90032376 item 220 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 22 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2000 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0220 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10461586 | PLUG,TUBE;BLANKING,PL,1.00",BLK | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0220 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 22 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 220 |  |  | 0 | 2000 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0100 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10461586 | PLUG,TUBE;BLANKING,PL,1.00",BLK | 1000 | EA | 1000 | 0 | 1152 | 1000 | EA | 02.03 - SOH @ AA02 | Supply for Order 500005166, Item 30 cannot be changed 90031501 item 120 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 30 | 0 | EA | 101000000149997 |  | 101000000150366 | 01-Road |  | 5-Completed |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1000 | 2025-03-04 | 2025-03-02 | Y | 1001 | 2025-02-13 | ODST-0090031501_0120 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10461586 | PLUG,TUBE;BLANKING,PL,1.00",BLK | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0120 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 30 |  | 0 |  | 25SDENA1 | MJ | 20005471 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 260 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2025-03-27 |  |  | 2025-02-28 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146436 | 0010 | 0030 | 200146436 | 1Y Cond Prod Pump Service - 5P2002B | AA53.5P2002B | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10462535 | GREASE,GP;SHELL,GADUS S2 V220 2,450G | 2 | CQ | 84 | 0 | 231 | 2 | CQ | 03.10 - SOH @ AA02 | Supply for Order 200146436, Item 3 cannot be changed 90025016 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015715 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90025016 | 05 | Preparation | 0000234313 | 3 | 0 | CQ | 102000000031897 | 102000000028420 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025016_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025016 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10462535 | GREASE,GP;SHELL,GADUS S2 V220 2,450G | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025016_0030 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231369 | S002 | 30 | 30 | 5300015715 | 30 |  |  | 0 | 2 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234313 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146437 | 0010 | 0030 | 200146437 | 1Y Cond Prod Pump Service - 5P2002A | AA53.5P2002A | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10462535 | GREASE,GP;SHELL,GADUS S2 V220 2,450G | 2 | CQ | 84 | 0 | 231 | 2 | CQ | 03.10 - SOH @ AA02 | Supply for Order 200146437, Item 3 cannot be changed 90025015 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015714 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90025015 | 05 | Preparation | 0000234314 | 3 | 0 | CQ | 102000000031890 | 102000000028422 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025015_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025015 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10462535 | GREASE,GP;SHELL,GADUS S2 V220 2,450G | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025015_0030 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231370 | S002 | 30 | 30 | 5300015714 | 30 |  |  | 0 | 2 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234314 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146438 | 0010 | 0030 | 200146438 | 1Y Cond Heater Pump Service - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10462535 | GREASE,GP;SHELL,GADUS S2 V220 2,450G | 2 | CQ | 84 | 0 | 231 | 2 | CQ | 03.10 - SOH @ AA02 | Supply for Order 200146438, Item 3 cannot be changed 90025014 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015713 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90025014 | 05 | Preparation | 0000234315 | 3 | 0 | CQ | 102000000031893 | 102000000028421 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025014_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025014 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10462535 | GREASE,GP;SHELL,GADUS S2 V220 2,450G | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 | Ready for Release | 90025014_0030 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231371 | S002 | 30 | 30 | 5300015713 | 30 |  |  | 0 | 2 | CQ | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234315 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146439 | 0010 | 0030 | 200146439 | 1Y Cond Heater Pump Service - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10462535 | GREASE,GP;SHELL,GADUS S2 V220 2,450G | 2 | CQ | 84 | 0 | 231 | 2 | CQ | 03.10 - SOH @ AA02 | Supply for Order 200146439, Item 3 cannot be changed 90025013 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015712 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90025013 | 05 | Preparation | 0000234316 | 3 | 0 | CQ | 102000000031907 | 102000000028399 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025013_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025013 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10462535 | GREASE,GP;SHELL,GADUS S2 V220 2,450G | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025013_0030 |  |  | ST5 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231372 | S002 | 30 | 30 | 5300015712 | 30 |  |  | 0 | 2 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234316 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0082 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 1 | EA | 16 | 0 | 4 | 1 | EA | 19.02 - At KGP | Supply for Order 100039666, Item 11 cannot be changed 90024949 item 100 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122883 | 9026893 | 05 | Preparation | 0000138170 | 11 | 0 | EA | 102000000029646 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391260_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056487 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230018_2025_0007 | 2025-03-01 | 144PT60 | 5000391260_2025_0004 | 0 | 2 | 0 | 90024949 | 1 | 0 | 180122911/180122883 | 2 | 0 | 0 | X | L | 4900230018 | 2025 |  | 5000391260 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026893_0100 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 11 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0072 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 1 | EA | 16 | 0 | 4 | 1 | EA | 29.01 - At KGP | Supply for Order 100039671, Item 10 cannot be changed 9026122 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117407 | 9026122 | 05 | Preparation | 0000138175 | 10 | 0 | EA | 102000000030523 | 101000000134373 | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000369098_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000054506 | 1020 | 2024-03-08 | 1 |  | 2025-01-22 | 4900216315_2025_0001 | 2025-03-01 | 244PT60 | 5000369098_2025_0001 | 0 | 2 | 0 | 90024950 | 1 | 0 | 180117407 | 2 | 0 | 0 | X | L | 4900216315 | 2025 |  | 5000369098 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 9026122_0090 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 10 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 | 30 | 30 | 5300002039 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0072 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 1 | EA | 16 | 0 | 4 | 1 | EA | 19.02 - At KGP | Supply for Order 100039740, Item 11 cannot be changed 9026895 item 100 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122885 | 9026895 | 05 | Preparation | 0000138264 | 11 | 0 | EA | 102000000030158 | 101000000134326 | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391238_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056489 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900229989_2025_0007 | 2025-03-01 | 344PT501 | 5000391238_2025_0004 | 0 | 2 | 0 | 90024951 | 1 | 0 | 180122920/180122885 | 2 | 0 | 0 | X | L | 4900229989 | 2025 |  | 5000391238 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026895_0100 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 11 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0010 | 0102 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 1 | EA | 16 | 0 | 4 | 1 | EA | 19.02 - At KGP | Supply for Order 100039741, Item 8 cannot be changed 9026898 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122893 | 9026898 | 05 | Preparation | 0000138265 | 8 | 0 | EA | 102000000030157 | 101000000134327 | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391263_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056492 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230033_2025_0005 | 2025-03-01 | 344PT504 | 5000391263_2025_0003 | 0 | 2 | 0 | 90024952 | 1 | 0 | 180122893 | 2 | 0 | 0 | X | L | 4900230033 | 2025 |  | 5000391263 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Management of Change | 9026898_0070 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 8 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 | 30 | 30 | 5300002054 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDFLR | Released | 2024-11-08 | 2025-02-12 | 2025-02-11 | 2025-05-01 | 2025-05-02 | INLEC | 600001756 | 0010 | 0040 | 600001756 | MOC-119238 Replace Flare Flowmtr 37FQI41 | AA53.37FQI41 | LOOP,MASS FLOW TO FLARE A3711B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10465252 | RAIL:SAFETY,BRANACH,S-PLT HANDRAIL | 2 | EA | 3 | 0 | 0 | 0 |  | 18.02 - SOH @ AA01 | Supply for Order 600001756, Item 4 cannot be changed 90030686 item 30 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007842 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030686 | 07 | Execution | 0000084652 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030686_0030 | 0 | 4 | 0 | 0 |  | 2025-02-10 | AA53 | 2025-05-01 |  |  | 2025-02-16 |  |  |  |  | 2024-09-05 | 0 |  | 2025-02-11 |  | 2025-02-16 | 37FQI40/41 |  | 0 | 2 | 0 | 90030686 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-11 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10465252 | RAIL:SAFETY,BRANACH,S-PLT HANDRAIL | 2025-02-11 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030686_0030 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084066 | S002 | 30 | 30 | 5300007842 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-11 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84652 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-02 | 2025-05-01 | 2025-05-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-02-12 | 2025-02-11 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0350 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10465252 | RAIL:SAFETY,BRANACH,S-PLT HANDRAIL | 1 | EA | 3 | 0 | 0 | 0 |  | 18.02 - SOH @ AA01 | Supply for Order 600001815, Item 45 cannot be changed 90030688 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030688 | 07 | Execution | 0000084731 | 45 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030688_0020 | 0 | 4 | 0 | 0 |  | 2025-02-10 | AA53 | 2025-02-08 |  |  | 2025-02-16 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-11 |  | 2025-02-16 | 37FQI40/41 |  | 0 | 2 | 0 | 90030688 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-11 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10465252 | RAIL:SAFETY,BRANACH,S-PLT HANDRAIL | 2025-02-11 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030688_0020 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 45 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 310 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-11 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-02-12 | 2025-02-11 | 2025-05-01 | 2025-05-02 | INLEC | 600001756 | 0010 | 0020 | 600001756 | MOC-119238 Replace Flare Flowmtr 37FQI41 | AA53.37FQI41 | LOOP,MASS FLOW TO FLARE A3711B | AA01 | 10 | Del to Maintenance after Reqmt Date | 10465254 | LADDER,STEP;BRANACH FPL12 | 1 | EA | 1 | 0 | 0 | 1 | EA | 11.02 - qty 3 SOH @ AA01 | Supply for Order 600001756, Item 2 cannot be changed 90030686 item 10 already exists | Material picked; currently at KSF-PACK-SD-LRG/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300007842 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030686 | 07 | Execution | 0000084652 | 2 | 0 | EA |  |  | 101000000146612 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-PACK-SD-LRG | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2025-02-27 | 2025-02-27 | Y | 1001 | 2024-03-13 | ODST-0090030686_0010 | 0 | 4 | 0 | 0 |  | 2025-02-10 | AA53 | 2025-05-01 |  |  | 2025-02-16 |  |  |  |  | 2024-09-05 | 0 |  | 2025-02-11 |  | 2025-02-16 | 37FQI40/41 |  | 0 | 2 | 0 | 90030686 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-11 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10465254 | LADDER,STEP;BRANACH FPL12 | 2025-02-11 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030686_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SDFLR | MJ | 20005556 | AU1072 | 1000084066 | S002 | 30 | 30 | 5300007842 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-11 |  |  | 2025-02-25 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84652 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-02 | 2025-05-01 | 2025-05-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-02-12 | 2025-02-11 | 2025-05-01 | 2025-05-02 | INLEC | 600001756 | 0010 | 0030 | 600001756 | MOC-119238 Replace Flare Flowmtr 37FQI41 | AA53.37FQI41 | LOOP,MASS FLOW TO FLARE A3711B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10465257 | LADDER,BRANACH FPL 2.1,2100MM,PLATFORM | 1 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 11.03.25 PO 4500045866 BLACKWOODS CPT | Supply for Order 600001756, Item 3 cannot be changed 90030686 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007842 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030686 | 07 | Execution | 0000084652 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030686_0020 | 0 | 4 | 0 | 0 |  | 2025-02-10 | AA53 | 2025-05-01 |  |  | 2025-02-16 |  |  |  |  | 2024-09-05 | 0 |  | 2025-02-11 |  | 2025-02-16 | 37FQI40/41 |  | 0 | 2 | 0 | 90030686 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-11 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10465257 | LADDER,BRANACH FPL 2.1,2100MM,PLATFORM | 2025-02-11 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030686_0020 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084066 | S002 | 30 | 30 | 5300007842 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-11 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84652 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-02 | 2025-05-01 | 2025-05-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital | C0-001035-6A-08-01
| 25SDFR1 | Released | 2024-01-02 | 2025-01-01 | 2024-11-05 | 2025-03-01 | 2025-05-16 | INLEC | 600001530 | 0010 | 0022 | 600001530 | MOC-107654/88803 Pre SD Scope 118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10465355 | CONDUIT;THD,25MM,4M,GALV ST | 6 | EA | 40 | 0 | 10 | 6 | EA | 29.01 - At KGP | Supply for Order 600001530, Item 4 cannot be changed 180091708 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004570 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180091708 | 90023577 | 05 | Preparation | 0000084445 | 4 | 0 | EA | 102000000023527 |  | 107000000000376 |  |  |  | P07YRDBY19 | WorkPackLink | P07YRDBY19 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000274880_2024 | 0 | 0 | 0 | 0 |  | 2024-11-05 | AA53 | 2025-03-01 |  |  | 2025-01-01 |  |  | 100000040526 | 1020 | 2025-07-31 | 6 |  | 2024-11-11 | 4900169465_2024_0001 | 2024-11-10 | 118UCV112 | 5000274880_2024_0001 | 0 | 2 | 0 | 90023577 | 6 | 0 | 180091708 | 2 | 0 | 0 | X | L | 4900169465 | 2024 |  | 5000274880 | 2024 | 0 |  | 2024-11-05 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10465355 | CONDUIT;THD,25MM,4M,GALV ST | 2024-01-02 | W |  | 0010 | MOC-88803 Frac 1 Pre Works | INT | MOC-88803 Frac 1 Pre Works | 0 |  | 90023577_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000083862 | S002 | 30 | 30 | 5300004570 | 30 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84445 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM06 | Capital
| 25SD4401 | Released | 2024-10-17 | 2025-03-01 | 2024-11-05 | 2025-03-01 | 2025-04-29 | INLEC | 100033849 | 0020 | 0010 | 100033849 | Replace Faulty RCU (1) K4401BPM1A | AA53.K4401BP1A | PUMP,SEAL OIL SYSTEM SUPPLY FOR K4401B | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10465376 | RCU;CCH GHG29343723202008FLMGVM251M321 | 1 | EA | 1 | 0 | 1 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 100033849, Item 1 cannot be changed 90023588 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016502 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023588 | 05 | Preparation | 0000132383 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090023588_0010 | 0 | 0 | 0 | 0 |  | 2024-11-05 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-22 | 0 |  | 2024-11-05 |  | 2024-11-10 | K4401BP1A |  | 0 | 2 | 0 | 90023588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10465376 | RCU;CCH GHG29343723202008FLMGVM251M321 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90023588_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000131785 | S002 | 30 | 30 | 5300016502 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132383 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-03-14 | 2025-03-09 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0270 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10466117 | FLASHLIGHT;EX,WOLF WOLFM60 | 10 | EA | 1 | 0 | 25 | 0 |  | 07.03 - ETA 13.03.25 PO 4500047611 BLACKWOODS CPT | Supply for Order 100090053, Item 27 cannot be changed 90032192 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032192 | 05 | Preparation | 0000289018 | 27 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032192_0020 | 0 | 0 | 0 | 0 |  | 2025-03-12 | AA53 | 2025-05-23 |  |  | 2025-03-14 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-09 |  | 2025-03-14 | 3E1405/Ray R |  | 0 | 2 | 0 | 90032192 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-09 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10466117 | FLASHLIGHT;EX,WOLF WOLFM60 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032192_0020 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 27 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 270 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-09 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146405 | 0010 | 0010 | 200146405 | 1Y Repl UV Tubes - 5F2001 | AA53.520XE041 | DET,FLAME HEATER 5F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10467961 | TUBE,SCANNER;FIREYE INC 43141 | 1 | EA | 3 | 0 | 1 | 1 | EA | 24.10 - SOH @ AA01 | Supply for Order 200146405, Item 1 cannot be changed 90025074 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016809 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025074 | 05 | Preparation | 0000234273 | 1 | 0 | EA | 102000000031903 | 102000000029939 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-24 | ODST-0090025074_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520XE041 |  | 0 | 2 | 0 | 90025074 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10467961 | TUBE,SCANNER;FIREYE INC 43141 | 2024-10-23 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90025074_0010 |  |  | ST5 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231358 | S002 | 30 | 30 | 5300016809 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234273 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147130 | 0010 | 0010 | 200147130 | 1Y INSP REPLACEMENT OF UV SOURCE | AA53.123XE041 | DET,FLAME 1F2301 BURNER NO 1 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10467961 | TUBE,SCANNER;FIREYE INC 43141 | 1 | EA | 3 | 0 | 1 | 1 | EA | 24.10 - SOH @ AA01 | Supply for Order 200147130, Item 1 cannot be changed 90025075 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016811 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025075 | 05 | Preparation | 0000235402 | 1 | 0 | EA | 102000000029938 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-24 | ODST-0090025075_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025075 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10467961 | TUBE,SCANNER;FIREYE INC 43141 | 2024-10-23 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90025075_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000232445 | S002 | 30 | 30 | 5300016811 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0010 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10470158 | GASKET;597X575MM,KLINGER K116007261 | 1 | EA | 1 | 0 | 1 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200082188, Item 1 cannot be changed 90028591 item 10 already exists | Material picked; currently at WH2-PACK-SD-1A/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020023 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028591 | 05 | Preparation | 0000117838 | 1 | 0 | EA |  |  | 102000000031805 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1A | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028591_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200082188 |  | 0 | 2 | 0 | 90028591 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10470158 | GASKET;597X575MM,KLINGER K116007261 | 2025-01-14 | W |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools |  |  | 90028591_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000117251 | S002 | 30 | 30 | 5300020023 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117838 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0020 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10470159 | GASKET;597X575MM,KLINGER K116007262 | 1 | EA | 2 | 0 | 0 | 1 | EA | 17.01 - SOH @ AA02 | Supply for Order 200082188, Item 2 cannot be changed 90028591 item 20 already exists | Material picked; currently at WH2-PACK-SD-1A/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020023 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028591 | 05 | Preparation | 0000117838 | 2 | 0 | EA |  |  | 102000000031806 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1A | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028591_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200082188 |  | 0 | 2 | 0 | 90028591 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10470159 | GASKET;597X575MM,KLINGER K116007262 | 2025-01-14 | W |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools |  |  | 90028591_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000117251 | S002 | 30 | 30 | 5300020023 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117838 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-03-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005190 | 0010 | 0080 | 500005190 | KGP 2025 Rotating Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 30 | No Issue identified | 10471184 | GASKET;1500X2000X1.50MM,KLINGER 757224 | 2 | EA | 0 | 0 | 0 | 0 |  | 07.03 - ETA 27.03.25 PO 4500048618 KLINGER CPT |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022062 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032308 | 05 | Preparation | 0000299465 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-03-05 | ODST-0090032308_0080 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-12 | 0 |  | 2025-03-27 |  | 2025-04-01 |  |  | 0 | 2 | 0 | 90032308 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10471184 | GASKET;1500X2000X1.50MM,KLINGER 757224 |  |  |  | 0010 | KGP 2025 Rotating Consumables | NCNF | KGP 2025 Rotating Consumables |  |  | 90032308_0080 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 8 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000292874 | S002 | 30 | 30 | 5300022062 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2025-03-05 | 299465 | 0 | 0 |  | 1020 | 3 |  |  | 5 | Low | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-12 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0070 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | PR due for release | 10473075 | CABLE,PWR,2C+E,10MM2,XLPE,SWA,PVC,ORN | 10 | M | 0 | 0 | 0 | 0 |  | 09.02 - PR 1000029414 | Supply for Order 600001815, Item 13 cannot be changed 90030392 item 50 already exists | PR approved; PO not issued | SP97 | Direct Multi-base | 131 | AA01 | 5300011702 | 60 |  | 7 | 1000029414 | 13 |  |  |  | 0 | 0 | M |  |  |  |  | 90030392 | 07 | Execution | 0000084731 | 13 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-06-18 | PRPO-1000029414_00013 | 0 | 134 | 134 | 134 | 2025-06-24 | 2025-02-22 | AA53 | 2025-02-08 |  |  | 2025-07-13 | 2025-06-26 | 2025-07-08 |  |  | 2024-08-30 | 0 |  | 2025-02-12 |  | 2025-02-24 | 37FQI40/41 |  | 0 | 2 | 2 | 90030392 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473075 | CABLE,PWR,2C+E,10MM2,XLPE,SWA,PVC,ORN | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030392_0050 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-06 | 10 |  | 2025-06-26 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 |  | 30 | 5300007843 | 80 |  | 5300011702 | 60 | 10 | M | 1001 | AA02 | 2025-02-12 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SD4401 | Released | 2025-01-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100033160 | 0020 | 0020 | 100033160 | MOC-146133 - Replace Tx - 244LT511 | AA53.244LT511 | TX,LEVEL K4401B-E2 DEGASSING TANK | AA01 | 30 | No issue identified | 10473305 | M/FOLD,VV;KEYSTONE AS4TVIS22SGGYIWP | 1 | EA | 0 | 1 | 6 | 0 |  | 24.01 - ETA 24.02.25 PO 4500031738 CPT |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020235 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029003 | 05 | Preparation | 0000131681 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-21 | ODST-0090029003_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-11-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 244LT511 |  | 0 | 2 | 0 | 90029003 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473305 | M/FOLD,VV;KEYSTONE AS4TVIS22SGGYIWP |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 90029003_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000131050 | S002 | 30 | 30 | 5300020235 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131681 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-10-04 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | VALVE | 100076445 | 0030 | 0020 | 100076445 | MV-RE 1/2" 300# 244LT512 | AA53.244LT512 | TX,LEVEL DRAIN POT 2K4401V5A | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.10.2024) | 10473305 | M/FOLD,VV;KEYSTONE AS4TVIS22SGGYIWP | 1 | EA | 0 | 1 | 6 | 1 | EA | 29.01 - At KGP | Supply for Order 100076445, Item 5 cannot be changed 180113542 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016044 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180113542 | 9024197 | 05 | Preparation | 0000232991 | 5 | 0 | EA | 101000000132169 |  | 102000000029402 | 01-Road |  | 3-In Transit |  | WorkPackLink | INLEC-CAGE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-04 | GRST-5000351331_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000051584 | 1020 | 2025-10-30 | 1 |  | 2025-01-10 | 4900207024_2025_0001 | 2025-03-01 | 244LT512 | 5000351331_2025_0001 | 0 | 2 | 0 | 90025022 | 1 | 0 | 180113542 | 2 | 0 | 0 | X | L | 4900207024 | 2025 |  | 5000351331 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473305 | M/FOLD,VV;KEYSTONE AS4TVIS22SGGYIWP | 2024-10-15 | W |  | 0030 | Complete Manifold Replacement | INT | Complete Manifold Replacement |  |  | 9024197_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SD4401 | MJ | 1000005296 | AU1072 | 1000230114 | S002 | 30 | 30 | 5300016044 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-03-07 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-04-17 | 232991 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFLR | Released | 2024-11-08 | 2025-03-31 | 2025-03-26 | 2025-05-01 | 2025-05-02 | INLEC | 600001756 | 0010 | 0050 | 600001756 | MOC-119238 Replace Flare Flowmtr 37FQI41 | AA53.37FQI41 | LOOP,MASS FLOW TO FLARE A3711B | AA01 | 10 | No Issue identified | 10473850 | TRAY,CABLE;2.4MX100X1.6MM,KOUNIS CTT10H | 18 | EA | 0 | 0 | 10 | 0 |  | 02.03 - ETA 04.04.25 PO 4500047817 MM CPT |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007842 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032207 | 07 | Execution | 0000084652 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-03-13 | ODST-0090032207_0010 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-05-01 |  |  | 2025-03-31 |  |  |  |  | 2024-09-05 | 0 |  | 2025-03-26 |  | 2025-03-31 | SCOTT KINLOC |  | 0 | 2 | 0 | 90032207 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473850 | TRAY,CABLE;2.4MX100X1.6MM,KOUNIS CTT10H |  |  |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90032207_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084066 | S002 | 30 | 30 | 5300007842 | 50 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84652 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-02 | 2025-05-01 | 2025-05-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-31 | 2025-03-26 | 2025-05-01 | 2025-05-02 | INLEC | 600001756 | 0010 | 0060 | 600001756 | MOC-119238 Replace Flare Flowmtr 37FQI41 | AA53.37FQI41 | LOOP,MASS FLOW TO FLARE A3711B | AA01 | 10 | No Issue identified | 10473854 | PLATE,SPLC;ST,KOUNIS CTPHK | 36 | EA | 0 | 0 | 0 | 0 |  | 02.03 - ETA 04.04.25 PO 4500047817 MM CPT |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007842 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032207 | 07 | Execution | 0000084652 | 6 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 36 |  |  | Y | 1001 | 2024-03-13 | ODST-0090032207_0020 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-05-01 |  |  | 2025-03-31 |  |  |  |  | 2024-09-05 | 0 |  | 2025-03-26 |  | 2025-03-31 | SCOTT KINLOC |  | 0 | 2 | 0 | 90032207 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473854 | PLATE,SPLC;ST,KOUNIS CTPHK |  |  |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90032207_0020 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084066 | S002 | 30 | 30 | 5300007842 | 60 |  |  | 0 | 36 | EA | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84652 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-02 | 2025-05-01 | 2025-05-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital | C0-001035-6A-08-01
| 25SDLN3 | Released | 2025-02-28 | 2025-05-19 | 2025-05-14 | 2025-05-19 | 2025-05-20 | VALVE | 100043286 | 0010 | 0010 | 100043286 | Replace Valve Gland Packing 311LCV03 | AA53.311LCV03 | VALVE,LVL BOTTOMS FROM 3C1101 | AA01 | 255 | No Issue identified | 10473939 | KIT,LIVE LOADING,VALTEK 094137.556.000 | 1 | KIT | 0 | 0 | 0 | 0 |  | 06.03 - ETA 21.05.25 PO 4500048444 SCORE CPT |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300021913 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT | [5 empty] | 05 | Preparation | 0000141787 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-28 | STST-5300021913_00010 | 0 | 0 | 0 | 0 |  | 2025-05-17 | AA53 | 2025-05-19 |  |  | 2025-05-19 |  |  |  |  | 2025-10-31 | 0 |  | 2025-05-14 |  | 2025-05-19 |  |  | 0 | 2 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-05-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473939 | KIT,LIVE LOADING,VALTEK 094137.556.000 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000141176 | S002 | 30 | 30 | 5300021913 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-05-14 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141787 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-20 | 2025-05-19 | 2025-05-19 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0120 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Shipped qty below requirement qty | 10477583 | CHAIN,SAFETY,SC-PWC-8MM,YLW,25M RL | 4 | EA | 1 | 0 | 3 | 3 | EA | 02.03 - SOH @ AA02 | Supply for Order 500004676, Item 12 cannot be changed 90031855 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180134140 | 9029111 | 07 | Execution | 0000278102 | 12 | 0 | EA |  |  | 101000000149696 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-12 | GRST-5000435327_2025 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060592 | 1020 | 2025-12-31 | 3 |  | 2025-03-10 | 4900263705_2025_0001 | 2025-04-01 | TA OPS/BAILS | 5000435327_2025_0001 | 0 | 2 | 0 | 90031855 | 3 | 0 | 180134140 | 1 | 0 | 0 | X | L | 4900263705 | 2025 |  | 5000435327 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10477583 | CHAIN,SAFETY,SC-PWC-8MM,YLW,25M RL | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0110/9029111_0110 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 12 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 120 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100042804 | 0001 | 0010 | 100042804 | Replace Indication Pilot Lamps GT4008CO2 | AA53.GT4008CO2 | SYSTEM,GT4008 CO2 FIRE SUPPRESSION | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(24.06.2024) | 10478885 | LAMP,GLOW;BLOHMVOSS 29537 | 10 | EA | 10 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA01 | Supply for Order 100042804, Item 4 cannot be changed 90024987 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300011994 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024987 | 05 | Preparation | 0000141258 | 4 | 0 | EA | 101000000142445 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-06-24 | ODST-0090024987_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-10-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024987 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10478885 | LAMP,GLOW;BLOHMVOSS 29537 | 2024-06-24 | W |  | 0001 | Materials Assurance | INT | Materials Assurance |  | Order Requires Replanning | 90024987_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000140640 | S002 |  | 30 | 5300011994 | 10 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141258 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-03-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005190 | 0010 | 0020 | 500005190 | KGP 2025 Rotating Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 30 | No Issue identified | 10479740 | LUBRICANT PENETRATING | 50 | CAN | 0 | 1 | 25 | 0 |  | 07.03 - PR 2000283759 RFQ |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022062 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  |  | 90032308 | 05 | Preparation | 0000299465 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-03-05 | ODST-0090032308_0020 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-12 | 0 |  | 2025-03-27 |  | 2025-04-01 |  |  | 0 | 2 | 0 | 90032308 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10479740 | LUBRICANT PENETRATING |  |  |  | 0010 | KGP 2025 Rotating Consumables | NCNF | KGP 2025 Rotating Consumables |  |  | 90032308_0020 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000292874 | S002 | 30 | 30 | 5300022062 | 20 |  |  | 0 | 50 | CAN | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2025-03-05 | 299465 | 0 | 0 |  | 1020 | 3 |  |  | 5 | Low | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0100 | 0120 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10480513 | WIRE,RET;NP 1697M73P02 | 1 | EA | 0 | 0 | 2 | 0 |  | 16.12 - ETA 16.04.25 PO 4500020584 ex BH FCA | Supply for Order 200147548, Item 12 cannot be changed 90025036 item 100 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 12 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Swivel Nut W |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10480513 | WIRE,RET;NP 1697M73P02 | 2024-10-16 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 | Ready for Release | 90025036_0100 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 12 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0100 | 0020 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10480513 | WIRE,RET;NP 1697M73P02 | 1 | EA | 0 | 0 | 2 | 0 |  | 18.12 - ETA 16.04.25 PO 4500020584 ex BH | Supply for Order 200147550, Item 17 cannot be changed 90025043 item 150 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 17 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Swivel Nut W |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10480513 | WIRE,RET;NP 1697M73P02 | 2024-10-17 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 | Ready for Release | 90025043_0150 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 17 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0100 | 0020 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10480513 | WIRE,RET;NP 1697M73P02 | 1 | EA | 0 | 0 | 2 | 0 |  | 16.12 - ETA 16.04.25 PO 4500020584 ex BH FCA | Supply for Order 200147552, Item 17 cannot be changed 90025045 item 160 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 17 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Swivel Nut W |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10480513 | WIRE,RET;NP 1697M73P02 | 2024-10-17 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 |  | 90025045_0160 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 17 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0460 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Orchestrated PR Item has been deleted | 10484516 | VALVE GATE | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 600001678, Item 44 cannot be changed 90028314 item 10 already exists | PR approved; PO not issued | SP97 | Direct Multi-base | 266 | AA02 | 5300004588 | 30 |  | 14 | 1000022386 | 44 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024966 | 05 | Preparation | 0000084596 | 44 | 0 | EA | 101000000111822 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  |  | 1001 | 2024-01-02 | PRPO-1000022386_00044 | 0 | 210 | 205 | 210 | 2025-08-04 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-09-27 | 2025-08-06 | 2025-09-22 |  |  | 2025-09-29 | 0 |  | 2025-02-24 |  | 2025-03-01 | Critical |  | 0 | 2 | 2 | 90024966 | 0 | 0 |  | 1 | 1 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10484516 | VALVE GATE | 2024-11-04 | W |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify |  |  | 90024966_0030 |  |  | ST5 |  | A1 | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-11-04 | 20 |  | 2025-08-06 | 44 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000084000 | S002 | 30 | 30 | 5300004588 | 30 |  | 5300017305 | 10 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84596 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDENA1 | Released | 2025-02-11 | 2025-04-01 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0040 | 0010 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10484767 | BOOK,REF;SUTTON FASTENERBLACKBOOK | 1 | EA | 0 | 0 | 0 | 0 |  | 07.03 - PR 2000283153 RFQ | Supply for Order 500004676, Item 23 cannot be changed 90032305 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032305 | 07 | Execution | 0000278102 | 23 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-12 | ODST-0090032305_0010 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | Sim/Tim |  | 0 | 2 | 0 | 90032305 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10484767 | BOOK,REF;SUTTON FASTENERBLACKBOOK | 2025-03-03 | W |  | 0040 | BLACKWOODS Consumables | NCNF | BLACKWOODS Consumables |  |  | 90032305_0010 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 23 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 220 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3070 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10485078 | BEARING,ALCATEL DRV;THOMASSEN 3030126700 | 2 | EA | 6 | 0 | 0 | 0 |  | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 436 cannot be changed 90028419 item 3070 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 436 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10485078 | BEARING,ALCATEL DRV;THOMASSEN 3030126700 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_3070 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 436 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10485079 | BEARING,ALCATEL DRV;THOMASSEN 3030126800 | 2 | EA | 7 | 0 | 0 | 0 |  | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 437 cannot be changed 90028419 item 3080 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 437 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10485079 | BEARING,ALCATEL DRV;THOMASSEN 3030126800 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_3080 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 437 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3110 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0070 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.12.2024) | 10486065 | CABLE ASY,4570MM,BENTLY 13053915 | 2 | ASY | 5 | 0 | 0 | 2 | ASY | 03.12 - SOH @ AA02 | Supply for Order 200063883, Item 32 cannot be changed 90028271 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90028271 | 05 | Preparation | 0000098185 | 32 | 0 | ASY | 102000000029956 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-08-13 | ODST-0090028271_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | XE503/4 |  | 0 | 2 | 0 | 90028271 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486065 | CABLE ASY,4570MM,BENTLY 13053915 | 2024-12-02 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90028271_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 32 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 270 |  |  | 0 | 2 | ASY | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0120 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10486195 | FITTING,CAL,1/4",ELBOW 90DEG,BLEED VV | 2 | ASY | 82 | 7 | 21 | 2 | ASY | 19.02 - At KGP | Supply for Order 100039740, Item 10 cannot be changed 9026897 item 90 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180122888 | 9026897 | 05 | Preparation | 0000138264 | 10 | 0 | ASY | 102000000027975 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391270_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056491 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900230032_2025_0007 | 2025-03-01 | 344PT501 | 5000391270_2025_0004 | 0 | 2 | 0 | 90024951 | 2 | 0 | 180122920/180122888 | 2 | 0 | 0 | X | L | 4900230032 | 2025 |  | 5000391270 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486195 | FITTING,CAL,1/4",ELBOW 90DEG,BLEED VV | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026897_0090 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 10 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 90 |  |  | 0 | 2 | ASY | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2024-03-01 | 2025-05-31 | 2025-06-01 | QMI | 100047965 | 0010 | 0060 | 100047965 | MOC-141289 Transmitter Replace 144FT84 | AA53.144FT84 | METER,DP FLOW,1V4450 OUTLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10486195 | FITTING,CAL,1/4",ELBOW 90DEG,BLEED VV | 1 | ASY | 82 | 7 | 21 | 1 | ASY | 19.02 - At KGP | Supply for Order 100047965, Item 6 cannot be changed 180009111 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300001827 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180009111 | 90001493 | 05 | Preparation | 0000146486 | 6 | 0 | ASY |  |  | 102000000002681 | 01-Road |  | 3-In Transit |  | WorkPackLink | QMP08CAGE | KCM-LNG | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000030950_2024 | 0 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2025-05-31 |  |  | 2025-03-01 |  |  | 100000002887 | 1020 | 2024-12-30 | 1 |  | 2024-03-06 | 4900035070_2024_0011 | 2024-03-04 | 144FT84 | 5000030950_2024_0005 | 0 | 2 | 0 | 90001493 | 1 | 0 | 180009111 | 2 | 0 | 0 | X | L | 4900035070 | 2024 |  | 5000030950 | 2024 | 0 |  | 2024-03-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486195 | FITTING,CAL,1/4",ELBOW 90DEG,BLEED VV | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Engineering Query/Management of Change | 90001493_0060 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 6 |  | 0 | 4900193788_2024 | 25SDLN1 | MJ | 1000000809 | AU1072 | 1000145855 | S002 | 30 | 30 | 5300001827 | 60 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2024-03-01 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146486 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-06-01 | 2025-05-31 | 2025-05-31 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100042804 | 0001 | 0030 | 100042804 | Replace Indication Pilot Lamps GT4008CO2 | AA53.GT4008CO2 | SYSTEM,GT4008 CO2 FIRE SUPPRESSION | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(24.06.2024) | 10486265 | LAMP,IND;EX,24V,GRN,CORTEM M04573V24 | 10 | EA | 10 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA01 | Supply for Order 100042804, Item 6 cannot be changed 90024987 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300011994 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024987 | 05 | Preparation | 0000141258 | 6 | 0 | EA | 101000000141991 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-06-24 | ODST-0090024987_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-10-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024987 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486265 | LAMP,IND;EX,24V,GRN,CORTEM M04573V24 | 2024-06-24 | W |  | 0001 | Materials Assurance | INT | Materials Assurance |  | Order Requires Replanning | 90024987_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000140640 | S002 | 30 | 30 | 5300011994 | 30 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141258 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100042804 | 0001 | 0020 | 100042804 | Replace Indication Pilot Lamps GT4008CO2 | AA53.GT4008CO2 | SYSTEM,GT4008 CO2 FIRE SUPPRESSION | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(24.06.2024) | 10486266 | LAMP,INDICATOR,RED,EX,CORTEM M04573R24 | 10 | EA | 10 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA01 | Supply for Order 100042804, Item 5 cannot be changed 90024987 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300011994 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024987 | 05 | Preparation | 0000141258 | 5 | 0 | EA | 101000000141984 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-06-24 | ODST-0090024987_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-10-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024987 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486266 | LAMP,INDICATOR,RED,EX,CORTEM M04573R24 | 2024-06-24 | W |  | 0001 | Materials Assurance | INT | Materials Assurance |  | Order Requires Replanning | 90024987_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000140640 | S002 | 30 | 30 | 5300011994 | 20 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141258 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-02-07 | 2025-02-17 | 2025-02-13 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0070 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.02.2025) | 10486415 | CLIP;CDUIT,40-44.5MM,HDG,CADDY 333CR423 | 50 | EA | 0 | 0 | 0 | 0 |  | 17.02 - PR 2000270167 RFQ | Supply for Order 600001473, Item 8 cannot be changed 90030804 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020972 | 70 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030804 | 05 | Preparation | 0000084391 | 8 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030804_0020 | 0 | 1 | 0 | 0 |  | 2025-02-15 | AA53 | 2025-05-08 |  |  | 2025-02-18 |  |  |  |  | 2025-12-15 | 0 |  | 2025-02-13 |  | 2025-02-18 | 4V1302 |  | 0 | 2 | 0 | 90030804 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-13 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486415 | CLIP;CDUIT,40-44.5MM,HDG,CADDY 333CR423 | 2025-02-13 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90030804_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083795 | S002 | 30 | 30 | 5300020972 | 70 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-02-13 |  | Engineering Query/Management of Change |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84391 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
1 | 25SDFLR | Released | 2024-11-08 | 2025-04-30 |  | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0030 | 0030 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | WO item has not been released yet | 10486597 | FLANGE,BLIND;50MM,CL150,RF,SS | 4 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000084731 | 6 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2024-08-30 | 0 |  |  |  |  | 37FQI40/41 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486597 | FLANGE,BLIND;50MM,CL150,RF,SS |  |  |  | 0030 | Provision of Flow Computers (MOC-119247) | ESRV | Provision of Flow Computers (MOC-119247) | [5 empty] | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDFLR | MJ |  |  | 1000084145 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0500 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10486599 | FLANGE,BLIND,100MM,CL150,RF,SS | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 50 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486599 | FLANGE,BLIND,100MM,CL150,RF,SS |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10490887 | FABRIC,COATED,BELLOWS,270MM X 12M | 5 | EA | 5 | 0 | 0 | 5 | EA | 13.02 - SOH @ AA02 | Supply for Order 200091513, Item 555 cannot be changed 90028419 item 4010 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4040 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 555 | 0 | EA | 101000000143385 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10490887 | FABRIC,COATED,BELLOWS,270MM X 12M | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_4010 |  |  | DG1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 555 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4040 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2500 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10490889 | FABRIC,COATED,BELLOWS,240MM X 9M | 5 | EA | 5 | 0 | 0 | 5 | EA | 13.02 - SOH @ AA02 | Supply for Order 200091513, Item 554 cannot be changed 90028419 item 4000 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4030 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 554 | 0 | EA | 101000000143386 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4000 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10490889 | FABRIC,COATED,BELLOWS,240MM X 9M | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_4000 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 554 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4030 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0020 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.01.2025) | 10490892 | VALVE,SW;AL,FISHER 167D2594180852 | 1 | EA | 0 | 0 | 0 | 0 |  | 03.02 - ETA 27.06.25 PO 4500044547 SCORE CPT no show stopper | Supply for Order 100085072, Item 4 cannot be changed 90029953 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029953 | 05 | Preparation | 0000267773 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029953_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10490892 | VALVE,SW;AL,FISHER 167D2594180852 | 2025-01-29 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029953_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 | 30 | 30 | 5300019757 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-12 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | VALVE | 100032671 | 0080 | 0040 | 100032671 | CV-OH 1" 300# 118TCV503 | AA53.118TCV503 | VALVE,K1820E1 S/OIL COOLER BYPASS TEMP | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | 23.01- PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131163 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-02 | 0 |  |  |  |  | 100032671 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0080 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130513 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | VALVE | 100032672 | 0020 | 0060 | 100032672 | CV-OH 1" 300# 118LCV505 | AA53.118LCV505 | VALVE,S/OIL O/H TK 1K1820V1 LVL CTRL | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131164 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 118LCV505 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130514 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2025-01-07 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | VALVE | 100032673 | 0020 | 0020 | 100032673 | CV-OH 1" 300# 118LCV508 | AA53.118LCV508 | VALVE,S/OIL DRN POT K1820V4A LOCAL LVL | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131165 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-02 | 0 |  |  |  |  | 100032673 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130515 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | VALVE | 100032674 | 0020 | 0060 | 100032674 | CV-OH 1" 300# 118LCV510 | AA53.118LCV510 | VALVE,S/OIL DRN POT K1820V4B LOCAL LVL | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131166 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032674 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130516 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-16 | VALVE | 100032676 | 0010 | 0110 | 100032676 | CV-OH 2" 300# 118PCV507 | AA53.118PCV507 | VALVE,1K1820E1 L/O PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 16 | EA | 53 | 0 | 0 | 0 |  | 19.01 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131168 | 11 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130518 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-17 | VALVE | 100032678 | 0020 | 0120 | 100032678 | CV-OH 1" 300# 118PDCV506 | AA53.118PDCV506 | VALVE,1K1820E1 S/OIL PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | 15.01 - 16 SOH @ AA02, 3 weeks LeadTime from Tristar, qty required 16 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131170 | 12 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032678 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130520 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDGT9 | Released | 2024-05-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100033225 | 0020 | 0020 | 100033225 | CV-RE 1" 300# 960UZ652 | AA53.960UZ652 | VALVE,GT4009V6 GAS TURB CO2 EXT DISCH | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000131737 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Punchlist & Closeout WP100033225MET001 | ENON | Punchlist & Closeout WP100033225MET001 | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000131147 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2024-10-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Partially confirmed/Job In Process/Material committed/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0020 | 0060 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132018 | 9 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033564 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131400 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0020 | 0060 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132019 | 9 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033565 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131501 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-01 | VALVE | 100034634 | 0030 | 0030 | 100034634 | OPSD 1" 600# unblock bypass 113LCV09 | AA53.113LICA09 | LOOP,LEVEL 1V1301 REGEN GAS WTR KO DRUM | AA01 | 30 | No Issue identified | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 8 | EA | 15.01 - SOH @ AA01 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300000146 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028266 | 05 | Preparation | 0000133166 | 3 | 0 | EA | 102000000032021 | 101000000146108 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028266_0010 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2024-11-20 | 0 |  | 2025-03-26 |  | 2025-03-31 | 100034634 |  | 0 | 2 | 0 | 90028266 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0030 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve |  | Opportune Shutdown | 90028266_0010 |  |  | LN1 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000132536 | S002 | 30 | 30 | 5300000146 | 20 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-03-26 |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133166 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Part printed/Material shortage | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-05-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100047394 | 0030 | 0080 | 100047394 | CV-OH 1" 600# 124PCV54 | AA53.124PCV54 | VALVE,CONT SEAL OIL BACK PRESS 1K2420 | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000145926 | 9 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2018-10-31 | 0 |  |  |  |  | 100047394 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0030 | Remove Valve 124PCV54 & Fit Blinds | INT | Remove Valve 124PCV54 & Fit Blinds | 5 |  |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000145296 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2024-05-23 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
1 | 25SDLN1 | Released | 2024-10-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | VALVE | 100078477 | 0020 | 0010 | 100078477 | CV-OH 1" 600# 113LCV09 | AA53.113LCV09 | VALVE,1V1301 REGEN GAS WTR KO DRUM | AA01 | 20 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000241492 | 1 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-16 | 0 |  |  |  |  | 100078477 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000238214 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-05-31 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-06 | VALVE | 100079171 | 0020 | 0010 | 100079171 | CV-OH 1" 600# 124PCV52 | AA53.124PCV52 | VALVE,CTRL PRESS BUFF GAS 1K2420 | AA01 | 255 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000244737 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000241416 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2025-01-07 | 2025-03-01 |  | 2025-03-01 | 2025-04-29 | VALVE | 100079184 | 0020 | 0020 | 100079184 | CV-OH 1" 600# 124LCV26 | AA53.124LCV26 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000244787 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000241339 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2025-01-07 | 2025-03-01 |  | 2025-03-01 | 2025-04-30 | VALVE | 100079185 | 0020 | 0020 | 100079185 | CV-OH 1" 600# 124LCV27 | AA53.124LCV27 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000244788 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000241340 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-30 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100079244 | 0010 | 0040 | 100079244 | CV-OH 1' 600# 124LCV23 | AA53.124LCV23 | VALVE,CTRL LEVEL S/O FILTER OUT 1K2420 | AA01 | 255 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000244777 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000241462 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDGT9 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0170 | 0020 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000277133 | 10 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-12-18 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0170 | Replace Spool (Bolt up scope) | INT | Replace Spool (Bolt up scope) |  | Management of Change |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000271703 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDGT9 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100087351 | 0020 | 0010 | 100087351 | CV Reverse 1" 300# Act BAV - 960UZ653 | AA53.960UZ653 | VALVE,GT4009V6 GEARBOX CO2 INIT DISCH | AA01 | 255 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000277149 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-11-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove & Replace Valve/Correct Direction | INT | Remove & Replace Valve/Correct Direction | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000271668 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | WORK | 200055989 | 0020 | 0040 | 200055989 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.118RV13 | PSV,1V1805 ON 2" LINE 1W41534 | AA01 | 10 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000090304 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200055989 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV |  | Ready for Release |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000089708 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | WORK | 200059456 | 0030 | 0050 | 200059456 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.520RV02 | PSV,5P20040 FROM 5K2001 | AA01 | 10 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000093805 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0030 | Remove / Install PSV | INT | Remove / Install PSV |  | Ready for Release |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000093175 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  | 2025-01-15 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed/Partially confirmed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0090 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 45 | EA | 53 | 0 | 0 | 37 | EA | 18.02 - SOH @ AA02 | Supply for Order 200073951, Item 9 cannot be changed 90028585 item 90 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 9 | 0 | EA | 102000000033657 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 45 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0090 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 90 |  |  | 0 | 45 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0090 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 45 | EA | 53 | 0 | 0 | 8 | EA | 18.02 - SOH @ AA02 | Supply for Order 200073951, Item 9 cannot be changed 90028585 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 9 | 0 | EA | 102000000031896 | 101000000139968 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 45 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0090 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 90 |  |  | 0 | 45 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200088517 | 0100 | 0020 | 200088517 | 8Y P01 INT INSP PRESS VESSEL 5V2004 | AA53.5V2004 | VE,FUEL GAS KNOCK OUT DRUM | AA01 | 10 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000126826 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0100 | Re-instate Vessel head / Spools | INT | Re-instate Vessel head / Spools | [5 empty] | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000126176 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200088517 | 0100 | 0040 | 200088517 | 8Y P01 INT INSP PRESS VESSEL 5V2004 | AA53.5V2004 | VE,FUEL GAS KNOCK OUT DRUM | AA01 | 10 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 8 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000126826 | 5 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0100 | Re-instate Vessel head / Spools | INT | Re-instate Vessel head / Spools | [5 empty] | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000126176 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146436 | 0020 | 0060 | 200146436 | 1Y Cond Prod Pump Service - 5P2002B | AA53.5P2002B | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234313 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146436 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231369 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146437 | 0020 | 0060 | 200146437 | 1Y Cond Prod Pump Service - 5P2002A | AA53.5P2002A | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234314 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146437 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231370 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146438 | 0020 | 0060 | 200146438 | 1Y Cond Heater Pump Service - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234315 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146438 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 | Ready for Release |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231371 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146439 | 0020 | 0060 | 200146439 | 1Y Cond Heater Pump Service - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234316 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146439 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231372 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2025-01-14 | 2025-02-27 |  | 2025-02-25 | 2025-03-13 | MECH | 200147078 | 0040 | 0030 | 200147078 | MOC-104398 4Y INSP INT EXCH 1K2420E4 | AA53.1K2420E4 | EXCH,HEAT SEAL OIL COOLER 1K2420 | AA01 | 10 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 40 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235349 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-02-27 |  |  | 2025-02-27 |  |  |  |  | 2025-09-16 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0040 | Remove Bonnet / Spools & Install Blinds | INT | Remove Bonnet / Spools & Install Blinds | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000232392 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-13 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2025-01-14 | 2025-02-28 |  | 2025-02-28 | 2025-03-02 | MECH | 200147112 | 0030 | 0030 | 200147112 | 16Y VE/SH INSP RVI 1K2420E1 | AA53.1K2420E1 | TANK,DEGASSING FOR SEAL OIL ON 1K2420 | AA01 | 10 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235383 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-02-28 |  |  | 2025-02-28 |  |  |  |  | 2025-07-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0030 | Remove Heater for Vessel Inspection | INT | Remove Heater for Vessel Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000232426 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0090 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | WO item has not been released yet | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 12 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235400 | 10 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232443 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-03-05 | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0030 | 0010 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | No issue identified | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" | 4 | EA | 53 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004588 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032272 | 05 | Preparation | 0000084596 | 47 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090032272_0010 | 0 | 9 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-10 |  |  |  |  | 2025-09-29 | 0 |  | 2025-03-05 |  | 2025-03-10 |  |  | 0 | 2 | 0 | 90032272 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | BLT STUD:90mm,CSLT,BLK,2,0.625" |  |  |  | 0030 | Fabricate spool1 as per:L2000.DM0010.001 | INT | Fabricate spool1 as per:L2000.DM0010.001 |  |  | 90032272_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 20 |  |  | 47 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000084000 | S002 | 30 | 30 | 5300004588 | 50 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-03-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84596 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100032677 | 0020 | 0070 | 100032677 | CV-OH 3" 300# 118TCV501 | AA53.118TCV501 | VALVE,1K1820E1 L/O COOL BYPASS TEMP CTRL | AA01 | 20 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 16 | EA | 24 | 0 | 0 | 0 |  | 15.01 - PR Never Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131169 | 7 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032677 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130519 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDDG1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-04-28 | VALVE | 100043452 | 0010 | 0030 | 100043452 | MV-IS 124MOV4 drain valve | AA53.124MOV04 | VALVE,MOV,TRANSMISSION GAS TO U2700 | AA01 | 20 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 4 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141984 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-25 | 0 |  |  |  |  | 100043452 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0010 | Repair Leaking Drain Point | INT | Repair Leaking Drain Point | 3 |  |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000141334 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100045781 | 0030 | 0010 | 100045781 | Replace Flange Studs - 1E180769 | AA53.1E1807069 | EXCH,HEAT DEBUTANISER CONDEN FRAC1 | AA01 | 30 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 8 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000144253 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2019-11-03 | 0 |  |  |  |  | 100045781 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0030 | Hot bolt flange using clamps | INT | Hot bolt flange using clamps | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000143683 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0140 | 0030 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 16 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000243763 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-12 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0140 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000240421 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0140 | 0010 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 32 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000243763 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-12 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0140 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000240421 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0160 | 0030 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 16 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000243730 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-12 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0160 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000240357 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0160 | 0010 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 32 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000243730 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-12 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0160 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000240357 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | VALVE | 100079243 | 0010 | 0020 | 100079243 | MV-RE 1.5" 300# 124GLV1110 | AA53.124LCV26 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.10.2024) | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 8 | EA | 24 | 0 | 0 | 8 | EA | 27.02 - SOH @ AA02 | Supply for Order 100079243, Item 2 cannot be changed 90025024 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016132 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025024 | 05 | Preparation | 0000244776 | 2 | 0 | EA | 102000000033080 |  | 102000000034100 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-07 | ODST-0090025024_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079243 |  | 0 | 2 | 0 | 90025024 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 2024-10-07 | W |  | 0010 | Replace Passing Bypass Valve 124GAV1305 | INT | Replace Passing Bypass Valve 124GAV1305 |  |  | 90025024_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241461 | S002 | 30 | 30 | 5300016132 | 20 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244776 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 |  | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0130 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 8 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000246943 | 13 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  |  |  |  | 100079771 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000243501 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-11-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | VALVE | 100087379 | 0080 | 0010 | 100087379 | MV-OH 4" 300# 960BAV2400 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 255 | No issue identified | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 16 | EA | 24 | 0 | 0 | 8 | EA | 27.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018141 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028278 | 05 | Preparation | 0000277207 | 3 | 0 | EA | 102000000033079 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-11-20 | ODST-0090028278_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-11-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100087379 |  | 0 | 2 | 0 | 90028278 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0080 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve |  |  | 90028278_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271762 | S002 | 30 | 30 | 5300018141 | 30 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277207 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-11-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | VALVE | 100087379 | 0080 | 0010 | 100087379 | MV-OH 4" 300# 960BAV2400 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 255 | No issue identified | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 16 | EA | 24 | 0 | 0 | 8 | EA | 27.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018141 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028278 | 05 | Preparation | 0000277207 | 3 | 0 | EA | 102000000030456 | 101000000134324 | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-11-20 | ODST-0090028278_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-11-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100087379 |  | 0 | 2 | 0 | 90028278 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0080 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve |  |  | 90028278_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271762 | S002 | 30 | 30 | 5300018141 | 30 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277207 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0090 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 8 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117838 | 11 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200082188 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000117251 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-10-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200147137 | 0020 | 0010 | 200147137 | 10Y MV-RE 3" 300# 141CHV2043 | AA53.141CHV2043 | VALVE,CHECK 1E407 RE INJ VAPOURISER | AA01 | 10 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 16 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235409 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  |  |  |  | 200147137 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0020 | Remove & Replace NRV | INT | Remove & Replace NRV | 5 | Ready for Release |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232452 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-08-15 | 2025-03-01 |  | 2025-02-19 | 2025-03-03 | MECH | 600003215 | 0020 | 0070 | 600003215 | MOC-117109 1E1303 Exchanger Replacement | AA53.1E1303 | EXCH,HEAT AIR COOL REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK | 16 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000254308 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491120 | STUDBOLT;0.750" X 110MM,L7,BLK |  |  |  | 0020 | Remove blanks For Inspection Access | INT | Remove blanks For Inspection Access |  | Management of Change |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000250524 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W35069 | 2024-08-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-02-19 | 2025-02-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200088517 | 0100 | 0060 | 200088517 | 8Y P01 INT INSP PRESS VESSEL 5V2004 | AA53.5V2004 | VE,FUEL GAS KNOCK OUT DRUM | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK | 16 | EA | 16 | 0 | 0 | 8 | EA | 24.02 - SOH @ AA02 | Supply for Order 200088517, Item 7 cannot be changed 90028592 item 10 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020030 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028592 | 05 | Preparation | 0000126826 | 7 | 0 | EA | 101000000147166 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028592_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200088517 |  | 0 | 2 | 0 | 90028592 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK | 2025-01-14 | W |  | 0100 | Re-instate Vessel head / Spools | INT | Re-instate Vessel head / Spools |  |  | 90028592_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126176 | S002 | 30 | 30 | 5300020030 | 10 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126826 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200088517 | 0100 | 0060 | 200088517 | 8Y P01 INT INSP PRESS VESSEL 5V2004 | AA53.5V2004 | VE,FUEL GAS KNOCK OUT DRUM | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK | 16 | EA | 16 | 0 | 0 | 8 | EA | 24.02 - SOH @ AA02 | Supply for Order 200088517, Item 7 cannot be changed 90028592 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020030 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028592 | 05 | Preparation | 0000126826 | 7 | 0 | EA | 101000000147171 |  | 101000000147006 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 16 |  | 2025-02-22 | Y | 1001 | 2025-01-14 | ODST-0090028592_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200088517 |  | 0 | 2 | 0 | 90028592 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK | 2025-01-14 | W |  | 0100 | Re-instate Vessel head / Spools | INT | Re-instate Vessel head / Spools |  |  | 90028592_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ | 20005043 | AU1072 | 1000126176 | S002 | 30 | 30 | 5300020030 | 10 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-20 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126826 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146438 | 0020 | 0070 | 200146438 | 1Y Cond Heater Pump Service - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK | 16 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234315 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146438 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 | Ready for Release |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231371 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146439 | 0020 | 0070 | 200146439 | 1Y Cond Heater Pump Service - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK | 16 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234316 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146439 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231372 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-11-12 | 2025-03-01 |  | 2025-03-01 | 2025-06-09 | VALVE | 100034564 | 0020 | 0040 | 100034564 | CV-OH 12" 600# 111UCV032 | AA53.111UCV032 | VALVE,CTRL REFLUX C1101 | AA01 | 10 | WO item has not been released yet | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK | 40 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000133016 | 5 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2027-10-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000132426 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-06-09 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDLN1 | Released | 2024-11-19 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | VALVE | 600003361 | 0020 | 0020 | 600003361 | MOC-120323 - CV-RE 10" 600# 141FCV01 | AA53.141FCV01 | VALVE,H/W FLOW TO 1E4101 CV | AA01 | 20 | WO item has not been released yet | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK | 32 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000266685 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-23 | 0 |  |  |  |  | 600003361 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK |  |  |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000261577 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-09-24 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Material shortage/Printed | AM06 | Capital
1 | 25SDLN1 | Released | 2024-11-19 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | VALVE | 600003400 | 0020 | 0030 | 600003400 | MOC-120323 - CV-RE 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV | AA01 | 255 | WO item has not been released yet | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK | 32 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000266702 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-09-14 | 0 |  |  |  |  | 600003400 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK |  |  |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000261698 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-09-24 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 6 | Very Low | RC00018003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Material shortage/Printed | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0020 | 0040 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK | 12 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132018 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033564 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131400 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0020 | 0040 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK | 12 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132019 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033565 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131501 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | WORK | 200059456 | 0030 | 0040 | 200059456 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.520RV02 | PSV,5P20040 FROM 5K2001 | AA01 | 10 | WO item has not been released yet | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK | 8 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000093805 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK |  |  |  | 0030 | Remove / Install PSV | INT | Remove / Install PSV |  | Ready for Release |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000093175 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  | 2025-01-15 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed/Partially confirmed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0050 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | WO item has not been released yet | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK | 8 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117838 | 6 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200082188 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK |  |  |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000117251 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0100 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | WO item has not been released yet | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK | 8 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235400 | 11 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK |  |  |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232443 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0020 | 0030 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | WO item has not been released yet | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK | 24 | EA | 4 | 0 | 0 | 0 |  | 23.01 - PR Never line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084710 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK |  |  |  | 0020 | Install 118UCV112 | INT | Install 118UCV112 | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000084094 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0020 | 0050 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK | 12 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132018 | 8 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033564 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131400 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0020 | 0050 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK | 12 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132019 | 8 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033565 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131501 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDDG1 | Released | 2025-02-11 | 2025-03-12 |  | 2025-03-01 | 2025-06-06 | MECH | 100086858 | 0130 | 0020 | 100086858 | 1E2406 externally corroded tube ends | AA53.1E2406 | EXCH,HEAT AFTER COOLER FOR COMPR | AA01 | 10 | WO item has not been released yet | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK | 290 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000275554 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 290 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-12 |  |  | 2025-03-12 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 100086858 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK |  |  |  | 0130 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000270168 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-06 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-06-06 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2025-02-11 | 2025-05-09 |  | 2025-03-01 | 2025-05-11 | MECH | 100086859 | 0130 | 0020 | 100086859 | 1E2405 externally corroded tube ends | AA53.1E2405 | EXCH,HEAT AFTER COOLER FOR COMPR | AA01 | 10 | WO item has not been released yet | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK | 128 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000275555 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 128 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-09 |  |  | 2025-05-09 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 100086859 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK |  |  |  | 0130 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000270169 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-06 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-11 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0100 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK | 15 | EA | 15 | 0 | 0 | 15 | EA | 13.02 - SOH @ AA02 | Supply for Order 200073951, Item 10 cannot be changed 90028585 item 100 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 10 | 0 | EA | 101000000144544 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 15 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0100 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 100 |  |  | 0 | 15 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0070 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | WO item has not been released yet | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK | 8 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117838 | 9 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200082188 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491148 | STUDBOLT;0.875" X 150MM,L7,BLK |  |  |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000117251 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0060 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | WO item has not been released yet | 10491149 | STUDBOLT;1.000" X 170MM,L7,BLK | 14 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139208 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 14 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-08-01 | 0 |  |  |  |  | 100040704 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491149 | STUDBOLT;1.000" X 170MM,L7,BLK |  |  |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000138559 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146436 | 0020 | 0070 | 200146436 | 1Y Cond Prod Pump Service - 5P2002B | AA53.5P2002B | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | WO item has not been released yet | 10491149 | STUDBOLT;1.000" X 170MM,L7,BLK | 16 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234313 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146436 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491149 | STUDBOLT;1.000" X 170MM,L7,BLK |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231369 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146437 | 0020 | 0070 | 200146437 | 1Y Cond Prod Pump Service - 5P2002A | AA53.5P2002A | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | WO item has not been released yet | 10491149 | STUDBOLT;1.000" X 170MM,L7,BLK | 16 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234314 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146437 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491149 | STUDBOLT;1.000" X 170MM,L7,BLK |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231370 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0200 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10492604 | HOLDER:DOCUMENT,225X355mm,PVC,YEL | 4 | EA | 0 | 0 | 0 | 0 |  | 21.02 - ETA 04.04.25 PO 4500046416 HARTAC CPT | Supply for Order 500004676, Item 20 cannot be changed 90031855 item 190 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 20 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0190 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10492604 | HOLDER:DOCUMENT,225X355mm,PVC,YEL | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0190 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 20 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 200 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 3 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDDG1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | VALVE | 100043452 | 0010 | 0010 | 100043452 | MV-IS 124MOV4 drain valve | AA53.124MOV04 | VALVE,MOV,TRANSMISSION GAS TO U2700 | AA01 | 20 | No issue identified | 10492893 | PACKING,EMISSION;KLINGER 191M396C030 | 1 | PAC | 2 | 1 | 0 | 1 | PAC | 02.10 - SOH @ AA02 |  | Material picked; currently at SW3R01H02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300001316 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAC |  |  |  |  | 90024943 | 05 | Preparation | 0000141984 | 1 | 0 | PAC |  |  | 102000000027728 |  |  |  |  | WorkPackLink | SW3R01H02B | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024943_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-25 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124MOV04 |  | 0 | 2 | 0 | 90024943 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10492893 | PACKING,EMISSION;KLINGER 191M396C030 |  |  |  | 0010 | Repair Leaking Drain Point | INT | Repair Leaking Drain Point | 3 |  | 90024943_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000141334 | S002 | 30 | 30 | 5300001316 | 10 |  |  | 0 | 1 | PAC | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141984 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0090 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10497788 | SCREW;SELF TAP,4.2X13MM,PAN,PHIL,SS | 200 | EA | 5044 | 2400 | 4253 | 200 | EA | Workpacked at KGP | Supply for Order 200089373, Item 9 cannot be changed 180091768 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180091768 | 9019016 | 07 | Execution | 0000127667 | 9 | 0 | EA |  |  | 102000000023519 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-KGP-RUNNER-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000275114_2024 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000040386 | 1020 | 2025-12-15 | 200 |  | 2024-11-11 | 4900169565_2024_0009 | 2024-11-10 | Troy Mac | 5000275114_2024_0001 | 0 | 2 | 0 | 90023594 | 200 | 0 | 180091768 | 2 | 0 | 0 | X | L | 4900169565 | 2024 |  | 5000275114 | 2024 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10497788 | SCREW;SELF TAP,4.2X13MM,PAN,PHIL,SS | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9019016_0090 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDFR2 | MJ | 1000004072 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 90 |  |  | 0 | 200 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | INLEC | 100087760 | 0010 | 0060 | 100087760 | Cyl Rod Drop Probes F/Test (4) 5K2001 | AA53.520XT11A | TXDCR,SENSOR PROX CYL 1 ROD DROP 5K2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10498945 | CABLE,EXTN;ARMOURED,4M,BENTLY 330730040> | 4 | EA | 4 | 0 | 0 | 4 | EA | 23.01 - SOH @ AA02 | Supply for Order 100087760, Item 6 cannot be changed 90028435 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018538 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028435 | 05 | Preparation | 0000278368 | 6 | 0 | EA | 101000000135813 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-28 | ODST-0090028435_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5K2001 |  | 0 | 2 | 0 | 90028435 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10498945 | CABLE,EXTN;ARMOURED,4M,BENTLY 330730040> | 2024-11-28 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's |  |  | 90028435_0030 |  |  | ST5 |  | C1 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272777 | S002 | 30 | 30 | 5300018538 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-11-20 | 278368 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0050 | 0060 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10499296 | LABEL;PROD ID,WASTE,BLK-WHT,ACS 50617 | 10 | EA | 885 | 0 | 0 | 10 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 6 cannot be changed 90028583 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 6 | 0 | EA | 102000000034120 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10499296 | LABEL;PROD ID,WASTE,BLK-WHT,ACS 50617 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028583_0060 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 60 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0060 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10499296 | LABEL;PROD ID,WASTE,BLK-WHT,ACS 50617 | 10 | EA | 885 | 0 | 0 | 10 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 17 cannot be changed 90028584 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 17 | 0 | EA | 102000000034029 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10499296 | LABEL;PROD ID,WASTE,BLK-WHT,ACS 50617 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028584_0170 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 170 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-03-27 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 100043910 | 0100 | 0020 | 100043910 | 1KT2420 Turbine- On Condition Materials | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | No Issue identified | 10499329 | NOZZLE;NP SMO1734792 | -1 | ASY | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY |  | DAMAGED |  |  |  | 05 | Preparation | 0000142424 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 | 5400000179 | 10 | 1 | ASY | 1 | 0 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-10-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10499329 | NOZZLE;NP SMO1734792 |  |  |  | 0100 | Refurb Materials | NCNF | Refurb Materials | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 | 4900042792_2024 | 25SD2420 | MJ |  |  | 1000141826 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1740 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | No issue identified | 10499329 | NOZZLE;NP SMO1734792 | -1 | ASY | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY |  | DAMAGED |  |  |  | 05 | Preparation | 0000129822 | 746 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10499329 | NOZZLE;NP SMO1734792 |  |  |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 3320 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.10.2024) | 10499329 | NOZZLE;NP SMO1734792 | 1 | ASY | 1 | 0 | 0 | 0 |  | 30.12 - SOH @ AA02 | Supply for Order 200091513, Item 770 cannot be changed 90028419 item 4900 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4940 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  | REFURB |  |  | 90028419 | 05 | Preparation | 0000129822 | 770 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4900 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10499329 | NOZZLE;NP SMO1734792 | 2024-10-02 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_4900 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 770 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4940 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0920 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | No issue identified | 10499350 | CAP + LINER,PIGNONE MS3002,ARR | -1 | KIT | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | KIT |  | DAMAGED |  |  |  | 05 | Preparation | 0000129822 | 737 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10499350 | CAP + LINER,PIGNONE MS3002,ARR |  |  |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 3300 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.10.2024) | 10499350 | CAP + LINER,PIGNONE MS3002,ARR | 1 | KIT | 1 | 0 | 0 | 1 | KIT | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 768 cannot be changed 90028419 item 4880 already exists | Material picked; currently at SW5R04D01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4920 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  | REFURB |  |  | 90028419 | 05 | Preparation | 0000129822 | 768 | 0 | KIT |  |  | 102000000031201 |  |  |  |  | WorkPackLink | SW5R04D01B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4880 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10499350 | CAP + LINER,PIGNONE MS3002,ARR | 2024-10-02 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_4880 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 768 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4920 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100086264 | 0020 | 0010 | 100086264 | Start Clutch/UV Purge Sol OH (3) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10501915 | SWITCH,LIMIT;15A,250V,EX,H/WELL EXAR800 | 1 | EA | 0 | 1 | 0 | 1 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086264, Item 1 cannot be changed 90025091 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017153 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124193 | 9027127 | 05 | Preparation | 0000272423 | 1 | 0 | EA | 102000000032149 | 102000000029162 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-31 | IDST-0180124193 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 1 |  | 2025-02-11 | 4900234099_2025_0001 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025091 | 0 | 0 | 180124193 | 2 | 0 | 0 | X | L | 4900234099 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10501915 | SWITCH,LIMIT;15A,250V,EX,H/WELL EXAR800 | 2024-10-29 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  |  | 9027127_0020 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267123 | S002 | 30 | 30 | 5300017153 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272423 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2910 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10501915 | SWITCH,LIMIT;15A,250V,EX,H/WELL EXAR800 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 569 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | startclutch |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10501915 | SWITCH,LIMIT;15A,250V,EX,H/WELL EXAR800 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1990 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.02.2025) | 10502354 | ACCUMULATOR,F+Y 973E0515–348A4766-P001++ | 2 | ASY | 2 | 0 | 0 | 2 | ASY | 03.02 - SOH @ AA02 | Supply for Order 200091513, Item 776 cannot be changed 90030042 item 30 already exists | Material picked; currently at 30-03-01-80A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 5010 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90030042 | 05 | Preparation | 0000129822 | 776 | 0 | ASY |  |  | 102000000026325 |  |  |  |  | WorkPackLink | 30-03-01-80A |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090030042_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030042 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10502354 | ACCUMULATOR,F+Y 973E0515–348A4766-P001++ | 2025-02-01 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90030042_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 776 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 5010 |  |  | 0 | 2 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100034776 | 0010 | 0020 | 100034776 | MOC-145870-PV CM G4007V3 Passing Fill Va | AA53.G4007V3 | VE,CO2 LOW PRESSURE,GT4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(31.01.2025) | 10502408 | TEFLON SHEET;1200MMX1000MMX2MM THK | 1 | EA | 1 | 0 | 0 | 0 |  | 31.01 - SOH @ AA02 | Supply for Order 100034776, Item 9 cannot be changed 90030057 item 50 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020137 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030057 | 05 | Preparation | 0000133257 | 9 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-17 | ODST-0090030057_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100034776 |  | 0 | 2 | 0 | 90030057 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10502408 | TEFLON SHEET;1200MMX1000MMX2MM THK | 2025-01-31 | W |  | 0010 | Erect scaffold Access | INT | Erect scaffold Access |  | Engineering Query/Management of Change | 90030057_0050 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000132686 | S002 | 30 | 30 | 5300020137 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0095 | 0010 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10502594 | WATER,DEMINERALISED;1000L IBC | 1 | CON | 0 | 0 | 1 | 1 | CON | 29.01 - At KGP | Supply for Order 200091126, Item 79 cannot be changed 9018163 item 360 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 610 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  | CUTOVER_S4 |  | 180089728 | 9018163 | 05 | Preparation | 0000129360 | 79 | 0 | CON | 102000000022599 |  | 107000000000121 |  |  |  | P07YRDBY35 | WorkPackLink | P07YRDBY35 | AU01-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000268551_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000039150 | 1020 | 2023-04-03 | 1 |  | 2024-11-05 | 4900165332_2024_0001 | 2025-03-01 | DEMIN | 5000268551_2024_0001 | 0 | 2 | 0 | 90023534 | 1 | 0 | 180089728 | 2 | 0 | 0 | X | L | 4900165332 | 2024 |  | 5000268551 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10502594 | WATER,DEMINERALISED;1000L IBC | 2024-05-11 | W |  | 0095 | COOLING WATER | INT | COOLING WATER |  |  | 9018163_0360 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 79 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 610 |  |  | 0 | 1 | CON | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10502717 | SEAL,VV;YOUNG AND FRANKLIN YF7552A023P0> | 4 | EA | 15 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 525 cannot be changed 90028419 item 3800 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 525 | 0 | EA | 102000000030501 | 102000000030476 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3800 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10502717 | SEAL,VV;YOUNG AND FRANKLIN YF7552A023P0> | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3800 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 525 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3830 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0040 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10503269 | FILTER,AIR;NORGREN F22400M1DA | 1 | ASY | 0 | 0 | 0 | 0 |  | 21.02 - ETA 10.04.25 PO 4500045916 IMI AUS CPT | Supply for Order 100085072, Item 6 cannot be changed 90029953 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90029953 | 05 | Preparation | 0000267773 | 6 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029953_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10503269 | FILTER,AIR;NORGREN F22400M1DA | 2025-01-30 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029953_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 | 30 | 30 | 5300019757 | 60 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0370 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10503523 | SOLVENT;DOP,LINE FLUSHING,DRUM 22KG | 4 | DR | 4 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 37 cannot be changed 90032376 item 350 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 37 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0350 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10503523 | SOLVENT;DOP,LINE FLUSHING,DRUM 22KG | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0350 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 37 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 370 |  |  | 0 | 4 | DR | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-02-27 | 2025-03-04 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0110 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10503857 | M/FOLD,DBB;AGCO M25VIS44FHDWOP | 4 | EA | 0 | 0 | 0 | 0 |  | 07.03 - PR 1000031151 | Supply for Order 600001363, Item 18 cannot be changed 90032160 item 10 already exists | PR approved; PO not issued | SP97 | Direct Multi-base | 48 | AA01 | 5300018439 | 40 |  | 7 | 1000031151 | 18 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032160 | 05 | Preparation | 0000084301 | 18 | 0 | [8 empty] | WorkPackLink |  | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-27 | PRPO-1000031151_00018 | 0 | 78 | 57 | 68 | 2025-04-28 | 2025-03-02 | AA53 | 2025-02-27 |  |  | 2025-05-26 | 2025-04-30 | 2025-05-11 |  |  | 2025-07-31 | 0 |  | 2025-03-04 |  | 2025-03-15 |  |  | 0 | 2 | 2 | 90032160 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10503857 | M/FOLD,DBB;AGCO M25VIS44FHDWOP | 2025-03-04 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90032160_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-03-04 | 5 |  | 2025-04-30 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000083685 | S001 | 30 | 30 | 5300018438 | 130 |  | 5300018439 | 40 | 4 | EA | 1001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDLN1 | Released | 2024-10-07 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-03 | VALVE | 100078477 | 0050 | 0050 | 100078477 | CV-OH 1" 600# 113LCV09 | AA53.113LCV09 | VALVE,1V1301 REGEN GAS WTR KO DRUM | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.10.2024) | 10504831 | RING:SEAT,FISHER CONTROLS PTY. LTD.,25A5 | 1 | EA | 1 | 0 | 0 | 1 | EA | 21.01 - SOH @ AA01 | Supply for Order 100078477, Item 7 cannot be changed 90028952 item 20 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 7 | AA02 | 5300016139 | 50 | CPT | 7 | 1000020713 | 7 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500031035 | 30 | 1 | EA | 2025-01-29 |  | /180116541 |  | 90025025 | 05 | Preparation | 0000241492 | 7 | 0 | EA | 101000000137074 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-07 | ODST-0090025025_0050 | 0 | 0 | 0 | 0 | 2025-03-11 | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 | 2025-03-13 | 2025-01-27 |  |  | 2024-10-16 | 0 | 5000367205_2025_0001 | 2025-03-26 |  | 2025-01-21 |  |  | 0 | 2 | 2 | 90025025 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000367205 |  | 0 | 2025 | /018011654 | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10504831 | RING:SEAT,FISHER CONTROLS PTY. LTD.,25A5 | 2024-10-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90025025_0050 |  |  | LN1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-02-24 | 20 |  | 2025-03-13 | 7 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000238214 | S002 | 30 | 30 | 5300016139 | 50 |  | 5300016140 | 20 | 1 | EA | 2001 | AA02 | 2025-03-26 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-05-31 | 241492 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-03-14 | 2025-03-09 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0260 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10505046 | THERMOMETER;IR,EX,FLUKE 568EX | 2 | EA | 0 | 0 | 0 | 0 |  | 10.03 - ETA 31.03.25 PO 4500049092 M&amp;H CPT | Supply for Order 100090053, Item 26 cannot be changed 90032192 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032192 | 05 | Preparation | 0000289018 | 26 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032192_0010 | 0 | 0 | 0 | 0 |  | 2025-03-12 | AA53 | 2025-05-23 |  |  | 2025-03-14 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-09 |  | 2025-03-14 | 3E1405/Ray R |  | 0 | 2 | 0 | 90032192 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-09 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10505046 | THERMOMETER;IR,EX,FLUKE 568EX | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032192_0010 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 26 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 260 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-09 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDTOT1 | Released | 2024-01-02 | 2025-03-01 | 2024-06-04 | 2025-03-01 | 2025-03-01 | INLEC | 100041904 | 0010 | 0010 | 100041904 | MOC-120096 Positioner Replace110PV452 | AA53.110PV452POS | POS,VALVE,PRESS 1PRS RUNDOWN 5 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10506321 | POSITIONER,VV;FISHER DVC6200H1F2A3A4A5C+ | 1 | EA | 8 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100041904, Item 1 cannot be changed 180056689 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300000626 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180056689 | 90011948 | 05 | Preparation | 0000140388 | 1 | 0 | EA | 101000000063662 |  | 107000000000391 |  |  |  | P07 - BENCH | WorkPackLink | P07-WAREHOUSE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000168361_2024 | 0 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000022924 | 1020 | 2025-05-07 | 1 |  | 2024-08-13 | 4900109473_2024_0001 | 2024-06-07 | 110PV452POS | 5000168361_2024_0001 | 0 | 2 | 0 | 90011948 | 1 | 0 | 180056689 | 2 | 0 | 0 | X | L | 4900109473 | 2024 |  | 5000168361 | 2024 | 0 |  | 2024-06-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10506321 | POSITIONER,VV;FISHER DVC6200H1F2A3A4A5C+ | 2024-01-01 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90011948_0010 |  |  | TT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDTOT1 | MJ |  | AU1072 | 1000139759 | S002 | 30 | 30 | 5300000626 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-06-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140388 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0250 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10506579 | INSULATION,ROCKWOOL,RL,2.5 X 1M X 75MM | 20 | ROL | 3 | 0 | 7 | 0 |  | 10.03 - ETA 27.03.25 PO 4500047066 ARMACELL CPT | Supply for Order 500005166, Item 45 cannot be changed 90031501 item 270 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 410 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 45 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0270 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10506579 | INSULATION,ROCKWOOL,RL,2.5 X 1M X 75MM | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0270 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 45 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 410 |  |  | 0 | 20 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-02-20 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0180 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(20.02.2025) | 10506818 | BAR,PODGER,900X20MM | 10 | EA | 0 | 10 | 0 | 6 | EA | DEL: 90031306 | Supply for Order 500005166, Item 53 cannot be changed 90031306 item 10 already exists | Material In-Transit on-01-Road | SP97 | Direct Multi-base | 30 | AA01 | 5300021228 | 40 | CPT | 7 | 1000030354 | 53 | 30000394 | J BLACKWOOD AND SON LTD | 4500047998 | 10 | 10 | EA | 2025-03-14 |  | /180131451 | 180133510 | 90031306 | 05 | Preparation | 0000294187 | 53 | 0 | EA | 101000000150839 |  | 101000000150645 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2025-03-09 | Y | 1001 | 2025-02-13 | IDST-0180133510 | 0 | 41 | 41 | 41 | 2025-03-31 | 2025-03-04 | AA53 | 2025-04-01 |  |  | 2025-04-21 | 2025-04-02 | 2025-04-16 | 100000430263 | 1010 |  | 10 | 5000425182_2025_0001/5000425172_2025_0001 | 2025-03-07 | 4900260614_2025_0001 | 2025-03-04 | TA LAG_VORN |  | 0 | 2 | 2 | 90031306 | 0 | 10 | 180133510 | 2 | 0 | 0 | X | L | 4900260614 | 2025 | 5000425172 |  | 0 | 2025 | /018013145 | 2025-02-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10506818 | BAR,PODGER,900X20MM | 2025-02-20 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031306_0010 | [5 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-21 | 99 | 6000015795 | 2025-04-02 | 0 |  | 0 |  | 25SDENA1 | MJ | 20005473 | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 480 |  | 5300021228 | 40 | 10 | EA | 1001 | AA02 | 2025-02-20 |  |  | 2025-03-07 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-02-20 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0180 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(20.02.2025) | 10506818 | BAR,PODGER,900X20MM | 10 | EA | 0 | 10 | 0 | 4 | EA | DEL: 90031306 | Supply for Order 500005166, Item 53 cannot be changed 90031306 item 10 already exists | Material In-Transit on-01-Road | SP97 | Direct Multi-base | 30 | AA01 | 5300021228 | 40 | CPT | 7 | 1000030354 | 53 | 30000394 | J BLACKWOOD AND SON LTD | 4500047998 | 10 | 10 | EA | 2025-03-14 |  | /180131451 | 180133510 | 90031306 | 05 | Preparation | 0000294187 | 53 | 0 | EA | 101000000150870 |  | 101000000150645 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2025-03-09 | Y | 1001 | 2025-02-13 | IDST-0180133510 | 0 | 41 | 41 | 41 | 2025-03-31 | 2025-03-04 | AA53 | 2025-04-01 |  |  | 2025-04-21 | 2025-04-02 | 2025-04-16 | 100000430263 | 1010 |  | 10 | 5000425182_2025_0001/5000425172_2025_0001 | 2025-03-07 | 4900260614_2025_0001 | 2025-03-04 | TA LAG_VORN |  | 0 | 2 | 2 | 90031306 | 0 | 10 | 180133510 | 2 | 0 | 0 | X | L | 4900260614 | 2025 | 5000425172 |  | 0 | 2025 | /018013145 | 2025-02-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10506818 | BAR,PODGER,900X20MM | 2025-02-20 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031306_0010 | [5 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-21 | 99 | 6000015795 | 2025-04-02 | 0 |  | 0 |  | 25SDENA1 | MJ | 20005473 | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 480 |  | 5300021228 | 40 | 10 | EA | 1001 | AA02 | 2025-02-20 |  |  | 2025-03-07 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0070 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Shipped qty below requirement qty | 10506833 | BIT;SCREWDRIVER,PWR,PH2,0.25" X 63.5MM | 100 | EA | 10 | 0 | 10 | 10 | EA | 24.02 - ETA 20.03.25 PO 4500046941 BLACKWOODS CPT | Supply for Order 500005166, Item 8 cannot be changed 90031023 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132201 | 9028444 | 05 | Preparation | 0000294187 | 8 | 0 | EA |  |  | 102000000033428 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 90 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427540_2025 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 |  |  | 100000060206 | 1020 |  | 10 |  | 2025-03-05 | 4900257474_2025_0003 | 2025-03-11 | TA LAG_VORN | 5000427540_2025_0002 | 0 | 2 | 0 | 90031023 | 10 | 0 | 180132201 | 1 | 0 | 0 | X | L | 4900257474 | 2025 |  | 5000427540 | 2025 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10506833 | BIT;SCREWDRIVER,PWR,PH2,0.25" X 63.5MM | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0070/9028444_0070 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 8 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 80 |  |  | 0 | 100 | EA | 2001 | AA02 | 2025-03-06 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0150 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10507056 | GRIP,HANDLE,PROTECTIVE,16MM | 10 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 14.03.25 PO 4500047444 ATOM CPT | Supply for Order 500005166, Item 17 cannot be changed 90031240 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031240 | 05 | Preparation | 0000294187 | 17 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031240_0010 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 | [5 empty] | 0 |  | 2025-03-06 |  | 2025-03-11 | TA LAG_VORN |  | 0 | 2 | 0 | 90031240 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507056 | GRIP,HANDLE,PROTECTIVE,16MM | 2025-02-19 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031240_0010 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 17 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 150 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0040 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10507117 | KNIFE,SHOE,120MM | 15 | EA | 0 | 0 | 0 | 0 |  | 20.02 - ETA 18.03.25 PO 4500046360 BLACKWOODS CPT | Supply for Order 500005166, Item 5 cannot be changed 90031023 item 40 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031023 | 05 | Preparation | 0000294187 | 5 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 15 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031023_0040 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 | [5 empty] | 0 |  | 2025-03-06 |  | 2025-03-11 | TA LAG_VORN |  | 0 | 2 | 0 | 90031023 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507117 | KNIFE,SHOE,120MM | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0040 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 5 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 50 |  |  | 0 | 15 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0280 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10507299 | SHADECLOTH,KNITTED,1830MM X 50M,UV,GRN | 2 | ROL | 0 | 0 | 45 | 0 |  | 02.12 - SOH @ AA02 | Supply for Order 100087648, Item 29 cannot be changed 90028417 item 270 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 29 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507299 | SHADECLOTH,KNITTED,1830MM X 50M,UV,GRN | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0270 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 29 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 280 |  |  | 0 | 2 | ROL | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0050 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10507299 | SHADECLOTH,KNITTED,1830MM X 50M,UV,GRN | 4 | ROL | 0 | 0 | 45 | 0 |  | 10.03 - DEL: 80019512 | Supply for Order 100090053, Item 5 cannot be changed 90032376 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 5 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0050 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507299 | SHADECLOTH,KNITTED,1830MM X 50M,UV,GRN | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0050 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 50 |  |  | 0 | 4 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0060 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10507299 | SHADECLOTH,KNITTED,1830MM X 50M,UV,GRN | 1 | ROL | 0 | 0 | 45 | 0 |  | 02.12 - SOH @ AA02 | Supply for Order 200089373, Item 6 cannot be changed 90023594 item 60 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90023594 | 07 | Execution | 0000127667 | 6 | 0 | [8 empty] | WorkPackLink |  | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-05 | ODST-0090023594_0060 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  |  |  | 2025-12-15 | 0 |  | 2024-11-05 |  | 2024-11-10 | Troy Mac |  | 0 | 2 | 0 | 90023594 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507299 | SHADECLOTH,KNITTED,1830MM X 50M,UV,GRN | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 90023594_0060 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDFR2 | MJ |  | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 60 |  |  | 0 | 1 | ROL | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-02-07 | 2025-02-28 | 2025-02-23 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0050 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10507669 | VALVE,POPPET;SS316,MIDLAND 2325M21VC2B | 4 | ASY | 8 | 0 | 0 | 4 | ASY | 17.02 - SOH @ AA02 | Supply for Order 600001473, Item 5 cannot be changed 90030760 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020972 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90030760 | 05 | Preparation | 0000084391 | 5 | 0 | ASY | 102000000034076 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030760_0010 | 0 | 0 | 0 | 0 |  | 2025-02-26 | AA53 | 2025-05-08 |  |  | 2025-02-28 |  |  |  |  | 2025-12-15 | 0 |  | 2025-02-23 |  | 2025-02-28 | 4V1302 |  | 0 | 2 | 0 | 90030760 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-23 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507669 | VALVE,POPPET;SS316,MIDLAND 2325M21VC2B | 2025-02-12 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90030760_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083795 | S002 | 30 | 30 | 5300020972 | 50 |  |  | 0 | 4 | ASY | 2001 | AA02 | 2025-02-23 |  | Engineering Query/Management of Change |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84391 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
| 25SDDG1 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-02 | ROTAT | 200089885 | 0080 | 0030 | 200089885 | 2Y 1KT2430 TURB AIR FILTER CHANGEOUT | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10509663 | ELEMENT,FLT;CLYDE APAC FSNP50610610 | 120 | EA | 275 | 62 | 12 | 0 |  | 19.02 - SOH @ AA02 | Supply for Order 200089885, Item 12 cannot be changed 90025008 item 30 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015697 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025008 | 05 | Preparation | 0000128154 | 12 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 120 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025008_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-10 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025008 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10509663 | ELEMENT,FLT;CLYDE APAC FSNP50610610 | 2024-09-23 | W |  | 0080 | Install New Filters | INT | Install New Filters | 0 | Ready for Release | 90025008_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127564 | S002 | 30 | 30 | 5300015697 | 60 |  |  | 0 | 120 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128154 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200090065 | 0070 | 0030 | 200090065 | 2Y 1KT2420 TURB FR3 AIR FILTER CHANGE | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10509663 | ELEMENT,FLT;CLYDE APAC FSNP50610610 | 60 | EA | 275 | 62 | 12 | 0 |  | 19.02 - SOH @ AA02 | Supply for Order 200090065, Item 8 cannot be changed 90025006 item 30 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015685 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025006 | 05 | Preparation | 0000128279 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 60 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025006_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-04 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025006 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10509663 | ELEMENT,FLT;CLYDE APAC FSNP50610610 | 2024-09-23 | W |  | 0070 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025006_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000127728 | S002 | 30 | 30 | 5300015685 | 30 |  |  | 0 | 60 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128279 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-02 | ROTAT | 200089885 | 0080 | 0040 | 200089885 | 2Y 1KT2430 TURB AIR FILTER CHANGEOUT | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10509665 | ELEMENT,FLT;CLYDE APAC IVN95610610305SS | 120 | EA | 66 | 0 | 2 | 2 | EA | 03.02 - ETA 24.03.25 PO 4500030204 VOKES CPT | Supply for Order 200089885, Item 13 cannot be changed 90025008 item 40 already exists | Material picked; currently at SW3R04C01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015697 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025008 | 05 | Preparation | 0000128154 | 13 | 0 | EA |  |  | 101000000082109 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R04C01B |  | 0 |  | 0 | 0 |  | 0 | 120 | 2025-02-19 | 2025-02-19 | Y | 1001 | 2024-09-24 | ODST-0090025008_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-10 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025008 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10509665 | ELEMENT,FLT;CLYDE APAC IVN95610610305SS | 2024-09-23 | W |  | 0080 | Install New Filters | INT | Install New Filters | 0 | Ready for Release | 90025008_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDDG1 | MJ | 20005142 | AU1072 | 1000127564 | S002 | 30 | 30 | 5300015697 | 70 |  |  | 0 | 120 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-17 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128154 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-02 | ROTAT | 200089885 | 0080 | 0040 | 200089885 | 2Y 1KT2430 TURB AIR FILTER CHANGEOUT | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10509665 | ELEMENT,FLT;CLYDE APAC IVN95610610305SS | 120 | EA | 66 | 0 | 2 | 4 | EA | 03.02 - ETA 24.03.25 PO 4500030204 VOKES CPT | Supply for Order 200089885, Item 13 cannot be changed 90025008 item 40 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015697 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025008 | 05 | Preparation | 0000128154 | 13 | 0 | EA |  |  | 102000000033505 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 120 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025008_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-10 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025008 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10509665 | ELEMENT,FLT;CLYDE APAC IVN95610610305SS | 2024-09-23 | W |  | 0080 | Install New Filters | INT | Install New Filters | 0 | Ready for Release | 90025008_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127564 | S002 | 30 | 30 | 5300015697 | 70 |  |  | 0 | 120 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128154 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200090065 | 0070 | 0040 | 200090065 | 2Y 1KT2420 TURB FR3 AIR FILTER CHANGE | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10509665 | ELEMENT,FLT;CLYDE APAC IVN95610610305SS | 60 | EA | 66 | 0 | 2 | 60 | EA | 03.10 -SOH @ AA02 | Supply for Order 200090065, Item 9 cannot be changed 90025006 item 40 already exists | Material picked; currently at 30-03-03-84B/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300015685 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025006 | 05 | Preparation | 0000128279 | 9 | 0 | EA |  |  | 102000000033504 |  |  |  |  | WorkPackLink | 30-03-03-84B |  | 0 |  | 0 | 0 |  | 0 | 60 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025006_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-04 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025006 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10509665 | ELEMENT,FLT;CLYDE APAC IVN95610610305SS | 2024-09-23 | W |  | 0070 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025006_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000127728 | S002 | 30 | 30 | 5300015685 | 40 |  |  | 0 | 60 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128279 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-10-07 | 2025-02-27 | 2025-02-11 | 2025-03-01 | 2025-03-01 | VALVE | 200147137 | 0020 | 0030 | 200147137 | 10Y MV-RE 3" 300# 141CHV2043 | AA53.141CHV2043 | VALVE,CHECK 1E407 RE INJ VAPOURISER | AA01 | 10 | Del to Maintenance after Reqmt Date | 10512437 | VALVE CHECK:80mm,CL300,RF,CS,C3SF | 1 | EA | 0 | 1 | 0 | 1 | EA | 04.02 - ETA 13.02.25 PO 4500032677 SCORE FOB ITALY | Supply for Order 200147137, Item 5 cannot be changed 90028996 item 10 already exists | Material In-Transit on-01-Road | SP97 | Direct Multi-base | 102 | AA01 | 5300016054 | 10 | FOB | 7 | 1000020569 | 5 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500032526 | 10 | 1 | EA | 2025-02-23 |  | 180128670/ | 180133643 | 90028996 | 05 | Preparation | 0000235409 | 5 | 0 | EA |  |  | 101000000149725 | 01-Road |  | 5-Completed |  | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 0 | 2025-03-10 | 2025-03-09 | Y | 1001 | 2024-10-04 | IDST-0180133643 | 0 | 0 | 0 | 0 | 2025-02-07 | 2025-02-20 | AA53 | 2025-03-01 |  |  | 2025-02-27 | 2025-02-09 | 2025-02-22 | 100000430276 | 1010 | 2025-09-30 | 1 | 5000420226_2025_0001 | 2025-03-07 | 4900260792_2025_0001 | 2025-02-27 | 200147137 |  | 0 | 2 | 2 | 90028996 | 0 | 1 | 180133643 | 1 | 0 | 0 | X | L | 4900260792 | 2025 | 5000420226 |  | 0 | 2025 | 180128670 | 2025-02-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10512437 | VALVE CHECK:80mm,CL300,RF,CS,C3SF | 2024-10-04 | W |  | 0020 | Remove & Replace NRV | INT | Remove & Replace NRV | 5 | Ready for Release | 90028996_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-10-21 | 5 | 6000010055 | 2025-02-09 | 0 |  | 0 |  | 25SD2301 | MJ | 20005604 | AU1009 | 1000232452 | S001 | 30 | 30 | 5300016053 | 10 |  | 5300016054 | 10 | 1 | EA | 1001 | AA02 | 2025-02-11 |  | Ready for Release | 2025-03-07 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0100 | 0010 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10515471 | TAP,HAND;UNF,1.125",INTER,CS | 2 | EA | 2 | 0 | 0 | 2 | EA | 18.02 - SOH @ AA02 | Supply for Order 200088516, Item 5 cannot be changed 90028586 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020032 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028586 | 05 | Preparation | 0000126825 | 5 | 0 | EA | 102000000031883 | 101000000143099 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028586_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028586 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10515471 | TAP,HAND;UNF,1.125",INTER,CS | 2025-01-14 | W |  | 0100 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | 5 | Ready for Release | 90028586_0050 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126175 | S002 | 30 | 30 | 5300020032 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126825 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0212 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10517813 | DRUM,STORAGE;M,205L,WHT,C/W STRAP,LID | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 38 cannot be changed 90023534 item 200 already exists | Material picked; currently at SW3R01E01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 38 | 0 | EA |  |  | 102000000001960 |  |  |  |  | WorkPackLink | SW3R01E01B | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10517813 | DRUM,STORAGE;M,205L,WHT,C/W STRAP,LID | 2024-01-02 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0200 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 38 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 340 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0120 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue detected, please check message in derivation or orchestration log | 10517846 | RULER MEASURING:19X150mm,STL | 1 | EA | 0 | 0 | 2 | 0 |  | 07.03 - PR 2000283124 RFQ | Supply for Order 500005166, Item 66 cannot be changed 90032306 item 100 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 66 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0100 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Scot.K |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10517846 | RULER MEASURING:19X150mm,STL | 2025-03-03 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0100 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 66 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 590 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0310 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10519010 | U-BOLT;GUIDE,M10,INS,316SS,UB0150 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 29 | 0 | [8 empty] | WorkPackLink |  | 23 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10519010 | U-BOLT;GUIDE,M10,INS,316SS,UB0150 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-11-29 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100033133 | 0020 | 0010 | 100033133 | Repl Shuttle Vlv For Mini Purge 4KM1430 | AA53.4KM1430 | MOTOR,HV,MR TRAIN STARTER/HELPER,4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(28.10.2024) | 10519034 | SENSOR,PRESS;EXPO EXS0030020 | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 100033133, Item 1 cannot be changed 90025085 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017040 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025085 | 05 | Preparation | 0000131665 | 1 | 0 | EA | 102000000030568 | 101000000134522 | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-29 | ODST-0090025085_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 4KM1430 |  | 0 | 2 | 0 | 90025085 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10519034 | SENSOR,PRESS;EXPO EXS0030020 | 2024-10-28 | W |  | 0020 | Vendor Support | ENON | Vendor Support |  |  | 90025085_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000131035 | S002 | 30 | 30 | 5300017040 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131665 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0160 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10519396 | NEEDLE SET,SCALER,3MM,12BGUN,VON ARX | 1 | SET | 0 | 0 | 3 | 1 | SET | 07.03 - SOH @ AA02 | Supply for Order 500005166, Item 18 cannot be changed 90031501 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180134139 | 9029110 | 05 | Preparation | 0000294187 | 18 | 0 | SET |  |  | 101000000150929 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000435328_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060591 | 1020 |  | 1 |  | 2025-03-10 | 4900263693_2025_0001 | 2025-04-01 | TA LAG_VORN | 5000435328_2025_0001 | 0 | 2 | 0 | 90031501 | 1 | 0 | 180134139 | 2 | 0 | 0 | X | L | 4900263693 | 2025 |  | 5000435328 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10519396 | NEEDLE SET,SCALER,3MM,12BGUN,VON ARX | 2025-02-19 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 9029110_0020 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 18 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 160 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | MECH | 100043807 | 0010 | 0032 | 100043807 | Repair/replace faulty N2 flow indicator | AA53.118FI503 | IND,N2 PURGE GAS TO RESERVOIR 1K1820V6 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10520285 | METER,FLOW;BROOKS 3809GBD07DABB1A00D0B | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 100043807, Item 3 cannot be changed 90024945 item 10 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300001423 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024945 | 06 | Scheduling | 0000142308 | 3 | 0 | EA | 102000000027651 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024945_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-01-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118FI503 |  | 0 | 2 | 0 | 90024945 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10520285 | METER,FLOW;BROOKS 3809GBD07DABB1A00D0B | 2024-01-01 | W |  | 0010 | Remove & Replace Flowmeter | INT | Remove & Replace Flowmeter | 5 |  | 90024945_0010 |  |  | FR1 |  | C2 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000141677 | S002 | 30 | 30 | 5300001423 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142308 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material shortage | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-05-15 | MECH | 100044203 | 0010 | 0012 | 100044203 | Repair/replace faulty N2 flow indicator | AA53.118FI502 | IND,N2 PURGE GAS TO RESERVOIR 1K1820V2 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10520285 | METER,FLOW;BROOKS 3809GBD07DABB1A00D0B | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 100044203, Item 3 cannot be changed 90024953 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002290 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024953 | 06 | Scheduling | 0000142657 | 3 | 0 | EA | 102000000027652 |  | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024953_0030 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2021-01-14 | 0 |  | 2025-03-26 |  | 2025-03-31 | 118FI502 |  | 0 | 2 | 0 | 90024953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10520285 | METER,FLOW;BROOKS 3809GBD07DABB1A00D0B | 2024-01-02 | W |  | 0010 | Remove & Replace Flowmeter | INT | Remove & Replace Flowmeter | 5 |  | 90024953_0030 |  |  | FR1 |  | B2 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000142019 | S002 | 30 | 30 | 5300002290 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142657 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material shortage | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0300 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10520443 | SPRING,TANK EXPANSION,4",316SS,FM INS | 150 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 31.03.25 PO 4500047669 TRINKOR CPT | Supply for Order 500005166, Item 50 cannot be changed 90031501 item 310 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 50 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 150 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0310 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10520443 | SPRING,TANK EXPANSION,4",316SS,FM INS | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0310 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 50 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 460 |  |  | 0 | 150 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0010 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521347 | BOLT,HEX,M10X20MM,SULZER 10008290 | 200 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.03.25 PO 4500047516 KONNECT CPT | Supply for Order 200073951, Item 20 cannot be changed 90030758 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 20 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521347 | BOLT,HEX,M10X20MM,SULZER 10008290 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 20 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 200 |  |  | 0 | 200 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0020 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521348 | BOLT,HEX,M10X40MM,SULZER 10008292 | 70 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.03.25 PO 4500047516 KONNECT CPT | Supply for Order 200073951, Item 21 cannot be changed 90030758 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 21 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521348 | BOLT,HEX,M10X40MM,SULZER 10008292 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0020 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 21 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 210 |  |  | 0 | 70 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0030 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521349 | BOLT,HEX,M16X40MM,SULZER 10008294 | 70 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.03.25 PO 4500047516 KONNECT CPT | Supply for Order 200073951, Item 22 cannot be changed 90030758 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 22 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521349 | BOLT,HEX,M16X40MM,SULZER 10008294 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0030 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 22 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 220 |  |  | 0 | 70 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0040 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521420 | BOLT,HEX,M16X50MM,SULZER 10008295 | 70 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.03.25 PO 4500047516 KONNECT CPT | Supply for Order 200073951, Item 23 cannot be changed 90030758 item 40 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 23 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521420 | BOLT,HEX,M16X50MM,SULZER 10008295 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0040 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 23 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 230 |  |  | 0 | 70 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0050 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521421 | BOLT,HEX,M16X60MM,SULZER 10008296 | 70 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.03.25 PO 4500047516 KONNECT CPT | Supply for Order 200073951, Item 24 cannot be changed 90030758 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 24 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521421 | BOLT,HEX,M16X60MM,SULZER 10008296 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0050 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 24 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 240 |  |  | 0 | 70 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0060 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521422 | NUT,HEX,M10,410 SS,SULZER 10008450 | 200 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.03.25 PO 4500047516 KONNECT CPT | Supply for Order 200073951, Item 25 cannot be changed 90030758 item 60 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 25 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521422 | NUT,HEX,M10,410 SS,SULZER 10008450 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0060 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 25 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 250 |  |  | 0 | 200 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0070 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521423 | NUT,HEX,M12,410 SS,SULZER 10008341 | 70 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.03.25 PO 4500047516 KONNECT CPT | Supply for Order 200073951, Item 26 cannot be changed 90030758 item 70 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 26 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521423 | NUT,HEX,M12,410 SS,SULZER 10008341 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 26 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 260 |  |  | 0 | 70 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0080 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521424 | NUT,HEX,M16,410 SS,SULZER 10006673 | 280 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.03.25 PO 4500047516 KONNECT CPT | Supply for Order 200073951, Item 27 cannot be changed 90030758 item 80 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 27 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 280 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521424 | NUT,HEX,M16,410 SS,SULZER 10006673 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 27 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 270 |  |  | 0 | 280 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0090 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521425 | STUD BOLT,M16X130MM,SULZER 10007703 | 15 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 101 Day PDT | Supply for Order 200073951, Item 28 cannot be changed 90030758 item 90 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 28 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 15 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521425 | STUD BOLT,M16X130MM,SULZER 10007703 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0090 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 28 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 280 |  |  | 0 | 15 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0100 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521426 | PLATE,BEAM,60X60X2MM,SULZER 10008870 | 50 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 101 Day PDT | Supply for Order 200073951, Item 29 cannot be changed 90030758 item 100 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 29 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521426 | PLATE,BEAM,60X60X2MM,SULZER 10008870 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0100 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 29 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 290 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0170 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521427 | WASHER,PLAIN,32X11X3MM,SULZER 10008833 | 200 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 60 Day PDT | Supply for Order 200073951, Item 36 cannot be changed 90030758 item 170 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 36 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521427 | WASHER,PLAIN,32X11X3MM,SULZER 10008833 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0170 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 36 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 360 |  |  | 0 | 200 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0180 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521428 | WASHER,PLAIN,32X14X3MM,SULZER 10008845 | 70 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 60 Day PDT | Supply for Order 200073951, Item 37 cannot be changed 90030758 item 180 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 37 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521428 | WASHER,PLAIN,32X14X3MM,SULZER 10008845 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0180 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 37 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 370 |  |  | 0 | 70 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0190 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521429 | WASHER,PLAIN,32X17X3MM,SULZER 10008820 | 140 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 41 Day PDT | Supply for Order 200073951, Item 38 cannot be changed 90030758 item 190 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 38 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 140 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521429 | WASHER,PLAIN,32X17X3MM,SULZER 10008820 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0190 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 38 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 380 |  |  | 0 | 140 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0200 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521450 | WASHER,PLAIN,50X17X6MM,SULZER 10010719 | 70 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 41 Day PDT | Supply for Order 200073951, Item 39 cannot be changed 90030758 item 200 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 39 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521450 | WASHER,PLAIN,50X17X6MM,SULZER 10010719 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0200 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 39 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 390 |  |  | 0 | 70 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0150 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521452 | CLAMP,TRAY,D12,410S SS,SULZER 10008965 | 50 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 41 Day PDT | Supply for Order 200073951, Item 34 cannot be changed 90030758 item 150 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 34 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521452 | CLAMP,TRAY,D12,410S SS,SULZER 10008965 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0150 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 34 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 340 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0160 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521453 | CLAMP,WEDGE,D12,410S SS,SULZER 10009198 | 60 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 30 Day PDT | Supply for Order 200073951, Item 35 cannot be changed 90030758 item 160 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 35 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 60 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521453 | CLAMP,WEDGE,D12,410S SS,SULZER 10009198 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0160 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 35 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 350 |  |  | 0 | 60 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0210 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521454 | WEDGE,85X1.5MM,410S SS,SULZER 10009183 | 170 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 70 Day PDT | Supply for Order 200073951, Item 40 cannot be changed 90030758 item 210 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 40 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 170 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521454 | WEDGE,85X1.5MM,410S SS,SULZER 10009183 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0210 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 40 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 400 |  |  | 0 | 170 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0110 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521455 | LUG,21.5X1.5MM,410S SS,SULZER 10008898 | 100 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 41 Day PDT | Supply for Order 200073951, Item 30 cannot be changed 90030758 item 110 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 30 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521455 | LUG,21.5X1.5MM,410S SS,SULZER 10008898 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0110 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 30 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 300 |  |  | 0 | 100 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0120 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521456 | LUG,24.5X1.5MM,410S SS,SULZER 10008916 | 50 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 41 Day PDT | Supply for Order 200073951, Item 31 cannot be changed 90030758 item 120 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 31 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521456 | LUG,24.5X1.5MM,410S SS,SULZER 10008916 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0120 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 31 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 310 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0130 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521457 | SEAL PLATE,80X20X1.5MM,SULZER 10008952 | 60 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 41 Day PDT | Supply for Order 200073951, Item 32 cannot be changed 90030758 item 130 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 32 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 60 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521457 | SEAL PLATE,80X20X1.5MM,SULZER 10008952 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0130 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 32 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 320 |  |  | 0 | 60 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0110 | 0140 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10521458 | VALVE,SNAP IN,10.5MM,SULZER 10009171 | 500 | EA | 0 | 0 | 0 | 0 |  | 13.02 - @ PR - 41 Day PDT | Supply for Order 200073951, Item 33 cannot be changed 90030758 item 140 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030758 | 05 | Preparation | 0000108267 | 33 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 500 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030758_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | HIGH |  | 0 | 2 | 0 | 90030758 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521458 | VALVE,SNAP IN,10.5MM,SULZER 10009171 | 2025-02-11 | W |  | 0110 | CRs - CSE Setup, Tray Rem/Repl & HPW | INT | CRs - CSE Setup, Tray Rem/Repl & HPW |  |  | 90030758_0140 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 33 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 330 |  |  | 0 | 500 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0290 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10521500 | WEATHERSTRIP,CRTD,918MM,EAVE | 200 | EA | 20 | 0 | 0 | 0 |  | 20.02 - PR 2000272645 | Supply for Order 500005166, Item 49 cannot be changed 90031501 item 300 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 49 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0300 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10521500 | WEATHERSTRIP,CRTD,918MM,EAVE | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0300 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 49 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 450 |  |  | 0 | 200 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDDG1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200090684 | 0010 | 0032 | 200090684 | 6Y P02 EXCHANGER INTERNAL INSPECT (2) | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10522860 | GASKET,CNAF,300MM,CL300,3MM,HX FLOATING | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200090684, Item 3 cannot be changed 90024962 item 30 already exists | Material picked; currently at SW3R01H02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004268 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024962 | 05 | Preparation | 0000128878 | 3 | 0 | EA |  |  | 102000000029648 |  |  |  |  | WorkPackLink | SW3R01H02B | AU01-P08-DG | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024962_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200613512 |  | 0 | 2 | 0 | 90024962 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10522860 | GASKET,CNAF,300MM,CL300,3MM,HX FLOATING | 2024-01-02 | W |  | 0010 | HPWW of Tube Bundles 1KKT2410E1 & E2 | ENON | HPWW of Tube Bundles 1KKT2410E1 & E2 | 5 |  | 90024962_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000128347 | S002 | 30 | 30 | 5300004268 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128878 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | MECH | 200147066 | 0040 | 0060 | 200147066 | 12Y EX/SH INSP TUB/RVI BUNREM 1KKT2410E1 | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(21.01.2025) | 10522860 | GASKET,CNAF,300MM,CL300,3MM,HX FLOATING | 1 | EA | 2 | 0 | 0 | 0 |  | 03.02 - ETA 21.03.25 PO 4500044454 KLINGER CPT | Supply for Order 200147066, Item 3 cannot be changed 90030055 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020024 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030055 | 05 | Preparation | 0000235151 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030055_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147066 |  | 0 | 2 | 0 | 90030055 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10522860 | GASKET,CNAF,300MM,CL300,3MM,HX FLOATING | 2025-01-21 | W |  | 0040 | Remove Bonnet & Bundle | INT | Remove Bonnet & Bundle |  |  | 90030055_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232217 | S002 | 30 | 30 | 5300020024 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-29 | 235151 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | MECH | 200147067 | 0040 | 0040 | 200147067 | 12Y EX/SH INSP TUB/RVI BUNREM 1KKT2410E2 | AA53.1KKT2410E2 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 S | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(21.01.2025) | 10522860 | GASKET,CNAF,300MM,CL300,3MM,HX FLOATING | 1 | EA | 2 | 0 | 0 | 0 |  | 03.02 - ETA 21.03.25 PO 4500044454 KLINGER CPT | Supply for Order 200147067, Item 4 cannot be changed 90030056 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020025 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030056 | 05 | Preparation | 0000235152 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090030056_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147067 |  | 0 | 2 | 0 | 90030056 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10522860 | GASKET,CNAF,300MM,CL300,3MM,HX FLOATING | 2025-01-21 | W |  | 0040 | Remove Bonnet & Bundle | INT | Remove Bonnet & Bundle |  |  | 90030056_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232218 | S002 | 30 | 30 | 5300020025 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-29 | 235152 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-10-17 | 2025-01-01 | 2024-12-27 | 2025-05-08 | 2025-05-08 | INLEC | 100044565 | 0020 | 0020 | 100044565 | MOC-151119 Press Switch Rpl (4) 4KT1410 | AA53.460PZ471A | SW,PRESS 4KT1410V5 CO2 STORAGE TNK HIHI | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(26.11.2024) | 10523581 | SWITCH,PRESS,GAS TURB,CO2 TANK,PRIDE | 4 | EA | 6 | 0 | 8 | 2 | EA | 04.03 - SOH @ AA01 | Supply for Order 100044565, Item 3 cannot be changed 90026157 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016507 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90026157 | 05 | Preparation | 0000143069 | 3 | 0 | EA | 102000000029972 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090026157_0020 | 0 | 0 | 0 | 0 |  | 2024-12-30 | AA53 | 2025-05-08 |  |  | 2025-01-01 |  |  |  |  | 2020-11-01 | 0 |  | 2024-12-27 |  | 2025-01-01 | 4KT1410 |  | 0 | 2 | 0 | 90026157 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-12-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10523581 | SWITCH,PRESS,GAS TURB,CO2 TANK,PRIDE | 2024-11-26 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  | Engineering Query/Management of Change/Order Requires Replanning | 90026157_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000142440 | S002 | 30 | 30 | 5300016507 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-12-27 |  | Engineering Query/Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143069 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD4403 | Released | 2024-11-05 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200161177 | 0010 | 0010 | 200161177 | 2Y SIF ESD Function Test (7) K4403 | AA53.44HZ125 | SW,K4403 CCR TRIP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(04.11.2024) | 10525558 | DIAPHRAGM,VV;1.5",304SS,CCI 133871 | 3 | EA | 5 | 0 | 3 | 3 | EA | 07.11 - SOH @ AA02 | Supply for Order 200161177, Item 1 cannot be changed 90025096 item 10 already exists | Material picked; currently at SW3R01B01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017347 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025096 | 05 | Preparation | 0000256797 | 1 | 0 | EA | 102000000027724 |  | 102000000026658 |  |  |  |  | WorkPackLink | SW3R01B01A |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-05 | ODST-0090025096_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-08 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025096 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10525558 | DIAPHRAGM,VV;1.5",304SS,CCI 133871 | 2024-11-04 | W |  | 0010 | Operations Assistance | INT | Operations Assistance | 5 |  | 90025096_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD4403 | MJ |  | AU1072 | 1000252893 | S002 | 30 | 30 | 5300017347 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-13 | 256797 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-08-19 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 200161965 | 0010 | 0060 | 200161965 | 4Y INSP EXP 1KM1310 PURGE UNIT | AA53.1KM1310PAP | PANEL,CTRL UNIT EEX P PURGE 1KM1310 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10525717 | SENSOR,FLOW;6.4MBARG,EXPO S0030/606 | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.02 - SOH @ AA01 | Supply for Order 200161965, Item 6 cannot be changed 90028297 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019288 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028297 | 07 | Execution | 0000257849 | 6 | 0 | EA | 101000000142536 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-18 | ODST-0090028297_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KM1310PAP |  | 0 | 2 | 0 | 90028297 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10525717 | SENSOR,FLOW;6.4MBARG,EXPO S0030/606 | 2024-12-18 | W |  | 0010 | Carry out 4Y Exp Inspection | INT | Carry out 4Y Exp Inspection | 5 |  | 90028297_0060 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000253830 | S002 | 30 | 30 | 5300019288 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-19 | 257849 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-08-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100038870 | 1000 | 0080 | 100038870 | MOC-123206 Replace JB 5PM2001BJ | AA53.5PM2001BJ | JB,MOTOR,RCU STABLI HEATER PUMP,5P2001B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10527196 | GLAND:BREATHER DRAIN,BRASS, NICKEL PLATE | 1 | EA | 1 | 0 | 0 | 1 | EA | 17.02 - SOH @ AA02 | Supply for Order 100038870, Item 8 cannot be changed 90030871 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013766 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030871 | 06 | Scheduling | 0000137402 | 8 | 0 | EA | 102000000033216 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-09 | ODST-0090030871_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5PM2001BJ |  | 0 | 2 | 0 | 90030871 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10527196 | GLAND:BREATHER DRAIN,BRASS, NICKEL PLATE | 2025-02-14 | W |  | 1000 | Function Test & Complete ITR/MITR | INT | Function Test & Complete ITR/MITR |  | Management of Change | 90030871_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000136732 | S002 | 30 | 30 | 5300013766 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-08-09 | 2025-03-01 | 2024-09-30 | 2025-03-01 | 2025-03-01 | INLEC | 100038870 | 1000 | 0030 | 100038870 | MOC-123206 Replace JB 5PM2001BJ | AA53.5PM2001BJ | JB,MOTOR,RCU STABLI HEATER PUMP,5P2001B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.08.2024) | 10527196 | GLAND:BREATHER DRAIN,BRASS, NICKEL PLATE | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - At KGP | Supply for Order 100038870, Item 3 cannot be changed 180075524 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300013766 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180075524 | 9015204 | 06 | Scheduling | 0000137402 | 3 | 0 | EA |  |  | 102000000018554 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08BENCH | AA53-TA-P07 | 0 | 5400001096 | 10 | 1 | EA | 1 | 0 |  |  | Y | 1001 | 2024-08-09 |  | 0 | 0 | 0 | 0 |  | 2024-10-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000032211 | 1020 | 2025-07-31 | 1 |  | 2024-09-29 | 4900141888_2024_0001 | 2024-10-03 | 5PM2001BJ | 5000224969_2024_0001 | 0 | 2 | 0 | 90020098 | 1 | 0 | 180075524/180130240 | 2 | 0 | 0 | X | L | 4900141888 | 2024 |  | 5000224969 | 2024 | 0 |  | 2024-09-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10527196 | GLAND:BREATHER DRAIN,BRASS, NICKEL PLATE | 2024-08-09 | W |  | 1000 | Function Test & Complete ITR/MITR | INT | Function Test & Complete ITR/MITR |  | Management of Change | 9015204_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ | 1000003543 | AU1072 | 1000136732 | S002 | 30 | 30 | 5300013766 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-09-30 |  | Management of Change | 2024-10-03 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0210 | 0010 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10528931 | COUPLING,SPIDER;RING,CAM,BIPEX 127 | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200063883, Item 23 cannot be changed 90024996 item 200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 23 | 0 | EA | 102000000033509 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090024996_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10528931 | COUPLING,SPIDER;RING,CAM,BIPEX 127 | 2024-08-13 | W |  | 0210 | Install SS Clutch and Barring gear Motor | INT | Install SS Clutch and Barring gear Motor |  | Ready for Release | 90024996_0200 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 23 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 200 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 200144506 | 0020 | 0010 | 200144506 | 2Y MOV Insp & Stroke Test 114MOV13 | AA53.114MOV13 | VALVE,FLO PROP VAP TO V1431 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10529357 | O-RING KIT,COVER;ACT,ROTORK A10KCA16A | 1 | EA | 0 | 0 | 0 | 0 |  | 03.02 - SOH @ AA01 | Supply for Order 200144506, Item 1 cannot be changed 90025028 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016422 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025028 | 05 | Preparation | 0000231611 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025028_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | 114MOV13 |  | 0 | 2 | 0 | 90025028 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10529357 | O-RING KIT,COVER;ACT,ROTORK A10KCA16A | 2024-10-16 | W |  | 0020 | Complete MOV Inspection | INT | Complete MOV Inspection | 5 |  | 90025028_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228778 | S002 | 30 | 30 | 5300016422 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231611 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0220 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.02.2025) | 10530362 | PIN,LK;CPLG,10MM TO 80MM,MILLENIUM MCLP | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.03 - SOH @ AA02 | Supply for Order 500004676, Item 22 cannot be changed 90031855 item 200 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 22 | 0 | EA | 101000000149752 |  | 101000000149860 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 2 |  | 2025-03-02 | Y | 1001 | 2025-02-12 | ODST-0090031855_0200 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10530362 | PIN,LK;CPLG,10MM TO 80MM,MILLENIUM MCLP | 2025-02-20 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0200 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 22 |  | 0 |  | 25SDENA1 | MJ | 20005413 | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 210 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-27 |  |  | 2025-02-28 |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 3 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0480 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10530795 | METER,FLOW;BROOKS 3809GBA08CGBF9A00B0B | 1 | EA | 2 | 0 | 0 | 1 | EA | 31.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 58 cannot be changed 90025019 item 570 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 58 | 0 | EA | 102000000027490 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0570 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10530795 | METER,FLOW;BROOKS 3809GBA08CGBF9A00B0B | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0570 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 58 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 570 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-04-26 | 2025-03-01 | 2025-05-06 | ROTAT | 100046308 | 0040 | 0010 | 100046308 | MOC-52386 - Tank Min Oil Replace - G4008 | AA53.G4008V1 | TANK,MINERAL OIL RESERVOIR G4008 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10531586 | LUBRICANT OIL:SHELL TURBO S4 X 32,1000L | 10 | CON | 27 | 0 | 10 | 0 |  | 19.02 - SOH @ AA02 | Supply for Order 100046308, Item 1 cannot be changed 90010061 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002735 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  |  |  |  | 90010061 | 05 | Preparation | 0000144829 | 1 | 0 | [8 empty] | WorkPackLink |  | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-02 | ODST-0090010061_0010 | 0 | 59 | 0 | 0 |  | 2025-04-27 | AA53 | 2025-03-01 |  |  | 2025-04-29 |  |  |  |  | 2020-06-25 | 0 |  | 2025-04-26 |  | 2025-04-29 | MLO S4X32 |  | 0 | 2 | 0 | 90010061 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-04-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10531586 | LUBRICANT OIL:SHELL TURBO S4 X 32,1000L | 2024-01-02 | W |  | 0040 | Fill MLO tank & carry out flush-3 micron | INT | Fill MLO tank & carry out flush-3 micron | 5 |  | 90010061_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000144178 | S002 | 30 | 30 | 5300002735 | 10 |  |  | 0 | 10 | CON | 2001 | AA02 | 2025-04-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144829 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Estimated costs | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0020 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10531586 | LUBRICANT OIL:SHELL TURBO S4 X 32,1000L | 3 | CON | 27 | 0 | 10 | 3 | CON | 19.02 - SOH @ AA02 | Supply for Order 200091108, Item 107 cannot be changed 90028420 item 710 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  | 0000001982 |  |  | 90028420 | 05 | Preparation | 0000129406 | 107 | 0 | CON |  |  | 102000000030794 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0710 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SO |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10531586 | LUBRICANT OIL:SHELL TURBO S4 X 32,1000L | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0710 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 107 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 | 30 | 30 | 5300013062 | 740 |  |  | 0 | 3 | CON | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10531586 | LUBRICANT OIL:SHELL TURBO S4 X 32,1000L | 10 | CON | 27 | 0 | 10 | 0 |  | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 612 cannot be changed 90028419 item 4160 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4190 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  | CUTOVER_S4 |  |  | 90028419 | 05 | Preparation | 0000129822 | 612 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10531586 | LUBRICANT OIL:SHELL TURBO S4 X 32,1000L | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4160 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 612 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4190 |  |  | 0 | 10 | CON | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-25 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0040 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.05.2024) | 10531963 | GASKET,SW;1350MM,CL150,316L/316L/FG/316L | 6 | EA | 6 | 0 | 0 | 6 | EA | 23.01 - SOH @ AA02 | Supply for Order 600001757, Item 10 cannot be changed 90024969 item 20 already exists | Material picked; currently at 30-03-04-81A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024969 | 07 | Execution | 0000084653 | 10 | 0 | EA |  |  | 101000000086400 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-04-81A | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 6 | 2025-01-18 | 2025-01-18 | Y | 1001 | 2024-01-24 | ODST-0090024969_0020 | 0 | 0 | 0 | 0 |  | 2025-02-26 | AA53 | 2025-04-30 |  |  | 2025-02-28 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-25 |  | 2025-02-28 | 600001757 |  | 0 | 2 | 0 | 90024969 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10531963 | GASKET,SW;1350MM,CL150,316L/316L/FG/316L | 2024-05-29 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024969_0020 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDFLR | MJ | 20004585 | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 90 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-25 |  | Management of Change/Order Requires Replanning | 2025-01-16 |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2025-02-12 | 2025-02-11 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0340 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10532940 | LADDER;STEP PLATFORM,BRANACH FPL 3.0 | 1 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 11.03.25 PO 4500045866 BLACKWOODS CPT | Supply for Order 600001815, Item 44 cannot be changed 90030688 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030688 | 07 | Execution | 0000084731 | 44 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030688_0010 | 0 | 4 | 0 | 0 |  | 2025-02-10 | AA53 | 2025-02-08 |  |  | 2025-02-16 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-11 |  | 2025-02-16 | 37FQI40/41 |  | 0 | 2 | 0 | 90030688 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-11 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10532940 | LADDER;STEP PLATFORM,BRANACH FPL 3.0 | 2025-02-11 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030688_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 44 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 300 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-11 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDLN1 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 200144508 | 0020 | 0010 | 200144508 | 2Y MOV Insp & Stroke Test 114MOV15 | AA53.114MOV15 | VALVE,FLO PROP VAP TO V1440 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10533896 | O-RING KIT,COVER;ACT,ROTORK A10KCA70A | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.02 - SOH @ AA02 | Supply for Order 200144508, Item 1 cannot be changed 90025029 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016423 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025029 | 05 | Preparation | 0000231613 | 1 | 0 | EA | 101000000142691 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025029_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | 114MOV15 |  | 0 | 2 | 0 | 90025029 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10533896 | O-RING KIT,COVER;ACT,ROTORK A10KCA70A | 2024-10-16 | W |  | 0020 | Complete MOV Inspection | INT | Complete MOV Inspection | 5 |  | 90025029_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228780 | S002 | 30 | 30 | 5300016423 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231613 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-11-08 | 2025-03-01 | 2025-02-21 | 2025-03-01 | 2025-03-01 | INLEC | 200144510 | 0020 | 0050 | 200144510 | 2Y MOV Insp & Stroke Test 114MOV121 | AA53.114MOV121 | VALVE,FLO CTRL PROPANE VAPOUR T0 1E1441A | AA01 | 10 | PR due for release | 10533896 | O-RING KIT,COVER;ACT,ROTORK A10KCA70A | 2 | EA | 1 | 0 | 1 | 0 |  | 24.02 - PR 1000030503 | Supply for Order 200144510, Item 5 cannot be changed 90031408 item 10 already exists | PR approved; PO not issued | SP97 | Direct Multi-base | 30 | AA01 | 5300021613 | 20 |  | 7 | 1000030503 | 5 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031408 | 05 | Preparation | 0000231615 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-21 | PRPO-1000030503_00005 | 0 | 51 | 40 | 51 | 2025-03-31 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-04-21 | 2025-04-02 | 2025-04-16 |  |  | 2025-11-10 | 0 |  | 2025-02-21 |  | 2025-03-07 | 114MOV121 |  | 0 | 2 | 2 | 90031408 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-21 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10533896 | O-RING KIT,COVER;ACT,ROTORK A10KCA70A | 2025-02-20 | W |  | 0020 | Complete MOV Inspection | INT | Complete MOV Inspection | 5 |  | 90031408_0010 |  |  | LN1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-21 | 10 |  | 2025-04-02 | 0 |  | 0 |  | 25SDLN1 | MJ |  | AU1009 | 1000228782 | S001 | 30 | 30 | 5300021612 | 20 |  | 5300021613 | 20 | 2 | EA | 1001 | AA02 | 2025-02-21 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0130 | 0150 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 6 | EA | 24 | 0 | 0 | 6 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 15 cannot be changed 90025036 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 15 | 0 | EA | 102000000028416 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | PCC bolts |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 2024-10-16 | W |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 3 | Ready for Release | 90025036_0130 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 15 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 130 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0130 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 6 | EA | 24 | 0 | 0 | 6 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 20 cannot be changed 90025043 item 180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 20 | 0 | EA | 102000000028417 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | PCC bolts |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 2024-10-17 | W |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 3 | Ready for Release | 90025043_0180 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 20 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 180 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0130 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 6 | EA | 24 | 0 | 0 | 6 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 20 cannot be changed 90025045 item 190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 20 | 0 | EA | 102000000028418 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | PCC bolts |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 2024-10-17 | W |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 3 |  | 90025045_0190 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 20 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 190 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0210 | 0240 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10537214 | O-RING;HCU FILTER,GE M832481110 | 1 | EA | 6 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 24 cannot be changed 90025036 item 210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 24 | 0 | EA | 102000000027247 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537214 | O-RING;HCU FILTER,GE M832481110 | 2024-10-16 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 | Ready for Release | 90025036_0210 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 24 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 210 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0210 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10537214 | O-RING;HCU FILTER,GE M832481110 | 1 | EA | 6 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 28 cannot be changed 90025043 item 260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 28 | 0 | EA | 102000000027248 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537214 | O-RING;HCU FILTER,GE M832481110 | 2024-10-17 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 | Ready for Release | 90025043_0260 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 28 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0210 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10537214 | O-RING;HCU FILTER,GE M832481110 | 1 | EA | 6 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 24 cannot be changed 90025045 item 230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 24 | 0 | EA | 102000000027249 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537214 | O-RING;HCU FILTER,GE M832481110 | 2024-10-17 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 |  | 90025045_0230 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 24 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 230 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 200144771 | 0010 | 0030 | 200144771 | 2Y Harm Filter Vesda Check 60JB870 | AA53.60JB870 | JB,NON I.S. JUNCTION BOX | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10537850 | FILTER;E FILTER,VESDA VSP96220 | 1 | EA | 3 | 0 | 4 | 1 | EA | 19.02 - At KGP | Supply for Order 200144771, Item 3 cannot be changed 9026644 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016479 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121312 | 9026644 | 05 | Preparation | 0000231921 | 3 | 0 | EA | 102000000032324 |  | 107000000000399 |  |  |  |  | WorkPackLink | INLEC-CAGE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000385859_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  | 100000056054 | 1020 | 2025-10-15 | 1 |  | 2025-02-04 | 4900226327_2025_0001 | 2025-03-01 | 60JB870 | 5000385859_2025_0001 | 0 | 2 | 0 | 90025042 | 1 | 0 | 180121312 | 2 | 0 | 0 | X | L | 4900226327 | 2025 |  | 5000385859 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537850 | FILTER;E FILTER,VESDA VSP96220 | 2024-10-16 | W |  | 0010 | Function Test & Complete PRT / MITR | INT | Function Test & Complete PRT / MITR | 2 |  | 9026644_0030 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000229037 | S002 | 30 | 30 | 5300016479 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231921 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100075029 | 0020 | 0050 | 100075029 | Replace Incorrect DVC Relay 414UV212 | AA53.414UY212 | POS,VALVE,4E1442 PROPANE OUTLET ISOLTN | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(01.11.2024) | 10539109 | RELAY:ASSY,FISHER-EMERSON INC,38B5786X12 | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 100075029, Item 5 cannot be changed 180110347 item 10 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 86 | AA02 | 5300017212 | 10 | CPT | 7 | 1000022286 | 5 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500033719 | 10 | 1 | EA | 2025-02-17 |  | /180107527 |  | 90025092 | 05 | Preparation | 0000227805 | 5 | 0 | EA | 102000000028729 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-01 | ODST-0090025092_0010 | 0 | 7 | 7 | 7 | 2025-02-17 | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-08 | 2025-02-19 | 2025-01-08 |  |  | 2025-10-31 | 0 | 5000331899_2024_0001 | 2025-02-24 |  | 2024-12-24 | 414UV212 |  | 0 | 2 | 2 | 90025092 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000331899 |  | 0 | 2024 | /018010752 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539109 | RELAY:ASSY,FISHER-EMERSON INC,38B5786X12 | 2024-11-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025092_0010 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-11-01 | 5 |  | 2025-02-19 | 5 |  | 65273 |  | 25SDLN4 | MJ |  | AU1072 | 1000225096 | S002 | 30 | 30 | 5300017212 | 10 |  | 5300017213 | 10 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-20 | 227805 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 |  | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10539733 | SEALANT,JOINT;50ML,LOCTITE 572 | 4 | EA | 5 | 0 | 0 | 4 | EA | 18.12 - SOH @ AA02 | Supply for Order 200063883, Item 17 cannot be changed 90024996 item 150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 17 | 0 | EA | 102000000027246 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-08-13 | ODST-0090024996_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539733 | SEALANT,JOINT;50ML,LOCTITE 572 | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 90024996_0150 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 150 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT7 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0100 | 0110 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | WO item has not been released yet | 10539834 | NUT,SWIVEL;GE J1317P10B | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235960 | 11 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | Swivel Nut O |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539834 | NUT,SWIVEL;GE J1317P10B |  |  |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000232966 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT8 | Released | 2024-10-17 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0100 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | WO item has not been released yet | 10539834 | NUT,SWIVEL;GE J1317P10B | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235962 | 16 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  |  |  |  | Swivel Nut O |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539834 | NUT,SWIVEL;GE J1317P10B |  |  |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000232968 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0100 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10539834 | NUT,SWIVEL;GE J1317P10B | 1 | EA | 0 | 0 | 3 | 0 |  | 18.10 - SOH @ AA01 | Supply for Order 200147552, Item 16 cannot be changed 90025045 item 150 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 16 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Swivel Nut O |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539834 | NUT,SWIVEL;GE J1317P10B | 2024-10-17 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 |  | 90025045_0150 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 16 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-05 | INLEC | 100033790 | 0020 | 0010 | 100033790 | EEHA - Replace RCU (1) GT4008KM1AR | AA53.GT4008KM1AR | RCU,FOR GT4008KM1A | AA01 | 10 | No issue identified | 10541214 | RCU;CCH GHG29343723202003FLMGVM251M321 | 1 | EA | 1 | 0 | 0 | 0 |  | 04.03 - SOH @ AA01 |  | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016500 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030044 | 05 | Preparation | 0000132342 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090030044_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-25 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4008KM1AR |  | 0 | 2 | 0 | 90030044 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541214 | RCU;CCH GHG29343723202003FLMGVM251M321 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query | 90030044_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000131692 | S002 | 30 | 30 | 5300016500 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132342 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-05 | INLEC | 100033793 | 0020 | 0020 | 100033793 | EEHA - Replace RCU (1) GT4008KM1BR | AA53.GT4008KM1BR | RCU,FOR GT4008KM1B | AA01 | 10 | No issue identified | 10541214 | RCU;CCH GHG29343723202003FLMGVM251M321 | 1 | EA | 1 | 0 | 0 | 1 | EA | 04.03 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016501 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030045 | 05 | Preparation | 0000132345 | 3 | 0 | EA | 101000000144657 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090030045_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-24 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4008KM1BR |  | 0 | 2 | 0 | 90030045 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541214 | RCU;CCH GHG29343723202003FLMGVM251M321 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query | 90030045_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000131695 | S002 | 30 | 30 | 5300016501 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132345 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material shortage | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-08-19 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 200161965 | 0010 | 0020 | 200161965 | 4Y INSP EXP 1KM1310 PURGE UNIT | AA53.1KM1310PAP | PANEL,CTRL UNIT EEX P PURGE 1KM1310 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10541275 | GAUGE,PRESS;50MM,0-10BAR,EXPO EXS0015018 | 1 | EA | 1 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA01 | Supply for Order 200161965, Item 2 cannot be changed 90028297 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019288 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028297 | 07 | Execution | 0000257849 | 2 | 0 | EA | 101000000136739 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-18 | ODST-0090028297_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KM1310PAP |  | 0 | 2 | 0 | 90028297 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541275 | GAUGE,PRESS;50MM,0-10BAR,EXPO EXS0015018 | 2024-12-18 | W |  | 0010 | Carry out 4Y Exp Inspection | INT | Carry out 4Y Exp Inspection | 5 |  | 90028297_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000253830 | S002 | 30 | 30 | 5300019288 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-19 | 257849 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-08-19 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 200161965 | 0010 | 0030 | 200161965 | 4Y INSP EXP 1KM1310 PURGE UNIT | AA53.1KM1310PAP | PANEL,CTRL UNIT EEX P PURGE 1KM1310 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10541276 | GAUGE;MIN,40MM,0-4 BAR,EXPO EXS0015135 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 200161965, Item 3 cannot be changed 90028297 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019288 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028297 | 07 | Execution | 0000257849 | 3 | 0 | EA | 101000000143773 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-18 | ODST-0090028297_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KM1310PAP |  | 0 | 2 | 0 | 90028297 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541276 | GAUGE;MIN,40MM,0-4 BAR,EXPO EXS0015135 | 2024-12-18 | W |  | 0010 | Carry out 4Y Exp Inspection | INT | Carry out 4Y Exp Inspection | 5 |  | 90028297_0030 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000253830 | S002 | 30 | 30 | 5300019288 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-19 | 257849 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-08-19 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 200161965 | 0010 | 0010 | 200161965 | 4Y INSP EXP 1KM1310 PURGE UNIT | AA53.1KM1310PAP | PANEL,CTRL UNIT EEX P PURGE 1KM1310 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10541277 | REGULATOR,FLT;40 UM,EXPO EXS0015275 | 1 | EA | 5 | 0 | 0 | 0 |  | 19.12 - SOH @ AA02 | Supply for Order 200161965, Item 1 cannot be changed 90028297 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019288 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028297 | 07 | Execution | 0000257849 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-18 | ODST-0090028297_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KM1310PAP |  | 0 | 2 | 0 | 90028297 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541277 | REGULATOR,FLT;40 UM,EXPO EXS0015275 | 2024-12-18 | W |  | 0010 | Carry out 4Y Exp Inspection | INT | Carry out 4Y Exp Inspection | 5 |  | 90028297_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000253830 | S002 | 30 | 30 | 5300019288 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-19 | 257849 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-08-19 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 200161965 | 0010 | 0070 | 200161965 | 4Y INSP EXP 1KM1310 PURGE UNIT | AA53.1KM1310PAP | PANEL,CTRL UNIT EEX P PURGE 1KM1310 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10541278 | SENSOR,PRESS;EXPO EXS0030016 | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.02 - SOH @ AA01 | Supply for Order 200161965, Item 7 cannot be changed 90028297 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019288 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028297 | 07 | Execution | 0000257849 | 7 | 0 | EA | 101000000142537 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-18 | ODST-0090028297_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KM1310PAP |  | 0 | 2 | 0 | 90028297 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541278 | SENSOR,PRESS;EXPO EXS0030016 | 2024-12-18 | W |  | 0010 | Carry out 4Y Exp Inspection | INT | Carry out 4Y Exp Inspection | 5 |  | 90028297_0070 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000253830 | S002 | 30 | 30 | 5300019288 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-19 | 257849 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-08-19 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 200161965 | 0010 | 0040 | 200161965 | 4Y INSP EXP 1KM1310 PURGE UNIT | AA53.1KM1310PAP | PANEL,CTRL UNIT EEX P PURGE 1KM1310 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10541279 | INDICATOR,ELEC;RED/GRN,EXPO EXS0015109 | 1 | EA | 1 | 0 | 0 | 1 | EA | 21.01 - SOH @ AA02 | Supply for Order 200161965, Item 4 cannot be changed 90028297 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019288 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028297 | 07 | Execution | 0000257849 | 4 | 0 | EA | 101000000136285 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-18 | ODST-0090028297_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KM1310PAP |  | 0 | 2 | 0 | 90028297 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541279 | INDICATOR,ELEC;RED/GRN,EXPO EXS0015109 | 2024-12-18 | W |  | 0010 | Carry out 4Y Exp Inspection | INT | Carry out 4Y Exp Inspection | 5 |  | 90028297_0040 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000253830 | S002 | 30 | 30 | 5300019288 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-19 | 257849 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-08-19 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 200161965 | 0010 | 0050 | 200161965 | 4Y INSP EXP 1KM1310 PURGE UNIT | AA53.1KM1310PAP | PANEL,CTRL UNIT EEX P PURGE 1KM1310 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10541290 | INDICATOR,ELEC;BLK/YLW,EXPO EXS0015077 | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200161965, Item 5 cannot be changed 90028297 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019288 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028297 | 07 | Execution | 0000257849 | 5 | 0 | EA | 101000000136286 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-18 | ODST-0090028297_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KM1310PAP |  | 0 | 2 | 0 | 90028297 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541290 | INDICATOR,ELEC;BLK/YLW,EXPO EXS0015077 | 2024-12-18 | W |  | 0010 | Carry out 4Y Exp Inspection | INT | Carry out 4Y Exp Inspection | 5 |  | 90028297_0050 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000253830 | S002 | 30 | 30 | 5300019288 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-19 | 257849 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2380 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10541397 | GASKET;KAMMPROFILE,316L/GRAPHITE,70X44 | 8 | EA | 8 | 0 | 0 | 8 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 530 cannot be changed 90028419 item 3850 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 530 | 0 | EA | 102000000030491 | 101000000135632 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3850 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10541397 | GASKET;KAMMPROFILE,316L/GRAPHITE,70X44 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_3850 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 530 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3880 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-03-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005190 | 0010 | 0050 | 500005190 | KGP 2025 Rotating Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 30 | No Issue identified | 10542833 | TAPE,ADH;PVC,WATERPROOF,3M 70006748027 | 100 | EA | 0 | 0 | 10 | 0 |  | 07.03 - PR 2000283775 RFQ |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022062 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032308 | 05 | Preparation | 0000299465 | 5 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2025-03-05 | ODST-0090032308_0050 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-12 | 0 |  | 2025-03-27 |  | 2025-04-01 |  |  | 0 | 2 | 0 | 90032308 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10542833 | TAPE,ADH;PVC,WATERPROOF,3M 70006748027 |  |  |  | 0010 | KGP 2025 Rotating Consumables | NCNF | KGP 2025 Rotating Consumables |  |  | 90032308_0050 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 5 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000292874 | S002 | 30 | 30 | 5300022062 | 50 |  |  | 0 | 100 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2025-03-05 | 299465 | 0 | 0 |  | 1020 | 3 |  |  | 5 | Low | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN1 | Released | 2024-09-19 | 2025-03-01 | 2025-02-20 | 2025-03-02 | 2025-05-31 | INLEC | 100082423 | 0010 | 0040 | 100082423 | $AS OPSD- 1KT1450 Load Comp Flame Det | AA53.160XE646A | DET,UV FLAME 1KT1450 LOAD COMPARTMENT | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.02.2025) | 10543122 | HSG:TX;PRESS,EX,EMERSON 300S1KFIG | 2 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 11.04.25 PO 4500048436 EMERSON CPT | Supply for Order 100082423, Item 5 cannot be changed 90031307 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 30 | AA01 | 5300021566 | 10 | CPT | 7 | 1000030422 | 5 | 30000401 | EMERSON PROCESS MANAGEMENT AUSTRALIA PTY LTD | 4500048436 | 20 | 2 | EA | 2025-03-28 |  |  |  | 90031307 | 07 | Execution | 0000255519 | 5 | 0 | [8 empty] | WorkPackLink |  | P19 FL Inlec | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-20 | ODST-0090031307_0010 | 0 | 51 | 41 | 51 | 2025-03-31 | 2025-02-22 | AA53 | 2024-10-19 |  |  | 2025-04-21 | 2025-04-02 | 2025-04-16 |  |  | 2025-05-31 | 0 |  | 2025-02-20 |  | 2025-03-06 | 3051S |  | 0 | 2 | 2 | 90031307 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543122 | HSG:TX;PRESS,EX,EMERSON 300S1KFIG | 2025-02-20 | W |  | 0010 | $AS OPSD- 1KT1450 Load Comp Flame Det | INT | $AS OPSD- 1KT1450 Load Comp Flame Det |  | Opportune Shutdown | 90031307_0010 |  |  | LN1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-21 | 5 | 6000015801 | 2025-04-02 | 0 |  | 0 |  | 25SDLN1 | MJ |  | AU1009 | 1000251657 | S001 | 30 | 30 | 5300015069 | 20 |  | 5300021566 | 10 | 2 | EA | 1001 | AA02 | 2025-02-20 |  | Opportune Shutdown |  | AU00 | 1070 |  | 2024-10-19 | 1001 | Woodside Energy Ltd | W001 | WOPFN4 | 2024-08-09 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-02 | 2025-03-02 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Job In Process/Material shortage/Partially confirmed/Date set by external system | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-11-29 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100033133 | 0020 | 0020 | 100033133 | Repl Shuttle Vlv For Mini Purge 4KM1430 | AA53.4KM1430 | MOTOR,HV,MR TRAIN STARTER/HELPER,4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(28.10.2024) | 10543368 | VALVE,PNEU;0.125",METALWORK 7010011100 | 1 | EA | 1 | 0 | 1 | 1 | EA | 29.01 - At KGP | Supply for Order 100033133, Item 2 cannot be changed 180112507 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017040 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180112507 | 9023982 | 05 | Preparation | 0000131665 | 2 | 0 | EA |  |  | 102000000029087 |  |  |  |  | WorkPackLink | KSF-POP-JOB-BENCH | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-29 | GRST-5000346528_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  | 100000050188 | 1020 | 2025-11-30 | 1 |  | 2025-01-08 | 4900205148_2025_0001 | 2025-03-01 | 4KM1430 | 5000346528_2025_0001 | 0 | 2 | 0 | 90025085 | 1 | 0 | 180112507 | 2 | 0 | 0 | X | L | 4900205148 | 2025 |  | 5000346528 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543368 | VALVE,PNEU;0.125",METALWORK 7010011100 | 2024-10-28 | W |  | 0020 | Vendor Support | ENON | Vendor Support |  |  | 9023982_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000131035 | S002 | 30 | 30 | 5300017040 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131665 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-11-29 | 2025-05-08 | 2025-01-07 | 2025-05-08 | 2025-05-08 | INLEC | 100033133 | 0020 | 0030 | 100033133 | Repl Shuttle Vlv For Mini Purge 4KM1430 | AA53.4KM1430 | MOTOR,HV,MR TRAIN STARTER/HELPER,4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 10543368 | VALVE,PNEU;0.125",METALWORK 7010011100 | 1 | EA | 1 | 0 | 1 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 100033133, Item 3 cannot be changed 90027986 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017040 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90027986 | 05 | Preparation | 0000131665 | 3 | 0 | EA | 101000000135558 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-29 | ODST-0090027986_0010 | 0 | 0 | 0 | 0 |  | 2025-01-05 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-11-30 | 0 |  | 2025-01-07 |  | 2025-01-12 | 4KM1430 |  | 0 | 2 | 0 | 90027986 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-01-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543368 | VALVE,PNEU;0.125",METALWORK 7010011100 | 2025-01-07 | W |  | 0020 | Vendor Support | ENON | Vendor Support |  |  | 90027986_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000131035 | S002 | 30 | 30 | 5300017040 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-01-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131665 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0080 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(03.12.2024) | 10543776 | CABLE:EXTN,4500mm,5MM X 8MM,BAKER HUGHES | 12 | EA | 0 | 0 | 12 | 12 | EA | 20.02 - SOH @ AA01 | Supply for Order 200063883, Item 33 cannot be changed 90029078 item 10 already exists | Material work-packed @AA53 | SP97 | Direct Multi-base | 140 | AA02 | 5300014051 | 280 | FCA | 7 | 1000024997 | 33 | 30002170 | BAKER HUGHES DIGITAL SOLUTIONS AUST PTY LTD | 4500039606 | 10 | 12 | EA | 2025-02-21 |  | 180126915 | 180130393 | 9028217 | 05 | Preparation | 0000098185 | 33 | 0 | EA | 102000000033941 |  | 107000000000758 |  |  |  | GT8 2025 | WorkPackLink | P07-WAREHOUSE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-08-13 | GRST-5000420150_2025 | 0 | 80 | 78 | 80 | 2025-04-29 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-05-18 | 2025-05-01 | 2025-05-15 | 100000059290 | 1020 | 2024-10-06 | 12 | 5000409355_2025_0001 | 2025-02-27 | 4900251092_2025_0001 | 2025-02-20 | GT4008 | 5000420150_2025_0001 | 0 | 2 | 2 | 90028271 | 12 | 12 | 180130393 | 2 | 0 | 0 | X | L | 4900251092 | 2025 | 5000409355 | 5000420150 | 2025 | 2025 | 180126915 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 2001 | 10543776 | CABLE:EXTN,4500mm,5MM X 8MM,BAKER HUGHES | 2024-12-03 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 9028217_0070 |  |  | UT1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-12-03 | 20 | 6000012887 | 2025-05-01 | 33 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 280 |  | 5300018701 | 10 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0080 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 1000 | EA | 1000 | 5000 | 2602 | 100 | EA | 29.01 - At KGP | Supply for Order 200089373, Item 8 cannot be changed 180104650 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121315 | 9026646 | 07 | Execution | 0000127667 | 8 | 0 | EA | 101000000132725 |  | 102000000029574 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-P25-STONE-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000385873_2025 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000056056 | 1020 | 2025-12-15 | 1000 |  | 2025-02-04 | 4900190837_2024_0001/4900190826_2024_0001/4900190095_2024_0001/4900226347_2025_0001/4900216423_2025_0001/4900206448_2025_0001 | 2024-11-10 | Troy Mac | 5000318780_2024_0001/5000318763_2024_0001/5000317409_2024_0001/5000385873_2025_0001/5000369393_2025_0001/5000349869_2025_0001 | 0 | 2 | 0 | 90023594 | 1000 | 0 | 180121315/180117498/180113237/180105163/180105165/180104650 | 2 | 0 | 0 | X | L | 4900226347 | 2025 |  | 5000385873 | 2025 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9026646_0080/9026131_0080/9024190_0080/9022419_0080/9022418_0080/9022093_0080 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDFR2 | MJ | 1000004703 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 80 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2024-11-05 |  |  | 2025-01-10 |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0080 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 1000 | EA | 1000 | 5000 | 2602 | 1 | EA | 29.01 - At KGP | Supply for Order 200089373, Item 8 cannot be changed 180104650 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121315 | 9026646 | 07 | Execution | 0000127667 | 8 | 0 | EA |  |  | 101000000119334 |  |  |  |  | WorkPackLink | KSF-P25-STONE-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000385873_2025 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000056056 | 1020 | 2025-12-15 | 1000 |  | 2025-02-04 | 4900190837_2024_0001/4900190826_2024_0001/4900190095_2024_0001/4900226347_2025_0001/4900216423_2025_0001/4900206448_2025_0001 | 2024-11-10 | Troy Mac | 5000318780_2024_0001/5000318763_2024_0001/5000317409_2024_0001/5000385873_2025_0001/5000369393_2025_0001/5000349869_2025_0001 | 0 | 2 | 0 | 90023594 | 1000 | 0 | 180121315/180117498/180113237/180105163/180105165/180104650 | 2 | 0 | 0 | X | L | 4900226347 | 2025 |  | 5000385873 | 2025 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9026646_0080/9026131_0080/9024190_0080/9022419_0080/9022418_0080/9022093_0080 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDFR2 | MJ |  | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 80 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0080 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Voyage arrived: too late to meet planned Reqmt Date | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 1000 | EA | 1000 | 5000 | 2602 | 396 | EA | 29.01 - At KGP | Supply for Order 200089373, Item 8 cannot be changed 180104650 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121315 | 9026646 | 07 | Execution | 0000127667 | 8 | 0 | EA |  |  | 102000000032342 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-P25-STONE-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 | 2025-02-05 |  | Y | 1001 | 2024-11-05 | GRST-5000385873_2025 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000056056 | 1020 | 2025-12-15 | 1000 |  | 2025-02-04 | 4900190837_2024_0001/4900190826_2024_0001/4900190095_2024_0001/4900226347_2025_0001/4900216423_2025_0001/4900206448_2025_0001 | 2024-11-10 | Troy Mac | 5000318780_2024_0001/5000318763_2024_0001/5000317409_2024_0001/5000385873_2025_0001/5000369393_2025_0001/5000349869_2025_0001 | 0 | 2 | 0 | 90023594 | 1000 | 0 | 180121315/180117498/180113237/180105163/180105165/180104650 | 1 | 0 | 0 | X | L | 4900226347 | 2025 |  | 5000385873 | 2025 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9026646_0080/9026131_0080/9024190_0080/9022419_0080/9022418_0080/9022093_0080 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDFR2 | MJ | 1000004988 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 80 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2024-11-05 |  |  | 2025-02-05 |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0080 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 1000 | EA | 1000 | 5000 | 2602 | 1 | EA | 29.01 - At KGP | Supply for Order 200089373, Item 8 cannot be changed 180104650 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121315 | 9026646 | 07 | Execution | 0000127667 | 8 | 0 | EA |  |  | 101000000119338 |  |  |  |  | WorkPackLink | KSF-P25-STONE-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000385873_2025 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000056056 | 1020 | 2025-12-15 | 1000 |  | 2025-02-04 | 4900190837_2024_0001/4900190826_2024_0001/4900190095_2024_0001/4900226347_2025_0001/4900216423_2025_0001/4900206448_2025_0001 | 2024-11-10 | Troy Mac | 5000318780_2024_0001/5000318763_2024_0001/5000317409_2024_0001/5000385873_2025_0001/5000369393_2025_0001/5000349869_2025_0001 | 0 | 2 | 0 | 90023594 | 1000 | 0 | 180121315/180117498/180113237/180105163/180105165/180104650 | 2 | 0 | 0 | X | L | 4900226347 | 2025 |  | 5000385873 | 2025 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9026646_0080/9026131_0080/9024190_0080/9022419_0080/9022418_0080/9022093_0080 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDFR2 | MJ |  | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 80 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0080 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 1000 | EA | 1000 | 5000 | 2602 | 500 | EA | 29.01 - At KGP | Supply for Order 200089373, Item 8 cannot be changed 180104650 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121315 | 9026646 | 07 | Execution | 0000127667 | 8 | 0 | EA |  |  | 101000000135688 |  |  |  |  | WorkPackLink | KSF-P25-STONE-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000385873_2025 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000056056 | 1020 | 2025-12-15 | 1000 |  | 2025-02-04 | 4900190837_2024_0001/4900190826_2024_0001/4900190095_2024_0001/4900226347_2025_0001/4900216423_2025_0001/4900206448_2025_0001 | 2024-11-10 | Troy Mac | 5000318780_2024_0001/5000318763_2024_0001/5000317409_2024_0001/5000385873_2025_0001/5000369393_2025_0001/5000349869_2025_0001 | 0 | 2 | 0 | 90023594 | 1000 | 0 | 180121315/180117498/180113237/180105163/180105165/180104650 | 2 | 0 | 0 | X | L | 4900226347 | 2025 |  | 5000385873 | 2025 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9026646_0080/9026131_0080/9024190_0080/9022419_0080/9022418_0080/9022093_0080 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDFR2 | MJ |  | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 80 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0080 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 1000 | EA | 1000 | 5000 | 2602 | 2 | EA | 29.01 - At KGP | Supply for Order 200089373, Item 8 cannot be changed 180104650 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121315 | 9026646 | 07 | Execution | 0000127667 | 8 | 0 | EA |  |  | 101000000120682 |  |  |  |  | WorkPackLink | KSF-P25-STONE-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000385873_2025 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000056056 | 1020 | 2025-12-15 | 1000 |  | 2025-02-04 | 4900190837_2024_0001/4900190826_2024_0001/4900190095_2024_0001/4900226347_2025_0001/4900216423_2025_0001/4900206448_2025_0001 | 2024-11-10 | Troy Mac | 5000318780_2024_0001/5000318763_2024_0001/5000317409_2024_0001/5000385873_2025_0001/5000369393_2025_0001/5000349869_2025_0001 | 0 | 2 | 0 | 90023594 | 1000 | 0 | 180121315/180117498/180113237/180105163/180105165/180104650 | 2 | 0 | 0 | X | L | 4900226347 | 2025 |  | 5000385873 | 2025 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543845 | WASHER,SEAL;12MM,SS,BLK,10/12G | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9026646_0080/9026131_0080/9024190_0080/9022419_0080/9022418_0080/9022093_0080 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDFR2 | MJ |  | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 80 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147457 | 0010 | 0010 | 200147457 | 6M Fire & Gas Function Test (20) GT4007 | AA53.760QZ661A | PANEL,GAS GT4007 VENT AIR DISCH REM DISP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10544152 | FILTER;DRAEGER 6811890 | 9 | EA | 61 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 200147457, Item 1 cannot be changed 90024981 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009779 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024981 | 05 | Preparation | 0000235867 | 1 | 0 | EA | 102000000030051 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024981_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024981 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544152 | FILTER;DRAEGER 6811890 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 3 |  | 90024981_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232873 | S002 | 30 | 30 | 5300009779 | 10 |  |  | 0 | 9 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235867 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147457 | 0010 | 0010 | 200147457 | 6M Fire & Gas Function Test (20) GT4007 | AA53.760QZ661A | PANEL,GAS GT4007 VENT AIR DISCH REM DISP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10544152 | FILTER;DRAEGER 6811890 | 9 | EA | 61 | 0 | 0 | 2 | EA | 02.03 - SOH @ AA02 | Supply for Order 200147457, Item 1 cannot be changed 90024981 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009779 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024981 | 05 | Preparation | 0000235867 | 1 | 0 | EA | 101000000135667 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024981_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024981 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544152 | FILTER;DRAEGER 6811890 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 3 |  | 90024981_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232873 | S002 | 30 | 30 | 5300009779 | 10 |  |  | 0 | 9 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235867 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147457 | 0010 | 0010 | 200147457 | 6M Fire & Gas Function Test (20) GT4007 | AA53.760QZ661A | PANEL,GAS GT4007 VENT AIR DISCH REM DISP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10544152 | FILTER;DRAEGER 6811890 | 9 | EA | 61 | 0 | 0 | 6 | EA | 02.03 - SOH @ AA02 | Supply for Order 200147457, Item 1 cannot be changed 90024981 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009779 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024981 | 05 | Preparation | 0000235867 | 1 | 0 | EA | 102000000033546 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024981_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024981 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544152 | FILTER;DRAEGER 6811890 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 3 |  | 90024981_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232873 | S002 | 30 | 30 | 5300009779 | 10 |  |  | 0 | 9 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235867 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147458 | 0010 | 0010 | 200147458 | 6M F&G Function Check(20) GT4008 | AA53.860QZ661A | PANEL,GAS GT4008 VENT AIR DISCH REM DISP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10544152 | FILTER;DRAEGER 6811890 | 9 | EA | 61 | 0 | 0 | 8 | EA | 02.03 - SOH @ AA02 | Supply for Order 200147458, Item 1 cannot be changed 90024982 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009780 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024982 | 05 | Preparation | 0000235868 | 1 | 0 | EA | 102000000027965 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024982_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024982 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544152 | FILTER;DRAEGER 6811890 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT / MITR | INT | Function Test & Complete PRT / MITR | 3 |  | 90024982_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232874 | S002 | 30 | 30 | 5300009780 | 10 |  |  | 0 | 9 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235868 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147458 | 0010 | 0010 | 200147458 | 6M F&G Function Check(20) GT4008 | AA53.860QZ661A | PANEL,GAS GT4008 VENT AIR DISCH REM DISP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10544152 | FILTER;DRAEGER 6811890 | 9 | EA | 61 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 200147458, Item 1 cannot be changed 90024982 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009780 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024982 | 05 | Preparation | 0000235868 | 1 | 0 | EA | 102000000030048 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024982_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024982 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544152 | FILTER;DRAEGER 6811890 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT / MITR | INT | Function Test & Complete PRT / MITR | 3 |  | 90024982_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232874 | S002 | 30 | 30 | 5300009780 | 10 |  |  | 0 | 9 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235868 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147459 | 0010 | 0010 | 200147459 | 6M F&G Function Check (18) - GT4009 | AA53.960QZ661A | PANEL,GAS GT4009 VENT AIR DISCH REM DISP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10544152 | FILTER;DRAEGER 6811890 | 9 | EA | 61 | 0 | 0 | 9 | EA | 02.03 - SOH @ AA02 | Supply for Order 200147459, Item 1 cannot be changed 90024983 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009781 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024983 | 05 | Preparation | 0000235869 | 1 | 0 | EA | 102000000030049 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024983_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4009 F&G |  | 0 | 2 | 0 | 90024983 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544152 | FILTER;DRAEGER 6811890 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT / MITR,s | INT | Function Test & Complete PRT / MITR,s | 3 |  | 90024983_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232875 | S002 | 30 | 30 | 5300009781 | 10 |  |  | 0 | 9 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235869 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-08-10 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200161133 | 0010 | 0010 | 200161133 | Fire & Gas Function Test (2) GT4007 | AA53.60UB2121 | ALARM,GAS HORN AUDIBLE G4007 GENERATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.08.2024) | 10544152 | FILTER;DRAEGER 6811890 | 1 | EA | 61 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 200161133, Item 1 cannot be changed 90024994 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013892 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024994 | 05 | Preparation | 0000256561 | 1 | 0 | EA | 102000000033483 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-10 | ODST-0090024994_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024994 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544152 | FILTER;DRAEGER 6811890 | 2024-08-10 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 3 |  | 90024994_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000252631 | S002 | 30 | 30 | 5300013892 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240810 | 2024-08-10 | 256561 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-08-10 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200161134 | 0010 | 0010 | 200161134 | 1Y F&G F/Check (2) GT4008 | AA53.60UB2221 | ALARM,GAS HORN AUDIBLE G4008 GENERATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.08.2024) | 10544152 | FILTER;DRAEGER 6811890 | 1 | EA | 61 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 200161134, Item 1 cannot be changed 90024995 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013893 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024995 | 05 | Preparation | 0000256562 | 1 | 0 | EA | 102000000030050 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-10 | ODST-0090024995_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024995 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544152 | FILTER;DRAEGER 6811890 | 2024-08-10 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 3 |  | 90024995_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000252632 | S002 | 30 | 30 | 5300013893 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240810 | 2024-08-10 | 256562 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0020 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(02.03.2025) | 10544341 | BLD:BANDSAW,1140mm | 1 | EA | 0 | 0 | 0 | 0 |  | 10.03 - DEL: 80033797 | Supply for Order 500005166, Item 55 cannot be changed 90032306 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 55 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0010 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | BMccrum |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10544341 | BLD:BANDSAW,1140mm | 2025-03-02 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0010 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 55 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 500 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN4 | Released | 2024-01-02 | 2025-02-24 | 2025-02-19 | 2025-03-11 | 2025-05-07 | INLEC | 100042936 | 0010 | 0020 | 100042936 | $AS OPSD 1 MCU Repair 4KT1430KM3A | AA53.4KT1430KM3A | MOTOR,BLOWER EXHAUST FRAME 4KT1430 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.08.2024) | 10545039 | SWITCHGEAR:DIGITAL,LV,MLINK,WITH-MOXA-CP | 2 | EA | 2 | 0 | 0 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 100042936, Item 3 cannot be changed 90026424 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014765 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90026424 | 07 | Execution | 0000141420 | 3 | 0 | EA | 102000000030778 | 101000000134661 | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-08-28 | ODST-0090026424_0010 | 0 | 0 | 0 | 0 |  | 2025-02-22 | AA53 | 2025-05-07 |  |  | 2025-02-24 |  |  |  |  | 2021-04-11 | 0 |  | 2025-02-19 |  | 2025-02-24 |  |  | 0 | 2 | 0 | 90026424 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10545039 | SWITCHGEAR:DIGITAL,LV,MLINK,WITH-MOXA-CP | 2024-08-28 | W |  | 0010 | $AS - FL - 4KT1430KM3A Comms fault | INT | $AS - FL - 4KT1430KM3A Comms fault |  | Opportune Shutdown/Engineering Query/Management of Change | 90026424_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000140831 | S002 | 30 | 30 | 5300014765 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-19 |  | Opportune Shutdown/Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141420 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-07 | 2025-03-11 | 2025-03-11 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-02-24 |  | 2025-03-11 | 2025-05-07 | INLEC | 100042936 | 0010 | 0010 | 100042936 | $AS OPSD 1 MCU Repair 4KT1430KM3A | AA53.4KT1430KM3A | MOTOR,BLOWER EXHAUST FRAME 4KT1430 | AA01 | 10 | WO item has not been released yet | 10545039 | SWITCHGEAR:DIGITAL,LV,MLINK,WITH-MOXA-CP | 2 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000141420 | 1 | 0 | [8 empty] | WorkPackLink |  | P07 - OPSD | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-07 |  |  | 2025-02-24 |  |  |  |  | 2021-04-11 | 0 |  |  |  |  | 4KT1430KM3A |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10545039 | SWITCHGEAR:DIGITAL,LV,MLINK,WITH-MOXA-CP |  |  |  | 0010 | $AS - FL - 4KT1430KM3A Comms fault | INT | $AS - FL - 4KT1430KM3A Comms fault |  | Opportune Shutdown/Engineering Query/Management of Change |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000140831 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Opportune Shutdown/Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-07 | 2025-03-11 | 2025-03-11 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-02-07 | 2025-01-31 | 2025-02-07 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0010 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(07.02.2025) | 10545764 | VALVE,SLND;BIFOLD FP06PS10432NUV77A24D35 | 2 | EA | 0 | 0 | 0 | 0 |  | 21.02 - ETA 01.05.25 PO 4500046940 ROTORK CRITICAL CPT | Supply for Order 600001473, Item 1 cannot be changed 90030516 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020972 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030516 | 05 | Preparation | 0000084391 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030516_0010 | 0 | 12 | 0 | 0 |  | 2025-01-29 | AA53 | 2025-05-08 |  |  | 2025-02-12 |  |  |  |  | 2025-12-15 | 0 |  | 2025-02-07 |  | 2025-02-12 | 4V1302 |  | 0 | 2 | 0 | 90030516 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-07 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10545764 | VALVE,SLND;BIFOLD FP06PS10432NUV77A24D35 | 2025-02-07 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90030516_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083795 | S002 | 30 | 30 | 5300020972 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-07 |  | Engineering Query/Management of Change |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84391 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
| 25SDLN4 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 200083915 | 0010 | 0010 | 200083915 | 4Y Repl Purge Air L/Switch (8) KT1410/30 | AA53.414GEO40A | SW,PROX PURGE AIR VALVE VA13-3 OPEN | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(15.10.2024) | 10547257 | SWITCH,MICRO;15A,125VAC,SPDT,V71C17D8201 | 3 | EA | 5 | 0 | 0 | 2 | EA | 02.03 - SOH @ AA02 | Supply for Order 200083915, Item 5 cannot be changed 90024960 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004053 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024960 | 05 | Preparation | 0000121941 | 5 | 0 | EA | 102000000029158 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024960_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2024-05-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 4K1410/30 |  | 0 | 2 | 0 | 90024960 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10547257 | SWITCH,MICRO;15A,125VAC,SPDT,V71C17D8201 | 2024-10-15 | W |  | 0010 | Isolate 414GEO40A & 414GEC40A | INT | Isolate 414GEO40A & 414GEC40A | 5 |  | 90024960_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000121313 | S002 | 30 | 30 | 5300004053 | 50 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121941 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 200083915 | 0010 | 0010 | 200083915 | 4Y Repl Purge Air L/Switch (8) KT1410/30 | AA53.414GEO40A | SW,PROX PURGE AIR VALVE VA13-3 OPEN | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(15.10.2024) | 10547257 | SWITCH,MICRO;15A,125VAC,SPDT,V71C17D8201 | 3 | EA | 5 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 200083915, Item 5 cannot be changed 90024960 item 10 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300004053 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024960 | 05 | Preparation | 0000121941 | 5 | 0 | EA | 102000000031496 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024960_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2024-05-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 4K1410/30 |  | 0 | 2 | 0 | 90024960 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10547257 | SWITCH,MICRO;15A,125VAC,SPDT,V71C17D8201 | 2024-10-15 | W |  | 0010 | Isolate 414GEO40A & 414GEC40A | INT | Isolate 414GEO40A & 414GEC40A | 5 |  | 90024960_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000121313 | S002 | 30 | 30 | 5300004053 | 50 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121941 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-03-01 |  | 2025-05-08 | 2025-05-08 | INLEC | 200083915 | 0010 | 0020 | 200083915 | 4Y Repl Purge Air L/Switch (8) KT1410/30 | AA53.414GEO40A | SW,PROX PURGE AIR VALVE VA13-3 OPEN | AA01 | 10 | WO item has not been released yet | 10547257 | SWITCH,MICRO;15A,125VAC,SPDT,V71C17D8201 | 5 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121941 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2024-05-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10547257 | SWITCH,MICRO;15A,125VAC,SPDT,V71C17D8201 |  |  |  | 0010 | Isolate 414GEO40A & 414GEC40A | INT | Isolate 414GEO40A & 414GEC40A | 5 |  |  |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000121313 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-10-28 | 2025-03-01 | 2025-02-24 | 2025-02-23 | 2025-03-14 | ROTAT | 200091127 | 0180 | 0010 | 200091127 | 5Y RE SD 1K2301 COMPR MAJOR LABOUR | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 10547404 | GAUGE,TEMP;100MM,BADOTHERM BDTG18 | 2 | EA | 1 | 0 | 0 | 1 | EA | 05.03 - SOH @ AA02 QTY 1 TO COME THROUGH | Supply for Order 200091127, Item 1 cannot be changed 90028301 item 10 already exists | Material picked; currently at SW3R02B02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019733 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028301 | 05 | Preparation | 0000129421 | 1 | 0 | EA |  |  | 102000000034184 |  |  |  |  | WorkPackLink | SW3R02B02B | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028301_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-19 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123TG06 |  | 0 | 2 | 0 | 90028301 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10547404 | GAUGE,TEMP;100MM,BADOTHERM BDTG18 | 2025-01-07 | W |  | 0180 | INSTALL & SET UP ALL INSTRUMENTATION | INT | INSTALL & SET UP ALL INSTRUMENTATION | 5 | Ready for Release | 90028301_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128790 | S002 | 30 | 30 | 5300019733 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129421 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-14 | 2025-02-23 | 2025-02-23 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0100 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue detected, please check message in derivation or orchestration log | 10561537 | BAG TOOL | 1 | EA | 0 | 0 | 0 | 0 |  | 07.03 - PR 2000283125 RFQ | Supply for Order 500005166, Item 64 cannot be changed 90032306 item 80 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 64 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0080 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Scot.K |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561537 | BAG TOOL | 2025-03-03 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0080 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 64 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 570 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD4401 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-04 | 2025-03-08 | INLEC | 100039667 | 0010 | 0130 | 100039667 | MOC-141259 TX Replace 144PT059 | AA53.144PT059 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10561791 | CVR:CURRENT,EMERSON RMTSUNSS245015RMTBRK | 1 | EA | 3 | 2 | 2 | 1 | EA | 19.02 - At KGP | Supply for Order 100039667, Item 13 cannot be changed 90023934 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017556 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122923 | 9027008 | 05 | Preparation | 0000138171 | 13 | 0 | EA | 102000000030711 | 101000000134669 | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000391252_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-04 |  |  | 2024-12-01 |  |  | 100000056805 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230046_2025_0003 | 2024-12-01 | 144PT059 | 5000391252_2025_0002 | 0 | 2 | 0 | 90023934 | 1 | 0 | 180122923 | 2 | 0 | 0 | X | L | 4900230046 | 2025 |  | 5000391252 | 2025 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561791 | CVR:CURRENT,EMERSON RMTSUNSS245015RMTBRK | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9027008_0060 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 13 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137582 | S002 | 30 | 30 | 5300017556 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138171 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-08 | 2025-03-04 | 2025-03-04 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-01 | INLEC | 100047874 | 0010 | 0060 | 100047874 | MOC-124841 Transmitter Replace 114PT87 | AA53.114PIC87 | LOOP,CTRL PRESS TO E1409 SHELL OUTLET | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10561791 | CVR:CURRENT,EMERSON RMTSUNSS245015RMTBRK | 1 | EA | 3 | 2 | 2 | 1 | EA | 29.01 - At KGP | Supply for Order 100047874, Item 6 cannot be changed 180101033 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017557 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180101033 | 9021092 | 05 | Preparation | 0000146415 | 6 | 0 | EA | 102000000025735 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000306138_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000044352 | 1020 | 2022-11-30 | 1 |  | 2024-12-04 | 4900185079_2024_0001 | 2024-12-01 | 114PT87 | 5000306138_2024_0001 | 0 | 2 | 0 | 90023935 | 1 | 0 | 180101033 | 2 | 0 | 0 | X | L | 4900185079 | 2024 |  | 5000306138 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561791 | CVR:CURRENT,EMERSON RMTSUNSS245015RMTBRK | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works | 5 |  | 9021092_0060 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000145844 | S002 | 30 | 30 | 5300017557 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146415 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100085112 | 0020 | 0060 | 100085112 | MOC-150252: Flow TX's Repl (2) 44FT21L/H | AA53.44FT21L | TX,FLOW LP FUEL GAS TO HEADER | AA01 | 20 | No issue identified | 10561791 | CVR:CURRENT,EMERSON RMTSUNSS245015RMTBRK | 2 | EA | 3 | 2 | 2 | 1 | EA | 09.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021006 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030534 | 05 | Preparation | 0000267756 | 7 | 0 | EA | 101000000146013 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-08 | ODST-0090030534_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 44FT21L/H |  | 0 | 2 | 0 | 90030534 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561791 | CVR:CURRENT,EMERSON RMTSUNSS245015RMTBRK |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030534_0060 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000262795 | S002 | 30 | 30 | 5300021006 | 60 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267756 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Printed/Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100085112 | 0020 | 0060 | 100085112 | MOC-150252: Flow TX's Repl (2) 44FT21L/H | AA53.44FT21L | TX,FLOW LP FUEL GAS TO HEADER | AA01 | 20 | No issue identified | 10561791 | CVR:CURRENT,EMERSON RMTSUNSS245015RMTBRK | 2 | EA | 3 | 2 | 2 | 1 | EA | 09.02 - SOH @ AA02 |  | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021006 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030534 | 05 | Preparation | 0000267756 | 7 | 0 | EA | 101000000141189 |  | 101000000141502 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  | 2025-02-07 | Y | 1001 | 2025-02-08 | ODST-0090030534_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 44FT21L/H |  | 0 | 2 | 0 | 90030534 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561791 | CVR:CURRENT,EMERSON RMTSUNSS245015RMTBRK |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030534_0060 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDDG1 | MJ | 20005067 | AU1072 | 1000262795 | S002 | 30 | 30 | 5300021006 | 60 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change | 2025-02-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267756 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Printed/Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0160 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10562101 | BANDING;SS316L,19MM,0.5MM | 5 | ROL | 21 | 0 | 2 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 16 cannot be changed 90032376 item 160 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 16 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0160 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10562101 | BANDING;SS316L,19MM,0.5MM | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0160 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 16 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 160 |  |  | 0 | 5 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0170 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10562101 | BANDING;SS316L,19MM,0.5MM | 12 | ROL | 21 | 0 | 2 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 37 cannot be changed 90031501 item 190 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 37 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0190 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10562101 | BANDING;SS316L,19MM,0.5MM | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0190 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 37 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 330 |  |  | 0 | 12 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN4 | Released | 2025-02-07 | 2025-02-17 | 2025-02-13 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0080 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.02.2025) | 10562140 | BUSH,CONDUIT;50MM,ABS,CABLE PROT | 50 | EA | 10 | 0 | 40 | 0 |  | 24.02 - ETA 14.03.25 PO 4500046920 MM CPT | Supply for Order 600001473, Item 9 cannot be changed 90030804 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020972 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030804 | 05 | Preparation | 0000084391 | 9 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030804_0030 | 0 | 1 | 0 | 0 |  | 2025-02-15 | AA53 | 2025-05-08 |  |  | 2025-02-18 |  |  |  |  | 2025-12-15 | 0 |  | 2025-02-13 |  | 2025-02-18 | 4V1302 |  | 0 | 2 | 0 | 90030804 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-13 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10562140 | BUSH,CONDUIT;50MM,ABS,CABLE PROT | 2025-02-13 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90030804_0030 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083795 | S002 | 30 | 30 | 5300020972 | 80 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-02-13 |  | Engineering Query/Management of Change |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84391 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0090 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10564597 | MAINTENANCE KIT,CLUTCH,FLENDER N160SM17+ | 1 | EA | 0 | 0 | 0 | 0 |  | 20.11 - ETA 04.03.25 PO 4500034833 BH | Supply for Order 200063883, Item 9 cannot be changed 90024996 item 70 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 9 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090024996_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10564597 | MAINTENANCE KIT,CLUTCH,FLENDER N160SM17+ | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 90024996_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-03-04 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0095 | 0070 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | PR due for release | 10564972 | COOLANT;PREMIXED,ALFLOC 3443,1000L | 1 | EA | 0 | 0 | 0 | 0 |  | 04.03 - PR 1000031160 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 48 | AA01 | 5300015752 | 40 |  | 14 | 1000031160 | 161 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032159 | 05 | Preparation | 0000129360 | 161 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-25 | PRPO-1000031160_00161 | 0 | 76 | 57 | 68 | 2025-04-28 | 2025-03-02 | AA53 | 2025-03-01 |  |  | 2025-05-24 | 2025-04-30 | 2025-05-11 |  |  | 2023-04-03 | 0 |  | 2025-03-04 |  | 2025-03-15 |  |  | 0 | 2 | 2 | 90032159 | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10564972 | COOLANT;PREMIXED,ALFLOC 3443,1000L |  |  |  | 0095 | COOLING WATER | INT | COOLING WATER |  |  | 90032159_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-04 | 20 |  | 2025-04-30 | 0 |  | 0 |  | 25SD2301 | MJ |  | AU1009 | 1000128789 | S001 | 30 | 30 | 5300004361 | 1310 |  | 5300015752 | 40 | 1 | EA | 1001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-01-01 | 2024-03-31 | 2024-03-28 | 2025-03-02 | 2025-05-09 | INLEC | 100035833 | 0020 | 0040 | 100035833 | OPSD - Replace 414FV055A/65A feedback ar | AA53.414FV055A | VALVE,FLOW CTRL GT1420A HVY MR TO E1450A | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2024) | 10565690 | MOUNTING KIT;SS316,VALTEK 164437150000 | 2 | EA | 0 | 0 | 0 | 2 | EA | 2000032246/00010 | Supply for Order 100035833, Item 4 cannot be changed 180083298 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300007533 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180083298 | 9016567 | 07 | Execution | 0000134354 | 4 | 0 | EA |  |  | 102000000021136 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP-RUNNER-SML | P19 FL INLEC | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-03-06 |  | 0 | 0 | 0 | 0 |  | 2024-03-29 | AA53 | 2025-03-02 |  |  | 2024-03-31 |  |  | 100000035687 | 1020 | 2023-12-30 | 2 |  | 2024-10-18 | 4900154922_2024_0001 | 2024-03-31 |  | 5000248772_2024_0001 | 0 | 2 | 0 | 90004428 | 2 | 0 | 180083298/180083312 | 2 | 0 | 0 | X | L | 4900154922 | 2024 |  | 5000248772 | 2024 | 0 |  | 2024-03-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10565690 | MOUNTING KIT;SS316,VALTEK 164437150000 | 2024-03-06 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 | Opportune Shutdown | 9016567_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN4 | MJ | 1000003714 | AU1072 | 1000133783 | S002 | 30 | 30 | 5300007533 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-03-28 |  | Opportune Shutdown | 2024-10-19 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134354 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-09 | 2025-03-02 | 2025-03-02 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Goods movement posted/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-08-15 | 2025-03-01 | 2025-02-24 | 2025-02-19 | 2025-03-03 | MECH | 600003215 | 0020 | 0010 | 600003215 | MOC-117109 1E1303 Exchanger Replacement | AA53.1E1303 | EXCH,HEAT AIR COOL REGENERATION GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.08.2024) | 10566416 | BUNDLE ASY,TBE;ACHE,1-E1303 | 1 | EA | 0 | 0 | 0 | 0 |  | 20.12 - ETA 01.05.25 PO 4500025225 TASOCS CPT | Supply for Order 600003215, Item 1 cannot be changed 90024997 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300014126 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024997 | 07 | Execution | 0000254308 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-15 | ODST-0090024997_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | CRITICAL |  | 0 | 2 | 0 | 90024997 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10566416 | BUNDLE ASY,TBE;ACHE,1-E1303 | 2024-08-14 | W |  | 0020 | Remove blanks For Inspection Access | INT | Remove blanks For Inspection Access |  | Management of Change | 90024997_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000250524 | S002 | 30 | 30 | 5300014126 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W35069 | 2024-08-01 | 254308 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-02-19 | 2025-02-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0140 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.03.2025) | 10567752 | BLOCK,TERM;800V,CER,WEIDMULLER SAKK4950+ | 50 | EA | 100 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 500005166, Item 68 cannot be changed 90032306 item 110 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 68 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0110 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Bmccrum |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10567752 | BLOCK,TERM;800V,CER,WEIDMULLER SAKK4950+ | 2025-03-05 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0110 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 68 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 610 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0300 | 0040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10569266 | RING;V,75MM,STATEWIDE BEARINGS V75S | 1 | EA | 1 | 0 | 1 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 720 cannot be changed 90028419 item 4830 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 720 | 0 | EA | 102000000030388 | 101000000135503 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4830 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10569266 | RING;V,75MM,STATEWIDE BEARINGS V75S | 2024-07-21 | W |  | 0300 | STARTER MOTOR M7 | INT | STARTER MOTOR M7 |  |  | 90028419_4830 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 720 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4870 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0300 | 0050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10569267 | RING;V,80MM,STATEWIDE BEARINGS V80S | 1 | EA | 1 | 0 | 1 | 1 | EA | 21.10 - SOH @ AA01 | Supply for Order 200091513, Item 721 cannot be changed 90028419 item 4840 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 721 | 0 | EA | 102000000030388 | 101000000135501 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10569267 | RING;V,80MM,STATEWIDE BEARINGS V80S | 2024-07-21 | W |  | 0300 | STARTER MOTOR M7 | INT | STARTER MOTOR M7 |  |  | 90028419_4840 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 721 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4880 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0650 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10569748 | GASKET,SW;102X130X1.5MM,NP KFZ326620324 | 12 | EA | 40 | 0 | 0 | 12 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 449 cannot be changed 90028419 item 3110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 449 | 0 | EA | 102000000030481 | 102000000030622 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10569748 | GASKET,SW;102X130X1.5MM,NP KFZ326620324 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3110 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 449 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3140 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2430 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10569786 | GASKET;DRN LINE,90X155X15MM,NBR | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 535 cannot be changed 90028419 item 3880 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3910 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 535 | 0 | EA | 102000000030491 | 101000000135633 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3880 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10569786 | GASKET;DRN LINE,90X155X15MM,NBR | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_3880 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 535 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3910 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0180 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10569805 | MATERIAL,SHT;INS,1X15MX1.2MM | 5 | EA | 0 | 0 | 0 | 0 |  | 07.03 - ETA 27.03.25 PO 4500047066 ARMACEL CPT | Supply for Order 100090053, Item 18 cannot be changed 90032376 item 180 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 18 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0180 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10569805 | MATERIAL,SHT;INS,1X15MX1.2MM | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0180 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 18 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 180 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0030 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10569805 | MATERIAL,SHT;INS,1X15MX1.2MM | 15 | EA | 0 | 0 | 0 | 0 |  | 24.02 - ETA 27.03.25 PO 4500047066 ARMACELL AUS CPT | Supply for Order 500005166, Item 22 cannot be changed 90031501 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 22 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 15 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0050 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10569805 | MATERIAL,SHT;INS,1X15MX1.2MM | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0050 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 22 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 190 |  |  | 0 | 15 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2301 | Released | 2024-10-28 | 2025-03-01 | 2025-02-24 | 2025-02-23 | 2025-03-14 | ROTAT | 200091127 | 0180 | 0030 | 200091127 | 5Y RE SD 1K2301 COMPR MAJOR LABOUR | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10570894 | REGULATOR;INSTR,0.25",FISHER 67CF166338> | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 200091127, Item 3 cannot be changed 90028301 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019733 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028301 | 05 | Preparation | 0000129421 | 3 | 0 | EA | 101000000143175 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028301_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-19 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123PCV25 |  | 0 | 2 | 0 | 90028301 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10570894 | REGULATOR;INSTR,0.25",FISHER 67CF166338> | 2025-01-08 | W |  | 0180 | INSTALL & SET UP ALL INSTRUMENTATION | INT | INSTALL & SET UP ALL INSTRUMENTATION | 5 | Ready for Release | 90028301_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128790 | S002 | 30 | 30 | 5300019733 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129421 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-14 | 2025-02-23 | 2025-02-23 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-02-08 | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0050 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.02.2025) | 10572013 | STAND;INSTR,DN50,350X350MM,SNGL,HDG | 2 | EA | 0 | 1 | 0 | 0 |  | 06.03 - ETA 18.04.25 PO 4500048506 BENDIGO METALS CPT | Supply for Order 600001363, Item 12 cannot be changed 90031986 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031986 | 05 | Preparation | 0000084301 | 12 | 0 | [8 empty] | WorkPackLink |  | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-27 | ODST-0090031986_0020 | 0 | 6 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-27 |  |  | 2025-03-05 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-28 |  | 2025-03-05 | Scott Kinloc |  | 0 | 2 | 0 | 90031986 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10572013 | STAND;INSTR,DN50,350X350MM,SNGL,HDG | 2025-02-28 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90031986_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 12 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 | 30 | 30 | 5300018438 | 70 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-28 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147116 | 0020 | 0070 | 200147116 | 3Y Vibration Probe Replace (7) 1KT2420 | AA53.124YE031 | TXDCR,ALARM VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10574752 | PROBE,VIB;BENTLY 33019108561005 | 3 | EA | 1 | 3 | 0 | 3 | EA | 20.11 - SOH @ AA02 | Supply for Order 200147116, Item 7 cannot be changed 9027115 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017864 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027115 | 05 | Preparation | 0000235387 | 7 | 0 | EA | 102000000032160 | 102000000027737 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-14 | GIST-4900234130_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 3 |  | 2025-02-11 | 4900234130_2025_0007 | 2025-03-01 | 1K2420 |  | 0 | 2 | 0 | 90025108 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234130 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10574752 | PROBE,VIB;BENTLY 33019108561005 | 2024-11-19 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027115_0050 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232430 | S002 | 30 | 30 | 5300017864 | 50 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235387 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-11-20 | 2025-02-12 | 2025-02-07 | 2025-03-01 | 2025-05-17 | VALVE | 100087379 | 0050 | 0010 | 100087379 | MV-OH 4" 300# 960BAV2400 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 255 | No issue identified | 10577006 | PACKING,VV STEM;P/H PACKT5F065100 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018141 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028277 | 05 | Preparation | 0000277207 | 1 | 0 | EA | 101000000149059 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090028277_0010 | 0 | 0 | 0 | 0 |  | 2025-02-10 | AA53 | 2025-03-01 |  |  | 2025-02-12 |  |  |  |  | 2026-11-04 | 0 |  | 2025-02-07 |  | 2025-02-12 |  |  | 0 | 2 | 0 | 90028277 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10577006 | PACKING,VV STEM;P/H PACKT5F065100 |  |  |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028277_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271762 | S002 | 30 | 30 | 5300018141 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277207 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-11-20 | 2025-02-12 | 2025-02-07 | 2025-03-01 | 2025-05-17 | VALVE | 100087379 | 0050 | 0020 | 100087379 | MV-OH 4" 300# 960BAV2400 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 255 | No issue identified | 10577055 | GASKET;BON,ANSI 300LB,P/H DIOT065AV | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018141 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028277 | 05 | Preparation | 0000277207 | 2 | 0 | EA | 101000000149058 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090028277_0020 | 0 | 0 | 0 | 0 |  | 2025-02-10 | AA53 | 2025-03-01 |  |  | 2025-02-12 |  |  |  |  | 2026-11-04 | 0 |  | 2025-02-07 |  | 2025-02-12 |  |  | 0 | 2 | 0 | 90028277 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10577055 | GASKET;BON,ANSI 300LB,P/H DIOT065AV |  |  |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028277_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271762 | S002 | 30 | 30 | 5300018141 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277207 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200081172 | 0020 | 0022 | 200081172 | 4Y CO2 System Replace Hoses (3) 4KT1410 | AA53.HOSE40645 | HOSE,CO2 4KT1410V5 TO 414RV409 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10577721 | HOSE ASY;CO2;25MM,0.42M,7000KPAG,190MM | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200081172, Item 4 cannot be changed 90024956 item 10 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003166 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024956 | 05 | Preparation | 0000115761 | 4 | 0 | EA | 102000000027654 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024956_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200682034 |  | 0 | 2 | 0 | 90024956 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10577721 | HOSE ASY;CO2;25MM,0.42M,7000KPAG,190MM | 2024-01-02 | W |  | 0020 | CO2 System Replace Hoses | INT | CO2 System Replace Hoses | 5 | Ready for Release | 90024956_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000115091 | S002 | 30 | 30 | 5300003166 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 115761 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200081173 | 0020 | 0012 | 200081173 | 4Y CO2 System Replace Hoses (3) 4KT1430 | AA53.HOSE40648 | HOSE,CO2 4KT1430V5 TO 414RV509 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10577721 | HOSE ASY;CO2;25MM,0.42M,7000KPAG,190MM | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200081173, Item 4 cannot be changed 90024957 item 10 already exists | Material picked; currently at SW3R01H02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003167 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024957 | 05 | Preparation | 0000115762 | 4 | 0 | EA |  |  | 102000000027656 |  |  |  |  | WorkPackLink | SW3R01H02B | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024957_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200682037 |  | 0 | 2 | 0 | 90024957 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10577721 | HOSE ASY;CO2;25MM,0.42M,7000KPAG,190MM | 2024-01-02 | W |  | 0020 | CO2 System Replace Hoses | INT | CO2 System Replace Hoses | 5 | Ready for Release | 90024957_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000115092 | S002 | 30 | 30 | 5300003167 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 115762 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0250 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10577778 | BAR,MET;FLAT,160X10MM,4M,6060 T5 AL,MILL | 4 | EA | 3 | 0 | 0 | 0 |  | 07.03 - PR 2000283138 QTY 3 IN STOCK | Supply for Order 100090053, Item 25 cannot be changed 90032376 item 250 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 25 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0250 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Ray R |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10577778 | BAR,MET;FLAT,160X10MM,4M,6060 T5 AL,MILL | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0250 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 25 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 250 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-02-25 | 2025-03-01 | MECH | 200090678 | 0080 | 0070 | 200090678 | 4Y INT INSP EXCHANGER 5P2002BE | AA53.5P2002BE | EXCH,SEAL OIL COOLER P2002B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10578889 | COOLER;SEAL,COIL,RH,FLOWSV B0436604Q1 | 1 | EA | 0 | 0 | 0 | 0 |  | 15.01 - ETA 01.07.25 PO 4500042689 FLOWSERVE CPT | Supply for Order 200090678, Item 8 cannot be changed 90028422 item 70 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019787 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028422 | 05 | Preparation | 0000128956 | 8 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028422_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090678 |  | 0 | 2 | 0 | 90028422 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578889 | COOLER;SEAL,COIL,RH,FLOWSV B0436604Q1 | 2025-01-08 | W |  | 0080 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028422_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128367 | S002 | 30 | 30 | 5300019787 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128956 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200090677 | 0100 | 0010 | 200090677 | 4Y INT INSP EXCHANGER 5P2002AE | AA53.5P2002AE | EXCH,SEAL OIL COOLER P2002A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.01.2025) | 10578918 | COOLER;SEAL,COIL,LH,FLOWSV B0433942Q1 | 1 | EA | 0 | 0 | 0 | 0 |  | 15.01 - ETA 01.07.25 PO 4500042689 FLOWSERVE CPT | Supply for Order 200090677, Item 9 cannot be changed 90028421 item 70 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019786 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028421 | 05 | Preparation | 0000128955 | 9 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028421_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090677 |  | 0 | 2 | 0 | 90028421 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578918 | COOLER;SEAL,COIL,LH,FLOWSV B0433942Q1 | 2025-01-10 | W |  | 0100 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028421_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128366 | S002 | 30 | 30 | 5300019786 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128955 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-11-18 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-02 | MECH | 100073990 | 0020 | 0050 | 100073990 | Filter House Broken Gate Hinges | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(31.01.2025) | 10578950 | ANG:40X40mmX3mX5mm,316 SS | 1 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 28.03.25 PO 4500048258 MRC CPT | Supply for Order 100073990, Item 5 cannot be changed 90029974 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300017984 | 50 | CPT | 7 | 1000028977 | 5 | 30000130 | MRC GLOBAL AUSTRALIA PTY LTD | 4500048258 | 10 | 1 | EA | 2025-03-28 |  |  |  | 90029974 | 06 | Scheduling | 0000224822 | 5 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-18 | ODST-0090029974_0010 | 0 | 45 | 45 | 45 | 2025-03-27 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-04-15 | 2025-03-29 | 2025-04-10 |  |  | 2025-02-22 | 0 |  | 2025-02-12 |  | 2025-02-24 |  |  | 0 | 2 | 2 | 90029974 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578950 | ANG:40X40mmX3mX5mm,316 SS | 2025-01-31 | W |  | 0020 | Modify Gate & Install Hinges | INT | Modify Gate & Install Hinges |  |  | 90029974_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-31 | 30 | 6000014822 | 2025-03-29 | 0 |  | 0 |  | 25SDGT9 | MJ |  | AU1009 | 1000222245 | S001 | 30 | 30 | 5300017981 | 50 |  | 5300017984 | 50 | 1 | EA | 1001 | AA02 | 2025-02-12 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-03-01 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material shortage | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144871 | 0010 | 0010 | 200144871 | 1Y Analyser Filter Replacement 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.04.2024) | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 2 | EA | 6 | 0 | 2 | 2 | EA | 29.01 - At KGP | Supply for Order 200144871, Item 1 cannot be changed 180109578 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009067 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180109578 | 9023417 | 05 | Preparation | 0000232066 | 1 | 0 | EA |  |  | 102000000028396 |  |  |  |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-04-13 | GRST-5000333029 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000049524 | 1020 | 2025-04-07 | 2 |  | 2024-12-26 | 4900197998_2024_0001 | 2025-03-01 |  | 5000333029_2024_0001 | 0 | 2 | 0 | 90024976 | 2 | 0 | 180109578 | 2 | 0 | 0 | X | L | 4900197998 | 2024 |  | 5000333029 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 2024-04-13 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 9023417_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229153 | S002 | 30 | 30 | 5300009067 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232066 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147431 | 0010 | 0010 | 200147431 | 1Y Analyser Filter Replacement 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 2 | EA | 6 | 0 | 2 | 0 |  | 31.01 - SOH @ AA02 | Supply for Order 200147431, Item 1 cannot be changed 90024979 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300009771 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024979 | 05 | Preparation | 0000235836 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024979_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90024979 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 2024-05-03 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | Ready for Release | 90024979_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232847 | S002 | 30 | 30 | 5300009771 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235836 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-08-10 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200160195 | 0010 | 0010 | 200160195 | 1Y Analyser Filter Replace 407QT501 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.08.2024) | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 2 | EA | 6 | 0 | 2 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200160195, Item 1 cannot be changed 90024993 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013873 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024993 | 05 | Preparation | 0000256082 | 1 | 0 | EA | 102000000029955 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-08-10 | ODST-0090024993_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 407QT501 |  | 0 | 2 | 0 | 90024993 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 2024-08-10 | W |  | 0010 | Complete Filter Replacement & PRT | INT | Complete Filter Replacement & PRT | 5 |  | 90024993_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000252060 | S002 | 30 | 30 | 5300013873 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240810 | 2024-08-10 | 256082 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144871 | 0010 | 0020 | 200144871 | 1Y Analyser Filter Replacement 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.04.2024) | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 2 | EA | 12 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200144871, Item 2 cannot be changed 90024976 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009067 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024976 | 05 | Preparation | 0000232066 | 2 | 0 | EA | 102000000027732 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024976_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024976 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 2024-04-13 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024976_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229153 | S002 | 30 | 30 | 5300009067 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232066 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147431 | 0010 | 0020 | 200147431 | 1Y Analyser Filter Replacement 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 2 | EA | 12 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147431, Item 2 cannot be changed 90024979 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009771 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024979 | 05 | Preparation | 0000235836 | 2 | 0 | EA | 102000000027733 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024979_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90024979 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 2024-05-03 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | Ready for Release | 90024979_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232847 | S002 | 30 | 30 | 5300009771 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235836 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-08-10 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200160195 | 0010 | 0020 | 200160195 | 1Y Analyser Filter Replace 407QT501 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.08.2024) | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 2 | EA | 12 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200160195, Item 2 cannot be changed 90024993 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013873 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024993 | 05 | Preparation | 0000256082 | 2 | 0 | EA | 102000000027734 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-08-10 | ODST-0090024993_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 407QT501 |  | 0 | 2 | 0 | 90024993 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 2024-08-10 | W |  | 0010 | Complete Filter Replacement & PRT | INT | Complete Filter Replacement & PRT | 5 |  | 90024993_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000252060 | S002 | 30 | 30 | 5300013873 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240810 | 2024-08-10 | 256082 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144870 | 0010 | 0010 | 200144870 | 2Y Analyser Inspection 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.04.2024) | 10579002 | SENSOR;ZIRCONIA,CER,HOBRE HI207299 | 1 | EA | 4 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200144870, Item 1 cannot be changed 90024977 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009068 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024977 | 05 | Preparation | 0000232065 | 1 | 0 | EA | 102000000027729 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024977_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408QT50 |  | 0 | 2 | 0 | 90024977 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579002 | SENSOR;ZIRCONIA,CER,HOBRE HI207299 | 2024-04-13 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 |  | 90024977_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229152 | S002 | 30 | 30 | 5300009068 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232065 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147430 | 0010 | 0010 | 200147430 | 2Y Analyser Inspection 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10579002 | SENSOR;ZIRCONIA,CER,HOBRE HI207299 | 1 | EA | 4 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA01/AA02 | Supply for Order 200147430, Item 1 cannot be changed 90024980 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009772 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024980 | 05 | Preparation | 0000235835 | 1 | 0 | EA | 101000000143509 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024980_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90024980 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579002 | SENSOR;ZIRCONIA,CER,HOBRE HI207299 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 | Ready for Release | 90024980_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232846 | S002 | 30 | 30 | 5300009772 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235835 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144870 | 0010 | 0070 | 200144870 | 2Y Analyser Inspection 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.10.2024) | 10579006 | ORIFICE;TBG,0.125"OD,HOBRE HI102152 | 1 | EA | 6 | 0 | 0 | 1 | EA | 23.10 - SOH @ AA02 | Supply for Order 200144870, Item 7 cannot be changed 90024977 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009068 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024977 | 05 | Preparation | 0000232065 | 7 | 0 | EA | 102000000027731 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024977_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408QT50 |  | 0 | 2 | 0 | 90024977 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579006 | ORIFICE;TBG,0.125"OD,HOBRE HI102152 | 2024-10-22 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 |  | 90024977_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229152 | S002 | 30 | 30 | 5300009068 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232065 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147430 | 0010 | 0070 | 200147430 | 2Y Analyser Inspection 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.12.2024) | 10579006 | ORIFICE;TBG,0.125"OD,HOBRE HI102152 | 1 | EA | 6 | 0 | 0 | 1 | EA | 11.12 - SOH @ AA02 | Supply for Order 200147430, Item 7 cannot be changed 90028269 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009772 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028269 | 05 | Preparation | 0000235835 | 7 | 0 | EA | 102000000031035 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-03 | ODST-0090028269_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90028269 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579006 | ORIFICE;TBG,0.125"OD,HOBRE HI102152 | 2024-12-10 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 | Ready for Release | 90028269_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232846 | S002 | 30 | 30 | 5300009772 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235835 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Goods movement posted | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3010 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10579550 | CABLE;14AWG,GE 362A2370P015 | 1000 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 579 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1000 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124T301-318 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579550 | CABLE;14AWG,GE 362A2370P015 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3020 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10579551 | CABLE;TC,TYPE K,18AWG,GE 362A2421P001 | 755 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 580 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 755 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | t/c |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579551 | CABLE;TC,TYPE K,18AWG,GE 362A2421P001 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3000 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10579552 | CABLE;18AWG,GE 362A2373P001 | 345 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 578 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 345 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124T301-318 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579552 | CABLE;18AWG,GE 362A2373P001 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDTOT2 | Released | 2025-02-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100081724 | 0010 | 0010 | 100081724 | Inst Air Hose Replace (4) TOT2PRS Run 4 | AA53.210HV841 | VALVE,CTRL 2PRS RUN 4 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10579643 | HOSE ASY,AIR;25MM,1M,7000KPAG,CRIMPED | 4 | EA | 0 | 0 | 0 | 0 |  | 16.02 - ETA 21.03.25 PO 4500046316 HDS HOSES CPT CRITICAL | Supply for Order 100081724, Item 1 cannot be changed 90030762 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021207 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030762 | 05 | Preparation | 0000253804 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-02-12 | ODST-0090030762_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100081724 |  | 0 | 2 | 0 | 90030762 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579643 | HOSE ASY,AIR;25MM,1M,7000KPAG,CRIMPED | 2025-02-12 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  |  | 90030762_0010 |  |  | TT2 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDTOT2 | MJ |  | AU1072 | 1000250026 | S002 | 30 | 30 | 5300021207 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-07-30 | 253804 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Order Approved/Released/Material shortage/Settlement rule created/Date set by external system/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10579978 | CABLE;14AWG,GE 362A2369P001 | 132 | FT | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | FT | [5 empty] | 05 | Preparation | 0000129822 | 587 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 132 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124T301-318 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579978 | CABLE;14AWG,GE 362A2369P001 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0080 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10581195 | TAPE,ADH;FOIL,50MMX50M,BELLIS TAMYL5050I | 10 | ROL | 0 | 0 | 10 | 10 | ROL | 26.02 - SOH @ AA02 | Supply for Order 500005166, Item 28 cannot be changed 9028651 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132829 | 9028651 | 05 | Preparation | 0000294187 | 28 | 0 | ROL |  |  | 101000000148367 |  |  |  |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000429492_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060148 | 1020 |  | 10 |  | 2025-03-06 | 4900259005_2025_0001 | 2025-04-01 | TA LAG_VORN | 5000429492_2025_0001 | 0 | 2 | 0 | 90031501 | 10 | 0 | 180132829 | 2 | 0 | 0 | X | L | 4900259005 | 2025 |  | 5000429492 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10581195 | TAPE,ADH;FOIL,50MMX50M,BELLIS TAMYL5050I | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 9028651_0100 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 28 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 240 |  |  | 0 | 10 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD4401 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100074497 | 0020 | 0010 | 100074497 | Regulator Replace 344URCA47 | AA53.344UZ412 | LOOP,BOOSTR COMP RECYC VLV 344URCA47 OPN | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10582819 | REG:1/4in,316 SS,-20 TO 135deg C,BIFOLD | 1 | EA | 1 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 100074497, Item 1 cannot be changed 90025054 item 10 already exists | Material picked; currently at SW3R01B01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016523 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025054 | 05 | Preparation | 0000226665 | 1 | 0 | EA | 102000000029408 |  | 102000000026658 |  |  |  |  | WorkPackLink | SW3R01B01A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025054_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 344URCA47 |  | 0 | 2 | 0 | 90025054 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10582819 | REG:1/4in,316 SS,-20 TO 135deg C,BIFOLD | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025054_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000223937 | S002 | 30 | 30 | 5300016523 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-13 | 226665 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0030 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10582870 | REGULATOR,FLT;0.25",NORGREN B38P252B1MA | 1 | EA | 0 | 0 | 4 | 0 |  | 13.02 - ETA 02.05.25 PO 4500045345 ex Score not a show stopper | Supply for Order 100085072, Item 5 cannot be changed 90029879 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029879 | 05 | Preparation | 0000267773 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029879_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029879 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10582870 | REGULATOR,FLT;0.25",NORGREN B38P252B1MA | 2025-01-30 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029879_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 | 30 | 30 | 5300019757 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144870 | 0010 | 0060 | 200144870 | 2Y Analyser Inspection 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.10.2024) | 10584554 | SCREW;HEX,ORIF,30UM,HOBRE HI106309 | 1 | EA | 4 | 0 | 0 | 1 | EA | 23.10 - SOH @ AA02 | Supply for Order 200144870, Item 6 cannot be changed 90024977 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009068 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024977 | 05 | Preparation | 0000232065 | 6 | 0 | EA | 102000000027730 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024977_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408QT50 |  | 0 | 2 | 0 | 90024977 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10584554 | SCREW;HEX,ORIF,30UM,HOBRE HI106309 | 2024-10-22 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 |  | 90024977_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229152 | S002 | 30 | 30 | 5300009068 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232065 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147430 | 0010 | 0060 | 200147430 | 2Y Analyser Inspection 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.12.2024) | 10584554 | SCREW;HEX,ORIF,30UM,HOBRE HI106309 | 1 | EA | 4 | 0 | 0 | 1 | EA | 11.12 - SOH @ AA02 | Supply for Order 200147430, Item 6 cannot be changed 90028269 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009772 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028269 | 05 | Preparation | 0000235835 | 6 | 0 | EA | 102000000031034 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-03 | ODST-0090028269_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90028269 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10584554 | SCREW;HEX,ORIF,30UM,HOBRE HI106309 | 2024-12-10 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 | Ready for Release | 90028269_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232846 | S002 | 30 | 30 | 5300009772 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235835 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 |  | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0160 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance |  | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2025) | 10584676 | PLIERS;LG NOSE,200MM,VDE,KNIPEX 2626200T | 1 | EA | 0 | 0 | 0 | 0 |  | 10.03 - NEEDS PURCHASE REQ | Supply Process could not be determined for item 70, material 10584676 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 70 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-04-01 | [8 empty] | 0 |  |  |  |  | Scot.K |  | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10584676 | PLIERS;LG NOSE,200MM,VDE,KNIPEX 2626200T | 2025-03-06 | E |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec | [11 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDENA1 | MJ |  |  | 1000287811 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0150 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10584758 | SLIDE UNIT;BOLTED,BINDER SU01 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 14 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10584758 | SLIDE UNIT;BOLTED,BINDER SU01 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDSTB5 | Released | 2024-08-08 | 2025-03-01 | 2025-01-13 | 2025-03-01 | 2025-03-01 | MECH | 200069587 | 1000 | 0020 | 200069587 | 8Y FG HOSE REPL FURNACE 5F2001 | AA53.520XE042HOSE01 | HOSE,FG 520XE042 B FLAME DET 5F2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.08.2024) | 10585972 | HOSE ASY;FL/GAS,10MM,1.5M,5600KPAG | 1 | EA | 0 | 0 | 0 | 0 |  | 16.12 - qty 1 SOH @ AA01 | Supply for Order 200069587, Item 2 cannot be changed 90018373 item 10 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA01 | 5300014129 | 10 | CPT | 7 | 1000017473 | 2 | 30000174 | PRESSURE DYNAMICS INTERNATIONAL PTY | 4500025831 | 10 | 1 | EA | 2024-09-04 |  | /180071378 |  | 90018373 | 06 | Scheduling | 0000103910 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-15 | ODST-0090018373_0010 | 0 | 124 | 0 | 124 | 2024-10-10 | 2025-01-22 | AA53 | 2025-03-01 |  |  | 2025-01-27 | 2024-10-12 | 2025-01-24 |  |  | 2025-10-31 | 0 | 5000220939_2024_0001 | 2025-01-13 |  | 2024-09-26 | HIGH |  | 0 | 2 | 2 | 90018373 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000220939 |  | 0 | 2024 | /018007137 | 2025-01-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10585972 | HOSE ASY;FL/GAS,10MM,1.5M,5600KPAG | 2024-08-14 | W |  | 1000 | Materials Assuarance | ENON | Materials Assuarance |  |  | 90018373_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0060 | Ready to Schedule (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-08-16 | 20 | 6000008226 | 2024-10-12 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000103326 | S001 | 30 | 30 | 5300013756 | 20 |  | 5300014129 | 10 | 1 | EA | 1001 | AA02 | 2025-01-13 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 1 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Ready For Scheduling/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200174926 | 0030 | 0050 | 200174926 | Replace Exchanger - 1KKT2430E3 | AA53.1KKT2430E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2430 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10586362 | BOLT ASY,HEX;M12X40MM,GDE 8.8,HDG,N+2W | 4 | EA | 4 | 0 | 0 | 4 | EA | 28.01 - ETA 28.02.25 PO 4500043784 ex Tristar | Supply for Order 200174926, Item 6 cannot be changed 90028606 item 40 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020026 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028606 | 05 | Preparation | 0000277561 | 6 | 0 | EA | 101000000145893 |  | 101000000145718 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  | 2025-02-20 | Y | 1001 | 2025-01-14 | ODST-0090028606_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-07-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174926 |  | 0 | 2 | 0 | 90028606 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10586362 | BOLT ASY,HEX;M12X40MM,GDE 8.8,HDG,N+2W | 2025-01-14 | W |  | 0030 | Remove Bonnet / Spools & Structure | INT | Remove Bonnet / Spools & Structure |  |  | 90028606_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDDG1 | MJ | 20005309 | AU1072 | 1000272048 | S002 | 30 | 30 | 5300020026 | 40 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-18 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277561 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0730 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10588368 | NUT;PST,GE SQP11687 | 2 | EA | 0 | 0 | 0 | 0 |  | 21.10 - ETA 02.04.25 PO 4500031815 BH | Supply for Order 200147980, Item 138 cannot be changed 90028418 item 500 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 138 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0500 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588368 | NUT;PST,GE SQP11687 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90028418_0500 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 138 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 510 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0790 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10588369 | SCREW;GE HMK10010 | 2 | EA | 0 | 0 | 0 | 0 |  | 21.10 - ETA 05.02.25 PO 4500031815 BH | Supply for Order 200147980, Item 144 cannot be changed 90028418 item 530 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 144 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0530 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588369 | SCREW;GE HMK10010 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90028418_0530 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 144 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 560 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFLR | Released | 2024-11-08 | 2025-02-08 | 2025-02-26 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0440 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(26.02.2025) | 10588372 | TOOL;INSTL,CABLE TIE,PANDUIT PANGS4MTE | 2 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 15.04.25 PO 4500048438 M&amp;H CPT | Supply for Order 600001815, Item 54 cannot be changed 90031784 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031784 | 07 | Execution | 0000084731 | 54 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-13 | ODST-0090031784_0010 | 0 | 23 | 0 | 0 |  | 2025-02-06 | AA53 | 2025-02-08 |  |  | 2025-03-03 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-26 |  | 2025-03-03 | 37FQI40/41 |  | 0 | 2 | 0 | 90031784 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588372 | TOOL;INSTL,CABLE TIE,PANDUIT PANGS4MTE | 2025-02-26 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90031784_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 54 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 380 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-26 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0800 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10588500 | SCREW;GE RVR20721 | 2 | EA | 0 | 0 | 0 | 0 |  | 21.10 - ETA 05.02.25 PO 4500031815 BH | Supply for Order 200147980, Item 145 cannot be changed 90028418 item 540 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 145 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0540 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588500 | SCREW;GE RVR20721 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90028418_0540 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 145 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 570 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0720 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10588501 | KEY,FEATHER;4X5X12.5MM,GE FBN04005 | 2 | EA | 0 | 0 | 0 | 0 |  | 05.02 - SOH @ AA53 PO TO COME THROUGH PO 4500031815 BH FCA | Supply for Order 200147980, Item 137 cannot be changed 90028418 item 490 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 137 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588501 | KEY,FEATHER;4X5X12.5MM,GE FBN04005 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90028418_0490 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 137 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 500 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0740 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10588502 | PIN;8X20MM,GE FJM08020 | 4 | EA | 0 | 0 | 0 | 0 |  | 21.10 - ETA 05.02.25 PO 4500031815 BH | Supply for Order 200147980, Item 139 cannot be changed 90028418 item 510 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 139 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0510 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588502 | PIN;8X20MM,GE FJM08020 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90028418_0510 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 139 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 520 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0670 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10588505 | NOZZLE;AXL FL/GAS,SS,GE SMR36933 | 6 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 06.06.25 PO 4500031675 BH | Supply for Order 200091513, Item 451 cannot be changed 90028419 item 3130 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 451 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588505 | NOZZLE;AXL FL/GAS,SS,GE SMR36933 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3130 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 451 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3160 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0600 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10588506 | SCREW;0.75-10UNC X 1.75",GE GQF19044 | 24 | EA | 0 | 0 | 0 | 0 |  | 07.02 - ETA 01.04.25 PO 4500031675 BH MOT GS4953941 10kg 35x35x20cm | Supply for Order 200091513, Item 60 cannot be changed 90028419 item 460 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 60 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588506 | SCREW;0.75-10UNC X 1.75",GE GQF19044 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0460 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 60 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 470 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0680 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10588506 | SCREW;0.75-10UNC X 1.75",GE GQF19044 | 24 | EA | 0 | 0 | 0 | 0 |  | 07.02 - ETA 01.04.25 PO 4500031675 BH MOT GS4953941 10kg 35x35x20cm | Supply for Order 200091513, Item 452 cannot be changed 90028419 item 3140 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 452 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588506 | SCREW;0.75-10UNC X 1.75",GE GQF19044 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3140 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 452 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3170 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0660 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10588987 | PLATE;LK,GE SMP50141 | 6 | EA | 6 | 0 | 0 | 6 | EA | 04.03 - SOH @ AA02 | Supply for Order 200091513, Item 450 cannot be changed 90028419 item 3120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 450 | 0 | EA | 102000000030481 | 101000000150218 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10588987 | PLATE;LK,GE SMP50141 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3120 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 450 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3150 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0030 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 1 | EA | 4 | 0 | 4 | 1 | EA | 03.01 - SOH @ AA02 | Supply for Order 200147548, Item 3 cannot be changed 90025036 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 3 | 0 | EA | 101000000121109 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 1 | EA | 4 | 0 | 4 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200147550, Item 3 cannot be changed 90025043 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 3 | 0 | EA | 102000000033857 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025043_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 1 | EA | 4 | 0 | 4 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200147552, Item 3 cannot be changed 90025045 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 3 | 0 | EA | 102000000033856 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0230 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10589686 | SCREW:S/TAP,4.2X13MM,PAN HD,PHIL,SS,WSHR | 2 | PAC | 0 | 0 | 0 | 0 |  | 07.03 - DEL: 80033617 | Supply for Order 100090053, Item 23 cannot be changed 90032376 item 230 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAC |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 23 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0230 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589686 | SCREW:S/TAP,4.2X13MM,PAN HD,PHIL,SS,WSHR | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0230 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 23 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 230 |  |  | 0 | 2 | PAC | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0110 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10589686 | SCREW:S/TAP,4.2X13MM,PAN HD,PHIL,SS,WSHR | 7 | PAC | 0 | 0 | 0 | 0 |  | 10.03 - DEL: 80033617 | Supply for Order 500005166, Item 31 cannot be changed 90031501 item 130 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAC |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 31 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 7 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0130 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589686 | SCREW:S/TAP,4.2X13MM,PAN HD,PHIL,SS,WSHR | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0130 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 31 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 270 |  |  | 0 | 7 | PAC | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDGT7 | Released | 2024-10-25 | 2025-03-01 | 2025-02-19 | 2025-03-01 | 2025-03-01 | MECH | 100034776 | 0040 | 0070 | 100034776 | MOC-145870-PV CM G4007V3 Passing Fill Va | AA53.G4007V3 | VE,CO2 LOW PRESSURE,GT4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(19.01.2025) | 10590067 | VALVE,GATE;DN15,CL300,RF,316SS,S3GN | 1 | EA | 2 | 0 | 2 | 0 |  | 03.02 - ETA 11.04.25 PO 4500044562 SCORE CPT | Supply for Order 100034776, Item 8 cannot be changed 90029636 item 20 already exists | Vendor PO raised | SP97 | Direct Multi-base | 266 | AA01 | 5300020138 | 20 | CPT | 7 | 1000028180 | 8 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500044562 | 10 | 1 | EA | 2025-04-11 |  |  |  | 90029636 | 05 | Preparation | 0000133257 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-17 | ODST-0090029636_0020 | 0 | 255 | 246 | 255 | 2025-10-21 | 2025-03-03 | AA53 | 2025-03-01 |  |  | 2025-11-11 | 2025-10-23 | 2025-11-06 |  |  | 2024-03-06 | 0 |  | 2025-02-19 |  | 2025-03-05 | 100034776 |  | 0 | 2 | 2 | 90029636 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-19 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10590067 | VALVE,GATE;DN15,CL300,RF,316SS,S3GN | 2025-01-19 | W |  | 0040 | Fabricate Spool ( site inspection ) | INT | Fabricate Spool ( site inspection ) |  | Engineering Query/Management of Change | 90029636_0020 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-20 | 20 | 6000014408 | 2025-10-23 | 0 |  | 0 |  | 25SDGT7 | MJ |  | AU1009 | 1000132686 | S001 | 30 | 30 | 5300020137 | 50 |  | 5300020138 | 20 | 1 | EA | 1001 | AA02 | 2025-02-19 |  | Engineering Query/Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-10-04 | 2025-02-28 | 2025-02-23 | 2025-03-01 | 2025-04-29 | VALVE | 100076445 | 0010 | 0030 | 100076445 | MV-RE 1/2" 300# 244LT512 | AA53.244LT512 | TX,LEVEL DRAIN POT 2K4401V5A | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(04.10.2024) | 10590067 | VALVE,GATE;DN15,CL300,RF,316SS,S3GN | 2 | EA | 2 | 0 | 0 | 2 | EA | 09.02 - SOH @ AA02 | Supply for Order 100076445, Item 3 cannot be changed 90027225 item 10 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 266 | AA02 | 5300016044 | 10 | CPT | 14 | 1000020548 | 3 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500032754 | 10 | 2 | EA | 2025-01-17 |  | /180107562 |  | 90025021 | 05 | Preparation | 0000232991 | 3 | 0 | EA | 101000000130245 |  | 102000000034357 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-04 | ODST-0090025021_0010 | 0 | 144 | 144 | 144 | 2025-07-04 | 2025-02-26 | AA53 | 2025-03-01 |  |  | 2025-07-22 | 2025-07-06 | 2025-06-28 |  |  | 2025-10-30 | 0 | 5000332146_2024_0001 | 2025-02-23 |  | 2024-12-24 | 100076445 |  | 0 | 2 | 2 | 90025021 | 0 | 2 |  | 2 | 0 | 0 | X | L |  | 0 | 5000332146 |  | 0 | 2024 | /018010756 | 2025-02-23 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10590067 | VALVE,GATE;DN15,CL300,RF,316SS,S3GN | 2024-10-04 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  |  | 90025021_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-10-04 | 20 | 6000010055 | 2025-07-06 | 3 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000230114 | S002 | 30 | 30 | 5300016044 | 10 |  | 5300016045 | 10 | 2 | EA | 2001 | AA02 | 2025-02-23 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-04-17 | 232991 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-11 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | VALVE | 100080816 | 0110 | 0010 | 100080816 | MOC-117208 Repl Accumulators (2) 1A1491 | AA53.1A1491 | PKG EQ,HYD PWR PACK |  | 10 | No Issue identified | 10590754 | ACCUMULATOR:PST,EXOTECH PA80229200SW6817 | -11 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000251583 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 | 5400001853 | 10 | 11 | EA | 11 | 0 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-31 | 0 |  |  |  |  | 1A1491 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10590754 | ACCUMULATOR:PST,EXOTECH PA80229200SW6817 |  |  |  | 0110 | refurbish exLNG2 accumulators pre shut | INT | refurbish exLNG2 accumulators pre shut | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 | 4900193770_2024 | 25SDLN1 | MJ |  |  | 1000247849 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPR07 | 2024-07-19 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-11 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100080929 | 0090 | 0010 | 100080929 | MOC-117208 Repl Accumulators (3) 1A1190 | AA53.1A1190 | PKG EQ,PWR PACK FOR HYD VALVES (SEE P1) |  | 10 | No issue identified | 10590754 | ACCUMULATOR:PST,EXOTECH PA80229200SW6817 | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb Return |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000251550 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-31 | 0 |  |  |  |  | 1A1190 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10590754 | ACCUMULATOR:PST,EXOTECH PA80229200SW6817 |  |  |  | 0090 | Punchlist & Closeout WP100080929MET001 | ENON | Punchlist & Closeout WP100080929MET001 | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000247889 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPR07 | 2024-07-19 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Error in cost calculation | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-11 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100080929 | 0040 | 0010 | 100080929 | MOC-117208 Repl Accumulators (3) 1A1190 | AA53.1A1190 | PKG EQ,PWR PACK FOR HYD VALVES (SEE P1) |  | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10590754 | ACCUMULATOR:PST,EXOTECH PA80229200SW6817 | 1 | EA | 0 | 0 | 0 | 0 |  | 11.02 - ETA 30.04.25 PO 4500044228 Press Dyn | Supply Process could not be determined for item 2, material 10590754 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  |  | 05 | Preparation | 0000251550 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-31 | 0 |  |  |  |  | 1A1190 |  | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10590754 | ACCUMULATOR:PST,EXOTECH PA80229200SW6817 | 2025-02-11 | E |  | 0040 | Remove & Replace Accumulators | INT | Remove & Replace Accumulators | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000247889 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPR07 | 2024-07-19 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Error in cost calculation | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-02-28 | 2025-05-19 | 2025-05-14 | 2025-05-19 | 2025-05-20 | VALVE | 100043286 | 0010 | 0020 | 100043286 | Replace Valve Gland Packing 311LCV03 | AA53.311LCV03 | VALVE,LVL BOTTOMS FROM 3C1101 | AA01 | 255 | No Issue identified | 10591311 | PACKING,SET;VALTEK 225129L4B000 | 1 | SET | 0 | 0 | 0 | 0 |  | 06.03 - ETA 21.05.25 PO 4500048444 SCORE CPT |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300021913 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000141787 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-28 | STST-5300021913_00020 | 0 | 0 | 0 | 0 |  | 2025-05-17 | AA53 | 2025-05-19 |  |  | 2025-05-19 |  |  |  |  | 2025-10-31 | 0 |  | 2025-05-14 |  | 2025-05-19 |  |  | 0 | 2 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-05-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10591311 | PACKING,SET;VALTEK 225129L4B000 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000141176 | S002 | 30 | 30 | 5300021913 | 20 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-05-14 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141787 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-20 | 2025-05-19 | 2025-05-19 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-02-28 | 2025-05-19 | 2025-05-14 | 2025-05-19 | 2025-05-20 | VALVE | 100043286 | 0010 | 0030 | 100043286 | Replace Valve Gland Packing 311LCV03 | AA53.311LCV03 | VALVE,LVL BOTTOMS FROM 3C1101 | AA01 | 255 | No Issue identified | 10591312 | SPACER;PKG,VALTEK 089400150000 | 2 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 21.05.25 PO 4500048444 SCORE CPT |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300021913 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141787 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-28 | STST-5300021913_00030 | 0 | 0 | 0 | 0 |  | 2025-05-17 | AA53 | 2025-05-19 |  |  | 2025-05-19 |  |  |  |  | 2025-10-31 | 0 |  | 2025-05-14 |  | 2025-05-19 |  |  | 0 | 2 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-05-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10591312 | SPACER;PKG,VALTEK 089400150000 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000141176 | S002 | 30 | 30 | 5300021913 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-05-14 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141787 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-20 | 2025-05-19 | 2025-05-19 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-02-28 | 2025-05-19 | 2025-05-14 | 2025-05-19 | 2025-05-20 | VALVE | 100043286 | 0010 | 0040 | 100043286 | Replace Valve Gland Packing 311LCV03 | AA53.311LCV03 | VALVE,LVL BOTTOMS FROM 3C1101 | AA01 | 255 | No Issue identified | 10591313 | SPACER;PKG,VALTEK 020902150000 | 1 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 21.05.25 PO 4500048444 SCORE CPT |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300021913 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141787 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-28 | STST-5300021913_00040 | 0 | 0 | 0 | 0 |  | 2025-05-17 | AA53 | 2025-05-19 |  |  | 2025-05-19 |  |  |  |  | 2025-10-31 | 0 |  | 2025-05-14 |  | 2025-05-19 |  |  | 0 | 2 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-05-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10591313 | SPACER;PKG,VALTEK 020902150000 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000141176 | S002 | 30 | 30 | 5300021913 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-05-14 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141787 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-20 | 2025-05-19 | 2025-05-19 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-02-28 | 2025-05-19 | 2025-05-14 | 2025-05-19 | 2025-05-20 | VALVE | 100043286 | 0010 | 0050 | 100043286 | Replace Valve Gland Packing 311LCV03 | AA53.311LCV03 | VALVE,LVL BOTTOMS FROM 3C1101 | AA01 | 255 | No Issue identified | 10591314 | SPACER;PKG,VALTEK 004684150000 | 1 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 21.05.25 PO 4500048444 SCORE CPT |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300021913 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141787 | 5 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-28 | STST-5300021913_00050 | 0 | 0 | 0 | 0 |  | 2025-05-17 | AA53 | 2025-05-19 |  |  | 2025-05-19 |  |  |  |  | 2025-10-31 | 0 |  | 2025-05-14 |  | 2025-05-19 |  |  | 0 | 2 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-05-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10591314 | SPACER;PKG,VALTEK 004684150000 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 5 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000141176 | S002 | 30 | 30 | 5300021913 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-05-14 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141787 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-20 | 2025-05-19 | 2025-05-19 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0160 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10592010 | SHIM;BOLTED,BINDER SP040180790140 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 15 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10592010 | SHIM;BOLTED,BINDER SP040180790140 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0210 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10592307 | ADHESIVE;FOSTER 8184NH PART A/8184PART B | 1 | KIT | 0 | 0 | 0 | 0 |  | 20.02 - SOH @ AA01 | Supply for Order 500005166, Item 41 cannot be changed 90031501 item 230 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 41 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0230 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10592307 | ADHESIVE;FOSTER 8184NH PART A/8184PART B | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0230 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 41 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 370 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0240 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10592953 | CEMENT;INS,SELF SETTING,25KG BAG | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 14.03.25 PO 4500047444 ATOM CPT | Supply for Order 500005166, Item 44 cannot be changed 90031501 item 260 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 44 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0260 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10592953 | CEMENT;INS,SELF SETTING,25KG BAG | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0260 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 44 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 400 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2301 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100085195 | 0020 | 0010 | 100085195 | MOC-150408: RTD Replace - 1K2301 | AA53.123TE052 | TXDCR,TEMP ALARM 1V2305A INLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(08.02.2025) | 10593156 | SENSOR,TEMP;EMERSON 214CRTSMB1S4M0255SL+ | 1 | EA | 0 | 0 | 0 | 0 |  | 21.02 - ETA 28.03.25 PO 4500046947 EMERSON CPT | Supply for Order 100085195, Item 1 cannot be changed 90030536 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021008 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030536 | 05 | Preparation | 0000267848 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-08 | ODST-0090030536_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123TE052 |  | 0 | 2 | 0 | 90030536 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10593156 | SENSOR,TEMP;EMERSON 214CRTSMB1S4M0255SL+ | 2025-02-08 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030536_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000262907 | S002 | 30 | 30 | 5300021008 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267848 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Printed/Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0030 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10593608 | GASKET,SW;61X44X28MM,KLINGER 5441401 | 3 | EA | 3 | 0 | 0 | 3 | EA | 18.02 - SOH @ AA02 | Supply for Order 200091108, Item 108 cannot be changed 90028420 item 720 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 108 | 0 | EA | 101000000143824 |  | 102000000034100 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0720 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOPiping |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10593608 | GASKET,SW;61X44X28MM,KLINGER 5441401 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0720 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 108 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 | 30 | 30 | 5300013062 | 750 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0040 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10593609 | GASKET,SW;68X52X35MM,KLINGER 5441402 | 9 | EA | 9 | 0 | 0 | 9 | EA | 18.02 - SOH @ AA02 | Supply for Order 200091108, Item 109 cannot be changed 90028420 item 730 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 109 | 0 | EA | 101000000143827 |  | 102000000034100 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOPiping |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10593609 | GASKET,SW;68X52X35MM,KLINGER 5441402 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0730 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 109 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 | 30 | 30 | 5300013062 | 760 |  |  | 0 | 9 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0050 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10593680 | GASKET,SW;66X45X28MM,KLINGER 5441403 | 3 | EA | 3 | 0 | 0 | 3 | EA | 18.02 - SOH @ AA02 | Supply for Order 200091108, Item 110 cannot be changed 90028420 item 740 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 110 | 0 | EA | 101000000143826 |  | 102000000034100 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOPiping |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10593680 | GASKET,SW;66X45X28MM,KLINGER 5441403 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0740 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 110 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 | 30 | 30 | 5300013062 | 770 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-12-05 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100046238 | 0020 | 0020 | 100046238 | EEHA - Replace Glands - 414PDT608A | AA53.414PDT608A | TX,DIFF PRESS S/GAS REF 4K1450LP | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(10.02.2025) | 10594035 | GLAND,CABLE;EX,0S-20S,M20,CCG 0572-0S HT | 6 | EA | 16 | 0 | 0 | 6 | EA | 20.02 - SOH @ AA02 | Supply for Order 100046238, Item 2 cannot be changed 90030598 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021048 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030598 | 05 | Preparation | 0000144782 | 2 | 0 | EA | 102000000033273 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-02-10 | ODST-0090030598_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2020-12-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414PDT608A |  | 0 | 2 | 0 | 90030598 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10594035 | GLAND,CABLE;EX,0S-20S,M20,CCG 0572-0S HT | 2025-02-10 | W |  | 0020 | Replace Glands | INT | Replace Glands |  | Engineering Query | 90030598_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000144153 | S002 | 30 | 30 | 5300021048 | 20 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144782 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0070 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10594070 | GLAND,CABLE;EX,1-20,M20,CCG 057201 HTLN | 30 | EA | 40 | 0 | 0 | 10 | EA | 02.03 - SOH @ AA02 | Supply for Order 600001416, Item 7 cannot be changed 90030040 item 900010 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 7 | 0 | EA | 102000000032250 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0020/90030040_0090_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10594070 | GLAND,CABLE;EX,1-20,M20,CCG 057201 HTLN | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0020/90030040_0090_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 7 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 | 30 | 30 | 5300004566 | 30 |  |  | 0 | 30 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0060 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue detected, please check message in derivation or orchestration log | 10594154 | INS,HEAT SHRINK;12.7MM,CABAC XLP13YG5M | 10 | BOX | 0 | 0 | 0 | 0 |  | 07.03 - ETA 14.03.25 PO 4500048466 M&amp;H CPT | Supply for Order 500005166, Item 60 cannot be changed 90032306 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 540 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 60 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0050 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Inlec Contai |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10594154 | INS,HEAT SHRINK;12.7MM,CABAC XLP13YG5M | 2025-03-03 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0050 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 60 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 540 |  |  | 0 | 10 | BOX | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0080 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10594468 | BLADE;SCRAPER,3-IN-1,OPEN-LOK,49252221 | 10 | EA | 0 | 0 | 0 | 0 |  | 24.02 - ETA 27.03.25 PO 4500046941 BLACKWOODS CPT | Supply for Order 500005166, Item 9 cannot be changed 90031023 item 80 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031023 | 05 | Preparation | 0000294187 | 9 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031023_0080 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 | [5 empty] | 0 |  | 2025-03-06 |  | 2025-03-11 | TA LAG_VORN |  | 0 | 2 | 0 | 90031023 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10594468 | BLADE;SCRAPER,3-IN-1,OPEN-LOK,49252221 | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0080 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 9 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 90 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-03-17 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1980 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10595104 | VALVE;PRESS REG,CI,GE RR015204 | 1 | EA | 0 | 0 | 0 | 0 |  | 05.03 - SOH @ AA02 QTY 1 PO TO COME THROUGH AND REPLACE VPR1 | Supply for Order 200091513, Item 723 cannot be changed 90031491 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300013091 | 10 | FCA | 7 | 1000015364 | 723 | 30000104 | BAKER HUGHES SERVICES AUSTRALIA PTY | 4500039084 | 20 | 1 | EA | 2025-07-04 |  |  |  | 90031491 | 05 | Preparation | 0000129822 | 723 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090031491_0010 | 0 | 32 | 0 | 32 | 2025-03-13 | 2025-03-26 | AA53 | 2025-03-01 |  |  | 2025-04-02 | 2025-03-15 | 2025-03-28 |  |  | 2025-07-03 | 0 |  | 2025-03-17 |  | 2025-03-28 |  |  | 0 | 2 | 2 | 90031491 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595104 | VALVE;PRESS REG,CI,GE RR015204 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90031491_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-17 | 20 | 6000009587 | 2025-03-15 | 0 |  | 0 |  | 25SD2420 | MJ |  | AU1009 | 1000129172 | S001 | 30 | 30 | 5300013090 | 10 |  | 5300013091 | 10 | 1 | EA | 1001 | AA02 | 2025-03-17 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200144598 | 0010 | 0020 | 200144598 | 2Y Bleed Air Valve F/T (2) 1KT1410 | AA53.114XCV35901 | VALVE,COMPRESSOR BLEED 1KT1410 |  | 255 | No issue identified | 10595299 | GREASE,GP;SHELL,GADUS S5 T460 1.5,450GM | 3 | CQ | 12 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016439 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90028272 | 05 | Preparation | 0000231723 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-16 | ODST-0090028272_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028272 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595299 | GREASE,GP;SHELL,GADUS S5 T460 1.5,450GM |  |  |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90028272_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228870 | S002 | 30 | 30 | 5300016439 | 20 |  |  | 0 | 3 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231723 | 0 | 0 |  | 1020 | 3 | SD | Shutdown |  |  | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200144599 | 0010 | 0020 | 200144599 | 2Y Bleed Air Valve Function Test (2) 1KT | AA53.114XCV45901 | VALVE,COMPRESSOR BLEED 1KT1420 |  | 255 | No issue identified | 10595299 | GREASE,GP;SHELL,GADUS S5 T460 1.5,450GM | 3 | CQ | 12 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016440 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90028273 | 05 | Preparation | 0000231724 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-16 | ODST-0090028273_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028273 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595299 | GREASE,GP;SHELL,GADUS S5 T460 1.5,450GM |  |  |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90028273_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228871 | S002 | 30 | 30 | 5300016440 | 20 |  |  | 0 | 3 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231724 | 0 | 0 |  | 1020 | 3 | SD | Shutdown |  |  | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200144600 | 0010 | 0020 | 200144600 | 2Y Bleed Air Valve F/T (2) 1KT1430 | AA53.114XCV55901 | VALVE,COMPRESSOR BLEED 1KT1430 |  | 255 | No issue identified | 10595299 | GREASE,GP;SHELL,GADUS S5 T460 1.5,450GM | 3 | CQ | 12 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016441 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90028274 | 05 | Preparation | 0000231725 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-16 | ODST-0090028274_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028274 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595299 | GREASE,GP;SHELL,GADUS S5 T460 1.5,450GM |  |  |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90028274_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228872 | S002 | 30 | 30 | 5300016441 | 20 |  |  | 0 | 3 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231725 | 0 | 0 |  | 1020 | 3 | SD | Shutdown |  |  | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200144601 | 0010 | 0020 | 200144601 | 2Y Bleed Air Valve Function Test (2) 1KT | AA53.114XCV65901 | VALVE,COMPRESSOR BLEED 1KT1440 |  | 255 | No issue identified | 10595299 | GREASE,GP;SHELL,GADUS S5 T460 1.5,450GM | 3 | CQ | 12 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016442 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90028275 | 05 | Preparation | 0000231726 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-16 | ODST-0090028275_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028275 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595299 | GREASE,GP;SHELL,GADUS S5 T460 1.5,450GM |  |  |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90028275_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228873 | S002 | 30 | 30 | 5300016442 | 20 |  |  | 0 | 3 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231726 | 0 | 0 |  | 1020 | 3 | SD | Shutdown |  |  | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2025-01-31 | 2025-03-01 | 2025-02-24 | 2025-05-11 | 2025-05-13 | INLEC | 100090545 | 0010 | 0020 | 100090545 | FAR4IPS1 - Tricon Card Replacement | AA53.FAR4IPS1 | PANEL,SYSTEM CABINET,IPS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(31.01.2025) | 10595797 | LINK,FUSE;6.3A,250V,WEIDMULLER 431400000 | 2 | EA | 2 | 0 | 0 | 2 | EA | 19.02 - SOH @ AA02 | Supply for Order 100090545, Item 2 cannot be changed 90030062 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020702 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030062 | 05 | Preparation | 0000291004 | 2 | 0 | EA | 101000000143561 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-31 | ODST-0090030062_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-11 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | FAR4IPS1 |  | 0 | 2 | 0 | 90030062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595797 | LINK,FUSE;6.3A,250V,WEIDMULLER 431400000 | 2025-01-31 | W |  | 0010 | Inlec Assistance | INT | Inlec Assistance |  |  | 90030062_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000284798 | S002 | 30 | 30 | 5300020702 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W43601 | 2025-01-17 | 291004 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-13 | 2025-05-11 | 2025-05-11 | Pre-costed/Object created/Order Approved/Released/Material shortage/Settlement rule created/Date set by external system/Printed | AM01 | Reactive Maintenance
1 | 25SDFR2 | Released | 2024-02-13 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | PROJ | 100041374 | 0090 | 0020 | 100041374 | KLE- Blast and Paint CL1801 | AA53.CL1801 | LOOP,CORR CL1801 | AA01 | 255 | WO item has not been released yet | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ | 1 | EA | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139858 | 2 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2026-02-01 | 0 |  |  |  |  | TALag_B.Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 30POST | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ |  |  |  | 0090 | Install Cladding at CL1801 | ENON | Install Cladding at CL1801 | 5 |  |  |  |  | LN0 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDFR2 | MJ |  |  | 1000139289 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | PJ | Project | 6 | Very Low | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling Canceled/Material committed | AM01 | Reactive Maintenance
1 | 25SDFR2 | Released | 2024-02-13 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | PROJ | 100041374 | 0090 | 0030 | 100041374 | KLE- Blast and Paint CL1801 | AA53.CL1801 | LOOP,CORR CL1801 | AA01 | 255 | WO item has not been released yet | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ | 1 | EA | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139858 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2026-02-01 | 0 |  |  |  |  | TALag_B.Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 30POST | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ |  |  |  | 0090 | Install Cladding at CL1801 | ENON | Install Cladding at CL1801 | 5 |  |  |  |  | LN0 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDFR2 | MJ |  |  | 1000139289 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | PJ | Project | 6 | Very Low | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling Canceled/Material committed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-18 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0110 | 0020 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.02.2025) | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ | 1 | EA | 0 | 0 | 0 | 0 |  | 24.02 - ETA 07.03.25 PO 4500047066 ARMACELL AUS CPT | Supply for Order 100087648, Item 35 cannot be changed 90031095 item 20 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018313 | 50 | DDP | 7 | 1000030203 | 35 | 30005435 | ARMACELL AUSTRALIA ENGINEERING PTY | 4500047066 | 20 | 1 | EA | 2025-03-27 |  |  |  | 90031095 | 05 | Preparation | 0000278190 | 35 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-23 | ODST-0090031095_0020 | 0 | 62 | 57 | 62 | 2025-04-14 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-05-02 | 2025-04-16 | 2025-04-27 |  |  | 2025-12-02 | 0 |  | 2025-02-18 |  | 2025-03-01 | TA LAG_VORN |  | 0 | 2 | 2 | 90031095 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ | 2025-02-18 | W |  | 0110 | Replace insulation & cladding | INT | Replace insulation & cladding |  |  | 90031095_0020 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-18 | 10 | 6000015614 | 2025-04-16 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000272706 | S001 | 30 | 30 | 5300018296 | 340 |  | 5300018313 | 50 | 1 | EA | 1001 | AA02 | 2025-02-18 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0190 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10595881 | RIBBON PRINT:ZEBRA DATA SCIENCES LTD,290 | 4 | EA | 0 | 0 | 27 | 0 |  | DEL: 80033206 | Supply for Order 500004676, Item 19 cannot be changed 90031855 item 180 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 19 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0180 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595881 | RIBBON PRINT:ZEBRA DATA SCIENCES LTD,290 | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0180 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 19 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 190 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 3 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0110 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue detected, please check message in derivation or orchestration log | 10596116 | BAG:BAG;ZIPPERED,PA,RALSTON QTHAHSBG | 1 | EA | 0 | 0 | 0 | 0 |  | 10.03 - ETA 29.04.25 PO 4500048825 TRANSEK CPT | Supply for Order 500005166, Item 65 cannot be changed 90032306 item 90 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 65 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0090 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Scot.K |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10596116 | BAG:BAG;ZIPPERED,PA,RALSTON QTHAHSBG | 2025-03-03 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0090 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 65 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 580 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0010 | 0030 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10596547 | COUPLING,DRV;JOHN CRANE 91125859 | 1 | EA | 0 | 0 | 2 | 1 | EA | 30.12 - SOH @ AA01 | Supply for Order 100033564, Item 3 cannot be changed 90025011 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015700 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180133948 | 9028682 | 05 | Preparation | 0000132018 | 3 | 0 | EA |  |  | 102000000031981 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-24 | GRST-5000434301_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060901 | 1020 | 2024-10-12 | 1 |  | 2025-03-10 | 4900263190_2025_0001 | 2025-03-01 |  | 5000434301_2025_0001 | 0 | 2 | 0 | 90025011 | 1 | 0 | 180133948 | 2 | 0 | 0 | X | L | 4900263190 | 2025 |  | 5000434301 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10596547 | COUPLING,DRV;JOHN CRANE 91125859 | 2024-09-23 | W |  | 0010 | As Found Alignment Record | INT | As Found Alignment Record |  |  | 9028682_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000131400 | S002 | 30 | 30 | 5300015700 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132018 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0010 | 0030 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10596547 | COUPLING,DRV;JOHN CRANE 91125859 | 1 | EA | 0 | 0 | 2 | 1 | EA | 30.12 - SOH @ AA01 | Supply for Order 100033565, Item 3 cannot be changed 90025012 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015705 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180133964 | 9028684 | 05 | Preparation | 0000132019 | 3 | 0 | EA |  |  | 101000000129499 | 01-Road |  | 5-Completed |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  | 0 | 0 | 2025-01-30 | 2025-01-30 | Y | 1001 | 2024-09-24 | GRST-5000434510_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060903 | 1020 | 2024-10-12 | 1 |  | 2025-03-10 | 4900263271_2025_0001 | 2025-03-01 |  | 5000434510_2025_0001 | 0 | 2 | 0 | 90025012 | 1 | 0 | 180133964 | 2 | 0 | 0 | X | L | 4900263271 | 2025 |  | 5000434510 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10596547 | COUPLING,DRV;JOHN CRANE 91125859 | 2024-09-24 | W |  | 0010 | As Found Alignment Record | INT | As Found Alignment Record |  |  | 9028684_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ | 20005113 | AU1072 | 1000131501 | S002 | 30 | 30 | 5300015705 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-28 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132019 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0060 | 0010 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 124 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089887, Item 1 cannot be changed 90025037 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132390 | 9028798 | 05 | Preparation | 0000128156 | 1 | 0 | EA |  |  | 102000000034220 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000427922_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 195 |  | 2025-02-24 | 4900257751_2025_0001/4900257750_2025_0001/4900257472_2025_0001/4900257429_2025_0001 | 2025-03-01 | Air Filters | 5000427931_2025_0001/5000427922_2025_0001 | 0 | 2 | 0 | 90025037 | 195 | 0 | 180132200/180132390 | 2 | 0 | 0 | X | L |  | 0 |  | 5000427922 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 9028798_0010/9028234_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 10 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0060 | 0010 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 71 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089887, Item 1 cannot be changed 90025037 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132390 | 9028798 | 05 | Preparation | 0000128156 | 1 | 0 | EA |  |  | 102000000034195 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000427922_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 195 |  | 2025-02-24 | 4900257751_2025_0001/4900257750_2025_0001/4900257472_2025_0001/4900257429_2025_0001 | 2025-03-01 | Air Filters | 5000427931_2025_0001/5000427922_2025_0001 | 0 | 2 | 0 | 90025037 | 195 | 0 | 180132200/180132390 | 2 | 0 | 0 | X | L |  | 0 |  | 5000427922 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 9028798_0010/9028234_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 10 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0060 | 0080 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 96 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089888, Item 8 cannot be changed 90025038 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132144 | 9028365 | 05 | Preparation | 0000128157 | 8 | 0 | EA |  |  | 102000000034118 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | IDST-0180132144 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 195 |  | 2025-02-24 | 4900257389_2025_0001/4900257356_2025_0001 | 2025-03-01 | 200089888 | 5000427327_2025_0001/5000427307_2025_0001 | 0 | 2 | 0 | 90025038 | 195 | 0 | 180132144/180132169 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 9028365_0020/9028229_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0060 | 0080 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 99 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089888, Item 8 cannot be changed 90025038 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132144 | 9028365 | 05 | Preparation | 0000128157 | 8 | 0 | EA |  |  | 102000000034086 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | IDST-0180132144 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 195 |  | 2025-02-24 | 4900257389_2025_0001/4900257356_2025_0001 | 2025-03-01 | 200089888 | 5000427327_2025_0001/5000427307_2025_0001 | 0 | 2 | 0 | 90025038 | 195 | 0 | 180132144/180132169 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 9028365_0020/9028229_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0060 | 0080 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 82 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089889, Item 8 cannot be changed 90025039 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132145 | 9028366 | 05 | Preparation | 0000128158 | 8 | 0 | EA |  |  | 102000000034088 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 22 |  |  | Y | 1001 | 2024-10-17 | IDST-0180132145 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 173 |  | 2025-02-24 | 4900257369_2025_0001/4900257357_2025_0001 | 2025-03-01 | 200089889 | 5000427374_2025_0001/5000427277_2025_0001 | 0 | 2 | 0 | 90025039 | 173 | 0 | 180132145/180132165 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025039_0020/9028366_0020/9028226_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0060 | 0080 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 4 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089889, Item 8 cannot be changed 90025039 item 20 already exists | Material picked; currently at 30-03-06-81B/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132145 | 9028366 | 05 | Preparation | 0000128158 | 8 | 0 | EA |  |  | 101000000069699 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-06-81B | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 22 | 2025-01-18 | 2025-01-18 | Y | 1001 | 2024-10-17 | IDST-0180132145 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 173 |  | 2025-02-24 | 4900257369_2025_0001/4900257357_2025_0001 | 2025-03-01 | 200089889 | 5000427374_2025_0001/5000427277_2025_0001 | 0 | 2 | 0 | 90025039 | 173 | 0 | 180132145/180132165 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025039_0020/9028366_0020/9028226_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ | 20004585 | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-01-16 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0060 | 0080 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 91 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089889, Item 8 cannot be changed 90025039 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132145 | 9028366 | 05 | Preparation | 0000128158 | 8 | 0 | EA |  |  | 102000000034084 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 22 |  |  | Y | 1001 | 2024-10-17 | IDST-0180132145 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 173 |  | 2025-02-24 | 4900257369_2025_0001/4900257357_2025_0001 | 2025-03-01 | 200089889 | 5000427374_2025_0001/5000427277_2025_0001 | 0 | 2 | 0 | 90025039 | 173 | 0 | 180132145/180132165 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025039_0020/9028366_0020/9028226_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0060 | 0080 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 18 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089889, Item 8 cannot be changed 90025039 item 20 already exists | Material picked; currently at SW3R01C05B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132145 | 9028366 | 05 | Preparation | 0000128158 | 8 | 0 | EA |  |  | 101000000026721 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R01C05B | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 22 | 2025-01-18 | 2025-01-18 | Y | 1001 | 2024-10-17 | IDST-0180132145 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 173 |  | 2025-02-24 | 4900257369_2025_0001/4900257357_2025_0001 | 2025-03-01 | 200089889 | 5000427374_2025_0001/5000427277_2025_0001 | 0 | 2 | 0 | 90025039 | 173 | 0 | 180132145/180132165 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025039_0020/9028366_0020/9028226_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ | 20004585 | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-01-16 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0080 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 99 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089890, Item 8 cannot be changed 90025059 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132392 | 9028799 | 05 | Preparation | 0000128159 | 8 | 0 | EA |  |  | 102000000034181 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-10-17 | IDST-0180132392 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060049 | 1020 | 2024-07-12 | 165 |  | 2025-03-05 | 4900257752_2025_0001/4900257400_2025_0001 | 2025-03-01 | 200089890 | 5000427366_2025_0001 | 0 | 2 | 0 | 90025059 | 99 | 0 | 180132166/180132392 | 2 | 0 | 0 | X | L | 4900257752 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025059_0010/9028799_0010/9028227_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 10 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0080 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 195 | EA | 22 | 66 | 752 | 66 | EA | 20.02 - SOH @ AA02 | Supply for Order 200089890, Item 8 cannot be changed 90025059 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132392 | 9028799 | 05 | Preparation | 0000128159 | 8 | 0 | EA |  |  | 102000000034194 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-10-17 | IDST-0180132392 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060049 | 1020 | 2024-07-12 | 165 |  | 2025-03-05 | 4900257752_2025_0001/4900257400_2025_0001 | 2025-03-01 | 200089890 | 5000427366_2025_0001 | 0 | 2 | 0 | 90025059 | 99 | 0 | 180132166/180132392 | 2 | 0 | 0 | X | L | 4900257752 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025059_0010/9028799_0010/9028227_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 10 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0060 | 0080 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 90 | EA | 22 | 66 | 752 | 80 | EA | 18.10 - SOH @ AA01 | Supply for Order 200089891, Item 8 cannot be changed 90025062 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132146 | 9028367 | 05 | Preparation | 0000128160 | 8 | 0 | EA |  |  | 102000000034083 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | IDST-0180132146 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 90 |  | 2025-02-24 | 4900257388_2025_0001/4900257333_2025_0001 | 2025-03-01 | 200089891 | 5000427358_2025_0001/5000427308_2025_0001 | 0 | 2 | 0 | 90025062 | 90 | 0 | 180132146/180132168 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 9028367_0010/9028228_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 10 |  |  | 0 | 90 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0060 | 0080 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 90 | EA | 22 | 66 | 752 | 10 | EA | 18.10 - SOH @ AA01 | Supply for Order 200089891, Item 8 cannot be changed 90025062 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132146 | 9028367 | 05 | Preparation | 0000128160 | 8 | 0 | EA |  |  | 102000000034187 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | IDST-0180132146 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 90 |  | 2025-02-24 | 4900257388_2025_0001/4900257333_2025_0001 | 2025-03-01 | 200089891 | 5000427358_2025_0001/5000427308_2025_0001 | 0 | 2 | 0 | 90025062 | 90 | 0 | 180132146/180132168 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597094 | FILTER,CYL;324MM,660MM,DONALDSON P039671 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 9028367_0010/9028228_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 10 |  |  | 0 | 90 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0060 | 0020 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Shipped qty below requirement qty | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 190 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089887, Item 2 cannot be changed 90025037 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132180 | 9028231 | 05 | Preparation | 0000128156 | 2 | 0 | EA |  |  | 102000000034190 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-10-17 | GRST-5000427386_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000059577 | 1020 | 2024-07-12 | 190 |  | 2025-03-05 | 4900257396_2025_0001 | 2025-03-01 | Air Filters | 5000427386_2025_0001 | 0 | 2 | 0 | 90025037 | 190 | 0 | 180132180 | 1 | 0 | 0 | X | L | 4900257396 | 2025 |  | 5000427386 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025037_0020/9028231_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0060 | 0090 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Shipped qty below requirement qty | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 190 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089888, Item 9 cannot be changed 90025038 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132195 | 9028232 | 05 | Preparation | 0000128157 | 9 | 0 | EA |  |  | 102000000034191 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-10-17 | GRST-5000427490_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000059581 | 1020 | 2024-07-12 | 190 |  | 2025-03-05 | 4900257424_2025_0001 | 2025-03-01 | 200089888 | 5000427490_2025_0001 | 0 | 2 | 0 | 90025038 | 190 | 0 | 180132195 | 1 | 0 | 0 | X | L | 4900257424 | 2025 |  | 5000427490 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025038_0030/9028232_0030 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 30 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0060 | 0090 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 195 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089889, Item 9 cannot be changed 90025039 item 30 already exists | Material picked; currently at KSF-PACK-SD-LRG/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 9 | 0 | EA |  |  | 102000000028342 |  |  |  |  | WorkPackLink | KSF-PACK-SD-LRG | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 195 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089889 |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-16 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025039_0030 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 30 |  |  | 0 | 195 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 8 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at SW3R02H05B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000026675 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R02H05B | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-01-18 | 2025-01-18 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20004585 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-01-16 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 16 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at SW3R01A05A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000143706 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R01A05A | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-02-16 | 2025-02-15 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20005137 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 16 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at SW3R01A05B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000143705 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R01A05B | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-02-16 | 2025-02-15 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20005137 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 5 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at SW3R01E05B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000143709 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R01E05B | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-02-16 | 2025-02-15 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20005137 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 8 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at SW3R01C05A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000026676 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R01C05A | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-01-18 | 2025-01-18 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20004585 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-01-16 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 16 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at 30-03-01-84A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000143708 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-01-84A | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-02-16 | 2025-02-15 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20005137 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 16 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at 30-03-02-84B/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000143704 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-02-84B | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-02-16 | 2025-02-15 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20005137 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at SW3R02H01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000026678 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R02H01B | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-01-18 | 2025-01-18 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20004585 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-01-16 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 8 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at SW3R01B05B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000026674 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R01B05B | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-01-18 | 2025-01-18 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20004585 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-01-16 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 16 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at 30-03-01-84B/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 101000000143707 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-01-84B | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 | 2025-02-16 | 2025-02-15 | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ | 20005137 | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release | 2025-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2024-11-30 | 2024-11-25 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0060 | 0090 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 195 | EA | 308 | 0 | 537 | 3 | EA | 19.02 - SOH @ AA02 | Supply for Order 200089890, Item 9 cannot be changed 90023315 item 10 already exists | Material picked; currently at SW3R02G01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023315 | 05 | Preparation | 0000128159 | 9 | 0 | EA |  |  | 102000000031336 |  |  |  |  | WorkPackLink | SW3R02G01B | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 195 |  |  | Y | 1001 | 2024-10-17 | ODST-0090023315_0010 | 0 | 0 | 0 | 0 |  | 2024-11-28 | AA53 | 2025-03-01 |  |  | 2024-11-30 |  |  |  |  | 2024-07-12 | 0 |  | 2024-11-25 |  | 2024-11-30 | 200089890 |  | 0 | 2 | 0 | 90023315 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90023315_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 20 |  |  | 0 | 195 | EA | 2001 | AA02 | 2024-11-25 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0060 | 0090 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 90 | EA | 308 | 0 | 537 | 0 |  | 06.01 - ETA 28.02.25 PO 4500032031 Donaldson FCA | Supply for Order 200089891, Item 9 cannot be changed 90025062 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025062 | 05 | Preparation | 0000128160 | 9 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 90 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025062_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089891 |  | 0 | 2 | 0 | 90025062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597095 | FILTER,CON;405MM,711MM,DONALDSON P903627 | 2024-10-17 | W |  | 0060 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025062_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 20 |  |  | 0 | 90 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0140 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10597477 | MOTOR,AC;EX,3KW,400V,50HZ,TOSHIBA D100L | 1 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 28.03.25 PO 4500046066 ex Toshiba | Supply for Order 100079771, Item 14 cannot be changed 90030759 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030759 | 07 | Execution | 0000246943 | 14 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090030759_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90030759 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597477 | MOTOR,AC;EX,3KW,400V,50HZ,TOSHIBA D100L | 2025-02-12 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90030759_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 14 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 | 30 | 30 | 5300020063 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0772 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10597633 | SHIM;67E416-441.3-ZZ,SUS304,1.6MM | 2 | EA | 2 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 85 cannot be changed 90025019 item 820 already exists | Material picked; currently at SW3R01D01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 85 | 0 | EA | 102000000027606 |  | 102000000029625 |  |  |  |  | WorkPackLink | SW3R01D01A | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0820 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597633 | SHIM;67E416-441.3-ZZ,SUS304,1.6MM | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0820 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 85 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 820 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0782 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10597634 | SHIM;67E416-441.3-ZZ,SUS304,0.8MM | 4 | EA | 4 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 86 cannot be changed 90025019 item 830 already exists | Material picked; currently at SW3R01D01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 86 | 0 | EA | 102000000027607 |  | 102000000029625 |  |  |  |  | WorkPackLink | SW3R01D01A | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0830 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597634 | SHIM;67E416-441.3-ZZ,SUS304,0.8MM | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0830 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 86 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 830 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0792 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10597635 | SHIM;74E410-448.4-ZZ,SUS304,1.6MM | 2 | EA | 2 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 87 cannot be changed 90025019 item 840 already exists | Material picked; currently at SW3R01D01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 87 | 0 | EA | 102000000027608 |  | 102000000029625 |  |  |  |  | WorkPackLink | SW3R01D01A | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597635 | SHIM;74E410-448.4-ZZ,SUS304,1.6MM | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0840 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 87 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 840 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0802 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10597636 | SHIM;74E410-448.4-ZZ,SUS304,0.8MM | 4 | EA | 4 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 88 cannot be changed 90025019 item 850 already exists | Material picked; currently at SW3R01D01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 88 | 0 | EA | 102000000027609 |  | 102000000029625 |  |  |  |  | WorkPackLink | SW3R01D01A | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0850 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10597636 | SHIM;74E410-448.4-ZZ,SUS304,0.8MM | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0850 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 88 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 850 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1640 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10598466 | SPACER,RING;2ND STG NOZ,BAKER SMR74434 | 32 | EA | 0 | 0 | 0 | 0 |  | 05.12 - ETA 01.03.25 PO 4500031678 BH MOT GS4960731 1.1kg 22x22x15 | Supply for Order 200091513, Item 505 cannot be changed 90028419 item 3610 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 505 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3610 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10598466 | SPACER,RING;2ND STG NOZ,BAKER SMR74434 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_3610 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 505 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3640 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1630 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10598566 | BUSH,BTM;2ND,NOZ,BAKER HUGHES SMU26188 | 32 | EA | 0 | 0 | 0 | 0 |  | 17.02 - ETA 19.02.25 PO 4500031678 MOT 40794 BH FCA | Supply for Order 200091513, Item 504 cannot be changed 90028419 item 3600 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 504 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3600 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10598566 | BUSH,BTM;2ND,NOZ,BAKER HUGHES SMU26188 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_3600 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 504 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3630 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0110 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10600397 | SAW HOLE:BIMETAL;25MM,BORDO 701025 | 10 | EA | 0 | 0 | 10 | 10 | EA | 07.03 - SOH @ AA02 | Supply for Order 500005166, Item 13 cannot be changed 90031023 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180134138 | 9029109 | 05 | Preparation | 0000294187 | 13 | 0 | EA |  |  | 101000000150777 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000435340_2025 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 |  |  | 100000060590 | 1020 |  | 10 |  | 2025-03-10 | 4900263721_2025_0001 | 2025-03-11 | TA LAG_VORN | 5000435340_2025_0001 | 0 | 2 | 0 | 90031023 | 10 | 0 | 180134138 | 2 | 0 | 0 | X | L | 4900263721 | 2025 |  | 5000435340 | 2025 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10600397 | SAW HOLE:BIMETAL;25MM,BORDO 701025 | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 9029109_0110 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 13 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 120 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0100 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10600399 | MANDREL,HOLESAW;0.250",BORDO 70505514 | 2 | EA | 2 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 500005166, Item 12 cannot be changed 90031023 item 100 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031023 | 05 | Preparation | 0000294187 | 12 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031023_0100 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 | [5 empty] | 0 |  | 2025-03-06 |  | 2025-03-11 | TA LAG_VORN |  | 0 | 2 | 0 | 90031023 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10600399 | MANDREL,HOLESAW;0.250",BORDO 70505514 | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0100 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 12 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 110 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0130 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC |  | 10 | Issue detected, please check message in derivation or orchestration log | 10600755 | GAS,COMP;AR,SHIELDING,CYL,069F3VIPR | 6 | EA | 0 | 2 | 3 | 0 |  | 07.03 - ETA 09.04.25 PO 4500048766 BOC CPT | Supply for Order 100090053, Item 13 cannot be changed 90032376 item 130 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 13 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0130 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Ray R |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10600755 | GAS,COMP;AR,SHIELDING,CYL,069F3VIPR | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0130 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 13 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 130 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0120 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10601288 | INSULATION,BLKT;DUCTWRAP,CSR 170594871 | 10 | ROL | 5 | 0 | 6 | 0 |  | 24.02 - ETA 27.03.25 PO 4500047066 ARMACELL AUS CPT | Supply for Order 500005166, Item 32 cannot be changed 90031501 item 140 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 32 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0140 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10601288 | INSULATION,BLKT;DUCTWRAP,CSR 170594871 | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0140 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 32 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 280 |  |  | 0 | 10 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0110 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Voyage arrived: too late to meet planned Reqmt Date | 10604974 | INS,BLANKET;FIBREMESH,1X4M,50MM | 8 | EA | 4 | 0 | 28 | 8 | EA | 29.01 - At KGP | Supply for Order 200089373, Item 11 cannot be changed 9020875 item 110 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100534 | 9020875 | 07 | Execution | 0000127667 | 11 | 0 | EA |  |  | 102000000025551 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-P25-STONE-LRG | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 | 2024-12-06 |  | Y | 1001 | 2024-11-05 | GRST-5000304556_2024 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000044433 | 1020 | 2025-12-15 | 8 |  | 2024-12-03 | 4900184474_2024_0001 | 2024-11-10 | Troy Mac | 5000304556_2024_0001 | 0 | 2 | 0 | 90023594 | 8 | 0 | 180100534 | 1 | 0 | 0 | X | L | 4900184474 | 2024 |  | 5000304556 | 2024 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10604974 | INS,BLANKET;FIBREMESH,1X4M,50MM | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9020875_0110 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDFR2 | MJ | 1000004374 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 110 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-11-05 |  |  | 2024-12-06 |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144870 | 0010 | 0020 | 200144870 | 2Y Analyser Inspection 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.04.2024) | 10605758 | RING;HD,25X16X1.5MM,GR,HOBRE HI003565 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA01 | Supply for Order 200144870, Item 2 cannot be changed 90024977 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009068 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024977 | 05 | Preparation | 0000232065 | 2 | 0 | EA | 102000000033493 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024977_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408QT50 |  | 0 | 2 | 0 | 90024977 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605758 | RING;HD,25X16X1.5MM,GR,HOBRE HI003565 | 2024-04-13 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 |  | 90024977_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229152 | S002 | 30 | 30 | 5300009068 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232065 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147430 | 0010 | 0020 | 200147430 | 2Y Analyser Inspection 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10605758 | RING;HD,25X16X1.5MM,GR,HOBRE HI003565 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA01 | Supply for Order 200147430, Item 2 cannot be changed 90024980 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009772 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024980 | 05 | Preparation | 0000235835 | 2 | 0 | EA | 102000000033548 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024980_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90024980 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605758 | RING;HD,25X16X1.5MM,GR,HOBRE HI003565 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 | Ready for Release | 90024980_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232846 | S002 | 30 | 30 | 5300009772 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235835 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144870 | 0010 | 0030 | 200144870 | 2Y Analyser Inspection 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.04.2024) | 10605759 | SCREW,HEX;5/16"-24,SS,HOBRE HI106308 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA01 | Supply for Order 200144870, Item 3 cannot be changed 90024977 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009068 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024977 | 05 | Preparation | 0000232065 | 3 | 0 | EA | 102000000033549 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024977_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408QT50 |  | 0 | 2 | 0 | 90024977 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605759 | SCREW,HEX;5/16"-24,SS,HOBRE HI106308 | 2024-04-13 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 |  | 90024977_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229152 | S002 | 30 | 30 | 5300009068 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232065 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147430 | 0010 | 0030 | 200147430 | 2Y Analyser Inspection 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10605759 | SCREW,HEX;5/16"-24,SS,HOBRE HI106308 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA01 | Supply for Order 200147430, Item 3 cannot be changed 90024980 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009772 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024980 | 05 | Preparation | 0000235835 | 3 | 0 | EA | 102000000033550 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024980_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90024980 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605759 | SCREW,HEX;5/16"-24,SS,HOBRE HI106308 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 | Ready for Release | 90024980_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232846 | S002 | 30 | 30 | 5300009772 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235835 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144870 | 0010 | 0040 | 200144870 | 2Y Analyser Inspection 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.04.2024) | 10605820 | O-RING;ZE MIX CHAMBER,HOBRE HI106904 | 1 | EA | 2 | 0 | 0 | 0 |  | 19.02 - SOH @ AA02 | Supply for Order 200144870, Item 4 cannot be changed 90024977 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300009068 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024977 | 05 | Preparation | 0000232065 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024977_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408QT50 |  | 0 | 2 | 0 | 90024977 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605820 | O-RING;ZE MIX CHAMBER,HOBRE HI106904 | 2024-04-13 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 |  | 90024977_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229152 | S002 | 30 | 30 | 5300009068 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232065 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147430 | 0010 | 0040 | 200147430 | 2Y Analyser Inspection 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10605820 | O-RING;ZE MIX CHAMBER,HOBRE HI106904 | 1 | EA | 2 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200147430, Item 4 cannot be changed 90024980 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009772 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024980 | 05 | Preparation | 0000235835 | 4 | 0 | EA | 102000000033920 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024980_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90024980 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605820 | O-RING;ZE MIX CHAMBER,HOBRE HI106904 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 | Ready for Release | 90024980_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232846 | S002 | 30 | 30 | 5300009772 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235835 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144870 | 0010 | 0050 | 200144870 | 2Y Analyser Inspection 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.04.2024) | 10605821 | O-RING;ZE MIX CHAMBER,HOBRE HI108885 | 1 | EA | 2 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200144870, Item 5 cannot be changed 90024977 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009068 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024977 | 05 | Preparation | 0000232065 | 5 | 0 | EA | 102000000033921 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024977_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408QT50 |  | 0 | 2 | 0 | 90024977 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605821 | O-RING;ZE MIX CHAMBER,HOBRE HI108885 | 2024-04-13 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 |  | 90024977_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229152 | S002 | 30 | 30 | 5300009068 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232065 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147430 | 0010 | 0050 | 200147430 | 2Y Analyser Inspection 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10605821 | O-RING;ZE MIX CHAMBER,HOBRE HI108885 | 1 | EA | 2 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200147430, Item 5 cannot be changed 90024980 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009772 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024980 | 05 | Preparation | 0000235835 | 5 | 0 | EA | 102000000033922 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024980_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90024980 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605821 | O-RING;ZE MIX CHAMBER,HOBRE HI108885 | 2024-05-03 | W |  | 0010 | Function Test & Complete PRT's | INT | Function Test & Complete PRT's | 5 | Ready for Release | 90024980_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232846 | S002 | 30 | 30 | 5300009772 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235835 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-04-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200144871 | 0010 | 0030 | 200144871 | 1Y Analyser Filter Replacement 408QT501 | AA53.408QT501 | ANLZ,GT4008FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.04.2024) | 10605822 | FILTER,HYD;HOBRE HI100706 | 2 | EA | 6 | 0 | 0 | 2 | EA | 07.03 - SOH @ AA02 | Supply for Order 200144871, Item 3 cannot be changed 90024976 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009067 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024976 | 05 | Preparation | 0000232066 | 3 | 0 | EA | 102000000033486 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-04-13 | ODST-0090024976_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-07 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024976 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605822 | FILTER,HYD;HOBRE HI100706 | 2024-04-13 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024976_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000229153 | S002 | 30 | 30 | 5300009067 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 232066 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-05-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200147431 | 0010 | 0030 | 200147431 | 1Y Analyser Filter Replacement 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(03.05.2024) | 10605822 | FILTER,HYD;HOBRE HI100706 | 2 | EA | 6 | 0 | 0 | 2 | EA | 07.03 - SOH @ AA02 | Supply for Order 200147431, Item 3 cannot be changed 90024979 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009771 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024979 | 05 | Preparation | 0000235836 | 3 | 0 | EA | 102000000033488 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-05-03 | ODST-0090024979_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 409QT501 |  | 0 | 2 | 0 | 90024979 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605822 | FILTER,HYD;HOBRE HI100706 | 2024-05-03 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | Ready for Release | 90024979_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232847 | S002 | 30 | 30 | 5300009771 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235836 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-08-10 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | QMI | 200160195 | 0010 | 0030 | 200160195 | 1Y Analyser Filter Replace 407QT501 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.08.2024) | 10605822 | FILTER,HYD;HOBRE HI100706 | 2 | EA | 6 | 0 | 0 | 2 | EA | 07.03 - SOH @ AA02 | Supply for Order 200160195, Item 3 cannot be changed 90024993 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013873 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024993 | 05 | Preparation | 0000256082 | 3 | 0 | EA | 102000000033487 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-08-10 | ODST-0090024993_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 407QT501 |  | 0 | 2 | 0 | 90024993 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605822 | FILTER,HYD;HOBRE HI100706 | 2024-08-10 | W |  | 0010 | Complete Filter Replacement & PRT | INT | Complete Filter Replacement & PRT | 5 |  | 90024993_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000252060 | S002 | 30 | 30 | 5300013873 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240810 | 2024-08-10 | 256082 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | VALVE | 100032678 | 0010 | 0090 | 100032678 | CV-OH 1" 300# 118PDCV506 | AA53.118PDCV506 | VALVE,1K1820E1 S/OIL PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10605918 | BUSH,PKG BX;VV,FISHER 1E839135012 | 1 | EA | 0 | 0 | 0 | 0 |  | 30.12 - ETA 14.04.25 PO 4500039296 SCORE CPT | Supply for Order 100032678, Item 9 cannot be changed 90028294 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019181 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028294 | 05 | Preparation | 0000131170 | 9 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028294_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032678 |  | 0 | 2 | 0 | 90028294 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605918 | BUSH,PKG BX;VV,FISHER 1E839135012 | 2024-12-16 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028294_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130520 | S002 | 30 | 30 | 5300019181 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131170 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-02-27 | 2025-03-04 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0060 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10606307 | RELAY,EARTHFAULT;0.02-5A,S&S CEP71EGJ | 1 | EA | 0 | 0 | 2 | 0 |  | 07.03 - PR 2000283508 RFQ | Supply for Order 600001363, Item 13 cannot be changed 90032183 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032183 | 05 | Preparation | 0000084301 | 13 | 0 | [8 empty] | WorkPackLink |  | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-27 | ODST-0090032183_0010 | 0 | 10 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-27 |  |  | 2025-03-09 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-04 |  | 2025-03-09 | Scott Kinloc |  | 0 | 2 | 0 | 90032183 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10606307 | RELAY,EARTHFAULT;0.02-5A,S&S CEP71EGJ | 2025-03-04 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90032183_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 13 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 | 30 | 30 | 5300018438 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDSTB5 | Released | 2025-02-08 | 2025-02-27 | 2025-03-04 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0080 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10606308 | XMFR,CURRENT,TORROID;45A,S&S CEP7CBCT1 | 1 | EA | 0 | 0 | 2 | 0 |  | 07.03 - PR 2000283498 RFQ | Supply for Order 600001363, Item 15 cannot be changed 90032183 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032183 | 05 | Preparation | 0000084301 | 15 | 0 | [8 empty] | WorkPackLink |  | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-27 | ODST-0090032183_0030 | 0 | 10 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-27 |  |  | 2025-03-09 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-04 |  | 2025-03-09 | Scott Kinloc |  | 0 | 2 | 0 | 90032183 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10606308 | XMFR,CURRENT,TORROID;45A,S&S CEP7CBCT1 | 2025-03-04 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90032183_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 15 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 | 30 | 30 | 5300018438 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100043726 | 0010 | 0070 | 100043726 | Accelerometer Replace 123XT105 1K2301 | AA53.123XT105 | TXDCR,ACCELEROMETER 1K2301 | AA01 | 30 | No issue identified | 10606829 | SENSOR,VIB;EX,100MV/G,BRUEL ASA0621001 | 2 | EA | 1 | 0 | 0 | 0 |  | 10.03 - ETA 28.03.25 PO 4500048732 NSK CPT |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001396 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030038 | 05 | Preparation | 0000142227 | 7 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030038_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123XT105 |  | 0 | 2 | 0 | 90030038 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10606829 | SENSOR,VIB;EX,100MV/G,BRUEL ASA0621001 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90030038_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 7 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000141596 | S002 | 30 | 30 | 5300001396 | 60 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100043726 | 0010 | 0040 | 100043726 | Accelerometer Replace 123XT105 1K2301 | AA53.123XT105 | TXDCR,ACCELEROMETER 1K2301 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(26.09.2024) | 10606829 | SENSOR,VIB;EX,100MV/G,BRUEL ASA0621001 | 1 | EA | 1 | 0 | 0 | 1 | EA | 10.03 - SOH @ AA02 | Supply for Order 100043726, Item 4 cannot be changed 90024944 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300001396 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024944 | 05 | Preparation | 0000142227 | 4 | 0 | EA | 101000000133715 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024944_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123XT105 |  | 0 | 2 | 0 | 90024944 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10606829 | SENSOR,VIB;EX,100MV/G,BRUEL ASA0621001 | 2024-09-26 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90024944_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000141596 | S002 | 30 | 30 | 5300001396 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0060 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10609359 | CONDUIT;16MMX15M,WATTMASTER AEF3815 | 30 | M | 30 | 0 | 0 | 15 | M | 24.02 - SOH @ AA02 | Supply for Order 200089806, Item 6 cannot be changed 90024958 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003900 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90024958 | 05 | Preparation | 0000128060 | 6 | 0 | M | 101000000136714 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024958_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024958 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10609359 | CONDUIT;16MMX15M,WATTMASTER AEF3815 | 2024-10-17 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024958_0040 |  |  | FR1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127469 | S002 | 30 | 30 | 5300003900 | 40 |  |  | 0 | 30 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128060 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0060 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10609359 | CONDUIT;16MMX15M,WATTMASTER AEF3815 | 30 | M | 30 | 0 | 0 | 15 | M | 24.02 - SOH @ AA02 | Supply for Order 200089806, Item 6 cannot be changed 90024958 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003900 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90024958 | 05 | Preparation | 0000128060 | 6 | 0 | M | 101000000147278 |  | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024958_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024958 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10609359 | CONDUIT;16MMX15M,WATTMASTER AEF3815 | 2024-10-17 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024958_0040 |  |  | FR1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127469 | S002 | 30 | 30 | 5300003900 | 40 |  |  | 0 | 30 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128060 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0070 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10609400 | FITTING,CDUIT;STR,M16,WATTMASTER C16M16 | 20 | EA | 20 | 0 | 0 | 20 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089806, Item 7 cannot be changed 90024958 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003900 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024958 | 05 | Preparation | 0000128060 | 7 | 0 | EA | 102000000031384 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024958_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024958 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10609400 | FITTING,CDUIT;STR,M16,WATTMASTER C16M16 | 2024-10-17 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024958_0050 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 7 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127469 | S002 | 30 | 30 | 5300003900 | 50 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128060 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-05-18 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0040 | 0020 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2024) | 10610690 | ACCUMULATOR,HYD;HEA HEA2311607D002 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - At KGP | Supply for Order 600001290, Item 2 cannot be changed 180033490 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180033490 | 9004496 | 05 | Preparation | 0000084206 | 2 | 0 | EA |  |  | 102000000008911 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08C12L3 | AA53-P08-LN | 0 | 5400001209 | 10 | 1 | EA | 1 | 0 |  |  | Y | 1001 | 2024-02-12 |  | 0 | 0 | 0 | 0 |  | 2024-05-19 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000012508 | 1020 | 2024-05-13 | 1 |  | 2024-06-10 | 4900072280_2024_0001 | 2024-05-21 |  | 5000113465_2024_0001 | 0 | 2 | 0 | 90006510 | 1 | 0 | 180033490/180101031 | 2 | 0 | 0 | X | L | 4900072280 | 2024 |  | 5000113465 | 2024 | 0 |  | 2024-05-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10610690 | ACCUMULATOR,HYD;HEA HEA2311607D002 | 2024-02-12 | W |  | 0040 | MOC-113604 Install BD 4KT1410V6A/B | INT | MOC-113604 Install BD 4KT1410V6A/B |  | Management of Change | 9004496_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ | 1000002010 | AU1072 | 1000083560 | S002 | 30 | 30 | 5300006479 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-18 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-05-09 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0110 | 0030 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.10.2024) | 10611470 | 5x HMV 16/233983 | 5 | EA | 5 | 0 | 0 | 5 | EA | 25.02 - SOH @ AA02 | Supply for Order 200091505, Item 101 cannot be changed 90025020 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025020 | 05 | Preparation | 0000129754 | 101 | 0 | EA | 101000000148358 |  | 101000000148055 | 01-Road |  | 5-Completed |  | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 5 | 2025-02-27 | 2025-02-26 | Y | 1001 | 2024-09-30 | ODST-0090025020_0010 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-03-01 |  |  | 2025-05-14 |  |  |  |  | 2025-06-05 | 0 |  | 2025-05-09 |  | 2025-05-14 | Sim/Jord |  | 0 | 2 | 0 | 90025020 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10611470 | 5x HMV 16/233983 | 2024-10-15 | W |  | 0110 | Special Tooling | INT | Special Tooling | 0 |  | 90025020_0010 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 101 |  | 0 |  | 25SDFR1 | MJ | 20005551 | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 890 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-05-09 |  |  | 2025-02-24 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0110 | 0040 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.10.2024) | 10611471 | 5x HMV 30/233983 | 5 | EA | 0 | 0 | 0 | 5 | EA | 29.01 - At KGP | Supply for Order 200091505, Item 102 cannot be changed 9026119 item 870 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 900 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117402 | 9026119 | 05 | Preparation | 0000129754 | 102 | 0 | EA | 101000000134371 |  | 102000000030520 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07-WAREHOUSE | P07 | 0 |  | 0 | 0 |  | 5 | 0 |  |  | Y | 1001 | 2024-09-30 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000054503 | 1020 | 2025-06-05 | 5 |  | 2025-01-22 | 4900216307_2025_0001 | 2025-03-01 | Sim/Jord | 5000369094_2025_0001 | 0 | 2 | 0 | 90025019 | 5 | 0 | 180117402 | 2 | 0 | 0 | X | L | 4900216307 | 2025 |  | 5000369094 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10611471 | 5x HMV 30/233983 | 2024-10-15 | W |  | 0110 | Special Tooling | INT | Special Tooling | 0 |  | 9026119_0870 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 102 |  | 0 |  | 25SDFR1 | MJ | 1000004874 | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 900 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-22 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-05-03 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0040 | 0040 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | No Issue identified | 10612501 | DISC,BURST;12MPAG,HYDENERGY PBST1212MPAG | 9 | EA | 2 | 0 | 9 | 0 |  | 13.02 - ETA 11.04.25 PO 4500045892 ex Hyd Energy |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084206 | 14 | 0 | [8 empty] | WorkPackLink |  | Sean Hill - Dylan Morgan | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2024-02-12 | STST-5300006479_00110 | 0 | 0 | 0 | 0 |  | 2025-05-06 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-05-13 | 0 |  | 2025-05-03 |  | 2025-05-08 |  |  | 0 | 2 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10612501 | DISC,BURST;12MPAG,HYDENERGY PBST1212MPAG |  |  |  | 0040 | MOC-113604 Install BD 4KT1410V6A/B | INT | MOC-113604 Install BD 4KT1410V6A/B |  | Management of Change |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 14 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083560 | S002 | 30 | 30 | 5300006479 | 110 |  |  | 0 | 9 | EA | 2001 | AA02 | 2025-05-03 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SD2301 | Released | 2024-01-02 | 2025-07-02 | 2025-06-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0100 | 0030 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10613407 | PISTON,HALF;CRANK,THOMASSEN 2734214100 | 2 | EA | 0 | 0 | 0 | 2 | EA | 29.01 - Consumed | Supply for Order 200091126, Item 150 cannot be changed 90023535 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180116481 | 90023535 | 05 | Preparation | 0000129360 | 150 | 0 | EA |  |  | 101000000053973 |  |  |  |  | WorkPackLink | P07-WAREHOUSE | P07 | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2025-06-30 | AA53 | 2025-03-01 |  |  | 2025-07-02 |  |  | 100000053327 | 1020 | 2023-04-03 | 2 |  | 2025-01-20 | 4900214561_2025_0001 | 2025-07-02 |  | 5000365671_2025_0001 | 0 | 2 | 0 | 90023535 | 2 | 0 | 180116481 | 2 | 0 | 0 | X | L | 4900214561 | 2025 |  | 5000365671 | 2025 | 0 |  | 2025-06-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613407 | PISTON,HALF;CRANK,THOMASSEN 2734214100 | 2024-09-30 | W |  | 0100 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90023535_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 150 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 1260 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-06-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-07-02 | 2025-06-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0100 | 0040 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(04.11.2024) | 10613408 | PISTON,HALF;HEAD,THOMASSEN 2734214200 | 2 | EA | 0 | 0 | 0 | 2 | EA | 29.01 - Consumed | Supply for Order 200091126, Item 151 cannot be changed 90023535 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180116481 | 90023535 | 05 | Preparation | 0000129360 | 151 | 0 | EA |  |  | 101000000053971 |  |  |  |  | WorkPackLink | P07-WAREHOUSE | P07 | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2025-06-30 | AA53 | 2025-03-01 |  |  | 2025-07-02 |  |  | 100000053327 | 1020 | 2023-04-03 | 2 |  | 2025-01-20 | 4900214561_2025_0003 | 2025-07-02 |  | 5000365671_2025_0002 | 0 | 2 | 0 | 90023535 | 2 | 0 | 180116481 | 2 | 0 | 0 | X | L | 4900214561 | 2025 |  | 5000365671 | 2025 | 0 |  | 2025-06-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613408 | PISTON,HALF;HEAD,THOMASSEN 2734214200 | 2024-11-04 | W |  | 0100 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90023535_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 151 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 1270 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-06-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-02-07 | 2025-01-31 | 2025-02-07 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0030 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(07.02.2025) | 10619073 | SWITCHBOX;K1,TOPWORX K1SN20FNMS00000N011 | 2 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 11.04.25 PO 4500045894 ex Severn CRITICAL | Supply for Order 600001473, Item 3 cannot be changed 90030516 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020972 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030516 | 05 | Preparation | 0000084391 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030516_0030 | 0 | 12 | 0 | 0 |  | 2025-01-29 | AA53 | 2025-05-08 |  |  | 2025-02-12 |  |  |  |  | 2025-12-15 | 0 |  | 2025-02-07 |  | 2025-02-12 | 4V1302 |  | 0 | 2 | 0 | 90030516 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-07 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10619073 | SWITCHBOX;K1,TOPWORX K1SN20FNMS00000N011 | 2025-02-07 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90030516_0030 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083795 | S002 | 30 | 30 | 5300020972 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-07 |  | Engineering Query/Management of Change |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84391 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 100042344 | 0010 | 0030 | 100042344 | MOC-118617 Inlet Fan Replace G4008S2KM1 | AA53.G4008S2KM1 | MOTOR,GEN AIRINLET FILTHSE SCAVFAN,G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(31.05.2024) | 11400357 | MOTOR,AC;EX,3PH,2P,0.75KW,415V,50HZ,IP56 | 1 | EA | 0 | 0 | 1 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 100042344, Item 3 cannot be changed 90024985 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300010986 | 10 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180130048 | 90024985 | 05 | Preparation | 0000140796 | 3 | 0 | EA | 102000000033816 |  | 107000000000758 |  |  |  | GT8 2025 | WorkPackLink | P07-WAREHOUSE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-31 | GRST-5000419341_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000059131 | 1020 | 2021-10-05 | 1 |  | 2025-02-27 | 4900250617_2025_0001 | 2025-03-01 | G40082KM1 | 5000419341_2025_0001 | 0 | 2 | 0 | 90024985 | 1 | 0 | 180130048 | 2 | 0 | 0 | X | L | 4900250617 | 2025 |  | 5000419341 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400357 | MOTOR,AC;EX,3PH,2P,0.75KW,415V,50HZ,IP56 | 2024-05-31 | W |  | 0010 | Remove & Replace Motor | INT | Remove & Replace Motor | 5 |  | 90024985_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000140226 | S002 | 30 | 30 | 5300010986 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140796 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038511 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038465 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038513 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038466 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038514 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038516 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038518 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038467 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038510 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038517 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038515 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-02-21 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-04-29 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Space Heaters Repl (12) - GT8 | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2024) | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100043183, Item 1 cannot be changed 180022648 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006924 | 10 | CPT | 48 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-22 |  | 180020135 | 180023282 | 90007460 | 05 | Preparation | 0000141707 | 1 | 0 | EA | 101000000038512 |  | 102000000005788 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-KGP P07P08 SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 12 | 0 |  |  | Y | 1001 | 2024-02-21 |  | 0 | 7 | 0 | 7 | 2024-04-18 | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2024-05-14 | 2024-04-20 | 2024-05-07 | 100000007718 | 1020 | 2022-06-15 | 12 | 5000072171_2024_0001/5000072166_2024_0001/5000072163_2024_0001/5000072157_2024_0001/5000072156_2024_0001/5000072155_2024_0001/5000072154_2024_0001/5000072149_2024_0001/5000072147_2024_0001/5000072144_2024_0001/5000072134_2024_0001/5000072133_2024_0001 | 2024-05-07 | 4900054536_2024_0001 | 2024-05-02 | G4008E2 | 5000075851_2024_0001 | 0 | 2 | 2 | 90007460 | 12 | 12 | 180023282 | 2 | 0 | 0 | X | L | 4900054536 | 2024 | 5000072157 | 5000075851 | 2024 | 2024 | 180020135 | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 2024-02-21 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90007460_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-23 | 20 |  | 2024-04-20 | 1 |  | 0 |  | 25SDGT8 | MJ | 1000001497 | AU1072 | 1000141038 | S002 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141707 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-03-05 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0010 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 |  | 10 | Supply too early, consider delaying | 11400906 | BAR,FLAT;60X3X1000MM,SS316 | 5 | EA | 5 | 4 | 0 | 0 |  | 16.12 - qty 5 SOH @ AA02 | Supply for Order 600001290, Item 13 cannot be changed 90023533 item 10 already exists | Material is received @AA02 | SP14 | Directs (Inventory) | 182 | AA02 | 5300006479 | 100 | CPT | 7 | 1000019389 | 13 | 30001929 | INFRABUILD TRADING PTY LTD | 4500029963 | 10 | 5 | EA | 2024-10-11 |  | 180089716 |  | 90023533 | 05 | Preparation | 0000084206 | 13 | 0 | [8 empty] | WorkPackLink |  | AA53-P08-LN | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-02-12 | ODST-0090023533_0010 | 0 | 19 | 0 | 19 | 2025-03-22 | 2025-03-08 | AA53 | 2025-05-08 |  |  | 2025-04-12 |  | 2025-03-24 |  |  | 2024-05-13 | 0 | 5000268426_2024_0001 | 2025-03-05 |  | 2024-11-05 |  |  | 0 | 2 | 2 | 90023533 | 0 | 5 |  | 1 | 0 | 0 | X | L |  | 0 | 5000268426 |  | 0 | 2024 | 180089716 | 2025-03-05 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400906 | BAR,FLAT;60X3X1000MM,SS316 | 2024-09-16 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 90023533_0010 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-09-17 | 5 | 6000009519 | 2025-03-24 | 13 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083560 | S002 | 30 | 30 | 5300006479 | 100 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-03-05 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-04-05 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0070 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(26.03.2024) | 11401449 | CONN TBG:0.25X0.5",GYRO 4CM8316EA | 4 | EA | 0 | 0 | 0 | 4 | EA | 02.10 - At KGP | Supply for Order 600001290, Item 11 cannot be changed 180017042 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 48 | AA02 | 5300006479 | 80 | CPT | 7 | 1000006895 | 11 | 30000271 | PROCHEM PIPELINE PRODUCTS PTY LTD | 4500009368 | 20 | 4 | EA | 2024-04-09 |  | /180015197 | 180017791 | 9001932 | 05 | Preparation | 0000084206 | 11 | 0 | EA |  |  | 102000000004588 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08C12R2 | AA53-P08-LN | 0 |  | 0 | 0 |  | 4 | 0 |  |  | Y | 1001 | 2024-02-12 |  | 0 | 66 | 57 | 66 | 2024-05-27 | 2024-04-06 | AA53 | 2025-05-08 |  |  | 2024-06-20 | 2024-05-29 | 2024-06-10 | 100000006221 | 1020 | 2024-05-13 | 4 | 5000054342_2024_0001 | 2024-04-14 | 4900046281_2024_0001 | 2024-04-08 |  | 5000060183_2024_0001 | 0 | 2 | 2 | 90006964 | 4 | 4 | 180017791/180099822 | 2 | 0 | 0 | X | L | 4900046281 | 2024 | 5000054342 | 5000060183 | 2024 | 2024 | /018001519 | 2024-04-05 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401449 | CONN TBG:0.25X0.5",GYRO 4CM8316EA | 2024-03-26 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9001932_0030 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-04-02 | 5 |  | 2024-05-29 | 11 |  | 0 |  | 25SDLN4 | MJ | 1000001218 | AU1072 | 1000083560 | S002 | 30 | 30 | 5300006479 | 80 |  | 5300008370 | 10 | 4 | EA | 2001 | AA02 | 2024-04-05 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-04-05 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0080 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(26.03.2024) | 11401535 | CONNECTOR,TBG;0.25X0.5",GYRO 4CF8316EZ | 4 | EA | 0 | 0 | 4 | 4 | EA | 29.01 - At KGP | Supply for Order 600001290, Item 12 cannot be changed 180037303 item 10 already exists | Materials handed over to w/ Maintenance | SP97 | Direct Multi-base | 48 | AA02 | 5300006479 | 90 | CPT | 7 | 1000006909 | 12 | 30000271 | PROCHEM PIPELINE PRODUCTS PTY LTD | 4500009368 | 10 | 4 | EA | 2024-06-05 |  | /180027198/180015197 | 180099823 | 9021311 | 05 | Preparation | 0000084206 | 12 | 0 | EA | 102000000025469 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-P08-LN | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-12 | GRST-5000301725_2024 | 0 | 215 | 57 | 145 | 2024-05-27 | 2024-04-06 | AA53 | 2025-05-08 |  |  | 2025-07-05 | 2024-05-29 | 2024-08-28 | 100000044260 | 1020 | 2024-05-13 | 4 | 5000112963_2024_0001 | 2024-12-02 | 4900183261_2024_0001 | 2024-06-17 |  | 5000301725_2024_0001 | 0 | 2 | 2 | 90006964 | 4 | 4 | 180099823/180099822 | 2 | 0 | 0 | X | L | 4900183261 | 2024 | 5000112963 | 5000301725 | 2024 | 2024 | /018002719 | 2024-04-05 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401535 | CONNECTOR,TBG;0.25X0.5",GYRO 4CF8316EZ | 2024-03-26 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9021311_0040 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-04-02 | 5 |  | 2024-05-29 | 12 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083560 | S002 | 30 | 30 | 5300006479 | 90 |  | 5300008370 | 20 | 4 | EA | 2001 | AA02 | 2024-04-05 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0110 | 0060 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | WO item has not been released yet | 11401610 | GASKET,SHLD PLUG;29X35X3MM,SI | 230 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000126825 | 11 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 230 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-10-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401610 | GASKET,SHLD PLUG;29X35X3MM,SI |  |  |  | 0110 | Punchlist & Closeout WP200088516MET001 | ENON | Punchlist & Closeout WP200088516MET001 | 5 | Ready for Release |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000126175 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0100 | 0050 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 11401610 | GASKET,SHLD PLUG;29X35X3MM,SI | 70 | EA | 0 | 0 | 0 | 0 |  | 21.02 - ETA 04.04.25 PO 4500046738 JORD EXW | Supply for Order 200088516, Item 9 cannot be changed 90029085 item 40 already exists | Vendor PO raised | SP97 | Direct Multi-base | 36 | AA01 | 5300020033 | 40 | EXW | 7 | 1000027748 | 9 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500046738 | 10 | 70 | EA | 2025-04-04 |  |  |  | 90029085 | 05 | Preparation | 0000126825 | 9 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2025-01-14 | ODST-0090029085_0040 | 0 | 16 | 16 | 16 | 2025-02-26 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-03-17 | 2025-02-28 | 2025-03-12 |  |  | 2025-10-31 | 0 |  | 2025-02-12 |  | 2025-02-24 |  |  | 0 | 2 | 2 | 90029085 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401610 | GASKET,SHLD PLUG;29X35X3MM,SI | 2025-01-14 | W |  | 0100 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | 5 | Ready for Release | 90029085_0040 |  |  | ST5 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-14 | 5 | 6000014382 | 2025-02-28 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000126175 | S001 | 30 | 30 | 5300020032 | 90 |  | 5300020033 | 40 | 70 | EA | 1001 | AA02 | 2025-02-12 |  | Ready for Release |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0100 | 0030 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 11401641 | PLUG,INSTR;1.125",12UNF,JORD JO-A2D-3Q4 | 35 | EA | 0 | 0 | 0 | 0 |  | 21.02 - ETA 18.04.25 PO 4500047058 JORD FCA | Supply for Order 200088516, Item 7 cannot be changed 90029085 item 20 already exists | Vendor PO raised | SP97 | Direct Multi-base | 36 | AA01 | 5300020033 | 20 | FCA | 7 | 1000027748 | 7 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500047058 | 10 | 35 | EA | 2025-04-18 |  |  |  | 90029085 | 05 | Preparation | 0000126825 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 35 |  |  | Y | 1001 | 2025-01-14 | ODST-0090029085_0020 | 0 | 16 | 16 | 16 | 2025-02-26 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-03-17 | 2025-02-28 | 2025-03-12 |  |  | 2025-10-31 | 0 |  | 2025-02-12 |  | 2025-02-24 |  |  | 0 | 2 | 2 | 90029085 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401641 | PLUG,INSTR;1.125",12UNF,JORD JO-A2D-3Q4 | 2025-01-14 | W |  | 0100 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | 5 | Ready for Release | 90029085_0020 |  |  | ST5 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-14 | 5 | 6000014091 | 2025-02-28 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000126175 | S001 | 30 | 30 | 5300020032 | 70 |  | 5300020033 | 20 | 35 | EA | 1001 | AA02 | 2025-02-12 |  | Ready for Release |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0100 | 0020 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 11401642 | TAP,HAND,UNF,1-1/8IN,TAPER,CS | 2 | EA | 2 | 0 | 0 | 2 | EA | 20.01 - ETA 19.02.25 PO 4500042929 BLACKWOODS CPT | Supply for Order 200088516, Item 6 cannot be changed 180125590 item 10 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 30 | AA02 | 5300020032 | 60 | CPT | 7 | 1000027748 | 6 | 30000394 | J BLACKWOOD AND SON LTD | 4500042929 | 40 | 2 | EA | 2025-02-19 |  | /180123558 |  | 90028586 | 05 | Preparation | 0000126825 | 6 | 0 | EA | 102000000031883 | 102000000033016 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028586_0060 | 0 | 10 | 10 | 10 | 2025-02-20 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-11 | 2025-02-22 | 2025-02-26 |  |  | 2025-10-31 | 0 | 5000394091_2025_0001 | 2025-02-24 |  | 2025-02-10 |  |  | 0 | 2 | 2 | 90028586 | 0 | 2 |  | 2 | 0 | 0 | X | L |  | 0 | 5000394091 |  | 0 | 2025 | /018012355 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401642 | TAP,HAND,UNF,1-1/8IN,TAPER,CS | 2025-01-14 | W |  | 0100 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | 5 | Ready for Release | 90028586_0060 |  |  | ST5 |  | A3 | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-14 | 5 | 6000014088 | 2025-02-22 | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126175 | S002 | 30 | 30 | 5300020032 | 60 |  | 5300020033 | 10 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126825 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0100 | 0040 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 11401651 | PLUG,INSTR;1.125",12UNF,JORD JO-A2D-3Q5 | 35 | EA | 0 | 0 | 0 | 0 |  | 24.02 - ETA 18.04.25 PO 4500047058 JORD FCA | Supply for Order 200088516, Item 8 cannot be changed 90029085 item 30 already exists | Vendor PO raised | SP97 | Direct Multi-base | 36 | AA01 | 5300020033 | 30 | FCA | 7 | 1000027748 | 8 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500047058 | 20 | 35 | EA | 2025-04-18 |  |  |  | 90029085 | 05 | Preparation | 0000126825 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 35 |  |  | Y | 1001 | 2025-01-14 | ODST-0090029085_0030 | 0 | 16 | 16 | 16 | 2025-02-26 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-03-17 | 2025-02-28 | 2025-03-12 |  |  | 2025-10-31 | 0 |  | 2025-02-12 |  | 2025-02-24 |  |  | 0 | 2 | 2 | 90029085 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401651 | PLUG,INSTR;1.125",12UNF,JORD JO-A2D-3Q5 | 2025-01-14 | W |  | 0100 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | 5 | Ready for Release | 90029085_0030 |  |  | ST5 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-14 | 5 | 6000014091 | 2025-02-28 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000126175 | S001 | 30 | 30 | 5300020032 | 80 |  | 5300020033 | 30 | 35 | EA | 1001 | AA02 | 2025-02-12 |  | Ready for Release |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-25 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0080 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.07.2024) | 11403708 | STUDBOLT;1.750"X350MM,B8MCL2,PLN | 52 | EA | 0 | 0 | 104 | 52 | EA | 16.12 - AT KGP | Supply for Order 600001757, Item 14 cannot be changed 180099144 item 20 already exists | Material work-packed @AA53 | SP97 | Direct Multi-base | 70 | AA02 | 5300005523 | 130 | CPT | 7 | 1000015448 | 14 | 30000148 | TRISTAR AUSTRALIA PTY LTD | 4500025023 | 20 | 52 | EA | 2025-01-05 |  | /180095308 | 180099854 | 9021322 | 07 | Execution | 0000084653 | 14 | 0 | EA |  |  | 101000000116115 |  |  |  |  | WorkPackLink | P07YRDBY13 | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-24 | GRST-5000301758_2024 | 0 | 0 | 0 | 0 | 2025-02-14 | 2025-02-26 | AA53 | 2025-04-30 |  |  | 2024-12-02 | 2025-02-16 | 2024-12-02 | 100000044276 | 1020 | 2025-08-30 | 52 | 5000294329_2024_0001 | 2024-12-02 | 4900183307_2024_0003 | 2024-11-26 | A3711B | 5000301758_2024_0001 | 0 | 2 | 2 | 90024969 | 52 | 52 | 180099854 | 2 | 0 | 0 | X | L | 4900183307 | 2024 | 5000294329 | 5000301758 | 2024 | 2024 | /018009530 | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11403708 | STUDBOLT;1.750"X350MM,B8MCL2,PLN | 2024-07-22 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 9021322_0060 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-11-29 | 10 | 6000007530 | 2025-02-16 | 14 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 130 |  | 5300005524 | 40 | 52 | EA | 2001 | AA02 | 2025-02-25 |  | Management of Change/Order Requires Replanning |  | AU00 | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-25 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0070 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.07.2024) | 11403708 | STUDBOLT;1.750"X350MM,B8MCL2,PLN | 52 | EA | 0 | 0 | 104 | 52 | EA | 16.12 - AT KGP | Supply for Order 600001757, Item 13 cannot be changed 180099144 item 10 already exists | Material work-packed @AA53 | SP97 | Direct Multi-base | 70 | AA02 | 5300005523 | 120 | CPT | 7 | 1000015448 | 13 | 30000148 | TRISTAR AUSTRALIA PTY LTD | 4500025023 | 10 | 52 | EA | 2025-01-05 |  | /180095308 | 180099854 | 9021322 | 07 | Execution | 0000084653 | 13 | 0 | EA |  |  | 101000000116113 |  |  |  |  | WorkPackLink | P07YRDBY13 | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-24 | GRST-5000301777_2024 | 0 | 0 | 0 | 0 | 2025-02-14 | 2025-02-26 | AA53 | 2025-04-30 |  |  | 2024-12-02 | 2025-02-16 | 2024-12-02 | 100000044276 | 1020 | 2025-08-30 | 52 | 5000294287_2024_0001 | 2024-12-02 | 4900183307_2024_0001 | 2024-11-26 | A3711A | 5000301777_2024_0001 | 0 | 2 | 2 | 90024969 | 52 | 52 | 180099854 | 2 | 0 | 0 | X | L | 4900183307 | 2024 | 5000294287 | 5000301777 | 2024 | 2024 | /018009530 | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11403708 | STUDBOLT;1.750"X350MM,B8MCL2,PLN | 2024-07-22 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 9021322_0050 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-11-29 | 10 | 6000007530 | 2025-02-16 | 13 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 120 |  | 5300005524 | 30 | 52 | EA | 2001 | AA02 | 2025-02-25 |  | Management of Change/Order Requires Replanning |  | AU00 | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-04-16 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0410 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 11404177 | SEAL ASY;CCW,38MB6,HOWDEN 22271449000 | 1 | EA | 0 | 0 | 0 | 1 | EA | 10.03 - DEL: 90032318 | Supply for Order 200091108, Item 99 cannot be changed 90032318 item 10 already exists | Workpack awaiting Shipment @AA01 | SP97 | Direct Multi-base | 168 | AA01 | 5300013063 | 10 | CPT | 7 | 1000015268 | 99 | 30002002 | HOWDEN AUSTRALIA PTY LTD | 4500023405 | 10 | 1 | EA | 2025-03-14 |  | 180132832/ |  | 90032318 | 05 | Preparation | 0000129406 | 99 | 0 | EA | 101000000153045 |  | 101000000152846 | 01-Road |  | 1-Not Started |  | WorkPackLink | 1020 KSF SUPPLY |  | 0 |  | 0 | 0 |  | 0 | 1 |  | 2025-03-12 | Y | 1001 | 2024-07-20 | ODST-0090032318_0010 | 0 | 58 | 0 | 0 | 2025-04-14 | 2025-04-23 | AA53 | 2025-03-01 |  |  | 2025-06-25 | 2025-04-16 | 2025-04-25 |  |  | 2025-04-28 | 0 | 5000434955_2025_0001 | 2025-04-16 |  | 2025-03-10 | SealAssy#6 |  | 0 | 2 | 2 | 90032318 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000434955 |  | 0 | 2025 | 180132832 | 2025-04-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404177 | SEAL ASY;CCW,38MB6,HOWDEN 22271449000 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 90032318_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-10-21 | 20 | 6000007392 | 2025-04-16 | 0 |  | 0 |  | 25SD2420 | MJ | 20005387 | AU1009 | 1000128737 | S001 | 30 | 30 | 5300013062 | 680 |  | 5300013063 | 10 | 1 | EA | 1001 | AA02 | 2025-04-16 |  |  | 2025-03-10 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 1 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0100 | 0060 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(04.03.2025) | 11404397 | PISTON ASY;CYL,HOERBIGER/THOMASSEN | 1 | EA | 0 | 0 | 0 | 0 |  | 07.03 - PR 10003678 | Supply Process could not be determined for item 162, material 11404397 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129360 | 162 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2023-04-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404397 | PISTON ASY;CYL,HOERBIGER/THOMASSEN | 2025-03-04 | E |  | 0100 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000128789 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0820 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(04.03.2025) | 11404398 | PISTON ASY;CYL,HOERBIGER/NUOVO PIGNONE | 1 | EA | 0 | 0 | 0 | 0 |  | piston package return number | Supply Process could not be determined for item 195, material 11404398 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 195 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-12-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404398 | PISTON ASY;CYL,HOERBIGER/NUOVO PIGNONE | 2025-03-04 | E |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-07 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-03 | VALVE | 100078477 | 0050 | 0030 | 100078477 | CV-OH 1" 600# 113LCV09 | AA53.113LCV09 | VALVE,1V1301 REGEN GAS WTR KO DRUM | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.10.2024) | 11404515 | PLUG/STEM ASSY;SS316,FISHER 15A6664X192 | 1 | EA | 1 | 0 | 0 | 1 | EA | 21.01 - SOH @ AA01 | Supply for Order 100078477, Item 5 cannot be changed 90028952 item 10 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 84 | AA02 | 5300016139 | 30 | CPT | 7 | 1000020713 | 5 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500031035 | 20 | 1 | EA | 2025-01-29 |  | /180116541 |  | 90025025 | 05 | Preparation | 0000241492 | 5 | 0 | EA | 101000000137073 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-07 | ODST-0090025025_0030 | 0 | 0 | 0 | 0 | 2025-03-11 | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 | 2025-03-13 | 2025-01-27 |  |  | 2024-10-16 | 0 | 5000367211_2025_0001 | 2025-03-26 |  | 2025-01-21 |  |  | 0 | 2 | 2 | 90025025 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000367211 |  | 0 | 2025 | /018011654 | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404515 | PLUG/STEM ASSY;SS316,FISHER 15A6664X192 | 2024-10-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90025025_0030 |  |  | LN1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-12-10 | 20 |  | 2025-03-13 | 5 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000238214 | S002 | 30 | 30 | 5300016139 | 30 |  | 5300016140 | 10 | 1 | EA | 2001 | AA02 | 2025-03-26 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-05-31 | 241492 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-14 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0040 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 11404544 | FOAM,POLYOL;APTANE P234 G4,230KG DRM | 920 | KG | 0 | 0 | 0 | 0 |  | 24.02 - ETA 31.03.25 PO 4500047054 ERA FCA | Supply for Order 500005166, Item 23 cannot be changed 90031361 item 20 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 90 | AA01 | 5300021228 | 30 | FCA | 7 | 1000030347 | 23 | 30001966 | ERA POLYMERS PTY LTD APPLIED POLYMERS | 4500047054 | 20 | 4 | KG | 2025-03-31 |  | 180134063 |  | 90031361 | 05 | Preparation | 0000294187 | 23 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 920 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031361_0020 | 0 | 76 | 76 | 76 | 2025-05-27 | 2025-03-25 | AA53 | 2025-04-01 |  |  | 2025-06-16 | 2025-05-29 | 2025-06-11 |  |  |  | 0 |  | 2025-03-14 |  | 2025-03-27 | TA LAG_VORN |  | 0 | 2 | 2 | 90031361 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | 180134063 | 2025-03-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404544 | FOAM,POLYOL;APTANE P234 G4,230KG DRM | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031361_0020 | [5 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-19 | 99 | 6000015620 | 2025-05-29 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 200 |  | 5300021228 | 30 | 920 | KG | 1001 | AA02 | 2025-03-14 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDSTB5 | Released | 2024-08-09 | 2025-03-01 | 2024-09-30 | 2025-03-01 | 2025-03-01 | INLEC | 100038870 | 1000 | 0040 | 100038870 | MOC-123206 Replace JB 5PM2001BJ | AA53.5PM2001BJ | JB,MOTOR,RCU STABLI HEATER PUMP,5P2001B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.08.2024) | 11404673 | BOX,JCT;EX,914X610X200MM,SS316,5XB | 1 | EA | 0 | 0 | 1 | 1 | EA | 30.01 - SOH @ AA01 | Supply for Order 100038870, Item 4 cannot be changed 90018896 item 10 already exists | Material work-packed @AA53 | SP97 | Direct Multi-base | 49 | AA02 | 5300013766 | 40 | CPT | 7 | 1000016844 | 4 | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD | 4500025157 | 10 | 1 | EA | 2024-10-24 |  | /180079034 | 180130236 | 9027794 | 06 | Scheduling | 0000137402 | 4 | 0 | EA | 102000000033882 |  | 107000000000114 |  |  |  | P07YRDBY28 | WorkPackLink | P07YRDBY28 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-08-09 | GRST-5000419653_2025 | 0 | 167 | 17 | 167 | 2024-10-09 | 2024-10-01 | AA53 | 2025-03-01 |  |  | 2025-08-13 | 2024-10-11 | 2025-03-16 | 100000059166 | 1020 | 2025-07-31 | 1 | 5000260631_2024_0001 | 2025-02-27 | 4900250849_2025_0001 | 2024-10-29 | 5PM2001BJ | 5000419653_2025_0001 | 0 | 2 | 2 | 90020098 | 1 | 1 | 180130236/180130240 | 2 | 0 | 0 | X | L | 4900250849 | 2025 | 5000260631 | 5000419653 | 2025 | 2024 | /018007903 | 2024-09-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11404673 | BOX,JCT;EX,914X610X200MM,SS316,5XB | 2024-08-09 | W |  | 1000 | Function Test & Complete ITR/MITR | INT | Function Test & Complete ITR/MITR |  | Management of Change | 9027794_0020 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-08-14 | 5 |  | 2024-10-11 | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000136732 | S002 | 30 | 30 | 5300013766 | 40 |  | 5300013767 | 10 | 1 | EA | 2001 | AA02 | 2024-09-30 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-11-18 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-02 | MECH | 100073990 | 0020 | 0040 | 100073990 | Filter House Broken Gate Hinges | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(19.01.2025) | 11406588 | HINGE DOOR:ASSY,71mm,90mm,2mm,316 SS,PLA | 1 | EA | 0 | 0 | 0 | 1 | EA | 10.03 - DEL: 90029073 | Supply for Order 100073990, Item 4 cannot be changed 90029073 item 40 already exists | Awaiting work-packing @AA01 | SP97 | Direct Multi-base | 35 | AA01 | 5300017984 | 40 | CPT | 7 | 1000028190 | 4 | 30000394 | J BLACKWOOD AND SON LTD | 4500044397 | 10 | 1 | EA | 2025-02-28 |  | /180134084 |  | 90029073 | 06 | Scheduling | 0000224822 | 4 | 0 | EA |  |  | 101000000153055 |  |  |  |  | WorkPackLink | BW TRANSIT | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-18 | ODST-0090029073_0040 | 0 | 22 | 22 | 22 | 2025-03-04 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-03-23 | 2025-03-06 | 2025-03-18 |  |  | 2025-02-22 | 0 | 5000435005_2025_0001 | 2025-02-12 |  | 2025-03-10 | 100073990 |  | 0 | 2 | 2 | 90029073 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000435005 |  | 0 | 2025 | /018013408 | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11406588 | HINGE DOOR:ASSY,71mm,90mm,2mm,316 SS,PLA | 2025-01-19 | W |  | 0020 | Modify Gate & Install Hinges | INT | Modify Gate & Install Hinges |  |  | 90029073_0040 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-20 | 30 |  | 2025-03-06 | 0 |  | 0 |  | 25SDGT9 | MJ |  | AU1009 | 1000222245 | S001 | 30 | 30 | 5300017981 | 40 |  | 5300017984 | 40 | 1 | EA | 1001 | AA02 | 2025-02-12 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-03-01 | 0 | 0 | 1 |  | 1010 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material shortage | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0120 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(06.01.2025) | 11406943 | FLOWMETER:VORTEX,0.5in,RF FLG,316L SS,24 | 1 | M3H | 0 | 0 | 1 | 1 | M3H | 09.02 - SOH @ AA01 | Supply for Order 100041844, Item 15 cannot be changed 90029081 item 20 already exists | Material work-packed @AA53 | SP97 | Direct Multi-base | 42 | AA02 | 5300000601 | 110 | CPT | 7 | 1000027172 | 15 | 30000401 | EMERSON PROCESS MANAGEMENT AUSTRALIA PTY LTD | 4500042856 | 10 | 1 | M3H | 2025-02-14 |  | 180126450 | 180130404 | 9028218 | 05 | Preparation | 0000140308 | 15 | 0 | M3H | 102000000033944 |  | 107000000000399 |  |  |  |  | WorkPackLink | INLEC-CAGE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000420154_2025 | 0 | 16 | 14 | 16 | 2025-02-24 | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-15 | 2025-02-26 | 2025-03-12 | 100000059294 | 1020 | 2022-01-21 | 1 | 5000407644_2025_0001 | 2025-02-27 | 4900251105_2025_0001 | 2025-02-19 | 100041844 | 5000420154_2025_0001 | 0 | 2 | 2 | 90028427 | 1 | 1 | 180130404 | 2 | 0 | 0 | X | L | 4900251105 | 2025 | 5000407644 | 5000420154 | 2025 | 2025 | 180126450 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11406943 | FLOWMETER:VORTEX,0.5in,RF FLG,316L SS,24 | 2025-01-06 | W |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change | 9028218_0080 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-06 | 20 | 6000013920 | 2025-02-26 | 15 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139679 | S002 | 30 | 30 | 5300000601 | 110 |  | 5300019636 | 20 | 1 | M3H | 2001 | AA02 | 2025-02-24 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140308 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDTOT1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-11 | 2025-03-01 | 2025-03-01 | INLEC | 100041904 | 0020 | 0020 | 100041904 | MOC-120096 Positioner Replace110PV452 | AA53.110PV452POS | POS,VALVE,PRESS 1PRS RUNDOWN 5 | AA01 | 10 | No issue identified | 11407231 | MOUNTING KIT:ACTUATOR,BRKT,FISHER CONTRO | 1 | ASY | 0 | 0 | 0 | 0 |  | 30.01 - ETA 28.05.25 PO 4500044276 ex WPC DD cannot be improved - CRITICAL |  | Vendor PO raised | SP97 | Direct Multi-base | 70 | AA01 | 5300018385 | 20 | CPT | 7 | 1000028602 | 4 | 30000278 | WESTERN PROCESS CONTROLS PTY LTD | 4500044276 | 10 | 1 | ASY | 2025-05-28 |  |  |  | 90029402 | 05 | Preparation | 0000140388 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-26 | ODST-0090029402_0010 | 0 | 64 | 64 | 64 | 2025-04-14 | 2025-02-20 | AA53 | 2025-03-01 |  |  | 2025-05-02 | 2025-04-16 | 2025-04-27 |  |  | 2025-05-07 | 0 |  | 2025-02-11 |  | 2025-02-22 | 110PV452 |  | 0 | 2 | 2 | 90029402 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11407231 | MOUNTING KIT:ACTUATOR,BRKT,FISHER CONTRO |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90029402_0010 |  |  | TT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-24 | 5 |  | 2025-04-16 | 0 |  | 0 |  | 25SDTOT1 | MJ |  | AU1009 | 1000139759 | S001 | 30 | 30 | 5300000626 | 30 |  | 5300018385 | 20 | 1 | ASY | 1001 | AA02 | 2025-02-11 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0110 | 0010 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 11408094 | GASKET:HEADER OUTLET,JORD INT P/L,JO-A2D | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 11.04.25 PO 4500040080 ex Sydney EXW | Supply for Order 100079012, Item 5 cannot be changed 90028558 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018553 | 10 | EXW | 7 | 1000024650 | 5 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500040080 | 30 | 2 | EA | 2025-04-11 |  |  |  | 90028558 | 05 | Preparation | 0000243763 | 5 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028558_0010 | 0 | 0 | 0 | 0 | 2025-02-03 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-02-21 | 2025-02-05 | 2025-02-16 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079012 |  | 0 | 2 | 2 | 90028558 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408094 | GASKET:HEADER OUTLET,JORD INT P/L,JO-A2D | 2024-11-28 | W |  | 0110 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028558_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-12-10 | 5 | 6000012603 | 2025-02-05 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240421 | S001 | 30 | 30 | 5300018551 | 10 |  | 5300018553 | 10 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0120 | 0040 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.12.2024) | 11408094 | GASKET:HEADER OUTLET,JORD INT P/L,JO-A2D | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 11.04.25 PO 4500040080 ex Sydney EXW | Supply for Order 100079012, Item 14 cannot be changed 90028558 item 40 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018553 | 40 | EXW | 7 | 1000026206 | 14 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500040080 | 70 | 2 | EA | 2025-04-11 |  |  |  | 90028558 | 05 | Preparation | 0000243763 | 14 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028558_0040 | 0 | 7 | 7 | 7 | 2025-02-10 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-02-28 | 2025-02-12 | 2025-02-23 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079012 |  | 0 | 2 | 2 | 90028558 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408094 | GASKET:HEADER OUTLET,JORD INT P/L,JO-A2D | 2024-12-17 | W |  | 0120 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028558_0040 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-12-17 | 5 | 6000012603 | 2025-02-12 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240421 | S001 | 30 | 30 | 5300018551 | 100 |  | 5300018553 | 40 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0140 | 0040 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.12.2024) | 11408094 | GASKET:HEADER OUTLET,JORD INT P/L,JO-A2D | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 11.04.25 PO 4500040080 ex Sydney EXW | Supply for Order 100079106, Item 14 cannot be changed 90028559 item 30 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018554 | 30 | EXW | 7 | 1000026205 | 14 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500040080 | 60 | 2 | EA | 2025-04-11 |  |  |  | 90028559 | 05 | Preparation | 0000243730 | 14 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028559_0030 | 0 | 7 | 7 | 7 | 2025-02-10 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-02-28 | 2025-02-12 | 2025-02-23 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079106 |  | 0 | 2 | 2 | 90028559 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408094 | GASKET:HEADER OUTLET,JORD INT P/L,JO-A2D | 2024-12-17 | W |  | 0140 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028559_0030 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-12-17 | 5 | 6000012603 | 2025-02-12 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240357 | S001 | 30 | 30 | 5300018552 | 90 |  | 5300018554 | 30 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0110 | 0020 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 11408105 | GASKET:HEADER INLET,JORD INT P/L,JO-A2D- | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 11.04.25 PO 4500040080 ex Sydney EXW | Supply for Order 100079012, Item 6 cannot be changed 90028558 item 20 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018553 | 20 | EXW | 7 | 1000024650 | 6 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500040080 | 10 | 2 | EA | 2025-04-11 |  |  |  | 90028558 | 05 | Preparation | 0000243763 | 6 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028558_0020 | 0 | 0 | 0 | 0 | 2025-02-03 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-02-21 | 2025-02-05 | 2025-02-16 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079012 |  | 0 | 2 | 2 | 90028558 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408105 | GASKET:HEADER INLET,JORD INT P/L,JO-A2D- | 2024-11-28 | W |  | 0110 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028558_0020 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-12-10 | 5 | 6000012603 | 2025-02-05 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240421 | S001 | 30 | 30 | 5300018551 | 20 |  | 5300018553 | 20 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0130 | 0020 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 11408105 | GASKET:HEADER INLET,JORD INT P/L,JO-A2D- | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 11.04.25 PO 4500040080 ex Sydney EXW | Supply for Order 100079106, Item 6 cannot be changed 90028559 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018554 | 10 | EXW | 7 | 1000024651 | 6 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500040080 | 20 | 2 | EA | 2025-04-11 |  |  |  | 90028559 | 05 | Preparation | 0000243730 | 6 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028559_0010 | 0 | 0 | 0 | 0 | 2025-02-03 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-02-21 | 2025-02-05 | 2025-02-16 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079106 |  | 0 | 2 | 2 | 90028559 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408105 | GASKET:HEADER INLET,JORD INT P/L,JO-A2D- | 2024-11-28 | W |  | 0130 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028559_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-12-10 | 5 | 6000012603 | 2025-02-05 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240357 | S001 | 30 | 30 | 5300018552 | 10 |  | 5300018554 | 10 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0130 | 0070 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 11408105 | GASKET:HEADER INLET,JORD INT P/L,JO-A2D- | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 18.04.25 PO 4500042126 JRD INTER EXW | Supply for Order 100079106, Item 15 cannot be changed 90028559 item 40 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018554 | 40 | EXW | 7 | 1000027411 | 15 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500042126 | 10 | 2 | EA | 2025-04-18 |  |  |  | 90028559 | 05 | Preparation | 0000243730 | 15 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028559_0040 | 0 | 29 | 29 | 29 | 2025-03-04 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-03-22 | 2025-03-06 | 2025-03-17 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079106 |  | 0 | 2 | 2 | 90028559 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408105 | GASKET:HEADER INLET,JORD INT P/L,JO-A2D- | 2025-01-08 | W |  | 0130 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028559_0040 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-09 | 5 |  | 2025-03-06 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240357 | S001 | 30 | 30 | 5300018552 | 100 |  | 5300018554 | 40 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0110 | 0030 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 11408123 | GASKET:HEADER RETURN,JORD INT P/L,JO-A2D | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 11.04.25 PO 4500040080 ex Sydney EXW | Supply for Order 100079012, Item 7 cannot be changed 90028558 item 30 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018553 | 30 | EXW | 7 | 1000024650 | 7 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500040080 | 40 | 2 | EA | 2025-04-11 |  |  |  | 90028558 | 05 | Preparation | 0000243763 | 7 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028558_0030 | 0 | 0 | 0 | 0 | 2025-02-03 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-02-21 | 2025-02-05 | 2025-02-16 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079012 |  | 0 | 2 | 2 | 90028558 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408123 | GASKET:HEADER RETURN,JORD INT P/L,JO-A2D | 2024-11-28 | W |  | 0110 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028558_0030 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-12-10 | 5 | 6000012603 | 2025-02-05 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240421 | S001 | 30 | 30 | 5300018551 | 30 |  | 5300018553 | 30 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0130 | 0080 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 11408123 | GASKET:HEADER RETURN,JORD INT P/L,JO-A2D | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 18.04.25 PO 4500042126 JRD INTER EXW | Supply for Order 100079106, Item 16 cannot be changed 90028559 item 50 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018554 | 50 | EXW | 7 | 1000027411 | 16 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500042126 | 20 | 2 | EA | 2025-04-18 |  |  |  | 90028559 | 05 | Preparation | 0000243730 | 16 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028559_0050 | 0 | 29 | 29 | 29 | 2025-03-04 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-03-22 | 2025-03-06 | 2025-03-17 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079106 |  | 0 | 2 | 2 | 90028559 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408123 | GASKET:HEADER RETURN,JORD INT P/L,JO-A2D | 2025-01-08 | W |  | 0130 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028559_0050 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-09 | 5 |  | 2025-03-06 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240357 | S001 | 30 | 30 | 5300018552 | 110 |  | 5300018554 | 50 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-05 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0130 | 0030 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 11408123 | GASKET:HEADER RETURN,JORD INT P/L,JO-A2D | 2 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 11.04.25 PO 4500040080 ex Sydney EXW | Supply for Order 100079106, Item 7 cannot be changed 90028559 item 20 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300018554 | 20 | EXW | 7 | 1000024651 | 7 | 30002284 | JORD INTERNATIONAL PTY LTD | 4500040080 | 50 | 2 | EA | 2025-04-11 |  |  |  | 90028559 | 05 | Preparation | 0000243730 | 7 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028559_0020 | 0 | 0 | 0 | 0 | 2025-02-03 | 2025-02-14 | AA53 | 2025-03-01 |  |  | 2025-02-21 | 2025-02-05 | 2025-02-16 |  |  | 2025-12-12 | 0 |  | 2025-02-05 |  | 2025-02-16 | 100079106 |  | 0 | 2 | 2 | 90028559 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408123 | GASKET:HEADER RETURN,JORD INT P/L,JO-A2D | 2024-11-28 | W |  | 0130 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028559_0020 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-12-10 | 5 | 6000012603 | 2025-02-05 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000240357 | S001 | 30 | 30 | 5300018552 | 20 |  | 5300018554 | 20 | 2 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | VALVE | 100032675 | 0010 | 0060 | 100032675 | CV-OH 1" 300# 118PCV505 | AA53.118PCV505 | VALVE,1K1820 BUFFER GAS SUPPL PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.12.2024) | 11408459 | REPAIR KIT:FISHER CONTROLS PTY. LTD.,R66 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 100032675, Item 10 cannot be changed 90029079 item 10 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 77 | AA02 | 5300019175 | 40 | CPT | 7 | 1000026092 | 10 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500039296 | 50 | 1 | EA | 2025-03-03 |  | /180122088 |  | 90028291 | 05 | Preparation | 0000131167 | 10 | 0 | EA | 102000000032985 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028291_0040 | 0 | 28 | 28 | 28 | 2025-03-10 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-29 | 2025-03-12 | 2025-03-16 |  |  | 2025-06-02 | 0 | 5000391915_2025_0001 | 2025-02-24 |  | 2025-02-07 | 100032675 |  | 0 | 2 | 2 | 90028291 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000391915 |  | 0 | 2025 | /018012208 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408459 | REPAIR KIT:FISHER CONTROLS PTY. LTD.,R66 | 2024-12-15 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028291_0040 |  |  | FR1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-12-16 | 20 |  | 2025-03-12 | 10 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130517 | S002 | 30 | 30 | 5300019175 | 40 |  | 5300019176 | 10 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131167 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100032677 | 0010 | 0060 | 100032677 | CV-OH 3" 300# 118TCV501 | AA53.118TCV501 | VALVE,1K1820E1 L/O COOL BYPASS TEMP CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 11408491 | REPAIR KIT:80MM,1250R-GL,FISHER CONTROLS | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 100032677, Item 9 cannot be changed – 4500039296 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 77 | AA02 | 5300019178 | 40 | CPT | 7 | 1000026102 | 9 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500039296 | 60 | 1 | EA | 2025-03-03 |  | /180122088 |  | 90028293 | 05 | Preparation | 0000131169 | 9 | 0 | EA | 102000000032986 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028293_0040 | 0 | 28 | 28 | 28 | 2025-03-10 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-29 | 2025-03-12 | 2025-03-16 |  |  | 2025-06-02 | 0 | 5000391946_2025_0001 | 2025-02-24 |  | 2025-02-07 |  |  | 0 | 2 | 2 | 90028293 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000391946 |  | 0 | 2025 | /018012208 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 11408491 | REPAIR KIT:80MM,1250R-GL,FISHER CONTROLS | 2024-12-16 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028293_0040 |  |  | FR1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-12-16 | 20 |  | 2025-03-12 | 9 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130519 | S002 | 30 | 30 | 5300019178 | 40 |  | 5300019179 | 10 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131169 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-14 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0010 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 11409425 | REDUCER:CABLE GLAND,1.25",MNPT, | 20 | EA | 0 | 0 | 0 | 0 |  | 20.02 - ETA 21.03.25 PO 4500046945 CCG EXW | Supply for Order 500005166, Item 1 cannot be changed 90031361 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300021228 | 10 | EXW | 7 | 1000029903 | 1 | 30002139 | CCG AUSTRALIA PTY LTD | 4500046945 | 30 | 20 | EA | 2025-03-21 |  |  |  | 90031361 | 05 | Preparation | 0000294187 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031361_0010 | 0 | 27 | 27 | 27 | 2025-04-08 | 2025-03-25 | AA53 | 2025-04-01 |  |  | 2025-04-28 | 2025-04-10 | 2025-04-23 |  |  |  | 0 |  | 2025-03-14 |  | 2025-03-27 | Inlec Con |  | 0 | 2 | 2 | 90031361 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11409425 | REDUCER:CABLE GLAND,1.25",MNPT, | 2025-02-12 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90031361_0010 | [5 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-13 | 99 | 6000015473 | 2025-04-10 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 10 |  | 5300021228 | 10 | 20 | EA | 1001 | AA02 | 2025-03-14 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-02-20 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0140 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(18.02.2025) | 11410813 | GRIP:HANDLE,PROTECTIVE,20MM | 10 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 14.03.25 PO 4500047444 ATOM CPT | Supply for Order 500005166, Item 16 cannot be changed 90031099 item 10 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 48 | AA01 | 5300021228 | 20 | CPT | 7 | 1000030183 | 16 | 30000407 | ATOM SUPPLY | 4500047444 | 10 | 10 | EA | 2025-03-14 |  | /180134082 |  | 90031099 | 05 | Preparation | 0000294187 | 16 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031099_0010 | 0 | 55 | 55 | 55 | 2025-04-14 | 2025-03-04 | AA53 | 2025-04-01 |  |  | 2025-05-05 | 2025-04-16 | 2025-04-30 |  |  |  | 0 |  | 2025-02-20 |  | 2025-03-06 | TA LAG_VORN |  | 0 | 2 | 2 | 90031099 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | /018013408 | 2025-02-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11410813 | GRIP:HANDLE,PROTECTIVE,20MM | 2025-02-18 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031099_0010 | [5 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-18 | 99 | 6000015615 | 2025-04-16 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 140 |  | 5300021228 | 20 | 10 | EA | 1001 | AA02 | 2025-02-20 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1490 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 30000255 | CASE | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 758 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000255 | CASE |  |  |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0821 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(25.09.2024) | 30000276 | NOZZLE,1ST STG,PIGNONE,2 VANE | 1 | EA | 0 | 0 | 1 | 1 | EA | 25.09 - SOH at AA01 | Supply for Order 200091513, Item 724 cannot be changed 9028207 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180129563 | 9028207 | 05 | Preparation | 0000129822 | 724 | 0 | EA |  |  | 102000000033754 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WHS-R6A |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000419172_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000059204 | 1020 | 2025-07-03 | 1 |  | 2025-02-26 | 4900249246_2025_0001 | 2025-03-01 |  | 5000419172_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180129563 | 2 | 0 | 0 | X | L | 4900249246 | 2025 |  | 5000419172 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000276 | NOZZLE,1ST STG,PIGNONE,2 VANE | 2024-09-25 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 9028207_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 724 |  | 0 |  | 25SD2420 | MJ | 1000005251 | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-27 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0090 | 0052 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(28.10.2024) | 30000355 | GEAR SET,RENK TA45X-420 GBX | 1 | EA | 0 | 0 | 0 | 0 |  | 24.01 - ETA 13.01.25 PO 4500031943 Refurb ex Renk Germany | Supply for Order 200091505, Item 111 cannot be changed 90025019 item 880 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 111 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0880 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000355 | GEAR SET,RENK TA45X-420 GBX | 2024-10-28 | W |  | 0090 | GEARBOX | INT | GEARBOX | 5 |  | 90025019_0880 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 111 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 990 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147410 | 0010 | 0030 | 200147410 | 6Y CV-RE 6 600# Act BUV - 408XV576 | AA53.408XV576 | VALVE,FLOW CONT 8TH STAGE BLEED GT4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 30000462 | VALVE,LM6000,6.0",8 TH STAGE BLEED AIR | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147410, Item 3 cannot be changed 90025001 item 20 already exists | Material picked; currently at SW3R01A01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015678 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025001 | 05 | Preparation | 0000235815 | 3 | 0 | EA |  |  | 102000000029610 |  |  |  |  | WorkPackLink | SW3R01A01B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025001_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | Stg 8 Valve |  | 0 | 2 | 0 | 90025001 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000462 | VALVE,LM6000,6.0",8 TH STAGE BLEED AIR | 2024-09-22 | W |  | 0010 | REPLACE STG 8 BLEED VALVE | INT | REPLACE STG 8 BLEED VALVE | 3 | Ready for Release | 90025001_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232826 | S002 | 30 | 30 | 5300015678 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235815 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-12-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-13 | ROTAT | 200174929 | 0020 | 0010 | 200174929 | 6Y GT4009 GEOMETRY VALVE 8TH STAGE | AA53.409XV576 | VALVE,GT4009 8TH STAGE BLEED VLV ACTUAT | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(03.12.2024) | 30000462 | VALVE,LM6000,6.0",8 TH STAGE BLEED AIR | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.12 - SOH @ AA02 | Supply for Order 200174929, Item 1 cannot be changed 90028285 item 10 already exists | Material picked; currently at SW3R01G02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018650 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028285 | 05 | Preparation | 0000277564 | 1 | 0 | EA |  |  | 102000000034073 |  |  |  |  | WorkPackLink | SW3R01G02B | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-03 | ODST-0090028285_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174929 |  | 0 | 2 | 0 | 90028285 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000462 | VALVE,LM6000,6.0",8 TH STAGE BLEED AIR | 2024-12-03 | W |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | 3 | Ready for Release | 90028285_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000272051 | S002 | 30 | 30 | 5300018650 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277564 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-13 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-12-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200068579 | 0010 | 0020 | 200068579 | 8Y SERIAL 192-189 MAJOR (DEPOT) SV | AA53.LM6000SPARE | TURB,GAS SPARE |  | 20 | No Issue identified | 30000491 | TURBINE,PIGNONE LM6000PD,GAS,SPARE ENG | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000102968 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 | 5400001716 | 10 | 1 | EA | 1 | 0 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2024-09-22 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000491 | TURBINE,PIGNONE LM6000PD,GAS,SPARE ENG |  |  |  | 0010 | Send engine for overhaul | ENON | Send engine for overhaul | [5 empty] | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 | 4900185114_2024 | 25SDGT8 | MJ |  |  | 1000102298 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 3131 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(25.09.2024) | 30000817 | ROTOR ASY,HP;NP SMO1435316 | 1 | EA | 0 | 0 | 1 | 1 | EA | 25.09 - qty 2 SOH at AA01 | Supply for Order 200091513, Item 725 cannot be changed 9028629 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132678 | 9028629 | 05 | Preparation | 0000129822 | 725 | 0 | EA |  |  | 102000000034291 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000429109_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060122 | 1020 | 2025-07-03 | 1 |  | 2025-03-06 | 4900258810_2025_0001 | 2025-03-01 |  | 5000429109_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180132678 | 2 | 0 | 0 | X | L | 4900258810 | 2025 |  | 5000429109 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000817 | ROTOR ASY,HP;NP SMO1435316 | 2024-09-25 | W |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  | 9028629_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 725 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0200 | 3140 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(25.09.2024) | 30001004 | ROTOR ASY;LP,NP SMO1184509 | 1 | EA | 0 | 0 | 1 | 1 | EA | 25.09 - SOH at AA01 | Supply for Order 200091513, Item 726 cannot be changed 9028629 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132678 | 9028629 | 05 | Preparation | 0000129822 | 726 | 0 | EA |  |  | 102000000034290 |  |  |  |  | WorkPackLink | KSF-P07-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000429109_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060122 | 1020 | 2025-07-03 | 1 |  | 2025-03-06 | 4900258810_2025_0003 | 2025-03-01 |  | 5000429109_2025_0002 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180132678 | 2 | 0 | 0 | X | L | 4900258810 | 2025 |  | 5000429109 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30001004 | ROTOR ASY;LP,NP SMO1184509 | 2024-09-25 | W |  | 0200 | LP ROTOR ASSEMBLY | INT | LP ROTOR ASSEMBLY | 5 |  | 9028629_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 726 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0020 | 0040 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(27.09.2024) | 30003261 | VALVE,GLOBE;6",CL300,FLOWSV,MARK100,CV5+ | 1 | EA | 1 | 0 | 0 | 1 | EA | 31.01 - SOH @ AA02 | Supply for Order 600001792, Item 10 cannot be changed 90024967 item 60 already exists | Material picked; currently at SW3R01F01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004604 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024967 | 05 | Preparation | 0000084710 | 10 | 0 | EA |  |  | 101000000039962 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R01F01A | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2025-01-30 | 2025-01-30 | Y | 1001 | 2024-01-02 | ODST-0090024967_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024967 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30003261 | VALVE,GLOBE;6",CL300,FLOWSV,MARK100,CV5+ | 2024-09-27 | W |  | 0020 | Install 118UCV112 | INT | Install 118UCV112 | 5 |  | 90024967_0060 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDFR1 | MJ | 20005113 | AU1072 | 1000084094 | S002 | 30 | 30 | 5300004604 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-28 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84710 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
| 25SDLN1 | Released | 2024-11-19 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 600003361 | 0020 | 0030 | 600003361 | MOC-120323 - CV-RE 10" 600# 141FCV01 | AA53.141FCV01 | VALVE,H/W FLOW TO 1E4101 CV |  | 20 | Issue detected, please check message in derivation or orchestration log | 30005275 | VALVE CNTRL:GLB,10 X 6in,CL600psi,A216 W | 1 | EA | 0 | 0 | 0 | 0 |  | 04.02 - ETA 22.08.25 PO 4500036632 SCORE CPT potential scar | Supply for Order 600003361, Item 4 cannot be changed 90025119 item 10 already exists |  | SP14 | Directs (Inventory) | 0 | AA02 | 5300018069 | 10 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025119 | 03 | Planning | 0000266685 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-19 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 | [7 empty] | 2025-09-23 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025119 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30005275 | VALVE CNTRL:GLB,10 X 6in,CL600psi,A216 W | 2024-11-19 | W |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve |  |  | 90025119_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000261577 | S002 | 30 | 30 | 5300018069 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-09-24 | 266685 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Material shortage/Printed | AM06 | Capital
| 25SDLN1 | Released | 2024-11-19 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 600003400 | 0020 | 0010 | 600003400 | MOC-120323 - CV-RE 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV |  | 255 | Issue detected, please check message in derivation or orchestration log | 30005275 | VALVE CNTRL:GLB,10 X 6in,CL600psi,A216 W | 1 | EA | 0 | 0 | 0 | 0 |  | 04.02 - ETA 22.08.25 PO 4500036632 SCORE CPT potential scar | Supply for Order 600003400, Item 1 cannot be changed 90025120 item 10 already exists |  | SP14 | Directs (Inventory) | 0 | AA02 | 5300018070 | 10 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025120 | 03 | Planning | 0000266702 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-19 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 | [7 empty] | 2026-09-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600003400 |  | 0 | 2 | 0 | 90025120 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30005275 | VALVE CNTRL:GLB,10 X 6in,CL600psi,A216 W | 2024-11-19 | W |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve |  |  | 90025120_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000261698 | S002 | 30 | 30 | 5300018070 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-09-24 | 266702 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 6 | Very Low | RC00018003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Material shortage/Printed | AM06 | Capital
| 25SDLN4 | Released | 2024-11-19 | 2025-03-01 | 2025-02-14 | 2025-05-08 | 2025-05-08 | VALVE | 100042223 | 0020 | 0030 | 100042223 | CV-RE 2" 600# 414UV356 | AA53.414UV356 | VALVE,CTRL 4V1404 HW TO SUPPLY | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(27.02.2024) | 70000328 | 2" ANSI 600# RF, Full Bore, Gate Valve | 1 | EA | 0 | 0 | 0 | 0 |  | 27.09 - ETA 12.04.25 PO 4500005861 SCORE | Supply for Order 100042223, Item 3 cannot be changed 90029371 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 365 | AA01 | 5300007227 | 10 | FCA | 365 | 1000003737 | 3 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500005861 | 10 | 1 | EA | 2025-04-12 |  |  |  | 90029371 | 05 | Preparation | 0000140764 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-27 | ODST-0090029371_0010 | 0 | 280 | 138 | 138 | 2025-06-26 | 2025-02-25 | AA53 | 2025-05-08 |  |  | 2026-04-27 | 2025-07-02 | 2025-07-19 |  |  | 2025-07-31 | 0 |  | 2025-02-14 |  | 2025-03-03 | 100042223 |  | 0 | 6 | 6 | 90029371 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70000328 | 2" ANSI 600# RF, Full Bore, Gate Valve | 2024-02-27 | W |  | 0020 | Remove & Replace Valve, Reuse Actuator | INT | Remove & Replace Valve, Reuse Actuator |  |  | 90029371_0010 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-06-19 | 5 |  | 2025-07-02 | 0 |  | 0 |  | 25SDLN4 | MJ |  | AU1009 | 1000140133 | S001 |  |  | 5300007226 | 10 |  | 5300007227 | 10 | 1 | EA | 1001 | AA02 | 2025-02-14 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-11 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0020 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Planned delivery after Reqmt Date | 70001163 | BURNER; FLARE 54" NFF-CG UPGRADE | 2 | EA | 0 | 0 | 0 | 0 |  | 24.02 - ETA 13.05.25 PO 4500002443 TRINKOR CPT | Supply for Order 600001757, Item 8 cannot be changed – 4500002443 already exists | Vendor PO raised | SP97 | Direct Multi-base | 329 | AA01 | 5300005524 | 20 | CPT | 329 | 1000011755 | 8 | 30001954 | TRINKOR PTY LTD | 4500002443 | 20 | 2 | EA | 2025-05-13 |  |  |  |  | 07 | Execution | 0000084653 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-24 | POPO-4500002443_00020 | 1 | 0 | 0 | 0 | 2024-06-05 | 2025-02-16 | AA53 | 2025-04-30 |  |  | 2025-02-28 | 2024-06-11 | 2025-02-22 |  |  | 2025-08-30 | 0 |  | 2025-02-11 |  | 2025-02-22 | 600001757 |  | 0 | 6 | 6 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70001163 | BURNER; FLARE 54" NFF-CG UPGRADE | 2024-05-29 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning |  |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-06-05 | 10 |  | 2024-06-11 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084067 | S001 |  |  | 5300005523 | 70 |  | 5300005524 | 20 | 2 | EA | 1001 | AA02 | 2025-02-11 |  | Management of Change/Order Requires Replanning |  | AU00 | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-01-01 | 2024-03-31 | 2024-02-26 | 2025-05-08 | 2025-05-10 | MECH | 100033581 | 0017 | 0010 | 100033581 | OPSD 4KT1430KM3B Noise & Vibration | AA53.4KT1430KM3B | MOTOR,BLOWER EXHAUST FRAME 4KT1430 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(26.02.2024) | 70003241 | Motor EX,415V,50HZ,75KW,2P,M3KP280SMB2 | 1 | EA | 0 | 0 | 0 | 1 | EA | 4500005868 ETA 13.8.2024 | Supply for Order 100033581, Item 3 cannot be changed 180091013 item 10 already exists | Material Consumed | SP97 | Direct Multi-base | 161 | AA02 | 5300007147 | 10 | FCA | 161 | 1000003615 | 3 | 30000411 | ABB AUSTRALIA PTY LTD | 4500005868 | 10 | 1 | EA | 2024-08-13 |  | 180051979/ | 180091589 | 9019206 | 07 | Execution | 0000132053 | 3 | 0 | EA |  |  | 102000000023461 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-P19-QMI-LRG | P19 FL MECH | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-26 |  | 0 | 657 | 175 | 433 | 2024-08-13 | 2024-01-27 | AA53 | 2025-05-08 |  |  | 2026-08-29 | 2024-08-19 | 2025-05-04 | 100000040048 | 1020 | 2023-11-30 | 1 | 5000267848_2024_0001 | 2024-11-10 | 4900169291_2024_0001 | 2024-11-05 | 4KT1430KM3B | 5000274157_2024_0001 | 0 | 5 | 6 | 90002401 | 1 | 1 | 180091589 | 2 | 0 | 0 | X | L | 4900169291 | 2024 | 5000267848 | 5000274157 | 2024 | 2024 | 180051979 | 2024-02-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70003241 | Motor EX,415V,50HZ,75KW,2P,M3KP280SMB2 | 2024-02-26 | W |  | 0017 | Replace Motor | INT | Replace Motor |  | Opportune Shutdown | 90002401_0010/9019206_0010 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-02-26 | 10 |  | 2024-08-19 | 3 |  | 0 |  | 25SDLN4 | MJ | 1000004081 | AU1072 | 1000131463 | S002 |  |  | 5300007147 | 10 |  | 5300007148 | 10 | 2 | EA | 2001 | AA02 | 2024-02-26 |  | Opportune Shutdown | 2024-11-11 | AU00 | 1070 |  | 2024-02-01 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132053 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-10 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Goods movement posted/Partially confirmed/Material committed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-02-07 | 2025-01-31 | 2025-02-07 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0040 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(07.02.2025) | 70005747 | SWITCHBOX:K1TOPWORX MNTG KIT 179KIT167SI | 2 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 11.04.25 PO 4500045894 ex Severn | Supply for Order 600001473, Item 4 cannot be changed 90030494 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 14 | AA01 | 5300020973 | 10 | CPT | 14 | 1000029517 | 4 | 30002472 | SEVERN GLOCON AUSTRALIA PTY LTD | 4500045894 | 20 | 2 | EA | 2025-04-11 |  |  |  | 90030494 | 05 | Preparation | 0000084391 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030494_0010 | 0 | 50 | 24 | 38 | 2025-02-28 | 2025-02-04 | AA53 | 2025-05-08 |  |  | 2025-04-03 | 2025-03-03 | 2025-03-17 |  |  | 2025-12-15 | 0 |  | 2025-02-07 |  | 2025-02-21 | 4V1302 |  | 0 | 3 | 3 | 90030494 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-07 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70005747 | SWITCHBOX:K1TOPWORX MNTG KIT 179KIT167SI | 2025-02-07 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90030494_0010 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-07 | 5 |  | 2025-03-03 | 0 |  | 0 |  | 25SDLN4 | MJ |  | AU1009 | 1000083795 | S001 |  |  | 5300020972 | 40 |  | 5300020973 | 10 | 2 | EA | 1001 | AA02 | 2025-02-07 |  | Engineering Query/Management of Change |  | AU00 | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2024-08-05 | 2024-07-19 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0030 | 0010 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.06.2024) | 70008538 | ABB Spirit-IT Flow X/S Flow Computers | 2 | EA | 0 | 2 | 0 | 2 | EA | 19.12 - KSF Work-Packed | Supply for Order 600001815, Item 3 cannot be changed 180102801 item 10 already exists |  | SP97 | Direct Multi-base | 56 | AA01 | 5300011702 | 10 | CPT | 56 | 1000013121 | 3 | 30000411 | ABB AUSTRALIA PTY LTD | 4500018967 | 10 | 2 | EA | 2024-08-29 |  | /180089987 | 180102801 | 9022108 | 07 | Execution | 0000084731 | 3 | 0 | EA |  |  | 101000000120226 |  |  |  |  | WorkPackLink |  | AA53-P08-QMI | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-06-18 | IDST-0180102801 | 0 | 39 | 39 | 39 | 2024-08-21 | 2024-07-24 | AA53 | 2025-04-30 |  |  | 2024-09-13 | 2024-08-27 | 2024-09-07 | 100000288040 | 1010 | 2024-08-30 | 2 | 5000311605_2024_0001 | 2024-12-09 | 4900187632_2024_0001 | 2024-12-09 | 37FQI40/41 |  | 0 | 6 | 6 | 90014049 | 0 | 2 | 180102801/180102808 | 2 | 0 | 0 | X | L | 4900187632 | 2024 | 5000311605 |  | 0 | 2024 | /018008998 | 2024-07-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70008538 | ABB Spirit-IT Flow X/S Flow Computers | 2024-06-17 | W |  | 0030 | Provision of Flow Computers (MOC-119247) | ESRV | Provision of Flow Computers (MOC-119247) |  |  | 9022108_0020 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-06-19 | 10 |  | 2024-08-27 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 |  |  | 5300007843 | 20 |  | 5300011702 | 10 | 2 | EA | 1001 | AA02 | 2024-07-19 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SD2301 | Released | 2024-08-07 | 2025-03-01 | 2025-04-11 | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 1000 | 0010 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.08.2024) | 70010662 | E-MOTOR DRIVEN LUBE OIL PUMP RETROFIT | 1 | PC | 0 | 0 | 0 | 0 |  | 27.09 - ETA 21.02.25 PO 4500024571 ex HOWDEN AUSTRALIA | Supply for Order 600001365, Item 2 cannot be changed – 4500024571 already exists | Vendor PO raised | SP97 | Direct Multi-base | 196 | AA01 | 5300013663 | 10 | FCA | 196 | 1000016660 | 2 | 30002002 | HOWDEN AUSTRALIA PTY LTD | 4500024571 | 10 | 1 | PC | 2025-04-11 |  |  |  |  | 05 | Preparation | 0000084303 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-06 | POPO-4500024571_00010 | 0 | 58 | 0 | 0 | 2025-04-03 | 2025-04-16 | AA53 | 2025-03-01 |  |  | 2025-06-25 | 2025-04-09 | 2025-04-22 |  |  | 2025-07-31 | 0 |  | 2025-04-11 |  | 2025-04-22 |  |  | 0 | 6 | 6 |  | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-04-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70010662 | E-MOTOR DRIVEN LUBE OIL PUMP RETROFIT | 2024-08-06 | W |  | 1000 | Material assurance | INT | Material assurance |  | Order Requires Replanning |  |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-09-12 | 5 |  | 2025-04-09 | 0 |  | 0 |  | 25SD2301 | MJ |  | AU1009 | 1000083687 | S001 |  |  | 5300013662 | 10 |  | 5300013663 | 10 | 1 | PC | 1001 | AA02 | 2025-04-11 |  | Order Requires Replanning |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-24 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0130 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance |  | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.03.2025) | 70011866 | Wire Marking Sleeve BRA110926 | 4 | EA | 0 | 0 | 0 | 0 |  | 07.03 - PR 1000022871 | Supply for Order 500005166, Item 67 cannot be changed 90032276 item 10 already exists | PR approved; PO not issued | SP14 | Directs (Inventory) | 2 | AA02 | 5300021227 | 600 |  | 2 | 1000031266 | 67 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032276 | 05 | Preparation | 0000294187 | 67 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031266_00067 | 0 | 0 | 0 | 0 | 2025-03-18 | 2025-03-27 | AA53 | 2025-04-01 |  |  | 2025-03-24 |  | 2025-03-24 |  |  |  | 0 |  | 2025-03-24 |  | 2025-04-01 | Bmccrum |  | 0 | 5 | 6 | 90032276 | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70011866 | Wire Marking Sleeve BRA110926 | 2025-03-05 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032276_0010 | [5 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-03-11 | 99 |  | 2025-03-24 | 67 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 |  |  | 5300021227 | 600 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-03-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN1 | Released | 2024-11-12 | 2025-04-14 | 2025-03-26 | 2025-03-01 | 2025-06-09 | VALVE | 100034564 | 0020 | 0010 | 100034564 | CV-OH 12" 600# 111UCV032 | AA53.111UCV032 | VALVE,CTRL REFLUX C1101 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.11.2024) | 70015587 | KIT,O/HAUL,BALL VALVE,300MM,CL600 | 1 | KIT | 0 | 0 | 0 | 0 |  | 22.11 - ETA 22.04.25 PO 4500035662 SCORE | Supply for Order 100034564, Item 2 cannot be changed – 4500035662 already exists | Vendor PO raised | SP97 | Direct Multi-base | 120 | AA01 | 5300017793 | 10 | FCA | 120 | 1000023050 | 2 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500035662 | 10 | 1 | KIT | 2025-04-22 |  |  |  | 90032200 | 05 | Preparation | 0000133016 | 2 | 0 | [8 empty] | WorkPackLink |  | Score LIA | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-12 | ODST-0090032200_0010 | 0 | 0 | 0 | 0 | 2025-03-21 | 2025-04-06 | AA53 | 2025-03-01 |  |  | 2025-04-14 | 2025-03-24 | 2025-04-09 |  |  | 2027-10-31 | 0 |  | 2025-03-26 |  | 2025-04-09 | 100034564 |  | 0 | 3 | 3 | 90032200 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70015587 | KIT,O/HAUL,BALL VALVE,300MM,CL600 | 2024-11-12 | W |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind |  |  | 90032200_0010 |  |  | LN1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-11-14 | 5 |  | 2025-03-24 | 0 |  | 0 |  | 25SDLN1 | MJ |  | AU1009 | 1000132426 | S001 |  |  | 5300017792 | 10 |  | 5300017793 | 10 | 1 | KIT | 1001 | AA02 | 2025-03-26 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-06-09 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0010 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 |  | 10 | Planned delivery after Reqmt Date | 70016067 | Replacement Tube Bundle for 5E2001 | 1 | ASY | 0 | 0 | 0 | 0 |  | 02.12 - ETA 15.05.25 PO 4500036764 TRINKOR EXW EX VIC | Supply for Order 100087648, Item 2 cannot be changed 90028417 item 10 already exists | Vendor PO raised | SP14 | Directs (Inventory) | 168 | AA02 | 5300018296 | 10 | EXW | 168 | 1000023936 | 2 | 30001954 | TRINKOR PTY LTD | 4500036764 | 10 | 1 | ASY | 2025-06-06 |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 2 | 0 | [8 empty] | WorkPackLink |  | P07 - KGP | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-22 | POPO-4500036764_00010 | 0 | 8 | 0 | 8 | 2025-03-01 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-12 |  | 2025-03-04 |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | CRITCAL |  | 0 | 2 | 3 | 90028417 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70016067 | Replacement Tube Bundle for 5E2001 | 2024-11-22 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-11-25 | 10 |  | 2025-03-04 | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 |  |  | 5300018296 | 10 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-02-08 | 2024-12-13 | 2024-12-05 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0030 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(27.11.2024) | 70016152 | MNS3 8E Module,7.5kW,module modification | 1 | EA | 0 | 0 | 1 | 1 | EA | 18.02 - SOH @ AA01 | Supply for Order 600001363, Item 6 cannot be changed 9027351 item 30 already exists | Materials handed over to w/ Maintenance | SP97 | Direct Multi-base | 56 | AA02 | 5300018438 | 30 | CPT | 56 | 1000024297 | 6 | 30000411 | ABB AUSTRALIA PTY LTD | 4500037202 | 10 | 1 | EA | 2025-06-09 |  | 180125489 | 180130379 | 9028215 | 05 | Preparation | 0000084301 | 6 | 0 | EA |  |  | 102000000033911 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P08-CAMP-SML | AA53-P08-DG | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-27 | GRST-5000420090_2025 | 0 | 228 | 69 | 152 | 2025-01-31 | 2024-12-08 | AA53 | 2025-02-27 |  |  | 2025-10-13 | 2025-02-06 | 2025-05-06 | 100000059267 | 1020 | 2025-07-31 | 1 | 5000403823_2025_0001 | 2025-02-27 | 4900251077_2025_0001 | 2025-02-17 | Inlec | 5000420090_2025_0001 | 0 | 5 | 6 | 90025735 | 1 | 1 | 180130379 | 2 | 0 | 0 | X | L | 4900251077 | 2025 | 5000403823 | 5000420090 | 2025 | 2025 | 180125489 | 2024-12-05 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70016152 | MNS3 8E Module,7.5kW,module modification | 2024-11-27 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 9028215_0030 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-11-29 | 5 |  | 2025-02-06 | 6 |  | 0 |  | 25SDSTB5 | MJ | 1000005301 | AU1072 | 1000083685 | S002 |  |  | 5300018438 | 30 |  | 5300018439 | 30 | 1 | EA | 2001 | AA02 | 2024-12-05 |  |  | 2025-02-28 | AU00 | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDSTB5 | Released | 2025-02-08 | 2024-12-13 | 2024-11-29 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0010 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(27.11.2024) | 70016164 | MNS3 8EModule,7.5kW,based L4000DE1500001 | 2 | EA | 0 | 0 | 0 | 0 |  | 19.02 - ETA 18.04.25 PO 4500037202 ABB CPT | Supply for Order 600001363, Item 2 cannot be changed 90025720 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 168 | AA01 | 5300018439 | 10 | CPT | 168 | 1000024297 | 2 | 30000411 | ABB AUSTRALIA PTY LTD | 4500037202 | 20 | 2 | EA | 2025-06-09 |  |  |  | 90025720 | 05 | Preparation | 0000084301 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-P08-DG | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-27 | ODST-0090025720_0010 | 0 | 192 | 181 | 192 | 2025-05-23 | 2024-11-29 | AA53 | 2025-02-27 |  |  | 2025-06-23 | 2025-05-29 | 2025-06-15 |  |  | 2025-07-31 | 0 |  | 2024-11-29 |  | 2024-12-16 | Inlec |  | 0 | 6 | 6 | 90025720 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-29 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70016164 | MNS3 8EModule,7.5kW,based L4000DE1500001 | 2024-11-27 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90025720_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-11-29 | 5 |  | 2025-05-29 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000083685 | S001 |  |  | 5300018438 | 10 |  | 5300018439 | 10 | 2 | EA | 1001 | AA02 | 2024-11-29 |  |  |  | AU00 | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDSTB5 | Released | 2025-02-08 | 2024-12-13 | 2024-11-29 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0020 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(27.11.2024) | 70016165 | MNS3 8EModule,2.2kW,based L4000DE1500001 | 1 | EA | 0 | 0 | 0 | 0 |  | 19.02 - ETA 18.04.25 PO 4500037202 ABB CPT | Supply for Order 600001363, Item 4 cannot be changed 90025720 item 20 already exists | Vendor PO raised | SP97 | Direct Multi-base | 168 | AA01 | 5300018439 | 20 | CPT | 168 | 1000024297 | 4 | 30000411 | ABB AUSTRALIA PTY LTD | 4500037202 | 30 | 1 | EA | 2025-06-09 |  |  |  | 90025720 | 05 | Preparation | 0000084301 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-P08-DG | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-27 | ODST-0090025720_0020 | 0 | 192 | 181 | 192 | 2025-05-23 | 2024-11-29 | AA53 | 2025-02-27 |  |  | 2025-06-23 | 2025-05-29 | 2025-06-15 |  |  | 2025-07-31 | 0 |  | 2024-11-29 |  | 2024-12-16 | Inlec |  | 0 | 6 | 6 | 90025720 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-29 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70016165 | MNS3 8EModule,2.2kW,based L4000DE1500001 | 2024-11-27 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90025720_0020 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2024-11-29 | 5 |  | 2025-05-29 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000083685 | S001 |  |  | 5300018438 | 20 |  | 5300018439 | 20 | 1 | EA | 1001 | AA02 | 2024-11-29 |  |  |  | AU00 | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDFLR | Released | 2024-01-24 | 2024-12-20 | 2024-12-12 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0160 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER |  | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.12.2024) | 70016606 | SWIVEL,BULLET NOSE 0.75T WLL YOKE | 1 | EA | 0 | 0 | 1 | 1 | EA | 20.02 - SOH @ AA02 | Supply for Order 600001757, Item 23 cannot be changed 90026209 item 10 already exists | Material work-packed @AA53 | SP14 | Directs (Inventory) | 7 | AA02 | 5300005523 | 190 | CPT | 7 | 1000025368 | 23 | 30000389 | TOTAL LIFTING AND RIGGING PTY LTD | 4500039009 | 10 | 1 | EA | 2024-12-19 |  | /180127029 | 180131426 | 90026209 | 07 | Execution | 0000084653 | 23 | 0 | EA |  |  | 102000000033295 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-MATERIALS | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-24 | GRST-5000424943_2025 | 0 | 12 | 0 | 12 | 2024-12-18 | 2024-12-15 | AA53 | 2025-04-30 |  |  | 2025-01-05 |  | 2024-12-24 | 100000059527 | 1020 | 2025-08-30 | 1 | 5000407937_2025_0001 | 2025-03-04 | 4900255606_2025_0001 | 2025-02-19 | 600001757 | 5000424943_2025_0001 | 0 | 5 | 6 | 90026209 | 1 | 1 | 180131426 | 2 | 0 | 0 | X | L | 4900255606 | 2025 | 5000407937 | 5000424943 | 2025 | 2025 | /018012702 | 2024-12-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70016606 | SWIVEL,BULLET NOSE 0.75T WLL YOKE | 2024-12-06 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90026209_0010 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-12-06 | 10 |  | 2024-12-24 | 23 |  | 0 |  | 25SDFLR | MJ | 1000005306 | AU1072 | 1000084067 | S002 |  |  | 5300005523 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-12-12 |  | Management of Change/Order Requires Replanning | 2025-03-05 | AU00 | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2024-12-20 | 2024-12-12 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0170 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER |  | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.12.2024) | 70016607 | CLAMP,BLUELINE WIRE ROPE 4T WLL 20-38MM | 1 | EA | 0 | 0 | 1 | 1 | EA | 20.02 - SOH @ AA02 | Supply for Order 600001757, Item 25 cannot be changed 90026209 item 20 already exists | Material work-packed @AA53 | SP14 | Directs (Inventory) | 7 | AA02 | 5300005523 | 200 | CPT | 7 | 1000025368 | 25 | 30000389 | TOTAL LIFTING AND RIGGING PTY LTD | 4500039009 | 20 | 1 | EA | 2024-12-19 |  | /180127031 | 180131426 | 90026209 | 07 | Execution | 0000084653 | 25 | 0 | EA |  |  | 102000000033294 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-MATERIALS | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-24 | GRST-5000424943_2025 | 0 | 12 | 0 | 12 | 2024-12-18 | 2024-12-15 | AA53 | 2025-04-30 |  |  | 2025-01-05 |  | 2024-12-24 | 100000059527 | 1020 | 2025-08-30 | 1 | 5000407953_2025_0001 | 2025-03-04 | 4900255606_2025_0003 | 2025-02-19 | 600001757 | 5000424943_2025_0002 | 0 | 5 | 6 | 90026209 | 1 | 1 | 180131426 | 2 | 0 | 0 | X | L | 4900255606 | 2025 | 5000407953 | 5000424943 | 2025 | 2025 | /018012703 | 2024-12-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70016607 | CLAMP,BLUELINE WIRE ROPE 4T WLL 20-38MM | 2024-12-06 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90026209_0020 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-12-06 | 10 |  | 2024-12-24 | 25 |  | 0 |  | 25SDFLR | MJ | 1000005306 | AU1072 | 1000084067 | S002 |  |  | 5300005523 | 200 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-12-12 |  | Management of Change/Order Requires Replanning | 2025-03-05 | AU00 | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-02-01 | 2025-01-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0180 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER |  | 10 | Planned delivery after Reqmt Date | 70016977 | SHEAVE, BLOCK DOUBLE FIXED EYE | 2 | EA | 0 | 0 | 0 | 0 |  | 19.12 - ETA 07.03.25 PO 4500040079 TOTAL LIFT CPT | Supply for Order 600001757, Item 27 cannot be changed 90027785 item 10 already exists | Vendor PO raised | SP14 | Directs (Inventory) | 49 | AA02 | 5300005523 | 210 | CPT | 49 | 1000026337 | 27 | 30000389 | TOTAL LIFTING AND RIGGING PTY LTD | 4500040079 | 10 | 2 | EA | 2025-03-13 |  |  |  | 90027785 | 07 | Execution | 0000084653 | 27 | 0 | [8 empty] | WorkPackLink |  | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-24 | POPO-4500040079_00010 | 0 | 23 | 0 | 23 | 2025-02-10 | 2025-01-27 | AA53 | 2025-04-30 |  |  | 2025-03-11 |  | 2025-02-16 |  |  | 2025-08-30 | 0 |  | 2025-01-24 |  | 2025-02-01 | 600001757 |  | 0 | 5 | 6 | 90027785 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-01-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70016977 | SHEAVE, BLOCK DOUBLE FIXED EYE | 2024-12-17 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90027785_0010 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | 104 | Proj & Brownfields | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-12-18 | 10 |  | 2025-02-16 | 27 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 |  |  | 5300005523 | 210 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-01-24 |  | Management of Change/Order Requires Replanning |  | AU00 | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-02-01 | 2025-01-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0190 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER |  | 10 | Planned delivery after Reqmt Date | 70016978 | SHACKLE,ROLLER 28MM | 1 | EA | 0 | 0 | 0 | 0 |  | 19.12 - ETA 07.03.25 PO 4500040079 TOTAL LIFT CPT | Supply for Order 600001757, Item 29 cannot be changed 90027785 item 20 already exists | Vendor PO raised | SP14 | Directs (Inventory) | 49 | AA02 | 5300005523 | 220 | CPT | 49 | 1000026337 | 29 | 30000389 | TOTAL LIFTING AND RIGGING PTY LTD | 4500040079 | 20 | 1 | EA | 2025-03-13 |  |  |  | 90027785 | 07 | Execution | 0000084653 | 29 | 0 | [8 empty] | WorkPackLink |  | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-24 | POPO-4500040079_00020 | 0 | 23 | 0 | 23 | 2025-02-10 | 2025-01-27 | AA53 | 2025-04-30 |  |  | 2025-03-11 |  | 2025-02-16 |  |  | 2025-08-30 | 0 |  | 2025-01-24 |  | 2025-02-01 | 600001757 |  | 0 | 5 | 6 | 90027785 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-01-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70016978 | SHACKLE,ROLLER 28MM | 2024-12-17 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90027785_0020 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | 104 | Proj & Brownfields | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2024-12-18 | 10 |  | 2025-02-16 | 29 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 |  |  | 5300005523 | 220 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-01-24 |  | Management of Change/Order Requires Replanning |  | AU00 | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFR1 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | VALVE | 100032673 | 0050 | 0010 | 100032673 | CV-OH 1" 300# 118LCV508 | AA53.118LCV508 | VALVE,S/OIL DRN POT K1820V4A LOCAL LVL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 70017467 | 1120-2401 Samson, Packing Set | 1 | KIT | 1 | 0 | 0 | 1 | KIT | 20.02 - SOH @ AA02 | Supply for Order 100032673, Item 6 cannot be changed – 4500041815 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 80 | AA02 | 5300019684 | 10 | CPT | 80 | 1000027266 | 6 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500041815 | 50 | 1 | KIT | 2025-03-25 |  | /180125986 |  | 90028298 | 05 | Preparation | 0000131165 | 6 | 0 | KIT | 101000000146165 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028298_0010 | 0 | 54 | 54 | 54 | 2025-04-04 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-04-24 | 2025-04-07 | 2025-04-16 |  |  | 2024-06-02 | 0 | 5000406637_2025_0001 | 2025-02-24 |  | 2025-02-18 | 100032673 |  | 0 | 2 | 3 | 90028298 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000406637 |  | 0 | 2025 | /018012598 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017467 | 1120-2401 Samson, Packing Set | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028298_0010 |  |  | FR1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-07 | 20 |  | 2025-04-07 | 6 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130515 | S002 |  |  | 5300019684 | 10 |  | 5300019685 | 10 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131165 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | VALVE | 100032673 | 0050 | 0020 | 100032673 | CV-OH 1" 300# 118LCV508 | AA53.118LCV508 | VALVE,S/OIL DRN POT K1820V4A LOCAL LVL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 70017468 | 8414-2611 Samson, Gasket Bonnet | 1 | EA | 1 | 0 | 0 | 1 | EA | 20.02 - SOH @ AA02 | Supply for Order 100032673, Item 8 cannot be changed – 4500041815 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 80 | AA02 | 5300019684 | 20 | CPT | 80 | 1000027266 | 8 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500041815 | 60 | 1 | EA | 2025-03-25 |  | /180125986 |  | 90028298 | 05 | Preparation | 0000131165 | 8 | 0 | EA | 101000000146166 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028298_0020 | 0 | 54 | 54 | 54 | 2025-04-04 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-04-24 | 2025-04-07 | 2025-04-16 |  |  | 2024-06-02 | 0 | 5000406681_2025_0001 | 2025-02-24 |  | 2025-02-18 | 100032673 |  | 0 | 2 | 3 | 90028298 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000406681 |  | 0 | 2025 | /018012598 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017468 | 8414-2611 Samson, Gasket Bonnet | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028298_0020 |  |  | FR1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-07 | 20 |  | 2025-04-07 | 8 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130515 | S002 |  |  | 5300019684 | 20 |  | 5300019685 | 20 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131165 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | VALVE | 100079184 | 0050 | 0010 | 100079184 | CV-OH 1" 600# 124LCV26 | AA53.124LCV26 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 70017494 | 1120-3188 Samson, Packing Set | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 19.02 - SOH @ AA02 | Supply for Order 100079184, Item 2 cannot be changed – 4500041815 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 80 | AA02 | 5300019686 | 10 | CPT | 80 | 1000027267 | 2 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500041815 | 10 | 1 | KIT | 2025-03-25 |  | /180125986 |  | 90028299 | 05 | Preparation | 0000244787 | 2 | 0 | KIT | 101000000146116 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028299_0010 | 0 | 54 | 54 | 54 | 2025-04-04 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-04-24 | 2025-04-07 | 2025-04-16 |  |  | 2026-06-04 | 0 | 5000406604_2025_0001 | 2025-02-24 |  | 2025-02-18 | 100079184 |  | 0 | 2 | 3 | 90028299 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000406604 |  | 0 | 2025 | /018012598 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017494 | 1120-3188 Samson, Packing Set | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028299_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-07 | 99 |  | 2025-04-07 | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241339 | S002 |  |  | 5300019686 | 10 |  | 5300019687 | 10 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244787 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-30 | VALVE | 100079185 | 0050 | 0010 | 100079185 | CV-OH 1" 600# 124LCV27 | AA53.124LCV27 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 70017494 | 1120-3188 Samson, Packing Set | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 19.02 - SOH @ AA02 | Supply for Order 100079185, Item 1 cannot be changed – 4500041815 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 80 | AA02 | 5300019688 | 10 | CPT | 80 | 1000027268 | 1 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500041815 | 20 | 1 | KIT | 2025-03-25 |  | /180125986 |  | 90028300 | 05 | Preparation | 0000244788 | 1 | 0 | KIT | 101000000146117 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028300_0010 | 0 | 54 | 54 | 54 | 2025-04-04 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-04-24 | 2025-04-07 | 2025-04-16 |  |  | 2026-06-04 | 0 | 5000406605_2025_0001 | 2025-02-24 |  | 2025-02-18 | 100079185 |  | 0 | 2 | 3 | 90028300 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000406605 |  | 0 | 2025 | /018012598 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017494 | 1120-3188 Samson, Packing Set | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028300_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-07 | 99 |  | 2025-04-07 | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241340 | S002 |  |  | 5300019688 | 10 |  | 5300019689 | 10 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244788 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-30 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | VALVE | 100079184 | 0050 | 0020 | 100079184 | CV-OH 1" 600# 124LCV26 | AA53.124LCV26 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 70017495 | 0430-3675 Samson, Gasket Bonnet | 1 | EA | 2 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 100079184, Item 4 cannot be changed – 4500041815 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 80 | AA02 | 5300019686 | 20 | CPT | 80 | 1000027267 | 4 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500041815 | 30 | 1 | EA | 2025-03-25 |  | /180125986 |  | 90028299 | 05 | Preparation | 0000244787 | 4 | 0 | EA | 101000000146163 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028299_0020 | 0 | 54 | 54 | 54 | 2025-04-04 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-04-24 | 2025-04-07 | 2025-04-16 |  |  | 2026-06-04 | 0 | 5000406665_2025_0001 | 2025-02-24 |  | 2025-02-18 | 100079184 |  | 0 | 2 | 3 | 90028299 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000406665 |  | 0 | 2025 | /018012598 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017495 | 0430-3675 Samson, Gasket Bonnet | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028299_0020 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-07 | 99 |  | 2025-04-07 | 4 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241339 | S002 |  |  | 5300019686 | 20 |  | 5300019687 | 20 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244787 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-30 | VALVE | 100079185 | 0050 | 0020 | 100079185 | CV-OH 1" 600# 124LCV27 | AA53.124LCV27 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 70017495 | 0430-3675 Samson, Gasket Bonnet | 1 | EA | 2 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 100079185, Item 2 cannot be changed – 4500041815 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 80 | AA02 | 5300019688 | 20 | CPT | 80 | 1000027268 | 2 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500041815 | 40 | 1 | EA | 2025-03-25 |  | /180125986 |  | 90028300 | 05 | Preparation | 0000244788 | 2 | 0 | EA | 101000000146164 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028300_0020 | 0 | 54 | 54 | 54 | 2025-04-04 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-04-24 | 2025-04-07 | 2025-04-16 |  |  | 2026-06-04 | 0 | 5000406654_2025_0001 | 2025-02-24 |  | 2025-02-18 | 100079185 |  | 0 | 2 | 3 | 90028300 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000406654 |  | 0 | 2025 | /018012598 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017495 | 0430-3675 Samson, Gasket Bonnet | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028300_0020 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-07 | 99 |  | 2025-04-07 | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241340 | S002 |  |  | 5300019688 | 20 |  | 5300019689 | 20 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244788 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-30 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2025-01-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | VALVE | 100032673 | 0050 | 0030 | 100032673 | CV-OH 1" 300# 118LCV508 | AA53.118LCV508 | VALVE,S/OIL DRN POT K1820V4A LOCAL LVL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.01.2025) | 70017521 | AK120 Samson, Actuator Repair Kit | 1 | KIT | 1 | 0 | 0 | 1 | KIT | 20.02 - SOH @ AA02 | Supply for Order 100032673, Item 10 cannot be changed – 4500041815 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 80 | AA02 | 5300019684 | 30 | CPT | 80 | 1000027266 | 10 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500041815 | 70 | 1 | KIT | 2025-03-25 |  | /180125986 |  | 90028298 | 05 | Preparation | 0000131165 | 10 | 0 | KIT | 102000000033552 | 101000000146168 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-07 | ODST-0090028298_0030 | 0 | 54 | 54 | 54 | 2025-04-04 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-04-24 | 2025-04-07 | 2025-04-16 |  |  | 2024-06-02 | 0 | 5000406671_2025_0001 | 2025-02-24 |  | 2025-02-18 | 100032673 |  | 0 | 2 | 3 | 90028298 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000406671 |  | 0 | 2025 | /018012598 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017521 | AK120 Samson, Actuator Repair Kit | 2025-01-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90028298_0030 |  |  | FR1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2025-01-07 | 20 |  | 2025-04-07 | 10 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130515 | S002 |  |  | 5300019684 | 30 |  | 5300019685 | 30 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131165 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2024-12-11 | 2025-03-01 | 2025-02-05 | 2025-03-01 | 2025-03-01 | ROTAT | 100084733 | 0050 | 0010 | 100084733 | Replace G/box Compartment Damper | AA53.GT4007K1A | FAN,TURB ACCOUSTIC ENCLOSURE VENT,GT4007 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 70017611 | Back Draft Damper For GT4007 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 16.04.25 PO 4500043718 ex Unique Metals Laser | Supply for Order 100084733, Item 2 cannot be changed 90028561 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 100 | AA01 | 5300019774 | 10 | CPT | 100 | 1000027345 | 2 | 30002705 | UNIQUE METALS LASER UNIQUE METAL WORKS PTY LTD | 4500043718 | 10 | 1 | EA | 2025-04-16 |  |  |  | 90028561 | 05 | Preparation | 0000266516 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-08 | ODST-0090028561_0010 | 0 | 88 | 88 | 88 | 2025-04-28 | 2025-02-15 | AA53 | 2025-03-01 |  |  | 2025-05-28 | 2025-05-04 | 2025-05-20 |  |  | 2026-05-09 | 0 |  | 2025-02-05 |  | 2025-02-21 | 100084733 |  | 0 | 6 | 6 | 90028561 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017611 | Back Draft Damper For GT4007 | 2025-01-08 | W |  | 0050 | Install New Damper | INT | Install New Damper |  |  | 90028561_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-10 | 99 |  | 2025-05-04 | 0 |  | 0 |  | 25SDGT7 | MJ |  | AU1009 | 1000261692 | S001 |  |  | 5300019767 | 10 |  | 5300019774 | 10 | 1 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2024-09-22 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2025-01-22 | 2025-03-01 | 2025-02-05 | 2025-03-01 | 2025-03-03 | ROTAT | 600003223 | 0060 | 0010 | 600003223 | Replace Turbine Comp Inlet Damper GT4008 | AA53.408DA001 | DAMP,ACTUATED,INLET GT4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.01.2025) | 70017612 | Gas Turbine Compartment Fire Damp G4008 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 16.04.25 PO 4500043718 ex Unique Metals Laser | Supply for Order 600003223, Item 1 cannot be changed 90029250 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 100 | AA01 | 5300020296 | 10 | CPT | 100 | 1000028375 | 1 | 30002705 | UNIQUE METALS LASER UNIQUE METAL WORKS PTY LTD | 4500043718 | 20 | 1 | EA | 2025-04-16 |  |  |  | 90029250 | 05 | Preparation | 0000257383 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-22 | ODST-0090029250_0010 | 0 | 102 | 102 | 102 | 2025-05-12 | 2025-02-15 | AA53 | 2025-03-01 |  |  | 2025-06-11 | 2025-05-18 | 2025-06-03 |  |  | 2025-12-19 | 0 |  | 2025-02-05 |  | 2025-02-21 |  |  | 0 | 6 | 6 | 90029250 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017612 | Gas Turbine Compartment Fire Damp G4008 | 2025-01-22 | W |  | 0060 | Install Inlet Fire damper 408DA001 | INT | Install Inlet Fire damper 408DA001 |  |  | 90029250_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-01-23 | 5 |  | 2025-05-18 | 0 |  | 0 |  | 25SDGT8 | MJ |  | AU1009 | 1000253320 | S001 |  |  | 5300020295 | 10 |  | 5300020296 | 10 | 1 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-08-16 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM06 | Capital
| 25SDGT7 | Released | 2025-01-22 | 2025-03-01 | 2025-02-05 | 2025-03-01 | 2025-03-03 | ROTAT | 600003156 | 0060 | 0010 | 600003156 | Replace Turbine Comp Inlet Damper GT4007 | AA53.407DA001 | DAMP,ACTUATED,INLET GT4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 70017613 | Gas Turbine Compartment Fire Damp G4007 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 16.04.25 PO 4500043718 ex Unique Metals Laser | Supply for Order 600003156, Item 1 cannot be changed 90028562 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 100 | AA01 | 5300019795 | 10 | CPT | 100 | 1000027415 | 1 | 30002705 | UNIQUE METALS LASER UNIQUE METAL WORKS PTY LTD | 4500043718 | 30 | 1 | EA | 2025-04-16 |  |  |  | 90028562 | 05 | Preparation | 0000257411 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028562_0010 | 0 | 88 | 88 | 88 | 2025-04-28 | 2025-02-15 | AA53 | 2025-03-01 |  |  | 2025-05-28 | 2025-05-04 | 2025-05-20 |  |  | 2025-12-19 | 0 |  | 2025-02-05 |  | 2025-02-21 | 600003156 |  | 0 | 6 | 6 | 90028562 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70017613 | Gas Turbine Compartment Fire Damp G4007 | 2025-01-08 | W |  | 0060 | Install Inlet Fire damper 407DA001 | INT | Install Inlet Fire damper 407DA001 |  |  | 90028562_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-01-10 | 5 |  | 2025-05-04 | 0 |  | 0 |  | 25SDGT7 | MJ |  | AU1009 | 1000253392 | S001 |  |  | 5300019794 | 10 |  | 5300019795 | 10 | 1 | EA | 1001 | AA02 | 2025-02-05 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-08-16 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM06 | Capital
| 25SDGT8 | Released | 2025-02-06 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-01 | ROTAT | 100088187 | 0010 | 0020 | 100088187 | Damage to Gear Box (AGB) vent hose#27 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 70019067 | AGB Hose 27 - BH723213P0001 | 1 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 28.06.25 PO 4500045959 ex BH | Supply for Order 100088187, Item 5 cannot be changed 90030311 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 130 | AA01 | 5300020879 | 10 | FCA | 130 | 1000029300 | 5 | 30000104 | BAKER HUGHES SERVICES AUSTRALIA PTY | 4500048275 | 10 | 1 | EA | 2025-06-23 |  |  |  | 90030311 | 05 | Preparation | 0000281252 | 5 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-05 | ODST-0090030311_0010 | 0 | 134 | 134 | 134 | 2025-06-23 | 2025-02-21 | AA53 | 2025-03-01 |  |  | 2025-07-13 | 2025-06-26 | 2025-07-08 |  |  | 2025-11-27 | 0 |  | 2025-02-12 |  | 2025-02-24 | 100088187 |  | 0 | 3 | 3 | 90030311 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019067 | AGB Hose 27 - BH723213P0001 | 2025-02-05 | W |  | 0010 | Remove & Replace Hose | INT | Remove & Replace Hose |  |  | 90030311_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-06 | 30 |  | 2025-06-26 | 0 |  | 0 |  | 25SDGT8 | MJ |  | AU1009 | 1000275607 | S001 |  |  | 5300020878 | 10 |  | 5300020879 | 10 | 1 | EA | 1001 | AA02 | 2025-02-12 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-12-02 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Material shortage/Order Approved/Released/Settlement rule created | AM01 | Reactive Maintenance
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-10 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0200 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.02.2025) | 70019206 | TX, PRESS, 3051CG3A02A1BH2E7Y2L4Q4Q8QTP1 | 2 | EA | 0 | 0 | 0 | 0 |  | 16.02 - ETA 06.03.25 PO 4500046133 EMERSON CPT | Supply for Order 600001815, Item 28 cannot be changed 90030573 item 10 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 21 | AA01 | 5300011702 | 70 | CPT | 21 | 1000029658 | 28 | 30000401 | EMERSON PROCESS MANAGEMENT AUSTRALIA PTY LTD | 4500046133 | 10 | 2 | EA | 2025-03-06 |  | 180134065 |  | 90030573 | 07 | Execution | 0000084731 | 28 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-06-18 | ODST-0090030573_0010 | 0 | 38 | 34 | 38 | 2025-03-10 | 2025-02-15 | AA53 | 2025-02-08 |  |  | 2025-04-08 | 2025-03-16 | 2025-03-31 |  |  | 2024-08-30 | 0 |  | 2025-02-10 |  | 2025-02-25 | 37FQI40/41 |  | 0 | 6 | 6 | 90030573 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | 180134065 | 2025-02-10 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019206 | TX, PRESS, 3051CG3A02A1BH2E7Y2L4Q4Q8QTP1 | 2025-02-10 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030573_0010 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-10 | 10 |  | 2025-03-16 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 |  |  | 5300007843 | 210 |  | 5300011702 | 70 | 2 | EA | 1001 | AA02 | 2025-02-10 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-10 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0210 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.02.2025) | 70019207 | TX, TEMP SENSOR 214CRWSMB1S4E0242SLE7M2 | 2 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 06.03.25 PO 4500046133 EMERSON CPT | Supply for Order 600001815, Item 29 cannot be changed 90030573 item 20 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 21 | AA01 | 5300011702 | 80 | CPT | 21 | 1000029658 | 29 | 30000401 | EMERSON PROCESS MANAGEMENT AUSTRALIA PTY LTD | 4500046133 | 20 | 2 | EA | 2025-03-06 |  | 180134065 |  | 90030573 | 07 | Execution | 0000084731 | 29 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-06-18 | ODST-0090030573_0020 | 0 | 38 | 34 | 38 | 2025-03-10 | 2025-02-15 | AA53 | 2025-02-08 |  |  | 2025-04-08 | 2025-03-16 | 2025-03-31 |  |  | 2024-08-30 | 0 |  | 2025-02-10 |  | 2025-02-25 | 37FQI40/41 |  | 0 | 6 | 6 | 90030573 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | 180134065 | 2025-02-10 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019207 | TX, TEMP SENSOR 214CRWSMB1S4E0242SLE7M2 | 2025-02-10 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030573_0020 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-10 | 10 |  | 2025-03-16 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 |  |  | 5300007843 | 220 |  | 5300011702 | 80 | 2 | EA | 1001 | AA02 | 2025-02-10 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-10 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0220 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.02.2025) | 70019208 | TX, TEMP 3144PD2A1E7C4Q4K1105 | 2 | EA | 0 | 0 | 0 | 0 |  | 16.02 - ETA 06.03.25 PO 4500046133 EMERSON CPT | Supply for Order 600001815, Item 31 cannot be changed 90030573 item 30 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 21 | AA01 | 5300011702 | 90 | CPT | 21 | 1000029658 | 31 | 30000401 | EMERSON PROCESS MANAGEMENT AUSTRALIA PTY LTD | 4500046133 | 30 | 2 | EA | 2025-03-06 |  | 180134065 |  | 90030573 | 07 | Execution | 0000084731 | 31 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-06-18 | ODST-0090030573_0030 | 0 | 59 | 55 | 59 | 2025-03-31 | 2025-02-15 | AA53 | 2025-02-08 |  |  | 2025-04-29 | 2025-04-06 | 2025-04-21 |  |  | 2024-08-30 | 0 |  | 2025-02-10 |  | 2025-02-25 | 37FQI40/41 |  | 0 | 6 | 6 | 90030573 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | 180134065 | 2025-02-10 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019208 | TX, TEMP 3144PD2A1E7C4Q4K1105 | 2025-02-10 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030573_0030 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-28 | 10 |  | 2025-04-06 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 |  |  | 5300007843 | 230 |  | 5300011702 | 90 | 2 | EA | 1001 | AA02 | 2025-02-10 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-10 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0230 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.02.2025) | 70019209 | JB, SS316L PEPPERL+FUCHS FXLS211D | 1 | EA | 0 | 0 | 0 | 0 |  | 16.02 - ETA 06.03.25 PO 4500046201 PEPPERL CPT | Supply for Order 600001815, Item 33 cannot be changed 90030573 item 40 already exists | Vendor PO raised | SP97 | Direct Multi-base | 21 | AA01 | 5300011702 | 100 | CPT | 21 | 1000029658 | 33 | 30002363 | PEPPERL AND FUCHS AUST PTY LTD | 4500046201 | 10 | 1 | EA | 2025-03-07 |  |  |  | 90030573 | 07 | Execution | 0000084731 | 33 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-06-18 | ODST-0090030573_0040 | 0 | 38 | 34 | 38 | 2025-03-10 | 2025-02-15 | AA53 | 2025-02-08 |  |  | 2025-04-08 | 2025-03-16 | 2025-03-31 |  |  | 2024-08-30 | 0 |  | 2025-02-10 |  | 2025-02-25 | 37FQI40/41 |  | 0 | 6 | 6 | 90030573 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-10 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019209 | JB, SS316L PEPPERL+FUCHS FXLS211D | 2025-02-10 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030573_0040 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-10 | 10 |  | 2025-03-16 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 |  |  | 5300007843 | 240 |  | 5300011702 | 100 | 1 | EA | 1001 | AA02 | 2025-02-10 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDDG1 | Released | 2025-02-17 | 2025-03-01 | 2025-02-12 | 2025-02-28 | 2025-03-01 | INLEC | 100043585 | 0020 | 0010 | 100043585 | MOC-150533 Junction Box Replace 124ST061 | AA53.124ST061J | JB,TXDCR,SPEED TURBO EXP 1KT2410 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 70019374 | CROUSE-HINDS EJBA1286GW24121801 | 1 | EA | 0 | 0 | 0 | 0 |  | 16.02 - ETA 18.04.25 PO 4500046223 MM ELECTRICALS CPT | Supply for Order 100043585, Item 2 cannot be changed 90030739 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 42 | AA01 | 5300021185 | 10 | CPT | 42 | 1000029826 | 2 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500046223 | 10 | 1 | EA | 2025-04-18 |  |  |  | 90030739 | 05 | Preparation | 0000142106 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-12 | ODST-0090030739_0010 | 0 | 52 | 52 | 52 | 2025-04-02 | 2025-02-21 | AA53 | 2025-03-01 |  |  | 2025-04-22 | 2025-04-05 | 2025-04-17 |  |  | 2021-04-05 | 0 |  | 2025-02-12 |  | 2025-02-24 | AA53.124ST06 |  | 0 | 3 | 3 | 90030739 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019374 | CROUSE-HINDS EJBA1286GW24121801 | 2025-02-12 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030739_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-12 | 99 |  | 2025-04-05 | 0 |  | 0 |  | 25SDDG1 | MJ |  | AU1009 | 1000141475 | S001 |  |  | 5300021184 | 10 |  | 5300021185 | 10 | 1 | EA | 1001 | AA02 | 2025-02-12 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Material shortage/Order Approved/Released/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-17 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0880 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.02.2025) | 70019625 | Box Stuffing C10-601-9939A | 2 | EA | 0 | 0 | 0 | 0 |  | 20.02 - ETA 24.04.25 PO 4500046479 TECH AUS CPT | Supply for Order 200147980, Item 193 cannot be changed 90030999 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 70 | AA01 | 5300020791 | 20 | CPT | 70 | 1000030104 | 193 | 30003106 | TECHNICAL AUSTRALIA PTY LTD | 4500046479 | 10 | 2 | EA | 2025-05-05 |  |  |  | 90030999 | 05 | Preparation | 0000236589 | 193 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-03 | ODST-0090030999_0010 | 0 | 94 | 83 | 94 | 2025-05-05 | 2025-02-15 | AA53 | 2025-03-01 |  |  | 2025-06-03 | 2025-05-11 | 2025-05-26 |  |  | 2025-12-14 | 0 |  | 2025-02-17 |  | 2025-03-04 |  |  | 0 | 6 | 6 | 90030999 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019625 | Box Stuffing C10-601-9939A | 2025-02-17 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90030999_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-17 | 20 |  | 2025-05-11 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000233553 | S001 |  |  | 5300015696 | 960 |  | 5300020791 | 20 | 2 | EA | 1001 | AA02 | 2025-02-17 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2025-02-08 | 2025-03-01 | 2025-02-18 | 2025-03-01 | 2025-03-01 | INLEC | 100085195 | 0020 | 0020 | 100085195 | MOC-150408: RTD Replace - 1K2301 | AA53.123TE052 | TXDCR,TEMP ALARM 1V2305A INLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(17.02.2025) | 70019661 | ROSEMOUNT, TEMP, SENSOR 214CRTSMA1S4M027 | 1 | EA | 0 | 0 | 0 | 0 |  | 20.02 - ETA 28.03.25 PO 4500046943 EMERSON CPT | Supply for Order 100085195, Item 3 cannot be changed 90031100 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 28 | AA01 | 5300021393 | 10 | CPT | 28 | 1000030182 | 3 | 30000401 | EMERSON PROCESS MANAGEMENT AUSTRALIA PTY LTD | 4500046943 | 10 | 1 | EA | 2025-03-28 |  |  |  | 90031100 | 05 | Preparation | 0000267848 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-18 | ODST-0090031100_0010 | 0 | 52 | 40 | 52 | 2025-03-24 | 2025-02-15 | AA53 | 2025-03-01 |  |  | 2025-04-22 | 2025-03-30 | 2025-04-14 |  |  | 2025-07-31 | 0 |  | 2025-02-18 |  | 2025-03-05 | 123TE052 |  | 0 | 6 | 6 | 90031100 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019661 | ROSEMOUNT, TEMP, SENSOR 214CRTSMA1S4M027 | 2025-02-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90031100_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-18 | 30 |  | 2025-03-30 | 0 |  | 0 |  | 25SD2301 | MJ |  | AU1009 | 1000262907 | S001 |  |  | 5300021008 | 20 |  | 5300021393 | 10 | 1 | EA | 1001 | AA02 | 2025-02-18 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Printed/Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance
| 25SD4403 | Released | 2025-02-24 | 2025-03-01 | 2025-02-21 | 2025-03-01 | 2025-03-02 | INLEC | 100031876 | 0030 | 0010 | 100031876 | Replace Needle Manifold - 44FV540 | AA53.44PDT531 | TX,PRESS K4403 SEALGAS PRIM VNT TO FLRE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2025) | 70019806 | RVO094488500 Manifold | 2 | EA | 0 | 0 | 0 | 0 |  | 24.02 - ETA 13.06.25 PO 4500047101 WIKA CPT | Supply for Order 100031876, Item 2 cannot be changed 90031409 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 112 | AA01 | 5300021637 | 10 | CPT | 112 | 1000030479 | 2 | 30000288 | WIKA AUSTRALIA PTY LTD | 4500047101 | 10 | 2 | EA | 2025-06-13 |  |  |  | 90031409 | 05 | Preparation | 0000130317 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-21 | ODST-0090031409_0010 | 0 | 134 | 122 | 134 | 2025-06-20 | 2025-02-21 | AA53 | 2025-03-01 |  |  | 2025-07-13 | 2025-06-23 | 2025-07-08 |  |  | 2024-11-08 | 0 |  | 2025-02-21 |  | 2025-03-08 | 100031876/77 |  | 0 | 3 | 3 | 90031409 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-21 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019806 | RVO094488500 Manifold | 2025-02-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 90031409_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-21 | 30 |  | 2025-06-23 | 0 |  | 0 |  | 25SD4403 | MJ |  | AU1009 | 1000129686 | S001 |  |  | 5300021636 | 10 |  | 5300021637 | 10 | 2 | EA | 1001 | AA02 | 2025-02-21 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Material shortage/Order Approved/Released/Settlement rule created/Part printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2025-02-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100076446 | 0020 | 0010 | 100076446 | MOC-150907 F/Meter Replace 144FI85 | AA53.144FI85 | METER,PURGE DEGASS TK K4401A | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(24.02.2025) | 70019848 | Brookes 3750CC2A113LAAA4A0 Rotameter | 1 | EA | 0 | 0 | 0 | 0 |  | 27.02 - ETA 07.04.25 PO 4500047299 MESURE PLUS CPT | Supply for Order 100076446, Item 2 cannot be changed 90031545 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 42 | AA01 | 5300021709 | 10 | CPT | 42 | 1000030604 | 2 | 30002444 | MEASUREMENT PLUS PTY LTD | 4500047299 | 10 | 1 | EA | 2025-04-07 |  |  |  | 90031545 | 05 | Preparation | 0000232992 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-24 | ODST-0090031545_0010 | 0 | 66 | 53 | 66 | 2025-04-15 | 2025-02-21 | AA53 | 2025-03-01 |  |  | 2025-05-06 | 2025-04-18 | 2025-05-01 |  |  | 2026-03-31 | 0 |  | 2025-02-24 |  | 2025-03-09 | 144FI85 |  | 0 | 3 | 3 | 90031545 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019848 | Brookes 3750CC2A113LAAA4A0 Rotameter | 2025-02-24 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90031545_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-24 | 99 |  | 2025-04-18 | 0 |  | 0 |  | 25SD4401 | MJ |  | AU1009 | 1000230115 | S001 |  |  | 5300021708 | 10 |  | 5300021709 | 10 | 1 | EA | 1001 | AA02 | 2025-02-24 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-04-17 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Material shortage/Order Approved/Released/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 | 2025-02-25 | 2025-02-28 | 2025-03-02 | ROTAT | 100033221 | 0042 | 0010 | 100033221 | MOC-115058 Regrout - 5K2001 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.02.2025) | 70019909 | Oversize Bolt D=65.3 Part No. SPQ71467 | 12 | EA | 0 | 0 | 0 | 0 |  | 27.02 - ETA 15.04.25 PO 4500047485 BH FCA | Supply for Order 100033221, Item 5 cannot be changed 90031653 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 49 | AA01 | 5300021759 | 10 | FCA | 49 | 1000030712 | 5 | 30000104 | BAKER HUGHES SERVICES AUSTRALIA PTY | 4500047485 | 10 | 12 | EA | 2025-04-29 |  |  |  | 90031653 | 05 | Preparation | 0000131733 | 5 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-02-25 | ODST-0090031653_0010 | 0 | 83 | 63 | 79 | 2025-04-23 | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-05-27 | 2025-04-29 | 2025-05-15 |  |  | 2025-07-31 | 0 |  | 2025-02-25 |  | 2025-03-13 |  |  | 0 | 6 | 6 | 90031653 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019909 | Oversize Bolt D=65.3 Part No. SPQ71467 | 2025-02-25 | W |  | 0042 | 5K2001 Regrout - MOC-115058 | INT | 5K2001 Regrout - MOC-115058 |  | Management of Change | 90031653_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-25 | 5 |  | 2025-04-29 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000131143 | S001 |  |  | 5300021758 | 10 |  | 5300021759 | 10 | 12 | EA | 1001 | AA02 | 2025-02-25 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Order Approved/Settlement rule created/Released/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0110 | 0040 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.02.2025) | 70019912 | V7-445 O RING VITON 75 DURO | 3 | EA | 0 | 0 | 0 | 3 | EA | 10.03 - DEL: 90031877 | Supply for Order 200091108, Item 133 cannot be changed 90031877 item 40 already exists | Workpack awaiting Shipment @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300013063 | 50 | CPT | 21 | 1000030819 | 133 | 30001936 | MINING AND HYDRAULIC SUPPLIES KEN FLETCHER FAMILY TRUST | 4500048336 | 10 | 3 | EA | 2025-03-28 |  | /180133373 |  | 90031877 | 05 | Preparation | 0000129406 | 133 | 0 | EA | 101000000153043 |  | 101000000152846 | 01-Road |  | 1-Not Started |  | WorkPackLink | 1020 KSF SUPPLY | P07 | 0 |  | 0 | 0 |  | 0 | 3 |  | 2025-03-12 | Y | 1001 | 2024-07-20 | ODST-0090031877_0040 | 0 | 50 | 32 | 47 | 2025-03-28 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-23 | 2025-03-31 | 2025-04-15 |  |  | 2025-04-28 | 0 | 5000434881_2025_0001 | 2025-02-27 |  | 2025-03-10 | HYD HD M70 |  | 0 | 3 | 3 | 90031877 | 0 | 3 |  | 2 | 0 | 0 | X | L |  | 0 | 5000434881 |  | 0 | 2025 | /018013337 | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019912 | V7-445 O RING VITON 75 DURO | 2025-02-27 | W |  | 0110 | SPECIAL TOOLING | INT | SPECIAL TOOLING |  |  | 90031877_0040 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-27 | 20 |  | 2025-03-31 | 0 |  | 0 |  | 25SD2420 | MJ | 20005387 | AU1009 | 1000128737 | S001 |  |  | 5300013062 | 950 |  | 5300013063 | 50 | 3 | EA | 1001 | AA02 | 2025-02-27 |  |  | 2025-03-10 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 3 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 | 2025-02-25 | 2025-02-28 | 2025-03-02 | ROTAT | 100033221 | 0042 | 0020 | 100033221 | MOC-115058 Regrout - 5K2001 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.02.2025) | 70019920 | Nut Part no. RDP03020 | 12 | EA | 0 | 0 | 0 | 0 |  | 27.02 - ETA 15.04.25 PO 4500047485 BH FCA | Supply for Order 100033221, Item 6 cannot be changed 90031653 item 20 already exists | Vendor PO raised | SP97 | Direct Multi-base | 63 | AA01 | 5300021759 | 20 | FCA | 63 | 1000030712 | 6 | 30000104 | BAKER HUGHES SERVICES AUSTRALIA PTY | 4500047485 | 20 | 12 | EA | 2025-04-29 |  |  |  | 90031653 | 05 | Preparation | 0000131733 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-02-25 | ODST-0090031653_0020 | 0 | 97 | 77 | 93 | 2025-05-07 | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-06-10 | 2025-05-13 | 2025-05-29 |  |  | 2025-07-31 | 0 |  | 2025-02-25 |  | 2025-03-13 |  |  | 0 | 6 | 6 | 90031653 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019920 | Nut Part no. RDP03020 | 2025-02-25 | W |  | 0042 | 5K2001 Regrout - MOC-115058 | INT | 5K2001 Regrout - MOC-115058 |  | Management of Change | 90031653_0020 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-25 | 5 |  | 2025-05-13 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000131143 | S001 |  |  | 5300021758 | 20 |  | 5300021759 | 20 | 12 | EA | 1001 | AA02 | 2025-02-25 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Order Approved/Settlement rule created/Released/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 | 2025-02-25 | 2025-02-28 | 2025-03-02 | ROTAT | 100033221 | 0042 | 0030 | 100033221 | MOC-115058 Regrout - 5K2001 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.02.2025) | 70019921 | Split Pin Part no FDJ10080 | 12 | EA | 0 | 0 | 0 | 0 |  | 27.02 - ETA 15.04.25 PO 4500047485 BH FCA | Supply for Order 100033221, Item 7 cannot be changed 90031653 item 30 already exists | Vendor PO raised | SP97 | Direct Multi-base | 42 | AA01 | 5300021759 | 30 | FCA | 42 | 1000030712 | 7 | 30000104 | BAKER HUGHES SERVICES AUSTRALIA PTY | 4500047485 | 30 | 12 | EA | 2025-04-29 |  |  |  | 90031653 | 05 | Preparation | 0000131733 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-02-25 | ODST-0090031653_0030 | 0 | 76 | 56 | 72 | 2025-04-16 | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-05-20 | 2025-04-22 | 2025-05-08 |  |  | 2025-07-31 | 0 |  | 2025-02-25 |  | 2025-03-13 |  |  | 0 | 6 | 6 | 90031653 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019921 | Split Pin Part no FDJ10080 | 2025-02-25 | W |  | 0042 | 5K2001 Regrout - MOC-115058 | INT | 5K2001 Regrout - MOC-115058 |  | Management of Change | 90031653_0030 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-25 | 5 |  | 2025-04-22 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000131143 | S001 |  |  | 5300021758 | 30 |  | 5300021759 | 30 | 12 | EA | 1001 | AA02 | 2025-02-25 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Order Approved/Settlement rule created/Released/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 | 2025-02-25 | 2025-02-28 | 2025-03-02 | ROTAT | 100033221 | 0042 | 0040 | 100033221 | MOC-115058 Regrout - 5K2001 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.02.2025) | 70019922 | Reamer RCO43473 | 1 | EA | 0 | 0 | 0 | 0 |  | 27.02 - ETA 15.04.25 PO 4500047485 BH FCA | Supply for Order 100033221, Item 8 cannot be changed 90031653 item 40 already exists | Vendor PO raised | SP97 | Direct Multi-base | 56 | AA01 | 5300021759 | 40 | FCA | 56 | 1000030712 | 8 | 30000104 | BAKER HUGHES SERVICES AUSTRALIA PTY | 4500047485 | 40 | 1 | EA | 2025-04-29 |  |  |  | 90031653 | 05 | Preparation | 0000131733 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-25 | ODST-0090031653_0040 | 0 | 90 | 70 | 86 | 2025-04-30 | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-06-03 | 2025-05-06 | 2025-05-22 |  |  | 2025-07-31 | 0 |  | 2025-02-25 |  | 2025-03-13 |  |  | 0 | 6 | 6 | 90031653 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019922 | Reamer RCO43473 | 2025-02-25 | W |  | 0042 | 5K2001 Regrout - MOC-115058 | INT | 5K2001 Regrout - MOC-115058 |  | Management of Change | 90031653_0040 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-25 | 5 |  | 2025-05-06 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000131143 | S001 |  |  | 5300021758 | 40 |  | 5300021759 | 40 | 1 | EA | 1001 | AA02 | 2025-02-25 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Order Approved/Settlement rule created/Released/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDKGP1 | Released | 2025-02-25 | 2025-04-26 | 2025-03-07 | 2025-04-26 | 2025-04-26 | NOMAINT | 600003962 | 0010 | 0040 | 600003962 | 25SD MINOR CAP Tooling & Equipment | AA53.1000 | KGP Non-Maintenance | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(25.02.2025) | 70019950 | Kit 1C3569GXXX Hyd VSV Actuator Unit | 1 | EA | 0 | 0 | 0 | 1 | EA | 27.02 - ETA 04.04.25 PO 4500047541 VRB TURB FCA | Supply for Order 600003962, Item 7 cannot be changed 90031655 item 10 already exists | Material work-packed @AA01 | SP97 | Direct Multi-base | 30 | AA01 | 5300021774 | 10 | FCA | 30 | 1000030742 | 7 | 30003334 | VBR TURBINE PARTNERS | 4500047541 | 10 | 1 | EA | 2025-04-04 |  | 180131698 |  | 90031655 | 05 | Preparation | 0000294038 | 7 | 0 | EA |  |  | 101000000153230 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-25 | ODST-0090031655_0010 | 0 | 31 | 31 | 31 | 2025-04-04 | 2025-03-18 | AA53 | 2025-04-26 |  |  | 2025-04-26 | 2025-04-07 | 2025-04-21 |  |  | 2025-12-31 | 0 | 5000435330_2025_0001 | 2025-03-07 |  | 2025-03-10 |  |  | 0 | 3 | 3 | 90031655 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000435330 |  | 0 | 2025 | 180131698 | 2025-03-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70019950 | Kit 1C3569GXXX Hyd VSV Actuator Unit | 2025-02-25 | W |  | 0010 | 25SD MINOR CAP Tooling & Equipment | INT | 25SD MINOR CAP Tooling & Equipment |  |  | 90031655_0010 | [5 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 104 | Proj & Brownfields | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-25 | 20 |  | 2025-04-07 | 0 |  | 0 |  | 25SDKGP1 | MJ |  | AU1009 | 1000287802 | S001 |  |  | 5300021763 | 30 |  | 5300021774 | 10 | 1 | EA | 1001 | AA02 | 2025-03-07 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2025-02-04 | 0 | 0 | 1 |  | 1010 | 1 | PJ | Project | 4 | Medium | RC00018003 | 2025-04-26 | 2025-04-26 | 2025-04-26 | Pre-costed/Object created/Settlement rule created/Released/Material shortage/Date set by external system | AM06 | Capital
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0110 | 0050 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.02.2025) | 70020008 | V7-445A O RING VITON 75 DURO | 3 | EA | 0 | 0 | 0 | 3 | EA | 10.03 - DEL: 90031877 | Supply for Order 200091108, Item 135 cannot be changed 90031877 item 50 already exists | Workpack awaiting Shipment @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300013063 | 60 | CPT | 21 | 1000030921 | 135 | 30001936 | MINING AND HYDRAULIC SUPPLIES KEN FLETCHER FAMILY TRUST | 4500048336 | 30 | 3 | EA | 2025-03-28 |  | /180133373 |  | 90031877 | 05 | Preparation | 0000129406 | 135 | 0 | EA | 101000000153044 |  | 101000000152846 | 01-Road |  | 1-Not Started |  | WorkPackLink | 1020 KSF SUPPLY | P07 | 0 |  | 0 | 0 |  | 0 | 3 |  | 2025-03-12 | Y | 1001 | 2024-07-20 | ODST-0090031877_0050 | 0 | 50 | 32 | 47 | 2025-03-28 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-23 | 2025-03-31 | 2025-04-15 |  |  | 2025-04-28 | 0 | 5000434913_2025_0001 | 2025-02-27 |  | 2025-03-10 | HYD HD M70 |  | 0 | 3 | 3 | 90031877 | 0 | 3 |  | 2 | 0 | 0 | X | L |  | 0 | 5000434913 |  | 0 | 2025 | /018013337 | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020008 | V7-445A O RING VITON 75 DURO | 2025-02-27 | W |  | 0110 | SPECIAL TOOLING | INT | SPECIAL TOOLING |  |  | 90031877_0050 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-27 | 20 |  | 2025-03-31 | 0 |  | 0 |  | 25SD2420 | MJ | 20005387 | AU1009 | 1000128737 | S001 |  |  | 5300013062 | 960 |  | 5300013063 | 60 | 3 | EA | 1001 | AA02 | 2025-02-27 |  |  | 2025-03-10 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 3 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0110 | 0010 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.02.2025) | 70020031 | V7-245 O RING VITON 75 DURO | 5 | EA | 0 | 0 | 0 | 5 | EA | 10.03 - DEL: 90031877 | Supply for Order 200091108, Item 127 cannot be changed 90031877 item 10 already exists | Workpack awaiting Shipment @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300013063 | 20 | CPT | 21 | 1000030868 | 127 | 30001936 | MINING AND HYDRAULIC SUPPLIES KEN FLETCHER FAMILY TRUST | 4500048336 | 20 | 5 | EA | 2025-03-28 |  | /180133373 |  | 90031877 | 05 | Preparation | 0000129406 | 127 | 0 | EA | 101000000153046 |  | 101000000152846 | 01-Road |  | 1-Not Started |  | WorkPackLink | 1020 KSF SUPPLY | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  | 2025-03-12 | Y | 1001 | 2024-07-20 | ODST-0090031877_0010 | 0 | 50 | 32 | 47 | 2025-03-28 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-23 | 2025-03-31 | 2025-04-15 |  |  | 2025-04-28 | 0 | 5000435053_2025_0001 | 2025-02-27 |  | 2025-03-10 | HYD HD 31/2" |  | 0 | 3 | 3 | 90031877 | 0 | 5 |  | 2 | 0 | 0 | X | L |  | 0 | 5000435053 |  | 0 | 2025 | /018013337 | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020031 | V7-245 O RING VITON 75 DURO | 2025-02-27 | W |  | 0110 | SPECIAL TOOLING | INT | SPECIAL TOOLING |  |  | 90031877_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-27 | 20 |  | 2025-03-31 | 0 |  | 0 |  | 25SD2420 | MJ | 20005387 | AU1009 | 1000128737 | S001 |  |  | 5300013062 | 920 |  | 5300013063 | 20 | 5 | EA | 1001 | AA02 | 2025-02-27 |  |  | 2025-03-10 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 5 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0110 | 0020 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.02.2025) | 70020039 | V7-254 O RING VITON 75 DURO | 5 | EA | 0 | 0 | 0 | 5 | EA | 10.03 - DEL: 90031877 | Supply for Order 200091108, Item 129 cannot be changed 90031877 item 20 already exists | Workpack awaiting Shipment @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300013063 | 30 | CPT | 21 | 1000030930 | 129 | 30001936 | MINING AND HYDRAULIC SUPPLIES KEN FLETCHER FAMILY TRUST | 4500048336 | 40 | 5 | EA | 2025-03-28 |  | /180133373 |  | 90031877 | 05 | Preparation | 0000129406 | 129 | 0 | EA | 101000000153047 |  | 101000000152846 | 01-Road |  | 1-Not Started |  | WorkPackLink | 1020 KSF SUPPLY | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  | 2025-03-12 | Y | 1001 | 2024-07-20 | ODST-0090031877_0020 | 0 | 50 | 32 | 47 | 2025-03-28 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-23 | 2025-03-31 | 2025-04-15 |  |  | 2025-04-28 | 0 | 5000435054_2025_0001 | 2025-02-27 |  | 2025-03-10 | HYD HD M64 |  | 0 | 3 | 3 | 90031877 | 0 | 5 |  | 2 | 0 | 0 | X | L |  | 0 | 5000435054 |  | 0 | 2025 | /018013337 | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020039 | V7-254 O RING VITON 75 DURO | 2025-02-27 | W |  | 0110 | SPECIAL TOOLING | INT | SPECIAL TOOLING |  |  | 90031877_0020 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-27 | 20 |  | 2025-03-31 | 0 |  | 0 |  | 25SD2420 | MJ | 20005387 | AU1009 | 1000128737 | S001 |  |  | 5300013062 | 930 |  | 5300013063 | 30 | 5 | EA | 1001 | AA02 | 2025-02-27 |  |  | 2025-03-10 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 5 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0110 | 0030 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.02.2025) | 70020043 | V7-356 O RING VITON 75 DURO | 5 | EA | 0 | 0 | 0 | 5 | EA | 10.03 - DEL: 90031877 | Supply for Order 200091108, Item 131 cannot be changed 90031877 item 30 already exists | Workpack awaiting Shipment @AA01 | SP97 | Direct Multi-base | 21 | AA01 | 5300013063 | 40 | CPT | 21 | 1000030931 | 131 | 30001936 | MINING AND HYDRAULIC SUPPLIES KEN FLETCHER FAMILY TRUST | 4500048336 | 50 | 5 | EA | 2025-03-28 |  | /180133373 |  | 90031877 | 05 | Preparation | 0000129406 | 131 | 0 | EA | 101000000153141 |  | 101000000152846 | 01-Road |  | 1-Not Started |  | WorkPackLink | 1020 KSF SUPPLY | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  | 2025-03-12 | Y | 1001 | 2024-07-20 | ODST-0090031877_0030 | 0 | 50 | 32 | 47 | 2025-03-28 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-23 | 2025-03-31 | 2025-04-15 |  |  | 2025-04-28 | 0 | 5000435099_2025_0001 | 2025-02-27 |  | 2025-03-10 | HYD HD M45 |  | 0 | 3 | 3 | 90031877 | 0 | 5 |  | 2 | 0 | 0 | X | L |  | 0 | 5000435099 |  | 0 | 2025 | /018013337 | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020043 | V7-356 O RING VITON 75 DURO | 2025-02-27 | W |  | 0110 | SPECIAL TOOLING | INT | SPECIAL TOOLING |  |  | 90031877_0030 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-27 | 20 |  | 2025-03-31 | 0 |  | 0 |  | 25SD2420 | MJ | 20005387 | AU1009 | 1000128737 | S001 |  |  | 5300013062 | 940 |  | 5300013063 | 40 | 5 | EA | 1001 | AA02 | 2025-02-27 |  |  | 2025-03-10 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 5 |  | 1010 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0100 | 0050 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.02.2025) | 70020050 | Piston Nut 2153.1013.000 | 2 | EA | 0 | 0 | 0 | 0 |  | 28.02 - ETA 13.05.25 PO 4500047852 HOWDEN CPT | Supply for Order 200091126, Item 155 cannot be changed 90031879 item 10 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 10 | AA01 | 5300015752 | 30 | CPT | 10 | 1000030925 | 155 | 30002002 | HOWDEN AUSTRALIA PTY LTD | 4500047852 | 10 | 2 | EA | 2025-05-22 |  | 180134076 |  | 90031879 | 05 | Preparation | 0000129360 | 155 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-25 | ODST-0090031879_0010 | 0 | 39 | 21 | 36 | 2025-03-17 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-12 | 2025-03-20 | 2025-04-04 |  |  | 2023-04-03 | 0 |  | 2025-02-27 |  | 2025-03-14 |  |  | 0 | 3 | 3 | 90031879 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | 180134076 | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020050 | Piston Nut 2153.1013.000 | 2025-02-27 | W |  | 0100 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90031879_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-27 | 20 |  | 2025-03-20 | 0 |  | 0 |  | 25SD2301 | MJ |  | AU1009 | 1000128789 | S001 |  |  | 5300004361 | 1300 |  | 5300015752 | 30 | 2 | EA | 1001 | AA02 | 2025-02-27 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-08-07 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0040 | 0010 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS |  | 10 | Planned delivery after Reqmt Date | 70020055 | SPLICE PLATE,NEMA3,HDG,EZYN3SH | 40 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 11.04.25 PO 4500048447 MM CPT | Supply for Order 600001365, Item 7 cannot be changed 90031897 item 10 already exists | Vendor PO raised | SP14 | Directs (Inventory) | 4 | AA02 | 5300013662 | 20 | CPT | 4 | 1000030929 | 7 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500048447 | 10 | 40 | EA | 2025-04-11 |  |  |  | 90031897 | 05 | Preparation | 0000084303 | 7 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2024-08-06 | POPO-4500048447_00010 | 0 | 21 | 0 | 15 | 2025-03-08 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-04 |  | 2025-03-14 |  |  | 2025-07-31 | 0 |  | 2025-02-27 |  | 2025-03-07 | 1K2301 |  | 0 | 5 | 6 | 90031897 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020055 | SPLICE PLATE,NEMA3,HDG,EZYN3SH | 2025-02-27 | W |  | 0040 | Electrical Tie In | INT | Electrical Tie In |  | Order Requires Replanning | 90031897_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-27 | 5 |  | 2025-03-14 | 7 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000083687 | S002 |  |  | 5300013662 | 20 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-02-27 |  | Order Requires Replanning |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84303 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SD2301 | Released | 2024-08-07 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0040 | 0020 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS |  | 10 | Planned delivery after Reqmt Date | 70020056 | SPLICE PLATE,HORIZON,NEMA3,HDG,EZYN3HSH | 20 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 11.04.25 PO 4500048447 MM CPT | Supply for Order 600001365, Item 8 cannot be changed 90031897 item 20 already exists | Vendor PO raised | SP14 | Directs (Inventory) | 4 | AA02 | 5300013662 | 30 | CPT | 4 | 1000030929 | 8 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500048447 | 20 | 20 | EA | 2025-04-11 |  |  |  | 90031897 | 05 | Preparation | 0000084303 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-08-06 | POPO-4500048447_00020 | 0 | 21 | 0 | 15 | 2025-03-08 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-04 |  | 2025-03-14 |  |  | 2025-07-31 | 0 |  | 2025-02-27 |  | 2025-03-07 | 1K2301 |  | 0 | 5 | 6 | 90031897 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020056 | SPLICE PLATE,HORIZON,NEMA3,HDG,EZYN3HSH | 2025-02-27 | W |  | 0040 | Electrical Tie In | INT | Electrical Tie In |  | Order Requires Replanning | 90031897_0020 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-27 | 5 |  | 2025-03-14 | 8 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000083687 | S002 |  |  | 5300013662 | 30 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-27 |  | Order Requires Replanning |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84303 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SD2301 | Released | 2024-08-07 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0040 | 0030 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS |  | 10 | Planned delivery after Reqmt Date | 70020057 | SPLICE BOLT,M10,HDG, NEMA, EZYSBH | 480 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 11.04.25 PO 4500048447 MM CPT | Supply for Order 600001365, Item 9 cannot be changed 90031897 item 30 already exists | Vendor PO raised | SP14 | Directs (Inventory) | 4 | AA02 | 5300013662 | 40 | CPT | 4 | 1000030929 | 9 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500048447 | 30 | 480 | EA | 2025-04-11 |  |  |  | 90031897 | 05 | Preparation | 0000084303 | 9 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 480 |  |  | Y | 1001 | 2024-08-06 | POPO-4500048447_00030 | 0 | 21 | 0 | 15 | 2025-03-08 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-04 |  | 2025-03-14 |  |  | 2025-07-31 | 0 |  | 2025-02-27 |  | 2025-03-07 | 1K2301 |  | 0 | 5 | 6 | 90031897 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020057 | SPLICE BOLT,M10,HDG, NEMA, EZYSBH | 2025-02-27 | W |  | 0040 | Electrical Tie In | INT | Electrical Tie In |  | Order Requires Replanning | 90031897_0030 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-27 | 5 |  | 2025-03-14 | 9 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000083687 | S002 |  |  | 5300013662 | 40 |  |  | 0 | 480 | EA | 2001 | AA02 | 2025-02-27 |  | Order Requires Replanning |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84303 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SD2301 | Released | 2024-08-07 | 2025-03-01 | 2025-02-27 | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0040 | 0040 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS |  | 10 | Planned delivery after Reqmt Date | 70020058 | SPLICE HEX NUT, M10,HDG,EZYCNH | 480 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 11.04.25 PO 4500048447 MM CPT | Supply for Order 600001365, Item 10 cannot be changed 90031897 item 40 already exists | Vendor PO raised | SP14 | Directs (Inventory) | 4 | AA02 | 5300013662 | 50 | CPT | 4 | 1000030929 | 10 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500048447 | 40 | 480 | EA | 2025-04-11 |  |  |  | 90031897 | 05 | Preparation | 0000084303 | 10 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 480 |  |  | Y | 1001 | 2024-08-06 | POPO-4500048447_00040 | 0 | 21 | 0 | 15 | 2025-03-08 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-04 |  | 2025-03-14 |  |  | 2025-07-31 | 0 |  | 2025-02-27 |  | 2025-03-07 | 1K2301 |  | 0 | 5 | 6 | 90031897 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020058 | SPLICE HEX NUT, M10,HDG,EZYCNH | 2025-02-27 | W |  | 0040 | Electrical Tie In | INT | Electrical Tie In |  | Order Requires Replanning | 90031897_0040 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-27 | 5 |  | 2025-03-14 | 10 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000083687 | S002 |  |  | 5300013662 | 50 |  |  | 0 | 480 | EA | 2001 | AA02 | 2025-02-27 |  | Order Requires Replanning |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84303 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SD2301 | Released | 2024-08-07 | 2025-03-01 | 2025-03-04 | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0040 | 0050 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS |  | 10 | Issue detected, please check message in derivation or orchestration log | 70020177 | SPLICE PLATE,VERT,NEMA3,HDG,EZYN3VSH | 20 | EA | 0 | 0 | 0 | 0 |  | 07.03 - PR 1000031112 | Supply for Order 600001365, Item 12 cannot be changed 90032178 item 10 already exists | PR approved; PO not issued | SP14 | Directs (Inventory) | 4 | AA02 | 5300013662 | 60 |  | 4 | 1000031112 | 12 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032178 | 05 | Preparation | 0000084303 | 12 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-08-06 | PRPO-1000031112_00012 | 0 | 26 | 0 | 15 | 2025-03-13 | 2025-02-24 | AA53 | 2025-03-01 |  |  | 2025-04-14 |  | 2025-03-19 |  |  | 2025-07-31 | 0 |  | 2025-03-04 |  | 2025-03-12 | 1K2301 |  | 0 | 5 | 6 | 90032178 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020177 | SPLICE PLATE,VERT,NEMA3,HDG,EZYN3VSH | 2025-03-04 | W |  | 0040 | Electrical Tie In | INT | Electrical Tie In |  | Order Requires Replanning | 90032178_0010 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-03-04 | 5 |  | 2025-03-19 | 12 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000083687 | S002 |  |  | 5300013662 | 60 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-03-04 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84303 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDKGP1 | Released | 2025-02-25 | 2025-04-26 | 2025-04-08 | 2025-04-26 | 2025-04-26 | NOMAINT | 600003962 | 0010 | 0060 | 600003962 | 25SD MINOR CAP Tooling & Equipment | AA53.1000 | KGP Non-Maintenance | AA01 | 20 | Issue detected, please check message in derivation or orchestration log | 70020189 | 734720 Optical Flat | 1 | EA | 0 | 0 | 0 | 0 |  | 07.03 - ETA 03.04.25 PO 4500048256 TRINKOR CPT | Supply for Order 600003962, Item 11 cannot be changed – 4500048256 already exists | Vendor PO raised | SP97 | Direct Multi-base | 14 | AA01 | 5300021774 | 30 | CPT | 14 | 1000031124 | 11 | 30001954 | TRINKOR PTY LTD | 4500048256 | 20 | 1 | EA | 2025-04-03 |  |  |  |  | 05 | Preparation | 0000294038 | 11 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-25 | POPO-4500048256_00020 | 0 | 0 | 0 | 0 | 2025-04-03 | 2025-04-18 | AA53 | 2025-04-26 |  |  | 2025-04-26 | 2025-04-06 | 2025-04-21 |  |  | 2025-12-31 | 0 |  | 2025-04-08 |  | 2025-04-21 |  |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-04-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020189 | 734720 Optical Flat | 2025-03-03 | W |  | 0010 | 25SD MINOR CAP Tooling & Equipment | INT | 25SD MINOR CAP Tooling & Equipment | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 104 | Proj & Brownfields | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-03-13 | 20 |  | 2025-04-06 | 0 |  | 0 |  | 25SDKGP1 | MJ |  | AU1009 | 1000287802 | S001 |  |  | 5300021763 | 50 |  | 5300021774 | 30 | 1 | EA | 1001 | AA02 | 2025-04-08 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | PJ | Project | 4 | Medium | RC00018003 | 2025-04-26 | 2025-04-26 | 2025-04-26 | Pre-costed/Object created/Settlement rule created/Released/Material shortage/Date set by external system | AM06 | Capital
| 25SDKGP1 | Released | 2025-02-25 | 2025-04-26 | 2025-04-08 | 2025-04-26 | 2025-04-26 | NOMAINT | 600003962 | 0010 | 0050 | 600003962 | 25SD MINOR CAP Tooling & Equipment | AA53.1000 | KGP Non-Maintenance | AA01 | 20 | Issue detected, please check message in derivation or orchestration log | 70020210 | 734718 Surface Roughness Tester | 1 | EA | 0 | 0 | 0 | 0 |  | 07.03 - ETA 03.04.25 PO 4500048256 TRINKOR CPT | Supply for Order 600003962, Item 9 cannot be changed – 4500048256 already exists | Vendor PO raised | SP97 | Direct Multi-base | 14 | AA01 | 5300021774 | 20 | CPT | 14 | 1000031029 | 9 | 30001954 | TRINKOR PTY LTD | 4500048256 | 10 | 1 | EA | 2025-04-03 |  |  |  |  | 05 | Preparation | 0000294038 | 9 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-25 | POPO-4500048256_00010 | 0 | 0 | 0 | 0 | 2025-04-03 | 2025-04-18 | AA53 | 2025-04-26 |  |  | 2025-04-26 | 2025-04-06 | 2025-04-21 |  |  | 2025-12-31 | 0 |  | 2025-04-08 |  | 2025-04-21 |  |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-04-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020210 | 734718 Surface Roughness Tester | 2025-03-03 | W |  | 0010 | 25SD MINOR CAP Tooling & Equipment | INT | 25SD MINOR CAP Tooling & Equipment | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 104 | Proj & Brownfields | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-03-13 | 20 |  | 2025-04-06 | 0 |  | 0 |  | 25SDKGP1 | MJ |  | AU1009 | 1000287802 | S001 |  |  | 5300021763 | 40 |  | 5300021774 | 20 | 1 | EA | 1001 | AA02 | 2025-04-08 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | PJ | Project | 4 | Medium | RC00018003 | 2025-04-26 | 2025-04-26 | 2025-04-26 | Pre-costed/Object created/Settlement rule created/Released/Material shortage/Date set by external system | AM06 | Capital
| 25SDKGP1 | Released | 2025-02-25 | 2025-04-26 | 2025-04-08 | 2025-04-26 | 2025-04-26 | NOMAINT | 600003962 | 0010 | 0070 | 600003962 | 25SD MINOR CAP Tooling & Equipment | AA53.1000 | KGP Non-Maintenance | AA01 | 20 | Issue detected, please check message in derivation or orchestration log | 70020222 | 734723 Flatness Gauge | 1 | EA | 0 | 0 | 0 | 0 |  | 07.03 - ETA 03.04.25 PO 4500048256 TRINKOR CPT | Supply for Order 600003962, Item 16 cannot be changed – 4500048256 already exists | Vendor PO raised | SP97 | Direct Multi-base | 14 | AA01 | 5300021774 | 60 | CPT | 14 | 1000031127 | 16 | 30001954 | TRINKOR PTY LTD | 4500048256 | 30 | 1 | EA | 2025-04-03 |  |  |  |  | 05 | Preparation | 0000294038 | 16 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-25 | POPO-4500048256_00030 | 0 | 0 | 0 | 0 | 2025-04-03 | 2025-04-18 | AA53 | 2025-04-26 |  |  | 2025-04-26 | 2025-04-06 | 2025-04-21 |  |  | 2025-12-31 | 0 |  | 2025-04-08 |  | 2025-04-21 |  |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-04-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020222 | 734723 Flatness Gauge | 2025-03-03 | W |  | 0010 | 25SD MINOR CAP Tooling & Equipment | INT | 25SD MINOR CAP Tooling & Equipment | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 104 | Proj & Brownfields | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-03-13 | 20 |  | 2025-04-06 | 0 |  | 0 |  | 25SDKGP1 | MJ |  | AU1009 | 1000287802 | S001 |  |  | 5300021763 | 80 |  | 5300021774 | 60 | 1 | EA | 1001 | AA02 | 2025-04-08 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | PJ | Project | 4 | Medium | RC00018003 | 2025-04-26 | 2025-04-26 | 2025-04-26 | Pre-costed/Object created/Settlement rule created/Released/Material shortage/Date set by external system | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2025-02-08 | 2025-03-04 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0450 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A |  | 10 | Issue detected, please check message in derivation or orchestration log | 70020226 | CABLE LABEL,STAINLESS STEEL 9.5MMH 89MML | 40 | EA | 0 | 0 | 0 | 0 |  | 07.03 - PR 1000031096 | Supply for Order 600001815, Item 56 cannot be changed 90032177 item 10 already exists | PR approved; PO not issued | SP14 | Directs (Inventory) | 14 | AA02 | 5300007843 | 390 |  | 14 | 1000031096 | 56 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032177 | 07 | Execution | 0000084731 | 56 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2024-03-13 | PRPO-1000031096_00056 | 0 | 57 | 0 | 25 | 2025-03-23 | 2025-02-03 | AA53 | 2025-02-08 |  |  | 2025-05-25 |  | 2025-03-29 |  |  | 2024-08-30 | 0 |  | 2025-03-04 |  | 2025-03-12 | SCOTT KINLOC |  | 0 | 5 | 6 | 90032177 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020226 | CABLE LABEL,STAINLESS STEEL 9.5MMH 89MML | 2025-03-04 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90032177_0010 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-03-04 | 10 |  | 2025-03-29 | 56 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 |  |  | 5300007843 | 390 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-03-05 | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0470 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | PR due for release | 70020236 | VALVE, GLOBE, 1" CL300, RED BORE | 1 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031264 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 120 | AA01 | 5300017305 | 20 |  | 120 | 1000031264 | 46 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032247 | 05 | Preparation | 0000084596 | 46 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-04 | PRPO-1000031264_00046 | 0 | 160 | 133 | 148 | 2025-07-10 | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-08-20 | 2025-07-16 | 2025-07-31 |  |  | 2025-09-29 | 0 |  | 2025-03-05 |  | 2025-03-20 | Critical |  | 0 | 6 | 6 | 90032247 | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020236 | VALVE, GLOBE, 1" CL300, RED BORE |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify |  |  | 90032247_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-03-05 | 20 |  | 2025-07-16 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000084000 | S001 |  |  | 5300004588 | 40 |  | 5300017305 | 20 | 1 | EA | 1001 | AA02 | 2025-03-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDKGP1 | Released | 2025-02-25 | 2025-04-26 | 2025-04-08 | 2025-04-26 | 2025-04-26 | NOMAINT | 600003962 | 0010 | 0080 | 600003962 | 25SD MINOR CAP Tooling & Equipment | AA53.1000 | KGP Non-Maintenance | AA01 | 20 | PR due for release | 70020251 | 8431063371 LTV39-2 R140-13 Nut Runner | 2 | EA | 0 | 0 | 0 | 0 |  | 07.03 - PR 1000031145 |  | PR not approved | SP97 | Direct Multi-base | 35 | AA01 | 5300021774 | 70 |  | 35 | 1000031145 | 18 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294038 | 18 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-25 | PRPO-1000031145_00018 | 0 | 10 | 10 | 10 | 2025-04-15 | 2025-04-18 | AA53 | 2025-04-26 |  |  | 2025-05-06 | 2025-04-18 | 2025-05-01 |  |  | 2025-12-31 | 0 |  | 2025-04-08 |  | 2025-04-21 |  |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-04-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020251 | 8431063371 LTV39-2 R140-13 Nut Runner |  |  |  | 0010 | 25SD MINOR CAP Tooling & Equipment | INT | 25SD MINOR CAP Tooling & Equipment | [8 empty] | 03 | In Release |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-03-04 | 20 |  | 2025-04-18 | 0 |  | 0 |  | 25SDKGP1 | MJ |  | AU1009 | 1000287802 | S001 |  |  | 5300021763 | 90 |  | 5300021774 | 70 | 2 | EA | 1001 | AA02 | 2025-04-08 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | PJ | Project | 4 | Medium | RC00018003 | 2025-04-26 | 2025-04-26 | 2025-04-26 | Pre-costed/Object created/Settlement rule created/Released/Material shortage/Date set by external system | AM06 | Capital
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0400 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020317 | Cut Key for 410, 406, S31 Safety Padlock | 9 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 180 |  | 28 | 1000031523 | 113 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 113 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00113 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020317 | Cut Key for 410, 406, S31 Safety Padlock |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1030 |  | 5300021228 | 180 | 9 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0390 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020317 | Cut Key for 410, 406, S31 Safety Padlock | 3 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 170 |  | 28 | 1000031523 | 112 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 112 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00112 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020317 | Cut Key for 410, 406, S31 Safety Padlock |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1020 |  | 5300021228 | 170 | 3 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0460 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020332 | Masterlock 406 Replacement | 64 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 240 |  | 28 | 1000031523 | 119 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 119 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 64 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00119 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020332 | Masterlock 406 Replacement |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1090 |  | 5300021228 | 240 | 64 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0420 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020332 | Masterlock 406 Replacement | 56 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 200 |  | 28 | 1000031523 | 115 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 115 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 56 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00115 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020332 | Masterlock 406 Replacement |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1050 |  | 5300021228 | 200 | 56 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0450 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020332 | Masterlock 406 Replacement | 75 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 230 |  | 28 | 1000031523 | 118 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 118 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 75 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00118 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020332 | Masterlock 406 Replacement |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1080 |  | 5300021228 | 230 | 75 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0410 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020332 | Masterlock 406 Replacement | 35 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 190 |  | 28 | 1000031523 | 114 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 114 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 35 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00114 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020332 | Masterlock 406 Replacement |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1040 |  | 5300021228 | 190 | 35 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0470 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020332 | Masterlock 406 Replacement | 28 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 250 |  | 28 | 1000031523 | 120 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 120 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 28 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00120 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020332 | Masterlock 406 Replacement |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1100 |  | 5300021228 | 250 | 28 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0430 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020332 | Masterlock 406 Replacement | 55 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 210 |  | 28 | 1000031523 | 116 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 116 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 55 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00116 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020332 | Masterlock 406 Replacement |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1060 |  | 5300021228 | 210 | 55 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0440 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020332 | Masterlock 406 Replacement | 175 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 220 |  | 28 | 1000031523 | 117 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 117 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 175 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00117 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020332 | Masterlock 406 Replacement |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1070 |  | 5300021228 | 220 | 175 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0480 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020333 | Masterlock 406 Replacement - with key | 3 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 260 |  | 28 | 1000031523 | 121 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 121 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00121 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020333 | Masterlock 406 Replacement - with key |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1110 |  | 5300021228 | 260 | 3 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0490 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020333 | Masterlock 406 Replacement - with key | 45 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 270 |  | 28 | 1000031523 | 122 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 122 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 45 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00122 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020333 | Masterlock 406 Replacement - with key |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1120 |  | 5300021228 | 270 | 45 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0500 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020333 | Masterlock 406 Replacement - with key | 79 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 280 |  | 28 | 1000031523 | 123 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 123 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 79 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00123 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020333 | Masterlock 406 Replacement - with key |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1130 |  | 5300021228 | 280 | 79 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDGT9 | Released | 2024-10-28 | 2025-03-01 | 2025-03-10 | 2025-03-01 | 2025-03-01 | ROTAT | 100083725 | 0010 | 0070 | 100083725 | GT4009K1A - Vent Fan DE Bearing | AA53.GT4009K1A | FAN,TURBINE ACOUSTIC ENCL VENT,GT4009 | AA01 | 20 | PR due for release | 70020341 | Bearing Assembly SNL520TGBFSRB | 2 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031469 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 14 | AA01 | 5300022281 | 10 |  | 14 | 1000031469 | 8 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032459 | 05 | Preparation | 0000260566 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-03-08 | PRPO-1000031469_00008 | 0 | 59 | 27 | 44 | 2025-03-31 | 2025-03-02 | AA53 | 2025-03-01 |  |  | 2025-05-14 | 2025-04-06 | 2025-04-21 |  |  | 2025-10-31 | 0 |  | 2025-03-10 |  | 2025-03-25 |  |  | 0 | 6 | 6 | 90032459 | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020341 | Bearing Assembly SNL520TGBFSRB |  |  |  | 0010 | GT4009K1A - Vent Fan DE Bearing | INT | GT4009K1A - Vent Fan DE Bearing |  |  | 90032459_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 20 |  | 2025-04-06 | 0 |  | 0 |  | 25SDGT9 | MJ |  | AU1009 | 1000256336 | S001 |  |  | 5300016986 | 60 |  | 5300022281 | 10 | 2 | EA | 1001 | AA02 | 2025-03-10 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-09-02 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0440 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020332 | Masterlock 406 Replacement | 175 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 220 |  | 28 | 1000031523 | 117 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 117 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 175 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00117 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020332 | Masterlock 406 Replacement |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1070 |  | 5300021228 | 220 | 175 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0490 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020333 | Masterlock 406 Replacement - with key | 45 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 270 |  | 28 | 1000031523 | 122 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 122 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 45 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00122 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020333 | Masterlock 406 Replacement - with key |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1120 |  | 5300021228 | 270 | 45 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-13 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0060 | 0500 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | PR due for release | 70020333 | Masterlock 406 Replacement - with key | 79 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 1000031523 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 28 | AA01 | 5300021228 | 280 |  | 28 | 1000031523 | 123 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000294187 | 123 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 79 |  |  | Y | 1001 | 2025-02-13 | PRPO-1000031523_00123 | 0 | 35 | 35 | 35 | 2025-04-14 | 2025-03-24 | AA53 | 2025-04-01 |  |  | 2025-05-06 | 2025-04-17 | 2025-05-01 |  |  |  | 0 |  | 2025-03-13 |  | 2025-03-27 | TA OPS/BAILS |  | 0 | 3 | 3 |  | 0 | 0 |  | 1 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-13 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 70020333 | Masterlock 406 Replacement - with key |  |  |  | 0060 | 2025 - Ops TA Consumables | NCNF | 2025 - Ops TA Consumables | [8 empty] | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-03-10 | 99 |  | 2025-04-17 | 0 |  | 0 |  | 25SDENA1 | MJ |  | AU1009 | 1000287811 | S001 | 30 | 30 | 5300021227 | 1130 |  | 5300021228 | 280 | 79 | EA | 1001 | AA02 | 2025-03-13 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution