## SAPUI5 Export
Release id (" "=rel., X=not yet,1=never) | MO Revision | MO Status | MO Actual Release date | Requirement date (MO component) | Material Staging date (STO) | MO basic Start date | MO basic Finish date | MO Main work centre | MO number | Oper/Act number of Reservation | BOM item number | MO Description | Description | Functional location | Description | Procurement plant | Req Priority for Material/Component | Alert / Exception | Material / Component | Material Description | Requirement quantity | Requirement UOM | Stock on-hand @ Base | Stock In-Transit into Remote | Stock on-hand @ Remote | HU Quantity | UoM of HU | Expediting Note / User Comment | Message log(Orchestration / Derivation) | Supply status | Supply Process | Supply Process (Desc.) | Planned Deliver Time (in days) (PR) | Supplying Plant (STO) | Current STO | Current STO Item | Incoterms | Planned Delivery Time (in days) (STO) | Purchase Requisition | Purchase Requisition Item | Vendor | Name of Supplier | Vendor PO | Vendor PO item | PO qty | Requirement UOM | Delivery date (PO) | Batch/Valuation type(from MO component) | Inbound Delivery (PO) | Latest Inbound Delivery (STO) | Latest Outbound Delivery STO | Process Phase | Short Description | Reservation | Reservation Item | Reservation item deletion indicator | UoM of HU | Nested HU Lvl 2 | Nested HU Lvl 3 | Top HU | Shipping Type | Voyage type | Voyage status | Container-ID | Linked Work-pack/HU | Workpack bin | Unloading Point | Incompletion indic. (Y/N) | Return STO | Return STO Item | Return STO Qty | Return STO UOM | Withdrawn quantity | Remaining quanity | Arrival (actual) | Arrival (plan) | Campaign (Y/N) | Company Code (STO) | Creation Date (STO) | Current document | Current STO Item has deletion code? | Delay @ Demand plant | Delay @ Procument plant | Delay @ Supply plant | Delivery date (PR) | Delivery date (STO) | Demand Plant | Early start date (MO) | Equipment | Description | ETA @ Demand plant | ETA @ Procument plant | ETA @ Supply plant | EWM task for GI (STO) | EWM Warehouse for GI (STO) | Final Due Date | GI qty (OBD for STO) | Good Receipt (PO) | Goods Issue date (STO) | Goods Issue Document (STO) | Goods Receipt End date (STO) | Goods Recipient | GR IBD Document (STO) | GR processing time | GR Processing time Demand plant (STO) | GR Processing time Supply plant (PR) | Ref Latest Outbound Delivery (STO) | GR qty (IBD for STO) | GR qty (PO) | Inbound Delivery (STO) | Internal alert code | Is PR Item Deleted? | Is Reservation Item Deleted(hard)? | isMessageThresholdBreached | Item category (BOM) | Latest GI (STO) | Latest GI STO Year | Latest GR (PO) | Latest GR IBD (STO) | Latest GR IBD Year(STO) | Latest GR PO Year | Latest IBD (PO) | Loading Date (STO) | Maint. Operation Exec. Stage Code | Maintenance Planning Plant | Name 1 | Maintenance Plant | Plant Name | Maintenance Storage Location | Material / Component description | Material Description | Message Text Date | Message Type | Oper. Phase Status | Operation / Activity | Operation description | Operation Control key | Operation description | Operation System Condition | Order Phase Status | Outbound Delivery (STO) | Person responsible | Picking bin | Plant Section | PO item deletion indic | Position | PR Processing State | Short Description | PR Release Indicator | Priority Type | Priority Type Text | Process Subphase | Subphase Description | Profile Status | Project stock | Purchasing Group | Purchasing Grp. Name | Purchasing group (STO) | Purchasing Grp. Name | Purchasing Organisation (STO) | Purchasing Processing time(PR) | Receiving Plant (STO) | Release date (PR) | Req Urgency for Material/Component | Request for Quotation | Requirements date (PR) | Reservation Item (reverse link) | Reservation Special Stock Ind. | Responsible Buyer (for PO) | Return doc (MvT 262) | Revision | Revision Type | Voyage-id | Route (STO) | Routing number (of MO Operation) | Shipping Point (STO) | Status of Material (Demand Plant) | Status of Material (Supplying Plant) | STO (Supplying) - 1st STO | STO (Supplying) - 1st STO Item | STO Committed date (STO) | STO for SP97 (2nd STO) | STO for SP97 2ndS STO Item | STO quantity (STO) | STO quantity UoM (STO) | Storage Location (STO) based on MO | Supplying Plant | Transportation Planning date (STO) | User Responsible | User-status | Vehicle departure date | Vendor PO Pur Org | Warehouse | MO Actual Finish date | MO Actual Start date | MO Company Code | Company Name | MO Controlling Area | MO created by | MO creation date | MO from PR (reverse link) | MO item number | Stock on-hand @ Procurement Plant | MO Overall Status | Warehouse Number(STO) | MO overall status code | MO Planner Group | Planner Group Name | MO Priority | Priority Text | MO Responsible Cost Center | MO Scheduled Finish date | MO Scheduled Release date | MO Scheduled Start date | MO System Status | MO type | Order Type Name | MO WBS element
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039735 | 0010 | 0010 | 100039735 | Replace Flange Bolting 1K1820V7A/B | AA53.1K1820V7A | VE,DRAIN POT & MIST ELIMIN SEAL OIL |  | 30 | No issue identified |  |  | 4 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10060916 CONSUMED PRE S4H WO 2100350441 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000138236 | 1 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2023-08-11 | 0 |  |  |  |  | 2100350441 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Replace 1K1820V7A - Gasket & Studs | INT | Replace 1K1820V7A - Gasket & Studs | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137645 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039735 | 0010 | 0020 | 100039735 | Replace Flange Bolting 1K1820V7A/B | AA53.1K1820V7A | VE,DRAIN POT & MIST ELIMIN SEAL OIL |  | 30 | No issue identified |  |  | 12 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10058199 CONSUMED PRE S4H WO 2100350441 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000138236 | 2 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2023-08-11 | 0 |  |  |  |  | 2100350441 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Replace 1K1820V7A - Gasket & Studs | INT | Replace 1K1820V7A - Gasket & Studs | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137645 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039735 | 0010 | 0030 | 100039735 | Replace Flange Bolting 1K1820V7A/B | AA53.1K1820V7A | VE,DRAIN POT & MIST ELIMIN SEAL OIL |  | 30 | No issue identified |  |  | 12 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10058192 CONSUMED PRE S4H WO 2100350441 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000138236 | 3 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2023-08-11 | 0 |  |  |  |  | 2100350441 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Replace 1K1820V7A - Gasket & Studs | INT | Replace 1K1820V7A - Gasket & Studs | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137645 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100040410 | 0030 | 0010 | 100040410 | MV-RE 1.5" 300# 408BAV0027 | AA53.GT4008 | TURB,GAS FOR G4008 |  | 255 | No issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10605598 BOX ID GS4550527 PO W451780583 BLOCKED STOCK |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138962 | 4 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2024-06-09 | 0 |  |  |  |  | GT-4008 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0030 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 |  |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000138312 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDTOT1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 100041904 | 0010 | 0020 | 100041904 | MOC-120096 Positioner Replace110PV452 | AA53.110PV452POS | POS,VALVE,PRESS 1PRS RUNDOWN 5 |  | 10 | No issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 04.11 - Gland don’t need Staged KGP Location ST3C03C13A (DWR 71027295) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140388 | 2 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-05-07 | 0 |  |  |  |  | 110PV452POS |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | TT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDTOT1 | MJ |  |  | 1000139759 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
1 | 25SDLN4 | Released | 2024-01-01 | 2025-03-01 |  | 2025-05-08 | 2025-05-08 | INLEC | 100042125 | 0001 | 0030 | 100042125 | OPSD2-FL-S24G2 - MOC 95759 INSUM Gateway | AA53.S24G2 | SWBD,415V EMERG SUPPLY SUB 2 |  | 10 | WO item has not been released yet |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000140617 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 | [7 empty] | 2024-07-30 | 0 |  |  |  |  | C.BROOKS |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0001 | ABB-Gateway Configuration/RCA M102 Relay | ESRV | ABB-Gateway Configuration/RCA M102 Relay | 0 |  |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000140027 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 100042344 | 0010 | 0010 | 100042344 | MOC-118617 Inlet Fan Replace G4008S2KM1 | AA53.G4008S2KM1 | MOTOR,GEN AIRINLET FILTHSE SCAVFAN,G4008 |  | 20 | No issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | WO: 2100329861 CONSUMED MN 10225813 MOTOR,AC;415V,1380RPM,0.55KW,EX |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140796 | 1 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2021-10-05 | 0 |  |  |  |  | IncorrectMTR |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Remove & Replace Motor | INT | Remove & Replace Motor | 5 |  |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000140226 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-04-29 | ROTAT | 100043283 | 0010 | 0010 | 100043283 | Repair 1K2420 L/O crossover valve | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 30 | No issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | WO: 2100323922 CONSUMED MN 10007125 O-RING;VIT,THOMASSEN 5141430X4 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141784 | 1 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2022-12-15 | 0 |  |  |  |  | LO XOver Vlv |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Repair L/O cooler xover valve | INT | Repair L/O cooler xover valve | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000141173 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-04-29 | ROTAT | 100043283 | 0010 | 0020 | 100043283 | Repair 1K2420 L/O crossover valve | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 30 | No issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | WO: 2100323922 CONSUMED MN 10060176 GASKET;CNAF,250 X 310 X 1.5MM,R |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141784 | 2 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2022-12-15 | 0 |  |  |  |  | LO XOver Vlv |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Repair L/O cooler xover valve | INT | Repair L/O cooler xover valve | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000141173 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100045781 | 0010 | 0010 | 100045781 | Replace Flange Studs - 1E180769 | AA53.1E1807069 | EXCH,HEAT DEBUTANISER CONDEN FRAC1 |  | 30 | No issue identified |  |  | 8 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10058486 CONSUMED PRE S4H |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000144253 | 1 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2019-11-03 | 0 |  |  |  |  | 2E1807061 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Hot bolt flange using clamps (historic) | INT | Hot bolt flange using clamps (historic) | 0 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000143683 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100045781 | 0010 | 0030 | 100045781 | Replace Flange Studs - 1E180769 | AA53.1E1807069 | EXCH,HEAT DEBUTANISER CONDEN FRAC1 |  | 30 | No issue identified |  |  | 4 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10059000 CONSUMED PRE S4H |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000144253 | 3 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2019-11-03 | 0 |  |  |  |  | 2E1807061 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Hot bolt flange using clamps (historic) | INT | Hot bolt flange using clamps (historic) | 0 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000143683 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100045781 | 0010 | 0020 | 100045781 | Replace Flange Studs - 1E180769 | AA53.1E1807069 | EXCH,HEAT DEBUTANISER CONDEN FRAC1 |  | 30 | No issue identified |  |  | 8 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10433043 CONSUMED PRE S4H |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000144253 | 2 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2019-11-03 | 0 |  |  |  |  | 2E1807061 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Hot bolt flange using clamps (historic) | INT | Hot bolt flange using clamps (historic) | 0 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000143683 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-05-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100047394 | 0030 | 0020 | 100047394 | CV-OH 1" 600# 124PCV54 | AA53.124PCV54 | VALVE,CONT SEAL OIL BACK PRESS 1K2420 |  | 20 | No issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | WO: 2100232650 DELIVERY CREATED at KGP Facility MN 10303469 GASKET;SWCI,25MM,CL |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000145926 | 1 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2018-10-31 | 0 |  |  |  |  | 124PCV54 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0030 | Remove Valve 124PCV54 & Fit Blinds | INT | Remove Valve 124PCV54 & Fit Blinds | 5 |  |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000145296 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  | 2024-05-23 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-05-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100047394 | 0030 | 0030 | 100047394 | CV-OH 1" 600# 124PCV54 | AA53.124PCV54 | VALVE,CONT SEAL OIL BACK PRESS 1K2420 |  | 20 | No issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | WO: 2100232650 DELIVERY CREATED at KGP Facility MN 10048539 FLANGE,BLIND;25MM,C |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000145926 | 2 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2018-10-31 | 0 |  |  |  |  | 124PCV54 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0030 | Remove Valve 124PCV54 & Fit Blinds | INT | Remove Valve 124PCV54 & Fit Blinds | 5 |  |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000145296 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  | 2024-05-23 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-05-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100047394 | 0050 | 0030 | 100047394 | CV-OH 1" 600# 124PCV54 | AA53.124PCV54 | VALVE,CONT SEAL OIL BACK PRESS 1K2420 |  | 20 | No issue identified |  |  | 8 | EA | 0 | 0 | 0 | 0 |  | WO: 2100232650 DELIVERY CREATED at KGP Facility MN 10218612 STUDBOLT;0.625"X100 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000145926 | 4 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2018-10-31 | 0 |  |  |  |  | 124PCV54 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0050 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve | 5 |  |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000145296 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  | 2024-05-23 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-05-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100047394 | 0050 | 0020 | 100047394 | CV-OH 1" 600# 124PCV54 | AA53.124PCV54 | VALVE,CONT SEAL OIL BACK PRESS 1K2420 |  | 20 | No issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | WO: 2100232650 DELIVERY CREATED at KGP Facility MN 10303469 GASKET;SWCI,25MM,CL |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000145926 | 3 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2018-10-31 | 0 |  |  |  |  | 124PCV54 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0050 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve | 5 |  |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000145296 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  | 2024-05-23 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | ROTAT | 200081172 | 0020 | 0010 | 200081172 | 4Y CO2 System Replace Hoses (3) 4KT1410 | AA53.HOSE40645 | HOSE,CO2 4KT1410V5 TO 414RV409 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | WO: 2200682034 CONSUMED MN 10577720 HOSE ASY;CO2;25MM,0.39M,7000KPA |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000115761 | 1 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 | [7 empty] | 2025-10-31 | 0 |  |  |  |  | 2200682034 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0020 | CO2 System Replace Hoses | INT | CO2 System Replace Hoses | 5 | Ready for Release |  |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000115091 |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | ROTAT | 200081173 | 0020 | 0020 | 200081173 | 4Y CO2 System Replace Hoses (3) 4KT1430 | AA53.HOSE40648 | HOSE,CO2 4KT1430V5 TO 414RV509 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | WO: 2200682037 CONSUMED MN 10577722 HOSE ASY;CO2;25MM,0.27M,7000KPA |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000115762 | 1 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 | [7 empty] | 2025-10-31 | 0 |  |  |  |  | 2200682037 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0020 | CO2 System Replace Hoses | INT | CO2 System Replace Hoses | 5 | Ready for Release |  |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000115092 |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0050 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL |  | 10 | No issue identified |  |  | 20 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10609400 BIN LOC SW3R15F01B @ AA02 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000128060 | 5 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2024-06-03 | 0 |  |  |  |  | 1K1820 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000127469 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0040 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL |  | 10 | No issue identified |  |  | 30 | M | 0 | 0 | 0 | 0 |  | 14.10 - MN 10609359 BIN LOC SW3R15F01B @ AA02 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | M | [5 empty] | 05 | Preparation | 0000128060 | 4 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2024-06-03 | 0 |  |  |  |  | 1K1820 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000127469 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0680 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE |  | 20 | No issue identified |  |  | 20 | EA | 0 | 0 | 0 | 0 |  | 14.10 - MN 10058984 CONSUMED PRE S4H |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129754 | 75 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-06-05 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000129164 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 600001503 | 0020 | 0010 | 600001503 | MOC-117240 Replace Gas Det (6) 1KT1430 | AA53.160QE561A | DET,GAS IR,1KT1430 TURBINE AIR INLET |  | 10 | No issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | WO: 2600015025 DELIVERY STAGED SW3R12A02A MN 70000030 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084425 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-04-27 | 0 |  |  |  |  | 1KT1430 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000083775 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 600001504 | 0020 | 0010 | 600001504 | MOC-117240 Replace Gas Det (6) 1KT1440 | AA53.160QE591A | DET,GAS IR,1KT1440 TURBINE AIR INLET |  | 10 | No issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | WO: 2600015026 DELIVERY STAGED SW3R12A02B MN 70000030 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084426 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-04-27 | 0 |  |  |  |  | 1KT1440 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000083776 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 600001505 | 0020 | 0010 | 600001505 | MOC-117240 Replace Gas Det (6) 1KT1450 | AA53.160QE621A | DET,GAS IR,1KT1450 TURBINE AIR INLET |  | 10 | No issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | WO: 2600015027 DELIVERY STAGED SW3R12A01B MN 70000030 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084427 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-04-27 | 0 |  |  |  |  | 1KT1450 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000083777 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM06 | Capital
| 25SDFR1 | Released | 2024-01-02 | 2025-05-16 |  | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0035 | 0060 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 |  | 10 | No Issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | WO: 2600014841 CONSUMED MN 10529603 GLAND,CABLE;00-20SS,E1EXUQS,CCG 057200 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084710 | 9 | 0 | [8 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-31 | 0 |  |  |  |  | 118UCV112 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | T |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | [6 empty] | 0035 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000084094 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1550 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10005921 | SCREW,CAP HD,1"X 70MM,ASTM A193-B16,8 UN | 6 | EA | 6 | 0 | 0 | 6 | EA | 31.01 - SOH @ AA01 | Supply for Order 200091513, Item 513 cannot be changed 90028419 item 3690 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 513 | 0 | EA | 102000000030488 | 101000000141636 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3690 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10005921 | SCREW,CAP HD,1"X 70MM,ASTM A193-B16,8 UN | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_3690 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 513 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3720 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0470 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10006039 | SCREW,CAP HD,1.00" X 57MM,SNB16,8UNC | 6 | EA | 8 | 0 | 0 | 4 | EA | 20.02 - SOH @ AA02 | Supply for Order 200091513, Item 465 cannot be changed 90028419 item 3270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 465 | 0 | EA | 102000000030386 | 102000000034124 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006039 | SCREW,CAP HD,1.00" X 57MM,SNB16,8UNC | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3270 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 465 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3300 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0470 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10006039 | SCREW,CAP HD,1.00" X 57MM,SNB16,8UNC | 6 | EA | 8 | 0 | 0 | 2 | EA | 20.02 - SOH @ AA02 | Supply for Order 200091513, Item 465 cannot be changed 90028419 item 3270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 465 | 0 | EA | 102000000030386 | 102000000030865 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006039 | SCREW,CAP HD,1.00" X 57MM,SNB16,8UNC | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3270 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 465 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3300 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1960 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10006043 | BOLT,HEX;0.375"X25MM,ALLOY ST,A193 | 40 | EA | 18 | 0 | 0 | 18 | EA | 10.12 - ETA 23.03.25 PO 4500031502 MOT30655 GS4945892 62.8kg 72x57x74cm | Supply for Order 200091513, Item 517 cannot be changed 90028419 item 3720 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 517 | 0 | EA | 102000000030389 | 102000000030830 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3720 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006043 | BOLT,HEX;0.375"X25MM,ALLOY ST,A193 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_3720 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 517 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3750 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1670 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10006128 | BOLT,HEX;0.50"X19MM,ALLOY ST,GR 8 | 32 | EA | 94 | 0 | 0 | 30 | EA | 02.03 - SOH @ AA02 | Supply for Order 200091513, Item 508 cannot be changed 90028419 item 3640 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 508 | 0 | EA | 102000000030498 | 102000000030241 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3640 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006128 | BOLT,HEX;0.50"X19MM,ALLOY ST,GR 8 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_3640 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 508 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3670 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 3140 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10006139 | SCREW,CAP;HD,0.375"X44MM,16UNC,ALLOY ST | 10 | EA | 32 | 0 | 0 | 10 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 542 cannot be changed 90028419 item 3930 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3960 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 542 | 0 | EA | 102000000030493 | 102000000030236 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3930 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006139 | SCREW,CAP;HD,0.375"X44MM,16UNC,ALLOY ST | 2024-07-21 | W |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  | 90028419_3930 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 542 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3960 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3210 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10006139 | SCREW,CAP;HD,0.375"X44MM,16UNC,ALLOY ST | 10 | EA | 32 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 623 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | INDUCTORHUB |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006139 | SCREW,CAP;HD,0.375"X44MM,16UNC,ALLOY ST |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 2370 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10006144 | PIN,SEAL;4.75X82.6MM,NP SMO44906 | 80 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 361 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006144 | PIN,SEAL;4.75X82.6MM,NP SMO44906 |  |  |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0200 | 2410 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10006144 | PIN,SEAL;4.75X82.6MM,NP SMO44906 | 80 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 366 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006144 | PIN,SEAL;4.75X82.6MM,NP SMO44906 |  |  |  | 0200 | LP ROTOR ASSEMBLY | INT | LP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0200 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10006183 | PIN,GUIDE VANE,INL;NP FJV06015 | 2 | EA | 5 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 453 cannot be changed 90028419 item 3150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 453 | 0 | EA | 102000000030489 | 102000000030168 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006183 | PIN,GUIDE VANE,INL;NP FJV06015 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_3150 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 453 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3180 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-11-28 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | INLEC | 100086242 | 0020 | 0010 | 100086242 | MOC-***** HYD Dump Vlve Repl (2) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | WO item has not been released yet | 10006192 | VALVE,SLND;EXD,NP 381A701434 | 2 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000272294 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  |  |  |  | 1KT2420 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006192 | VALVE,SLND;EXD,NP 381A701434 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000267031 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2980 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10006192 | VALVE,SLND;EXD,NP 381A701434 | 1 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 576 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 20HD |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006192 | VALVE,SLND;EXD,NP 381A701434 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10006205 | BEARING,PIGNONE MS3002,NO 1,LINER,STD | 1 | EA | 0 | 0 | 1 | 1 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 651 cannot be changed 9027132 item 4370 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124220 | 9027132 | 05 | Preparation | 0000129822 | 651 | 0 | EA |  |  | 102000000030129 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000396399_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056767 | 1020 | 2025-07-03 | 1 |  | 2025-02-11 | 4900234166_2025_0001 | 2025-03-01 |  | 5000396399_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180124220 | 2 | 0 | 0 | X | L | 4900234166 | 2025 |  | 5000396399 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006205 | BEARING,PIGNONE MS3002,NO 1,LINER,STD | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 9027132_4370 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 651 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4400 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1720 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10006214 | BEARING,NP MS3002,NO 4,TILT,STD | 1 | ASY | 0 | 0 | 1 | 1 | ASY | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 654 cannot be changed 9027131 item 4400 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4430 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180124208 | 9027131 | 05 | Preparation | 0000129822 | 654 | 0 | ASY |  |  | 102000000031289 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000396434_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056766 | 1020 | 2025-07-03 | 1 |  | 2025-02-11 | 4900234113_2025_0001 | 2025-03-01 |  | 5000396434_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180124208 | 2 | 0 | 0 | X | L | 4900234113 | 2025 |  | 5000396434 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10006214 | BEARING,NP MS3002,NO 4,TILT,STD | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 9027131_4400 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 654 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4430 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-01 | INLEC | 100086263 | 0020 | 0020 | 100086263 | SRV, GCV, 2S Nozzle Overhaul 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10007074 | VALVE,SERVO;THOMASSEN 3032139101 | 1 | EA | 4 | 1 | 0 | 1 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086263, Item 2 cannot be changed 90025090 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017085 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124188 | 90025090 | 05 | Preparation | 0000272422 | 2 | 0 | EA | 102000000032140 | 102000000029234 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-30 | IDST-0180124188 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 1 |  | 2025-02-11 | 4900234047_2025_0003 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025090 | 0 | 0 | 180124188 | 2 | 0 | 0 | X | L | 4900234047 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007074 | VALVE,SERVO;THOMASSEN 3032139101 | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025090_0020 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267122 | S002 |  | 30 | 5300017085 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007074 | VALVE,SERVO;THOMASSEN 3032139101 | 1 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 583 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 2SNmoog |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007074 | VALVE,SERVO;THOMASSEN 3032139101 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0800 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007075 | SEAL,NOZ;THOMASSEN 3045103801 | 12 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 93 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007075 | SEAL,NOZ;THOMASSEN 3045103801 |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2350 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007079 | NUT/BOLT SET;0.375",GE IRG369470261 | 1 | SET | 0 | 0 | 0 | 0 |  | 02.10 - ETA 20.05.25 PO 4500028567 ex BH FCA | Supply for Order 200091513, Item 347 cannot be changed 90028419 item 2680 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2710 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 347 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2680 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007079 | NUT/BOLT SET;0.375",GE IRG369470261 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2680 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 347 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2710 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0710 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007083 | CLAMP,BLK;THOMASSEN 3056104601 | 6 | EA | 18 | 0 | 0 | 5 | EA | 02.03 - SOH @ AA02 | Supply for Order 200091513, Item 79 cannot be changed 90028419 item 620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 79 | 0 | EA | 102000000030502 | 102000000030066 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007083 | CLAMP,BLK;THOMASSEN 3056104601 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0620 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 79 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 630 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2500 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007083 | CLAMP,BLK;THOMASSEN 3056104601 | 1 | EA | 18 | 0 | 0 | 0 |  | 30.12 - SOH @ AA02 | Supply for Order 200091513, Item 539 cannot be changed 90028419 item 3910 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3940 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 539 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3910 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007083 | CLAMP,BLK;THOMASSEN 3056104601 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_3910 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 539 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3940 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0430 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007086 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100895 | 96 | EA | 192 | 0 | 0 | 96 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 43 cannot be changed 90028419 item 350 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 43 | 0 | EA | 102000000031114 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 96 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0350 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007086 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100895 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0350 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 43 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 360 |  |  | 0 | 96 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0460 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007088 | RETAINER;THOMASSEN 3011101001 | 8 | EA | 8 | 0 | 0 | 8 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 46 cannot be changed 90028419 item 380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 46 | 0 | EA | 102000000030481 | 102000000030350 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007088 | RETAINER;THOMASSEN 3011101001 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0380 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 46 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 390 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007092 | STUD,FTD;THOMASSEN 3025103006 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 118 cannot be changed 90028419 item 930 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 940 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 118 | 0 | EA | 102000000030487 | 102000000030977 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0930 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007092 | STUD,FTD;THOMASSEN 3025103006 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0930 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 118 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 940 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1310 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 8 | EA | 28 | 0 | 0 | 4 | EA | 15.10 - SOH @ AA02 | Supply for Order 200091513, Item 690 cannot be changed 90028419 item 4580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4620 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 690 | 0 | EA | 102000000030487 | 102000000031162 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_4580 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 690 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4620 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1310 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 8 | EA | 28 | 0 | 0 | 4 | EA | 15.10 - SOH @ AA02 | Supply for Order 200091513, Item 690 cannot be changed 90028419 item 4580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4620 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 690 | 0 | EA | 102000000030487 | 102000000031312 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_4580 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 690 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4620 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1670 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 4 | EA | 28 | 0 | 0 | 4 | EA | 15.10 - SOH @ AA02 | Supply for Order 200091513, Item 234 cannot be changed 90028419 item 1770 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 234 | 0 | EA | 102000000030497 | 102000000031160 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1770 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 234 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1800 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0280 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 4 | EA | 28 | 0 | 0 | 4 | EA | 13.01 - SOH @ AA01 | Supply for Order 200091513, Item 29 cannot be changed 90028419 item 250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 29 | 0 | EA | 102000000030386 | 102000000031159 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0250 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 29 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 260 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1950 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 4 | EA | 28 | 0 | 0 | 4 | EA | 15.10 - SOH @ AA02 | Supply for Order 200091513, Item 516 cannot be changed 90028419 item 3710 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 516 | 0 | EA | 102000000030389 | 102000000031161 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3710 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007093 | NUT;ALLEN,1",THOMASSEN 9931030837 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_3710 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 516 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3740 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0270 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007097 | STUD,BODY BOUND;THOMASSEN 3025103003 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 28 cannot be changed 90028419 item 240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 28 | 0 | EA | 102000000030386 | 102000000030958 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007097 | STUD,BODY BOUND;THOMASSEN 3025103003 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0240 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 28 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 250 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0290 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007098 | STUD,BODY BOUND;THOMASSEN 3025103100 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 30 cannot be changed 90028419 item 260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 30 | 0 | EA | 102000000030386 | 102000000030974 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007098 | STUD,BODY BOUND;THOMASSEN 3025103100 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0260 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 30 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 270 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007099 | HELICOIL,LKG;THOMASSEN 1445210161 | 8 | EA | 16 | 0 | 0 | 8 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 119 cannot be changed 90028419 item 940 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 950 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 119 | 0 | EA | 102000000030487 | 102000000030068 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0940 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007099 | HELICOIL,LKG;THOMASSEN 1445210161 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0940 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 119 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 950 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1590 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007099 | HELICOIL,LKG;THOMASSEN 1445210161 | 2 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 697 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007099 | HELICOIL,LKG;THOMASSEN 1445210161 |  |  |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0220 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007099 | HELICOIL,LKG;THOMASSEN 1445210161 | 2 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 23 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007099 | HELICOIL,LKG;THOMASSEN 1445210161 |  |  |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0480 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007100 | HELICOIL,LKG;THOMASSEN 1445210121 | 16 | EA | 20 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 466 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007100 | HELICOIL,LKG;THOMASSEN 1445210121 |  |  |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0390 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007101 | HELICOIL,LKG;THOMASSEN 1445210081 | 16 | EA | 34 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 36 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007101 | HELICOIL,LKG;THOMASSEN 1445210081 |  |  |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0910 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007101 | HELICOIL,LKG;THOMASSEN 1445210081 | 6 | EA | 34 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 685 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007101 | HELICOIL,LKG;THOMASSEN 1445210081 |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0260 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007102 | SCREW,CAP;ALLOY ST,THOMASSEN 1525080825 | 4 | EA | 1 | 0 | 0 | 1 | EA | 15.10 - ETA 18.03.25 PO 4500031515 BH | Supply for Order 200091513, Item 27 cannot be changed 90028419 item 230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 27 | 0 | EA | 102000000030386 | 102000000030839 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007102 | SCREW,CAP;ALLOY ST,THOMASSEN 1525080825 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0230 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 27 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 240 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007103 | PIN,DOWEL;THOMASSEN 158A5457P39 | 4 | EA | 8 | 0 | 0 | 4 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 26 cannot be changed 90028419 item 220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 26 | 0 | EA | 102000000030386 | 102000000030171 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007103 | PIN,DOWEL;THOMASSEN 158A5457P39 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0220 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 26 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 230 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0230 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007104 | HELICOIL,BBL,INNER;THOMASSEN 1445220082 | 4 | EA | 6 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 24 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007104 | HELICOIL,BBL,INNER;THOMASSEN 1445220082 |  |  |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0140 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007105 | STUD,BODY BOUND;THOMASSEN 3025103007 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 13 cannot be changed 90028419 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 13 | 0 | EA | 102000000030489 | 102000000030957 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007105 | STUD,BODY BOUND;THOMASSEN 3025103007 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0120 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0150 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007106 | STUD,BODY BOUND;THOMASSEN 3025103200 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 14 cannot be changed 90028419 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 14 | 0 | EA | 102000000030489 | 102000000030973 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007106 | STUD,BODY BOUND;THOMASSEN 3025103200 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0130 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 140 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1680 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007107 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100895 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 509 cannot be changed 90028419 item 3650 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 509 | 0 | EA | 102000000030498 | 102000000030862 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3650 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007107 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100895 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_3650 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 509 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3680 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0220 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007107 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100895 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 455 cannot be changed 90028419 item 3170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 455 | 0 | EA | 102000000030489 | 102000000030861 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007107 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100895 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_3170 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 455 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3200 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007109 | GASKET;CNAF,THOMASSEN 2422107200 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 288 cannot be changed 90028419 item 2220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 288 | 0 | EA | 102000000030360 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007109 | GASKET;CNAF,THOMASSEN 2422107200 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2220 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 288 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007110 | GASKET;CNAF,THOMASSEN 2422105000 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 289 cannot be changed 90028419 item 2230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 289 | 0 | EA | 102000000030361 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007110 | GASKET;CNAF,THOMASSEN 2422105000 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2230 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 289 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007111 | GASKET;CNAF,THOMASSEN 2422107500 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 290 cannot be changed 90028419 item 2240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 290 | 0 | EA | 102000000030281 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007111 | GASKET;CNAF,THOMASSEN 2422107500 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2240 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 290 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2270 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1130 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007112 | BOLT,HEX;ALLOY ST,THOMASSEN 1510080635 | 4 | EA | 17 | 0 | 0 | 4 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 486 cannot be changed 90028419 item 3420 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 486 | 0 | EA | 102000000030487 | 102000000031151 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3420 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007112 | BOLT,HEX;ALLOY ST,THOMASSEN 1510080635 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3420 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 486 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3450 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1990 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007116 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100701 | 1 | EA | 48 | 0 | 0 | 1 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 519 cannot be changed 90028419 item 3740 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 519 | 0 | EA | 102000000030501 | 102000000030979 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007116 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100701 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3740 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 519 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3770 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2130 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007125 | O-RING;VIT,THOMASSEN 5141430X4 | 8 | EA | 12 | 0 | 0 | 8 | EA | 10.01 - SOH @ AA02 | Supply for Order 200091513, Item 293 cannot be changed 90028419 item 2270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 293 | 0 | EA | 102000000030491 | 102000000030299 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007125 | O-RING;VIT,THOMASSEN 5141430X4 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2270 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 293 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2300 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007127 | GASKET;206MM OD X 190MM ID X 2MM THK | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 292 cannot be changed 90028419 item 2260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 292 | 0 | EA | 102000000030491 | 102000000030659 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007127 | GASKET;206MM OD X 190MM ID X 2MM THK | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2260 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 292 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2290 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0200 | 3130 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007130 | SCREW,CAP HD,0.625"X 50MM,ALLOY ST,18UNF | 18 | EA | 37 | 0 | 0 | 18 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 639 cannot be changed 90028419 item 4250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 639 | 0 | EA | 102000000030486 | 102000000030234 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007130 | SCREW,CAP HD,0.625"X 50MM,ALLOY ST,18UNF | 2024-07-21 | W |  | 0200 | LP ROTOR ASSEMBLY | INT | LP ROTOR ASSEMBLY | 5 |  | 90028419_4250 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 639 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4280 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2360 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007131 | GASKET;C4500,KLINGER 0W0010007131 | 1 | EA | 3 | 0 | 0 | 1 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 348 cannot be changed 90028419 item 2690 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 348 | 0 | EA | 102000000030717 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2690 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007131 | GASKET;C4500,KLINGER 0W0010007131 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2690 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 348 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2720 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0710 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007136 | CLAMP,HORIZ JOINT;THOMASSEN 3045103401 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 84 cannot be changed 90028419 item 670 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 84 | 0 | EA | 102000000030492 | 102000000030777 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007136 | CLAMP,HORIZ JOINT;THOMASSEN 3045103401 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0670 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 84 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 680 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0790 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007138 | SEAL,THOMASSEN M3142J GAS TURBINE,STRIP | 12 | EA | 12 | 0 | 0 | 12 | EA | 20.02 - SOH @ AA02 | Supply for Order 200091513, Item 92 cannot be changed 90028419 item 740 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 92 | 0 | EA | 102000000030492 | 101000000146894 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007138 | SEAL,THOMASSEN M3142J GAS TURBINE,STRIP | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0740 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 92 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 750 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1620 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007142 | SCREW,CAP;ALLOY ST,THOMASSEN 1525120705 | 8 | EA | 8 | 0 | 0 | 8 | EA | 27.02 - SOH @ AA02 | Supply for Order 200091513, Item 700 cannot be changed 90028419 item 4650 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 700 | 0 | EA | 102000000030488 | 102000000030836 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4650 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007142 | SCREW,CAP;ALLOY ST,THOMASSEN 1525120705 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_4650 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 700 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4690 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1480 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007144 | PIN,DOWEL;THOMASSEN 2236113300 | 4 | EA | 10 | 0 | 0 | 4 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 210 cannot be changed 90028419 item 1600 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 210 | 0 | EA | 102000000030488 | 102000000030181 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1600 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007144 | PIN,DOWEL;THOMASSEN 2236113300 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_1600 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 210 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1630 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1600 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007146 | PIN,LK;THOMASSEN 3025100302 | 2 | EA | 8 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 698 cannot be changed 90028419 item 4630 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 698 | 0 | EA | 102000000030488 | 102000000030169 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4630 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007146 | PIN,LK;THOMASSEN 3025100302 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_4630 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 698 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4670 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1610 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007147 | BOLT,HEX;ALLOY ST,THOMASSEN 1510121335 | 4 | EA | 5 | 0 | 0 | 4 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 699 cannot be changed 90028419 item 4640 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 699 | 0 | EA | 102000000030488 | 102000000030828 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4640 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007147 | BOLT,HEX;ALLOY ST,THOMASSEN 1510121335 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_4640 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 699 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4680 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1520 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007148 | SCREW,CAP;ALLOY ST,THOMASSEN 3025103700 | 2 | EA | 5 | 0 | 0 | 2 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 217 cannot be changed 90028419 item 1640 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 217 | 0 | EA | 102000000030483 | 102000000031115 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1640 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007148 | SCREW,CAP;ALLOY ST,THOMASSEN 3025103700 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 90028419_1640 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 217 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1670 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1540 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007149 | SCREW,CAP;ALLOY ST,THOMASSEN 3025112200 | 8 | EA | 16 | 0 | 0 | 8 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 219 cannot be changed 90028419 item 1650 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 219 | 0 | EA | 102000000030483 | 102000000031116 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1650 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007149 | SCREW,CAP;ALLOY ST,THOMASSEN 3025112200 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 90028419_1650 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 219 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1680 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1560 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007150 | PIN,STR;THOMASSEN 2236116000 | 4 | EA | 9 | 0 | 0 | 4 | EA | 02.10 - SOH at AA02 | Supply for Order 200091513, Item 221 cannot be changed 90028419 item 1660 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 221 | 0 | EA | 102000000030483 | 102000000030184 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007150 | PIN,STR;THOMASSEN 2236116000 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 90028419_1660 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 221 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1690 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1600 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007151 | SCREW,CAP,HEX;THOMASSEN 1510120635 | 2 | EA | 18 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 225 cannot be changed 90028419 item 1690 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 225 | 0 | EA | 102000000030483 | 102000000031152 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1690 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007151 | SCREW,CAP,HEX;THOMASSEN 1510120635 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 90028419_1690 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 225 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1720 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1610 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007152 | PLATE,LKG;CS,THOMASSEN 2231104600 | 4 | EA | 56 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 226 cannot be changed 90028419 item 1700 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 226 | 0 | EA | 102000000030483 | 102000000030594 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1700 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007152 | PLATE,LKG;CS,THOMASSEN 2231104600 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 90028419_1700 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 226 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1730 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1680 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007153 | PIN,LK;THOMASSEN 3025100306 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 235 cannot be changed 90028419 item 1780 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 235 | 0 | EA | 102000000030497 | 102000000030190 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007153 | PIN,LK;THOMASSEN 3025100306 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1780 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 235 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1810 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1710 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007155 | SCREW,CAP HD,1.00"X 63MM,ALLOY ST,8UNC | 8 | EA | 9 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 238 cannot be changed 90028419 item 1810 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 238 | 0 | EA | 102000000030497 | 102000000030995 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1810 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007155 | SCREW,CAP HD,1.00"X 63MM,ALLOY ST,8UNC | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1810 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 238 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1840 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1640 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007156 | STUD,FTD;THOMASSEN 3025103014 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 231 cannot be changed 90028419 item 1740 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 231 | 0 | EA | 102000000030497 | 102000000030976 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007156 | STUD,FTD;THOMASSEN 3025103014 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1740 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 231 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1770 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1650 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007157 | STUD,FTD;THOMASSEN 3025103013 | 2 | EA | 5 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 232 cannot be changed 90028419 item 1750 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 232 | 0 | EA | 102000000030497 | 102000000030978 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007157 | STUD,FTD;THOMASSEN 3025103013 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1750 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 232 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1780 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007158 | BOLT,12 PNT;THOMASSEN 1514120762 | 44 | EA | 196 | 0 | 0 | 44 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 120 cannot be changed 90028419 item 950 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 960 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 120 | 0 | EA | 102000000030990 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 44 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0950 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007158 | BOLT,12 PNT;THOMASSEN 1514120762 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0950 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 120 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 960 |  |  | 0 | 44 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0770 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007159 | BOLT,12 PNT;THOMASSEN 1514120822 | 48 | EA | 49 | 0 | 0 | 41 | EA | 02.03 - SOH @ AA02 | Supply for Order 200091513, Item 478 cannot be changed 90028419 item 3370 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 478 | 0 | EA | 102000000033971 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3370 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007159 | BOLT,12 PNT;THOMASSEN 1514120822 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_3370 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 478 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3400 |  |  | 0 | 48 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0840 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007160 | BOLT,12 PNT;THOMASSEN 1514201142 | 6 | EA | 9 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 99 cannot be changed 90028419 item 770 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 99 | 0 | EA | 102000000030980 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007160 | BOLT,12 PNT;THOMASSEN 1514201142 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0770 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 99 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 780 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1220 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007160 | BOLT,12 PNT;THOMASSEN 1514201142 | 6 | EA | 9 | 0 | 0 | 3 | EA | 15.10 - ETA 18.03.25 PO 4500031469 BH | Supply for Order 200091513, Item 495 cannot be changed 90028419 item 3510 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 495 | 0 | EA | 102000000030487 | 102000000030981 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3510 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007160 | BOLT,12 PNT;THOMASSEN 1514201142 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3510 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 495 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3540 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0840 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007161 | BOLT,12 PNT;THOMASSEN 151410>WSE10251329 | 68 | EA | 84 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 675 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 68 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007161 | BOLT,12 PNT;THOMASSEN 151410>WSE10251329 |  |  |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1230 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007162 | BOLT,12 PNT;THOMASSEN 1514121522 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 496 cannot be changed 90028419 item 3520 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 496 | 0 | EA | 102000000030487 | 102000000033972 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3520 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007162 | BOLT,12 PNT;THOMASSEN 1514121522 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3520 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 496 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3550 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0850 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007163 | BOLT,12 PNT;THOMASSEN 1514100513 | 4 | EA | 17 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 676 cannot be changed 90028419 item 4530 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 676 | 0 | EA | 102000000030481 | 102000000030240 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4530 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007163 | BOLT,12 PNT;THOMASSEN 1514100513 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_4530 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 676 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4560 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1240 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007163 | BOLT,12 PNT;THOMASSEN 1514100513 | 6 | EA | 17 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 497 cannot be changed 90028419 item 3530 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 497 | 0 | EA | 102000000030487 | 102000000030239 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3530 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007163 | BOLT,12 PNT;THOMASSEN 1514100513 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3530 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 497 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3560 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007164 | BOLT:BOLT,12 PNT;THOMASSEN 15141211430 | 12 | EA | 12 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 498 cannot be changed 90028419 item 3540 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 498 | 0 | EA | 102000000030487 | 102000000033973 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3540 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007164 | BOLT:BOLT,12 PNT;THOMASSEN 15141211430 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3540 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 498 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3570 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0500 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007165 | PIN,STR;THOMASSEN 2236113900 | 6 | EA | 18 | 0 | 0 | 6 | EA | 10.01 - SOH @ AA02 | Supply for Order 200091513, Item 468 cannot be changed 90028419 item 3290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 468 | 0 | EA | 102000000030386 | 102000000029869 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007165 | PIN,STR;THOMASSEN 2236113900 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3290 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 468 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3320 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1300 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007165 | PIN,STR;THOMASSEN 2236113900 | 6 | EA | 18 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 689 cannot be changed 90028419 item 4570 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 689 | 0 | EA | 102000000030487 | 102000000030161 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4570 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007165 | PIN,STR;THOMASSEN 2236113900 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_4570 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 689 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4610 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0160 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007167 | GASKET;THOMASSEN 2424125400 | 1 | EA | 4 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 15 cannot be changed 90028419 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 15 | 0 | EA | 102000000030489 | 102000000030293 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007167 | GASKET;THOMASSEN 2424125400 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0140 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0170 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007168 | GASKET;THOMASSEN 2424125500 | 1 | EA | 3 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 16 cannot be changed 90028419 item 150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 16 | 0 | EA | 102000000030489 | 102000000030370 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007168 | GASKET;THOMASSEN 2424125500 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0150 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 2000 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007172 | GASKET;AL,THOMASSEN 3044103101 | 2 | SET | 4 | 0 | 0 | 2 | SET | 17.01 - SOH @ AA01 | Supply for Order 200091513, Item 703 cannot be changed 90028419 item 4680 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4720 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 703 | 0 | SET | 101000000139456 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4680 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007172 | GASKET;AL,THOMASSEN 3044103101 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_4680 |  |  | DG1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 703 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4720 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2490 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007172 | GASKET;AL,THOMASSEN 3044103101 | 2 | SET | 4 | 0 | 0 | 2 | SET | 17.01 - SOH @ AA01 | Supply for Order 200091513, Item 376 cannot be changed 90028419 item 2830 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2860 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 376 | 0 | SET | 101000000139632 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2830 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007172 | GASKET;AL,THOMASSEN 3044103101 | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_2830 |  |  | DG1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 376 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2860 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007175 | SWITCH,LIMIT;EX,THOMASSEN 99012808000 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 582 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | airinletfilt |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007175 | SWITCH,LIMIT;EX,THOMASSEN 99012808000 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3000 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007181 | BEARING,THR;ST,THOMASSEN 3030133300 | 2 | SET | 2 | 0 | 2 | 2 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 429 cannot be changed 9027133 item 3000 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3030 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180124227 | 9027133 | 05 | Preparation | 0000129822 | 429 | 0 | SET |  |  | 102000000030144 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000396389_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056768 | 1020 | 2025-07-03 | 2 |  | 2025-02-11 | 4900234167_2025_0009 | 2025-03-01 |  | 5000396389_2025_0001 | 0 | 2 | 0 | 90028419 | 2 | 0 | 180124227 | 2 | 0 | 0 | X | L | 4900234167 | 2025 |  | 5000396389 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007181 | BEARING,THR;ST,THOMASSEN 3030133300 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 9027133_3000 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 429 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3030 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007183 | BEARING,ALCATEL DRV;THOMASSEN 3030126800 | 2 | SET | 0 | 0 | 0 | 0 |  | 18.11 - ETA 18.03.25 PO 4500034679 BH | Supply for Order 200091513, Item 598 cannot be changed 90028419 item 4070 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4100 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 598 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007183 | BEARING,ALCATEL DRV;THOMASSEN 3030126800 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_4070 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 598 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 70 | 30 | 5300013090 | 4100 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3010 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007184 | O-RING,SEAL;11MM,GE KHA010702600 | 2 | EA | 2 | 1 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 430 cannot be changed 90028419 item 3010 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3040 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 430 | 0 | EA | 102000000030494 | 102000000030638 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007184 | O-RING,SEAL;11MM,GE KHA010702600 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_3010 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 430 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3040 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2960 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007186 | GEARBOX;THOMASSEN 3030122000 | 1 | EA | 4 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 425 cannot be changed 90028419 item 2960 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 425 | 0 | EA | 102000000030494 | 102000000031283 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2960 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007186 | GEARBOX;THOMASSEN 3030122000 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2960 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 425 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2990 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0870 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007187 | PIN,STR;THOMASSEN 2236113200 | 18 | EA | 36 | 0 | 0 | 18 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 102 cannot be changed 90028419 item 800 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 102 | 0 | EA | 102000000030487 | 102000000029867 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0800 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007187 | PIN,STR;THOMASSEN 2236113200 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0800 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 102 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 810 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0260 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007197 | SPACER,RING;CS,THOMASSEN 3042100101 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 662 cannot be changed 90028419 item 4410 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 662 | 0 | EA | 102000000030489 | 102000000030661 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4410 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007197 | SPACER,RING;CS,THOMASSEN 3042100101 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_4410 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 662 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  |  | 5300013090 | 4440 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0270 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007198 | SPACER,RING;CS,THOMASSEN 3042100102 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 663 cannot be changed 90028419 item 4420 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 663 | 0 | EA | 102000000030489 | 102000000030662 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4420 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007198 | SPACER,RING;CS,THOMASSEN 3042100102 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_4420 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 663 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  |  | 5300013090 | 4450 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2990 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007204 | THERMOCOUPLE,THOMASSEN M3142J,LUB OIL | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 577 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124TI90 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007204 | THERMOCOUPLE,THOMASSEN M3142J,LUB OIL |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007205 | HELICOIL,LKG;THOMASSEN 9931031222 | 2 | EA | 229 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007205 | HELICOIL,LKG;THOMASSEN 9931031222 |  |  |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2560 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007205 | HELICOIL,LKG;THOMASSEN 9931031222 | 30 | EA | 229 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 562 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007205 | HELICOIL,LKG;THOMASSEN 9931031222 |  |  |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1210 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007205 | HELICOIL,LKG;THOMASSEN 9931031222 | 1 | EA | 229 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 494 cannot be changed 90028419 item 3500 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 494 | 0 | EA | 102000000030487 | 102000000030774 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3500 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007205 | HELICOIL,LKG;THOMASSEN 9931031222 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3500 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 494 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3530 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1760 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007206 | STUD,EXH FRAME;THOMASSEN 3025101806 | 6 | EA | 9 | 0 | 0 | 6 | EA | 30.01 - SOH @ AA02 | Supply for Order 200091513, Item 243 cannot be changed 90028419 item 1860 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 243 | 0 | EA | 102000000030389 | 102000000030975 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1860 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007206 | STUD,EXH FRAME;THOMASSEN 3025101806 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1860 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 243 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1890 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1930 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007207 | PIN,DOWEL;THOMASSEN 2236115600 | 4 | EA | 6 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 514 cannot be changed 90028419 item 3700 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 514 | 0 | EA | 102000000030389 | 102000000030160 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3700 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007207 | PIN,DOWEL;THOMASSEN 2236115600 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_3700 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 514 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3730 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0670 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007208 | PLATE,LKG;CS,THOMASSEN 2231116400 | 4 | EA | 6 | 0 | 0 | 4 | EA | 30.01 - SOH @ AA02 | Supply for Order 200091513, Item 75 cannot be changed 90028419 item 580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 75 | 0 | EA | 102000000030502 | 102000000030593 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007208 | PLATE,LKG;CS,THOMASSEN 2231116400 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0580 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 75 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 590 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0980 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007211 | PIN,STR;THOMASSEN 2237117700 | 2 | EA | 2 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 113 cannot be changed 90028419 item 900 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 910 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 113 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0900 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007211 | PIN,STR;THOMASSEN 2237117700 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0900 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 113 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 910 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0850 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007212 | PLATE,LKG;SS,THOMASSEN 3022101501 | 12 | EA | 12 | 0 | 0 | 12 | EA | 30.01 - SOH @ AA02 | Supply for Order 200091513, Item 100 cannot be changed 90028419 item 780 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 100 | 0 | EA | 102000000030487 | 102000000030914 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007212 | PLATE,LKG;SS,THOMASSEN 3022101501 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0780 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 100 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 790 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0910 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007213 | BOLT,HEX;ALLOY ST,THOMASSEN 1510060455 | 36 | EA | 72 | 0 | 0 | 36 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 106 cannot be changed 90028419 item 840 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 106 | 0 | EA | 102000000030487 | 102000000030986 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 36 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007213 | BOLT,HEX;ALLOY ST,THOMASSEN 1510060455 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0840 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 106 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 850 |  |  | 0 | 36 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007214 | BOLT,HEX;ALLOY ST,THOMASSEN 1510060325 | 12 | EA | 38 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 17 cannot be changed 90028419 item 160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 17 | 0 | EA | 102000000030489 | 102000000030826 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007214 | BOLT,HEX;ALLOY ST,THOMASSEN 1510060325 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0160 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 170 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0690 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007214 | BOLT,HEX;ALLOY ST,THOMASSEN 1510060325 | 8 | EA | 38 | 0 | 0 | 8 | EA | 10.01 - SOH @ AA02 | Supply for Order 200091513, Item 77 cannot be changed 90028419 item 600 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 77 | 0 | EA | 102000000030502 | 102000000030827 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0600 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007214 | BOLT,HEX;ALLOY ST,THOMASSEN 1510060325 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0600 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 77 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 610 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1070 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007215 | PLATE,LKG;SS,23X76MM,0.375",NP SMR50006 | 18 | EA | 36 | 0 | 0 | 18 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 130 cannot be changed 90028419 item 1040 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1050 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 130 | 0 | EA | 102000000030480 | 102000000030592 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007215 | PLATE,LKG;SS,23X76MM,0.375",NP SMR50006 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1040 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 130 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1050 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1860 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007225 | BOLT,HEX;ALLOY ST,THOMASSEN 1511060160 | 32 | EA | 59 | 0 | 0 | 5 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 253 cannot be changed 90028419 item 1940 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 253 | 0 | EA | 102000000030389 | 102000000031310 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1940 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007225 | BOLT,HEX;ALLOY ST,THOMASSEN 1511060160 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1940 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 253 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1970 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1720 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007225 | BOLT,HEX;ALLOY ST,THOMASSEN 1511060160 | 2 | EA | 59 | 0 | 0 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 694 cannot be changed 90028419 item 4620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 694 | 0 | EA | 102000000030498 | 102000000031311 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007225 | BOLT,HEX;ALLOY ST,THOMASSEN 1511060160 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_4620 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 694 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4660 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1860 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007225 | BOLT,HEX;ALLOY ST,THOMASSEN 1511060160 | 32 | EA | 59 | 0 | 0 | 27 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 253 cannot be changed 90028419 item 1940 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 253 | 0 | EA | 102000000030389 | 102000000030249 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1940 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007225 | BOLT,HEX;ALLOY ST,THOMASSEN 1511060160 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1940 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 253 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1970 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2540 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007226 | BOLT,HEX;ALLOY ST,THOMASSEN 1510080285 | 16 | EA | 4 | 0 | 0 | 0 |  | 24.01 - ETA 15.04.25 PO 4500031473 BH | Supply for Order 200091513, Item 713 cannot be changed 90028419 item 4760 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 713 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4760 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007226 | BOLT,HEX;ALLOY ST,THOMASSEN 1510080285 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_4760 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 713 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4800 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0680 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007226 | BOLT,HEX;ALLOY ST,THOMASSEN 1510080285 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 76 cannot be changed 90028419 item 590 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 76 | 0 | EA | 102000000030502 | 102000000030253 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0590 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007226 | BOLT,HEX;ALLOY ST,THOMASSEN 1510080285 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0590 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 76 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 600 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0550 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007227 | SCREW,CAP;ALLOY ST,THOMASSEN 1525161275 | 20 | EA | 20 | 0 | 0 | 0 |  | 15.10 - ETA 18.03.25 PO 4500031469 BH | Supply for Order 200091513, Item 674 cannot be changed 90028419 item 4520 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 674 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4520 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007227 | SCREW,CAP;ALLOY ST,THOMASSEN 1525161275 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_4520 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 674 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4550 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0970 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007227 | SCREW,CAP;ALLOY ST,THOMASSEN 1525161275 | 20 | EA | 20 | 0 | 0 | 20 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 112 cannot be changed 90028419 item 890 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 900 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 112 | 0 | EA | 102000000031153 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0890 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007227 | SCREW,CAP;ALLOY ST,THOMASSEN 1525161275 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0890 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 112 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 900 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007228 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100575 | 2 | EA | 38 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 213 cannot be changed 90028419 item 1610 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 213 | 0 | EA | 102000000030488 | 102000000030860 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1610 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007228 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100575 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_1610 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 213 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1640 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0520 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007228 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100575 | 8 | EA | 38 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 671 cannot be changed 90028419 item 4490 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 671 | 0 | EA | 102000000030386 | 102000000030864 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007228 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100575 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_4490 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 671 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4520 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0320 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007228 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100575 | 14 | EA | 38 | 0 | 0 | 14 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 668 cannot be changed 90028419 item 4460 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 668 | 0 | EA | 102000000030489 | 102000000030863 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 14 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007228 | SCREW,CAP;ALLOY ST,THOMASSEN 1525100575 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_4460 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 668 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4490 |  |  | 0 | 14 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007229 | SCREW,CAP;ALLOY ST,THOMASSEN 1525160825 | 2 | EA | 23 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 7 cannot be changed 90028419 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 7 | 0 | EA | 102000000030489 | 102000000031111 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007229 | SCREW,CAP;ALLOY ST,THOMASSEN 1525160825 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0090 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1730 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007230 | NUT,HEX;THOMASSEN 3026100905 | 66 | EA | 394 | 0 | 0 | 66 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 240 cannot be changed 90028419 item 1830 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 240 | 0 | EA | 102000000030389 | 102000000031163 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 66 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1830 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007230 | NUT,HEX;THOMASSEN 3026100905 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1830 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 240 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1860 |  |  | 0 | 66 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1740 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007231 | NUT,LK;THOMASSEN 1441870080 | 22 | EA | 44 | 0 | 10 | 22 | EA | 16.12 - qty 22 SOH @ AA02 | Supply for Order 200091513, Item 241 cannot be changed 90028419 item 1840 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 241 | 0 | EA | 102000000030389 | 102000000030194 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 22 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007231 | NUT,LK;THOMASSEN 1441870080 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1840 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 241 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1870 |  |  | 0 | 22 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1410 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007232 | NUT,LK;CS,THOMASSEN 9900271500 | 12 | EA | 111 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 183 cannot be changed 90028419 item 1390 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 183 | 0 | EA | 102000000030498 | 102000000031122 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1390 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007232 | NUT,LK;CS,THOMASSEN 9900271500 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1390 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 183 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1420 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1770 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007232 | NUT,LK;CS,THOMASSEN 9900271500 | 12 | EA | 111 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 244 cannot be changed 90028419 item 1870 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1900 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 244 | 0 | EA | 102000000030389 | 102000000031123 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1870 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007232 | NUT,LK;CS,THOMASSEN 9900271500 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1870 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 244 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1900 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0230 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007233 | NUT,LK;CS,THOMASSEN 1441870120 | 4 | EA | 40 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 456 cannot be changed 90028419 item 3180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 456 | 0 | EA | 102000000030489 | 102000000031158 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007233 | NUT,LK;CS,THOMASSEN 1441870120 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_3180 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 456 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3210 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0300 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007233 | NUT,LK;CS,THOMASSEN 1441870120 | 4 | EA | 40 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 31 cannot be changed 90028419 item 270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 31 | 0 | EA | 102000000030386 | 102000000031157 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007233 | NUT,LK;CS,THOMASSEN 1441870120 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0270 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 31 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 280 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0200 | 3120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007237 | BOLT ASY;LOW PRESS,THOMASSEN M3142J | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 548 cannot be changed 90028419 item 3940 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 548 | 0 | EA | 102000000030486 | 102000000030832 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3940 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007237 | BOLT ASY;LOW PRESS,THOMASSEN M3142J | 2024-07-21 | W |  | 0200 | LP ROTOR ASSEMBLY | INT | LP ROTOR ASSEMBLY | 5 |  | 90028419_3940 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 548 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3970 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1140 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007241 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100455 | 4 | EA | 27 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 487 cannot be changed 90028419 item 3430 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 487 | 0 | EA | 102000000030487 | 102000000030991 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3430 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007241 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100455 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3430 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 487 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3460 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0770 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007241 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100455 | 6 | EA | 27 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 634 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | AIRPIN |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007241 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100455 |  |  |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0200 | 2400 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007243 | TWISTLOCK,THOMASSEN/NP FRAME 3 TURB | 1 | SET | 3.05 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000129822 | 365 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007243 | TWISTLOCK,THOMASSEN/NP FRAME 3 TURB |  |  |  | 0200 | LP ROTOR ASSEMBLY | INT | LP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 3120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007243 | TWISTLOCK,THOMASSEN/NP FRAME 3 TURB | 1 | SET | 3.05 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000129822 | 364 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007243 | TWISTLOCK,THOMASSEN/NP FRAME 3 TURB |  |  |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 100086264 | 0020 | 0060 | 100086264 | Start Clutch/UV Purge Sol OH (3) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 10 | No issue identified | 10007253 | VALVE,SLND;CS,THOMASSEN 2133126201 | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000272423 | 6 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-11-05 | 0 |  |  |  |  | 1KT2420 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007253 | VALVE,SLND;CS,THOMASSEN 2133126201 |  |  |  | 0020 | Complete Replacements | INT | Complete Replacements | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000267123 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100086264 | 0020 | 0050 | 100086264 | Start Clutch/UV Purge Sol OH (3) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(30.10.2024) | 10007253 | VALVE,SLND;CS,THOMASSEN 2133126201 | 1 | EA | 0 | 0 | 0 | 0 |  | 06.02 - ETA 29.04.25 PO 4500044909 ex Thomassen | Supply for Order 100086264, Item 5 cannot be changed 90025091 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017153 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  |  | 90025091 | 05 | Preparation | 0000272423 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-31 | ODST-0090025091_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025091 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007253 | VALVE,SLND;CS,THOMASSEN 2133126201 | 2024-10-30 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  |  | 90025091_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267123 | S002 | 30 | 30 | 5300017153 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272423 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3270 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007253 | VALVE,SLND;CS,THOMASSEN 2133126201 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  |  | 05 | Preparation | 0000129822 | 755 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007253 | VALVE,SLND;CS,THOMASSEN 2133126201 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2950 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007253 | VALVE,SLND;CS,THOMASSEN 2133126201 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  |  | 05 | Preparation | 0000129822 | 573 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007253 | VALVE,SLND;CS,THOMASSEN 2133126201 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0440 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007264 | NUT,HEX;ALLOY ST,THOMASSEN 1440010101 | 224 | EA | 224 | 0 | 0 | 224 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 44 cannot be changed 90028419 item 360 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 44 | 0 | EA | 102000000030928 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 224 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0360 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007264 | NUT,HEX;ALLOY ST,THOMASSEN 1440010101 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0360 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 44 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 370 |  |  | 0 | 224 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2530 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007264 | NUT,HEX;ALLOY ST,THOMASSEN 1440010101 | 48 | EA | 224 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 715 cannot be changed 90028419 item 4780 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 715 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007264 | NUT,HEX;ALLOY ST,THOMASSEN 1440010101 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_4780 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 715 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4820 |  |  | 0 | 48 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1150 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007282 | BOLT,HEX;ALLOY ST,THOMASSEN 3025102209 | 2 | EA | 587 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 488 cannot be changed 90028419 item 3440 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 488 | 0 | EA | 102000000030487 | 102000000030984 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3440 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007282 | BOLT,HEX;ALLOY ST,THOMASSEN 3025102209 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3440 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 488 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3470 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1160 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007290 | STUD,THOMASSEN M5352B,LOCATOR,TRANSIT | 1 | EA | 56 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 489 cannot be changed 90028419 item 3450 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 489 | 0 | EA | 102000000030487 | 102000000030972 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007290 | STUD,THOMASSEN M5352B,LOCATOR,TRANSIT | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3450 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 489 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3480 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0490 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007294 | SCREW,CAP;ALLOY ST,THOMASSEN 3025117600 | 12 | EA | 24 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 467 cannot be changed 90028419 item 3280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 467 | 0 | EA | 102000000030386 | 102000000031150 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007294 | SCREW,CAP;ALLOY ST,THOMASSEN 3025117600 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3280 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 467 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3310 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0920 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007296 | HELICOIL,0.75"X 1.0 DIA LG,10UN,INCONEL | 4 | EA | 76 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 686 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007296 | HELICOIL,0.75"X 1.0 DIA LG,10UN,INCONEL |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0240 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007296 | HELICOIL,0.75"X 1.0 DIA LG,10UN,INCONEL | 6 | EA | 76 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 25 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007296 | HELICOIL,0.75"X 1.0 DIA LG,10UN,INCONEL |  |  |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1870 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007298 | BOLT,12 PNT;THOMASSEN 1514161141 | 6 | EA | 53 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 254 cannot be changed 90028419 item 1950 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1980 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 254 | 0 | EA | 102000000030389 | 102000000030982 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1950 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007298 | BOLT,12 PNT;THOMASSEN 1514161141 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1950 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 254 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1980 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1260 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007299 | BOLT,12 PNT;THOMASSEN 1514160892 | 16 | EA | 36 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 499 cannot be changed 90028419 item 3550 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 499 | 0 | EA | 102000000030983 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007299 | BOLT,12 PNT;THOMASSEN 1514160892 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3550 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 499 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3580 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 3170 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007300 | HELICOIL,LKG;THOMASSEN 1445230062 | 10 | EA | 301 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 545 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007300 | HELICOIL,LKG;THOMASSEN 1445230062 |  |  |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0490 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007322 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100765 | 32 | EA | 172 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 49 cannot be changed 90028419 item 410 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 49 | 0 | EA | 102000000030959 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0410 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007322 | BOLT,HEX;ALLOY ST,THOMASSEN 1510100765 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0410 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 49 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 420 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1650 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007325 | NUT,LK;CS,THOMASSEN 2160110800 | 64 | EA | 230 | 0 | 0 | 64 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 506 cannot be changed 90028419 item 3620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 506 | 0 | EA | 102000000030498 | 102000000031166 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 64 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007325 | NUT,LK;CS,THOMASSEN 2160110800 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_3620 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 506 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3650 |  |  | 0 | 64 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1230 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007325 | NUT,LK;CS,THOMASSEN 2160110800 | 6 | EA | 230 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 165 cannot be changed 90028419 item 1240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 165 | 0 | EA | 102000000030498 | 102000000031164 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007325 | NUT,LK;CS,THOMASSEN 2160110800 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1240 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 165 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1270 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2920 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007342 | SWITCH,LIMIT;THOMASSEN 3032140301 | 2 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 570 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | shutoffdamp |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007342 | SWITCH,LIMIT;THOMASSEN 3032140301 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-05-01 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147102 | 0040 | 0010 | 200147102 | 1Y F10 TURB COMP VENT FUNC TEST/REP (6) | AA53.1KT24202F | FAN,VENTILATION SYSTEM 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.10.2024) | 10007342 | SWITCH,LIMIT;THOMASSEN 3032140301 | 4 | EA | 2 | 4 | 0 | 4 | EA | 29.10 - SOH @ AA02 | Supply for Order 200147102, Item 1 cannot be changed 9027114 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017012 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027114 | 05 | Preparation | 0000235353 | 1 | 0 | EA | 102000000029967 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-28 | GIST-4900234108_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 4 |  | 2025-02-11 | 4900234108_2025_0001 | 2025-03-01 | 124DA01 |  | 0 | 2 | 0 | 90025084 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234108 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007342 | SWITCH,LIMIT;THOMASSEN 3032140301 | 2024-10-28 | W |  | 0040 | Complete Replacement | INT | Complete Replacement |  |  | 9027114_0010 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232396 | S002 | 30 | 30 | 5300017012 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235353 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2140 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007344 | SEAT,VV;THOMASSEN 24311023000 | 2 | SET | 7 | 0 | 0 | 2 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 294 cannot be changed 90028419 item 2280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2310 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 294 | 0 | SET | 102000000030491 | 102000000030645 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007344 | SEAT,VV;THOMASSEN 24311023000 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2280 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 294 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2310 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0520 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007356 | SPRING,COMP;ST,THOMASSEN 3010101901 | 10 | EA | 30 | 0 | 0 | 10 | EA | 03.10 - SOH at AA02 | Supply for Order 200091513, Item 52 cannot be changed 90028419 item 440 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 52 | 0 | EA | 102000000030481 | 102000000030118 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0440 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007356 | SPRING,COMP;ST,THOMASSEN 3010101901 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0440 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 52 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 450 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1850 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007383 | SCREW,CAP;ALLOY ST,THOMASSEN 3025109400 | 38 | EA | 78 | 0 | 0 | 38 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 252 cannot be changed 90028419 item 1930 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1960 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 252 | 0 | EA | 102000000031125 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 38 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1930 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007383 | SCREW,CAP;ALLOY ST,THOMASSEN 3025109400 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1930 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 252 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1960 |  |  | 0 | 38 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1520 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007383 | SCREW,CAP;ALLOY ST,THOMASSEN 3025109400 | 2 | EA | 78 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 214 cannot be changed 90028419 item 1620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 214 | 0 | EA | 102000000030488 | 102000000031124 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007383 | SCREW,CAP;ALLOY ST,THOMASSEN 3025109400 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_1620 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 214 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1650 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0060 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007384 | SCREW,CAP;ALLOY ST,THOMASSEN 1525121145 | 16 | EA | 32 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 5 cannot be changed 90028419 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 5 | 0 | EA | 102000000030489 | 102000000031113 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007384 | SCREW,CAP;ALLOY ST,THOMASSEN 1525121145 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0070 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 80 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007400 | SCREW,CAP,HEX;1/2"-13UNC | 72 | EA | 152 | 0 | 0 | 36 | EA | 20.02 - SOH @ AA02 | Supply for Order 200091513, Item 167 cannot be changed 90028419 item 1250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 167 | 0 | EA | 102000000030498 | 102000000033976 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 72 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007400 | SCREW,CAP,HEX;1/2"-13UNC | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1250 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 167 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1280 |  |  | 0 | 72 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007400 | SCREW,CAP,HEX;1/2"-13UNC | 72 | EA | 152 | 0 | 0 | 36 | EA | 20.02 - SOH @ AA02 | Supply for Order 200091513, Item 167 cannot be changed 90028419 item 1250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 167 | 0 | EA | 102000000030498 | 102000000030994 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 72 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007400 | SCREW,CAP,HEX;1/2"-13UNC | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1250 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 167 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1280 |  |  | 0 | 72 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0200 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007400 | SCREW,CAP,HEX;1/2"-13UNC | 8 | EA | 152 | 0 | 0 | 8 | EA | 09.02 - SOH @ AA02 | Supply for Order 200091513, Item 21 cannot be changed 90028419 item 200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 21 | 0 | EA | 102000000030386 | 102000000030970 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007400 | SCREW,CAP,HEX;1/2"-13UNC | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0200 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 21 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 210 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1270 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007410 | BOLT,12 PNT;THOMASSEN 1514160951 | 16 | EA | 38 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 500 cannot be changed 90028419 item 3560 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 500 | 0 | EA | 102000000030987 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007410 | BOLT,12 PNT;THOMASSEN 1514160951 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3560 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 500 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3590 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1800 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007416 | BOLT,HEX;0.5"X25MM,ALLOY ST,NP GTH12025 | 8 | EA | 58 | 0 | 0 | 8 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 247 cannot be changed 90028419 item 1890 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1920 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 247 | 0 | EA | 102000000030389 | 102000000030822 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1890 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007416 | BOLT,HEX;0.5"X25MM,ALLOY ST,NP GTH12025 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1890 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 247 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1920 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0210 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007416 | BOLT,HEX;0.5"X25MM,ALLOY ST,NP GTH12025 | 6 | EA | 58 | 0 | 0 | 6 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 454 cannot be changed 90028419 item 3160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 454 | 0 | EA | 102000000030489 | 102000000030823 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007416 | BOLT,HEX;0.5"X25MM,ALLOY ST,NP GTH12025 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_3160 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 454 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3190 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100086237 | 0020 | 0010 | 100086237 | Compressor Inlet TC Replace (2) 1KT2420 | AA53.124TE32 | TXDCR,TEMP 1K2420 SUCT TEMP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.10.2024) | 10007429 | INSTRUMENT,TC;THOMASSEN 3047158302 | 2 | EA | 3 | 2 | 0 | 2 | EA | 28.10 - SOH @ AA02 | Supply for Order 100086237, Item 1 cannot be changed 90025082 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016893 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124185 | 90025082 | 05 | Preparation | 0000272411 | 1 | 0 | EA | 102000000032153 | 102000000027504 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-25 | IDST-0180124185 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-28 | 2 |  | 2025-02-11 | 4900234104_2025_0001 | 2025-03-01 | 124TE133/165 |  | 0 | 2 | 0 | 90025082 | 0 | 0 | 180124185 | 2 | 0 | 0 | X | L | 4900234104 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007429 | INSTRUMENT,TC;THOMASSEN 3047158302 | 2024-10-25 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025082_0010 |  |  | DG1 |  | A2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267110 | S002 | 30 | 30 | 5300016893 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272411 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2760 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007429 | INSTRUMENT,TC;THOMASSEN 3047158302 | 4 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 404 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007429 | INSTRUMENT,TC;THOMASSEN 3047158302 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3110 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007429 | INSTRUMENT,TC;THOMASSEN 3047158302 | 1 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 589 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | compinlet |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007429 | INSTRUMENT,TC;THOMASSEN 3047158302 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3140 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007432 | INSTRUMENT,TC;THOMASSEN 2122145513 | 2 | EA | 6 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 592 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007432 | INSTRUMENT,TC;THOMASSEN 2122145513 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-30 | INLEC | 100086118 | 0020 | 0010 | 100086118 | TC Replace Bearing # 1,2,3 (4) 1KT2420 | AA53.124TIA88 | LOOP,ALARM TEMP L/O LOAD T/BRG 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.10.2024) | 10007433 | INSTRUMENT,TC;THOMASSEN 2122145102 | 4 | EA | 4 | 6 | 0 | 4 | EA | 28.10 - SOH @ AA02 | Supply for Order 100086118, Item 1 cannot be changed 90025079 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016890 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025079 | 05 | Preparation | 0000272239 | 1 | 0 | EA | 102000000027500 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-25 | GIST-4900234140_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 4 |  | 2025-02-11 | 4900234140_2025_0001 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025079 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234140 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007433 | INSTRUMENT,TC;THOMASSEN 2122145102 | 2024-10-25 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025079_0010 |  |  | DG1 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000266972 | S002 |  | 30 | 5300016890 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272239 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-30 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086205 | 0020 | 0010 | 100086205 | TC Replace Bearing # 4 (2) 1KT2420 | AA53.124TI87 | LOOP,IND TEMP L/O BRG#4 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.10.2024) | 10007433 | INSTRUMENT,TC;THOMASSEN 2122145102 | 2 | EA | 4 | 6 | 0 | 2 | EA | 28.10 - SOH @ AA02 | Supply for Order 100086205, Item 1 cannot be changed 90025081 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016892 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025081 | 05 | Preparation | 0000272397 | 1 | 0 | EA | 102000000027501 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-25 | GIST-4900234124_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 2 |  | 2025-02-11 | 4900234124_2025_0001 | 2025-03-01 | 124TE85/87 |  | 0 | 2 | 0 | 90025081 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234124 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007433 | INSTRUMENT,TC;THOMASSEN 2122145102 | 2024-10-25 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025081_0010 |  |  | DG1 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267096 | S002 |  | 30 | 5300016892 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272397 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2850 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007433 | INSTRUMENT,TC;THOMASSEN 2122145102 | 5 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 563 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | drain tc |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007433 | INSTRUMENT,TC;THOMASSEN 2122145102 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3240 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007433 | INSTRUMENT,TC;THOMASSEN 2122145102 | 1 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 626 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007433 | INSTRUMENT,TC;THOMASSEN 2122145102 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0380 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007440 | WASHER,SPRG;CS,BELV,THOMASSEN 2231115000 | 6 | EA | 18 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 38 cannot be changed 90028419 item 320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 38 | 0 | EA | 102000000030481 | 102000000030287 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007440 | WASHER,SPRG;CS,BELV,THOMASSEN 2231115000 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0320 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 38 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 330 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0050 | 0070 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 16 | EA | 256 | 0 | 112 | 16 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 7 cannot be changed 90028583 item 70 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 7 | 0 | EA | 102000000031798 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028583_0070 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 |  | 30 | 5300020057 | 70 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0070 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 16 | EA | 256 | 0 | 112 | 16 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 18 cannot be changed 90028584 item 180 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 18 | 0 | EA | 102000000031797 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028584_0180 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 18 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 |  | 30 | 5300020058 | 180 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0150 | 0030 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 16 | EA | 256 | 0 | 112 | 16 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089887, Item 12 cannot be changed 90025037 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 12 | 0 | EA | 102000000031995 | 102000000026581 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Flame Eye |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 2024-10-16 | W |  | 0150 | Mechanical Restoration Post Waterwash | INT | Mechanical Restoration Post Waterwash | 5 | Ready for Release | 90025037_0120 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 |  | 30 | 5300016467 | 120 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0140 | 0020 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 16 | EA | 256 | 0 | 112 | 16 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089888, Item 17 cannot be changed 90025038 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025038 | 05 | Preparation | 0000128157 | 17 | 0 | EA | 102000000032004 | 102000000026582 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025038_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Waterwash |  | 0 | 2 | 0 | 90025038 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 2024-10-16 | W |  | 0140 | Water Wash Turbine | INT | Water Wash Turbine |  | Ready for Release | 90025038_0110 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 |  | 30 | 5300016473 | 110 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0140 | 0020 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 16 | EA | 256 | 0 | 112 | 16 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089889, Item 17 cannot be changed 90025039 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 17 | 0 | EA | 102000000031998 | 102000000026580 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Waterwash |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 2024-10-16 | W |  | 0140 | Water Wash Turbine | INT | Water Wash Turbine |  | Ready for Release | 90025039_0110 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 |  | 30 | 5300016474 | 110 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1910 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 14 | EA | 256 | 0 | 112 | 14 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 271 cannot be changed 90028419 item 2100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 271 | 0 | EA | 102000000030501 | 102000000031791 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 14 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ONCONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_2100 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 271 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2130 |  |  | 0 | 14 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0800 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 16 | EA | 256 | 0 | 112 | 16 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 637 cannot be changed 90028419 item 4240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 637 | 0 | EA | 102000000030481 | 102000000031792 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007441 | PLATE,LKG;SS,THOMASSEN 2231105500 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_4240 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 637 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4270 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2110 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007455 | RING,PKG;VIT,THOMASSEN 30380022012 | 2 | EA | 7 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 291 cannot be changed 90028419 item 2250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 291 | 0 | EA | 102000000030491 | 102000000030478 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007455 | RING,PKG;VIT,THOMASSEN 30380022012 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2250 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 291 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2280 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2160 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007456 | RING,PKG;VIT,THOMASSEN 2372118800 | 2 | EA | 23 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 295 cannot be changed 90028419 item 2290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 295 | 0 | EA | 102000000030491 | 102000000030479 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007456 | RING,PKG;VIT,THOMASSEN 2372118800 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2290 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 295 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2320 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007457 | RING,PKG;VIT,THOMASSEN 2372119000 | 2 | EA | 6 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 297 cannot be changed 90028419 item 2310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 297 | 0 | EA | 102000000030491 | 102000000030477 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007457 | RING,PKG;VIT,THOMASSEN 2372119000 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2310 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 297 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2340 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2170 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007458 | RING,PKG;VIT,THOMASSEN 2372119100 | 1 | EA | 6 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 296 cannot be changed 90028419 item 2300 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 296 | 0 | EA | 102000000030491 | 102000000030308 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2300 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007458 | RING,PKG;VIT,THOMASSEN 2372119100 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2300 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 296 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2330 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2190 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007459 | RING,PKG;THOMASSEN 2372119300 | 2 | EA | 7 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 298 cannot be changed 90028419 item 2320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 298 | 0 | EA | 102000000030491 | 102000000030510 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007459 | RING,PKG;THOMASSEN 2372119300 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2320 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 298 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2350 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2200 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007460 | RING,PKG;VIT,THOMASSEN 2372119400 | 3 | EA | 8 | 0 | 0 | 3 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 299 cannot be changed 90028419 item 2330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 299 | 0 | EA | 102000000030491 | 102000000030623 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007460 | RING,PKG;VIT,THOMASSEN 2372119400 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2330 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 299 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2360 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2490 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007462 | RING,PKG;VIT,THOMASSEN 2372119600 | 1 | EA | 5 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 709 cannot be changed 90028419 item 4740 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 709 | 0 | EA | 102000000030491 | 102000000030559 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007462 | RING,PKG;VIT,THOMASSEN 2372119600 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_4740 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 709 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4780 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2650 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007493 | SENSOR,THOMASSEN M5352B,VIBRATE,5485C.06 | 4 | EA | 31 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 393 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007493 | SENSOR,THOMASSEN M5352B,VIBRATE,5485C.06 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147115 | 0020 | 0010 | 200147115 | 3Y F/T SIF 1K/KT2420 TXDCR Replace (4) 1 | AA53.124YE012A | TXDCR,VIBRATION BRG 1 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10007493 | SENSOR,THOMASSEN M5352B,VIBRATE,5485C.06 | 4 | EA | 31 | 4 | 2 | 4 | EA | 31.10 - SOH @ AA02 | Supply for Order 200147115, Item 1 cannot be changed 90025086 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017061 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124183 | 90025086 | 05 | Preparation | 0000235386 | 1 | 0 | EA | 102000000032162 | 102000000029885 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-29 | IDST-0180124183 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-22 | 4 |  | 2025-02-11 | 4900234068_2025_0001 | 2025-03-01 | 124YE012A |  | 0 | 2 | 0 | 90025086 | 0 | 0 | 180124183 | 2 | 0 | 0 | X | L | 4900234068 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007493 | SENSOR,THOMASSEN M5352B,VIBRATE,5485C.06 | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025086_0010 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232429 | S002 |  | 30 | 5300017061 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235386 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Released/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2660 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007494 | REPAIR KIT;MOD,VIB SENS,NP SMO1433098 | 4 | KIT | 35 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | KIT | [5 empty] | 05 | Preparation | 0000129822 | 394 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007494 | REPAIR KIT;MOD,VIB SENS,NP SMO1433098 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147115 | 0020 | 0020 | 200147115 | 3Y F/T SIF 1K/KT2420 TXDCR Replace (4) 1 | AA53.124YE012A | TXDCR,VIBRATION BRG 1 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10007494 | REPAIR KIT;MOD,VIB SENS,NP SMO1433098 | 4 | KIT | 35 | 4 | 1 | 4 | KIT | 31.10 - SOH @ AA02 | Supply for Order 200147115, Item 2 cannot be changed 90025086 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017061 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180124183 | 90025086 | 05 | Preparation | 0000235386 | 2 | 0 | KIT | 102000000032162 | 102000000029430 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-29 | IDST-0180124183 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-22 | 4 |  | 2025-02-11 | 4900234068_2025_0003 | 2025-03-01 | 124YE012A |  | 0 | 2 | 0 | 90025086 | 0 | 0 | 180124183 | 2 | 0 | 0 | X | L | 4900234068 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007494 | REPAIR KIT;MOD,VIB SENS,NP SMO1433098 | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025086_0020 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232429 | S002 | 30 | 30 | 5300017061 | 20 |  |  | 0 | 4 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235386 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Released/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2450 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007507 | NUT,HEX;0.375"-16 UNC,SS,NP FFE64609 | 32 | EA | 12 | 0 | 0 | 12 | EA | 10.12 - ETA 23.03.25 PO 4500031502 MOT30655 GS4945892 62.8kg 72x57x74cm | Supply for Order 200091513, Item 372 cannot be changed 90028419 item 2800 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 372 | 0 | EA | 102000000030385 | 102000000030196 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2800 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007507 | NUT,HEX;0.375"-16 UNC,SS,NP FFE64609 | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_2800 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 372 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2830 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2460 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007508 | NUT,HEX;0.500"-13 UNC,SS,NP FFE64612 | 56 | EA | 12 | 0 | 0 | 12 | EA | 15.10 - ETA 18.03.25 PO 4500031516 BH | Supply for Order 200091513, Item 373 cannot be changed 90028419 item 2810 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 373 | 0 | EA | 102000000030385 | 102000000030199 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 56 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2810 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007508 | NUT,HEX;0.500"-13 UNC,SS,NP FFE64612 | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_2810 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 373 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2840 |  |  | 0 | 56 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007512 | WASHER,THR;NP RRZ41581 | 32 | EA | 32 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 184 cannot be changed 90028419 item 1400 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 184 | 0 | EA | 102000000030498 | 102000000030362 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1400 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007512 | WASHER,THR;NP RRZ41581 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1400 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 184 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1430 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1110 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007513 | HELICOIL,LKG;NP RFR331490000 | 20 | EA | 84 | 0 | 0 | 20 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 484 cannot be changed 90028419 item 3400 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 484 | 0 | EA | 102000000030487 | 102000000030071 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3400 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007513 | HELICOIL,LKG;NP RFR331490000 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3400 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 484 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3430 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007517 | WASHER;NP FLD025007016 | 31 | EA | 62 | 0 | 0 | 31 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 133 cannot be changed 90028419 item 1070 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1080 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 133 | 0 | EA | 102000000030480 | 102000000030283 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007517 | WASHER;NP FLD025007016 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1070 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 133 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1080 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007518 | SPACER;NP SMR40063 | 18 | EA | 38 | 0 | 0 | 18 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 131 cannot be changed 90028419 item 1050 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1060 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 131 | 0 | EA | 102000000030480 | 102000000030664 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007518 | SPACER;NP SMR40063 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1050 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 131 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1060 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007519 | SPACER;NP SMR40062 | 31 | EA | 62 | 0 | 0 | 31 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 126 cannot be changed 90028419 item 1000 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1010 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 126 | 0 | EA | 102000000030480 | 102000000030663 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1000 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007519 | SPACER;NP SMR40062 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1000 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 126 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1010 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2480 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007520 | COUPLING;NP RGO33867 | 1 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 360 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007520 | COUPLING;NP RGO33867 |  |  |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0450 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007521 | BLADE,TURB/SET;NP SMO0834127 | 1 | SET | 2 | 0 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 463 cannot be changed 90028419 item 3250 already exists | Material picked; currently at 30-03-08-80A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3280 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 463 | 0 | SET |  |  | 102000000033270 |  |  |  |  | WorkPackLink | 30-03-08-80A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007521 | BLADE,TURB/SET;NP SMO0834127 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3250 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 463 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3280 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0720 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007524 | BOLT;NP RPQ32589 | 6 | EA | 6 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 80 cannot be changed 90028419 item 630 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 80 | 0 | EA | 102000000030502 | 102000000030246 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0630 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007524 | BOLT;NP RPQ32589 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0630 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 80 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 640 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0730 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007525 | BOLT,CLP,PIGNONE MS3002,TRANS PCE ARG | 4 | EA | 10 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 81 cannot be changed 90028419 item 640 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 81 | 0 | EA | 102000000030502 | 102000000030243 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0640 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007525 | BOLT,CLP,PIGNONE MS3002,TRANS PCE ARG | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0640 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 81 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 650 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0900 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | No issue identified | 10007526 | ELBOW,COMB;NP SMU8315882 | -2 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000129822 | 735 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007526 | ELBOW,COMB;NP SMU8315882 |  |  |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 3290 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.10.2024) | 10007526 | ELBOW,COMB;NP SMU8315882 | 2 | EA | 0 | 0 | 0 | 0 |  | 30.12 - ETA 16.04.25 PO W451776523 NP FCA | Supply for Order 200091513, Item 767 cannot be changed 90028419 item 4870 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4910 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90028419 | 05 | Preparation | 0000129822 | 767 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4870 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007526 | ELBOW,COMB;NP SMU8315882 | 2024-10-02 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_4870 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 767 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4910 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0910 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | No issue identified | 10007527 | ELBOW,COMB;NP SMU8315883 | -4 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000129822 | 736 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007527 | ELBOW,COMB;NP SMU8315883 |  |  |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 3280 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Shipped qty below requirement qty | 10007527 | ELBOW,COMB;NP SMU8315883 | 4 | EA | 0 | 0 | 2 | 2 | EA | 30.12 - ETA 16.04.25 PO W451776523 NP FCA | Supply for Order 200091513, Item 766 cannot be changed 90028419 item 4860 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4900 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  | 180129773 | 9028210 | 05 | Preparation | 0000129822 | 766 | 0 | EA |  |  | 102000000033821 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R6FL |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | GRST-5000418238_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000059235 | 1020 | 2025-07-03 | 2 |  | 2025-02-26 | 4900249734_2025_0001 | 2025-03-01 |  | 5000418238_2025_0001 | 0 | 2 | 0 | 90028419 | 2 | 0 | 180129773/180129773 | 1 | 0 | 0 | X | L | 4900249734 | 2025 |  | 5000418238 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007527 | ELBOW,COMB;NP SMU8315883 | 2024-10-02 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_4860/9028210_0090_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 766 |  | 0 |  | 25SD2420 | MJ | 1000005251 | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4900 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-27 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0450 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007529 | BOLT,HEX;ALLOY ST,NP GQF15095 | 96 | EA | 192 | 0 | 0 | 96 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 45 cannot be changed 90028419 item 370 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 45 | 0 | EA | 102000000030988 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 96 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0370 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007529 | BOLT,HEX;ALLOY ST,NP GQF15095 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0370 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 45 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 380 |  |  | 0 | 96 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2500 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007531 | SCREW,HEX;SS,NP GQL12031 | 56 | EA | 168 | 0 | 0 | 56 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 377 cannot be changed 90028419 item 2840 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 377 | 0 | EA | 102000000030385 | 102000000031117 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 56 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007531 | SCREW,HEX;SS,NP GQL12031 | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_2840 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 377 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2870 |  |  | 0 | 56 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1980 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007531 | SCREW,HEX;SS,NP GQL12031 | 56 | EA | 168 | 0 | 0 | 56 | EA | 31.01 - SOH @ AA01 | Supply for Order 200091513, Item 701 cannot be changed 90028419 item 4660 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4700 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 701 | 0 | EA | 102000000030389 | 101000000142121 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 56 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007531 | SCREW,HEX;SS,NP GQL12031 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_4660 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 701 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4700 |  |  | 0 | 56 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1880 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007532 | SCREW,CAP,HEX;ALLOY ST,NP GTG25063 | 6 | EA | 10 | 0 | 0 | 2 | EA | 24.02 - SOH @ AA02 | Supply for Order 200091513, Item 255 cannot be changed 90028419 item 1960 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 255 | 0 | EA | 102000000030389 | 101000000142542 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1960 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007532 | SCREW,CAP,HEX;ALLOY ST,NP GTG25063 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1960 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 255 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1990 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1880 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007532 | SCREW,CAP,HEX;ALLOY ST,NP GTG25063 | 6 | EA | 10 | 0 | 0 | 4 | EA | 24.02 - SOH @ AA02 | Supply for Order 200091513, Item 255 cannot be changed 90028419 item 1960 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 255 | 0 | EA | 102000000030389 | 102000000030237 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1960 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007532 | SCREW,CAP,HEX;ALLOY ST,NP GTG25063 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1960 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 255 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1990 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007532 | SCREW,CAP,HEX;ALLOY ST,NP GTG25063 | 2 | EA | 10 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 557 cannot be changed 90028419 item 4020 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4050 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 557 | 0 | EA | 102000000030385 | 102000000034123 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007532 | SCREW,CAP,HEX;ALLOY ST,NP GTG25063 | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_4020 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 557 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4050 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2470 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007535 | BOLT,HEX;0.375"X40MM,SS,16UN | 32 | EA | 17 | 0 | 0 | 17 | EA | 10.12 - ETA 23.03.25 PO 4500031502 MOT 30655 | Supply for Order 200091513, Item 374 cannot be changed 90028419 item 2820 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 374 | 0 | EA | 102000000030385 | 102000000030247 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2820 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007535 | BOLT,HEX;0.375"X40MM,SS,16UN | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_2820 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 374 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2850 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0740 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007536 | BOLT,HEX;SS,NP GTL12114 | 4 | EA | 14 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 82 cannot be changed 90028419 item 650 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 82 | 0 | EA | 102000000030502 | 102000000030255 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0650 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007536 | BOLT,HEX;SS,NP GTL12114 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0650 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 82 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 660 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0960 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007538 | SCREW,CAP;ALLOY ST,NP HEF25101 | 6 | EA | 10 | 0 | 0 | 6 | EA | 13.01 - SOH @ AA02 | Supply for Order 200091513, Item 111 cannot be changed 90028419 item 880 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 111 | 0 | EA | 102000000030487 | 102000000030929 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0880 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007538 | SCREW,CAP;ALLOY ST,NP HEF25101 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0880 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 111 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 890 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0540 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007539 | SCREW,CAP;ALLOY ST,NP HEH19063 | 20 | EA | 50 | 0 | 0 | 20 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 673 cannot be changed 90028419 item 4510 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 673 | 0 | EA | 102000000030386 | 102000000031128 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4510 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007539 | SCREW,CAP;ALLOY ST,NP HEH19063 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_4510 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 673 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4540 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1440 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007539 | SCREW,CAP;ALLOY ST,NP HEH19063 | 2 | EA | 50 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 622 cannot be changed 90028419 item 4180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 622 | 0 | EA | 102000000030480 | 102000000031127 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007539 | SCREW,CAP;ALLOY ST,NP HEH19063 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_4180 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 622 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4210 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1700 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007539 | SCREW,CAP;ALLOY ST,NP HEH19063 | 8 | EA | 50 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 237 cannot be changed 90028419 item 1800 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 237 | 0 | EA | 102000000030497 | 102000000031126 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1800 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007539 | SCREW,CAP;ALLOY ST,NP HEH19063 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1800 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 237 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1830 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0070 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007540 | SCREW,CAP;ALLOY ST,NP HEH19076 | 10 | EA | 21 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 6 cannot be changed 90028419 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 6 | 0 | EA | 102000000030489 | 102000000031129 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007540 | SCREW,CAP;ALLOY ST,NP HEH19076 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0080 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 90 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0830 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007541 | SCREW,CAP;ALLOY ST,NP HEH19082 | 27 | EA | 54 | 0 | 0 | 27 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 98 cannot be changed 90028419 item 760 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 98 | 0 | EA | 102000000030487 | 102000000031154 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 27 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0760 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007541 | SCREW,CAP;ALLOY ST,NP HEH19082 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0760 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 98 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 770 |  |  | 0 | 27 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0920 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007542 | SCREW,CAP;ALLOY ST,NP HEH19152 | 2 | EA | 10 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 107 cannot be changed 90028419 item 850 already exists | Material picked; currently at SW3R01H02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 107 | 0 | EA |  |  | 102000000033974 |  |  |  |  | WorkPackLink | SW3R01H02B |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0850 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007542 | SCREW,CAP;ALLOY ST,NP HEH19152 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0850 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 107 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 860 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0530 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007543 | SCREW,CAP;ALLOY ST,NP HEH25038 | 12 | EA | 25 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 672 cannot be changed 90028419 item 4500 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 672 | 0 | EA | 102000000030386 | 102000000031075 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4500 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007543 | SCREW,CAP;ALLOY ST,NP HEH25038 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_4500 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 672 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4530 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0700 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007544 | SCREW,CAP;ALLOY ST,NP HEH25095 | 1 | EA | 9 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 471 cannot be changed 90028419 item 3300 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 471 | 0 | EA | 102000000030481 | 102000000031130 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3300 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007544 | SCREW,CAP;ALLOY ST,NP HEH25095 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3300 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 471 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3330 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1840 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007545 | SCREW,SELF TAP;SS304,NP HVA48160 | 8 | EA | 16 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 251 cannot be changed 90028419 item 1920 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1950 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 251 | 0 | EA | 102000000030389 | 102000000030820 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1920 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007545 | SCREW,SELF TAP;SS304,NP HVA48160 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1920 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 251 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1950 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1690 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007546 | SCREW,CAP;ALLOY ST,NP HYC070619076 | 6 | EA | 18 | 0 | 0 | 3 | EA | 02.03 - SOH @ AA02 | Supply for Order 200091513, Item 510 cannot be changed 90028419 item 3660 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 510 | 0 | EA | 102000000030498 | 102000000030835 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007546 | SCREW,CAP;ALLOY ST,NP HYC070619076 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_3660 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 510 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3690 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1430 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007546 | SCREW,CAP;ALLOY ST,NP HYC070619076 | 6 | EA | 18 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 185 cannot be changed 90028419 item 1410 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 185 | 0 | EA | 102000000030498 | 102000000030834 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1410 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007546 | SCREW,CAP;ALLOY ST,NP HYC070619076 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1410 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 185 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1440 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0750 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007547 | SCREW,CAP,HEX;ALLOY ST,NP GTJ12038 | 10 | EA | 21 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 88 cannot be changed 90028419 item 710 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 88 | 0 | EA | 102000000030492 | 102000000030817 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0710 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007547 | SCREW,CAP,HEX;ALLOY ST,NP GTJ12038 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0710 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 88 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 720 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0800 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007550 | SCREW,CAP;ALLOY ST,NP HED15050 | 16 | EA | 16 | 0 | 0 | 0 |  | 07.02 - ETA 01.04.25 PO 4500031515 x 128 MOT 30655 GS4949926 157.4kg 150x75x70cm | Supply for Order 200091513, Item 683 cannot be changed 90028419 item 4550 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 683 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007550 | SCREW,CAP;ALLOY ST,NP HED15050 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_4550 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 683 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4580 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0790 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007550 | SCREW,CAP;ALLOY ST,NP HED15050 | 16 | EA | 16 | 0 | 0 | 16 | EA | 27.02 - SOH @ AA02 | Supply for Order 200091513, Item 636 cannot be changed 90028419 item 4230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 636 | 0 | EA | 102000000030481 | 102000000030235 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007550 | SCREW,CAP;ALLOY ST,NP HED15050 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_4230 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 636 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4260 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0630 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007551 | SCREW,CAP;NP HED15076 | 68 | EA | 136 | 0 | 0 | 65 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 71 cannot be changed 90028419 item 550 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 71 | 0 | EA | 102000000031121 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 68 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007551 | SCREW,CAP;NP HED15076 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0550 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 71 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 560 |  |  | 0 | 68 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0720 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007552 | SCREW,CAP;ALLOY ST,NP HYV290615127 | 4 | EA | 5 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 85 cannot be changed 90028419 item 680 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 85 | 0 | EA | 102000000030492 | 102000000030819 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0680 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007552 | SCREW,CAP;ALLOY ST,NP HYV290615127 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0680 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 85 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 690 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1430 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007553 | SCREW,CAP;ASTM A 437 B4B,NP HEK19063 | 18 | EA | 36 | 0 | 0 | 18 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 502 cannot be changed 90028419 item 3580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 502 | 0 | EA | 102000000030480 | 102000000031120 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007553 | SCREW,CAP;ASTM A 437 B4B,NP HEK19063 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_3580 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 502 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3610 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0640 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007554 | SCREW,CAP,SKT;135X19MM,NP HYV290619114 | 12 | EA | 24 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 72 cannot be changed 90028419 item 560 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 72 | 0 | EA | 102000000030502 | 102000000031119 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007554 | SCREW,CAP,SKT;135X19MM,NP HYV290619114 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0560 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 72 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 570 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0610 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007556 | SCREW,CAP,HEX;ASTM A 437 B4B,NP GTH09034 | 6 | EA | 12 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 69 cannot be changed 90028419 item 530 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 69 | 0 | EA | 102000000030502 | 102000000030816 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0530 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007556 | SCREW,CAP,HEX;ASTM A 437 B4B,NP GTH09034 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0530 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 69 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 540 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0620 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007557 | BOLT,12 PNT;ALLOY ST,NP GFY31114 | 22 | EA | 16 | 0 | 0 | 16 | EA | 07.02 - ETA 01.04.25 PO 4500031502 x 22 MOT 30655 GS4945892 62.6kg 72x57x74cm | Supply for Order 200091513, Item 70 cannot be changed 90028419 item 540 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 70 | 0 | EA | 102000000030989 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 22 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0540 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007557 | BOLT,12 PNT;ALLOY ST,NP GFY31114 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0540 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 70 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 550 |  |  | 0 | 22 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0860 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007558 | PLUG,SQ;CS,0.250" NPT,NP JLE03013 | 22 | EA | 357 | 0 | 0 | 22 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 101 cannot be changed 90028419 item 790 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 101 | 0 | EA | 102000000030487 | 102000000030911 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 22 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0790 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007558 | PLUG,SQ;CS,0.250" NPT,NP JLE03013 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0790 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 101 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 800 |  |  | 0 | 22 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2110 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007558 | PLUG,SQ;CS,0.250" NPT,NP JLE03013 | 22 | EA | 357 | 0 | 0 | 22 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 707 cannot be changed 90028419 item 4720 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 707 | 0 | EA | 102000000030501 | 102000000030913 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 22 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4720 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007558 | PLUG,SQ;CS,0.250" NPT,NP JLE03013 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_4720 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 707 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4760 |  |  | 0 | 22 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0380 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007558 | PLUG,SQ;CS,0.250" NPT,NP JLE03013 | 8 | EA | 357 | 0 | 0 | 8 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 35 cannot be changed 90028419 item 310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 35 | 0 | EA | 102000000030386 | 102000000030917 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007558 | PLUG,SQ;CS,0.250" NPT,NP JLE03013 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0310 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 35 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 320 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007559 | GASKET;C4500,KLINGER 0WOO10007559 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 345 cannot be changed 90028419 item 2670 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2700 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 345 | 0 | EA | 102000000030495 | 102000000030655 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007559 | GASKET;C4500,KLINGER 0WOO10007559 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2670 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 345 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2700 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0650 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007560 | GASKET;C4500,KLINGER 0WOO10007560 | 4 | EA | 95 | 0 | 0 | 4 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 73 cannot be changed 90028419 item 570 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 73 | 0 | EA | 102000000030502 | 102000000030610 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0570 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007560 | GASKET;C4500,KLINGER 0WOO10007560 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0570 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 73 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 580 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007561 | PACKING ASY,DISCH CSG;NP KFZ326830324 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 19 cannot be changed 90028419 item 180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 19 | 0 | EA | 102000000030386 | 102000000030111 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007561 | PACKING ASY,DISCH CSG;NP KFZ326830324 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0180 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 19 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2310 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007566 | GASKET;NP KFZ326820604 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 343 cannot be changed 90028419 item 2650 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 343 | 0 | EA | 102000000030495 | 102000000030085 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2650 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007566 | GASKET;NP KFZ326820604 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2650 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 343 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2680 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0710 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007568 | GASKET;NP KFZ326810004 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 200091513, Item 472 cannot be changed 90028419 item 3310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 472 | 0 | EA | 101000000143915 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007568 | GASKET;NP KFZ326810004 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3310 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 472 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3340 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2320 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007573 | GASKET;KLINGERSIL C4500,NP KFZ287170604 | 1 | EA | 5 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 344 cannot be changed 90028419 item 2660 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 344 | 0 | EA | 102000000030601 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007573 | GASKET;KLINGERSIL C4500,NP KFZ287170604 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2660 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 344 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2690 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007582 | SEAL,PIPE,DRN;VIT A,NP KFZ320720904 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 283 cannot be changed 90028419 item 2190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 283 | 0 | EA | 102000000030491 | 102000000030631 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007582 | SEAL,PIPE,DRN;VIT A,NP KFZ320720904 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2190 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 283 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2220 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007584 | SEAL,PIPE,DRN;VIT A,NP KFZ321130904 | 4 | EA | 25 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 284 cannot be changed 90028419 item 2200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 284 | 0 | EA | 102000000030491 | 102000000030471 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007584 | SEAL,PIPE,DRN;VIT A,NP KFZ321130904 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2200 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 284 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2230 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2010 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007586 | SEAL,CPLG,TOP;VIT A,NP KFZ195620904 | 1 | EA | 24 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 281 cannot be changed 90028419 item 2180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 281 | 0 | EA | 102000000030491 | 102000000030305 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007586 | SEAL,CPLG,TOP;VIT A,NP KFZ195620904 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2180 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 281 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2210 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007590 | BEARING,THR;NP SM037701 | 1 | ASY | 1 | 0 | 1 | 1 | ASY | 16.12 - qty 1 SOH @ AA02 | Supply for Order 200091513, Item 11 cannot be changed 9027133 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180124227 | 9027133 | 05 | Preparation | 0000129822 | 11 | 0 | ASY |  |  | 102000000030732 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000396329_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056768 | 1020 | 2025-07-03 | 1 |  | 2025-02-11 | 4900234167_2025_0001 | 2025-03-01 |  | 5000396329_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180124227 | 2 | 0 | 0 | X | L | 4900234167 | 2025 |  | 5000396329 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007590 | BEARING,THR;NP SM037701 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 9027133_0100 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 110 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0242 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10007593 | HELICOIL,LKG;NP RFR330070000 | 18 | EA | 260 | 0 | 0 | 18 | EA | 24.09 - SOH at AA02 | Supply for Order 200091126, Item 120 cannot be changed 90023534 item 680 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 120 | 0 | EA | 102000000030443 | 102000000030072 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0680 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007593 | HELICOIL,LKG;NP RFR330070000 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0680 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 120 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 970 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0110 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007593 | HELICOIL,LKG;NP RFR330070000 | 16 | EA | 260 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 10 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007593 | HELICOIL,LKG;NP RFR330070000 |  |  |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2480 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007594 | HELICOIL,LKG;NP RFR330950000 | 56 | EA | 68 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 375 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 56 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007594 | HELICOIL,LKG;NP RFR330950000 |  |  |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1170 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007595 | HELICOIL,LKG;NP RFU330070060 | 1 | EA | 807 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 490 cannot be changed 90028419 item 3460 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 490 | 0 | EA | 102000000030487 | 102000000030073 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007595 | HELICOIL,LKG;NP RFU330070060 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3460 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 490 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3490 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0880 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007596 | HELICOIL,LKG;NP RFU331180060 | 2 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 482 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007596 | HELICOIL,LKG;NP RFU331180060 |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1620 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007597 | JOINT,BALL;NP RGO07014 | 1 | EA | 64 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 203 cannot be changed 90028419 item 1580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 203 | 0 | EA | 102000000030498 | 102000000030099 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007597 | JOINT,BALL;NP RGO07014 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1580 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 203 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1610 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1240 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007601 | CLAMP;NP RGR00035 | 4 | EA | 8 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 147 cannot be changed 90028419 item 1120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 147 | 0 | EA | 102000000030480 | 102000000030065 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007601 | CLAMP;NP RGR00035 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1120 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 147 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1130 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1260 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007608 | SPRING,COMP;SS302,NP RMR09363 | 32 | EA | 64 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 168 cannot be changed 90028419 item 1260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 168 | 0 | EA | 102000000030119 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007608 | SPRING,COMP;SS302,NP RMR09363 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1260 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 168 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1290 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0340 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007609 | NOZZLE;SS,NP RPO08133 | 4 | EA | 2 | 0 | 0 | 2 | EA | 21.10 - ETA 01.10.25 PO 4500031834 BH QTY 2 | Supply for Order 200091513, Item 670 cannot be changed 90028419 item 4480 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 670 | 0 | EA | 102000000030489 | 102000000030598 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4480 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007609 | NOZZLE;SS,NP RPO08133 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_4480 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 670 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  |  | 5300013090 | 4510 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1070 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007612 | PLUG,BORESCOPE;ALLOY ST,NP RTR04121 | 1 | EA | 7 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 122 cannot be changed 90028419 item 960 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 122 | 0 | EA | 102000000030487 | 102000000030912 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0960 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007612 | PLUG,BORESCOPE;ALLOY ST,NP RTR04121 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0960 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 122 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 970 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007613 | PIN,THD END;NP RPQ02256 | 4 | EA | 71 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 148 cannot be changed 90028419 item 1130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 148 | 0 | EA | 102000000030480 | 102000000030183 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007613 | PIN,THD END;NP RPQ02256 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1130 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 148 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1140 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1450 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007615 | PIN,AIR INL;NP RPQ02662 | 6 | EA | 14 | 0 | 0 | 4 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 692 cannot be changed 90028419 item 4600 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 692 | 0 | EA | 102000000030480 | 102000000030162 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4600 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007615 | PIN,AIR INL;NP RPQ02662 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_4600 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 692 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4640 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0240 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007615 | PIN,AIR INL;NP RPQ02662 | 4 | EA | 14 | 0 | 0 | 4 | EA | 15.01 - KSF Work-Packed | Supply for Order 200091513, Item 457 cannot be changed 90028419 item 3190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 457 | 0 | EA | 102000000030489 | 102000000029868 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007615 | PIN,AIR INL;NP RPQ02662 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_3190 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 457 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3220 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1450 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007615 | PIN,AIR INL;NP RPQ02662 | 6 | EA | 14 | 0 | 0 | 2 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 692 cannot be changed 90028419 item 4600 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 692 | 0 | EA | 102000000030480 | 102000000034122 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4600 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007615 | PIN,AIR INL;NP RPQ02662 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_4600 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 692 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4640 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1200 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007617 | PIN,DOWEL;NP RPR01838 | 6 | EA | 12 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 143 cannot be changed 90028419 item 1110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 143 | 0 | EA | 102000000030480 | 102000000030163 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007617 | PIN,DOWEL;NP RPR01838 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1110 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 143 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1120 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1310 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007618 | WASHER,SPRG;28.5X16.3X1.18MM,NP RRQ40125 | 32 | EA | 32 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 173 cannot be changed 90028419 item 1300 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 173 | 0 | EA | 102000000030498 | 102000000030288 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1300 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007618 | WASHER,SPRG;28.5X16.3X1.18MM,NP RRQ40125 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1300 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 173 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1330 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007619 | WASHER,RET;28MM ODX3MM THK,NP RRR40124 | 32 | PAA | 33 | 0 | 0 | 32 | PAA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 175 cannot be changed 90028419 item 1310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1340 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 175 | 0 | PAA | 102000000030498 | 102000000030368 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007619 | WASHER,RET;28MM ODX3MM THK,NP RRR40124 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1310 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 175 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1340 |  |  | 0 | 32 | PAA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086265 | 0020 | 0050 | 100086265 | WS TC & Cable Replace (8) 1KT2420 | AA53.124TI1671 | LOOP,IND TEMP TURB WHEEL 1 AFT 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10007621 | INSTRUMENT,TC;K,1290MM,NP RTO876260037 | 2 | EA | 16 | 2 | 0 | 2 | EA | 25.10 - SOH @ AA02 | Supply for Order 100086265, Item 5 cannot be changed 90025078 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016830 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027126 | 05 | Preparation | 0000272424 | 5 | 0 | EA | 102000000031665 | 102000000029966 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-24 | GIST-4900234132_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 2 |  | 2025-02-11 | 4900234132_2025_0007 | 2025-03-01 | 124TI1691/92 |  | 0 | 2 | 0 | 90025078 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234132 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007621 | INSTRUMENT,TC;K,1290MM,NP RTO876260037 | 2024-10-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027126_0050 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267124 | S002 |  | 30 | 5300016830 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272424 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2690 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007621 | INSTRUMENT,TC;K,1290MM,NP RTO876260037 | 10 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 397 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124TI1691/92 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007621 | INSTRUMENT,TC;K,1290MM,NP RTO876260037 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086265 | 0020 | 0010 | 100086265 | WS TC & Cable Replace (8) 1KT2420 | AA53.124TI1671 | LOOP,IND TEMP TURB WHEEL 1 AFT 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10007622 | INSTRUMENT,TC;NP RTO876260176 | 2 | EA | 1 | 2 | 0 | 2 | EA | 25.10 - SOH @ AA02 | Supply for Order 100086265, Item 1 cannot be changed 90025078 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016830 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027126 | 05 | Preparation | 0000272424 | 1 | 0 | EA | 102000000031665 | 102000000029971 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-24 | GIST-4900234132_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 2 |  | 2025-02-11 | 4900234132_2025_0001 | 2025-03-01 | 124TE1681/82 |  | 0 | 2 | 0 | 90025078 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234132 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007622 | INSTRUMENT,TC;NP RTO876260176 | 2024-10-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027126_0010 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267124 | S002 |  | 30 | 5300016830 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272424 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2700 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007622 | INSTRUMENT,TC;NP RTO876260176 | 3 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 398 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124TI1681/82 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007622 | INSTRUMENT,TC;NP RTO876260176 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086241 | 0020 | 0010 | 100086241 | Com Disch TC Replace (2) 1KT2420 | AA53.124TE36 | TXDCR,TEMP 1K2420 DISCH TEMP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10007623 | INSTR:TC;NP RTO876260038 | 2 | EA | 0 | 0 | 0 | 0 |  | 06.01 - ETA 08.04.25 PO 4500038049 BH FCA | Supply for Order 100086241, Item 1 cannot be changed 90025077 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016829 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025077 | 05 | Preparation | 0000272293 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-24 | ODST-0090025077_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124TE34/5 |  | 0 | 2 | 0 | 90025077 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007623 | INSTR:TC;NP RTO876260038 | 2024-10-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025077_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267030 | S002 | 30 | 30 | 5300016829 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272293 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3150 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007623 | INSTR:TC;NP RTO876260038 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 593 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | comp disch |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007623 | INSTR:TC;NP RTO876260038 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086241 | 0020 | 0020 | 100086241 | Com Disch TC Replace (2) 1KT2420 | AA53.124TE36 | TXDCR,TEMP 1K2420 DISCH TEMP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10007624 | INSTRUMENT,TC;NP RTO28649 | 2 | EA | 0 | 5 | 0 | 2 | EA | 28.10 - SOH @ AA02 | Supply for Order 100086241, Item 2 cannot be changed 90025077 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016829 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027122 | 05 | Preparation | 0000272293 | 2 | 0 | EA | 102000000032141 | 102000000029963 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-24 | GIST-4900234107_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 2 |  | 2025-02-11 | 4900234107_2025_0001 | 2025-03-01 | 124TE34/5 |  | 0 | 2 | 0 | 90025077 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234107 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007624 | INSTRUMENT,TC;NP RTO28649 | 2024-10-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027122_0020 |  |  | DG1 |  | A2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267030 | S002 |  | 30 | 5300016829 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272293 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086265 | 0020 | 0040 | 100086265 | WS TC & Cable Replace (8) 1KT2420 | AA53.124TI1671 | LOOP,IND TEMP TURB WHEEL 1 AFT 1KT2420 | AA01 | 10 | Shipped qty below requirement qty | 10007624 | INSTRUMENT,TC;NP RTO28649 | 2 | EA | 0 | 5 | 0 | 1 | EA | 20.12 - ETA 09.04.25 PO 4500032876 NP FCA | Supply for Order 100086265, Item 4 cannot be changed 90025078 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016830 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027126 | 05 | Preparation | 0000272424 | 4 | 0 | EA | 102000000031665 | 102000000029965 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-24 | GIST-4900234132_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 1 |  | 2025-02-11 | 4900234132_2025_0005 | 2025-03-01 | 124TI1701/02 |  | 0 | 2 | 0 | 90025078 | 0 | 0 |  | 1 | 0 | 0 | X | L | 4900234132 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007624 | INSTRUMENT,TC;NP RTO28649 | 2024-10-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025078_0040/9027126_0040 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267124 | S002 |  | 30 | 5300016830 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272424 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086265 | 0020 | 0030 | 100086265 | WS TC & Cable Replace (8) 1KT2420 | AA53.124TI1671 | LOOP,IND TEMP TURB WHEEL 1 AFT 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10007624 | INSTRUMENT,TC;NP RTO28649 | 2 | EA | 0 | 5 | 0 | 2 | EA | 25.10 - SOH @ AA02 | Supply for Order 100086265, Item 3 cannot be changed 90025078 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016830 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027126 | 05 | Preparation | 0000272424 | 3 | 0 | EA | 102000000031665 | 102000000029964 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-24 | GIST-4900234132_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 2 |  | 2025-02-11 | 4900234132_2025_0003 | 2025-03-01 | 124TE1671/72 |  | 0 | 2 | 0 | 90025078 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234132 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007624 | INSTRUMENT,TC;NP RTO28649 | 2024-10-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027126_0030 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267124 | S002 |  | 30 | 5300016830 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272424 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2710 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007624 | INSTRUMENT,TC;NP RTO28649 | 3 | EA | 0 | 0 | 0 | 0 |  | 29.10 - ETA 22.04.25 PO 4500032876 BH |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 399 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124TI1701/02 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007624 | INSTRUMENT,TC;NP RTO28649 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3220 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007624 | INSTRUMENT,TC;NP RTO28649 | 4 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 624 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007624 | INSTRUMENT,TC;NP RTO28649 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086265 | 0020 | 0020 | 100086265 | WS TC & Cable Replace (8) 1KT2420 | AA53.124TI1671 | LOOP,IND TEMP TURB WHEEL 1 AFT 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10007625 | INSTRUMENT,TC;NP RTO876260177 | 2 | EA | 0 | 0 | 0 | 0 |  | 18.11 - ETA 18.02.25 PO 4500034835 BH | Supply for Order 100086265, Item 2 cannot be changed 90025078 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016830 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025078 | 05 | Preparation | 0000272424 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-24 | ODST-0090025078_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124TE1671/72 |  | 0 | 2 | 0 | 90025078 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007625 | INSTRUMENT,TC;NP RTO876260177 | 2024-10-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025078_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267124 | S002 |  | 30 | 5300016830 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272424 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2720 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007625 | INSTRUMENT,TC;NP RTO876260177 | 3 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 400 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124TI1671/72 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007625 | INSTRUMENT,TC;NP RTO876260177 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3190 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007625 | INSTRUMENT,TC;NP RTO876260177 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 597 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124TI1671/72 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007625 | INSTRUMENT,TC;NP RTO876260177 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0590 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007633 | SCREW SET;ALLOY ST,NP HQM910070453 | 2 | EA | 2 | 0 | 0 | 2 | EA | 27.02 - SOH @ AA02 | Supply for Order 200091513, Item 59 cannot be changed 90028419 item 450 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 59 | 0 | EA | 102000000030481 | 102000000030837 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007633 | SCREW SET;ALLOY ST,NP HQM910070453 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0450 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 59 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 460 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0790 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007633 | SCREW SET;ALLOY ST,NP HQM910070453 | 2 | EA | 2 | 0 | 0 | 0 |  | 27.02 - ETA 14.03.25 PO 4500031859 BH FCA | Supply for Order 200091513, Item 682 cannot be changed 90028419 item 4540 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 682 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4540 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007633 | SCREW SET;ALLOY ST,NP HQM910070453 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_4540 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 682 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4570 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0720 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007636 | SCREW SET;ALLOY ST,NP HQM830070453 | 2 | EA | 5 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 473 cannot be changed 90028419 item 3320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 473 | 0 | EA | 102000000030481 | 102000000030838 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007636 | SCREW SET;ALLOY ST,NP HQM830070453 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3320 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 473 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3350 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0280 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007637 | BOLT,HEX;ALLOY ST,NP GTH12025 | 4 | EA | 119 | 0 | 0 | 4 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 664 cannot be changed 90028419 item 4430 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 664 | 0 | EA | 102000000030489 | 102000000030993 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4430 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007637 | BOLT,HEX;ALLOY ST,NP GTH12025 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_4430 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 664 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4460 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0770 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007637 | BOLT,HEX;ALLOY ST,NP GTH12025 | 6 | EA | 119 | 0 | 0 | 6 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 90 cannot be changed 90028419 item 720 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 90 | 0 | EA | 102000000030492 | 102000000030992 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0720 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007637 | BOLT,HEX;ALLOY ST,NP GTH12025 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0720 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 90 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 730 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1890 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007638 | SCREW,CAP;HEX,ALLOY ST,NP GTH12038 | 6 | EA | 6 | 0 | 0 | 6 | EA | 31.01 - SOH @ AA01 | Supply for Order 200091513, Item 256 cannot be changed 90028419 item 1970 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2000 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 256 | 0 | EA | 102000000030389 | 101000000141810 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1970 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007638 | SCREW,CAP;HEX,ALLOY ST,NP GTH12038 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1970 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 256 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2000 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1720 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007639 | BOLT,HEX;ALLOY ST,NP GTH12044 | 22 | EA | 22 | 0 | 0 | 22 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 239 cannot be changed 90028419 item 1820 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 239 | 0 | EA | 102000000030389 | 102000000030245 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 22 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1820 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007639 | BOLT,HEX;ALLOY ST,NP GTH12044 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1820 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 239 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1850 |  |  | 0 | 22 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0570 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007640 | BOLT,HEX;1/2" X28MM,ALLOY ST,NP RVQ20393 | 6 | EA | 6 | 0 | 0 | 6 | EA | 27.02 - SOH @ AA02 | Supply for Order 200091513, Item 65 cannot be changed 90028419 item 490 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 65 | 0 | EA | 102000000030502 | 102000000030821 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007640 | BOLT,HEX;1/2" X28MM,ALLOY ST,NP RVQ20393 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0490 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 65 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 500 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007641 | SCREW,SHROUD;ALLOY ST,NP RVQ21300 | 12 | EA | 18 | 0 | 0 | 12 | EA | 06.01 - SOH @ AA02 | Supply for Order 200091513, Item 485 cannot be changed 90028419 item 3410 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 485 | 0 | EA | 102000000030487 | 102000000031118 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3410 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007641 | SCREW,SHROUD;ALLOY ST,NP RVQ21300 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3410 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 485 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3440 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0210 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007645 | PLUG,HEX;AL,NP RVS19428 | 8 | EA | 8 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 22 cannot be changed 90028419 item 210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 22 | 0 | EA | 102000000030386 | 102000000030907 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007645 | PLUG,HEX;AL,NP RVS19428 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0210 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 22 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 220 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0290 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007645 | PLUG,HEX;AL,NP RVS19428 | 4 | EA | 8 | 0 | 0 | 0 |  | 05.03 - SOH @ AA53 SQUIRREL STOCK LET PO COME IN | Supply for Order 200091513, Item 665 cannot be changed 90028419 item 4440 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 665 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4440 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007645 | PLUG,HEX;AL,NP RVS19428 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_4440 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 665 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4470 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0370 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007645 | PLUG,HEX;AL,NP RVS19428 | 8 | EA | 8 | 0 | 0 | 0 |  | 05.03 - SOH @ AA53 SQUIRREL STOCK LET PO COME IN | Supply for Order 200091513, Item 34 cannot be changed 90028419 item 300 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 34 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0300 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007645 | PLUG,HEX;AL,NP RVS19428 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0300 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 34 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 310 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0830 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007647 | GLASS,SIGHT;NP SMO0459702 | 1 | EA | 6 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 96 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007647 | GLASS,SIGHT;NP SMO0459702 |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0860 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007647 | GLASS,SIGHT;NP SMO0459702 | 6 | EA | 6 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 677 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007647 | GLASS,SIGHT;NP SMO0459702 |  |  |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0470 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007654 | TUBE,CROSSFIRE;NP SMO0464601 | 4 | EA | 8 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 47 cannot be changed 90028419 item 390 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 47 | 0 | EA | 102000000030481 | 102000000030189 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0390 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007654 | TUBE,CROSSFIRE;NP SMO0464601 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0390 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 47 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 400 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0620 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007655 | SEAL,TUBE;SS304,NP SMO0462300 | 4 | EA | 9 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 62 cannot be changed 90028419 item 470 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 62 | 0 | EA | 102000000030135 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0470 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007655 | SEAL,TUBE;SS304,NP SMO0462300 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0470 |  |  | DG1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 62 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 480 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 3310 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.10.2024) | 10007657 | TRANSITION PCE,PIGNONE MS3002,H TECH | 6 | EA | 6 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 769 cannot be changed 90028419 item 4890 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4930 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90028419 | 05 | Preparation | 0000129822 | 769 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4890 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007657 | TRANSITION PCE,PIGNONE MS3002,H TECH | 2024-10-02 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_4890 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 769 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4930 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0820 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR |  | 20 | No issue identified | 10007657 | TRANSITION PCE,PIGNONE MS3002,H TECH | -6 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000129822 | 741 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007657 | TRANSITION PCE,PIGNONE MS3002,H TECH |  |  |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0930 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.02.2025) | 10007660 | SHROUD,1ST STG;NP SMO1031173 | 1 | SET | 1 | 0 | 0 | 0 |  | 03.02 - SOH @ AA02 | Supply for Order 200091513, Item 108 cannot be changed 90030042 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 5000 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90030042 | 05 | Preparation | 0000129822 | 108 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090030042_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030042 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007660 | SHROUD,1ST STG;NP SMO1031173 | 2025-02-01 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90030042_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 108 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 5000 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1820 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007661 | SHROUD,2ND STG;NP SMO1031115 | 1 | SET | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000129822 | 249 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007661 | SHROUD,2ND STG;NP SMO1031115 |  |  |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0020 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007664 | SEAL,OIL;BZE,NP SMO1512100 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.01 - SOH @ AA02 | Supply for Order 200091513, Item 2 cannot be changed 90028419 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 2 | 0 | EA | 102000000030489 | 102000000030306 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007664 | SEAL,OIL;BZE,NP SMO1512100 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0050 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0130 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007665 | BEARING,THR;NP SMO37745 | 1 | ASY | 0 | 0 | 1 | 1 | ASY | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 12 cannot be changed 9027133 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180124227 | 9027133 | 05 | Preparation | 0000129822 | 12 | 0 | ASY |  |  | 102000000030738 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000396417_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056768 | 1020 | 2025-07-03 | 1 |  | 2025-02-11 | 4900234167_2025_0003 | 2025-03-01 |  | 5000396417_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180124227 | 2 | 0 | 0 | X | L | 4900234167 | 2025 |  | 5000396417 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007665 | BEARING,THR;NP SMO37745 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 9027133_0110 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 120 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1610 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007666 | BEARING,THR;NP SMO37700 | 1 | EA | 0 | 0 | 1 | 1 | EA | 02.10 - SOH @ AA01 | Supply for Order 200091513, Item 228 cannot be changed 9027133 item 1710 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124227 | 9027133 | 05 | Preparation | 0000129822 | 228 | 0 | EA |  |  | 101000000011738 | 01-Road |  | 5-Completed |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 | 2025-01-22 | 2025-01-22 | Y | 1001 | 2024-07-22 | GRST-5000396366_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056768 | 1020 | 2025-07-03 | 1 |  | 2025-02-11 | 4900234167_2025_0005 | 2025-03-01 |  | 5000396366_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180124227 | 2 | 0 | 0 | X | L | 4900234167 | 2025 |  | 5000396366 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007666 | BEARING,THR;NP SMO37700 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 9027133_1710 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 228 |  | 0 |  | 25SD2420 | MJ | 20005006 | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1740 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-20 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1620 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007668 | BEARING,THR;NP SMO37750 | 1 | EA | 1 | 0 | 1 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 229 cannot be changed 9027133 item 1720 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124227 | 9027133 | 05 | Preparation | 0000129822 | 229 | 0 | EA |  |  | 102000000030734 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000396430_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056768 | 1020 | 2025-07-03 | 1 |  | 2025-02-11 | 4900234167_2025_0007 | 2025-03-01 |  | 5000396430_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180124227 | 2 | 0 | 0 | X | L | 4900234167 | 2025 |  | 5000396430 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007668 | BEARING,THR;NP SMO37750 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 9027133_1720 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 229 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1750 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1970 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007672 | VALVE,TRIP;CS,NP SMO1554701 | 1 | EA | 0 | 0 | 0 | 0 |  | 30.01 - ETA 17.12.25 PO 4500044323 ex BH DELETE FROM MO | Supply for Order 200091513, Item 704 cannot be changed 90028419 item 4690 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 704 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4690 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007672 | VALVE,TRIP;CS,NP SMO1554701 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_4690 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 704 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4730 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1440 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007675 | ACTUATOR,HYD;NP RAO20592 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 186 cannot be changed 90028419 item 1420 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 186 | 0 | EA |  |  | 102000000030027 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1420 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007675 | ACTUATOR,HYD;NP RAO20592 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1420 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 186 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1450 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0630 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007678 | STOP,COMB ELB;NP SMQ21886 | 12 | EA | 13 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 63 cannot be changed 90028419 item 480 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 63 | 0 | EA | 102000000030481 | 102000000030719 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0480 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007678 | STOP,COMB ELB;NP SMQ21886 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0480 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 63 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 490 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1300 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007681 | BUSH,BTM,2ND NOZ;SS,NP SMQ25576 | 32 | EA | 64 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 172 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007681 | BUSH,BTM,2ND NOZ;SS,NP SMQ25576 |  |  |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1450 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007682 | BLOCK,TERM;22.6X17.9X6.1MM,NP SMR21392 | 32 | EA | 62 | 0 | 0 | 32 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 187 cannot be changed 90028419 item 1430 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 187 | 0 | EA | 102000000030498 | 102000000030626 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1430 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007682 | BLOCK,TERM;22.6X17.9X6.1MM,NP SMR21392 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1430 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 187 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1460 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1460 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007683 | BUSH,TOP,2ND NOZ;SS,NP SMQ25577 | 64 | EA | 64 | 0 | 0 | 0 |  | 07.02 - ETA 01.04.25 PO 4500031515 x 128 MOT 30655 GS4949926 157.4kg 150x75x70cm | Supply for Order 200091513, Item 188 cannot be changed 90028419 item 1440 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 188 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 64 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1440 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007683 | BUSH,TOP,2ND NOZ;SS,NP SMQ25577 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1440 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 188 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1470 |  |  | 0 | 64 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1270 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007683 | BUSH,TOP,2ND NOZ;SS,NP SMQ25577 | 64 | EA | 64 | 0 | 0 | 64 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 169 cannot be changed 90028419 item 1270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 169 | 0 | EA | 102000000033879 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 64 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007683 | BUSH,TOP,2ND NOZ;SS,NP SMQ25577 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1270 |  |  | DG1 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 169 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1300 |  |  | 0 | 64 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1470 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007684 | BLOCK,SEAL,DIFFUSER SEGM;NP SMR21391 | 16 | EA | 16 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 189 cannot be changed 90028419 item 1450 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 189 | 0 | EA | 102000000030498 | 102000000030627 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007684 | BLOCK,SEAL,DIFFUSER SEGM;NP SMR21391 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1450 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 189 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1480 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1480 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007685 | BLOCK,SEAL,DIFFUSER SEGM;NP SMR21390 | 30 | EA | 30 | 0 | 0 | 30 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 190 cannot be changed 90028419 item 1460 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 190 | 0 | EA | 102000000030498 | 102000000030629 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007685 | BLOCK,SEAL,DIFFUSER SEGM;NP SMR21390 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1460 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 190 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1490 |  |  | 0 | 30 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1000 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007686 | PLATE,LKG;SS,NP SMR50008 | 12 | EA | 34 | 0 | 0 | 8 | EA | 25.02 - SOH @ AA02 | Supply for Order 200091513, Item 115 cannot be changed 90028419 item 920 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 930 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 115 | 0 | EA | 102000000030487 | 102000000030591 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0920 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007686 | PLATE,LKG;SS,NP SMR50008 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0920 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 115 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 930 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0780 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007686 | PLATE,LKG;SS,NP SMR50008 | 10 | EA | 34 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 91 cannot be changed 90028419 item 730 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 91 | 0 | EA | 102000000030492 | 102000000031794 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007686 | PLATE,LKG;SS,NP SMR50008 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0730 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 91 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 740 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007686 | PLATE,LKG;SS,NP SMR50008 | 8 | EA | 34 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 708 cannot be changed 90028419 item 4730 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 708 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007686 | PLATE,LKG;SS,NP SMR50008 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_4730 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 708 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4770 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1490 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007687 | BLOCK,TERM;21.1X17.7X6.1MM,NP SMR21389 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 191 cannot be changed 90028419 item 1470 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 191 | 0 | EA | 102000000030498 | 102000000030628 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1470 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007687 | BLOCK,TERM;21.1X17.7X6.1MM,NP SMR21389 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1470 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 191 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1500 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1830 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007688 | PIN,SHROUD;NP SMR21227 | 4 | EA | 12 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 250 cannot be changed 90028419 item 1910 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1940 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 250 | 0 | EA | 102000000030389 | 102000000030174 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1910 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007688 | PIN,SHROUD;NP SMR21227 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1910 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 250 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1940 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1190 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007689 | BLOCK,SEAL,DIFFUSER SEGM;NP SMR21387 | 5 | EA | 10 | 0 | 0 | 5 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 142 cannot be changed 90028419 item 1100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 142 | 0 | EA | 102000000030480 | 102000000030310 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007689 | BLOCK,SEAL,DIFFUSER SEGM;NP SMR21387 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1100 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 142 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1110 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1260 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007690 | SEAL,BLK;NP SMR21385 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 149 cannot be changed 90028419 item 1140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 149 | 0 | EA | 102000000030480 | 102000000030632 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007690 | SEAL,BLK;NP SMR21385 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1140 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 149 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1150 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1500 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007691 | BLOCK,SEAL,GAS TURB;NP SMR21388 | 3 | EA | 2 | 0 | 0 | 2 | EA | 15.10 - ETA 18.03.25 PO 4500031473 BH | Supply for Order 200091513, Item 192 cannot be changed 90028419 item 1480 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 192 | 0 | EA | 102000000030498 | 102000000030624 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1480 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007691 | BLOCK,SEAL,GAS TURB;NP SMR21388 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1480 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 192 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1510 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1270 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007692 | SEAL,BLK;NP SMR21386 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 150 cannot be changed 90028419 item 1150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 150 | 0 | EA | 102000000030480 | 102000000030633 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007692 | SEAL,BLK;NP SMR21386 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1150 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 150 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1160 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1340 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007693 | SHROUD,OUTER;NP SMO0607377 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 176 cannot be changed 90028419 item 1320 already exists | Material picked; currently at 30-03-03-80B/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 176 | 0 | EA |  |  | 102000000033128 |  |  |  |  | WorkPackLink | 30-03-03-80B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007693 | SHROUD,OUTER;NP SMO0607377 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1320 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 176 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1350 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1350 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007695 | SHROUD,INNTER;NP SMR80133 | 1 | SET | 2 | 0 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 177 cannot be changed 90028419 item 1330 already exists | Material picked; currently at 30-03-03-80A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1360 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 177 | 0 | SET |  |  | 102000000033129 |  |  |  |  | WorkPackLink | 30-03-03-80A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007695 | SHROUD,INNTER;NP SMR80133 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1330 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 177 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1360 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1290 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007696 | PLUG,MACH;SS,NP SMR22419 | 1 | EA | 5 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 152 cannot be changed 90028419 item 1160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 152 | 0 | EA | 102000000030480 | 102000000030909 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007696 | PLUG,MACH;SS,NP SMR22419 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1160 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 152 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1180 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1320 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007696 | PLUG,MACH;SS,NP SMR22419 | 2 | EA | 5 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 691 cannot be changed 90028419 item 4590 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 691 | 0 | EA | 102000000030487 | 102000000030910 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4590 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007696 | PLUG,MACH;SS,NP SMR22419 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_4590 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 691 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4630 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007697 | BLOCK,SEAL,HEAT SHIELD;NP SMR21393 | 6 | EA | 0 | 0 | 0 | 0 |  | 15.10 - ETA 18.03.25 PO 4500031502 BH | Supply for Order 200091513, Item 193 cannot be changed 90028419 item 1490 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 193 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007697 | BLOCK,SEAL,HEAT SHIELD;NP SMR21393 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1490 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 193 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1520 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1520 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007699 | BLOCK,TERM;185X20X2MM,NP SMR21394 | 16 | EA | 32 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 194 cannot be changed 90028419 item 1500 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 194 | 0 | EA | 102000000030498 | 102000000030625 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1500 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007699 | BLOCK,TERM;185X20X2MM,NP SMR21394 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1500 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 194 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1530 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1320 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007701 | SPACER,RING;CS,NP SMR40047 | 32 | EA | 64 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 174 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007701 | SPACER,RING;CS,NP SMR40047 |  |  |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1810 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007702 | PLATE,LKG;SS,50X30MM,NP SMR50084 | 40 | EA | 81 | 0 | 0 | 40 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 248 cannot be changed 90028419 item 1900 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1930 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 248 | 0 | EA | 102000000030389 | 102000000031790 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1900 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007702 | PLATE,LKG;SS,50X30MM,NP SMR50084 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1900 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 248 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1930 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1290 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007703 | SHIM,PIGNONE MS3002 24 X 34 X 0.05MM,SS | 10 | EA | 57 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 171 cannot be changed 90028419 item 1290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 171 | 0 | EA | 102000000030498 | 102000000030595 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007703 | SHIM,PIGNONE MS3002 24 X 34 X 0.05MM,SS | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1290 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 171 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1320 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1280 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007704 | SPACER;SS,NP SMR7950567 | 12 | SET | 13 | 0 | 0 | 2 | SET | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 170 cannot be changed 90028419 item 1280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1310 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 170 | 0 | SET | 102000000030498 | 102000000030665 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007704 | SPACER;SS,NP SMR7950567 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1280 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 170 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1310 |  |  | 0 | 12 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1280 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007704 | SPACER;SS,NP SMR7950567 | 12 | SET | 13 | 0 | 0 | 10 | SET | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 170 cannot be changed 90028419 item 1280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1310 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 170 | 0 | SET | 102000000030498 | 102000000033434 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007704 | SPACER;SS,NP SMR7950567 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1280 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 170 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1310 |  |  | 0 | 12 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2000 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007705 | NOZZLE,FUEL;SS304,NP SMR82551 | 2 | EA | 6 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 520 cannot be changed 90028419 item 3750 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 520 | 0 | EA | 102000000030501 | 102000000030597 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007705 | NOZZLE,FUEL;SS304,NP SMR82551 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3750 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 520 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3780 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0580 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007706 | PLATE,SAF;SS,70MM W,NP SMR66722 | 6 | EA | 6 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 66 cannot be changed 90028419 item 500 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 66 | 0 | EA | 102000000030502 | 102000000031795 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0500 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007706 | PLATE,SAF;SS,70MM W,NP SMR66722 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0500 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 66 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 510 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0590 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007707 | SEAL,TRANSIT PCE;SS,NP SMR66724 | 6 | EA | 6 | 0 | 0 | 6 | EA | 13.01 - SOH @AA02 | Supply for Order 200091513, Item 67 cannot be changed 90028419 item 510 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 67 | 0 | EA | 102000000030502 | 102000000030468 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0510 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007707 | SEAL,TRANSIT PCE;SS,NP SMR66724 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0510 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 67 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 520 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0600 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007708 | PLATE,LKG;SS,NP SMR66729 | 6 | EA | 6 | 0 | 0 | 6 | EA | 13.01 - SOH @ AA02 | Supply for Order 200091513, Item 68 cannot be changed 90028419 item 520 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 68 | 0 | EA | 102000000030502 | 102000000031793 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0520 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007708 | PLATE,LKG;SS,NP SMR66729 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0520 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 68 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 530 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1690 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007709 | SEAL,OIL;AL,NP SMS37570 | 1 | SET | 1 | 0 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 236 cannot be changed 90028419 item 1790 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1820 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 236 | 0 | SET | 102000000030901 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1790 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007709 | SEAL,OIL;AL,NP SMS37570 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1790 |  |  | DG1 |  | B1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 236 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1820 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007711 | SEAL,PIGNONE MS3002,LABYTH,BRG NO 1 | 1 | SET | 1 | 0 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 4 cannot be changed 90028419 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 4 | 0 | SET | 102000000030489 | 102000000030303 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007711 | SEAL,PIGNONE MS3002,LABYTH,BRG NO 1 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0060 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 70 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0190 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007712 | DEFLECTOR,AIR;NP SMS35113 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 18 cannot be changed 90028419 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 18 | 0 | EA | 102000000030489 | 102000000030596 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007712 | DEFLECTOR,AIR;NP SMS35113 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_0170 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 18 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 180 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007713 | SEAL,LABYTH;AL,NP SMS35143 | 2 | SET | 4 | 0 | 0 | 2 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 204 cannot be changed 90028419 item 1590 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1620 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 204 | 0 | SET | 102000000030488 | 102000000031282 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1590 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007713 | SEAL,LABYTH;AL,NP SMS35143 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_1590 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 204 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1620 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1630 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007714 | SEAL,LABYTH;AL,NP SMS35145 | 1 | SET | 2 | 0 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 230 cannot be changed 90028419 item 1730 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1760 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 230 | 0 | SET | 102000000030138 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007714 | SEAL,LABYTH;AL,NP SMS35145 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1730 |  |  | DG1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 230 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1760 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007715 | SEAL,OIL;AL,NP SMS37566 | 1 | SET | 1 | 0 | 0 | 1 | SET | 13.01 - SOH @ AA02 | Supply for Order 200091513, Item 216 cannot be changed 90028419 item 1630 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1660 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 216 | 0 | SET | 102000000030483 | 102000000030136 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1630 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007715 | SEAL,OIL;AL,NP SMS37566 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 90028419_1630 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 216 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1660 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1580 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007716 | SEAL,LABYTH;AL,NP SMS37568 | 1 | SET | 2 | 0 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 223 cannot be changed 90028419 item 1680 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1710 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 223 | 0 | SET | 102000000030137 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1680 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007716 | SEAL,LABYTH;AL,NP SMS37568 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 90028419_1680 |  |  | DG1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 223 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1710 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1570 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007717 | PIN,BRG ASY;NP RPP01423 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 222 cannot be changed 90028419 item 1670 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1700 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 222 | 0 | EA | 102000000030483 | 102000000030165 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007717 | PIN,BRG ASY;NP RPP01423 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 90028419_1670 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 222 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1700 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1530 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007718 | RING,PST;ALLOY ST,NP SQQ27435 | 32 | EA | 32 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 195 cannot be changed 90028419 item 1510 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 195 | 0 | EA | 102000000030498 | 102000000030372 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1510 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007718 | RING,PST;ALLOY ST,NP SQQ27435 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1510 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 195 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1540 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2160 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007722 | GASKET,JKT;NP IRF3712901 | 2 | EA | 5 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 321 cannot be changed 90028419 item 2500 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 321 | 0 | EA | 102000000030605 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2500 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007722 | GASKET,JKT;NP IRF3712901 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2500 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 321 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2530 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2220 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007732 | O-RING;VIT A,NP KHA089605301 | 4 | EA | 5 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 301 cannot be changed 90028419 item 2350 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 301 | 0 | EA | 102000000030491 | 102000000030375 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2350 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007732 | O-RING;VIT A,NP KHA089605301 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2350 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 301 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2380 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2210 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007733 | O-RING;0.210" THK,VIT A,NP KHA278705301 | 2 | EA | 3 | 0 | 0 | 1 | EA | 07.03 - SOH @ AA02 | Supply for Order 200091513, Item 300 cannot be changed 90028419 item 2340 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 300 | 0 | EA | 102000000030491 | 102000000030639 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2340 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007733 | O-RING;0.210" THK,VIT A,NP KHA278705301 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2340 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 300 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2370 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2520 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007736 | SCREW,MACH;NP HAP83007 | 32 | EA | 16 | 0 | 0 | 16 | EA | 15.10 - ETA 20.03.25 PO 4500031516 BH | Supply for Order 200091513, Item 558 cannot be changed 90028419 item 4030 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4060 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 558 | 0 | EA | 102000000030385 | 102000000030818 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007736 | SCREW,MACH;NP HAP83007 | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_4030 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 558 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4060 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2380 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007738 | GASKET;C4500,KLINGER 0WOO10007738 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 350 cannot be changed 90028419 item 2700 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 350 | 0 | EA | 102000000030606 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2700 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007738 | GASKET;C4500,KLINGER 0WOO10007738 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2700 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 350 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2730 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1360 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007751 | LINK,CASE ARG;NP SMO0826002 | 32 | ASY | 64 | 0 | 0 | 32 | ASY | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 178 cannot be changed 90028419 item 1340 already exists | Material picked; currently at SW3R01A02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1370 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 178 | 0 | ASY |  |  | 102000000030115 |  |  |  |  | WorkPackLink | SW3R01A02A |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1340 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007751 | LINK,CASE ARG;NP SMO0826002 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1340 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 178 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1370 |  |  | 0 | 32 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1380 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007752 | PIN,CASE ARG;NP RPP03066 | 32 | EA | 64 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 180 cannot be changed 90028419 item 1360 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 180 | 0 | EA | 102000000030498 | 102000000030170 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1360 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007752 | PIN,CASE ARG;NP RPP03066 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1360 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 180 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1390 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1540 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007753 | WASHER,PLN;13X44X2.5MM,NP FLD044013025 | 32 | EA | 32 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 196 cannot be changed 90028419 item 1520 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 196 | 0 | EA | 102000000030498 | 102000000030367 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1520 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007753 | WASHER,PLN;13X44X2.5MM,NP FLD044013025 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1520 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 196 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1550 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0760 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007763 | SPACER,SHIM;NP SMQ5952079 | 2 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 89 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007763 | SPACER,SHIM;NP SMQ5952079 |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0400 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007770 | SPACER,SHIM;NP SMR33927 | 10 | EA | 11 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 458 cannot be changed 90028419 item 3200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 458 | 0 | EA | 102000000030386 | 102000000030668 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007770 | SPACER,SHIM;NP SMR33927 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3200 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 458 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3230 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0410 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007771 | SPACER,SHIM;NP SMR33928 | 10 | EA | 25 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 459 cannot be changed 90028419 item 3210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 459 | 0 | EA | 102000000030386 | 102000000030666 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007771 | SPACER,SHIM;NP SMR33928 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3210 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 459 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3240 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007772 | SPACER,SHIM;NP ISM083160029 | 10 | EA | 11 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 460 cannot be changed 90028419 item 3220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 460 | 0 | EA | 102000000030386 | 102000000030669 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007772 | SPACER,SHIM;NP ISM083160029 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3220 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 460 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3250 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0430 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007773 | SPACER,SHIM;NP SMR33930 | 10 | EA | 10 | 0 | 0 | 10 | EA | 05.02 - SOH @ AA02 | Supply for Order 200091513, Item 461 cannot be changed 90028419 item 3230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 461 | 0 | EA | 102000000030386 | 102000000030670 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007773 | SPACER,SHIM;NP SMR33930 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3230 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 461 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3260 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0440 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007774 | SPACER,SHIM;NP SMR33931 | 10 | EA | 21 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 462 cannot be changed 90028419 item 3240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 462 | 0 | EA | 102000000030386 | 102000000030671 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007774 | SPACER,SHIM;NP SMR33931 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3240 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 462 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3270 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0350 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007775 | KEY,BLD,STATOR;NP SMP33909 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 32 cannot be changed 90028419 item 280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 32 | 0 | EA | 102000000030386 | 102000000033858 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007775 | KEY,BLD,STATOR;NP SMP33909 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0280 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 32 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 290 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0360 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007776 | KEY,BLD,STATOR;NP ISM268120481 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 33 cannot be changed 90028419 item 290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 33 | 0 | EA | 102000000030654 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007776 | KEY,BLD,STATOR;NP ISM268120481 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0290 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 33 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 300 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0730 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007777 | PIN,ECC,NOZ;NP SMQ5952077 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 86 cannot be changed 90028419 item 690 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 700 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 86 | 0 | EA | 102000000030492 | 102000000030172 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0690 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007777 | PIN,ECC,NOZ;NP SMQ5952077 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0690 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 86 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 700 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039735 | 0010 | 0050 | 100039735 | Replace Flange Bolting 1K1820V7A/B | AA53.1K1820V7A | VE,DRAIN POT & MIST ELIMIN SEAL OIL | AA01 | 30 | WO item has not been released yet | 10007788 | NUT,HEX;0.750"-10 UNC,SS,NP FFF64619 | 16 | EA | 106 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item, 106 SOH @ AA02 17.01 - 106 SOH @ AA02 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000138236 | 5 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-08-11 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007788 | NUT,HEX;0.750"-10 UNC,SS,NP FFF64619 |  |  |  | 0010 | Replace 1K1820V7A - Gasket & Studs | INT | Replace 1K1820V7A - Gasket & Studs | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137645 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007797 | BOLT,HEX;ALLOY ST,NP GQL19044 | 64 | EA | 128 | 0 | 0 | 64 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 42 cannot be changed 90028419 item 340 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 42 | 0 | EA | 102000000030996 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 64 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0340 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007797 | BOLT,HEX;ALLOY ST,NP GQL19044 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0340 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 42 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 350 |  |  | 0 | 64 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2530 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007804 | BOLT,HEX;SS,NP GTL12044 | 110 | EA | 110 | 0 | 0 | 110 | EA | 31.01 - SOH @ AA01 | Supply for Order 200091513, Item 559 cannot be changed 90028419 item 4040 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4070 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 559 | 0 | EA | 101000000142140 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 110 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007804 | BOLT,HEX;SS,NP GTL12044 | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_4040 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 559 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4070 |  |  | 0 | 110 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1900 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007808 | BOLT,HEX;ALLOY ST,NP GTL25101 | 8 | EA | 2 | 0 | 0 | 2 | EA | 15.10 - ETA 15.04.25 PO 4500031516 BH | Supply for Order 200091513, Item 257 cannot be changed 90028419 item 1980 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2010 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 257 | 0 | EA | 102000000030389 | 102000000030833 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1980 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007808 | BOLT,HEX;ALLOY ST,NP GTL25101 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1980 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 257 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2010 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007815 | SCREW,MACH;ALLOY ST,NP GTJ12044 | 48 | EA | 48 | 0 | 0 | 48 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 123 cannot be changed 90028419 item 970 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 980 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 123 | 0 | EA | 102000000030487 | 102000000031112 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0970 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007815 | SCREW,MACH;ALLOY ST,NP GTJ12044 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0970 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 123 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 980 |  |  | 0 | 48 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1910 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007815 | SCREW,MACH;ALLOY ST,NP GTJ12044 | 48 | EA | 48 | 0 | 0 | 0 |  | 10.12 - ETA 23.03.25 MOT 30655 PO 4500031515 x 128 GS4949926 157.4kg 150x75x70cm |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 258 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007815 | SCREW,MACH;ALLOY ST,NP GTJ12044 |  |  |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0050 | 0030 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10007826 | ELEMENT,FLT;NP IRF0242701 | 1 | EA | 8 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 3 cannot be changed 90028583 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 3 | 0 | EA | 102000000033620 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007826 | ELEMENT,FLT;NP IRF0242701 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028583_0030 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 |  | 30 | 5300020057 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0030 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10007826 | ELEMENT,FLT;NP IRF0242701 | 1 | EA | 8 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 14 cannot be changed 90028584 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 14 | 0 | EA | 102000000033623 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007826 | ELEMENT,FLT;NP IRF0242701 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028584_0140 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 |  | 30 | 5300020058 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2360 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007826 | ELEMENT,FLT;NP IRF0242701 | 2 | EA | 8 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 340 cannot be changed 90028419 item 2630 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 340 | 0 | EA | 102000000030482 | 102000000030672 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2630 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007826 | ELEMENT,FLT;NP IRF0242701 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2630 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 340 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2660 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2730 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007832 | GASKET;CU,NP KFZ194380704 | 3 | EA | 8 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 401 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | sparkpluggas |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007832 | GASKET;CU,NP KFZ194380704 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2450 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007835 | GASKET;CNAF,NP KFZ196510144 | 2 | EA | 3 | 0 | 0 | 0 |  | 26.02 - SOH @ AA02 | Supply for Order 200091513, Item 549 cannot be changed 90028419 item 3950 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3980 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 549 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3950 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007835 | GASKET;CNAF,NP KFZ196510144 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_3950 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 549 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3980 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2520 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007835 | GASKET;CNAF,NP KFZ196510144 | 1 | EA | 3 | 0 | 0 | 0 |  | 26.02 - SOH @ AA02 | Supply for Order 200091513, Item 714 cannot be changed 90028419 item 4770 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 714 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007835 | GASKET;CNAF,NP KFZ196510144 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_4770 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 714 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4810 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2390 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007845 | GASKET;C4500,KLINGER 0WOO10007845 | 5 | EA | 6 | 0 | 0 | 3 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 351 cannot be changed 90028419 item 2710 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 351 | 0 | EA | 102000000030650 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2710 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007845 | GASKET;C4500,KLINGER 0WOO10007845 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2710 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 351 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2740 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2400 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007846 | GASKET:PIGNONE MS5352B,OIL PIPING | 2 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 03.04.25 PO 4500045034 ex BH | Supply for Order 200091513, Item 352 cannot be changed 90028419 item 2720 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 352 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2720 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007846 | GASKET:PIGNONE MS5352B,OIL PIPING | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2720 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 352 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2750 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007893 | O-RING;VIT A,NP KHA031303501 | 6 | EA | 26 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 285 cannot be changed 90028419 item 2210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 285 | 0 | EA | 102000000030491 | 102000000030634 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007893 | O-RING;VIT A,NP KHA031303501 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2210 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 285 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2240 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1860 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007893 | O-RING;VIT A,NP KHA031303501 | 12 | EA | 26 | 0 | 0 | 12 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 260 cannot be changed 90028419 item 1990 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2020 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 260 | 0 | EA | 102000000030504 | 102000000030320 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1990 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007893 | O-RING;VIT A,NP KHA031303501 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_1990 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 260 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2020 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1870 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007894 | O-RING;VIT A,NP KHA028103531 | 4 | EA | 69 | 0 | 0 | 4 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 261 cannot be changed 90028419 item 2000 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2030 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 261 | 0 | EA | 102000000030504 | 102000000030322 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2000 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007894 | O-RING;VIT A,NP KHA028103531 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2000 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 261 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2030 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2240 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007895 | O-RING;VIT A,0.364",NP KHA009201701 | 1 | EA | 24 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 303 cannot be changed 90028419 item 2360 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 303 | 0 | EA | 102000000030491 | 102000000030636 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2360 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007895 | O-RING;VIT A,0.364",NP KHA009201701 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2360 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 303 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2390 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1660 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007896 | O-RING;41X3.6MM,NP KHE034503501 | 8 | EA | 61 | 0 | 0 | 8 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 507 cannot be changed 90028419 item 3630 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 507 | 0 | EA | 102000000030498 | 102000000030637 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3630 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007896 | O-RING;41X3.6MM,NP KHE034503501 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_3630 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 507 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3660 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1910 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007897 | O-RING;VIT A,NP KHA056703501 | 4 | EA | 6 | 0 | 0 | 4 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 265 cannot be changed 90028419 item 2040 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2070 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 265 | 0 | EA | 102000000030504 | 101000000143080 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007897 | O-RING;VIT A,NP KHA056703501 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2040 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 265 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2070 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1890 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007899 | O-RING;VIT A,NP KHA120203501 | 1 | EA | 3 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 263 cannot be changed 90028419 item 2020 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2050 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 263 | 0 | EA | 102000000030504 | 102000000030635 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007899 | O-RING;VIT A,NP KHA120203501 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2020 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 263 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2050 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1700 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007913 | BEARING,NDL;BZE,NP RCT30701 | 1 | EA | 6 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 511 cannot be changed 90028419 item 3670 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3700 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 511 | 0 | EA | 102000000030498 | 102000000030128 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007913 | BEARING,NDL;BZE,NP RCT30701 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_3670 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 511 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3700 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1930 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007917 | FILTER,OIL,HYD;NP RFO37045 | 1 | EA | 4 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 273 cannot be changed 90028419 item 2120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 273 | 0 | EA | 102000000030094 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ONCONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007917 | FILTER,OIL,HYD;NP RFO37045 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_2120 |  |  | DG1 |  | C5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 273 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2740 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007927 | SWITCH,LIMIT;EX,NP RJO21403 | 8 | EA | 9 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 402 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007927 | SWITCH,LIMIT;EX,NP RJO21403 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2970 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007927 | SWITCH,LIMIT;EX,NP RJO21403 | 2 | EA | 9 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 575 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | HP/LP |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007927 | SWITCH,LIMIT;EX,NP RJO21403 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007941 | SPRING,COMP;CS,NP RMQ14566 | 2 | EA | 9 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 524 cannot be changed 90028419 item 3790 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 524 | 0 | EA | 102000000030902 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3790 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007941 | SPRING,COMP;CS,NP RMQ14566 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3790 |  |  | DG1 |  | B1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 524 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3820 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1550 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007949 | PIN,STR;NP RPQ47510 | 12 | EA | 131 | 0 | 0 | 12 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 197 cannot be changed 90028419 item 1530 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 197 | 0 | EA | 102000000030498 | 102000000030173 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1530 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007949 | PIN,STR;NP RPQ47510 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1530 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 197 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1560 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0460 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007950 | PIN,CSG,DISCH;19.1X64MM,NP RPQ02578 | 2 | EA | 26 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 464 cannot be changed 90028419 item 3260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 464 | 0 | EA | 102000000030386 | 102000000030186 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007950 | PIN,CSG,DISCH;19.1X64MM,NP RPQ02578 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_3260 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 464 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3290 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0750 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007956 | PIN,STR;NP RPQ02807 | 4 | EA | 10 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 83 cannot be changed 90028419 item 660 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 83 | 0 | EA | 102000000030502 | 102000000030179 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007956 | PIN,STR;NP RPQ02807 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_0660 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 83 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 670 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0850 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10007956 | PIN,STR;NP RPQ02807 | 2 | EA | 10 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 479 cannot be changed 90028419 item 3380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 479 | 0 | EA | 102000000030492 | 102000000030182 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007956 | PIN,STR;NP RPQ02807 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_3380 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 479 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3410 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-03-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200065935 | 0020 | 0010 | 200065935 | 6Y Vib/Speed Probe Repl (7) 1K2420 | AA53.124GE026 | TXDCR,TRIP VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.10.2024) | 10007971 | PICK UP,NP MS5352B,MAG,LP/HP PROT | 12 | EA | 30 | 12 | 0 | 12 | EA | 29.10 - SOH @ AA02 | Supply for Order 200065935, Item 5 cannot be changed 90024974 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300008306 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024974 | 05 | Preparation | 0000100270 | 5 | 0 | EA | 102000000032156 | 102000000026771 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-03-25 | GIST-4900234089_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 12 |  | 2025-02-11 | 4900234089_2025_0001 | 2025-03-01 | 124SE002A |  | 0 | 2 | 0 | 90024974 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234089 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007971 | PICK UP,NP MS5352B,MAG,LP/HP PROT | 2024-10-28 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90024974_0010 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000099654 | S002 | 30 | 30 | 5300008306 | 50 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100270 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2750 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007971 | PICK UP,NP MS5352B,MAG,LP/HP PROT | 8 | EA | 30 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 403 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007971 | PICK UP,NP MS5352B,MAG,LP/HP PROT |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3200 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007971 | PICK UP,NP MS5352B,MAG,LP/HP PROT | 4 | EA | 30 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 621 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | MAGSPPROBE |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007971 | PICK UP,NP MS5352B,MAG,LP/HP PROT |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3160 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007971 | PICK UP,NP MS5352B,MAG,LP/HP PROT | 4 | EA | 30 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 594 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | HP/LP |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007971 | PICK UP,NP MS5352B,MAG,LP/HP PROT |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086238 | 0020 | 0020 | 100086238 | Ignitors, Trans & Cable O/H (4) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10007979 | XFMR,IGN;NP RTO44010 | 4 | EA | 8 | 0 | 0 | 4 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086238, Item 2 cannot be changed 90025087 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017068 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025087 | 05 | Preparation | 0000272412 | 2 | 0 | EA | 102000000033126 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-29 | ODST-0090025087_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025087 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007979 | XFMR,IGN;NP RTO44010 | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025087_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267111 | S002 |  | 30 | 5300017068 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272412 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007979 | XFMR,IGN;NP RTO44010 | 4 | EA | 8 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 586 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | sparkplug |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007979 | XFMR,IGN;NP RTO44010 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-17 | 2025-03-31 | 2024-10-22 | 2025-03-01 | 2025-03-02 | INLEC | 100074496 | 0020 | 0010 | 100074496 | MOC-117424 TC Replace 114TE403G 1KT1420 | AA53.114TE403G | TXDCR,KT1420 TURB EXH DUCT TEMP | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10007980 | INSTRUMENT,TC;NP RTO96268 | 1 | EA | 55 | 0 | 0 | 1 | EA | 29.01 - Consumed | Supply for Order 100074496, Item 1 cannot be changed 180084746 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300016522 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180084746 | 90022461 | 07 | Execution | 0000226664 | 1 | 0 | EA |  |  | 102000000021652 |  |  |  |  | WorkPackLink | KSF-POP-JOB-BENCH | P19 FL Inlec | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-10-17 |  | 0 | 0 | 0 | 0 |  | 2024-10-22 | AA53 | 2024-10-22 |  |  | 2025-03-31 |  |  | 100000036954 | 1020 | 2026-03-03 | 1 |  | 2024-10-22 | 4900157492_2024_0001 | 2024-10-27 | 114TE403G | 5000252938_2024_0001 | 0 | 2 | 0 | 90022461 | 1 | 0 | 180084746 | 2 | 0 | 0 | X | L | 4900157492 | 2024 |  | 5000252938 | 2024 | 0 |  | 2024-10-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007980 | INSTRUMENT,TC;NP RTO96268 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90022461_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000223936 | S002 | 30 | 30 | 5300016522 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-10-22 |  | Management of Change |  |  | 1070 |  | 2024-10-22 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-13 | 226664 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-02 | INLEC | 100074496 | 0020 | 0020 | 100074496 | MOC-117424 TC Replace 114TE403G 1KT1420 | AA53.114TE403G | TXDCR,KT1420 TURB EXH DUCT TEMP | AA01 | 255 | No Issue identified | 10007980 | INSTRUMENT,TC;NP RTO96268 | 1 | EA | 55 | 0 | 0 | 0 |  | 24.01 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016522 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032208 | 07 | Execution | 0000226664 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090032208_0010 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2024-10-22 |  |  | 2025-03-31 |  |  |  |  | 2026-03-03 | 0 |  | 2025-03-26 |  | 2025-03-31 | 114TE403G |  | 0 | 2 | 0 | 90032208 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007980 | INSTRUMENT,TC;NP RTO96268 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90032208_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000223936 | S002 | 30 | 30 | 5300016522 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-26 |  | Management of Change |  |  | 1070 |  | 2024-10-22 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-13 | 226664 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-30 | INLEC | 100086118 | 0020 | 0020 | 100086118 | TC Replace Bearing # 1,2,3 (4) 1KT2420 | AA53.124TIA88 | LOOP,ALARM TEMP L/O LOAD T/BRG 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.10.2024) | 10007986 | INSTRUMENT,TC;TYPE K,AIR INL,NP RTO97388 | 4 | EA | 4 | 8 | 0 | 4 | EA | 28.10 - SOH @ AA02 | Supply for Order 100086118, Item 2 cannot be changed 90025079 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016890 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025079 | 05 | Preparation | 0000272239 | 2 | 0 | EA | 102000000032142 | 102000000029968 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-25 | GIST-4900234140_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 4 |  | 2025-02-11 | 4900234140_2025_0003 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025079 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234140 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007986 | INSTRUMENT,TC;TYPE K,AIR INL,NP RTO97388 | 2024-10-25 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025079_0020 |  |  | DG1 |  | A3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000266972 | S002 |  | 30 | 5300016890 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272239 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-30 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086205 | 0020 | 0020 | 100086205 | TC Replace Bearing # 4 (2) 1KT2420 | AA53.124TI87 | LOOP,IND TEMP L/O BRG#4 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.10.2024) | 10007986 | INSTRUMENT,TC;TYPE K,AIR INL,NP RTO97388 | 2 | EA | 4 | 8 | 0 | 2 | EA | 28.10 - SOH @ AA02 | Supply for Order 100086205, Item 2 cannot be changed 90025081 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016892 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025081 | 05 | Preparation | 0000272397 | 2 | 0 | EA | 102000000032154 | 102000000029969 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-25 | GIST-4900234124_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 2 |  | 2025-02-11 | 4900234124_2025_0003 | 2025-03-01 | 124TE85/87 |  | 0 | 2 | 0 | 90025081 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234124 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007986 | INSTRUMENT,TC;TYPE K,AIR INL,NP RTO97388 | 2024-10-25 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025081_0020 |  |  | DG1 |  | A3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267096 | S002 |  | 30 | 5300016892 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272397 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100086237 | 0020 | 0020 | 100086237 | Compressor Inlet TC Replace (2) 1KT2420 | AA53.124TE32 | TXDCR,TEMP 1K2420 SUCT TEMP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.10.2024) | 10007986 | INSTRUMENT,TC;TYPE K,AIR INL,NP RTO97388 | 2 | EA | 4 | 8 | 0 | 2 | EA | 28.10 - SOH @ AA02 | Supply for Order 100086237, Item 2 cannot be changed 90025082 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016893 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124185 | 90025082 | 05 | Preparation | 0000272411 | 2 | 0 | EA | 102000000032153 | 102000000029970 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-25 | IDST-0180124185 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-28 | 2 |  | 2025-02-11 | 4900234104_2025_0003 | 2025-03-01 | 124TE133/165 |  | 0 | 2 | 0 | 90025082 | 0 | 0 | 180124185 | 2 | 0 | 0 | X | L | 4900234104 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007986 | INSTRUMENT,TC;TYPE K,AIR INL,NP RTO97388 | 2024-10-25 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025082_0020 |  |  | DG1 |  | A2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267110 | S002 |  | 30 | 5300016893 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272411 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3130 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007986 | INSTRUMENT,TC;TYPE K,AIR INL,NP RTO97388 | 1 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 591 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | compinlet |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007986 | INSTRUMENT,TC;TYPE K,AIR INL,NP RTO97388 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086205 | 0020 | 0030 | 100086205 | TC Replace Bearing # 4 (2) 1KT2420 | AA53.124TI87 | LOOP,IND TEMP L/O BRG#4 1KT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10007991 | INSTRUMENT,TC;NP RTO65735 | 10 | EA | 28 | 10 | 0 | 10 | EA | 18.11 - SOH @ AA02 | Supply for Order 100086205, Item 3 cannot be changed 90025081 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016892 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025081 | 05 | Preparation | 0000272397 | 3 | 0 | EA | 102000000032154 | 102000000029157 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-25 | GIST-4900234124_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 10 |  | 2025-02-11 | 4900234124_2025_0005 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025081 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234124 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007991 | INSTRUMENT,TC;NP RTO65735 | 2024-11-13 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025081_0030 |  |  | DG1 |  | A3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267096 | S002 |  | 30 | 5300016892 | 30 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272397 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3170 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10007991 | INSTRUMENT,TC;NP RTO65735 | 1 | EA | 28 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 595 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124TI87/88 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10007991 | INSTRUMENT,TC;NP RTO65735 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1940 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008000 | TXDCR,LIN;EX,GE RTO72680 | 4 | EA | 22 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 274 cannot be changed 90028419 item 2130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 274 | 0 | EA | 102000000030501 | 102000000030620 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ONCONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008000 | TXDCR,LIN;EX,GE RTO72680 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_2130 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 274 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2160 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086238 | 0020 | 0030 | 100086238 | Ignitors, Trans & Cable O/H (4) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10008001 | LEAD,SHORT;NP RTO74548 | 2 | EA | 5 | 2 | 0 | 2 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086238, Item 3 cannot be changed 90025087 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017068 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124191 | 9027113 | 05 | Preparation | 0000272412 | 3 | 0 | EA | 102000000029695 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-29 | IDST-0180124191 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 2 |  | 2025-02-11 | 4900234106_2025_0001 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025087 | 0 | 0 | 180124191 | 2 | 0 | 0 | X | L | 4900234106 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008001 | LEAD,SHORT;NP RTO74548 | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027113_0030 |  |  | DG1 |  | C2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267111 | S002 |  | 30 | 5300017068 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272412 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2930 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008001 | LEAD,SHORT;NP RTO74548 | 4 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 571 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | sparkplug |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008001 | LEAD,SHORT;NP RTO74548 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086238 | 0020 | 0040 | 100086238 | Ignitors, Trans & Cable O/H (4) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10008002 | LEAD,LG;NP RTO74651 | 4 | EA | 10 | 4 | 0 | 4 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086238, Item 4 cannot be changed 90025087 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017068 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124191 | 9027113 | 05 | Preparation | 0000272412 | 4 | 0 | EA | 102000000029696 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-29 | IDST-0180124191 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 4 |  | 2025-02-11 | 4900234106_2025_0003 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025087 | 0 | 0 | 180124191 | 2 | 0 | 0 | X | L | 4900234106 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008002 | LEAD,LG;NP RTO74651 | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027113_0040 |  |  | DG1 |  | C2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267111 | S002 | 30 | 30 | 5300017068 | 40 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272412 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1960 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008006 | VALVE,CHK;NP RVO11562 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 270 cannot be changed 90028419 item 2090 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 270 | 0 | EA | 102000000030773 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008006 | VALVE,CHK;NP RVO11562 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2090 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 270 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2770 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008009 | VALVE,SERVO;NP RVO08355 | 3 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 405 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | moog |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008009 | VALVE,SERVO;NP RVO08355 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008009 | VALVE,SERVO;NP RVO08355 | 3 | EA | 12 | 0 | 0 | 3 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 705 cannot be changed 90028419 item 4700 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 705 | 0 | EA | 102000000030501 | 102000000030772 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4700 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008009 | VALVE,SERVO;NP RVO08355 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_4700 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 705 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4740 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2020 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008018 | CYLINDER,HYD;NP RAO2080001 | 2 | EA | 14 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 522 cannot be changed 90028419 item 3770 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 522 | 0 | EA | 102000000034072 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008018 | CYLINDER,HYD;NP RAO2080001 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3770 |  |  | DG1 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 522 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3800 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086238 | 0020 | 0010 | 100086238 | Ignitors, Trans & Cable O/H (4) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10008023 | SPARK PLUG ASY;NP SMO0480502 | 4 | EA | 18 | 0 | 0 | 4 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086238, Item 1 cannot be changed 90025087 item 10 already exists | Material picked; currently at WH2-PACK-SD-1A/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300017068 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025087 | 05 | Preparation | 0000272412 | 1 | 0 | EA |  |  | 102000000032483 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-29 | ODST-0090025087_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025087 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008023 | SPARK PLUG ASY;NP SMO0480502 | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025087_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267111 | S002 | 30 | 30 | 5300017068 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272412 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2780 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008023 | SPARK PLUG ASY;NP SMO0480502 | 4 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 406 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008023 | SPARK PLUG ASY;NP SMO0480502 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008059 | SPRING,COMP;SS,NP SMQ33873 | 2 | EA | 14 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 523 cannot be changed 90028419 item 3780 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 523 | 0 | EA | 102000000030501 | 102000000030130 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008059 | SPRING,COMP;SS,NP SMQ33873 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3780 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 523 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3810 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3230 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008060 | PLATE,LKG;NP SMR50004 | 4 | EA | 86 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 625 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008060 | PLATE,LKG;NP SMR50004 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1300 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008060 | PLATE,LKG;NP SMR50004 | 31 | EA | 86 | 0 | 0 | 27 | EA | 21.10 - ETA 14.03.25 PO 4500031859 QTY 58 SOH FCA | Supply for Order 200091513, Item 153 cannot be changed 90028419 item 1170 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 153 | 0 | EA |  |  | 102000000030916 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008060 | PLATE,LKG;NP SMR50004 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1170 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 153 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1190 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008060 | PLATE,LKG;NP SMR50004 | 31 | EA | 86 | 0 | 0 | 31 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 132 cannot be changed 90028419 item 1060 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1070 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 132 | 0 | EA | 102000000030480 | 102000000030915 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008060 | PLATE,LKG;NP SMR50004 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1060 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 132 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1070 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2680 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008060 | PLATE,LKG;NP SMR50004 | 2 | EA | 86 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 396 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008060 | PLATE,LKG;NP SMR50004 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0730 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008074 | PLATE,LKG;SS304,NP SMR22241 | 4 | EA | 239 | 0 | 0 | 4 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 474 cannot be changed 90028419 item 3330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 474 | 0 | EA | 102000000030481 | 102000000031815 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008074 | PLATE,LKG;SS304,NP SMR22241 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3330 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 474 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3360 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1950 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008077 | BUSH,VV;SS,NP SMR26007 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 275 cannot be changed 90028419 item 2140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 275 | 0 | EA | 102000000030501 | 102000000031194 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ONCONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008077 | BUSH,VV;SS,NP SMR26007 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_2140 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 275 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2170 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0990 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008079 | PLATE,LKG;SS304,NP SMR50010 | 20 | EA | 26 | 0 | 0 | 20 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 114 cannot be changed 90028419 item 910 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 920 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 114 | 0 | EA | 102000000030487 | 102000000030590 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0910 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008079 | PLATE,LKG;SS304,NP SMR50010 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0910 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 114 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 920 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0610 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008093 | SEAL,TUBE,SPARK PLUG;SS304,NP SMR67407 | 2 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 61 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008093 | SEAL,TUBE,SPARK PLUG;SS304,NP SMR67407 |  |  |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1960 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008103 | RING,PKG;PTFE,NP SMZ33868 | 6 | EA | 0 | 0 | 0 | 0 |  | 10.02 - ETA 19.02.25 PO 4500031502 BH MOT 40794 | Supply for Order 200091513, Item 276 cannot be changed 90028419 item 2150 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 276 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ONCONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008103 | RING,PKG;PTFE,NP SMZ33868 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_2150 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 276 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2180 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1530 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008110 | HELICOIL,LKG;NP RFR330000000 | 2 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 218 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008110 | HELICOIL,LKG;NP RFR330000000 |  |  |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1580 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008112 | HELICOIL,LKG;NP RFR330030000 | 8 | EA | 806 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 696 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008112 | HELICOIL,LKG;NP RFR330030000 |  |  |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008112 | HELICOIL,LKG;NP RFR330030000 | 18 | EA | 806 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 9 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008112 | HELICOIL,LKG;NP RFR330030000 |  |  |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1550 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008117 | HELICOIL,LKG;NP RFR331080000 | 8 | EA | 651 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 220 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008117 | HELICOIL,LKG;NP RFR331080000 |  |  |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0860 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008120 | HELICOIL,LKG;NP RFU331090060 | 26 | EA | 634 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 480 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 26 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008120 | HELICOIL,LKG;NP RFU331090060 |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008120 | HELICOIL,LKG;NP RFU331090060 | 1 | EA | 634 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 491 cannot be changed 90028419 item 3470 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 491 | 0 | EA | 102000000030487 | 102000000030775 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3470 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008120 | HELICOIL,LKG;NP RFU331090060 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3470 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 491 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3500 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0300 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008120 | HELICOIL,LKG;NP RFU331090060 | 2 | EA | 634 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 666 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008120 | HELICOIL,LKG;NP RFU331090060 |  |  |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1190 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008121 | HELICOIL,LKG;NP RFU330030060 | 1 | EA | 116 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 492 cannot be changed 90028419 item 3480 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 492 | 0 | EA | 102000000030487 | 102000000030070 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3480 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008121 | HELICOIL,LKG;NP RFU330030060 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3480 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 492 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3510 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008122 | HELICOIL;NP RFU331040060 | 18 | EA | 142 | 0 | 0 | 18 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 128 cannot be changed 90028419 item 1020 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1030 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 128 | 0 | EA | 102000000030480 | 102000000030075 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008122 | HELICOIL;NP RFU331040060 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1020 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 128 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1030 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0310 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008124 | NUT,ALLEN;0.750"-10 UN,CS,NP RDQ00226 | 4 | EA | 60 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 667 cannot be changed 90028419 item 4450 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 667 | 0 | EA | 102000000030489 | 102000000031156 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008124 | NUT,ALLEN;0.750"-10 UN,CS,NP RDQ00226 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_4450 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 667 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4480 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0120 | 1660 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008124 | NUT,ALLEN;0.750"-10 UN,CS,NP RDQ00226 | 4 | EA | 60 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 233 cannot be changed 90028419 item 1760 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 233 | 0 | EA | 102000000030497 | 102000000031155 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1760 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008124 | NUT,ALLEN;0.750"-10 UN,CS,NP RDQ00226 | 2024-07-21 | W |  | 0120 | NO 4 BEARING & LP THRUST | INT | NO 4 BEARING & LP THRUST | 5 |  | 90028419_1760 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 233 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1790 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008127 | O-RING;0.139",VIT A,NP KHA152003501 | 2 | EA | 5 | 0 | 2 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 317 cannot be changed 90028419 item 2490 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 317 | 0 | EA | 102000000030482 | 102000000030316 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008127 | O-RING;0.139",VIT A,NP KHA152003501 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2490 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 317 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2520 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3020 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008165 | GASKET;C4500,KLINGER 0WOO10008165 | 3 | EA | 6 | 0 | 0 | 3 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 431 cannot be changed 90028419 item 3020 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3050 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 431 | 0 | EA | 102000000030494 | 102000000030089 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008165 | GASKET;C4500,KLINGER 0WOO10008165 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_3020 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 431 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3050 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008166 | GASKET;C4500,KLINGER 0WOO10008166 | 3 | EA | 4 | 0 | 0 | 2 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 432 cannot be changed 90028419 item 3030 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3060 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 432 | 0 | EA | 102000000030609 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008166 | GASKET;C4500,KLINGER 0WOO10008166 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_3030 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 432 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3060 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2840 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008168 | BEARING,HALF;NP IRR185950007 | 4 | EA | 0 | 0 | 4 | 4 | EA | 06.01 - SOH @ AA02 | Supply for Order 200091513, Item 413 cannot be changed 9026844 item 2860 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122102 | 9026844 | 05 | Preparation | 0000129822 | 413 | 0 | EA |  |  | 102000000030737 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000389443_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056463 | 1020 | 2025-07-03 | 4 |  | 2025-02-05 | 4900228036_2025_0001 | 2025-03-01 |  | 5000389443_2025_0001 | 0 | 2 | 0 | 90028419 | 4 | 0 | 180122102 | 2 | 0 | 0 | X | L | 4900228036 | 2025 |  | 5000389443 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008168 | BEARING,HALF;NP IRR185950007 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 9026844_2860 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 413 |  | 0 |  | 25SD2420 | MJ | 1000005037 | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2890 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2850 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008169 | BEARING,HALF;NP IRR185951494 | 4 | EA | 0 | 0 | 4 | 4 | EA | 27.09 - qty 4 SOH at AA02 | Supply for Order 200091513, Item 414 cannot be changed 9026473 item 2870 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2900 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122408 | 9026473 | 05 | Preparation | 0000129822 | 414 | 0 | EA |  |  | 102000000030739 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000389650_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055871 | 1020 | 2025-07-03 | 4 |  | 2025-02-06 | 4900228955_2025_0001 | 2025-03-01 |  | 5000389650_2025_0001 | 0 | 2 | 0 | 90028419 | 4 | 0 | 180122408 | 2 | 0 | 0 | X | L | 4900228955 | 2025 |  | 5000389650 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008169 | BEARING,HALF;NP IRR185951494 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 9026473_2870 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 414 |  | 0 |  | 25SD2420 | MJ | 1000005037 | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2900 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2950 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008170 | DRIVER,QUILL SHFT;NP SMO0920603 | 1 | EA | 9 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 424 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008170 | DRIVER,QUILL SHFT;NP SMO0920603 |  |  |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2870 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008172 | BEARING,DRV;144X76X51MM,CS,NP SMO0920621 | 2 | EA | 4 | 0 | 2 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 416 cannot be changed 9026847 item 2880 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2910 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122106 | 9026847 | 05 | Preparation | 0000129822 | 416 | 0 | EA |  |  | 102000000030770 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000389424_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056466 | 1020 | 2025-07-03 | 2 |  | 2025-02-05 | 4900228037_2025_0001 | 2025-03-01 |  | 5000389424_2025_0001 | 0 | 2 | 0 | 90028419 | 2 | 0 | 180122106 | 2 | 0 | 0 | X | L | 4900228037 | 2025 |  | 5000389424 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008172 | BEARING,DRV;144X76X51MM,CS,NP SMO0920621 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 9026847_2880 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 416 |  | 0 |  | 25SD2420 | MJ | 1000005037 | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2910 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2880 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008173 | BEARING,DRV,OIL PP;CS,NP SMO0920622 | 2 | EA | 5 | 0 | 2 | 2 | EA | 06.01 - SOH @ AA02 | Supply for Order 200091513, Item 417 cannot be changed 9026847 item 2890 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2920 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122106 | 9026847 | 05 | Preparation | 0000129822 | 417 | 0 | EA |  |  | 102000000030736 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000389423_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056466 | 1020 | 2025-07-03 | 2 |  | 2025-02-05 | 4900228037_2025_0003 | 2025-03-01 |  | 5000389423_2025_0001 | 0 | 2 | 0 | 90028419 | 2 | 0 | 180122106 | 2 | 0 | 0 | X | L | 4900228037 | 2025 |  | 5000389423 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008173 | BEARING,DRV,OIL PP;CS,NP SMO0920622 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 9026847_2890 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 417 |  | 0 |  | 25SD2420 | MJ | 1000005037 | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2920 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2930 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008174 | GEAR,NP MS5352B &MS3002,HELICAL,DRV | 1 | EA | 6 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 422 cannot be changed 90028419 item 2940 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 422 | 0 | EA | 102000000030731 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2940 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008174 | GEAR,NP MS5352B &MS3002,HELICAL,DRV | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2940 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 422 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2970 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2940 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008175 | GEAR,DRV;NP IRR185950160 | 1 | EA | 2 | 0 | 0 | 1 | EA | 06.01 - SOH @ AA02 | Supply for Order 200091513, Item 423 cannot be changed 90028419 item 2950 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2980 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 423 | 0 | EA | 102000000030903 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2950 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008175 | GEAR,DRV;NP IRR185950160 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2950 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 423 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2980 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2980 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008178 | SEAL,OIL;AL,NP SMS23066 | 2 | EA | 1 | 0 | 0 | 1 | EA | 20.12 - ETA 01.10.25 PO 4500031516 BH FCA | Supply for Order 200091513, Item 427 cannot be changed 90028419 item 2980 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3010 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 427 | 0 | EA | 102000000030494 | 102000000030470 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2980 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008178 | SEAL,OIL;AL,NP SMS23066 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2980 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 427 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3010 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2990 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008179 | SEAL,OIL;AL,NP SMS23101 | 2 | EA | 0 | 0 | 0 | 0 |  | 10.03 - ETA 10.03.25 PO 4500049087 BH FCA | Supply for Order 200091513, Item 428 cannot be changed 90028419 item 2990 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3020 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 428 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2990 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008179 | SEAL,OIL;AL,NP SMS23101 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2990 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 428 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3020 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1920 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008187 | PUMP,HYD;NP RPO10017 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 266 cannot be changed 90028419 item 2050 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2080 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 266 | 0 | EA | 102000000031284 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008187 | PUMP,HYD;NP RPO10017 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2050 |  |  | DG1 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 266 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2080 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1930 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008190 | PUMP,AUX;HYD OIL,GE 267A8438P001 | 1 | EA | 3 | 0 | 1 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 267 cannot be changed 90028419 item 2060 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2090 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 267 | 0 | EA | 102000000030095 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008190 | PUMP,AUX;HYD OIL,GE 267A8438P001 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2060 |  |  | DG1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 267 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2090 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0010 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008193 | GASKET;470X490X1.5MM KX2,NP SVZ46640 | 2 | EA | 14 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 603 cannot be changed 90028419 item 4100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 603 | 0 | EA | 102000000030607 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008193 | GASKET;470X490X1.5MM KX2,NP SVZ46640 | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4100 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 603 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008204 | ROLL PIN,NP MS5352B,RAM POST,3X12MM | 32 | EA | 901 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 433 cannot be changed 90028419 item 3040 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3070 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 433 | 0 | EA | 102000000030494 | 102000000030600 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008204 | ROLL PIN,NP MS5352B,RAM POST,3X12MM | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_3040 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 433 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3070 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1560 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008204 | ROLL PIN,NP MS5352B,RAM POST,3X12MM | 32 | EA | 901 | 0 | 0 | 32 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 198 cannot be changed 90028419 item 1540 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 198 | 0 | EA | 102000000030498 | 102000000030599 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1540 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008204 | ROLL PIN,NP MS5352B,RAM POST,3X12MM | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1540 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 198 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1570 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2920 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008207 | RAM,HYD;NP SMO0920696 | 2 | EA | 8 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 421 cannot be changed 90028419 item 2930 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2960 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 421 | 0 | EA | 102000000030494 | 102000000030232 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2930 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008207 | RAM,HYD;NP SMO0920696 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2930 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 421 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2960 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0870 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10008238 | HELICOIL;NP RFU330950060 | 4 | EA | 1124 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 481 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008238 | HELICOIL;NP RFU330950060 |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1200 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008238 | HELICOIL;NP RFU330950060 | 2 | EA | 1124 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 493 cannot be changed 90028419 item 3490 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 493 | 0 | EA | 102000000030487 | 102000000030776 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008238 | HELICOIL;NP RFU330950060 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_3490 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 493 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3520 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008255 | PIN,STR;NP FJV03009 | 4 | EA | 14 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 501 cannot be changed 90028419 item 3570 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 501 | 0 | EA | 102000000030480 | 102000000030166 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3570 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008255 | PIN,STR;NP FJV03009 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_3570 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 501 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3600 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0050 | 0760 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008260 | BOLT,HEX;ALLOY ST,NP GTG19050 | 16 | EA | 73 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 477 cannot be changed 90028419 item 3360 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 477 | 0 | EA | 102000000030502 | 102000000030985 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3360 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008260 | BOLT,HEX;ALLOY ST,NP GTG19050 | 2024-07-21 | W |  | 0050 | WRAPPER & TRANSITION PIECES | INT | WRAPPER & TRANSITION PIECES | 5 |  | 90028419_3360 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 477 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3390 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008262 | SEAL,PIPE,DRN;VIT A,NP KFZ320710904 | 5 | EA | 23 | 0 | 0 | 5 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 304 cannot be changed 90028419 item 2370 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 304 | 0 | EA | 102000000030491 | 102000000030472 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2370 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008262 | SEAL,PIPE,DRN;VIT A,NP KFZ320710904 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2370 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 304 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2400 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2260 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008263 | SEAL,PIPE,DRN;VIT A,NP KFZ320710904 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 305 cannot be changed 90028419 item 2380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 305 | 0 | EA | 102000000030491 | 102000000030473 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008263 | SEAL,PIPE,DRN;VIT A,NP KFZ320710904 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2380 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 305 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2410 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1400 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008268 | SHAFT,RING RL,NOZ;NP RPQ03176 | 6 | EA | 24 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 182 cannot be changed 90028419 item 1380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 182 | 0 | EA | 102000000030498 | 102000000031167 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008268 | SHAFT,RING RL,NOZ;NP RPQ03176 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1380 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 182 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1410 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2440 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008342 | ELEMENT,FLT;NP IRS2629702 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA01 | Supply for Order 200091513, Item 722 cannot be changed 90028419 item 4850 already exists | Material picked; currently at SW3R02A05A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 722 | 0 | EA |  |  | 102000000032802 |  |  |  |  | WorkPackLink | SW3R02A05A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4850 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008342 | ELEMENT,FLT;NP IRS2629702 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_4850 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 722 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4890 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0640 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10008632 | O-RING;BS245,DEMAG 23230810281219151030 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091505, Item 72 cannot be changed 90025019 item 700 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 700 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 72 | 0 | EA | 102000000032113 | 102000000027597 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0700 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008632 | O-RING;BS245,DEMAG 23230810281219151030 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0700 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 72 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 700 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10008750 | CORD:O-RING,VITON,NP,MAV200134 | 1 | EA | 50 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091513, Item 124 cannot be changed 90028419 item 980 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 124 | 0 | EA | 102000000030487 | 102000000030295 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0980 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008750 | CORD:O-RING,VITON,NP,MAV200134 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0980 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 124 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 990 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0090 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008802 | GASKET,METALLIC;NP KBA002401720 | 2 | EA | 6 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 168 cannot be changed 90028418 item 750 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 168 | 0 | EA | 102000000030535 | 102000000030884 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | frame gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008802 | GASKET,METALLIC;NP KBA002401720 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0750 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 168 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 780 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0760 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008944 | RING,PST;CPI 192,NP SQO28316 | 6 | EA | 8 | 0 | 0 | 6 | EA | 29.01 - Consumed | Supply for Order 200147980, Item 141 cannot be changed 180087838 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180087838 | 90023056 | 05 | Preparation | 0000236589 | 141 | 0 | EA |  |  | 102000000022473 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  | 6 | 0 |  |  | Y | 1001 | 2024-09-24 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000038415 | 1020 | 2025-12-14 | 6 |  | 2024-10-30 | 4900161867_2024_0001 | 2025-03-01 |  | 5000262420_2024_0001 | 0 | 2 | 0 | 90023056 | 6 | 0 | 180087838 | 2 | 0 | 0 | X | L | 4900161867 | 2024 |  | 5000262420 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008944 | RING,PST;CPI 192,NP SQO28316 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90023056_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 141 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 530 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0770 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008945 | RING,RIDER;CPI 192,NP SQO87275 | 4 | EA | 4 | 0 | 0 | 4 | EA | 29.01 - Consumed | Supply for Order 200147980, Item 142 cannot be changed 180087838 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180087838 | 90023056 | 05 | Preparation | 0000236589 | 142 | 0 | EA |  |  | 102000000022474 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  | 4 | 0 |  |  | Y | 1001 | 2024-09-24 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000038415 | 1020 | 2025-12-14 | 4 |  | 2024-10-30 | 4900161867_2024_0003 | 2025-03-01 |  | 5000262430_2024_0001 | 0 | 2 | 0 | 90023056 | 4 | 0 | 180087838 | 2 | 0 | 0 | X | L | 4900161867 | 2024 |  | 5000262430 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008945 | RING,RIDER;CPI 192,NP SQO87275 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90023056_0020 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 142 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 540 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0770 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008946 | RING,PKG;CPI 192,NP SPO73996 | 10 | EA | 20 | 0 | 0 | 10 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 147 cannot be changed 90028418 item 560 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 147 | 0 | EA | 102000000030538 | 102000000030868 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008946 | RING,PKG;CPI 192,NP SPO73996 | 2024-09-23 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90028418_0560 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 147 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 590 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0780 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008947 | RING,PKG;CPI 192,NP SPO73995 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 148 cannot be changed 90028418 item 570 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 148 | 0 | EA | 102000000030538 | 102000000030869 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0570 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008947 | RING,PKG;CPI 192,NP SPO73995 | 2024-09-23 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90028418_0570 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 148 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 600 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0130 | 0600 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008948 | RING,PKG;CPI 192,NP SPO73997 | 4 | EA | 10 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 60 cannot be changed 90028418 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 60 | 0 | EA | 102000000030540 | 102000000030872 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008948 | RING,PKG;CPI 192,NP SPO73997 | 2024-09-23 | W |  | 0130 | INTERMEDIATE PACKING | INT | INTERMEDIATE PACKING | 5 |  | 90028418_0080 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 60 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 90 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0790 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008948 | RING,PKG;CPI 192,NP SPO73997 | 2 | EA | 10 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 149 cannot be changed 90028418 item 580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 149 | 0 | EA | 102000000030538 | 102000000030874 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008948 | RING,PKG;CPI 192,NP SPO73997 | 2024-09-23 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90028418_0580 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 149 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 610 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0150 | 0690 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008948 | RING,PKG;CPI 192,NP SPO73997 | 2 | EA | 10 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 120 cannot be changed 90028418 item 390 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 120 | 0 | EA | 102000000030547 | 102000000030873 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0390 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008948 | RING,PKG;CPI 192,NP SPO73997 | 2024-09-23 | W |  | 0150 | PARTITION COVER OIL SCRAPPER | INT | PARTITION COVER OIL SCRAPPER | 5 |  | 90028418_0390 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 120 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 400 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0750 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.10.2024) | 10008951 | PISTON;NP SRP56116 | 2 | EA | 1 | 0 | 0 | 2 | EA | 31.10 - AT KGP | Supply for Order 200147980, Item 140 cannot be changed 180087895 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 910 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180087895 | 90023066 | 05 | Preparation | 0000236589 | 140 | 0 | EA |  |  | 102000000022552 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-09-24 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000038466 | 1020 | 2025-12-14 | 2 |  | 2024-10-30 | 4900161981_2024_0001 | 2025-03-01 |  | 5000262467_2024_0001 | 0 | 2 | 0 | 90023066 | 2 | 0 | 180087895 | 2 | 0 | 0 | X | L | 4900161981 | 2024 |  | 5000262467 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008951 | PISTON;NP SRP56116 | 2024-10-30 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90023066_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 140 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 910 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0080 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008953 | WASHER;NP RRP41569 | 8 | EA | 32 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 167 cannot be changed 90028418 item 740 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 167 | 0 | EA | 102000000030535 | 102000000030363 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Main washer |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008953 | WASHER;NP RRP41569 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0740 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 167 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 770 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0070 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008954 | NUT,COMP;NP RDO02292 | 8 | EA | 11 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 166 cannot be changed 90028418 item 730 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 166 | 0 | EA | 102000000030535 | 102000000030948 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Main nut |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008954 | NUT,COMP;NP RDO02292 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0730 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 166 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 760 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0060 | 0020 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008969 | GASKET;2MMTHK,NP KFZ257650604 | 4 | EA | 12 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 182 cannot be changed 90028418 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 182 | 0 | EA | 102000000030942 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008969 | GASKET;2MMTHK,NP KFZ257650604 | 2024-09-23 | W |  | 0060 | CYLINDER | INT | CYLINDER | 5 |  | 90028418_0010 |  |  | ST5 |  | B1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 182 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0050 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008970 | GASKET;1510X1115MM,NEOP,NP KFZ274760684 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 164 cannot be changed 90028418 item 710 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 164 | 0 | EA | 102000000030535 | 102000000030282 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0710 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Cov gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008970 | GASKET;1510X1115MM,NEOP,NP KFZ274760684 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0710 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 164 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 740 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0140 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008971 | GASKET;JIG SAW PUZZLE,NP KFZ274770604 | 2 | EA | 6 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 173 cannot be changed 90028418 item 800 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 173 | 0 | EA | 102000000030535 | 102000000030086 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0800 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE Shield |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008971 | GASKET;JIG SAW PUZZLE,NP KFZ274770604 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0800 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 173 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 830 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0150 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008972 | GASKET;CNAF C4500,NP KFZ274920604 | 1 | EA | 5 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 174 cannot be changed 90028418 item 810 already exists | Material picked; currently at SW3R01D02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 174 | 0 | EA |  |  | 102000000030943 |  |  |  |  | WorkPackLink | SW3R01D02A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0810 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE Shield |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008972 | GASKET;CNAF C4500,NP KFZ274920604 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0810 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 174 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 840 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0170 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008972 | GASKET;CNAF C4500,NP KFZ274920604 | 1 | EA | 5 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 176 cannot be changed 90028418 item 830 already exists | Material picked; currently at SW3R01D02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 176 | 0 | EA |  |  | 102000000030944 |  |  |  |  | WorkPackLink | SW3R01D02A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0830 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | NDE Shield |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008972 | GASKET;CNAF C4500,NP KFZ274920604 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0830 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 176 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 860 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0190 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008973 | GASKET;208X400MM INNER,NP 0WOO10008973 | 4 | EA | 10 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 178 cannot be changed 90028418 item 850 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 178 | 0 | EA | 102000000030535 | 102000000030084 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0850 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Crosshead |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008973 | GASKET;208X400MM INNER,NP 0WOO10008973 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0850 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 178 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 880 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0200 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008974 | GASKET;CNAF C4430,NP KFZ274990604 | 4 | EA | 10 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 179 cannot be changed 90028418 item 860 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 179 | 0 | EA | 102000000030890 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0860 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Crosshead |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008974 | GASKET;CNAF C4430,NP KFZ274990604 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0860 |  |  | ST5 |  | B1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 179 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 890 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0290 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008977 | O-RING;NP KHA089605300 | 2 | EA | 6 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 129 cannot be changed 90028418 item 450 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 129 | 0 | EA | 102000000030531 | 102000000030805 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008977 | O-RING;NP KHA089605300 | 2024-09-23 | W |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  | 90028418_0450 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 129 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 460 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0160 | 0810 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008978 | SEAL,OIL;NTRL RBR,NP RAZ13246 | 2 | EA | 6 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 146 cannot be changed 90028418 item 550 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 146 | 0 | EA | 102000000030536 | 102000000030304 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008978 | SEAL,OIL;NTRL RBR,NP RAZ13246 | 2024-09-23 | W |  | 0160 | PISTON ASSEMBLY | INT | PISTON ASSEMBLY | 5 |  | 90028418_0550 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 146 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 580 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0320 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10008981 | SHOE,XHD,COMP;NP SRN59196 | 2 | EA | 0 | 0 | 0 | 0 |  | 18.10 - BLOCKED STOCK @ AA01 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 132 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008981 | SHOE,XHD,COMP;NP SRN59196 |  |  |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0150 | 0700 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008982 | RING,SCRAPER;BZE,NP SPT55618 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 121 cannot be changed 90028418 item 400 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 121 | 0 | EA | 102000000030547 | 102000000030867 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0400 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008982 | RING,SCRAPER;BZE,NP SPT55618 | 2024-09-23 | W |  | 0150 | PARTITION COVER OIL SCRAPPER | INT | PARTITION COVER OIL SCRAPPER | 5 |  | 90028418_0400 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 121 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 410 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0150 | 0710 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008983 | RING,OIL SCRAPER;BZE,NP SPT55619 | 4 | EA | 8 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 122 cannot be changed 90028418 item 410 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 122 | 0 | EA | 102000000030547 | 102000000030870 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0410 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008983 | RING,OIL SCRAPER;BZE,NP SPT55619 | 2024-09-23 | W |  | 0150 | PARTITION COVER OIL SCRAPPER | INT | PARTITION COVER OIL SCRAPPER | 5 |  | 90028418_0410 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 122 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 420 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0150 | 0720 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008984 | RING,OIL SCRAPER;BZE,NP SPT55620 | 4 | EA | 8 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 123 cannot be changed 90028418 item 420 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 123 | 0 | EA | 102000000030547 | 102000000030871 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0420 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008984 | RING,OIL SCRAPER;BZE,NP SPT55620 | 2024-09-23 | W |  | 0150 | PARTITION COVER OIL SCRAPPER | INT | PARTITION COVER OIL SCRAPPER | 5 |  | 90028418_0420 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 123 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 430 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0800 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008985 | O-RING;VIT,NP KHA158402601 | 6 | EA | 13 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 150 cannot be changed 90028418 item 590 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 620 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 150 | 0 | EA | 102000000030538 | 102000000030314 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0590 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008985 | O-RING;VIT,NP KHA158402601 | 2024-09-23 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90028418_0590 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 150 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 620 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0180 | 0780 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008986 | RING,SHLD HALF;BZE,NP SPT56111 | 2 | EA | 2 | 0 | 0 | 2 | EA | 20.02 - SOH @ AA02 | Supply for Order 200147980, Item 158 cannot be changed 90028418 item 660 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 690 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 158 | 0 | EA | 101000000146895 |  | 101000000146341 | 01-Road |  | 3-In Transit |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  | 2025-02-21 | Y | 1001 | 2024-09-24 | ODST-0090028418_0660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008986 | RING,SHLD HALF;BZE,NP SPT56111 | 2024-09-23 | W |  | 0180 | SHOULDER HALF RING | INT | SHOULDER HALF RING | 5 |  | 90028418_0660 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 158 |  | 0 |  | 25SDSTB5 | MJ | 20005096 | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 690 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-19 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0040 | 0120 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10008991 | BUSH,PST RON;ALLOY ST,NP SPP682250400 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 111 | 0 | [8 empty] | WorkPackLink |  | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  |  |  |  | Little end |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008991 | BUSH,PST RON;ALLOY ST,NP SPP682250400 |  |  |  | 0040 | CONNECTING ROD | INT | CONNECTING ROD | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0810 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10008995 | O-RING;BS159,VIT,NP KHA126602601 | 6 | EA | 7 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 151 cannot be changed 90028418 item 600 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 151 | 0 | EA | 102000000030482 | 102000000030804 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0600 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008995 | O-RING;BS159,VIT,NP KHA126602601 | 2024-09-23 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90028418_0600 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 151 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 630 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0300 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10008999 | PIN,XHD,COMP;NP SRQ41118 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 130 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008999 | PIN,XHD,COMP;NP SRQ41118 |  |  |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0270 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10009000 | NUT,XHD;ALLOY ST 40CRM04,NP SQQ11695 | 1 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 127 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009000 | NUT,XHD;ALLOY ST 40CRM04,NP SQQ11695 |  |  |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0260 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10009001 | NUT,CROSS;ALLOY ST 40CRM04,NP SQQ11696 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 126 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009001 | NUT,CROSS;ALLOY ST 40CRM04,NP SQQ11696 |  |  |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0340 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009002 | WASHER,TAB;1.5MM THK,CS,NP FNJ01370 | 4 | EA | 9 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 134 cannot be changed 90028418 item 480 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 134 | 0 | EA | 102000000030531 | 102000000030284 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0480 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009002 | WASHER,TAB;1.5MM THK,CS,NP FNJ01370 | 2024-09-23 | W |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  | 90028418_0480 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 134 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 490 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0820 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009003 | O-RING;BS010,VIT,NP KHA006001701 | 34 | EA | 72 | 0 | 0 | 34 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 152 cannot be changed 90028418 item 610 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 152 | 0 | EA | 102000000030538 | 102000000030298 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 34 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0610 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009003 | O-RING;BS010,VIT,NP KHA006001701 | 2024-09-23 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90028418_0610 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 152 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 640 |  |  | 0 | 34 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0060 | 0030 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009007 | QUILL,LUB,OIL;NP SNO2701104 | 4 | EA | 2 | 0 | 0 | 2 | EA | 15.10 - ETA 18.03.25 PO 4500031473 BH | Supply for Order 200147980, Item 183 cannot be changed 90028418 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 183 | 0 | EA | 102000000030532 | 102000000030808 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009007 | QUILL,LUB,OIL;NP SNO2701104 | 2024-09-23 | W |  | 0060 | CYLINDER | INT | CYLINDER | 5 |  | 90028418_0020 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 183 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0280 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009024 | O-RING;161.9MM ID,BUNA-N,NP KHA161906900 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 128 cannot be changed 90028418 item 440 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 128 | 0 | EA | 102000000030531 | 102000000030875 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0440 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009024 | O-RING;161.9MM ID,BUNA-N,NP KHA161906900 | 2024-09-23 | W |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  | 90028418_0440 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 128 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 450 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0150 | 0730 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009044 | O-RING;BS259,NP KHA158303500 | 2 | EA | 8 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 124 cannot be changed 90028418 item 430 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 124 | 0 | EA | 102000000030547 | 102000000030803 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0430 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009044 | O-RING;BS259,NP KHA158303500 | 2024-09-23 | W |  | 0150 | PARTITION COVER OIL SCRAPPER | INT | PARTITION COVER OIL SCRAPPER | 5 |  | 90028418_0430 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 124 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 440 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0350 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10009080 | WASHER;NP FNC01210 | 16 | EA | 54 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 135 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009080 | WASHER;NP FNC01210 |  |  |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0360 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10009081 | WASHER;NP FNJ01210 | 16 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 136 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009081 | WASHER;NP FNJ01210 |  |  |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-03-04 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0220 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | No issue identified | 10009083 | BEARING,HALF,MN;AL CTD,NP SQP078300200 | 4 | EA | 0 | 0 | 8 | 0 |  | 07.03 - DEL: 80033368 |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032182 | 05 | Preparation | 0000236589 | 194 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090032182_0010 | 0 | 8 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-09 |  |  |  |  | 2025-12-14 | 0 |  | 2025-03-04 |  | 2025-03-09 | Main Bearing |  | 0 | 2 | 0 | 90032182 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009083 | BEARING,HALF,MN;AL CTD,NP SQP078300200 |  |  |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90032182_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 194 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 970 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0040 | 0110 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009083 | BEARING,HALF,MN;AL CTD,NP SQP078300200 | 4 | EA | 0 | 0 | 8 | 4 | EA | 23.01 - SOH @ AA02 | Supply for Order 200147980, Item 107 cannot be changed 9026560 item 290 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180123210 | 9026560 | 05 | Preparation | 0000236589 | 107 | 0 | EA | 102000000032720 |  | 107000000000134 |  |  |  | P07WH-R3FL | WorkPackLink | P07WH-R3FL | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-24 | GRST-5000391766_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056707 | 1020 | 2025-12-14 | 4 |  | 2025-02-07 | 4900230425_2025_0003 | 2025-03-01 |  | 5000391766_2025_0002 | 0 | 2 | 0 | 90028418 | 4 | 0 | 180123210 | 2 | 0 | 0 | X | L | 4900230425 | 2025 |  | 5000391766 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009083 | BEARING,HALF,MN;AL CTD,NP SQP078300200 | 2024-09-23 | W |  | 0040 | CONNECTING ROD | INT | CONNECTING ROD | 5 |  | 9026560_0290 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 107 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 300 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0860 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10009085 | BOX,STUFFING;NP SNO9738546 | 2 | ASY | 0 | 0 | 2 | 2 | ASY | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 186 cannot be changed 9026469 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  | REFURB |  | 180122345 | 9026469 | 05 | Preparation | 0000236589 | 186 | 0 | ASY |  |  | 102000000030940 | 01-Road |  | 1-Not Started |  | WorkPackLink | P07WHS-R5A |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-24 | GRST-5000389464_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055867 | 1020 | 2025-12-14 | 2 |  | 2025-02-06 | 4900228860_2025_0001 | 2025-03-01 |  | 5000389464_2025_0001 | 0 | 2 | 0 | 90028418 | 2 | 0 | 180122345 | 2 | 0 | 0 | X | L | 4900228860 | 2025 |  | 5000389464 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009085 | BOX,STUFFING;NP SNO9738546 | 2024-09-30 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 9026469_0050 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 186 |  | 0 |  | 25SDSTB5 | MJ | 1000004969 | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 60 |  |  | 0 | 2 | ASY | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-07 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0060 | 0040 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009086 | O-RING;BS460,SI RBR,NP KHA393006901 | 6 | EA | 6 | 0 | 0 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 184 cannot be changed 90028418 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 184 | 0 | EA | 102000000030532 | 102000000030312 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009086 | O-RING;BS460,SI RBR,NP KHA393006901 | 2024-09-23 | W |  | 0060 | CYLINDER | INT | CYLINDER | 5 |  | 90028418_0030 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 184 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 1050 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009265 | SEALANT,PIGNONE MCL,HORIZ SPLIT LINE | 3 | CQ | 24 | 0 | 0 | 3 | CQ | 02.10 - SOH @ AA02 | Supply for Order 200147980, Item 105 cannot be changed 90028418 item 270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 105 | 0 | CQ | 102000000030309 | 102000000030131 | 102000000034408 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009265 | SEALANT,PIGNONE MCL,HORIZ SPLIT LINE | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0270 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 105 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 280 |  |  | 0 | 3 | CQ | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0162 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009536 | FRAME KIT;THOMASSEN 2395000100 | 1 | KIT | 1 | 0 | 0 | 1 | KIT | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 137 cannot be changed 90023534 item 850 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1140 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 137 | 0 | KIT | 102000000030435 | 102000000030999 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0850 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009536 | FRAME KIT;THOMASSEN 2395000100 | 2024-05-11 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 90023534_0850 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 137 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1140 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0212 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009565 | GASKET;SI,THOMASSEN 2428000100 | 2 | EA | 10 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 111 cannot be changed 90023534 item 620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 111 | 0 | EA | 102000000030443 | 102000000031103 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009565 | GASKET;SI,THOMASSEN 2428000100 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0620 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 111 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 890 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0142 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009586 | O-RING;NTRL,THOMASSEN 2430126101 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 21 cannot be changed 90023534 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 21 | 0 | EA | 102000000030454 | 102000000031172 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009586 | O-RING;NTRL,THOMASSEN 2430126101 | 2024-01-02 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0130 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 21 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 200 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0100 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009587 | O-RING;NTRL,THOMASSEN 2430108501 | 8 | EA | 0 | 0 | 0 | 0 |  | 09.12 - ETA 19.03.25 PO 4500037854 ex Howden | Supply for Order 200091126, Item 116 cannot be changed 90023534 item 650 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 940 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 116 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0650 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009587 | O-RING;NTRL,THOMASSEN 2430108501 | 2024-05-11 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 90023534_0650 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 116 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 940 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0152 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009598 | GASKET;CS,THOMASSEN 2428127300 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 20 cannot be changed 90023534 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 20 | 0 | EA | 102000000030454 | 102000000031098 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009598 | GASKET;CS,THOMASSEN 2428127300 | 2024-01-02 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0120 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 20 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 190 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0162 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009602 | GASKET;CS,THOMASSEN 2428102000 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 22 cannot be changed 90023534 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 22 | 0 | EA | 102000000030454 | 102000000031096 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009602 | GASKET;CS,THOMASSEN 2428102000 | 2024-01-02 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0140 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 22 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 210 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0192 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009610 | BUSH,WIPER,COMP;THOMASSEN 2137164300 | 8 | EA | 0 | 0 | 0 | 0 |  | 09.03 - ETA 19.03.25 PO 4500037854 ex Howden CPT | Supply for Order 200091126, Item 131 cannot be changed 90023534 item 790 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1080 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 131 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0790 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | unloader |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009610 | BUSH,WIPER,COMP;THOMASSEN 2137164300 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0790 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 131 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1080 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0232 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009615 | PACKING,SET;ACUTATOR,HOERBIGER 3365405 | 4 | SET | 8 | 0 | 0 | 4 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 135 cannot be changed 90023534 item 830 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1120 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 135 | 0 | SET | 102000000030448 | 102000000029844 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0830 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | unloader |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009615 | PACKING,SET;ACUTATOR,HOERBIGER 3365405 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0830 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 135 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1120 |  |  | 0 | 4 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0212 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 4 | EA | 32 | 0 | 0 | 4 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091126, Item 133 cannot be changed 90023534 item 810 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 133 | 0 | EA |  |  | 102000000034369 |  |  |  |  | WorkPackLink | PACKING | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0810 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | unloader |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0810 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 133 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1100 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146436 | 0010 | 0010 | 200146436 | 1Y Cond Prod Pump Service - 5P2002B | AA53.5P2002B | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 4 | EA | 32 | 0 | 0 | 4 | EA | 19.02 - SOH @ AA02 | Supply for Order 200146436, Item 1 cannot be changed 90025016 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015715 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025016 | 05 | Preparation | 0000234313 | 1 | 0 | EA | 102000000031887 | 102000000034390 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025016_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025016 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025016_0010 |  |  | ST5 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231369 | S002 |  | 30 | 5300015715 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234313 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146437 | 0010 | 0010 | 200146437 | 1Y Cond Prod Pump Service - 5P2002A | AA53.5P2002A | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 4 | EA | 32 | 0 | 0 | 4 | EA | 19.02 - SOH @ AA02 | Supply for Order 200146437, Item 1 cannot be changed 90025015 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015714 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025015 | 05 | Preparation | 0000234314 | 1 | 0 | EA | 102000000031890 | 102000000034392 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025015_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025015 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025015_0010 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231370 | S002 |  | 30 | 5300015714 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234314 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146438 | 0010 | 0010 | 200146438 | 1Y Cond Heater Pump Service - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 8 | EA | 32 | 0 | 0 | 8 | EA | 19.02 - SOH @ AA02 | Supply for Order 200146438, Item 1 cannot be changed 90025014 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015713 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025014 | 05 | Preparation | 0000234315 | 1 | 0 | EA | 102000000031900 | 102000000034391 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025014_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025014 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 | Ready for Release | 90025014_0010 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231371 | S002 |  | 30 | 5300015713 | 10 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234315 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146439 | 0010 | 0010 | 200146439 | 1Y Cond Heater Pump Service - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 8 | EA | 32 | 0 | 0 | 8 | EA | 19.02 - SOH @ AA02 | Supply for Order 200146439, Item 1 cannot be changed 90025013 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015712 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025013 | 05 | Preparation | 0000234316 | 1 | 0 | EA | 102000000031907 | 102000000027841 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025013_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025013 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009625 | GASKET;C4430,THOMASSEN 2137152800 | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025013_0010 |  |  | ST5 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231372 | S002 |  | 30 | 5300015712 | 10 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234316 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0202 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009671 | BUSHING;CENTERING,HOERBIRGER 1116753 | 8 | EA | 8 | 0 | 0 | 8 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091126, Item 132 cannot be changed 90023534 item 800 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1090 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 132 | 0 | EA | 102000000030448 | 102000000030525 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0800 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | unloader |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009671 | BUSHING;CENTERING,HOERBIRGER 1116753 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0800 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 132 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 1090 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0222 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009675 | GASKET;THOMASSEN 2137154900 | 4 | EA | 12 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 134 cannot be changed 90023534 item 820 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 134 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0820 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | unloader |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009675 | GASKET;THOMASSEN 2137154900 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0820 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 134 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1110 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-03-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0012 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009723 | SCREW SET;THOMASSEN 1531052150 | 2 | EA | 0 | 0 | 0 | 2 | EA | 29.01 - Consumed | Supply for Order 200091126, Item 29 cannot be changed 180087670 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180087670 | 90023053 | 05 | Preparation | 0000129360 | 29 | 0 | EA | 102000000022406 |  | 107000000000391 |  |  |  | P07 - BENCH | WorkPackLink | P07-WAREHOUSE | P07 | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 31 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-03-01 |  |  | 2025-04-01 |  |  | 100000037985 | 1020 | 2023-04-03 | 2 |  | 2024-10-30 | 4900161656_2024_0003 | 2025-04-01 |  | 5000261860_2024_0002 | 0 | 2 | 0 | 90023053 | 2 | 0 | 180087670 | 2 | 0 | 0 | X | L | 4900161656 | 2024 |  | 5000261860 | 2024 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009723 | SCREW SET;THOMASSEN 1531052150 | 2024-01-02 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 90023053_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 29 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 270 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0130 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(25.09.2024) | 10009724 | NUT,PST;THOMASSEN 2153103600 | 2 | EA | 0 | 0 | 0 | 2 | EA | 29.01 - Consumed | Supply for Order 200091126, Item 148 cannot be changed 9025300 item 920 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180116480 | 9025300 | 05 | Preparation | 0000129360 | 148 | 0 | EA |  |  | 101000000135949 |  |  |  |  | WorkPackLink | P07-WAREHOUSE | P07 | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053326 | 1020 | 2023-04-03 | 2 |  | 2025-01-20 | 4900214560_2025_0003 | 2025-03-01 | pistonnut | 5000365663_2025_0002 | 0 | 2 | 0 | 90023534 | 2 | 0 | 180116480 | 2 | 0 | 0 | X | L | 4900214560 | 2025 |  | 5000365663 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009724 | NUT,PST;THOMASSEN 2153103600 | 2024-09-25 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 9025300_0920 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 148 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1240 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0022 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009769 | STUD,CYL;THOMASSEN 1501100753 | 16 | EA | 16 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 18 cannot be changed 90023534 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 18 | 0 | EA | 102000000030454 | 102000000031109 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009769 | STUD,CYL;THOMASSEN 1501100753 | 2024-01-02 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0100 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 18 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 170 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0012 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009770 | NUT,CYL;THOMASSEN 1441010108 | 16 | EA | 16 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 19 cannot be changed 90023534 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 19 | 0 | EA | 102000000030454 | 102000000031097 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009770 | NUT,CYL;THOMASSEN 1441010108 | 2024-01-02 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0110 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 19 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 180 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0102 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009771 | BEARING,BUSH;THOMASSEN 2583300502 | 1 | SET | 0 | 0 | 1 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 99 cannot be changed 9027111 item 510 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 780 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180124182 | 9027111 | 05 | Preparation | 0000129360 | 99 | 0 | SET |  |  | 102000000005586 |  |  |  |  | WorkPackLink | P07WHS-R3A | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000396369_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056762 | 1020 | 2023-04-03 | 1 |  | 2025-02-11 | 4900234046_2025_0001 | 2025-03-01 | NDE mains | 5000396369_2025_0001 | 0 | 2 | 0 | 90023534 | 1 | 0 | 180124182 | 2 | 0 | 0 | X | L | 4900234046 | 2025 |  | 5000396369 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009771 | BEARING,BUSH;THOMASSEN 2583300502 | 2024-05-11 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 9027111_0510 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 99 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 780 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0122 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009772 | GASKET;RBR,THOMASSEN 2424117100 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 101 cannot be changed 90023534 item 530 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 101 | 0 | EA | 102000000030435 | 102000000031175 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0530 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | NDE crank |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009772 | GASKET;RBR,THOMASSEN 2424117100 | 2024-05-11 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 90023534_0530 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 101 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 800 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0232 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009773 | STRAINER;SUCT,THOMASSEN 2720181600 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA01 | Supply for Order 200091126, Item 62 cannot be changed 90023534 item 220 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 62 | 0 | EA | 102000000030583 | 101000000134754 | 102000000030447 |  |  |  |  | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO Strainer |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009773 | STRAINER;SUCT,THOMASSEN 2720181600 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0220 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 62 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 460 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0252 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009774 | GASKET;61 ID X 132 OD X 0.8MM THK,C4430 | 1 | EA | 1 | 0 | 0 | 1 | EA | 24.02 - SOH @ AA02 | Supply for Order 200091126, Item 64 cannot be changed 90023534 item 230 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 64 | 0 | EA | 101000000146898 |  | 101000000146341 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  | 2025-02-21 | Y | 1001 | 2024-01-02 | ODST-0090023534_0230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO Strainer |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009774 | GASKET;61 ID X 132 OD X 0.8MM THK,C4430 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0230 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 64 |  | 0 |  | 25SD2301 | MJ | 20005096 | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 480 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-19 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0130 | 0022 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009775 | O-RING;RBR,THOMASSEN 0853855010 | 1 | EA | 0 | 0 | 0 | 0 |  | 09.03 - ETA 19.03.25 PO 4500037854 ex Howden CPT | Supply for Order 200091126, Item 138 cannot be changed 90023534 item 860 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 138 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0860 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009775 | O-RING;RBR,THOMASSEN 0853855010 | 2024-05-11 | W |  | 0130 | PRIMARY, INTER & OIL SCRAPER SEALS | INT | PRIMARY, INTER & OIL SCRAPER SEALS |  |  | 90023534_0860 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 138 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0130 | 0032 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009776 | RING,SEAL;PA 6,THOMASSEN 1478310120 | 1 | EA | 12 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 139 cannot be changed 90023534 item 870 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 139 | 0 | EA | 102000000030453 | 102000000031084 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0870 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009776 | RING,SEAL;PA 6,THOMASSEN 1478310120 | 2024-05-11 | W |  | 0130 | PRIMARY, INTER & OIL SCRAPER SEALS | INT | PRIMARY, INTER & OIL SCRAPER SEALS |  |  | 90023534_0870 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 139 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0132 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009778 | BEARING,LINING HALVES;THOMASSEN 2583300> | 1 | SET | 0 | 0 | 1 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 102 cannot be changed 9027109 item 540 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 810 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180124170 | 9027109 | 05 | Preparation | 0000129360 | 102 | 0 | SET |  |  | 102000000005585 |  |  |  |  | WorkPackLink | P07WHS-R3A | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000396433_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056760 | 1020 | 2023-04-03 | 1 |  | 2025-02-11 | 4900234064_2025_0001 | 2025-03-01 | DE mains | 5000396433_2025_0001 | 0 | 2 | 0 | 90023534 | 1 | 0 | 180124170 | 2 | 0 | 0 | X | L | 4900234064 | 2025 |  | 5000396433 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009778 | BEARING,LINING HALVES;THOMASSEN 2583300> | 2024-05-11 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 9027109_0540 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 102 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 810 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0142 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009779 | GASKET;NEOP,THOMASSEN 2424116900 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 103 cannot be changed 90023534 item 550 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 103 | 0 | EA | 102000000030435 | 102000000031176 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | top inspect |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009779 | GASKET;NEOP,THOMASSEN 2424116900 | 2024-05-11 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 90023534_0550 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 103 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 820 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0312 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009780 | GASKET;128MM ID,THOMASSEN 2426172102 | 1 | EA | 1 | 0 | 0 | 1 | EA | 24.02 - SOH @ AA02 | Supply for Order 200091126, Item 143 cannot be changed 90023534 item 890 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 143 | 0 | EA | 101000000147746 |  | 101000000147720 | 01-Road |  | 5-Completed |  | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2025-02-24 | 2025-02-23 | Y | 1001 | 2024-01-02 | ODST-0090023534_0890 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009780 | GASKET;128MM ID,THOMASSEN 2426172102 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0890 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 143 |  | 0 |  | 25SD2301 | MJ | 20005353 | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1200 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-21 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0322 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009781 | GASKET;102MM ID,THOMASSEN 2426142102 | 1 | EA | 1 | 0 | 0 | 1 | EA | 24.02 - SOH @ AA02 | Supply for Order 200091126, Item 144 cannot be changed 90023534 item 900 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 144 | 0 | EA | 101000000147747 |  | 101000000147720 | 01-Road |  | 5-Completed |  | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2025-02-24 | 2025-02-23 | Y | 1001 | 2024-01-02 | ODST-0090023534_0900 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009781 | GASKET;102MM ID,THOMASSEN 2426142102 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0900 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 144 |  | 0 |  | 25SD2301 | MJ | 20005353 | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1210 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-21 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0132 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009782 | GASKET;NEOP,THOMASSEN 2424106500 | 4 | EA | 9 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 85 cannot be changed 90023534 item 400 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 85 | 0 | EA | 102000000030443 | 102000000031177 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0400 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | xheadguidein |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009782 | GASKET;NEOP,THOMASSEN 2424106500 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0400 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 85 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 650 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0222 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009783 | RING,SEAL;THOMASSEN 2746108500 | 2 | SET | 4 | 0 | 0 | 2 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 112 cannot be changed 90023534 item 630 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 900 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 112 | 0 | SET | 102000000030443 | 102000000031071 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0630 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009783 | RING,SEAL;THOMASSEN 2746108500 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0630 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 112 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 900 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0172 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009784 | O-RING;THOMASSEN 2430100201 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 107 cannot be changed 90023534 item 580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 107 | 0 | EA | 102000000030443 | 102000000031165 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009784 | O-RING;THOMASSEN 2430100201 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0580 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 107 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 850 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0182 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009785 | GASKET;NEOP,THOMASSEN 2424107500 | 2 | EA | 5 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 108 cannot be changed 90023534 item 590 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 108 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0590 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009785 | GASKET;NEOP,THOMASSEN 2424107500 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0590 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 108 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 860 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0192 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009786 | RING,SEALING;RBR,THOMASSEN 1026100700 | 4 | EA | 5 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 109 cannot be changed 90023534 item 600 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 109 | 0 | EA | 102000000030443 | 102000000031070 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0600 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009786 | RING,SEALING;RBR,THOMASSEN 1026100700 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0600 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 109 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 870 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0252 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009787 | GASKET;NEOP,THOMASSEN 2424106400 | 2 | EA | 5 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 121 cannot be changed 90023534 item 690 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 980 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 121 | 0 | EA | 102000000030443 | 102000000029796 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0690 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009787 | GASKET;NEOP,THOMASSEN 2424106400 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0690 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 121 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 980 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0262 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009788 | GASKET;C4430,THOMASSEN 2426200202 | 2 | EA | 3 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 122 cannot be changed 90023534 item 700 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 122 | 0 | EA | 102000000030443 | 102000000031104 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0700 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009788 | GASKET;C4430,THOMASSEN 2426200202 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0700 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 122 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 990 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0202 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009789 | RING,SEALING;THOMASSEN 2746112800 | 4 | EA | 5 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 110 cannot be changed 90023534 item 610 already exists | Material picked; currently at KSF-PACK-REV-SML/Z83 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 110 | 0 | EA |  |  | 102000000031085 |  |  |  |  | WorkPackLink | KSF-PACK-REV-SML | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0610 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009789 | RING,SEALING;THOMASSEN 2746112800 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0610 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 110 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 880 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0212 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | WO item has not been released yet | 10009790 | GUIDE ASY,XHD;THOMASSEN 2746105000 | 2 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129360 | 106 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009790 | GUIDE ASY,XHD;THOMASSEN 2746105000 |  |  |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000128789 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0182 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009791 | PIN,COTTER;THOMASSEN 1410100500 | 4 | EA | 10 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 92 cannot be changed 90023534 item 440 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 710 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 92 | 0 | EA | 102000000030454 | 102000000030191 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0440 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | bigendsplit |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009791 | PIN,COTTER;THOMASSEN 1410100500 | 2024-05-11 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0440 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 92 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 710 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0192 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009792 | NUT,CASTELLATED;THOMASSEN 2160002001 | 4 | EA | 4 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 93 cannot be changed 90023534 item 450 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 93 | 0 | EA | 102000000030454 | 102000000030198 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | bigendnut |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009792 | NUT,CASTELLATED;THOMASSEN 2160002001 | 2024-05-11 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0450 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 93 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 720 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0202 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009793 | BOLT,RDHD;ALLOY ST,THOMASSEN 2203101001 | 4 | EA | 8 | 0 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 94 cannot be changed 90023534 item 460 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 94 | 0 | EA | 102000000030727 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | bigendbolt |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009793 | BOLT,RDHD;ALLOY ST,THOMASSEN 2203101001 | 2024-05-11 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0460 |  |  | DG1 |  | B1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 94 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 730 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0112 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009794 | BUSH,XHD PIN;THOMASSEN 2272101102 | 2 | EA | 2 | 0 | 0 | 2 | EA | 25.02 - SOH @AA02 | Supply for Order 200091126, Item 82 cannot be changed 90023534 item 380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 82 | 0 | EA | 101000000148122 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | xheadpin |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009794 | BUSH,XHD PIN;THOMASSEN 2272101102 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0380 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 82 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 630 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0122 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009795 | BUSH,XHD PIN;BZE,THOMASSEN 2272101300 | 4 | EA | 4 | 0 | 0 | 4 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091126, Item 83 cannot be changed 90023534 item 390 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 83 | 0 | EA | 102000000030713 | 101000000134755 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0390 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | xheadbush |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009795 | BUSH,XHD PIN;BZE,THOMASSEN 2272101300 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0390 |  |  | DG1 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 83 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 640 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0092 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009796 | SCREW,HDLESS;CS,THOMASSEN 1532040060 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 15 cannot be changed 90023534 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 15 | 0 | EA | 102000000030443 | 102000000031110 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | xheadbushloc |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009796 | SCREW,HDLESS;CS,THOMASSEN 1532040060 | 2024-01-02 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0080 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 150 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0102 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009797 | CIRCLIP,EXT;THOMASSEN 1061501100 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 16 cannot be changed 90023534 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 16 | 0 | EA | 102000000030443 | 102000000031099 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | xheadpin |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009797 | CIRCLIP,EXT;THOMASSEN 1061501100 | 2024-01-02 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0090 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 160 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0172 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009798 | BEARING,PIN,CRANK;THOMASSEN 2582300502 | 2 | SET | 0 | 0 | 2 | 2 | SET | 29.01 - At KGP | Supply for Order 200091126, Item 91 cannot be changed 9026034 item 430 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 700 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180117539 | 9026034 | 05 | Preparation | 0000129360 | 91 | 0 | SET | 102000000031033 | 101000000134750 | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000369550_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000054620 | 1020 | 2023-04-03 | 2 |  | 2025-01-22 | 4900216517_2025_0001 | 2025-03-01 | bigendliner | 5000369550_2025_0001 | 0 | 2 | 0 | 90023534 | 2 | 0 | 180117539 | 2 | 0 | 0 | X | L | 4900216517 | 2025 |  | 5000369550 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009798 | BEARING,PIN,CRANK;THOMASSEN 2582300502 | 2024-05-11 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 9026034_0430 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 91 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 700 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0072 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009800 | NUT,RND;ALLOY ST,THOMASSEN 2160108600 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 14 cannot be changed 90023534 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 14 | 0 | EA | 102000000030443 | 102000000031133 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | pilgrim nut |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009800 | NUT,RND;ALLOY ST,THOMASSEN 2160108600 | 2024-01-02 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0070 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 140 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0152 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009801 | RING,SEAL;RBR,THOMASSEN 2160108800 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 88 cannot be changed 90023534 item 420 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 88 | 0 | EA | 102000000030443 | 102000000031083 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0420 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | rbr ring |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009801 | RING,SEAL;RBR,THOMASSEN 2160108800 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0420 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 88 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 670 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0022 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009802 | SPACER,SHIM;THOMASSEN 2160108900 | 2 | SET | 2 | 0 | 0 | 2 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 11 cannot be changed 90023534 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 11 | 0 | SET | 102000000031093 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | shim |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009802 | SPACER,SHIM;THOMASSEN 2160108900 | 2024-01-02 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 110 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0052 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009803 | PLUG ASY,XHD;THOMASSEN 2160109800 | 8 | EA | 8 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 9 cannot be changed 90023534 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 9 | 0 | EA | 102000000030443 | 102000000031094 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | steel plug |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009803 | PLUG ASY,XHD;THOMASSEN 2160109800 | 2024-01-02 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0020 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 90 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0012 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009804 | DISC,TEFLON,COMP;THOMASSEN 2160109900 | 16 | EA | 16 | 0 | 0 | 16 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 10 cannot be changed 90023534 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 10 | 0 | EA | 102000000030443 | 102000000031095 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | disc |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009804 | DISC,TEFLON,COMP;THOMASSEN 2160109900 | 2024-01-02 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0030 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 100 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0042 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009805 | RING;ALLOY ST,THOMASSEN 2160110000 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 12 cannot be changed 90023534 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 12 | 0 | EA | 102000000030443 | 102000000031131 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ringmtlcup |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009805 | RING;ALLOY ST,THOMASSEN 2160110000 | 2024-01-02 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0050 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 120 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0062 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009806 | SPACER,SHIM;CS,THOMASSEN 2232159800 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 13 cannot be changed 90023534 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 13 | 0 | EA | 102000000030443 | 102000000031132 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | pstrod-xhead |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009806 | SPACER,SHIM;CS,THOMASSEN 2232159800 | 2024-01-02 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0060 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0272 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009807 | BOX,STUFFING;THOMASSEN 22691542000 | 2 | EA | 0 | 0 | 2 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 123 cannot be changed 9026470 item 710 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1000 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  | 180122346 | 9026470 | 05 | Preparation | 0000129360 | 123 | 0 | EA |  |  | 102000000030725 | 01-Road |  | 1-Not Started |  | WorkPackLink | P07WHS-R3A | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000389481_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055868 | 1020 | 2023-04-03 | 2 |  | 2025-02-06 | 4900228825_2025_0001 | 2025-03-01 | stuffingbox | 5000389481_2025_0001 | 0 | 2 | 0 | 90023534 | 2 | 0 | 180122346 | 2 | 0 | 0 | X | L | 4900228825 | 2025 |  | 5000389481 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009807 | BOX,STUFFING;THOMASSEN 22691542000 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 9026470_0710 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 123 |  | 0 |  | 25SD2301 | MJ | 1000004969 | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 1000 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-07 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0110 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS |  | 20 | WO item has not been released yet | 10009808 | SLEEVE,CYL;THOMASSEN 2761237100 | 2 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129360 | 117 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009808 | SLEEVE,CYL;THOMASSEN 2761237100 |  |  |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000128789 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0362 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009809 | ELEMENT,FLT;ALLOY,THOMASSEN 27201806000 | 2 | EA | 1 | 0 | 2 | 1 | EA | 09.03 - ETA 19.03.25 PO 4500037854 ex Howden CPT | Supply for Order 200091126, Item 75 cannot be changed 90023534 item 330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 75 | 0 | EA | 102000000030447 | 102000000031101 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO Filter |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009809 | ELEMENT,FLT;ALLOY,THOMASSEN 27201806000 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0330 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 75 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 580 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0402 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009810 | O-RING KIT;THOMASSEN 2720185600 | 1 | SET | 1 | 0 | 2 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 147 cannot be changed 90023534 item 910 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1230 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 147 | 0 | SET | 102000000030447 | 102000000029825 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0910 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009810 | O-RING KIT;THOMASSEN 2720185600 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0910 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 147 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1230 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0382 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009811 | VALVE,TSTAT;THOMASSEN 2384175900 | 1 | EA | 3 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 77 cannot be changed 90023534 item 350 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 77 | 0 | EA | 102000000030726 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0350 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | TCV51 |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009811 | VALVE,TSTAT;THOMASSEN 2384175900 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0350 |  |  | DG1 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 77 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 600 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0095 | 0040 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009812 | GASKET;THOMASSEN C25-2,OIL COOL,CNAF,SET | 2 | SET | 3 | 4 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 95 cannot be changed 90023534 item 470 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 95 | 0 | SET | 102000000030437 | 102000000031036 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0470 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009812 | GASKET;THOMASSEN C25-2,OIL COOL,CNAF,SET | 2024-05-11 | W |  | 0095 | COOLING WATER | INT | COOLING WATER |  |  | 90023534_0470 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 95 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 740 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0372 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009815 | VALVE,PRESS RED;THOMASSEN 2142108500 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 76 cannot be changed 90023534 item 340 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 76 | 0 | EA | 102000000030728 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0340 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | PCV23 |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009815 | VALVE,PRESS RED;THOMASSEN 2142108500 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0340 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 76 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 590 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-07 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0392 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009816 | VALVE,REL;1.5",698.7KPAG,VSF7RHSXS101 | 1 | EA | 0 | 1 | 0 | 0 |  | 27.02 - ETA 13.03.25 PO 4500014679 SCORE CPT | Supply for Order 200091126, Item 78 cannot be changed 90028438 item 20 already exists | Awaiting picking (check stock levels) @AA03 | SP12 | Stock at Base | 0 | AA03 | 5300010137 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028438 | 05 | Preparation | 0000129360 | 78 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-11 | ODST-0090028438_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-07 |  | 2025-03-01 | PCV24 RV |  | 0 | 2 | 0 | 90028438 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009816 | VALVE,REL;1.5",698.7KPAG,VSF7RHSXS101 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028438_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 78 |  | 0 |  | 25SD2301 | MJ |  | AU1098 | 1000128789 | S003 | 30 | 30 | 5300010137 | 20 |  |  | 0 | 1 | EA | 2001 | AA03 | 2025-02-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1190 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0232 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009824 | SEAL,RING;PTFE/C,THOMASSEN 22700001320 | 2 | SET | 11 | 0 | 0 | 2 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 119 cannot be changed 90023534 item 670 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 960 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 119 | 0 | SET | 102000000030443 | 102000000031081 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009824 | SEAL,RING;PTFE/C,THOMASSEN 22700001320 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0670 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 119 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 960 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0172 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009826 | VALVE,SUCT,COMP;THOMASSEN 54552136 | 4 | EA | 1 | 0 | 0 | 0 |  | 15.11 - SOH @ AA01 | Supply for Order 200091126, Item 129 cannot be changed 90023534 item 770 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1060 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90023534 | 05 | Preparation | 0000129360 | 129 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | suction |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009826 | VALVE,SUCT,COMP;THOMASSEN 54552136 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0770 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 129 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 1060 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-03-27 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0022 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009830 | RING,PST;THOMASSEN 2354213500 | 8 | EA | 0 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 28 cannot be changed 180087670 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180087670 | 90023053 | 05 | Preparation | 0000129360 | 28 | 0 | EA | 102000000022406 |  | 107000000000391 |  |  |  | P07 - BENCH | WorkPackLink | P07-WAREHOUSE | P07 | 0 |  | 0 | 0 |  | 8 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 31 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-03-01 |  |  | 2025-04-01 |  |  | 100000037985 | 1020 | 2023-04-03 | 8 |  | 2024-10-30 | 4900161656_2024_0001 | 2025-04-01 | pstnring | 5000261860_2024_0001 | 0 | 2 | 0 | 90023053 | 8 | 0 | 180087670 | 2 | 0 | 0 | X | L | 4900161656 | 2024 |  | 5000261860 | 2024 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009830 | RING,PST;THOMASSEN 2354213500 | 2024-01-02 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 90023053_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 28 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 260 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0032 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10009831 | RING,RIDER;THOMASSEN 2354213400 | 4 | EA | 0 | 0 | 0 | 4 | EA | 29.01 - Consumed | Supply for Order 200091126, Item 30 cannot be changed 180104971 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180104971 | 9022272 | 05 | Preparation | 0000129360 | 30 | 0 | EA |  |  | 102000000026651 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 | 0 |  | 0 | 0 |  | 4 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000046087 | 1020 | 2023-04-03 | 4 |  | 2024-12-13 | 4900190554_2024_0001 | 2025-03-01 | riderband | 5000318214_2024_0001 | 0 | 2 | 0 | 90023534 | 4 | 0 | 180104971 | 2 | 0 | 0 | X | L | 4900190554 | 2024 |  | 5000318214 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009831 | RING,RIDER;THOMASSEN 2354213400 | 2024-01-02 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 9022272_0180 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 30 |  | 0 |  | 25SD2301 | MJ | 1000004500 | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 280 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2024-12-17 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0120 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009833 | PLATE,LKG;CS,THOMASSEN 1480020400 | 2 | EA | 6 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 118 cannot be changed 90023534 item 660 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 950 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 118 | 0 | EA | 102000000030438 | 102000000030998 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009833 | PLATE,LKG;CS,THOMASSEN 1480020400 | 2024-05-11 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 90023534_0660 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 118 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 950 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0162 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009836 | GASKET;ALLOY ST,THOMASSEN 2428128900 | 8 | EA | 8 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091126, Item 128 cannot be changed 90023534 item 760 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1050 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 128 | 0 | EA | 102000000030448 | 102000000031107 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0760 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | discharge |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009836 | GASKET;ALLOY ST,THOMASSEN 2428128900 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0760 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 128 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1050 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0152 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009838 | VALVE,DISCH;THOMASSEN 2450196285 | 4 | EA | 0 | 0 | 0 | 0 |  | 19.11 - SOH @ AA01 | Supply for Order 200091126, Item 127 cannot be changed 90023534 item 750 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1040 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90023534 | 05 | Preparation | 0000129360 | 127 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | discharge |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009838 | VALVE,DISCH;THOMASSEN 2450196285 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0750 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 127 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 1040 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0080 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009839 | ROD,PST;THOMASSEN 2654318601 | 2 | EA | 0 | 0 | 0 | 1 | EA | 29.01 - Consumed | Supply for Order 200091126, Item 105 cannot be changed 9025300 item 570 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180116480 | 9025300 | 05 | Preparation | 0000129360 | 105 | 0 | EA |  |  | 101000000134446 |  |  |  |  | WorkPackLink | P07-WAREHOUSE | P07 | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053326 | 1020 | 2023-04-03 | 2 |  | 2025-01-20 | 4900214560_2025_0001 | 2025-03-01 | pistonrod | 5000365663_2025_0001 | 0 | 2 | 0 | 90023534 | 2 | 0 | 180116480 | 2 | 0 | 0 | X | L | 4900214560 | 2025 |  | 5000365663 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009839 | ROD,PST;THOMASSEN 2654318601 | 2024-05-11 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 9025300_0570 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 105 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 840 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0050 | 0080 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10009839 | ROD,PST;THOMASSEN 2654318601 | 2 | EA | 0 | 0 | 0 | 1 | EA | 29.01 - Consumed | Supply for Order 200091126, Item 105 cannot be changed 9025300 item 570 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180116480 | 9025300 | 05 | Preparation | 0000129360 | 105 | 0 | EA |  |  | 101000000134447 |  |  |  |  | WorkPackLink | P07-WAREHOUSE | P07 | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053326 | 1020 | 2023-04-03 | 2 |  | 2025-01-20 | 4900214560_2025_0001 | 2025-03-01 | pistonrod | 5000365663_2025_0001 | 0 | 2 | 0 | 90023534 | 2 | 0 | 180116480 | 2 | 0 | 0 | X | L | 4900214560 | 2025 |  | 5000365663 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009839 | ROD,PST;THOMASSEN 2654318601 | 2024-05-11 | W |  | 0050 | CYLINDER SUB-ASSEMBLY | INT | CYLINDER SUB-ASSEMBLY | 5 |  | 9025300_0570 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 105 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 840 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0130 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009848 | WIRE,LKG,COMP;THOMASSEN 1285030120 | 3 | M | 8 | 9 | 0 | 3 | M | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 101 cannot be changed 9027124 item 670 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 700 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 101 | 0 | M | 102000000030439 | 102000000030766 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 3 |  | 2025-02-11 | 4900234150_2025_0097 | 2025-03-01 | LockWire#13 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009848 | WIRE,LKG,COMP;THOMASSEN 1285030120 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0670 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 101 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 700 |  |  | 0 | 3 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0030 | 0200 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009848 | WIRE,LKG,COMP;THOMASSEN 1285030120 | 3 | M | 8 | 9 | 0 | 3 | M | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 23 cannot be changed 9027124 item 160 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 23 | 0 | M | 102000000030450 | 102000000030768 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 3 |  | 2025-02-11 | 4900234150_2025_0023 | 2025-03-01 | LockWire#5 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009848 | WIRE,LKG,COMP;THOMASSEN 1285030120 | 2024-07-20 | W |  | 0030 | BEARING/SEAL ARRANGEMENT (JOURNAL END) | INT | BEARING/SEAL ARRANGEMENT (JOURNAL END) | 5 |  | 9027124_0160 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 23 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 160 |  |  | 0 | 3 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0070 | 0810 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009848 | WIRE,LKG,COMP;THOMASSEN 1285030120 | 3 | M | 8 | 9 | 0 | 3 | M | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 106 cannot be changed 9027124 item 700 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 730 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 106 | 0 | M | 102000000030452 | 102000000030767 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 3 |  | 2025-02-11 | 4900234150_2025_0101 | 2025-03-01 | LockWire#14 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009848 | WIRE,LKG,COMP;THOMASSEN 1285030120 | 2024-07-20 | W |  | 0070 | BEARING & SEAL ARRANGEMENT NON-DRIVE END | INT | BEARING & SEAL ARRANGEMENT NON-DRIVE END | 5 |  | 9027124_0700 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 106 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 730 |  |  | 0 | 3 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0010 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009849 | SEAL,LABYTH;THOMASSEN 3777961380 | 1 | SET | 6 | 1 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 1 cannot be changed 9027124 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 1 | 0 | SET | 102000000030439 | 102000000030750 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0001 | 2025-03-01 | M24Impel#14 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009849 | SEAL,LABYTH;THOMASSEN 3777961380 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0010 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 10 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0020 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009850 | SEAL,LABYTH;THOMASSEN 3777961480 | 1 | SET | 1 | 1 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 2 cannot be changed 9027124 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 2 | 0 | SET | 102000000030439 | 102000000030752 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0003 | 2025-03-01 | M26Impel#15 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009850 | SEAL,LABYTH;THOMASSEN 3777961480 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0020 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 20 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0030 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009851 | SEAL,LABYTH;THOMASSEN 3777961580 | 3 | SET | 2 | 3 | 0 | 3 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 3 cannot be changed 9027124 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 3 | 0 | SET | 102000000030769 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 3 |  | 2025-02-11 | 4900234150_2025_0005 | 2025-03-01 | M28-30Imp#16 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009851 | SEAL,LABYTH;THOMASSEN 3777961580 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0030 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 30 |  |  | 0 | 3 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0040 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009852 | SEAL,LABYTH;THOMASSEN 3777961680 | 1 | SET | 1 | 1 | 0 | 1 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 4 cannot be changed 9027124 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 4 | 0 | SET | 102000000030439 | 102000000030753 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0007 | 2025-03-01 | M32Impel#17 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009852 | SEAL,LABYTH;THOMASSEN 3777961680 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0040 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 40 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0050 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009853 | SEAL,LABYTH;THOMASSEN 3938172180 | 5 | SET | 0 | 5 | 0 | 5 | SET | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 5 cannot be changed 9027124 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 5 | 0 | SET | 102000000030439 | 102000000030751 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 5 |  | 2025-02-11 | 4900234150_2025_0009 | 2025-03-01 | LabShSeal#18 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009853 | SEAL,LABYTH;THOMASSEN 3938172180 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0050 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 50 |  |  | 0 | 5 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0160 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | WO item has not been released yet | 10009854 | SEAL,LABYTH;THOMASSEN 3938172200 | 1 | SET | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000129406 | 136 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  |  |  |  | BalPstSea#19 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009854 | SEAL,LABYTH;THOMASSEN 3938172200 |  |  |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000128737 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0060 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009854 | SEAL,LABYTH;THOMASSEN 3938172200 | 1 | SET | 0 | 1 | 0 | 1 | SET | RETURNED AND ADDED AS ON-COND 10/03/25 AJ - STO 5400002317 | Supply for Order 200091108, Item 6 cannot be changed 9028685 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180133965 | 9028685 | 05 | Preparation | 0000129406 | 6 | 0 | SET |  |  | 101000000135767 | 01-Road |  | 5-Completed |  | WorkPackLink | P99PICKUPFROMWHSE |  | 0 | 5400002317 | 10 | 1 | SET | 0 | 0 | 2025-01-21 | 2025-01-19 | Y | 1001 | 2024-07-20 | GRST-5000434520_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060904 | 1020 | 2025-04-28 | 1 |  | 2025-03-10 | 4900263262_2025_0001 | 2025-03-01 | BalPstSea#19 | 5000434520_2025_0001 | 0 | 2 | 0 | 90028420 | 1 | 0 | 180133965 | 2 | 0 | 0 | X | L | 4900263262 | 2025 |  | 5000434520 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009854 | SEAL,LABYTH;THOMASSEN 3938172200 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9028685_0060 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SD2420 | MJ | 20004701 | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 60 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-17 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0070 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009855 | SEAL,STRING;VIT,THOMASSEN 0859121326 | 12 | M | 40 | 12 | 0 | 12 | M | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 7 cannot be changed 9027124 item 70 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 7 | 0 | M | 102000000030439 | 102000000030319 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 12 |  | 2025-02-11 | 4900234150_2025_0011 | 2025-03-01 | SealStrng#37 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009855 | SEAL,STRING;VIT,THOMASSEN 0859121326 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0070 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 70 |  |  | 0 | 12 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0080 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009856 | O-RING;NTRL RBR,THOMASSEN 2430116201 | 1 | EA | 4 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 8 cannot be changed 9027124 item 80 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 8 | 0 | EA | 102000000030439 | 102000000030765 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0013 | 2025-03-01 | BrlOring#48 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009856 | O-RING;NTRL RBR,THOMASSEN 2430116201 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0080 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086119 | 0020 | 0030 | 100086119 | Pressure/Temp Gauge Function Test 1K2420 | AA53.124PG | GAUGE,PRESSURE UNIT 2400 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10009857 | THERMOMETER,DIAL;THOMASSEN 2113181100 | 2 | EA | 3 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 | Supply for Order 100086119, Item 3 cannot be changed 90028281 item 30 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018528 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028281 | 05 | Preparation | 0000272240 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-28 | ODST-0090028281_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124TG13/16 |  | 0 | 2 | 0 | 90028281 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009857 | THERMOMETER,DIAL;THOMASSEN 2113181100 | 2024-11-28 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90028281_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000266973 | S002 |  | 30 | 5300018528 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272240 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0140 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | WO item has not been released yet | 10009857 | THERMOMETER,DIAL;THOMASSEN 2113181100 | 2 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129406 | 102 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  |  |  |  | JrnlBear#60 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009857 | THERMOMETER,DIAL;THOMASSEN 2113181100 |  |  |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000128737 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086119 | 0020 | 0020 | 100086119 | Pressure/Temp Gauge Function Test 1K2420 | AA53.124PG | GAUGE,PRESSURE UNIT 2400 | AA01 | 10 | Shipped qty below requirement qty | 10009858 | THERMOMETER;THOMASSEN 2113169200 | 2 | EA | 0 | 1 | 0 | 1 | EA | 03.02 - ETA 15.05.25 PO 4500044486 HOWDEN CPT | Supply for Order 100086119, Item 2 cannot be changed 90028281 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300018528 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027128 | 05 | Preparation | 0000272240 | 2 | 0 | EA | 102000000029947 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-28 | GIST-4900234120_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 1 |  | 2025-02-11 | 4900234120_2025_0001 | 2025-03-01 | 124TG13/16 |  | 0 | 2 | 0 | 90028281 | 0 | 0 |  | 1 | 0 | 0 | X | L | 4900234120 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009858 | THERMOMETER;THOMASSEN 2113169200 | 2024-11-28 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90028281_0020/9027128_0020 |  |  | DG1 |  | A2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000266973 | S002 | 30 | 30 | 5300018528 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272240 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0150 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | WO item has not been released yet | 10009858 | THERMOMETER;THOMASSEN 2113169200 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129406 | 103 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  |  |  |  | ThrBear#61 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009858 | THERMOMETER;THOMASSEN 2113169200 |  |  |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000128737 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0010 | 0090 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009859 | O-RING;VIT MS343,THOMASSEN 2430124801 | 4 | EA | 4 | 4 | 0 | 4 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 9 cannot be changed 9027124 item 90 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 9 | 0 | EA | 102000000030439 | 102000000030209 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 4 |  | 2025-02-11 | 4900234150_2025_0015 | 2025-03-01 | BrlOring#31 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009859 | O-RING;VIT MS343,THOMASSEN 2430124801 | 2024-07-20 | W |  | 0010 | COMPR BARREL ASSEMBLY | INT | COMPR BARREL ASSEMBLY | 5 |  | 9027124_0090 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 90 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0100 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009861 | WASHER,LK;ALLOY ST,THOMASSEN 2231103300 | 1 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 13 cannot be changed 90028420 item 100 already exists | Material picked; currently at SW3R01B02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 13 | 0 | EA |  |  | 102000000030290 |  |  |  |  | WorkPackLink | SW3R01B02B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | LockWash#4 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009861 | WASHER,LK;ALLOY ST,THOMASSEN 2231103300 | 2024-07-20 | W |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  | 90028420_0100 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0110 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009862 | RING,BACK UP;PTFE,THOMASSEN 2427138000 | 2 | EA | 2 | 1 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 14 cannot be changed 90028420 item 110 already exists | Material picked; currently at SW3R01B02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 14 | 0 | EA |  |  | 102000000030302 |  |  |  |  | WorkPackLink | SW3R01B02B |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | BackupRng#6 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009862 | RING,BACK UP;PTFE,THOMASSEN 2427138000 | 2024-07-20 | W |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  | 90028420_0110 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 110 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0430 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009862 | RING,BACK UP;PTFE,THOMASSEN 2427138000 | 1 | EA | 2 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 64 cannot be changed 9027124 item 520 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 64 | 0 | EA | 102000000030445 | 102000000030466 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0079 | 2025-03-01 | CouplArr#8 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009862 | RING,BACK UP;PTFE,THOMASSEN 2427138000 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 9027124_0520 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 64 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 520 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0120 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009863 | O-RING;NTRL RBR,THOMASSEN 2430100800 | 2 | EA | 5 | 1 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 15 cannot be changed 90028420 item 120 already exists | Material picked; currently at SW3R01B02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 15 | 0 | EA |  |  | 102000000030315 |  |  |  |  | WorkPackLink | SW3R01B02B |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | O-ring#7 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009863 | O-RING;NTRL RBR,THOMASSEN 2430100800 | 2024-07-20 | W |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  | 90028420_0120 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 120 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0390 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009863 | O-RING;NTRL RBR,THOMASSEN 2430100800 | 1 | EA | 5 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 60 cannot be changed 9027124 item 480 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 60 | 0 | EA | 102000000030445 | 102000000030756 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0073 | 2025-03-01 | CouplArr#4 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009863 | O-RING;NTRL RBR,THOMASSEN 2430100800 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 9027124_0480 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 60 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 480 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0130 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | WO item has not been released yet | 10009864 | DISC,THR;ALLOY ST,THOMASSEN 3923104700 | 1 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129406 | 16 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  |  |  |  | ThrDisc#14 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009864 | DISC,THR;ALLOY ST,THOMASSEN 3923104700 |  |  |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000128737 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0140 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009865 | NUT,LK;ALLOY ST,THOMASSEN 3980105500 | 1 | EA | 1 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 17 cannot be changed 9027124 item 130 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 17 | 0 | EA | 102000000030449 | 102000000030792 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0017 | 2025-03-01 | DELockNut#27 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009865 | NUT,LK;ALLOY ST,THOMASSEN 3980105500 | 2024-07-20 | W |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  | 9027124_0130 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 130 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0150 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009866 | NUT,LK;ALLOY ST,THOMASSEN 3980124800 | 1 | EA | 2 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 18 cannot be changed 9027124 item 140 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 18 | 0 | EA | 102000000030449 | 102000000030793 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0019 | 2025-03-01 | NDELocNut#28 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009866 | NUT,LK;ALLOY ST,THOMASSEN 3980124800 | 2024-07-20 | W |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  | 9027124_0140 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 18 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0160 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009867 | O-RING;NTRL RBR,THOMASSEN 2430132101 | 2 | EA | 0 | 2 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 19 cannot be changed 9027124 item 150 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 19 | 0 | EA | 102000000030449 | 102000000030757 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0021 | 2025-03-01 | O-ring#29 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009867 | O-RING;NTRL RBR,THOMASSEN 2430132101 | 2024-07-20 | W |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  | 9027124_0150 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 19 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 150 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0170 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | WO item has not been released yet | 10009868 | BEARING,SLVE;THOMASSEN 3927209200 | 2 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129406 | 20 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  |  |  |  | BrngSlv#17 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009868 | BEARING,SLVE;THOMASSEN 3927209200 |  |  |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000128737 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0180 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | WO item has not been released yet | 10009869 | BEARING,SLVE;THOMASSEN 3927226200 | 2 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129406 | 21 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  |  |  |  | BrngSlv#24 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009869 | BEARING,SLVE;THOMASSEN 3927226200 |  |  |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000128737 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0020 | 0190 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | WO item has not been released yet | 10009870 | BEARING,SLVE;THOMASSEN 3927223800 | 2 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129406 | 22 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  |  |  |  | BrngSlv#18 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009870 | BEARING,SLVE;THOMASSEN 3927223800 |  |  |  | 0020 | ROTOR ASSEMBLY | INT | ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000128737 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0250 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009871 | O-RING;VIT MS343,THOMASSEN 2430122201 | 2 | EA | 5 | 4 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 29 cannot be changed 9027124 item 200 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 29 | 0 | EA | 102000000030446 | 102000000030758 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0031 | 2025-03-01 | O-ring#3 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009871 | O-RING;VIT MS343,THOMASSEN 2430122201 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0200 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 29 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 200 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0330 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009871 | O-RING;VIT MS343,THOMASSEN 2430122201 | 2 | EA | 5 | 4 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 46 cannot be changed 9027124 item 350 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 46 | 0 | EA | 102000000030440 | 102000000030759 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0053 | 2025-03-01 | O-ring#3 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009871 | O-RING;VIT MS343,THOMASSEN 2430122201 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0350 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 46 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 350 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0330 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009872 | SEAL,RING;ALLOY ST,THOMASSEN 3935113300 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 37 cannot be changed 9027124 item 270 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 37 | 0 | EA | 102000000030446 | 102000000030754 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0043 | 2025-03-01 | SeRngShf#4 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009872 | SEAL,RING;ALLOY ST,THOMASSEN 3935113300 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0270 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 37 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 270 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0340 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009872 | SEAL,RING;ALLOY ST,THOMASSEN 3935113300 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 47 cannot be changed 9027124 item 360 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 47 | 0 | EA | 102000000030440 | 102000000030755 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0055 | 2025-03-01 | SeRngShf#4 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009872 | SEAL,RING;ALLOY ST,THOMASSEN 3935113300 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0360 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 47 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 360 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0350 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009873 | O-RING;VIT MS343,THOMASSEN 2430107201 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 39 cannot be changed 9027124 item 290 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 39 | 0 | EA | 102000000030446 | 102000000030321 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0047 | 2025-03-01 | O-ring#7 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009873 | O-RING;VIT MS343,THOMASSEN 2430107201 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0290 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 39 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 290 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0420 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009873 | O-RING;VIT MS343,THOMASSEN 2430107201 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 55 cannot be changed 9027124 item 430 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 55 | 0 | EA | 102000000030440 | 102000000030762 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0067 | 2025-03-01 | O-ring#7 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009873 | O-RING;VIT MS343,THOMASSEN 2430107201 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0430 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 55 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 430 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0430 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009874 | SEAL,LABYTH;THOMASSEN 3938171700 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 56 cannot be changed 9027124 item 440 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 56 | 0 | EA | 102000000030440 | 102000000030789 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0069 | 2025-03-01 | LabSeal#8 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009874 | SEAL,LABYTH;THOMASSEN 3938171700 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0440 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 56 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 440 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0360 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009874 | SEAL,LABYTH;THOMASSEN 3938171700 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 40 cannot be changed 9027124 item 300 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 40 | 0 | EA | 102000000030446 | 102000000030785 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0049 | 2025-03-01 | LabSeal#8 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009874 | SEAL,LABYTH;THOMASSEN 3938171700 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0300 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 40 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 300 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0440 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009875 | O-RING;BUNA-N,THOMASSEN 2430131501 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 57 cannot be changed 90028420 item 450 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 57 | 0 | EA |  |  | 102000000031274 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | O-ring#9 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009875 | O-RING;BUNA-N,THOMASSEN 2430131501 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 90028420_0450 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 57 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 450 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0370 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009875 | O-RING;BUNA-N,THOMASSEN 2430131501 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 41 cannot be changed 90028420 item 310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 41 | 0 | EA | 102000000031268 |  | 102000000034100 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | O-ring#9 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009875 | O-RING;BUNA-N,THOMASSEN 2430131501 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 90028420_0310 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 41 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 310 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0450 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009876 | WIRE,LKG,COMP;THOMASSEN 1285030075 | 2 | M | 0 | 0 | 0 | 0 |  | 09.03 - ETA 19.03.25 PO 4500037854 ex Howden | Supply for Order 200091108, Item 58 cannot be changed 90028420 item 460 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 58 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | LockWire#11 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009876 | WIRE,LKG,COMP;THOMASSEN 1285030075 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 90028420_0460 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 58 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 460 |  |  | 0 | 2 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0380 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009876 | WIRE,LKG,COMP;THOMASSEN 1285030075 | 2 | M | 0 | 0 | 0 | 0 |  | 09.03 - ETA 19.03.25 PO 4500037854 ex Howden | Supply for Order 200091108, Item 42 cannot be changed 90028420 item 320 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 42 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | LkSealAs#11 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009876 | WIRE,LKG,COMP;THOMASSEN 1285030075 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 90028420_0320 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 42 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 320 |  |  | 0 | 2 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0390 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009877 | SEAL,LABYTH;THOMASSEN 3938163100 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 43 cannot be changed 90028420 item 330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 43 | 0 | EA | 102000000030786 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | WindBack#13 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009877 | SEAL,LABYTH;THOMASSEN 3938163100 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 90028420_0330 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 43 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 330 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0400 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009878 | O-RING,SEAL;NTRL,THOMASSEN 24301316010 | 2 | EA | 0 | 4 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 44 cannot be changed 9027124 item 340 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 44 | 0 | EA | 102000000030446 | 102000000030760 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0051 | 2025-03-01 | O-ring#15 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009878 | O-RING,SEAL;NTRL,THOMASSEN 24301316010 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0340 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 44 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 340 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0360 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009878 | O-RING,SEAL;NTRL,THOMASSEN 24301316010 | 2 | EA | 0 | 4 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 49 cannot be changed 9027124 item 370 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 49 | 0 | EA | 102000000030440 | 102000000030761 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0057 | 2025-03-01 | O-ring#15 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009878 | O-RING,SEAL;NTRL,THOMASSEN 24301316010 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0370 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 49 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 370 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0470 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009879 | SEAL,LABYTH;THOMASSEN 3938163200 | 1 | EA | 1 | 1 | 0 | 1 | EA | 15.10 - SOH @ AA02 | Supply for Order 200091108, Item 105 cannot be changed 9027124 item 690 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 105 | 0 | EA | 102000000030440 | 102000000030790 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0099 | 2025-03-01 | WindBack#14 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009879 | SEAL,LABYTH;THOMASSEN 3938163200 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0690 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 105 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 720 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0260 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009880 | SEAL,RING;ALLOY ST,THOMASSEN 3935115200 | 1 | EA | 2 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 30 cannot be changed 9027124 item 210 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 30 | 0 | EA | 102000000030446 | 102000000030781 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0033 | 2025-03-01 | SealRing#6* |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009880 | SEAL,RING;ALLOY ST,THOMASSEN 3935115200 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0210 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 30 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 210 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0270 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009881 | SPRING,SPLIT WAVE;THOMASSEN 2350990048 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 31 cannot be changed 90028420 item 220 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 31 | 0 | EA | 102000000030109 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | Spring#6* |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009881 | SPRING,SPLIT WAVE;THOMASSEN 2350990048 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 90028420_0220 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 31 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 220 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0390 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009881 | SPRING,SPLIT WAVE;THOMASSEN 2350990048 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 52 cannot be changed 90028420 item 400 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 52 | 0 | EA | 102000000030110 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0400 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | Spring#6* |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009881 | SPRING,SPLIT WAVE;THOMASSEN 2350990048 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 90028420_0400 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 52 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 400 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0400 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009882 | O-RING;VIT MS343,THOMASSEN 2430122001 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 53 cannot be changed 9027124 item 410 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 53 | 0 | EA | 102000000030440 | 102000000031272 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0063 | 2025-03-01 | O-ring#6* |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009882 | O-RING;VIT MS343,THOMASSEN 2430122001 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0410 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 53 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 410 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0280 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009882 | O-RING;VIT MS343,THOMASSEN 2430122001 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 32 cannot be changed 9027124 item 230 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 32 | 0 | EA | 102000000030446 | 102000000031266 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0035 | 2025-03-01 | O-ring#6* |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009882 | O-RING;VIT MS343,THOMASSEN 2430122001 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0230 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 32 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 230 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0290 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009883 | O-RING;BUNA-N,THOMASSEN 2430131701 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 33 cannot be changed 9027124 item 240 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 33 | 0 | EA | 102000000030446 | 102000000031267 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0037 | 2025-03-01 | O-ring#6* |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009883 | O-RING;BUNA-N,THOMASSEN 2430131701 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0240 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 33 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 240 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0410 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009883 | O-RING;BUNA-N,THOMASSEN 2430131701 | 1 | EA | 0 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 54 cannot be changed 9027124 item 420 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 54 | 0 | EA | 102000000030440 | 102000000031273 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0065 | 2025-03-01 | O-ring#6* |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009883 | O-RING;BUNA-N,THOMASSEN 2430131701 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0420 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 54 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 420 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0380 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009884 | SEAL,RING;ALLOY ST,THOMASSEN 3935115300 | 1 | EA | 2 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 51 cannot be changed 9027124 item 390 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 51 | 0 | EA | 102000000030440 | 102000000030788 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0061 | 2025-03-01 | SealRing#6* |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009884 | SEAL,RING;ALLOY ST,THOMASSEN 3935115300 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0390 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 51 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 390 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0070 | 0600 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009885 | SEAL,RING;THOMASSEN 3935106401 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 74 cannot be changed 90028420 item 580 already exists | Material picked; currently at SW3R01B02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 74 | 0 | EA |  |  | 102000000030311 |  |  |  |  | WorkPackLink | SW3R01B02B |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SeRngNDE#5 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009885 | SEAL,RING;THOMASSEN 3935106401 | 2024-07-20 | W |  | 0070 | BEARING & SEAL ARRANGEMENT NON-DRIVE END | INT | BEARING & SEAL ARRANGEMENT NON-DRIVE END | 5 |  | 90028420_0580 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 74 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 580 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0070 | 0610 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009886 | BEARING,THR;THOMASSEN 3900165200 | 2 | EA | 2 | 0 | 2 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 75 cannot be changed 9026846 item 590 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 590 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122104 | 9026846 | 05 | Preparation | 0000129406 | 75 | 0 | EA |  |  | 102000000030791 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GRST-5000389477_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056465 | 1020 | 2025-04-28 | 2 |  | 2025-02-05 | 4900228063_2025_0001 | 2025-03-01 | ThrBrng#7 | 5000389477_2025_0001 | 0 | 2 | 0 | 90028420 | 2 | 0 | 180122104 | 2 | 0 | 0 | X | L | 4900228063 | 2025 |  | 5000389477 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009886 | BEARING,THR;THOMASSEN 3900165200 | 2024-07-20 | W |  | 0070 | BEARING & SEAL ARRANGEMENT NON-DRIVE END | INT | BEARING & SEAL ARRANGEMENT NON-DRIVE END | 5 |  | 9026846_0590 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 75 |  | 0 |  | 25SD2420 | MJ | 1000005037 | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 590 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0030 | 0260 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009887 | BEARING,JRNL;THOMASSEN 3900150500 | 1 | EA | 0 | 1 | 1 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 104 cannot be changed 9026472 item 680 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 710 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122387 | 9026472 | 05 | Preparation | 0000129406 | 104 | 0 | EA |  |  | 102000000030142 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GRST-5000389551_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055870 | 1020 | 2025-04-28 | 1 |  | 2025-02-06 | 4900228935_2025_0001 | 2025-03-01 | JrnBrng#3 | 5000389551_2025_0001 | 0 | 2 | 0 | 90028420 | 1 | 0 | 180122387 | 2 | 0 | 0 | X | L | 4900228935 | 2025 |  | 5000389551 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009887 | BEARING,JRNL;THOMASSEN 3900150500 | 2024-07-20 | W |  | 0030 | BEARING/SEAL ARRANGEMENT (JOURNAL END) | INT | BEARING/SEAL ARRANGEMENT (JOURNAL END) | 5 |  | 9026472_0680 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 104 |  | 0 |  | 25SD2420 | MJ | 1000005037 | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 710 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0070 | 0620 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009887 | BEARING,JRNL;THOMASSEN 3900150500 | 1 | EA | 0 | 1 | 1 | 1 | EA | 25.02 - KGP WH in HU 107000000000767 | Supply for Order 200091108, Item 76 cannot be changed 9027124 item 600 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 76 | 0 | EA | 102000000030452 | 102000000030141 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0085 | 2025-03-01 | JrnBrng#9 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009887 | BEARING,JRNL;THOMASSEN 3900150500 | 2024-07-20 | W |  | 0070 | BEARING & SEAL ARRANGEMENT NON-DRIVE END | INT | BEARING & SEAL ARRANGEMENT NON-DRIVE END | 5 |  | 9027124_0600 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 76 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 600 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0070 | 0630 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009888 | O-RING;THOMASSEN 2430133201 | 1 | EA | 8 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 77 cannot be changed 9027124 item 610 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 77 | 0 | EA | 102000000030452 | 102000000031275 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0087 | 2025-03-01 | O-ring#16 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009888 | O-RING;THOMASSEN 2430133201 | 2024-07-20 | W |  | 0070 | BEARING & SEAL ARRANGEMENT NON-DRIVE END | INT | BEARING & SEAL ARRANGEMENT NON-DRIVE END | 5 |  | 9027124_0610 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 77 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 610 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0030 | 0220 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009888 | O-RING;THOMASSEN 2430133201 | 1 | EA | 8 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 25 cannot be changed 9027124 item 170 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 25 | 0 | EA | 102000000030450 | 102000000031265 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0025 | 2025-03-01 | O-ring#6 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009888 | O-RING;THOMASSEN 2430133201 | 2024-07-20 | W |  | 0030 | BEARING/SEAL ARRANGEMENT (JOURNAL END) | INT | BEARING/SEAL ARRANGEMENT (JOURNAL END) | 5 |  | 9027124_0170 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 25 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 170 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0030 | 0230 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009889 | SEAL,LABYTH;THOMASSEN 3938172900 | 1 | EA | 1 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 26 cannot be changed 9027124 item 180 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 26 | 0 | EA | 102000000030450 | 102000000030780 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0027 | 2025-03-01 | OtbrdLab#26 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009889 | SEAL,LABYTH;THOMASSEN 3938172900 | 2024-07-20 | W |  | 0030 | BEARING/SEAL ARRANGEMENT (JOURNAL END) | INT | BEARING/SEAL ARRANGEMENT (JOURNAL END) | 5 |  | 9027124_0180 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 26 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 180 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0030 | 0240 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009890 | O-RING;NTRL RBR,THOMASSEN 2430135401 | 1 | EA | 2 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 27 cannot be changed 9027124 item 190 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 27 | 0 | EA | 102000000030450 | 102000000031276 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0029 | 2025-03-01 | InbdBrng#27 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009890 | O-RING;NTRL RBR,THOMASSEN 2430135401 | 2024-07-20 | W |  | 0030 | BEARING/SEAL ARRANGEMENT (JOURNAL END) | INT | BEARING/SEAL ARRANGEMENT (JOURNAL END) | 5 |  | 9027124_0190 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 27 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0300 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009891 | SEAL,RING;ALLOY ST,THOMASSEN 2227140000 | 1 | EA | 2 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 34 cannot be changed 9027124 item 250 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 34 | 0 | EA | 102000000030446 | 102000000030782 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0039 | 2025-03-01 | LabSealInner |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009891 | SEAL,RING;ALLOY ST,THOMASSEN 2227140000 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0250 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 34 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0310 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009892 | SEAL,RING;ALLOY ST,THOMASSEN 2227140100 | 1 | EA | 1 | 1 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 35 cannot be changed 9027124 item 260 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 35 | 0 | EA | 102000000030446 | 102000000030783 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0041 | 2025-03-01 | LabSealOuter |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009892 | SEAL,RING;ALLOY ST,THOMASSEN 2227140100 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0260 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 35 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0050 | 0370 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009893 | SEAL,RING;ALLOY ST,THOMASSEN 2227139800 | 1 | EA | 1 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 50 cannot be changed 9027124 item 380 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 50 | 0 | EA | 102000000030440 | 102000000030787 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0059 | 2025-03-01 | SeRngHous |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009893 | SEAL,RING;ALLOY ST,THOMASSEN 2227139800 | 2024-07-20 | W |  | 0050 | SEAL ARRANGEMENT NON-DRIVE END CW | INT | SEAL ARRANGEMENT NON-DRIVE END CW | 5 |  | 9027124_0380 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 50 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 380 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0040 | 0340 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009893 | SEAL,RING;ALLOY ST,THOMASSEN 2227139800 | 1 | EA | 1 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200091108, Item 38 cannot be changed 9027124 item 280 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 38 | 0 | EA | 102000000030446 | 102000000030784 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0045 | 2025-03-01 | SeRngHous |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009893 | SEAL,RING;ALLOY ST,THOMASSEN 2227139800 | 2024-07-20 | W |  | 0040 | SEAL ARRANGEMENT DRIVE END CCW | INT | SEAL ARRANGEMENT DRIVE END CCW | 5 |  | 9027124_0280 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 38 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 280 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0460 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009896 | RING,BACK UP;TEFLON,THOMASSEN 2427138400 | 1 | EA | 4 | 0 | 0 | 1 | EA | 03.10 - 4 SOH @ AA02 | Supply for Order 200091108, Item 67 cannot be changed 90028420 item 550 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 67 | 0 | EA | 102000000030492 | 102000000030461 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | CouplArr#9 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009896 | RING,BACK UP;TEFLON,THOMASSEN 2427138400 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 90028420_0550 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 67 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 550 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0420 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009898 | RING,BACK UP;THOMASSEN 2427138500 | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - 2 SOH @ AA02 | Supply for Order 200091108, Item 63 cannot be changed 90028420 item 510 already exists | Material picked; currently at SW3R01B02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 63 | 0 | EA |  |  | 102000000030300 |  |  |  |  | WorkPackLink | SW3R01B02B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0510 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | CouplArr#10 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009898 | RING,BACK UP;THOMASSEN 2427138500 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 90028420_0510 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 63 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 510 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0440 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009899 | RING,BACK UP;TEFLON,THOMASSEN 2427138300 | 1 | EA | 3 | 1 | 0 | 1 | EA | 03.10 - 4 SOH @ AA02 | Supply for Order 200091108, Item 65 cannot be changed 9027124 item 530 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 65 | 0 | EA | 102000000030445 | 102000000030460 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0081 | 2025-03-01 | CouplArr#7 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009899 | RING,BACK UP;TEFLON,THOMASSEN 2427138300 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 9027124_0530 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 65 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 530 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0450 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009900 | RING,BACK UP;TEFLON,THOMASSEN 2427138400 | 1 | EA | 2 | 1 | 0 | 1 | EA | 03.10 - 3 SOH @ AA02 | Supply for Order 200091108, Item 66 cannot be changed 9027124 item 540 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 66 | 0 | EA | 102000000030445 | 102000000030463 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0083 | 2025-03-01 | CouplArr#9 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009900 | RING,BACK UP;TEFLON,THOMASSEN 2427138400 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 9027124_0540 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 66 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 540 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0400 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009901 | O-RING;NTRL RBR,THOMASSEN 2430007600 | 1 | EA | 3 | 1 | 0 | 1 | EA | 03.10 - 4 SOH @ AA02 | Supply for Order 200091108, Item 61 cannot be changed 9027124 item 490 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 61 | 0 | EA | 102000000030445 | 102000000030764 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0075 | 2025-03-01 | CouplArr#3 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009901 | O-RING;NTRL RBR,THOMASSEN 2430007600 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 9027124_0490 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 61 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 490 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0410 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009902 | O-RING;NTRL RBR,THOMASSEN 2430128600 | 1 | EA | 1 | 1 | 0 | 1 | EA | 03.10 - 2 SOH @ AA02 | Supply for Order 200091108, Item 62 cannot be changed 9027124 item 500 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 62 | 0 | EA | 102000000030445 | 102000000031270 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0077 | 2025-03-01 | CouplArr#5 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009902 | O-RING;NTRL RBR,THOMASSEN 2430128600 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 9027124_0500 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 62 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 500 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0380 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009903 | O-RING;THOMASSEN 2430128700 | 1 | EA | 3 | 1 | 0 | 1 | EA | 03.10 - 4 SOH @ AA02 | Supply for Order 200091108, Item 59 cannot be changed 9027124 item 470 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 59 | 0 | EA | 102000000030445 | 102000000030763 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0071 | 2025-03-01 | CouplArr#6 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009903 | O-RING;THOMASSEN 2430128700 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 9027124_0470 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 59 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 470 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0080 | 0580 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009904 | O-RING;NTRL RBR,THOMASSEN 2430101600 | 1 | EA | 2 | 1 | 0 | 1 | EA | 03.10 - 3 SOH @ AA02 | Supply for Order 200091108, Item 92 cannot be changed 9027124 item 620 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 620 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 92 | 0 | EA | 102000000030436 | 102000000031269 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0089 | 2025-03-01 | ThrDisc#3 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009904 | O-RING;NTRL RBR,THOMASSEN 2430101600 | 2024-07-20 | W |  | 0080 | THRUST DISC ARRANGEMENT HYDRAULIC FIT | INT | THRUST DISC ARRANGEMENT HYDRAULIC FIT | 5 |  | 9027124_0620 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 92 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 620 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0080 | 0590 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009905 | O-RING;THOMASSEN 2430102700 | 1 | EA | 3 | 1 | 0 | 1 | EA | 03.10 - 4 SOH @ AA02 | Supply for Order 200091108, Item 93 cannot be changed 9027124 item 630 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 93 | 0 | EA | 102000000030436 | 102000000031271 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0091 | 2025-03-01 | ThrDisc#5 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009905 | O-RING;THOMASSEN 2430102700 | 2024-07-20 | W |  | 0080 | THRUST DISC ARRANGEMENT HYDRAULIC FIT | INT | THRUST DISC ARRANGEMENT HYDRAULIC FIT | 5 |  | 9027124_0630 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 93 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 630 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0080 | 0600 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009906 | RING,BACK UP;TEFLON,THOMASSEN 2427137600 | 1 | EA | 2 | 1 | 0 | 1 | EA | 03.10 - 3 SOH @ AA02 | Supply for Order 200091108, Item 94 cannot be changed 9027124 item 640 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 94 | 0 | EA | 102000000030436 | 102000000030464 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0093 | 2025-03-01 | ThrDisc#4 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009906 | RING,BACK UP;TEFLON,THOMASSEN 2427137600 | 2024-07-20 | W |  | 0080 | THRUST DISC ARRANGEMENT HYDRAULIC FIT | INT | THRUST DISC ARRANGEMENT HYDRAULIC FIT | 5 |  | 9027124_0640 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 94 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 640 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0080 | 0610 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009907 | RING,BACK UP;TEFLON,THOMASSEN 2427137500 | 1 | EA | 1 | 1 | 0 | 1 | EA | 03.10 - 3 SOH @ AA02 | Supply for Order 200091108, Item 95 cannot be changed 9027124 item 650 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 95 | 0 | EA | 102000000030436 | 102000000030465 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 1 |  | 2025-02-11 | 4900234150_2025_0095 | 2025-03-01 | ThrDisc#6 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009907 | RING,BACK UP;TEFLON,THOMASSEN 2427137500 | 2024-07-20 | W |  | 0080 | THRUST DISC ARRANGEMENT HYDRAULIC FIT | INT | THRUST DISC ARRANGEMENT HYDRAULIC FIT | 5 |  | 9027124_0650 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 95 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 650 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0470 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009949 | RING,BACK UP;TEFLON,THOMASSEN 2427134700 | 1 | EA | 0 | 0 | 0 | 0 |  | 09.03 - ETA 19.03.25 PO 4500037854 ex Howden | Supply for Order 200091108, Item 68 cannot be changed 90028420 item 560 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 68 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | CouplArr#9 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009949 | RING,BACK UP;TEFLON,THOMASSEN 2427134700 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 90028420_0560 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 68 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 560 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0060 | 0480 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10009950 | RING,BACK UP;TEFLON,THOMASSEN 2427134800 | 1 | EA | 0 | 0 | 0 | 0 |  | DEL: 80032577 | Supply for Order 200091108, Item 69 cannot be changed 90028420 item 570 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 69 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0570 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | CouplArr#9 |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009950 | RING,BACK UP;TEFLON,THOMASSEN 2427134800 | 2024-07-20 | W |  | 0060 | COUPLING HUB ARRANGEMENT | INT | COUPLING HUB ARRANGEMENT | 5 |  | 90028420_0570 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 69 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 570 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-02 | ROTAT | 200089885 | 0080 | 0010 | 200089885 | 2Y 1KT2430 TURB AIR FILTER CHANGEOUT | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009956 | CLIP,THOMASSEN 38MB9 COMP,2" AIR FILTERS | 240 | EA | 1350 | 0 | 120 | 240 | EA | 03.10 - 1350 SOH @ AA02 | Supply for Order 200089885, Item 4 cannot be changed 90025008 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015697 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025008 | 05 | Preparation | 0000128154 | 4 | 0 | EA | 102000000026949 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 240 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025008_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-10 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025008 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009956 | CLIP,THOMASSEN 38MB9 COMP,2" AIR FILTERS | 2024-09-23 | W |  | 0080 | Install New Filters | INT | Install New Filters | 0 | Ready for Release | 90025008_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127564 | S002 |  | 30 | 5300015697 | 10 |  |  | 0 | 240 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128154 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200090065 | 0070 | 0020 | 200090065 | 2Y 1KT2420 TURB FR3 AIR FILTER CHANGE | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009956 | CLIP,THOMASSEN 38MB9 COMP,2" AIR FILTERS | 120 | EA | 1350 | 0 | 120 | 120 | EA | 29.01 - At KGP | Supply for Order 200090065, Item 2 cannot be changed 180100947 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015685 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100947 | 9021453 | 05 | Preparation | 0000128279 | 2 | 0 | EA | 102000000025717 |  | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-23 | GRST-5000305881_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000044762 | 1020 | 2024-07-04 | 120 |  | 2024-12-04 | 4900185007_2024_0001 | 2025-03-01 |  | 5000305881_2024_0001 | 0 | 2 | 0 | 90025006 | 120 | 0 | 180100947 | 2 | 0 | 0 | X | L | 4900185007 | 2024 |  | 5000305881 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009956 | CLIP,THOMASSEN 38MB9 COMP,2" AIR FILTERS | 2024-09-23 | W |  | 0070 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 9021453_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000127728 | S002 |  | 30 | 5300015685 | 20 |  |  | 0 | 120 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128279 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-02 | ROTAT | 200089885 | 0080 | 0020 | 200089885 | 2Y 1KT2430 TURB AIR FILTER CHANGEOUT | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009957 | CLIP,THOMASSEN GAS TURB,AIR INLET SYS | 240 | EA | 360 | 0 | 0 | 40 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089885, Item 5 cannot be changed 90025008 item 20 already exists | Material picked; currently at WH2-PACK-SD-2A/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300015697 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180127670 | 9027828 | 05 | Preparation | 0000128154 | 5 | 0 | EA |  |  | 102000000032932 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2A |  | 0 |  | 0 | 0 |  | 0 | 240 |  |  | Y | 1001 | 2024-09-24 | IDST-0180127670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-10 | 0 |  | 2025-02-24 | 4900242843_2025_0001/4900242837_2025_0001 | 2025-03-01 |  |  | 0 | 2 | 0 | 90025008 | 0 | 0 | 180127670 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009957 | CLIP,THOMASSEN GAS TURB,AIR INLET SYS | 2024-09-23 | W |  | 0080 | Install New Filters | INT | Install New Filters | 0 | Ready for Release | 90025008_0020/9027828_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127564 | S002 |  | 30 | 5300015697 | 20 |  |  | 0 | 240 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128154 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-02 | ROTAT | 200089885 | 0080 | 0020 | 200089885 | 2Y 1KT2430 TURB AIR FILTER CHANGEOUT | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009957 | CLIP,THOMASSEN GAS TURB,AIR INLET SYS | 240 | EA | 360 | 0 | 0 | 180 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089885, Item 5 cannot be changed 90025008 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015697 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180127670 | 9027828 | 05 | Preparation | 0000128154 | 5 | 0 | EA | 101000000135803 |  | 101000000135601 | 01-Road |  | 3-In Transit |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 240 |  | 2025-01-18 | Y | 1001 | 2024-09-24 | IDST-0180127670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-10 | 0 |  | 2025-02-24 | 4900242843_2025_0001/4900242837_2025_0001 | 2025-03-01 |  |  | 0 | 2 | 0 | 90025008 | 0 | 0 | 180127670 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009957 | CLIP,THOMASSEN GAS TURB,AIR INLET SYS | 2024-09-23 | W |  | 0080 | Install New Filters | INT | Install New Filters | 0 | Ready for Release | 90025008_0020/9027828_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ | 20004610 | AU1072 | 1000127564 | S002 |  | 30 | 5300015697 | 20 |  |  | 0 | 240 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-01-16 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128154 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-02 | ROTAT | 200089885 | 0080 | 0020 | 200089885 | 2Y 1KT2430 TURB AIR FILTER CHANGEOUT | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009957 | CLIP,THOMASSEN GAS TURB,AIR INLET SYS | 240 | EA | 360 | 0 | 0 | 20 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089885, Item 5 cannot be changed 90025008 item 20 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015697 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180127670 | 9027828 | 05 | Preparation | 0000128154 | 5 | 0 | EA |  |  | 102000000033445 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 240 |  |  | Y | 1001 | 2024-09-24 | IDST-0180127670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-10 | 0 |  | 2025-02-24 | 4900242843_2025_0001/4900242837_2025_0001 | 2025-03-01 |  |  | 0 | 2 | 0 | 90025008 | 0 | 0 | 180127670 | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009957 | CLIP,THOMASSEN GAS TURB,AIR INLET SYS | 2024-09-23 | W |  | 0080 | Install New Filters | INT | Install New Filters | 0 | Ready for Release | 90025008_0020/9027828_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127564 | S002 |  | 30 | 5300015697 | 20 |  |  | 0 | 240 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128154 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200090065 | 0070 | 0010 | 200090065 | 2Y 1KT2420 TURB FR3 AIR FILTER CHANGE | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10009957 | CLIP,THOMASSEN GAS TURB,AIR INLET SYS | 120 | EA | 360 | 0 | 0 | 120 | EA | 23.01 - SOH @ AA02 | Supply for Order 200090065, Item 1 cannot be changed 90025006 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015685 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025006 | 05 | Preparation | 0000128279 | 1 | 0 | EA | 102000000032938 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 120 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025006_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-04 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025006 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10009957 | CLIP,THOMASSEN GAS TURB,AIR INLET SYS | 2024-09-23 | W |  | 0070 | Install New Filters | INT | Install New Filters | 5 | Ready for Release | 90025006_0010 |  |  | DG1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000127728 | S002 |  | 30 | 5300015685 | 10 |  |  | 0 | 120 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128279 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0140 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | WO item has not been released yet | 10010556 | PLATE,BAFFLE;ALUM ALLOY,KHI SRV32E03 | 1 | SET | 2 | 0 | 0 | 0 |  | 23.01- PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000129754 | 11 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  |  |  |  | DEBafflePlat |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010556 | PLATE,BAFFLE;ALUM ALLOY,KHI SRV32E03 |  |  |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000129164 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0010 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010556 | PLATE,BAFFLE;ALUM ALLOY,KHI SRV32E03 | 1 | SET | 2 | 0 | 0 | 1 | SET | 17.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 1 cannot be changed 90025019 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 1 | 0 | SET | 102000000032118 | 102000000026583 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | DEBafflePlat |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010556 | PLATE,BAFFLE;ALUM ALLOY,KHI SRV32E03 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 90025019_0040 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 40 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0150 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | WO item has not been released yet | 10010557 | BEARING,THR;KHI ZRC32B06 | 1 | SET | 2 | 0 | 0 | 0 |  | 23.01- PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000129754 | 12 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  |  |  |  | ThrBrgPads |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010557 | BEARING,THR;KHI ZRC32B06 |  |  |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000129164 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0160 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010558 | BEARING,JRNL;KHI SRS32C25 | 8 | EA | 20 | 0 | 10 | 8 | EA | 17.01 - 30 SOH @ AA02 | Supply for Order 200091505, Item 13 cannot be changed 9026849 item 140 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122115 | 9026849 | 05 | Preparation | 0000129754 | 13 | 0 | EA |  |  | 102000000029387 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R3FL | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000389143_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056468 | 1020 | 2025-06-05 | 8 |  | 2025-02-05 | 4900228104_2025_0001 | 2025-03-01 | JrnlBeargPad | 5000389143_2025_0001 | 0 | 2 | 0 | 90025019 | 8 | 0 | 180122115 | 2 | 0 | 0 | X | L | 4900228104 | 2025 |  | 5000389143 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010558 | BEARING,JRNL;KHI SRS32C25 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 9026849_0140 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDFR1 | MJ | 1000005037 | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 140 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0020 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010558 | BEARING,JRNL;KHI SRS32C25 | 2 | EA | 20 | 0 | 10 | 2 | EA | 15.01 - 30 SOH @ AA02 | Supply for Order 200091505, Item 2 cannot be changed 9026843 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122099 | 9026843 | 05 | Preparation | 0000129754 | 2 | 0 | EA |  |  | 102000000029385 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R3FL | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000389442_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056461 | 1020 | 2025-06-05 | 2 |  | 2025-02-05 | 4900228049_2025_0001 | 2025-03-01 | JrnlBeargPad | 5000389442_2025_0001 | 0 | 2 | 0 | 90025019 | 2 | 0 | 180122099 | 2 | 0 | 0 | X | L | 4900228049 | 2025 |  | 5000389442 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010558 | BEARING,JRNL;KHI SRS32C25 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 9026843_0050 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ | 1000005037 | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0030 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010559 | RETAINER,BRG;KHI ZRV32D20 | 1 | SET | 3 | 0 | 0 | 1 | SET | 15.01 - 1 SOH @ AA02 | Supply for Order 200091505, Item 3 cannot be changed 90025019 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 3 | 0 | SET | 102000000032118 | 102000000027492 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | BrgInnerReta |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010559 | RETAINER,BRG;KHI ZRV32D20 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 90025019_0060 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 60 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0040 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010560 | RETAINER,BRG;KHI ZRV32D21 | 1 | SET | 3 | 0 | 0 | 1 | SET | 17.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 4 cannot be changed 90025019 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 4 | 0 | SET | 102000000032118 | 102000000027493 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | BrgOuterReta |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010560 | RETAINER,BRG;KHI ZRV32D21 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 90025019_0070 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 70 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0050 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010561 | SEAL,RING;AL ALLOY,KHI SRU32J01 | 1 | EA | 2 | 0 | 0 | 1 | EA | 17.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 5 cannot be changed 90025019 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 5 | 0 | EA | 102000000032118 | 102000000027708 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | ThrustSealRg |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010561 | SEAL,RING;AL ALLOY,KHI SRU32J01 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 90025019_0080 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0060 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010562 | O-RING;BS-440,VIT,KHI BR40E111 | 1 | EA | 3 | 0 | 0 | 1 | EA | 17.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 6 cannot be changed 90025019 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 6 | 0 | EA | 102000000032118 | 102000000027591 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | ThrBrgEndCov |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010562 | O-RING;BS-440,VIT,KHI BR40E111 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 90025019_0090 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0120 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010563 | GASKET;275MM ID X 362MM OD,KLINGER C4430 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 10 cannot be changed 90025019 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 10 | 0 | EA | 102000000032118 | 102000000027810 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | BrgCovNDE |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010563 | GASKET;275MM ID X 362MM OD,KLINGER C4430 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 90025019_0130 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 130 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0070 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010563 | GASKET;275MM ID X 362MM OD,KLINGER C4430 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 7 cannot be changed 90025019 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 7 | 0 | EA | 102000000032118 | 102000000027809 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | BrgCovNDE |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010563 | GASKET;275MM ID X 362MM OD,KLINGER C4430 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 90025019_0100 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0080 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010564 | GASKET;270MMIDX365MMOD,KHI ZRC32L08 | 1 | EA | 3 | 0 | 0 | 1 | EA | 15.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 8 cannot be changed 90025019 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 8 | 0 | EA | 102000000032118 | 102000000027811 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | BRGCovDE |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010564 | GASKET;270MMIDX365MMOD,KHI ZRC32L08 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 90025019_0110 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0200 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010568 | SEAL,LABYTH;AL ALLOY,KHI SRV35D07 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 24 cannot be changed 90025019 item 250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 24 | 0 | EA | 102000000032103 | 102000000027517 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealLabHsg |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010568 | SEAL,LABYTH;AL ALLOY,KHI SRV35D07 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0250 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 24 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0210 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010569 | SEAL,RING;ST WITH AL LINING,KHI SRV35F17 | 1 | SET | 3 | 0 | 0 | 1 | SET | 15.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 25 cannot be changed 90025019 item 260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 25 | 0 | SET | 102000000032103 | 102000000027513 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealRingLP |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010569 | SEAL,RING;ST WITH AL LINING,KHI SRV35F17 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0260 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 25 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 260 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0220 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010570 | SEAL,RING;ST WITH AL LINING,KHI SRV35E09 | 1 | ASY | 3 | 0 | 0 | 1 | ASY | 18.01 - Qty 3 SOH ex AA02 KSF - 241 day lead time. | Supply for Order 200091505, Item 26 cannot be changed 90025019 item 270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 26 | 0 | ASY | 102000000032103 | 102000000027515 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealRingHP |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010570 | SEAL,RING;ST WITH AL LINING,KHI SRV35E09 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0270 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 26 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 270 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0230 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010571 | SPRING,COIL,SEAL RING;KHI BR24A101 | 1 | EA | 12 | 0 | 0 | 1 | EA | 17.01 - 12 SOH @ AA02 | Supply for Order 200091505, Item 27 cannot be changed 90025019 item 280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 27 | 0 | EA | 102000000032103 | 102000000029443 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SprngSealRng |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010571 | SPRING,COIL,SEAL RING;KHI BR24A101 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0280 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 27 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 280 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0360 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010572 | O-RING;7MM THK SP DESIGN,KHI BR40E132 | 1 | EA | 4 | 0 | 0 | 1 | EA | 17.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 39 cannot be changed 90025019 item 400 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 39 | 0 | EA | 102000000032103 | 102000000027611 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0400 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | HSG O-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010572 | O-RING;7MM THK SP DESIGN,KHI BR40E132 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0400 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 39 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 400 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0240 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010572 | O-RING;7MM THK SP DESIGN,KHI BR40E132 | 1 | EA | 4 | 0 | 0 | 1 | EA | 17.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 28 cannot be changed 90025019 item 290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 28 | 0 | EA | 102000000032103 | 102000000027610 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | HSG O-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010572 | O-RING;7MM THK SP DESIGN,KHI BR40E132 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0290 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 28 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 290 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0250 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010573 | O-RING;7MM THK SP DESIGN,KHI BR40E114 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 29 cannot be changed 90025019 item 300 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 29 | 0 | EA | 102000000032103 | 102000000027612 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0300 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | HSG O-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010573 | O-RING;7MM THK SP DESIGN,KHI BR40E114 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0300 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 29 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 300 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0370 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010573 | O-RING;7MM THK SP DESIGN,KHI BR40E114 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 40 cannot be changed 90025019 item 410 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 40 | 0 | EA | 102000000032103 | 102000000027617 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0410 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | HSG O-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010573 | O-RING;7MM THK SP DESIGN,KHI BR40E114 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0410 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 40 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 410 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0260 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010574 | O-RING;3.5MM THK SP DESIGN,KHI BR40E122 | 1 | EA | 7 | 0 | 0 | 1 | EA | 15.02 - 7 SOH @ AA02 | Supply for Order 200091505, Item 30 cannot be changed 90025019 item 310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 30 | 0 | EA | 102000000032103 | 102000000027613 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | HSG O-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010574 | O-RING;3.5MM THK SP DESIGN,KHI BR40E122 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0310 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 30 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 310 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0340 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010574 | O-RING;3.5MM THK SP DESIGN,KHI BR40E122 | 2 | EA | 7 | 0 | 0 | 2 | EA | 15.02 - 7 SOH @ AA02 | Supply for Order 200091505, Item 37 cannot be changed 90025019 item 380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 37 | 0 | EA | 102000000032103 | 102000000027615 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | HSG O-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010574 | O-RING;3.5MM THK SP DESIGN,KHI BR40E122 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0380 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 37 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 380 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0270 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010575 | O-RING;3.5MM C/S SP DESIGN,KHI BR40E160 | 1 | EA | 7 | 0 | 0 | 1 | EA | 15.01 - 7 SOH @ AA02 | Supply for Order 200091505, Item 31 cannot be changed 90025019 item 320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 31 | 0 | EA | 102000000032103 | 102000000027614 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | WndBackLab |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010575 | O-RING;3.5MM C/S SP DESIGN,KHI BR40E160 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0320 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 31 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 320 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0350 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010575 | O-RING;3.5MM C/S SP DESIGN,KHI BR40E160 | 2 | EA | 7 | 0 | 0 | 2 | EA | 15.01 - 7 SOH @ AA02 | Supply for Order 200091505, Item 38 cannot be changed 90025019 item 390 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 38 | 0 | EA | 102000000032103 | 102000000027616 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0390 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | HSG O-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010575 | O-RING;3.5MM C/S SP DESIGN,KHI BR40E160 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0390 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 38 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 390 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0400 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010576 | O-RING;3.5MM C/S SP DESIGN,KHI BR40E106 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 41 cannot be changed 90025019 item 420 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 41 | 0 | EA | 102000000032103 | 102000000027259 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0420 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealHPO-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010576 | O-RING;3.5MM C/S SP DESIGN,KHI BR40E106 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0420 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 41 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 420 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0280 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010576 | O-RING;3.5MM C/S SP DESIGN,KHI BR40E106 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 32 cannot be changed 90025019 item 330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 32 | 0 | EA | 102000000032103 | 102000000027256 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealHPO-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010576 | O-RING;3.5MM C/S SP DESIGN,KHI BR40E106 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0330 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 32 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 330 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0290 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010577 | SEAL,LABYTH;KHI SRV35D08 | 1 | EA | 1 | 0 | 1 | 1 | EA | 29.01 - At KGP | Supply for Order 200091505, Item 33 cannot be changed 180105844 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180105844 | 9022932 | 05 | Preparation | 0000129754 | 33 | 0 | EA | 102000000027217 |  | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000321723_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000047532 | 1020 | 2025-06-05 | 1 |  | 2024-12-16 | 4900192129_2024_0001 | 2025-03-01 | SLWDischarge | 5000321723_2024_0001 | 0 | 2 | 0 | 90025019 | 1 | 0 | 180105844 | 2 | 0 | 0 | X | L | 4900192129 | 2024 |  | 5000321723 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010577 | SEAL,LABYTH;KHI SRV35D08 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 9022932_0340 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 33 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 340 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0300 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010578 | SEAL,LABYTH;KHI SRV35D09 | 1 | EA | 1 | 0 | 1 | 1 | EA | 29.01 - At KGP | Supply for Order 200091505, Item 34 cannot be changed 180105844 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180105844 | 9022932 | 05 | Preparation | 0000129754 | 34 | 0 | EA | 102000000027218 |  | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000321723_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000047532 | 1020 | 2025-06-05 | 1 |  | 2024-12-16 | 4900192129_2024_0003 | 2025-03-01 | SLWSuction | 5000321723_2024_0002 | 0 | 2 | 0 | 90025019 | 1 | 0 | 180105844 | 2 | 0 | 0 | X | L | 4900192129 | 2024 |  | 5000321723 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010578 | SEAL,LABYTH;KHI SRV35D09 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 9022932_0350 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 34 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 350 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0310 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010579 | O-RING;6.99MM THK SP,VIT,KHI BR40E179 | 1 | EA | 4 | 0 | 0 | 1 | EA | 17.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 35 cannot be changed 90025019 item 360 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 35 | 0 | EA | 102000000032103 | 102000000027577 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0360 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealCasOuter |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010579 | O-RING;6.99MM THK SP,VIT,KHI BR40E179 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0360 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 35 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 360 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0410 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010579 | O-RING;6.99MM THK SP,VIT,KHI BR40E179 | 1 | EA | 4 | 0 | 0 | 1 | EA | 17.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 42 cannot be changed 90025019 item 430 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 42 | 0 | EA | 102000000032103 | 102000000027593 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0430 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealCasOuter |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010579 | O-RING;6.99MM THK SP,VIT,KHI BR40E179 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0430 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 42 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 430 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0320 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010580 | O-RING;6.99MM THK SP,VIT,KHI BR40E117 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 36 cannot be changed 90025019 item 370 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 36 | 0 | EA | 102000000032103 | 102000000027594 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0370 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealCasInner |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010580 | O-RING;6.99MM THK SP,VIT,KHI BR40E117 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0370 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 36 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 370 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0420 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010580 | O-RING;6.99MM THK SP,VIT,KHI BR40E117 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 43 cannot be changed 90025019 item 440 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 43 | 0 | EA | 102000000032103 | 102000000027595 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0440 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealCasInner |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010580 | O-RING;6.99MM THK SP,VIT,KHI BR40E117 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0440 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 43 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 440 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0010 | 0090 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010581 | BEARING,THR;KHI DRGZRC32B06ITEMS1TO12 | 1 | ASY | 1 | 0 | 1 | 1 | ASY | 15.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 9 cannot be changed 9026842 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180122098 | 9026842 | 05 | Preparation | 0000129754 | 9 | 0 | ASY |  |  | 102000000029386 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R3FL | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000389433_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056460 | 1020 | 2025-06-05 | 1 |  | 2025-02-05 | 4900228051_2025_0001 | 2025-03-01 | ThrustBrng | 5000389433_2025_0001 | 0 | 2 | 0 | 90025019 | 1 | 0 | 180122098 | 2 | 0 | 0 | X | L | 4900228051 | 2025 |  | 5000389433 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010581 | BEARING,THR;KHI DRGZRC32B06ITEMS1TO12 | 2024-07-20 | W |  | 0010 | DE & NDE BEARINGS | INT | DE & NDE BEARINGS | 5 |  | 9026842_0120 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDFR1 | MJ | 1000005037 | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 120 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0490 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010583 | SEAL SET,LABYTH;KHI 14031703 | 2 | SET | 3 | 0 | 0 | 2 | SET | 17.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 59 cannot be changed 90025019 item 580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 580 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 59 | 0 | SET | 102000000032113 | 102000000027721 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | G/Box Labys |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010583 | SEAL SET,LABYTH;KHI 14031703 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0580 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 59 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 580 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0100 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010585 | SEAL,SHFT,LABYTH;KHI SRC27B02 | 1 | SET | 3 | 0 | 0 | 1 | SET | 15.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 14 cannot be changed 90025019 item 150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 14 | 0 | SET | 102000000032103 | 102000000027722 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealLabSht#1 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010585 | SEAL,SHFT,LABYTH;KHI SRC27B02 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0150 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 150 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0110 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010586 | SEAL,SHFT,LABYTH;KHI SRC27B01 | 4 | SET | 8 | 0 | 0 | 4 | SET | 15.01 - 8 SOH @ AA02 | Supply for Order 200091505, Item 15 cannot be changed 90025019 item 160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 15 | 0 | SET | 102000000032103 | 102000000027516 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SLS#2,3,4,5 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010586 | SEAL,SHFT,LABYTH;KHI SRC27B01 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0160 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 160 |  |  | 0 | 4 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0120 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010587 | SEAL,SHFT;AL ALLOY TWO PCE,KHI SRV27B10 | 1 | SET | 2 | 0 | 0 | 1 | SET | 15.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 16 cannot be changed 90025019 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 16 | 0 | SET | 102000000032103 | 102000000027720 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealLabSht#5 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010587 | SEAL,SHFT;AL ALLOY TWO PCE,KHI SRV27B10 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0170 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 170 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0130 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010588 | SEAL,SHFT;AL ALLOY TWO PCE,KHI SRV27B09 | 1 | SET | 3 | 0 | 0 | 1 | SET | 15.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 17 cannot be changed 90025019 item 180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 17 | 0 | SET | 102000000032103 | 102000000027709 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SLS#7,8 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010588 | SEAL,SHFT;AL ALLOY TWO PCE,KHI SRV27B09 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0180 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 180 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0140 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010589 | SEAL,LABYTH;KHI SRV27E10 | 1 | SET | 2 | 0 | 0 | 1 | SET | 15.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 18 cannot be changed 90025019 item 190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 18 | 0 | SET | 102000000032103 | 102000000027706 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealLabImp#1 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010589 | SEAL,LABYTH;KHI SRV27E10 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0190 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 18 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 190 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0150 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010590 | SEAL,LABYTH;KHI SRV27E11 | 1 | SET | 2 | 0 | 0 | 1 | SET | 15.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 19 cannot be changed 90025019 item 200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 19 | 0 | SET | 102000000032103 | 102000000027518 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealLabImp#2 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010590 | SEAL,LABYTH;KHI SRV27E11 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0200 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 19 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 200 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0160 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010591 | SEAL,LABYTH;KHI SRV27E03 | 4 | SET | 9 | 0 | 0 | 4 | SET | 15.01 - 9 SOH @ AA02 | Supply for Order 200091505, Item 20 cannot be changed 90025019 item 210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 20 | 0 | SET | 102000000032103 | 102000000027520 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SLI#3,4,5,6 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010591 | SEAL,LABYTH;KHI SRV27E03 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0210 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 20 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 210 |  |  | 0 | 4 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0170 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010592 | SEAL,LABYTH;KHI SRV27E12 | 1 | SET | 2 | 0 | 0 | 1 | SET | 17.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 21 cannot be changed 90025019 item 220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 21 | 0 | SET | 102000000032103 | 102000000027707 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealLabImp#7 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010592 | SEAL,LABYTH;KHI SRV27E12 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0220 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 21 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 220 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0180 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010593 | SEAL,LABYTH;KHI SRV27E13 | 1 | SET | 3 | 0 | 0 | 1 | SET | 15.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 22 cannot be changed 90025019 item 230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 22 | 0 | SET | 102000000032103 | 102000000027521 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealLabImp#8 |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010593 | SEAL,LABYTH;KHI SRV27E13 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0230 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 22 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 230 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0020 | 0190 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010594 | SEAL,LABYTH;KHI SRC27H01 | 1 | SET | 2 | 0 | 0 | 1 | SET | 15.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 23 cannot be changed 90025019 item 240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 23 | 0 | SET | 102000000032103 | 102000000027519 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SLBalPstn |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010594 | SEAL,LABYTH;KHI SRC27H01 | 2024-07-20 | W |  | 0020 | DE & NDE SEALS | INT | DE & NDE SEALS | 5 |  | 90025019_0240 |  |  | FR1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 23 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 240 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0330 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010596 | WASHER;ALLOY ST,KHI JISB1555AW16 | 1 | EA | 2 | 0 | 0 | 1 | EA | 17.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 44 cannot be changed 90025019 item 450 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 44 | 0 | EA | 102000000032113 | 102000000027244 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0450 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | RtrThrWasher |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010596 | WASHER;ALLOY ST,KHI JISB1555AW16 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0450 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 44 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 450 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0340 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010597 | COLLAR,THR;KHI SRS32B15 | 1 | EA | 3 | 0 | 0 | 1 | EA | 17.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 45 cannot be changed 90025019 item 460 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 45 | 0 | EA | 102000000028936 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | RtrThrCollar |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010597 | COLLAR,THR;KHI SRS32B15 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0460 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 45 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 460 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0350 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010598 | O-RING;VIT 90 DURO,KHI V9234VITON90 | 1 | EA | 9 | 0 | 0 | 1 | EA | 10.01 - Picked @ KSF | Supply for Order 200091505, Item 46 cannot be changed 90025019 item 470 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 46 | 0 | EA | 102000000032113 | 102000000027587 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0470 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | CplngO-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010598 | O-RING;VIT 90 DURO,KHI V9234VITON90 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0470 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 46 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 470 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0740 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010598 | O-RING;VIT 90 DURO,KHI V9234VITON90 | 5 | EA | 9 | 0 | 0 | 3 | EA | 27.09 - qty 6 SOH at AA01 | Supply for Order 200091505, Item 80 cannot be changed 90025019 item 770 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 80 | 0 | EA | 102000000032113 | 102000000031196 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | CplO-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010598 | O-RING;VIT 90 DURO,KHI V9234VITON90 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0770 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 80 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 770 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0740 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010598 | O-RING;VIT 90 DURO,KHI V9234VITON90 | 5 | EA | 9 | 0 | 0 | 2 | EA | 27.09 - qty 6 SOH at AA01 | Supply for Order 200091505, Item 80 cannot be changed 90025019 item 770 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 80 | 0 | EA | 102000000032113 | 102000000027598 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | CplO-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010598 | O-RING;VIT 90 DURO,KHI V9234VITON90 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0770 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 80 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 770 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0360 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010599 | O-RING;VIT 90 DURO,KHI JISW1516AN6230B15 | 1 | EA | 9 | 0 | 0 | 1 | EA | 17.01 - 9 SOH @ AA02 | Supply for Order 200091505, Item 47 cannot be changed 90025019 item 480 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 47 | 0 | EA | 102000000032113 | 102000000027596 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0480 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | CplngO-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010599 | O-RING;VIT 90 DURO,KHI JISW1516AN6230B15 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0480 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 47 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 480 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0750 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010599 | O-RING;VIT 90 DURO,KHI JISW1516AN6230B15 | 5 | EA | 9 | 0 | 0 | 5 | EA | 17.01 - 9 SOH @ AA02 | Supply for Order 200091505, Item 81 cannot be changed 90025019 item 780 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 81 | 0 | EA | 102000000032113 | 102000000027599 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | CplO-ring |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010599 | O-RING;VIT 90 DURO,KHI JISW1516AN6230B15 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0780 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 81 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 780 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0812 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE |  | 20 | No issue identified | 10010610 | COUPLING;KHI DRGZRC74B08 | -1 | SET | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET |  | DAMAGED |  |  |  | 05 | Preparation | 0000129754 | 95 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-06-05 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010610 | COUPLING;KHI DRGZRC74B08 |  |  |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000129164 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0842 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10010610 | COUPLING;KHI DRGZRC74B08 | 1 | SET | 1 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 | Supply for Order 200091505, Item 98 cannot be changed 90025019 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  | NEW |  |  | 90025019 | 05 | Preparation | 0000129754 | 98 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | Coupling HS |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010610 | COUPLING;KHI DRGZRC74B08 | 2024-09-30 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0010 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 98 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 10 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0390 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010612 | NUT KIT,BLT+LK;KHI DRGL1800XR006030ITEM> | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 17.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 50 cannot be changed 90025019 item 490 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 50 | 0 | KIT | 102000000032113 | 102000000029547 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0490 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | LS-GearLoad |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010612 | NUT KIT,BLT+LK;KHI DRGL1800XR006030ITEM> | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0490 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 50 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 490 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0400 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10010613 | NUT KIT,BLT+LK;KHI DRGL1800XR006030ITEM> | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 17.01 - 2 SOH @ AA02 | Supply for Order 200091505, Item 51 cannot be changed 90025019 item 500 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 500 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 51 | 0 | KIT | 102000000032113 | 102000000029293 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0500 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | LS-MotrLoad |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10010613 | NUT KIT,BLT+LK;KHI DRGL1800XR006030ITEM> | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0500 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 51 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 500 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0262 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10012388 | INSERT,ALLWEILER 80R42 PP,48/46/28,& SCR | 1 | SET | 0 | 0 | 1 | 1 | SET | 29.01 - At KGP | Supply for Order 200091126, Item 65 cannot be changed 9026108 item 240 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180117356 | 9026108 | 05 | Preparation | 0000129360 | 65 | 0 | SET | 102000000030813 | 101000000134314 | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000368989_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053986 | 1020 | 2023-04-03 | 1 |  | 2025-01-22 | 4900216238_2025_0001 | 2025-03-01 | LO Pump | 5000368989_2025_0001 | 0 | 2 | 0 | 90023534 | 1 | 0 | 180117356 | 2 | 0 | 0 | X | L | 4900216238 | 2025 |  | 5000368989 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012388 | INSERT,ALLWEILER 80R42 PP,48/46/28,& SCR | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 9026108_0240 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 65 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 490 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0272 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10012389 | GASKET;C4430,ALLWEILER 80R42 PP,21/22/24 | 1 | SET | 2 | 0 | 0 | 1 | SET | 03.10 - SOH at AA02 | Supply for Order 200091126, Item 66 cannot be changed 90023534 item 250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 500 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 66 | 0 | SET | 102000000030447 | 102000000031092 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO Pump |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012389 | GASKET;C4430,ALLWEILER 80R42 PP,21/22/24 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0250 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 66 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 500 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0282 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10012390 | BUSH;BAL,SET,SIL70,ALLWEILER 669717 | 1 | SET | 2 | 0 | 0 | 1 | SET | 03.10 - SOH at AA02 | Supply for Order 200091126, Item 67 cannot be changed 90023534 item 260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 510 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 67 | 0 | SET | 102000000030447 | 102000000030149 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO Pump |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012390 | BUSH;BAL,SET,SIL70,ALLWEILER 669717 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0260 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 67 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 510 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0030 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10012858 | BUSH,STORK PVML SNGL STG PP,THROAT | 1 | EA | 0 | 0 | 0 | 0 |  | 05.03 - SOH @ AA53 PO TO COME THROUGH PO 4500045034 BH FCA | Supply for Order 100079771, Item 3 cannot be changed 90028600 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012858 | BUSH,STORK PVML SNGL STG PP,THROAT | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 |  |  | 5300020063 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0040 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10012859 | RING,STORK PVML PP,WEAR,CASE | 1 | SET | 0 | 0 | 0 | 0 |  | 05.02 - SOH @ AA53 PO TO COME THROUGH PO 4500045034 BH FCA | Supply for Order 100079771, Item 4 cannot be changed 90028600 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012859 | RING,STORK PVML PP,WEAR,CASE | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 |  |  | 5300020063 | 20 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0050 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10012860 | RING,STORK PVML PP,WEAR,IMP | 1 | SET | 0 | 0 | 0 | 0 |  | 05.02 - SOH @ AA53 PO TO COME THROUGH PO 4500045034 BH FCA | Supply for Order 100079771, Item 5 cannot be changed 90028600 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 5 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012860 | RING,STORK PVML PP,WEAR,IMP | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 |  |  | 5300020063 | 30 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0290 | 0050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10012993 | RETAINER,GREASE,NIJHUIS VD1-65.280 PP | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 645 cannot be changed 90028419 item 4310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 645 | 0 | EA | 102000000030485 | 101000000135512 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | AUX LO PUMP |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012993 | RETAINER,GREASE,NIJHUIS VD1-65.280 PP | 2024-07-21 | W |  | 0290 | AUX LO PUMP | INT | AUX LO PUMP |  |  | 90028419_4310 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 645 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4340 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0290 | 0060 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10012994 | THROWER,GREASE,NIJTHUIS VD1-65.280 PP | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 646 cannot be changed 90028419 item 4320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 646 | 0 | EA | 102000000030485 | 101000000135515 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | AUX LO PUMP |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012994 | THROWER,GREASE,NIJTHUIS VD1-65.280 PP | 2024-07-21 | W |  | 0290 | AUX LO PUMP | INT | AUX LO PUMP |  |  | 90028419_4320 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 646 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4350 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0290 | 0070 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10012995 | COUPLING,NIJHUIS VD1-65.280 PP,FLEX | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 647 cannot be changed 90028419 item 4330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 647 | 0 | EA | 101000000002852 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | AUX LO PUMP |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10012995 | COUPLING,NIJHUIS VD1-65.280 PP,FLEX | 2024-07-21 | W |  | 0290 | AUX LO PUMP | INT | AUX LO PUMP |  |  | 90028419_4330 |  |  | DG1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 647 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4360 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0330 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10014156 | CKT:BREAKER,2A,1P,MCB,6KA,DIN RAIL M | 2 | EA | 2 | 0 | 0 | 2 | EA | 26.02 - SOH @ AA02 | Supply for Order 600001815, Item 43 cannot be changed 180129367 item 10 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 48 | AA02 | 5300007843 | 290 | CPT | 7 | 1000029750 | 43 | 30000070 | MM ELECTRICAL MERCHANDISING | 4500046448 | 10 | 2 | EA | 2025-03-07 |  | /180128245 |  | 90030687 | 07 | Execution | 0000084731 | 43 | 0 | EA | 101000000148393 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030687_0010 | 0 | 60 | 56 | 60 | 2025-04-07 | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-04-30 | 2025-04-09 | 2025-04-25 |  |  | 2024-08-30 | 0 | 5000414304_2025_0001 | 2025-02-24 |  | 2025-02-24 | 37FQI40/41 |  | 0 | 2 | 2 | 90030687 | 0 | 2 |  | 2 | 0 | 0 | X | L |  | 0 | 5000414304 |  | 0 | 2025 | /018012824 | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10014156 | CKT:BREAKER,2A,1P,MCB,6KA,DIN RAIL M | 2025-02-11 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030687_0010 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-11 | 10 | 6000015391 | 2025-04-09 | 43 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 290 |  | 5300011702 | 150 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2290 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10015069 | GASKET,CNAF,410 X 430 X 3MM THK,RF | 4 | EA | 11 | 0 | 0 | 4 | EA | 03.10 - SOH at AA02 | Supply for Order 200091513, Item 334 cannot be changed 90028419 item 2600 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2630 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 334 | 0 | EA | 102000000030608 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2600 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015069 | GASKET,CNAF,410 X 430 X 3MM THK,RF | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2600 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 334 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2630 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200090684 | 0010 | 0022 | 200090684 | 6Y P02 EXCHANGER INTERNAL INSPECT (2) | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10015541 | GASKET;T109,LA2,418X478MM,KLINGER 133662 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200090684, Item 2 cannot be changed 90024962 item 20 already exists | Material picked; currently at SW3R01H02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004268 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024962 | 05 | Preparation | 0000128878 | 2 | 0 | EA |  |  | 102000000029647 |  |  |  |  | WorkPackLink | SW3R01H02B | AU01-P08-DG | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024962_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200613512 |  | 0 | 2 | 0 | 90024962 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015541 | GASKET;T109,LA2,418X478MM,KLINGER 133662 | 2024-01-02 | W |  | 0010 | HPWW of Tube Bundles 1KKT2410E1 & E2 | ENON | HPWW of Tube Bundles 1KKT2410E1 & E2 | 5 |  | 90024962_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000128347 | S002 |  | 30 | 5300004268 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128878 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200090684 | 0010 | 0042 | 200090684 | 6Y P02 EXCHANGER INTERNAL INSPECT (2) | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10015541 | GASKET;T109,LA2,418X478MM,KLINGER 133662 | 2 | EA | 4 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200090684, Item 4 cannot be changed 90024962 item 40 already exists | Material picked; currently at SW3R01H02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004268 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024962 | 05 | Preparation | 0000128878 | 4 | 0 | EA |  |  | 102000000029649 |  |  |  |  | WorkPackLink | SW3R01H02B | AU01-P08-DG | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024962_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200613512 |  | 0 | 2 | 0 | 90024962 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015541 | GASKET;T109,LA2,418X478MM,KLINGER 133662 | 2024-01-02 | W |  | 0010 | HPWW of Tube Bundles 1KKT2410E1 & E2 | ENON | HPWW of Tube Bundles 1KKT2410E1 & E2 | 5 |  | 90024962_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000128347 | S002 |  | 30 | 5300004268 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128878 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-22 | 2025-02-28 | 2025-03-01 | MECH | 200147066 | 0040 | 0010 | 200147066 | 12Y EX/SH INSP TUB/RVI BUNREM 1KKT2410E1 | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10015541 | GASKET;T109,LA2,418X478MM,KLINGER 133662 | 2 | EA | 4 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147066, Item 4 cannot be changed 90028594 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020024 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028594 | 05 | Preparation | 0000235151 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028594_0010 | 0 | 0 | 0 | 0 |  | 2025-02-25 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-12 | 0 |  | 2025-02-22 |  | 2025-02-27 | 200147066 |  | 0 | 2 | 0 | 90028594 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015541 | GASKET;T109,LA2,418X478MM,KLINGER 133662 | 2025-01-14 | W |  | 0040 | Remove Bonnet & Bundle | INT | Remove Bonnet & Bundle |  |  | 90028594_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232217 | S002 |  | 30 | 5300020024 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-29 | 235151 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-22 | 2025-02-28 | 2025-03-01 | MECH | 200147067 | 0040 | 0010 | 200147067 | 12Y EX/SH INSP TUB/RVI BUNREM 1KKT2410E2 | AA53.1KKT2410E2 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 S | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10015541 | GASKET;T109,LA2,418X478MM,KLINGER 133662 | 2 | EA | 4 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147067, Item 1 cannot be changed 90028593 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020025 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028593 | 05 | Preparation | 0000235152 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028593_0010 | 0 | 0 | 0 | 0 |  | 2025-02-25 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-12 | 0 |  | 2025-02-22 |  | 2025-02-27 | 200147067 |  | 0 | 2 | 0 | 90028593 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015541 | GASKET;T109,LA2,418X478MM,KLINGER 133662 | 2025-01-14 | W |  | 0040 | Remove Bonnet & Bundle | INT | Remove Bonnet & Bundle |  |  | 90028593_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232218 | S002 |  | 30 | 5300020025 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-29 | 235152 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200090684 | 0010 | 0052 | 200090684 | 6Y P02 EXCHANGER INTERNAL INSPECT (2) | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10015542 | GASKET;T109,LA2,418X478MM,KLINGER 133664 | 2 | EA | 0 | 0 | 2 | 2 | EA | 29.01 - At KGP | Supply for Order 200090684, Item 5 cannot be changed 180113620 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004268 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180113620 | 9024093 | 05 | Preparation | 0000128878 | 5 | 0 | EA |  |  | 102000000029650 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-MATERIALS | AU01-P08-DG | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000351706_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000051428 | 1020 | 2025-07-31 | 2 |  | 2025-01-10 | 4900207107_2025_0001 | 2025-03-01 | 2200613512 | 5000351706_2025_0001 | 0 | 2 | 0 | 90024962 | 2 | 0 | 180113620 | 2 | 0 | 0 | X | L | 4900207107 | 2025 |  | 5000351706 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015542 | GASKET;T109,LA2,418X478MM,KLINGER 133664 | 2024-01-02 | W |  | 0010 | HPWW of Tube Bundles 1KKT2410E1 & E2 | ENON | HPWW of Tube Bundles 1KKT2410E1 & E2 | 5 |  | 9024093_0050 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ | 1000004695 | AU1072 | 1000128347 | S002 |  | 30 | 5300004268 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-15 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128878 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-22 | 2025-02-28 | 2025-03-01 | MECH | 200147066 | 0040 | 0020 | 200147066 | 12Y EX/SH INSP TUB/RVI BUNREM 1KKT2410E1 | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10015542 | GASKET;T109,LA2,418X478MM,KLINGER 133664 | 2 | EA | 0 | 0 | 2 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147066, Item 5 cannot be changed 90028594 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020024 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028594 | 05 | Preparation | 0000235151 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028594_0020 | 0 | 0 | 0 | 0 |  | 2025-02-25 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-12 | 0 |  | 2025-02-22 |  | 2025-02-27 | 200147066 |  | 0 | 2 | 0 | 90028594 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015542 | GASKET;T109,LA2,418X478MM,KLINGER 133664 | 2025-01-14 | W |  | 0040 | Remove Bonnet & Bundle | INT | Remove Bonnet & Bundle |  |  | 90028594_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232217 | S002 |  | 30 | 5300020024 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-29 | 235151 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-22 | 2025-02-28 | 2025-03-01 | MECH | 200147067 | 0040 | 0020 | 200147067 | 12Y EX/SH INSP TUB/RVI BUNREM 1KKT2410E2 | AA53.1KKT2410E2 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 S | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10015542 | GASKET;T109,LA2,418X478MM,KLINGER 133664 | 2 | EA | 0 | 0 | 2 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147067, Item 2 cannot be changed 90028593 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020025 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028593 | 05 | Preparation | 0000235152 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028593_0020 | 0 | 0 | 0 | 0 |  | 2025-02-25 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-12 | 0 |  | 2025-02-22 |  | 2025-02-27 | 200147067 |  | 0 | 2 | 0 | 90028593 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015542 | GASKET;T109,LA2,418X478MM,KLINGER 133664 | 2025-01-14 | W |  | 0040 | Remove Bonnet & Bundle | INT | Remove Bonnet & Bundle |  |  | 90028593_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232218 | S002 |  | 30 | 5300020025 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-29 | 235152 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200090684 | 0010 | 0060 | 200090684 | 6Y P02 EXCHANGER INTERNAL INSPECT (2) | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10015543 | GASKET;T109,LA2,310X290MM,KLINGER 133663 | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 200090684, Item 1 cannot be changed 90024962 item 10 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300004268 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024962 | 05 | Preparation | 0000128878 | 1 | 0 | EA | 102000000026607 |  | 102000000029606 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | AU01-P08-DG | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024962_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200613512 |  | 0 | 2 | 0 | 90024962 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015543 | GASKET;T109,LA2,310X290MM,KLINGER 133663 | 2024-01-02 | W |  | 0010 | HPWW of Tube Bundles 1KKT2410E1 & E2 | ENON | HPWW of Tube Bundles 1KKT2410E1 & E2 | 5 |  | 90024962_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000128347 | S002 |  | 30 | 5300004268 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128878 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-22 | 2025-02-28 | 2025-03-01 | MECH | 200147066 | 0040 | 0030 | 200147066 | 12Y EX/SH INSP TUB/RVI BUNREM 1KKT2410E1 | AA53.1KKT2410E1 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10015543 | GASKET;T109,LA2,310X290MM,KLINGER 133663 | 2 | EA | 2 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147066, Item 6 cannot be changed 90028594 item 30 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020024 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028594 | 05 | Preparation | 0000235151 | 6 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028594_0030 | 0 | 0 | 0 | 0 |  | 2025-02-25 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-12 | 0 |  | 2025-02-22 |  | 2025-02-27 | 200147066 |  | 0 | 2 | 0 | 90028594 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015543 | GASKET;T109,LA2,310X290MM,KLINGER 133663 | 2025-01-14 | W |  | 0040 | Remove Bonnet & Bundle | INT | Remove Bonnet & Bundle |  |  | 90028594_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232217 | S002 |  | 30 | 5300020024 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-29 | 235151 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-22 | 2025-02-28 | 2025-03-01 | MECH | 200147067 | 0040 | 0030 | 200147067 | 12Y EX/SH INSP TUB/RVI BUNREM 1KKT2410E2 | AA53.1KKT2410E2 | EXCH,HEAT LUBEOIL COOLER 1KKT2410 S | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10015543 | GASKET;T109,LA2,310X290MM,KLINGER 133663 | 2 | EA | 2 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147067, Item 3 cannot be changed 90028593 item 30 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020025 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028593 | 05 | Preparation | 0000235152 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028593_0030 | 0 | 0 | 0 | 0 |  | 2025-02-25 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-12 | 0 |  | 2025-02-22 |  | 2025-02-27 | 200147067 |  | 0 | 2 | 0 | 90028593 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015543 | GASKET;T109,LA2,310X290MM,KLINGER 133663 | 2025-01-14 | W |  | 0040 | Remove Bonnet & Bundle | INT | Remove Bonnet & Bundle |  |  | 90028593_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232218 | S002 |  | 30 | 5300020025 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-29 | 235152 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200090882 | 0040 | 0020 | 200090882 | 12Y INT INSP EXCHANGER 1K1820E1A | AA53.1K1820E1A | EXCH,HEAT LUBE OIL FRAC T1 1K1820 | AA01 | 10 | WO item has not been released yet | 10015562 | PLUG,1.125"UNF X 42MM,CS,A105N | 2 | EA | 40 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000129132 | 1 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200090882 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015562 | PLUG,1.125"UNF X 42MM,CS,A105N |  |  |  | 0040 | Remove Fin Fan Plugs (16) | INT | Remove Fin Fan Plugs (16) | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000128534 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Ready For Scheduling/Material committed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-08-15 | 2025-03-01 |  | 2025-02-19 | 2025-03-03 | MECH | 600003215 | 0020 | 0080 | 600003215 | MOC-117109 1E1303 Exchanger Replacement | AA53.1E1303 | EXCH,HEAT AIR COOL REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10015562 | PLUG,1.125"UNF X 42MM,CS,A105N | 20 | EA | 40 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000254308 | 8 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015562 | PLUG,1.125"UNF X 42MM,CS,A105N |  |  |  | 0020 | Remove blanks For Inspection Access | INT | Remove blanks For Inspection Access |  | Management of Change |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000250524 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W35069 | 2024-08-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-02-19 | 2025-02-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0030 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10015665 | PLUG,APCI CRY HEAT EXCH,MODIFIED 6",AL | 8 | EA | 24 | 0 | 0 | 8 | EA | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 3 cannot be changed 90032376 item 30 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 3 | 0 | EA |  |  | 102000000034530 |  |  |  |  | WorkPackLink | PACKING | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0030 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015665 | PLUG,APCI CRY HEAT EXCH,MODIFIED 6",AL | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0030 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 |  | 30 | 5300022012 | 30 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0010 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.01.2025) | 10015709 | GASKET;WE SMITH IE23022E2302 | 2 | EA | 1 | 0 | 0 | 1 | EA | 21.01 - ETA 12.03.25 PO 4500043420 KLINGER CPT | Supply for Order 200147128, Item 1 cannot be changed 90030059 item 10 already exists | Material picked; currently at SW3R02A02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020226 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030059 | 05 | Preparation | 0000235400 | 1 | 0 | EA |  |  | 102000000033943 |  |  |  |  | WorkPackLink | SW3R02A02B | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-20 | ODST-0090030059_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147128 |  | 0 | 2 | 0 | 90030059 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015709 | GASKET;WE SMITH IE23022E2302 | 2025-01-20 | W |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection |  |  | 90030059_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000232443 | S002 |  | 30 | 5300020226 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235400 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0300 | 0010 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10017159 | BEARING,BALL,RAD,80 X 140 X 26MM THK,C3 | 1 | EA | 3 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 717 cannot be changed 90028419 item 4800 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 717 | 0 | EA | 102000000030388 | 102000000030143 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4800 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017159 | BEARING,BALL,RAD,80 X 140 X 26MM THK,C3 | 2024-07-21 | W |  | 0300 | STARTER MOTOR M7 | INT | STARTER MOTOR M7 |  |  | 90028419_4800 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 717 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4840 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0292 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10017185 | BEARING,BALL,RAD,20 X 52 X 15MM THK,C3 | 2 | EA | 6 | 0 | 0 | 2 | EA | 06.01 - SOH @ AA02 | Supply for Order 200091126, Item 68 cannot be changed 90023534 item 270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 68 | 0 | EA | 102000000030447 | 102000000030147 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO Pump |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017185 | BEARING,BALL,RAD,20 X 52 X 15MM THK,C3 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0270 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 68 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 520 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2970 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10017279 | BEARING,BALL,RAD,120 X 180 X 28MM THK,2Z | 1 | EA | 2 | 0 | 0 | 0 |  | 03.10 - SOH at AA02 | Supply for Order 200091513, Item 426 cannot be changed 90028419 item 2970 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3000 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 426 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2970 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017279 | BEARING,BALL,RAD,120 X 180 X 28MM THK,2Z | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2970 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 426 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3000 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10017335 | BEARING,BALL,RAD,100 X 180 X 34MM THK,2Z | 2 | EA | 7 | 0 | 0 | 2 | EA | 03.10 - SOH at AA02 | Supply for Order 200091513, Item 599 cannot be changed 90028419 item 4080 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 599 | 0 | EA | 102000000030496 | 102000000030733 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017335 | BEARING,BALL,RAD,100 X 180 X 34MM THK,2Z | 2024-07-21 | W |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  | 90028419_4080 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 599 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4110 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0290 | 0080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10017362 | BRG BALL | 2 | EA | 7 | 0 | 0 | 2 | EA | 03.10 - SOH at AA02 | Supply for Order 200091513, Item 648 cannot be changed 90028419 item 4340 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 648 | 0 | EA | 102000000030485 | 102000000030146 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4340 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | AUX LO PUMP |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017362 | BRG BALL | 2024-07-21 | W |  | 0290 | AUX LO PUMP | INT | AUX LO PUMP |  |  | 90028419_4340 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 648 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4370 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0290 | 0090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10017475 | BEARING,BALL;SELF-ALIGN,35X80X23MM | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 649 cannot be changed 90028419 item 4350 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 649 | 0 | EA | 102000000030485 | 101000000135506 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4350 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | AUX LO PUMP |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017475 | BEARING,BALL;SELF-ALIGN,35X80X23MM | 2024-07-21 | W |  | 0290 | AUX LO PUMP | INT | AUX LO PUMP |  |  | 90028419_4350 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 649 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4380 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0300 | 0020 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10017513 | BEARING,RL,CYL,75 X 130 X 25MM THK | 1 | EA | 1 | 0 | 1 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 718 cannot be changed 90028419 item 4810 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 718 | 0 | EA | 102000000030388 | 101000000146593 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4810 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017513 | BEARING,RL,CYL,75 X 130 X 25MM THK | 2024-07-21 | W |  | 0300 | STARTER MOTOR M7 | INT | STARTER MOTOR M7 |  |  | 90028419_4810 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 718 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4850 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0300 | 0030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10017514 | BEARING,RL,CYL,80 X 140 X 26MM THK | 1 | EA | 1 | 0 | 1 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 719 cannot be changed 90028419 item 4820 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 719 | 0 | EA | 102000000030388 | 101000000146592 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4820 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017514 | BEARING,RL,CYL,80 X 140 X 26MM THK | 2024-07-21 | W |  | 0300 | STARTER MOTOR M7 | INT | STARTER MOTOR M7 |  |  | 90028419_4820 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 719 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4860 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-07-23 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 200146424 | 0010 | 0010 | 200146424 | 5Y SVC 5KM2001 MOTOR MAJOR MATERIAL 2HF1 | AA53.5KM2001 | MOTOR,HV,MAIN,STABILIZER COMP,5K2001 |  | 20 | WO item has not been released yet | 10017741 | BEARING,SLVE;200MM,SIEMENS DRG31021B | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234301 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017741 | BEARING,SLVE;200MM,SIEMENS DRG31021B |  |  |  | 0010 | MOTOR MAJOR MATERIALS 2HF1 | INT | MOTOR MAJOR MATERIALS 2HF1 | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231257 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-22 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-07-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146424 | 0010 | 0030 | 200146424 | 5Y SVC 5KM2001 MOTOR MAJOR MATERIAL 2HF1 | AA53.5KM2001 | MOTOR,HV,MAIN,STABILIZER COMP,5K2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.07.2024) | 10017748 | RING,SEALING;AL99F101,SIEMENS 8MUN54111 | 1 | EA | 3 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200146424, Item 3 cannot be changed 90024989 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013117 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024989 | 05 | Preparation | 0000234301 | 3 | 0 | EA | 102000000031789 | 102000000027582 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-23 | ODST-0090024989_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-04 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024989 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017748 | RING,SEALING;AL99F101,SIEMENS 8MUN54111 | 2024-07-22 | W |  | 0010 | MOTOR MAJOR MATERIALS 2HF1 | INT | MOTOR MAJOR MATERIALS 2HF1 | 5 |  | 90024989_0020 |  |  | ST5 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231257 | S002 |  | 30 | 5300013117 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-22 | 234301 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0060 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10017976 | SEAL,MECH;FLOWSV A1T2104001Q1 | 1 | EA | 1 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 100079771, Item 6 cannot be changed 90028600 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 6 | 0 | EA | 102000000032254 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017976 | SEAL,MECH;FLOWSV A1T2104001Q1 | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0040 |  |  | ST5 |  | C1 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 | 30 | 30 | 5300020063 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0540 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10017999 | SEAL,MECH,BW UZ-1500/5N4A,>WSE10231355 | 1 | EA | 1 | 0 | 0 | 1 | EA | 17.01 - 1 SOH @ AA02 | Supply for Order 200091505, Item 62 cannot be changed 90025019 item 610 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 62 | 0 | EA | 102000000027741 |  | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0610 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | LOPump |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10017999 | SEAL,MECH,BW UZ-1500/5N4A,>WSE10231355 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0610 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 62 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 74 | 74 | 5300015903 | 610 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0312 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10018041 | SEAL MECH | 1 | EA | 0 | 0 | 0 | 0 |  | 02.10 - ETA 14.03.25 PO 4500029644 ex Flowserv | Supply for Order 200091126, Item 70 cannot be changed 90023534 item 290 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 70 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO Pump |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018041 | SEAL MECH | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0290 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 70 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 540 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0832 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE |  | 20 | No issue identified | 10018055 | SEAL MECH | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000129754 | 97 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-06-05 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018055 | SEAL MECH |  |  |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000129164 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0852 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10018055 | SEAL MECH | 1 | EA | 5 | 0 | 0 | 1 | EA | 30.09 - SOH @ AA02 | Supply for Order 200091505, Item 99 cannot be changed 90025019 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90025019 | 05 | Preparation | 0000129754 | 99 | 0 | EA | 102000000027744 |  | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOPump |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018055 | SEAL MECH | 2024-09-30 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0020 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 99 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0070 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10018065 | SLV SHFT | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 14.03.25 PO 4500043947 ex Flowserve | Supply for Order 100079771, Item 7 cannot be changed 90028600 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 7 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018065 | SLV SHFT | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0050 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 |  | 30 | 5300020063 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0332 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10018307 | O-RING;VIT,BW DRGA3G0616S13 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 200091126, Item 72 cannot be changed 90023534 item 310 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 72 | 0 | EA | 101000000143085 |  | 101000000143157 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  | 2025-02-13 | Y | 1001 | 2024-01-02 | ODST-0090023534_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO Pump |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018307 | O-RING;VIT,BW DRGA3G0616S13 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90023534_0310 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 72 |  | 0 |  | 25SD2301 | MJ | 20005191 | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 560 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-11 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0290 | 0100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10018428 | SEAL,OIL;045-072-10MM,NTRL/CS,SNGL | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 650 cannot be changed 90028419 item 4360 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 650 | 0 | EA | 102000000030485 | 101000000135546 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4360 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | AUX LO PUMP |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018428 | SEAL,OIL;045-072-10MM,NTRL/CS,SNGL | 2024-07-21 | W |  | 0290 | AUX LO PUMP | INT | AUX LO PUMP |  |  | 90028419_4360 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 650 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4390 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0282 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10018442 | SEAL,OIL;075-095-10MM,NTRL/CS,SNGL | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH at AA02 | Supply for Order 200091126, Item 124 cannot be changed 90023534 item 720 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1010 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 124 | 0 | EA | 102000000030443 | 102000000031082 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0720 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018442 | SEAL,OIL;075-095-10MM,NTRL/CS,SNGL | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0720 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 124 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1010 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1970 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10018468 | SEAL,OIL;1.375-2.062-0.375",NTRL/CS,SNGL | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 277 cannot be changed 90028419 item 2160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 277 | 0 | EA | 102000000030501 | 102000000030630 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ONCONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018468 | SEAL,OIL;1.375-2.062-0.375",NTRL/CS,SNGL | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_2160 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 277 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2190 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2110 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10018645 | ELEMENT,FLT;HYD,PALL HC9601FHP11ZYGE | 2 | EA | 14 | 0 | 0 | 2 | EA | 06.01 - SOH @ AA02 | Supply for Order 200091513, Item 316 cannot be changed 90028419 item 2480 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2510 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 316 | 0 | EA | 102000000030096 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2480 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018645 | ELEMENT,FLT;HYD,PALL HC9601FHP11ZYGE | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2480 |  |  | DG1 |  | C5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 316 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2510 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0110 | 0010 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(03.02.2025) | 10018647 | FILTER,OIL;LUBE OIL,PALL HC8400FKS26H | 1 | EA | 2 | 0 | 0 | 1 | EA | 27.02 - SOH at AA02 | Supply for Order 200147980, Item 188 cannot be changed 90030140 item 20 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 930 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030140 | 05 | Preparation | 0000236589 | 188 | 0 | EA | 101000000144060 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090030140_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030140 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018647 | FILTER,OIL;LUBE OIL,PALL HC8400FKS26H | 2025-02-03 | W |  | 0110 | FILTER CARTRIDGE | INT | FILTER CARTRIDGE | 5 |  | 90030140_0020 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 188 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 930 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-06 | ROTAT | 100046308 | 0050 | 0050 | 100046308 | MOC-52386 - Tank Min Oil Replace - G4008 | AA53.G4008V1 | TANK,MINERAL OIL RESERVOIR G4008 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z | 2 | EA | 8 | 0 | 6 | 2 | EA | 18.12 - SOH @ AA02 | Supply for Order 100046308, Item 5 cannot be changed 90024955 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002735 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024955 | 05 | Preparation | 0000144829 | 5 | 0 | EA | 102000000027388 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024955_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-06-25 | 0 |  | 2025-02-24 |  | 2025-03-01 | MLO FILTER |  | 0 | 2 | 0 | 90024955 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z | 2024-01-02 | W |  | 0050 | Replace lube oil filters - 12 micron | INT | Replace lube oil filters - 12 micron | 5 |  | 90024955_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 5 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000144178 | S002 | 30 | 30 | 5300002735 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144829 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Estimated costs | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0140 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018700 | O-RING;ARLON BDGH 2230 DUPLEX FLT,BS244 | 2 | EA | 0 | 0 | 0 | 0 |  | 18.12 - qty 2 SOH at AA01 | Supply for Order 200091108, Item 119 cannot be changed 90028420 item 810 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 119 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0810 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOX-Over |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018700 | O-RING;ARLON BDGH 2230 DUPLEX FLT,BS244 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0810 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 119 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 850 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0150 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018701 | O-RING;BUNAN,0.103",0.862"ID,70,BS118 | 2 | EA | 0 | 2 | 0 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091108, Item 120 cannot be changed 9027124 item 820 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 120 | 0 | EA | 102000000030563 | 101000000134535 | 102000000030441 |  |  |  |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0109 | 2025-03-01 | SOX-Over |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018701 | O-RING;BUNAN,0.103",0.862"ID,70,BS118 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 9027124_0820 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 120 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 860 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0170 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018702 | O-RING;BUNAN,0.139",2.734"ID,70,BS233 | 2 | EA | 0 | 2 | 0 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091108, Item 122 cannot be changed 9027124 item 840 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 122 | 0 | EA | 102000000030564 | 101000000134536 | 102000000030441 |  |  |  |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0113 | 2025-03-01 | SOX-Over |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018702 | O-RING;BUNAN,0.139",2.734"ID,70,BS233 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 9027124_0840 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 122 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 880 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0130 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018703 | O-RING;ARLON BDGH 2230 DUPLEX FLT,BS027 | 2 | EA | 0 | 2 | 0 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091108, Item 118 cannot be changed 9027124 item 800 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 118 | 0 | EA | 102000000030441 | 101000000134537 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0107 | 2025-03-01 | SOX-Over |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018703 | O-RING;ARLON BDGH 2230 DUPLEX FLT,BS027 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 9027124_0800 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 118 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 840 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0160 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018704 | O-RING;BUNAN,0.139",1.609"ID,70,BS223 | 2 | EA | 0 | 2 | 0 | 2 | EA | 13.02 - SOH @ AA02 | Supply for Order 200091108, Item 121 cannot be changed 9027124 item 830 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 121 | 0 | EA | 102000000030566 | 101000000134538 | 102000000030441 |  |  |  |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0111 | 2025-03-01 | SOX-Over |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018704 | O-RING;BUNAN,0.139",1.609"ID,70,BS223 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 9027124_0830 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 121 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 870 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0180 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018705 | O-RING;BUNAN,0.139",3.234"ID,70,BS236 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091108, Item 123 cannot be changed 90028420 item 850 already exists | Material picked; currently at SW3R01B02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 890 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 123 | 0 | EA |  |  | 102000000030313 |  |  |  |  | WorkPackLink | SW3R01B02B |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0850 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOX-Over |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018705 | O-RING;BUNAN,0.139",3.234"ID,70,BS236 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0850 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 123 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 890 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0190 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018707 | PACKING,ARLON BDGH 2-230 FILTER,CARBON | 2 | EA | 5 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091108, Item 124 cannot be changed 90028420 item 860 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 900 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 124 | 0 | EA | 102000000030112 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0860 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOX-Over |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018707 | PACKING,ARLON BDGH 2-230 FILTER,CARBON | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0860 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 124 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 | 70 | 70 | 5300013062 | 900 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0080 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018708 | FILTER ELEM,OIL,ARLON TXX5-10,PAPER,10UM | 2 | EA | 6 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091108, Item 113 cannot be changed 90028420 item 760 already exists | Material picked; currently at SW3R01B02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 113 | 0 | EA |  |  | 102000000030097 |  |  |  |  | WorkPackLink | SW3R01B02A |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0760 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOFilter |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018708 | FILTER ELEM,OIL,ARLON TXX5-10,PAPER,10UM | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0760 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 113 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 790 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2230 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10018708 | FILTER ELEM,OIL,ARLON TXX5-10,PAPER,10UM | 2 | EA | 6 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 328 cannot be changed 90028419 item 2550 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 328 | 0 | EA | 101000000142795 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018708 | FILTER ELEM,OIL,ARLON TXX5-10,PAPER,10UM | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2550 |  |  | DG1 |  | C5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 328 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2580 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0120 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018709 | NUT,HEX,M10,ISO MTR,GR,CS,PLTD,CASTLE | 2 | EA | 0 | 2 | 0 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091108, Item 117 cannot be changed 9027124 item 790 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 117 | 0 | EA | 102000000030155 | 101000000134320 | 102000000030441 |  |  |  |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0105 | 2025-03-01 | SOX-Over |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018709 | NUT,HEX,M10,ISO MTR,GR,CS,PLTD,CASTLE | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 9027124_0790 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 117 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 830 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0450 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10018744 | GASKET;ACCEPTABLE ALTERNATIVES | 4 | EA | 6 | 0 | 0 | 4 | EA | 10.01 - Picked @ KSF | Supply for Order 200091505, Item 55 cannot be changed 90025019 item 540 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 55 | 0 | EA | 102000000032113 | 102000000026606 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0540 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealOilFilt |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018744 | GASKET;ACCEPTABLE ALTERNATIVES | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0540 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 55 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 540 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0030 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z | 3 | EA | 15 | 0 | 0 | 3 | EA | 10.01 - Picked @ KSF | Supply for Order 200085979, Item 3 cannot be changed 90025121 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 3 | 0 | EA | 102000000032090 | 102000000027967 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0030 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0030 |  |  | FR0 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 | 30 | 30 | 5300018160 | 30 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0010 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z | 1 | EA | 15 | 0 | 0 | 1 | EA | 10.01 - Picked @ KSF | Supply for Order 200146440, Item 1 cannot be changed 90025098 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 1 | 0 | EA | 102000000027966 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 | 30 | 30 | 5300017633 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0010 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON | 1 | EA | 9 | 0 | 0 | 1 | EA | 10.01 - Picked @ KSF | Supply for Order 200085979, Item 1 cannot be changed 90025121 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 1 | 0 | EA | 102000000032090 | 102000000027964 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0010 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0010 |  |  | FR0 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 |  | 30 | 5300018160 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0020 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON | 1 | EA | 9 | 0 | 0 | 1 | EA | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 2 cannot be changed 90025098 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 2 | 0 | EA | 102000000027963 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0020 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 |  | 30 | 5300017633 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0060 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10018775 | FILTER,ELEM;HYD,12UM,PALL HC2217FHS4Z | 1 | EA | 9 | 0 | 0 | 1 | EA | 21.11 - SOH @ AA02 | Supply for Order 200085979, Item 6 cannot be changed 90025121 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 6 | 0 | EA | 102000000032090 | 102000000026773 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0060 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018775 | FILTER,ELEM;HYD,12UM,PALL HC2217FHS4Z | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0060 |  |  | FR0 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 | 30 | 30 | 5300018160 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0030 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018775 | FILTER,ELEM;HYD,12UM,PALL HC2217FHS4Z | 1 | EA | 9 | 0 | 0 | 1 | EA | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 3 cannot be changed 90025098 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 3 | 0 | EA | 102000000026772 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018775 | FILTER,ELEM;HYD,12UM,PALL HC2217FHS4Z | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0030 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 | 30 | 30 | 5300017633 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0040 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018778 | ELEMENT,FLT;12UM,PALL HC2237FHS6Z | 1 | EA | 4 | 0 | 0 | 1 | EA | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 4 cannot be changed 90025098 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 4 | 0 | EA | 102000000026767 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018778 | ELEMENT,FLT;12UM,PALL HC2237FHS6Z | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0040 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 |  | 30 | 5300017633 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0050 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018779 | ELEMENT,FLT;12UM,PALL HC2246FRS6H50 | 1 | EA | 5 | 0 | 0 | 1 | EA | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 5 cannot be changed 90025098 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 5 | 0 | EA | 102000000026769 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018779 | ELEMENT,FLT;12UM,PALL HC2246FRS6H50 | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0050 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 |  | 30 | 5300017633 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0090 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10018784 | ELEMENT,FLT;HYD,PALL HC2226FRS4H50 | 1 | EA | 1 | 0 | 0 | 1 | EA | 21.11 - SOH @ AA02 | Supply for Order 200085979, Item 9 cannot be changed 90025121 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 9 | 0 | EA | 102000000032090 | 102000000027962 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0090 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018784 | ELEMENT,FLT;HYD,PALL HC2226FRS4H50 | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0090 |  |  | FR0 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 |  | 30 | 5300018160 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0080 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10018832 | REPAIR KIT;HYDAC 304311 | 3 | KIT | 10 | 1 | 0 | 3 | KIT | 21.11 - SOH @ AA02 | Supply for Order 200085979, Item 8 cannot be changed 90025121 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 8 | 0 | KIT | 102000000032090 | 102000000029451 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0080 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018832 | REPAIR KIT;HYDAC 304311 | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0080 |  |  | FR0 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 | 30 | 30 | 5300018160 | 80 |  |  | 0 | 3 | KIT | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0060 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018832 | REPAIR KIT;HYDAC 304311 | 1 | KIT | 10 | 1 | 0 | 1 | KIT | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 6 cannot be changed 90025098 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 6 | 0 | KIT | 102000000029431 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018832 | REPAIR KIT;HYDAC 304311 | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0060 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 | 30 | 30 | 5300017633 | 60 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0040 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 | 1 | KIT | 9 | 1 | 0 | 1 | KIT | 21.11 - SOH @ AA02 | Supply for Order 200085979, Item 4 cannot be changed 90025121 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 4 | 0 | KIT | 102000000032090 | 102000000029432 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0040 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0040 |  |  | FR0 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 |  | 30 | 5300018160 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0070 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 | 1 | KIT | 9 | 1 | 0 | 1 | KIT | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 7 cannot be changed 90025098 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 7 | 0 | KIT | 102000000029450 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 |  | 30 | 5300017633 | 70 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0080 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018835 | SEAL KIT;O-RING,HYDAC 313828 | 1 | KIT | 3 | 0 | 0 | 1 | KIT | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 8 cannot be changed 90025098 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 8 | 0 | KIT | 102000000027592 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018835 | SEAL KIT;O-RING,HYDAC 313828 | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 | 30 | 30 | 5300017633 | 80 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0050 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10018845 | SEAL KIT:FLTR,HYDAC,1267827 | 1 | KIT | 8 | 0 | 0 | 1 | KIT | 21.11 - SOH @ AA02 | Supply for Order 200085979, Item 5 cannot be changed 90025121 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 5 | 0 | KIT | 102000000032090 | 102000000027569 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0050 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018845 | SEAL KIT:FLTR,HYDAC,1267827 | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0050 |  |  | FR0 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 | 30 | 30 | 5300018160 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0090 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018845 | SEAL KIT:FLTR,HYDAC,1267827 | 1 | KIT | 8 | 0 | 0 | 1 | KIT | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 9 cannot be changed 90025098 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 9 | 0 | KIT | 102000000027568 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018845 | SEAL KIT:FLTR,HYDAC,1267827 | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0090 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 | 30 | 30 | 5300017633 | 90 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0020 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10018847 | SEAL | 1 | KIT | 1 | 0 | 0 | 1 | KIT | 23.01 - SOH @ AA02 | Supply for Order 200085979, Item 2 cannot be changed 90025121 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 2 | 0 | KIT | 102000000030565 | 101000000134534 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0020 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018847 | SEAL | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0020 |  |  | FR0 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 | 30 | 30 | 5300018160 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0100 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10018848 | KT | 1 | KIT | 8 | 1 | 0 | 1 | KIT | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 10 cannot be changed 90025098 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 10 | 0 | KIT | 102000000029434 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018848 | KT | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0100 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 |  | 30 | 5300017633 | 100 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0112 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10019306 | FILTER,BREATHER THOMASSEN C25-2,G/BOX | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 100 cannot be changed 90023534 item 520 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 100 | 0 | EA | 102000000030435 | 102000000031108 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0520 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | crank breath |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019306 | FILTER,BREATHER THOMASSEN C25-2,G/BOX | 2024-05-11 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 90023534_0520 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 100 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 790 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0200 | 0830 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10019378 | VALVE,COMPRESSOR,SUCTION,234CMD | 4 | EA | 3 | 0 | 0 | 1 | EA | 25.02 - SOH @ AA02 | Supply for Order 200147980, Item 119 cannot be changed 90028418 item 380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 119 | 0 | EA | 101000000148141 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Suc Valve |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019378 | VALVE,COMPRESSOR,SUCTION,234CMD | 2024-09-23 | W |  | 0200 | SUCTION VALVE ASSY | INT | SUCTION VALVE ASSY | 5 |  | 90028418_0380 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 119 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 390 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0200 | 0830 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10019378 | VALVE,COMPRESSOR,SUCTION,234CMD | 4 | EA | 3 | 0 | 0 | 1 | EA | 25.02 - SOH @ AA02 | Supply for Order 200147980, Item 119 cannot be changed 90028418 item 380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 119 | 0 | EA | 101000000148142 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Suc Valve |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019378 | VALVE,COMPRESSOR,SUCTION,234CMD | 2024-09-23 | W |  | 0200 | SUCTION VALVE ASSY | INT | SUCTION VALVE ASSY | 5 |  | 90028418_0380 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 119 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 390 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0200 | 0830 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10019378 | VALVE,COMPRESSOR,SUCTION,234CMD | 4 | EA | 3 | 0 | 0 | 1 | EA | 25.02 - SOH @ AA02 | Supply for Order 200147980, Item 119 cannot be changed 90028418 item 380 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 119 | 0 | EA | 101000000148135 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0380 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Suc Valve |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019378 | VALVE,COMPRESSOR,SUCTION,234CMD | 2024-09-23 | W |  | 0200 | SUCTION VALVE ASSY | INT | SUCTION VALVE ASSY | 5 |  | 90028418_0380 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 119 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 390 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0070 | 0380 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10019379 | VALVE,DISCH;COMP,234CMK,HOERBIGER 20992+ | 4 | EA | 4 | 0 | 0 | 1 | EA | 27.06 - SOH @ AA02 | Supply for Order 200147980, Item 110 cannot be changed 90028418 item 320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 110 | 0 | EA | 101000000144731 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019379 | VALVE,DISCH;COMP,234CMK,HOERBIGER 20992+ | 2024-09-23 | W |  | 0070 | DISCHARGE VALVE ASSY | INT | DISCHARGE VALVE ASSY | 5 |  | 90028418_0320 |  |  | ST5 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 110 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 330 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0070 | 0380 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10019379 | VALVE,DISCH;COMP,234CMK,HOERBIGER 20992+ | 4 | EA | 4 | 0 | 0 | 1 | EA | 27.06 - SOH @ AA02 | Supply for Order 200147980, Item 110 cannot be changed 90028418 item 320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 110 | 0 | EA | 101000000120887 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019379 | VALVE,DISCH;COMP,234CMK,HOERBIGER 20992+ | 2024-09-23 | W |  | 0070 | DISCHARGE VALVE ASSY | INT | DISCHARGE VALVE ASSY | 5 |  | 90028418_0320 |  |  | ST5 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 110 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 330 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0070 | 0380 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10019379 | VALVE,DISCH;COMP,234CMK,HOERBIGER 20992+ | 4 | EA | 4 | 0 | 0 | 1 | EA | 27.06 - SOH @ AA02 | Supply for Order 200147980, Item 110 cannot be changed 90028418 item 320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 110 | 0 | EA | 101000000144917 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019379 | VALVE,DISCH;COMP,234CMK,HOERBIGER 20992+ | 2024-09-23 | W |  | 0070 | DISCHARGE VALVE ASSY | INT | DISCHARGE VALVE ASSY | 5 |  | 90028418_0320 |  |  | ST5 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 110 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 330 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0070 | 0380 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10019379 | VALVE,DISCH;COMP,234CMK,HOERBIGER 20992+ | 4 | EA | 4 | 0 | 0 | 1 | EA | 27.06 - SOH @ AA02 | Supply for Order 200147980, Item 110 cannot be changed 90028418 item 320 already exists | Material picked; currently at 30-03-07-81A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 110 | 0 | EA |  |  | 101000000120888 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-07-81A |  | 0 |  | 0 | 0 |  | 0 | 4 | 2025-01-26 | 2025-01-26 | Y | 1001 | 2024-09-24 | ODST-0090028418_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019379 | VALVE,DISCH;COMP,234CMK,HOERBIGER 20992+ | 2024-09-23 | W |  | 0070 | DISCHARGE VALVE ASSY | INT | DISCHARGE VALVE ASSY | 5 |  | 90028418_0320 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 110 |  | 0 |  | 25SDSTB5 | MJ | 20005055 | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 330 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-24 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0302 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10019437 | MEMBRANE,DRV CPLG+CLUTCH;METASTREAM 799> | 1 | EA | 1 | 0 | 1 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 69 cannot be changed 9026640 item 280 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180121305 | 9026640 | 05 | Preparation | 0000129360 | 69 | 0 | EA | 102000000032338 |  | 107000000000132 |  |  |  | P07WHS-R3B | WorkPackLink | P07WHS-R3B | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000385872_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056049 | 1020 | 2023-04-03 | 1 |  | 2025-02-04 | 4900226372_2025_0001 | 2025-03-01 | LO Pump | 5000385872_2025_0001 | 0 | 2 | 0 | 90023534 | 1 | 0 | 180121305 | 2 | 0 | 0 | X | L | 4900226372 | 2025 |  | 5000385872 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019437 | MEMBRANE,DRV CPLG+CLUTCH;METASTREAM 799> | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 9026640_0280 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 69 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 530 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0560 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10019444 | BOLT SET;METASTREAM BFM597BFM628 | 2 | SET | 3 | 0 | 0 | 2 | SET | 17.01 - 3 SOH @ AA02 | Supply for Order 200091505, Item 64 cannot be changed 90025019 item 620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 620 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 64 | 0 | SET | 102000000032113 | 102000000029544 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | LO/SOCplng |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019444 | BOLT SET;METASTREAM BFM597BFM628 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0620 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 64 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 620 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-07-20 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0090 | 0012 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | WO item has not been released yet | 10019561 | BEARING SET,RENK TA45X GBX,4301 & 4302 | 1 | EA | 1 | 0 | 0 | 0 |  | 17.01 - Need purchasing qty x 1. SOH @ AA02 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129754 | 91 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019561 | BEARING SET,RENK TA45X GBX,4301 & 4302 |  |  |  | 0090 | GEARBOX | INT | GEARBOX | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000129164 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0510 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10019562 | BEARING,RENK TA45X GBX,AXIAL,NOS.5 & 6 | 2 | SET | 2 | 0 | 2 | 2 | SET | 17.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 60 cannot be changed 9027110 item 590 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 590 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180124179 | 9027110 | 05 | Preparation | 0000129754 | 60 | 0 | SET |  |  | 102000000029388 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000396418_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056761 | 1020 | 2025-06-05 | 2 |  | 2025-02-11 | 4900234085_2025_0001 | 2025-03-01 | G/Box #5&6 | 5000396418_2025_0001 | 0 | 2 | 0 | 90025019 | 2 | 0 | 180124179 | 2 | 0 | 0 | X | L | 4900234085 | 2025 |  | 5000396418 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019562 | BEARING,RENK TA45X GBX,AXIAL,NOS.5 & 6 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 9027110_0590 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 60 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 590 |  |  | 0 | 2 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT9 | Released | 2024-10-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 100083725 | 0010 | 0040 | 100083725 | GT4009K1A - Vent Fan DE Bearing | AA53.GT4009K1A | FAN,TURBINE ACOUSTIC ENCL VENT,GT4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(27.10.2024) | 10019764 | BUSH,TAPERLOCK,3535 X 80MM BORE | 1 | EA | 2 | 0 | 0 | 1 | EA | 28.10 - SOH @ AA02 | Supply for Order 100083725, Item 4 cannot be changed 90025083 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016986 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025083 | 05 | Preparation | 0000260566 | 4 | 0 | EA | 102000000029290 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-28 | ODST-0090025083_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025083 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019764 | BUSH,TAPERLOCK,3535 X 80MM BORE | 2024-10-27 | W |  | 0010 | GT4009K1A - Vent Fan DE Bearing | INT | GT4009K1A - Vent Fan DE Bearing |  |  | 90025083_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000256336 | S002 |  | 30 | 5300016986 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-09-02 | 260566 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0040 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2 | EA | 24 | 5 | 12 | 2 | EA | 19.02 - At KGP | Supply for Order 100039666, Item 3 cannot be changed 90024949 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122912 | 9027003 | 05 | Preparation | 0000138170 | 3 | 0 | EA | 102000000027573 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391243_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056499 | 1020 | 2024-03-07 | 2 |  | 2025-02-07 | 4900230053_2025_0001 | 2025-03-01 | 144PT60 | 5000391243_2025_0001 | 0 | 2 | 0 | 90024949 | 2 | 0 | 180122911/180122912 | 2 | 0 | 0 | X | L | 4900230053 | 2025 |  | 5000391243 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9027003_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0020 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2 | EA | 24 | 5 | 12 | 2 | EA | 19.02 - At KGP | Supply for Order 100039671, Item 2 cannot be changed 9027004 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122915 | 9027004 | 05 | Preparation | 0000138175 | 2 | 0 | EA | 102000000027576 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391261_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056801 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900230024_2025_0001 | 2025-03-01 | 244PT60 | 5000391261_2025_0001 | 0 | 2 | 0 | 90024950 | 2 | 0 | 180122915 | 2 | 0 | 0 | X | L | 4900230024 | 2025 |  | 5000391261 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 9027004_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 | 30 | 30 | 5300002039 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0020 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2 | EA | 24 | 5 | 12 | 2 | EA | 19.02 - At KGP | Supply for Order 100039740, Item 2 cannot be changed 9027005 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122918 | 9027005 | 05 | Preparation | 0000138264 | 2 | 0 | EA | 102000000027575 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391242_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056802 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900230025_2025_0001 | 2025-03-01 | 344PT501 | 5000391242_2025_0001 | 0 | 2 | 0 | 90024951 | 2 | 0 | 180122920/180122918 | 2 | 0 | 0 | X | L | 4900230025 | 2025 |  | 5000391242 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9027005_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0010 | 0040 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2 | EA | 24 | 5 | 12 | 2 | EA | 19.02 - At KGP | Supply for Order 100039741, Item 2 cannot be changed 9027006 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122919 | 9027006 | 05 | Preparation | 0000138265 | 2 | 0 | EA | 102000000027574 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391209_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056803 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900230038_2025_0001 | 2025-03-01 | 344PT504 | 5000391209_2025_0001 | 0 | 2 | 0 | 90024952 | 2 | 0 | 180122919 | 2 | 0 | 0 | X | L | 4900230038 | 2025 |  | 5000391209 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Management of Change | 9027006_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 | 30 | 30 | 5300002054 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100085112 | 0020 | 0020 | 100085112 | MOC-150252: Flow TX's Repl (2) 44FT21L/H | AA53.44FT21L | TX,FLOW LP FUEL GAS TO HEADER | AA01 | 20 | No issue identified | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2 | EA | 24 | 5 | 12 | 2 | EA | 09.02 - SOH @ AA01 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021006 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030534 | 05 | Preparation | 0000267756 | 2 | 0 | EA | 102000000033138 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-08 | ODST-0090030534_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 44FT21L/H |  | 0 | 2 | 0 | 90030534 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030534_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000262795 | S002 | 30 | 30 | 5300021006 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267756 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Printed/Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-10-07 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-03 | VALVE | 100078477 | 0050 | 0010 | 100078477 | CV-OH 1" 600# 113LCV09 | AA53.113LCV09 | VALVE,1V1301 REGEN GAS WTR KO DRUM | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.10.2024) | 10021415 | MAINT KIT;FISHER RPACKX00012 | 1 | KIT | 3 | 0 | 1 | 1 | KIT | 08.10 - SOH at AA02 | Supply for Order 100078477, Item 3 cannot be changed 90025025 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016139 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025025 | 05 | Preparation | 0000241492 | 3 | 0 | KIT | 102000000027254 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-07 | ODST-0090025025_0010 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2024-10-16 | 0 |  | 2025-03-26 |  | 2025-03-31 |  |  | 0 | 2 | 0 | 90025025 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021415 | MAINT KIT;FISHER RPACKX00012 | 2024-10-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90025025_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000238214 | S002 |  | 30 | 5300016139 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-05-31 | 241492 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-06 | VALVE | 100079171 | 0010 | 0040 | 100079171 | CV-OH 1" 600# 124PCV52 | AA53.124PCV52 | VALVE,CTRL PRESS BUFF GAS 1K2420 | AA01 | 255 | No issue identified | 10021415 | MAINT KIT;FISHER RPACKX00012 | 1 | KIT | 3 | 0 | 1 | 1 | KIT | 20.02 - SOH at AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019182 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028295 | 05 | Preparation | 0000244737 | 6 | 0 | KIT | 101000000146580 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028295_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124PCV52 |  | 0 | 2 | 0 | 90028295 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021415 | MAINT KIT;FISHER RPACKX00012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  |  | 90028295_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 6 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241416 | S002 |  | 30 | 5300019182 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244737 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100079244 | 0010 | 0060 | 100079244 | CV-OH 1' 600# 124LCV23 | AA53.124LCV23 | VALVE,CTRL LEVEL S/O FILTER OUT 1K2420 | AA01 | 255 | No issue identified | 10021415 | MAINT KIT;FISHER RPACKX00012 | 1 | KIT | 3 | 0 | 1 | 1 | KIT | 25.02 - SOH @AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019183 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028296 | 05 | Preparation | 0000244777 | 7 | 0 | KIT | 101000000146581 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028296_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124LCV23 |  | 0 | 2 | 0 | 90028296 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021415 | MAINT KIT;FISHER RPACKX00012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  |  | 90028296_0030 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 7 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241462 | S002 |  | 30 | 5300019183 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244777 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-16 | VALVE | 100032676 | 0010 | 0130 | 100032676 | CV-OH 2" 300# 118PCV507 | AA53.118PCV507 | VALVE,1K1820E1 L/O PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.12.2024) | 10021416 | PACKING KIT,VV,CONTR;FISHER RPACKX00022 | 1 | KIT | 3 | 0 | 0 | 1 | KIT | 22.01 - ETA 10.02.25 PO W451767609 ex BH MOT tba IN TRANSIT | Supply for Order 100032676, Item 13 cannot be changed 90028292 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019177 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028292 | 05 | Preparation | 0000131168 | 13 | 0 | KIT | 102000000029846 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028292_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028292 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021416 | PACKING KIT,VV,CONTR;FISHER RPACKX00022 | 2024-12-15 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028292_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130518 | S002 |  | 30 | 5300019177 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131168 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | VALVE | 100032678 | 0010 | 0120 | 100032678 | CV-OH 1" 300# 118PDCV506 | AA53.118PDCV506 | VALVE,1K1820E1 S/OIL PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10021416 | PACKING KIT,VV,CONTR;FISHER RPACKX00022 | 1 | KIT | 3 | 0 | 0 | 1 | KIT | 22.01 - ETA 10.02.25 PO W451767609 ex BH MOT tba IN TRANSIT | Supply for Order 100032678, Item 15 cannot be changed 90028294 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019181 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028294 | 05 | Preparation | 0000131170 | 15 | 0 | KIT | 102000000029845 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028294_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028294 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021416 | PACKING KIT,VV,CONTR;FISHER RPACKX00022 | 2024-12-16 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028294_0030 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130520 | S002 |  | 30 | 5300019181 | 30 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-10-07 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-03-03 | VALVE | 100078477 | 0050 | 0020 | 100078477 | CV-OH 1" 600# 113LCV09 | AA53.113LCV09 | VALVE,1V1301 REGEN GAS WTR KO DRUM | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.10.2024) | 10021426 | GASKET SET,VV,CONTR;FISHER RGASKETX162 | 1 | KIT | 3 | 0 | 2 | 1 | KIT | 18.02 - SOH @ AA02 | Supply for Order 100078477, Item 4 cannot be changed 90025025 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016139 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025025 | 05 | Preparation | 0000241492 | 4 | 0 | KIT | 101000000143301 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-07 | ODST-0090025025_0020 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2024-10-16 | 0 |  | 2025-03-26 |  | 2025-03-31 |  |  | 0 | 2 | 0 | 90025025 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021426 | GASKET SET,VV,CONTR;FISHER RGASKETX162 | 2024-10-07 | W |  | 0050 | Overhaul Valve | ENON | Overhaul Valve |  |  | 90025025_0020 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000238214 | S002 |  | 30 | 5300016139 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-05-31 | 241492 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-06 | VALVE | 100079171 | 0010 | 0010 | 100079171 | CV-OH 1" 600# 124PCV52 | AA53.124PCV52 | VALVE,CTRL PRESS BUFF GAS 1K2420 | AA01 | 255 | No issue identified | 10021426 | GASKET SET,VV,CONTR;FISHER RGASKETX162 | 1 | KIT | 3 | 0 | 2 | 1 | KIT | 18.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019182 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028295 | 05 | Preparation | 0000244737 | 1 | 0 | KIT | 101000000143300 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028295_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124PCV52 |  | 0 | 2 | 0 | 90028295 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021426 | GASKET SET,VV,CONTR;FISHER RGASKETX162 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  |  | 90028295_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241416 | S002 |  | 30 | 5300019182 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244737 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100079244 | 0010 | 0010 | 100079244 | CV-OH 1' 600# 124LCV23 | AA53.124LCV23 | VALVE,CTRL LEVEL S/O FILTER OUT 1K2420 | AA01 | 255 | No issue identified | 10021426 | GASKET SET,VV,CONTR;FISHER RGASKETX162 | 1 | KIT | 3 | 0 | 2 | 1 | KIT | 25.02 - SOH @AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019183 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028296 | 05 | Preparation | 0000244777 | 1 | 0 | KIT | 101000000148136 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028296_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124LCV23 |  | 0 | 2 | 0 | 90028296 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021426 | GASKET SET,VV,CONTR;FISHER RGASKETX162 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  |  | 90028296_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241462 | S002 |  | 30 | 5300019183 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244777 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | VALVE | 100032678 | 0010 | 0080 | 100032678 | CV-OH 1" 300# 118PDCV506 | AA53.118PDCV506 | VALVE,1K1820E1 S/OIL PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10021813 | DIAPHRAGM,ACT;FARRIS 0F092802162 | 1 | EA | 0 | 0 | 0 | 0 |  | 30.12 - ETA 14.04.25 PO 4500039296 SCORE CPT | Supply for Order 100032678, Item 8 cannot be changed 90028294 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019181 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028294 | 05 | Preparation | 0000131170 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028294_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032678 |  | 0 | 2 | 0 | 90028294 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021813 | DIAPHRAGM,ACT;FARRIS 0F092802162 | 2024-12-16 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028294_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130520 | S002 |  | 30 | 5300019181 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-06 | VALVE | 100079171 | 0010 | 0030 | 100079171 | CV-OH 1" 600# 124PCV52 | AA53.124PCV52 | VALVE,CTRL PRESS BUFF GAS 1K2420 | AA01 | 255 | No Issue identified | 10021819 | DIAPHRAGM,ACT;NTRL,FISHER 2E670002202 | 1 | EA | 2 | 2 | 0 | 1 | EA | 17.12 - SOH @ AA02 |  |  | SP12 | Stock at Base | 0 | AA02 | 5300019182 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124189 | 9027116 | 05 | Preparation | 0000244737 | 3 | 0 | EA | 102000000032143 | 102000000029951 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-12-16 | IDST-0180124189 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2026-06-04 | 1 |  | 2025-02-11 | 4900234069_2025_0001 | 2025-03-01 | 124PCV52 |  | 0 | 2 | 0 | 90028295 | 0 | 0 | 180124189 | 3 | 0 | 0 |  | L | 4900234069 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021819 | DIAPHRAGM,ACT;NTRL,FISHER 2E670002202 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  |  | 9027116_0020 |  |  | DG1 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241416 | S002 |  | 30 | 5300019182 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244737 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100079244 | 0010 | 0030 | 100079244 | CV-OH 1' 600# 124LCV23 | AA53.124LCV23 | VALVE,CTRL LEVEL S/O FILTER OUT 1K2420 | AA01 | 255 | No Issue identified | 10021819 | DIAPHRAGM,ACT;NTRL,FISHER 2E670002202 | 1 | EA | 2 | 2 | 0 | 1 | EA | 17.12 - SOH @ AA02 |  |  | SP12 | Stock at Base | 0 | AA02 | 5300019183 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027123 | 05 | Preparation | 0000244777 | 3 | 0 | EA | 102000000032151 | 102000000029952 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-12-16 | GIST-4900234141_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2026-06-04 | 1 |  | 2025-02-11 | 4900234141_2025_0001 | 2025-03-01 | 124LCV23 |  | 0 | 2 | 0 | 90028296 | 0 | 0 |  | 3 | 0 | 0 |  | L | 4900234141 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021819 | DIAPHRAGM,ACT;NTRL,FISHER 2E670002202 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  |  | 9027123_0020 |  |  | DG1 |  | A3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241462 | S002 |  | 30 | 5300019183 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244777 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | VALVE | 100032675 | 0010 | 0030 | 100032675 | CV-OH 1" 300# 118PCV505 | AA53.118PCV505 | VALVE,1K1820 BUFFER GAS SUPPL PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.12.2024) | 10021823 | DIAPHRAGM,ACT;FISHER 2E800002202 | 1 | EA | 3 | 0 | 0 | 1 | EA | 15.01 - 2 SOH @ AA02, WO @ Created stage | Supply for Order 100032675, Item 3 cannot be changed 90028291 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019175 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028291 | 05 | Preparation | 0000131167 | 3 | 0 | EA | 102000000032115 | 102000000029849 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028291_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118PCV505 |  | 0 | 2 | 0 | 90028291 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021823 | DIAPHRAGM,ACT;FISHER 2E800002202 | 2024-12-15 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028291_0010 |  |  | FR1 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130517 | S002 |  | 30 | 5300019175 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131167 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | VALVE | 100032671 | 0010 | 0020 | 100032671 | CV-OH 1" 300# 118TCV503 | AA53.118TCV503 | VALVE,K1820E1 S/OIL COOLER BYPASS TEMP | AA01 | 20 | No issue identified | 10021829 | DIAPHRAGM,ACT;FARRIS 39A4774X012 | 1 | EA | 3 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019089 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028287 | 05 | Preparation | 0000131163 | 2 | 0 | EA | 102000000033355 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-12 | ODST-0090028287_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032671 |  | 0 | 2 | 0 | 90028287 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021829 | DIAPHRAGM,ACT;FARRIS 39A4774X012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028287_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130513 | S002 |  | 30 | 5300019089 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131163 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-05-15 | VALVE | 100032672 | 0010 | 0020 | 100032672 | CV-OH 1" 300# 118LCV505 | AA53.118LCV505 | VALVE,S/OIL O/H TK 1K1820V1 LVL CTRL | AA01 | 20 | No Issue identified | 10021829 | DIAPHRAGM,ACT;FARRIS 39A4774X012 | 1 | EA | 3 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019173 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028288 | 05 | Preparation | 0000131164 | 2 | 0 | EA | 101000000148272 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028288_0020 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2025-06-02 | 0 |  | 2025-03-26 |  | 2025-03-31 | 118LCV505 |  | 0 | 2 | 0 | 90028288 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021829 | DIAPHRAGM,ACT;FARRIS 39A4774X012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028288_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130514 | S002 |  | 30 | 5300019173 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131164 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | VALVE | 100032674 | 0010 | 0020 | 100032674 | CV-OH 1" 300# 118LCV510 | AA53.118LCV510 | VALVE,S/OIL DRN POT K1820V4B LOCAL LVL | AA01 | 20 | No issue identified | 10021829 | DIAPHRAGM,ACT;FARRIS 39A4774X012 | 1 | EA | 3 | 0 | 0 | 1 | EA | 25.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019174 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028290 | 05 | Preparation | 0000131166 | 2 | 0 | EA | 102000000033353 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028290_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032674 |  | 0 | 2 | 0 | 90028290 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021829 | DIAPHRAGM,ACT;FARRIS 39A4774X012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028290_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130516 | S002 |  | 30 | 5300019174 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131166 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100032677 | 0010 | 0010 | 100032677 | CV-OH 3" 300# 118TCV501 | AA53.118TCV501 | VALVE,1K1820E1 L/O COOL BYPASS TEMP CTRL | AA01 | 20 | No issue identified | 10021830 | DIAPHRAGM,ACT;FARRIS 39A4813X012 | 1 | EA | 2 | 0 | 0 | 1 | EA | 15.01 - 2 SOH @ AA02. |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019178 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028293 | 05 | Preparation | 0000131169 | 1 | 0 | EA | 102000000029950 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028293_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032677 |  | 0 | 2 | 0 | 90028293 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021830 | DIAPHRAGM,ACT;FARRIS 39A4813X012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028293_0010 |  |  | FR1 |  | C2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130519 | S002 | 30 | 30 | 5300019178 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131169 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | VALVE | 100032675 | 0010 | 0040 | 100032675 | CV-OH 1" 300# 118PCV505 | AA53.118PCV505 | VALVE,1K1820 BUFFER GAS SUPPL PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.12.2024) | 10021847 | MAINT KIT;FISHER R667X000302 | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 15.01 - 1 SOH @ AA02, WO @ Created stage | Supply for Order 100032675, Item 4 cannot be changed 90028291 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019175 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028291 | 05 | Preparation | 0000131167 | 4 | 0 | KIT | 102000000032115 | 102000000029813 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028291_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118PCV505 |  | 0 | 2 | 0 | 90028291 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021847 | MAINT KIT;FISHER R667X000302 | 2024-12-15 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028291_0020 |  |  | FR1 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130517 | S002 |  | 30 | 5300019175 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131167 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | VALVE | 100032671 | 0010 | 0030 | 100032671 | CV-OH 1" 300# 118TCV503 | AA53.118TCV503 | VALVE,K1820E1 S/OIL COOLER BYPASS TEMP | AA01 | 20 | No issue identified | 10021867 | O-RING;BS218,NTRL,FARRIS 1E264306992 | 1 | EA | 3 | 0 | 1 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019089 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028287 | 05 | Preparation | 0000131163 | 5 | 0 | EA | 102000000033927 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-12 | ODST-0090028287_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028287 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021867 | O-RING;BS218,NTRL,FARRIS 1E264306992 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028287_0030 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130513 | S002 |  | 30 | 5300019089 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131163 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | VALVE | 100032672 | 0010 | 0040 | 100032672 | CV-OH 1" 300# 118LCV505 | AA53.118LCV505 | VALVE,S/OIL O/H TK 1K1820V1 LVL CTRL | AA01 | 20 | No issue identified | 10021867 | O-RING;BS218,NTRL,FARRIS 1E264306992 | 1 | EA | 3 | 0 | 1 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019173 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028289 | 05 | Preparation | 0000131164 | 8 | 0 | EA | 102000000033931 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028289_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028289 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021867 | O-RING;BS218,NTRL,FARRIS 1E264306992 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028289_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130514 | S002 |  | 30 | 5300019173 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131164 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | VALVE | 100032674 | 0010 | 0030 | 100032674 | CV-OH 1" 300# 118LCV510 | AA53.118LCV510 | VALVE,S/OIL DRN POT K1820V4B LOCAL LVL | AA01 | 20 | No issue identified | 10021867 | O-RING;BS218,NTRL,FARRIS 1E264306992 | 1 | EA | 3 | 0 | 1 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019174 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028290 | 05 | Preparation | 0000131166 | 7 | 0 | EA | 102000000033929 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028290_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028290 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021867 | O-RING;BS218,NTRL,FARRIS 1E264306992 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028290_0030 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130516 | S002 |  | 30 | 5300019174 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131166 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-05-28 | 2025-03-01 | 2024-06-14 | 2025-03-01 | 2025-03-01 | VALVE | 100047394 | 0030 | 0070 | 100047394 | CV-OH 1" 600# 124PCV54 | AA53.124PCV54 | VALVE,CONT SEAL OIL BACK PRESS 1K2420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.06.2024) | 10021867 | O-RING;BS218,NTRL,FARRIS 1E264306992 | 1 | EA | 3 | 0 | 1 | 1 | EA | 16.12 - Materials consumed | Supply for Order 100047394, Item 5 cannot be changed 180089157 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300011592 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180089157 | 90013066 | 07 | Execution | 0000145926 | 5 | 0 | EA | 102000000022469 |  | 107000000000391 |  |  |  | P07 - BENCH | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-06-14 | GRST-5000266704_2024 | 0 | 0 | 0 | 0 |  | 2024-05-21 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000038577 | 1020 | 2018-10-31 | 1 |  | 2024-11-04 | 4900164057_2024_0001 | 2024-06-17 |  | 5000266704_2024_0001 | 0 | 2 | 0 | 90013066 | 1 | 0 | 180089157 | 2 | 0 | 0 | X | L | 4900164057 | 2024 |  | 5000266704 | 2024 | 0 |  | 2024-06-14 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021867 | O-RING;BS218,NTRL,FARRIS 1E264306992 | 2024-06-14 | W |  | 0030 | Remove Valve 124PCV54 & Fit Blinds | INT | Remove Valve 124PCV54 & Fit Blinds | 5 |  | 90013066_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000145296 | S002 |  | 30 | 5300011592 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-06-14 |  |  |  |  | 1070 |  | 2024-05-23 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145926 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100032677 | 0010 | 0020 | 100032677 | CV-OH 3" 300# 118TCV501 | AA53.118TCV501 | VALVE,1K1820E1 L/O COOL BYPASS TEMP CTRL | AA01 | 20 | No issue identified | 10021868 | O-RING;FARRIS 15A8505X032 | 1 | EA | 1 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019178 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028293 | 05 | Preparation | 0000131169 | 2 | 0 | EA | 102000000033354 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028293_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032677 |  | 0 | 2 | 0 | 90028293 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021868 | O-RING;FARRIS 15A8505X032 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028293_0020 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130519 | S002 |  | 30 | 5300019178 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131169 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100032677 | 0010 | 0030 | 100032677 | CV-OH 3" 300# 118TCV501 | AA53.118TCV501 | VALVE,1K1820E1 L/O COOL BYPASS TEMP CTRL | AA01 | 20 | No issue identified | 10021869 | O-RING;FARRIS 1J108506992 | 1 | EA | 1 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019178 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028293 | 05 | Preparation | 0000131169 | 3 | 0 | EA | 102000000033350 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028293_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032677 |  | 0 | 2 | 0 | 90028293 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021869 | O-RING;FARRIS 1J108506992 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028293_0030 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130519 | S002 |  | 30 | 5300019178 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131169 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2220 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10023047 | DIAPHRAGM,MASONEILAN 4" 525 CONTR VV | 1 | EA | 5 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 327 cannot be changed 90028419 item 2540 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2570 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 327 | 0 | EA | 102000000030482 | 102000000030108 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2540 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10023047 | DIAPHRAGM,MASONEILAN 4" 525 CONTR VV | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2540 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 327 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2570 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0010 | 0010 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10023996 | LINER;CAP,H/WHEEL,VALTEK 001885.676.000 | 1 | EA | 2 | 0 | 0 | 1 | EA | 09.02 - SOH @ AA02 | Supply for Order 100085072, Item 1 cannot be changed 90028434 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028434 | 05 | Preparation | 0000267773 | 1 | 0 | EA | 101000000143781 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-08 | ODST-0090028434_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028434 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10023996 | LINER;CAP,H/WHEEL,VALTEK 001885.676.000 | 2025-01-08 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  | Management of Change/Order Requires Replanning | 90028434_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 |  | 30 | 5300019757 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100085092 | 0010 | 0010 | 100085092 | ACT-IS 123FCV03 | AA53.123FCV03 | VALVE,CTRL FLOW REGEN GAS TO 1E2302 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(14.11.2024) | 10023996 | LINER;CAP,H/WHEEL,VALTEK 001885.676.000 | 1 | EA | 2 | 0 | 0 | 1 | EA | 09.02 - SOH @ AA02 | Supply for Order 100085092, Item 1 cannot be changed 90025111 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017886 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025111 | 05 | Preparation | 0000267720 | 1 | 0 | EA | 102000000032998 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025111_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-24 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025111 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10023996 | LINER;CAP,H/WHEEL,VALTEK 001885.676.000 | 2024-11-14 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  |  | 90025111_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000262780 | S002 |  | 30 | 5300017886 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267720 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-05 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200144588 | 0010 | 0010 | 200144588 | 2Y CO2 F/Test (82) 1KT1410 | AA53.160GA512A | TXDCR,1KT1410 CO2 CYL WEIGHT LOW | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(04.11.2024) | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 4 | EA | 83 | 0 | 3 | 4 | EA | 07.11 - SOH @ AA02 | Supply for Order 200144588, Item 1 cannot be changed 90025095 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017345 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025095 | 05 | Preparation | 0000231713 | 1 | 0 | EA | 102000000027427 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-05 | ODST-0090025095_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90025095 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 2024-11-04 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90025095_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228840 | S002 | 30 | 30 | 5300017345 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231713 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200144590 | 0010 | 0010 | 200144590 | 2Y CO2 F/Test (92) - 1KT1420 | AA53.160GA542A | TXDCR,1KT1420 CO2 CYL WEIGHT LOW | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 4 | EA | 83 | 0 | 3 | 4 | EA | 18.11 - SOH @ AA02 | Supply for Order 200144590, Item 1 cannot be changed 90025110 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017866 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025110 | 05 | Preparation | 0000231715 | 1 | 0 | EA | 102000000027428 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025110_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1420 |  | 0 | 2 | 0 | 90025110 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 2024-11-13 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90025110_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228862 | S002 | 30 | 30 | 5300017866 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231715 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 200144594 | 0010 | 0010 | 200144594 | 2Y F19 CO2 F/Test (82) 1KT1440 | AA53.160GA602A | TXDCR,1KT1440 CO2 CYL WEIGHT LOW | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 3 | EA | 83 | 0 | 3 | 3 | EA | 17.10 - SOH @ AA02 | Supply for Order 200144594, Item 1 cannot be changed 90025030 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016437 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025030 | 05 | Preparation | 0000231719 | 1 | 0 | EA | 102000000027425 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025030_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1440 CO2 |  | 0 | 2 | 0 | 90025030 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 2024-10-16 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90025030_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228866 | S002 | 30 | 30 | 5300016437 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231719 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 200144596 | 0010 | 0010 | 200144596 | 2Y F19 CO2 FUNCTION CHECK(132) 1KT1450 | AA53.160GA632A | TXDCR,1KT1450 CO2 MAIN CYL WEIGHT LOW | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 3 | EA | 83 | 0 | 3 | 3 | EA | 17.10 - SOH @ AA02 | Supply for Order 200144596, Item 1 cannot be changed 90025031 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016438 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025031 | 05 | Preparation | 0000231721 | 1 | 0 | EA | 102000000027426 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025031_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1450 CO2 |  | 0 | 2 | 0 | 90025031 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 2024-10-16 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90025031_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000228868 | S002 | 30 | 30 | 5300016438 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231721 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147173 | 0010 | 0020 | 200147173 | 1Y CO2 Function Test (105) 1KT2430 | AA53.160GA1312A | TXDCR,1KT2430 CO2 CYL WEIGHT LOW | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.11.2024) | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 3 | EA | 83 | 0 | 3 | 3 | EA | 12.11 - SOH @ AA02 | Supply for Order 200147173, Item 3 cannot be changed 90025101 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017681 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025101 | 05 | Preparation | 0000235474 | 3 | 0 | EA | 102000000027429 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-11 | ODST-0090025101_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT2430 |  | 0 | 2 | 0 | 90025101 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 2024-11-10 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 3 |  | 90025101_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232528 | S002 | 30 | 30 | 5300017681 | 20 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 235474 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SD4401 | Released | 2024-11-05 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0060 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 19.02 - At KGP | Supply for Order 100039665, Item 18 cannot be changed 90023592 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180122922 | 9027007 | 05 | Preparation | 0000138169 | 18 | 0 | KIT | 102000000025832 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000391237_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056804 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900229998_2025_0005 | 2024-12-01 | 144PT504 | 5000391237_2025_0003 | 0 | 2 | 0 | 90023592 | 1 | 0 | 180122922/180122921 | 2 | 0 | 0 | X | L | 4900229998 | 2025 |  | 5000391237 | 2025 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-11-05 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9027007_0050 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 18 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 | 30 | 30 | 5300017367 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0070 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 19.02 - At KGP | Supply for Order 100039666, Item 6 cannot be changed 90024949 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180122883 | 9026893 | 05 | Preparation | 0000138170 | 6 | 0 | KIT | 102000000028602 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391260_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056487 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230018_2025_0001 | 2025-03-01 | 144PT60 | 5000391260_2025_0001 | 0 | 2 | 0 | 90024949 | 1 | 0 | 180122911/180122883 | 2 | 0 | 0 | X | L | 4900230018 | 2025 |  | 5000391260 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026893_0050 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 6 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-04 | 2025-03-08 | INLEC | 100039667 | 0010 | 0090 | 100039667 | MOC-141259 TX Replace 144PT059 | AA53.144PT059 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 18.12 - qty 6 SOH at AA02 At QA HOLD | Supply for Order 100039667, Item 9 cannot be changed 90023934 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017556 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90023934 | 05 | Preparation | 0000138171 | 9 | 0 | KIT | 101000000142890 |  | 102000000034357 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-07 | ODST-0090023934_0030 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-04 |  |  | 2024-12-01 |  |  |  |  | 2024-03-07 | 0 |  | 2024-11-26 |  | 2024-12-01 | 144PT059 |  | 0 | 2 | 0 | 90023934 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 90023934_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 9 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137582 | S002 | 30 | 30 | 5300017556 | 30 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138171 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-08 | 2025-03-04 | 2025-03-04 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-21 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-03 | INLEC | 100039668 | 0030 | 0040 | 100039668 | MOC-141262 Transmitter Replace 244PT58 | AA53.244PT58 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 19.02 - At KGP | Supply for Order 100039668, Item 4 cannot be changed 90025183 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300018207 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180122904 | 9027002 | 05 | Preparation | 0000138172 | 4 | 0 | KIT | 102000000025833 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-21 | GRST-5000391251_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056496 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230023_2025_0005 | 2024-12-01 | 244PT58 | 5000391251_2025_0003 | 0 | 2 | 0 | 90025183 | 1 | 0 | 180122904/180122906 | 2 | 0 | 0 | X | L | 4900230023 | 2025 |  | 5000391251 | 2025 | 0 |  | 2024-11-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-11-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9027002_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137583 | S002 | 30 | 30 | 5300018207 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138172 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-21 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-04 | INLEC | 100039669 | 0030 | 0040 | 100039669 | MOC-146093 Pressure TX Replace 244PT501 | AA53.244PT501 | TX,PRESS K4401B-P2A/P2B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 19.02 - At KGP | Supply for Order 100039669, Item 4 cannot be changed 90025184 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300018206 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180122902 | 9027001 | 05 | Preparation | 0000138173 | 4 | 0 | KIT | 102000000028942 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-21 | GRST-5000391236_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056495 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230051_2025_0001 | 2024-12-01 | 244PT501 | 5000391236_2025_0001 | 0 | 2 | 0 | 90025184 | 1 | 0 | 180122902/180122901 | 2 | 0 | 0 | X | L | 4900230051 | 2025 |  | 5000391236 | 2025 | 0 |  | 2024-11-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-11-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9027001_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137584 | S002 | 30 | 30 | 5300018206 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138173 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0060 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 19.02 - At KGP | Supply for Order 100039671, Item 6 cannot be changed 9026894 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180122884 | 9026894 | 05 | Preparation | 0000138175 | 6 | 0 | KIT | 102000000029828 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391239_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056488 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230007_2025_0007 | 2025-03-01 | 244PT60 | 5000391239_2025_0004 | 0 | 2 | 0 | 90024950 | 1 | 0 | 180122884 | 2 | 0 | 0 | X | L | 4900230007 | 2025 |  | 5000391239 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 9026894_0050 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 6 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 | 30 | 30 | 5300002039 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0060 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 19.02 - At KGP | Supply for Order 100039740, Item 6 cannot be changed 9026895 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180122885 | 9026895 | 05 | Preparation | 0000138264 | 6 | 0 | KIT | 102000000029827 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391238_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056489 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900229989_2025_0005 | 2025-03-01 | 344PT501 | 5000391238_2025_0003 | 0 | 2 | 0 | 90024951 | 1 | 0 | 180122920/180122885 | 2 | 0 | 0 | X | L | 4900229989 | 2025 |  | 5000391238 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026895_0050 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 6 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0010 | 0090 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 19.02 - At KGP | Supply for Order 100039741, Item 6 cannot be changed 9026899 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180122896 | 9026899 | 05 | Preparation | 0000138265 | 6 | 0 | KIT | 101000000122744 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391272_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056493 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900229979_2025_0003 | 2025-03-01 | 344PT504 | 5000391272_2025_0002 | 0 | 2 | 0 | 90024952 | 1 | 0 | 180122896 | 2 | 0 | 0 | X | L | 4900229979 | 2025 |  | 5000391272 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Management of Change | 9026899_0050 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 6 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 | 30 | 30 | 5300002054 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-03-01 | 2024-05-24 | 2025-05-08 | 2025-05-08 | INLEC | 100044402 | 0020 | 0020 | 100044402 | LOC Needle Valve Replace (2) 414PDT022 | AA53.414PDT022A | TX,DIFF PRESS COMP SURGE CNT 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2 | KIT | 4 | 3 | 13 | 2 | KIT | 25.09 - At KGP | Supply for Order 100044402, Item 2 cannot be changed 180029516 item 20 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002364 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180029516 | 90006485 | 06 | Scheduling | 0000142926 | 2 | 0 | KIT | 102000000004049 | 102000000003545 | 102000000007342 |  |  |  |  | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000122800 | 0 | 0 | 0 | 0 |  | 2024-05-25 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  | 100000013638 | 1020 | 2020-09-04 | 2 |  | 2024-06-19 | 4900076349_2024_0003/4900076188_2024_0003/4900066697_2024_0003 | 2024-05-27 | 414PDT022A | 5000122800_2024_0002 | 0 | 2 | 0 | 90006485 | 2 | 0 | 180029516 | 2 | 0 | 0 | X | L | 4900076349 | 2024 |  | 5000122800 | 2024 | 0 |  | 2024-05-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-01-02 | W |  | 0020 | Complete Replacement Needle Valves | INT | Complete Replacement Needle Valves | 2 |  | 90006485_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000142277 | S002 | 30 | 30 | 5300002364 | 20 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2024-05-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142926 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-01 | INLEC | 100047874 | 0010 | 0050 | 100047874 | MOC-124841 Transmitter Replace 114PT87 | AA53.114PIC87 | LOOP,CTRL PRESS TO E1409 SHELL OUTLET | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 4 | 3 | 13 | 1 | KIT | 18.12 - qty 6 SOH at AA02 At QA HOLD | Supply for Order 100047874, Item 5 cannot be changed 90023935 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017557 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90023935 | 05 | Preparation | 0000146415 | 5 | 0 | KIT | 101000000142889 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-07 | ODST-0090023935_0050 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  |  |  | 2022-11-30 | 0 |  | 2024-11-26 |  | 2024-12-01 | 114PT87 |  | 0 | 2 | 0 | 90023935 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works | 5 |  | 90023935_0050 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000145844 | S002 | 30 | 30 | 5300017557 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146415 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-05 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0050 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10025304 | MTG KIT;4X37MM,4X44MM BOLT,SS316 | 1 | SET | 10 | 3 | 5 | 1 | SET | 19.02 - At KGP | Supply for Order 100039665, Item 17 cannot be changed 90023592 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180122922 | 9027007 | 05 | Preparation | 0000138169 | 17 | 0 | SET | 102000000025799 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000391237_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056804 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900229998_2025_0003 | 2024-12-01 | 144PT504 | 5000391237_2025_0002 | 0 | 2 | 0 | 90023592 | 1 | 0 | 180122922/180122921 | 2 | 0 | 0 | X | L | 4900229998 | 2025 |  | 5000391237 | 2025 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025304 | MTG KIT;4X37MM,4X44MM BOLT,SS316 | 2024-11-05 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9027007_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 17 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 |  | 30 | 5300017367 | 40 |  |  | 0 | 1 | SET | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-04 | 2025-03-08 | INLEC | 100039667 | 0010 | 0080 | 100039667 | MOC-141259 TX Replace 144PT059 | AA53.144PT059 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10025304 | MTG KIT;4X37MM,4X44MM BOLT,SS316 | 1 | SET | 10 | 3 | 5 | 1 | SET | 19.02 - At KGP | Supply for Order 100039667, Item 8 cannot be changed 90023934 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017556 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180122923 | 9027008 | 05 | Preparation | 0000138171 | 8 | 0 | SET | 102000000025797 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000391252_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-04 |  |  | 2024-12-01 |  |  | 100000056805 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230046_2025_0001 | 2024-12-01 | 144PT059 | 5000391252_2025_0001 | 0 | 2 | 0 | 90023934 | 1 | 0 | 180122923 | 2 | 0 | 0 | X | L | 4900230046 | 2025 |  | 5000391252 | 2025 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025304 | MTG KIT;4X37MM,4X44MM BOLT,SS316 | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9027008_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 8 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137582 | S002 |  | 30 | 5300017556 | 20 |  |  | 0 | 1 | SET | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138171 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-08 | 2025-03-04 | 2025-03-04 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-01 | INLEC | 100047874 | 0010 | 0040 | 100047874 | MOC-124841 Transmitter Replace 114PT87 | AA53.114PIC87 | LOOP,CTRL PRESS TO E1409 SHELL OUTLET | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10025304 | MTG KIT;4X37MM,4X44MM BOLT,SS316 | 1 | SET | 10 | 3 | 5 | 1 | SET | 19.02 - At KGP | Supply for Order 100047874, Item 4 cannot be changed 90023935 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017557 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  | 180122924 | 9027009 | 05 | Preparation | 0000146415 | 4 | 0 | SET | 102000000025798 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000391235_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056806 | 1020 | 2022-11-30 | 1 |  | 2025-02-07 | 4900230055_2025_0001 | 2024-12-01 | 114PT87 | 5000391235_2025_0001 | 0 | 2 | 0 | 90023935 | 1 | 0 | 180122924 | 2 | 0 | 0 | X | L | 4900230055 | 2025 |  | 5000391235 | 2025 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025304 | MTG KIT;4X37MM,4X44MM BOLT,SS316 | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works | 5 |  | 9027009_0040 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000145844 | S002 |  | 30 | 5300017557 | 40 |  |  | 0 | 1 | SET | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146415 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-03-26 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 100039780 | 0020 | 0020 | 100039780 | 160PG563 - PASSING PRESSURE GAUGE | AA53.160PG563 | GAUGE,PRESS 1KT1430 N2 TO SOL VLVS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10025641 | GAUGE,PRESS;0 TO 4000 KPA,100MM | 1 | EA | 2 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 100039780, Item 2 cannot be changed 90024975 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300008406 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024975 | 06 | Scheduling | 0000138214 | 2 | 0 | EA | 102000000032018 | 102000000027491 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-26 | ODST-0090024975_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-01-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 160PG563 |  | 0 | 2 | 0 | 90024975 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025641 | GAUGE,PRESS;0 TO 4000 KPA,100MM | 2024-10-16 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 2 |  | 90024975_0010 |  |  | LN1 |  | A5 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000137636 | S002 |  | 30 | 5300008406 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138214 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-03-26 | 2024-06-03 | 2024-06-07 | 2025-03-01 | 2025-05-31 | INLEC | 100039780 | 0020 | 0010 | 100039780 | 160PG563 - PASSING PRESSURE GAUGE | AA53.160PG563 | GAUGE,PRESS 1KT1430 N2 TO SOL VLVS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(26.03.2024) | 10025641 | GAUGE,PRESS;0 TO 4000 KPA,100MM | 1 | EA | 2 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 100039780, Item 1 cannot be changed 180029544 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300008406 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180029544 | 90006978 | 06 | Scheduling | 0000138214 | 1 | 0 | EA | 102000000006224 | 102000000003957 | 102000000007333 |  |  |  | LP-NWS-01 | WorkPackLink | P08YRDBAY6 | AU01-P08-LN | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-03-26 |  | 0 | 7 | 0 | 0 |  | 2024-06-08 | AA53 | 2025-03-01 |  |  | 2024-06-10 |  |  | 100000013638 | 1020 | 2023-01-01 | 1 |  | 2024-06-19 | 4900076355_2024_0001/4900076137_2024_0001/4900066721_2024_0001 | 2024-06-10 | 160PG563 | 5000122726_2024_0001 | 0 | 2 | 0 | 90006978 | 1 | 0 | 180029544 | 2 | 0 | 0 | X | L | 4900076355 | 2024 |  | 5000122726 | 2024 | 0 |  | 2024-06-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025641 | GAUGE,PRESS;0 TO 4000 KPA,100MM | 2024-03-26 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 2 |  | 90006978_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000137636 | S002 |  | 30 | 5300008406 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-06-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138214 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0040 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.02.2025) | 10025680 | GAUGE,PRESS;0.5",1000BAR,WIKA 68160364 | 2 | EA | 3 | 0 | 0 | 2 | EA | 02.03 - SOH @ AA02 | Supply for Order 600001363, Item 11 cannot be changed 90031986 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031986 | 05 | Preparation | 0000084301 | 11 | 0 | EA | 102000000034491 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-27 | ODST-0090031986_0010 | 0 | 6 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-27 |  |  | 2025-03-05 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-28 |  | 2025-03-05 | Scott Kinloc |  | 0 | 2 | 0 | 90031986 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025680 | GAUGE,PRESS;0.5",1000BAR,WIKA 68160364 | 2025-02-28 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90031986_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 | 30 | 30 | 5300018438 | 60 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-28 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-06 | ROTAT | 200091503 | 0070 | 0020 | 200091503 | 8Y Compressor BSR Labour - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10025686 | GAUGE,PRESS;0-400KPA,130MM,0.5",AS1349 | 1 | EA | 5 | 0 | 1 | 1 | EA | 22.11 - SOH @ AA02 | Supply for Order 200091503, Item 2 cannot be changed 90028279 item 20 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018198 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028279 | 05 | Preparation | 0000129752 | 2 | 0 | EA | 102000000029809 |  | 102000000032112 |  |  |  |  | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-21 | ODST-0090028279_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-06-23 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118PG521 |  | 0 | 2 | 0 | 90028279 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025686 | GAUGE,PRESS;0-400KPA,130MM,0.5",AS1349 | 2024-11-21 | W |  | 0070 | REMOVE INSTRUMENTATION | INT | REMOVE INSTRUMENTATION | 5 |  | 90028279_0020 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129162 | S002 |  | 30 | 5300018198 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129752 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-06 | ROTAT | 200091503 | 0070 | 0010 | 200091503 | 8Y Compressor BSR Labour - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10025692 | GAUGE,PRESS;0.5",2500KPA,WIKA 68172943 | 1 | EA | 6 | 0 | 3 | 0 |  | 22.11 - SOH @ AA02 | Supply for Order 200091503, Item 1 cannot be changed 90028279 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018198 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028279 | 05 | Preparation | 0000129752 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-21 | ODST-0090028279_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-06-23 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118PG512 |  | 0 | 2 | 0 | 90028279 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025692 | GAUGE,PRESS;0.5",2500KPA,WIKA 68172943 | 2024-11-21 | W |  | 0070 | REMOVE INSTRUMENTATION | INT | REMOVE INSTRUMENTATION | 5 |  | 90028279_0010 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129162 | S002 | 30 | 30 | 5300018198 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129752 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-10-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | VALVE | 100045269 | 0010 | 0010 | 100045269 | Replace Pressure Gauge - 118PG11 | AA53.118PG11 | GAUGE,PRESS E1801 DE-ETH REBOILER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(22.10.2024) | 10025695 | GAUGE,PRESS;6000 KPA,130MM,0>WSE10605804 | 1 | EA | 5 | 0 | 0 | 1 | EA | 23.10 - SOH @ AA02 | Supply for Order 100045269, Item 1 cannot be changed 90025071 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016694 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025071 | 05 | Preparation | 0000143781 | 1 | 0 | EA | 102000000025802 |  | 102000000034359 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-22 | ODST-0090025071_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-04-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118PG11 |  | 0 | 2 | 0 | 90025071 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025695 | GAUGE,PRESS;6000 KPA,130MM,0>WSE10605804 | 2024-10-22 | W |  | 0010 | Replace Pressure Gauge - 118PG11 | INT | Replace Pressure Gauge - 118PG11 | 2 |  | 90025071_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000143151 | S002 |  | 30 | 5300016694 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143781 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-05 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0100 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 19.02 - At KGP | Supply for Order 100039665, Item 22 cannot be changed 90027934 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122907 | 90027934 | 05 | Preparation | 0000138169 | 22 | 0 | EA | 102000000029018 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000391250_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056498 | 1020 | 2024-03-07 | 1 |  | 2025-02-07 | 4900230036_2025_0001 | 2025-03-01 | 144PT504 | 5000391250_2025_0001 | 0 | 2 | 0 | 90027934 | 1 | 0 | 180122907 | 2 | 0 | 0 | X | L | 4900230036 | 2025 |  | 5000391250 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-12-13 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 90027934_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 22 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 | 30 | 30 | 5300017367 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-05 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0010 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 29.01 - At KGP | Supply for Order 100039665, Item 13 cannot be changed 180100942 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100942 | 9021448 | 05 | Preparation | 0000138169 | 13 | 0 | EA | 102000000025714 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000305864_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000044757 | 1020 | 2024-03-07 | 1 |  | 2024-12-04 | 4900184985_2024_0001 | 2024-12-01 | 144PT504 | 5000305864_2024_0001 | 0 | 2 | 0 | 90023592 | 1 | 0 | 180100942/180122921 | 2 | 0 | 0 | X | L | 4900184985 | 2024 |  | 5000305864 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-11-05 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9021448_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 13 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 | 30 | 30 | 5300017367 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-04 | 2025-03-08 | INLEC | 100039667 | 0010 | 0020 | 100039667 | MOC-141259 TX Replace 144PT059 | AA53.144PT059 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 29.01 - At KGP | Supply for Order 100039667, Item 2 cannot be changed 180100943 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300017556 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100943 | 9021449 | 05 | Preparation | 0000138171 | 2 | 0 | EA | 102000000025676 |  | 107000000000399 |  |  |  |  | WorkPackLink | INLEC-CAGE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000305871_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-04 |  |  | 2024-12-01 |  |  | 100000044758 | 1020 | 2024-03-07 | 1 |  | 2024-12-04 | 4900185005_2024_0001 | 2024-12-01 | 144PT059 | 5000305871_2024_0001 | 0 | 2 | 0 | 90023934 | 1 | 0 | 180100943 | 2 | 0 | 0 | X | L | 4900185005 | 2024 |  | 5000305871 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9021449_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137582 | S002 | 30 | 30 | 5300017556 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138171 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-08 | 2025-03-04 | 2025-03-04 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-21 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-03 | INLEC | 100039668 | 0030 | 0030 | 100039668 | MOC-141262 Transmitter Replace 244PT58 | AA53.244PT58 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 19.02 - At KGP | Supply for Order 100039668, Item 3 cannot be changed 90025183 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300018207 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122904 | 9027002 | 05 | Preparation | 0000138172 | 3 | 0 | EA | 102000000025835 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-21 | GRST-5000391251_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056496 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230023_2025_0003 | 2024-12-01 | 244PT58 | 5000391251_2025_0002 | 0 | 2 | 0 | 90025183 | 1 | 0 | 180122904/180122906 | 2 | 0 | 0 | X | L | 4900230023 | 2025 |  | 5000391251 | 2025 | 0 |  | 2024-11-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-11-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9027002_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137583 | S002 | 30 | 30 | 5300018207 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138172 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-11-21 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-04 | INLEC | 100039669 | 0030 | 0030 | 100039669 | MOC-146093 Pressure TX Replace 244PT501 | AA53.244PT501 | TX,PRESS K4401B-P2A/P2B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.11.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 19.02 - At KGP | Supply for Order 100039669, Item 3 cannot be changed 90025184 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300018206 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122898 | 9027000 | 05 | Preparation | 0000138173 | 3 | 0 | EA | 102000000025834 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-21 | GRST-5000391223_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056494 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230034_2025_0005 | 2024-12-01 | 244PT501 | 5000391223_2025_0003 | 0 | 2 | 0 | 90025184 | 1 | 0 | 180122898/180122901 | 2 | 0 | 0 | X | L | 4900230034 | 2025 |  | 5000391223 | 2025 | 0 |  | 2024-11-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-11-21 | W |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9027000_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137584 | S002 | 30 | 30 | 5300018206 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138173 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0090 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 19.02 - At KGP | Supply for Order 100039671, Item 8 cannot be changed 9026894 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122884 | 9026894 | 05 | Preparation | 0000138175 | 8 | 0 | EA | 102000000028270 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391239_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056488 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230007_2025_0011 | 2025-03-01 | 244PT60 | 5000391239_2025_0006 | 0 | 2 | 0 | 90024950 | 1 | 0 | 180122884 | 2 | 0 | 0 | X | L | 4900230007 | 2025 |  | 5000391239 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 9026894_0070 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 8 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 | 30 | 30 | 5300002039 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0090 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 19.02 - At KGP | Supply for Order 100039740, Item 8 cannot be changed 9026897 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122888 | 9026897 | 05 | Preparation | 0000138264 | 8 | 0 | EA |  |  | 102000000027401 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391270_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056491 | 1020 | 2024-03-08 | 1 |  | 2025-02-07 | 4900230032_2025_0005 | 2025-03-01 | 344PT501 | 5000391270_2025_0003 | 0 | 2 | 0 | 90024951 | 1 | 0 | 180122920/180122888 | 2 | 0 | 0 | X | L | 4900230032 | 2025 |  | 5000391270 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026897_0070 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 8 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-07 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-01 | INLEC | 100047874 | 0010 | 0030 | 100047874 | MOC-124841 Transmitter Replace 114PT87 | AA53.114PIC87 | LOOP,CTRL PRESS TO E1409 SHELL OUTLET | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(07.11.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 29.01 - At KGP | Supply for Order 100047874, Item 3 cannot be changed 180100944 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017557 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100944 | 9021450 | 05 | Preparation | 0000146415 | 3 | 0 | EA | 102000000025713 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-07 | GRST-5000305882_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000044759 | 1020 | 2022-11-30 | 1 |  | 2024-12-04 | 4900184986_2024_0001 | 2024-12-01 | 114PT87 | 5000305882_2024_0001 | 0 | 2 | 0 | 90023935 | 1 | 0 | 180100944 | 2 | 0 | 0 | X | L | 4900184986 | 2024 |  | 5000305882 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-11-07 | W |  | 0010 | TX Pre Works | INT | TX Pre Works | 5 |  | 9021450_0030 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000145844 | S002 | 30 | 30 | 5300017557 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-11-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146415 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2024-03-01 | 2025-05-31 | 2025-06-01 | QMI | 100047965 | 0010 | 0010 | 100047965 | MOC-141289 Transmitter Replace 144FT84 | AA53.144FT84 | METER,DP FLOW,1V4450 OUTLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 29.01 - At KGP | Supply for Order 100047965, Item 1 cannot be changed 180009111 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300001827 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180009111 | 90001493 | 05 | Preparation | 0000146486 | 1 | 0 | EA |  |  | 102000000002681 | 01-Road |  | 3-In Transit |  | WorkPackLink | QMP08CAGE | KCM-LNG | 0 | 5400001854 | 10 | 1 | EA | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000030950_2024 | 0 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2025-05-31 |  |  | 2025-03-01 |  |  | 100000002887 | 1020 | 2024-12-30 | 1 |  | 2024-03-06 | 4900035070_2024_0001 | 2024-03-04 | 144FT84 | 5000030950_2024_0001 | 0 | 2 | 0 | 90001493 | 1 | 0 | 180009111 | 2 | 0 | 0 | X | L | 4900035070 | 2024 |  | 5000030950 | 2024 | 0 |  | 2024-03-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Engineering Query/Management of Change | 90001493_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 | 4900193788_2024 | 25SDLN1 | MJ | 1000000809 | AU1072 | 1000145855 | S002 | 30 | 30 | 5300001827 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-03-01 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146486 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-06-01 | 2025-05-31 | 2025-05-31 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-10-04 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | VALVE | 100076445 | 0030 | 0010 | 100076445 | MV-RE 1/2" 300# 244LT512 | AA53.244LT512 | TX,LEVEL DRAIN POT 2K4401V5A | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.10.2024) | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 11 | 4 | 13 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 100076445, Item 4 cannot be changed 90025022 item 10 already exists | Material picked; currently at SW3R01B01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016044 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025022 | 05 | Preparation | 0000232991 | 4 | 0 | EA | 102000000027400 |  | 102000000026658 |  |  |  |  | WorkPackLink | SW3R01B01A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-04 | ODST-0090025022_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 244LT512 |  | 0 | 2 | 0 | 90025022 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS | 2024-10-15 | W |  | 0030 | Complete Manifold Replacement | INT | Complete Manifold Replacement |  |  | 90025022_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000230114 | S002 | 30 | 30 | 5300016044 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-04-17 | 232991 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100085112 | 0020 | 0050 | 100085112 | MOC-150252: Flow TX's Repl (2) 44FT21L/H | AA53.44FT21L | TX,FLOW LP FUEL GAS TO HEADER | AA01 | 20 | No issue identified | 10025892 | PLATE,MTG;C/W BRACKETS | 2 | EA | 11 | 4 | 13 | 0 |  | 09.02 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021006 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030534 | 05 | Preparation | 0000267756 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-08 | ODST-0090030534_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 44FT21L/H |  | 0 | 2 | 0 | 90030534 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030534_0050 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000262795 | S002 | 30 | 30 | 5300021006 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267756 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Printed/Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2025-02-10 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100087067 | 0010 | 0010 | 100087067 | LO Temp Switch FT/Replace 124TS95 | AA53.1KKT2430 | PKG EQ,TURBINE COMPR | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(09.02.2025) | 10025908 | SWITCH,TEMP,CCS,FLP,35-140DEGF,5FT CAPIL | 1 | EA | 2 | 0 | 0 | 1 | EA | 11.02 - qty 2 SOH @ AA02 | Supply for Order 100087067, Item 1 cannot be changed 90030597 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021038 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030597 | 05 | Preparation | 0000275734 | 1 | 0 | EA |  |  | 102000000033272 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-10 | ODST-0090030597_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030597 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025908 | SWITCH,TEMP,CCS,FLP,35-140DEGF,5FT CAPIL | 2025-02-09 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  |  | 90030597_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000270282 | S002 |  | 30 | 5300021038 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-07 | 275734 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100087068 | 0010 | 0020 | 100087068 | LO Temp Switch FT/Replace 124TS81 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(08.02.2025) | 10025908 | SWITCH,TEMP,CCS,FLP,35-140DEGF,5FT CAPIL | 1 | EA | 2 | 0 | 0 | 1 | EA | 11.02 - qty 2 SOH @ AA02 | Supply for Order 100087068, Item 2 cannot be changed 90030535 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021007 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030535 | 05 | Preparation | 0000275735 | 2 | 0 | EA |  |  | 102000000033271 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-08 | ODST-0090030535_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030535 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025908 | SWITCH,TEMP,CCS,FLP,35-140DEGF,5FT CAPIL | 2025-02-08 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  |  | 90030535_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000270283 | S002 |  | 30 | 5300021007 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-07 | 275735 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | INLEC | 100087761 | 0010 | 0030 | 100087761 | Suct/Disch Temp F/Test (8) 5K2001 | AA53.520TE110A | TXDCR,RTD CYL 1 SUCT HE VLV 5K2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10026065 | RTD;PT100,R/MOUNT 214CRWSMB1S4E0062SLM2 | 3 | EA | 7 | 0 | 0 | 3 | EA | 02.12 - SOH @ AA02 | Supply for Order 100087761, Item 3 cannot be changed 90028436 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018539 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028436 | 05 | Preparation | 0000278369 | 3 | 0 | EA | 102000000033127 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-28 | ODST-0090028436_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520110/11A-D |  | 0 | 2 | 0 | 90028436 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026065 | RTD;PT100,R/MOUNT 214CRWSMB1S4E0062SLM2 | 2024-11-28 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's |  |  | 90028436_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272778 | S002 | 30 | 30 | 5300018539 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-11-20 | 278369 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0240 | 0010 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue detected, please check message in derivation or orchestration log | 10026289 | VALVE | 1 | EA | 0 | 0 | 0 | 0 |  | 09.02 - NEED PURCHAAE REQ | Linked PR creation failed for Order 187 Item |  | SP97 | Direct Multi-base | 0 | AA01 | 5300020791 | 10 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030107 | 05 | Preparation | 0000236589 | 187 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-03 |  | 0 | 0 | 0 | 0 |  | 2025-02-22 | AA53 | 2025-03-01 | [7 empty] | 2025-12-14 | 0 |  | 2025-02-12 |  | 2025-02-24 |  |  | 0 | 2 | 0 | 90030107 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026289 | VALVE | 2025-02-03 | E |  | 0240 | 520TCV502 Valve | INT | 520TCV502 Valve |  |  | 90030107_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA02 |  | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000233553 | S001 | 71 | 71 | 5300015696 | 920 |  | 5300020791 | 10 | 1 | EA | 1001 | AA02 | 2025-02-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086262 | 0020 | 0020 | 100086262 | Heat Detector Replace (12) 1KT2420 | AA53.160TS1201A | DET,HEAT 1KT2420 AUX COMPARTMENT | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10026434 | DETECTOR,TEMP;RATE COMP,450DEGF,SS,EXD | 6 | EA | 64 | 6 | 0 | 6 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086262, Item 2 cannot be changed 90025089 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017084 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124186 | 90025089 | 05 | Preparation | 0000272421 | 2 | 0 | EA | 102000000027735 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-30 | IDST-0180124186 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 6 |  | 2025-02-11 | 4900234088_2025_0003 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025089 | 0 | 0 | 180124186 | 2 | 0 | 0 | X | L | 4900234088 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026434 | DETECTOR,TEMP;RATE COMP,450DEGF,SS,EXD | 2024-10-29 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  |  | 90025089_0020 |  |  | DG1 |  | C2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267121 | S002 | 30 | 30 | 5300017084 | 20 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272421 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2790 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10026434 | DETECTOR,TEMP;RATE COMP,450DEGF,SS,EXD | 4 | EA | 64 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 407 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026434 | DETECTOR,TEMP;RATE COMP,450DEGF,SS,EXD |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086262 | 0020 | 0030 | 100086262 | Heat Detector Replace (12) 1KT2420 | AA53.160TS1201A | DET,HEAT 1KT2420 AUX COMPARTMENT | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10026437 | DETECTOR,TEMP;RATE COMP,600DEG F,125V/5A | 3 | EA | 33 | 3 | 0 | 3 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086262, Item 3 cannot be changed 90025089 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017084 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124186 | 90025089 | 05 | Preparation | 0000272421 | 3 | 0 | EA | 102000000031667 | 102000000029896 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-30 | IDST-0180124186 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 3 |  | 2025-02-11 | 4900234088_2025_0005 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025089 | 0 | 0 | 180124186 | 2 | 0 | 0 | X | L | 4900234088 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026437 | DETECTOR,TEMP;RATE COMP,600DEG F,125V/5A | 2024-10-29 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  |  | 90025089_0030 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267121 | S002 | 30 | 30 | 5300017084 | 30 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272421 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2800 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10026437 | DETECTOR,TEMP;RATE COMP,600DEG F,125V/5A | 3 | EA | 33 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 408 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 160TS1221A-C |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026437 | DETECTOR,TEMP;RATE COMP,600DEG F,125V/5A |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100086262 | 0020 | 0010 | 100086262 | Heat Detector Replace (12) 1KT2420 | AA53.160TS1201A | DET,HEAT 1KT2420 AUX COMPARTMENT | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10026438 | DETECTOR,TEMP;SS,NP RTO876160019 | 3 | EA | 25 | 3 | 0 | 3 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086262, Item 1 cannot be changed 90025089 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017084 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124186 | 90025089 | 05 | Preparation | 0000272421 | 1 | 0 | EA | 102000000031667 | 102000000029894 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-30 | IDST-0180124186 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 3 |  | 2025-02-11 | 4900234088_2025_0001 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025089 | 0 | 0 | 180124186 | 2 | 0 | 0 | X | L | 4900234088 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026438 | DETECTOR,TEMP;SS,NP RTO876160019 | 2024-10-29 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  |  | 90025089_0010 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267121 | S002 |  | 30 | 5300017084 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272421 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3060 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10026438 | DETECTOR,TEMP;SS,NP RTO876160019 | 3 | EA | 25 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 584 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 160TS1201A-C |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026438 | DETECTOR,TEMP;SS,NP RTO876160019 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDLN3 | Released | 2024-11-02 | 2025-05-19 |  | 2025-05-19 | 2025-05-19 | INLEC | 100086628 | 0010 | 0010 | 100086628 | OPSD $AS 314XE706C flame detector Fault | AA53.314XE706C | DET,U/V 3KT1450 TURB COMBUSTION CHBR #4 | AA01 | 20 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 1 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000274260 | 1 | 0 | [8 empty] | WorkPackLink |  | P19 FL INLEC | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-19 |  |  | 2025-05-19 |  |  |  |  | 2025-05-03 | 0 |  |  |  |  | LNG 3 OPSD |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  |  |  | 0010 | OPSD $AS 314XE706C flame detector Fault | INT | OPSD $AS 314XE706C flame detector Fault |  | Opportune Shutdown |  |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000268951 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W36179 | 2024-11-02 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-19 | 2025-05-19 | 2025-05-19 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2860 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 0 | 0 | 0 |  | 12.11 - SOH @ AA02 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 564 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124BE101-104 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDLN1 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144602 | 0010 | 0010 | 200144602 | 2Y Flame Eyes F/Test/Repl (4) 1KT1410 | AA53.114XE306A | DET,FLAME LOSS IN CHAMBER 2 KT1410 | AA01 | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231727 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228874 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144603 | 0010 | 0030 | 200144603 | 2Y Flame Eyes F/Test/Repl (4) 1KT1420 | AA53.114XE406A | DET,FLAME LOSS IN CHAMBER 2 KT1420 | AA01 | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231728 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228875 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144604 | 0010 | 0030 | 200144604 | 2Y Flame Eyes F/Test/Repl (4) 1KT1430 | AA53.114XE506A | DET,FLAME LOSS IN CHAMBER 2 KT1430 | AA01 | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231729 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228876 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144605 | 0010 | 0030 | 200144605 | 2Y Flame Eyes F/Test/Repl (4) 1KT1440 | AA53.114XE606A | DET,FLAME LOSS IN CHAMBER 2 KT1440 | AA01 | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231730 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228877 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-10-17 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144606 | 0010 | 0030 | 200144606 | 2Y Flame Eyes F/Test/Repl (4) 1KT1450 | AA53.114XE706A | DET,FLAME LOSS IN CHAMBER 1 KT1450 | AA01 | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231731 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228878 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | INLEC | 200146372 | 0010 | 0010 | 200146372 | 2Y Flame Eyes Repl (4) 1K2420 | AA53.124BE101 | DET,1KT2420 COMBUSTION FLAME EYE CAN2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.11.2024) | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 8 | 8 | 1 | EA | 12.11 - SOH @ AA02 | Supply for Order 200146372, Item 1 cannot be changed 90025099 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017679 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124190 | 90025099 | 05 | Preparation | 0000234482 | 1 | 0 | EA | 102000000032164 | 102000000030922 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-11 | IDST-0180124190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 4 |  | 2025-02-11 | 4900234048_2025_0001 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025099 | 0 | 0 | 180124190 | 2 | 0 | 0 | X | L | 4900234048 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 2024-11-10 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90025099_0010 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000231480 | S002 | 30 | 30 | 5300017679 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-25 | 234482 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | INLEC | 200146372 | 0010 | 0010 | 200146372 | 2Y Flame Eyes Repl (4) 1K2420 | AA53.124BE101 | DET,1KT2420 COMBUSTION FLAME EYE CAN2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.11.2024) | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 8 | 8 | 1 | EA | 12.11 - SOH @ AA02 | Supply for Order 200146372, Item 1 cannot be changed 90025099 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017679 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124190 | 90025099 | 05 | Preparation | 0000234482 | 1 | 0 | EA | 102000000032164 | 102000000028275 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-11 | IDST-0180124190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 4 |  | 2025-02-11 | 4900234048_2025_0001 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025099 | 0 | 0 | 180124190 | 2 | 0 | 0 | X | L | 4900234048 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 2024-11-10 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90025099_0010 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000231480 | S002 | 30 | 30 | 5300017679 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-25 | 234482 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | INLEC | 200146372 | 0010 | 0010 | 200146372 | 2Y Flame Eyes Repl (4) 1K2420 | AA53.124BE101 | DET,1KT2420 COMBUSTION FLAME EYE CAN2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.11.2024) | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 8 | 8 | 2 | EA | 12.11 - SOH @ AA02 | Supply for Order 200146372, Item 1 cannot be changed 90025099 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017679 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124190 | 90025099 | 05 | Preparation | 0000234482 | 1 | 0 | EA | 102000000032164 | 102000000029148 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-11 | IDST-0180124190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 4 |  | 2025-02-11 | 4900234048_2025_0001 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025099 | 0 | 0 | 180124190 | 2 | 0 | 0 | X | L | 4900234048 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 2024-11-10 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90025099_0010 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000231480 | S002 | 30 | 30 | 5300017679 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-25 | 234482 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200156282 | 0010 | 0010 | 200156282 | 2Y Flame Eyes Repl (4) 2K2430 | AA53.224BE105 | DET,2KT2430 COMBUSTION FLAME EYE | AA01 | 10 | Shipped qty below requirement qty | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 8 | 8 | 1 | EA | 19.02 - At KGP | Supply for Order 200156282, Item 1 cannot be changed 90025113 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300017912 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117369 | 9026115 | 05 | Preparation | 0000248881 | 1 | 0 | EA | 102000000030923 | 101000000134685 | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-14 | GRST-5000369038 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053996 | 1020 | 2025-06-28 | 2 |  | 2025-01-22 | 4900216206_2025_0001 | 2025-03-01 | 1KT2430 | 5000369038_2025_0001 | 0 | 2 | 0 | 90025113 | 2 | 0 | 180117369 | 1 | 0 | 0 | X | L | 4900216206 | 2025 |  | 5000369038 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 2024-11-14 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90025113_0010/9026115_0010 |  |  | DG2 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000245303 | S002 | 30 | 30 | 5300017912 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240706 | 2024-07-06 | 248881 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200156282 | 0010 | 0010 | 200156282 | 2Y Flame Eyes Repl (4) 2K2430 | AA53.224BE105 | DET,2KT2430 COMBUSTION FLAME EYE | AA01 | 10 | Shipped qty below requirement qty | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 8 | 8 | 1 | EA | 19.02 - At KGP | Supply for Order 200156282, Item 1 cannot be changed 90025113 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300017912 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117369 | 9026115 | 05 | Preparation | 0000248881 | 1 | 0 | EA | 102000000032508 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-14 | GRST-5000369038 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053996 | 1020 | 2025-06-28 | 2 |  | 2025-01-22 | 4900216206_2025_0001 | 2025-03-01 | 1KT2430 | 5000369038_2025_0001 | 0 | 2 | 0 | 90025113 | 2 | 0 | 180117369 | 1 | 0 | 0 | X | L | 4900216206 | 2025 |  | 5000369038 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 2024-11-14 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90025113_0010/9026115_0010 |  |  | DG2 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000245303 | S002 | 30 | 30 | 5300017912 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240706 | 2024-07-06 | 248881 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200156282 | 0010 | 0010 | 200156282 | 2Y Flame Eyes Repl (4) 2K2430 | AA53.224BE105 | DET,2KT2430 COMBUSTION FLAME EYE | AA01 | 10 | Shipped qty below requirement qty | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 3 | 8 | 8 | 2 | EA | 19.02 - At KGP | Supply for Order 200156282, Item 1 cannot be changed 90025113 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300017912 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117369 | 9026115 | 05 | Preparation | 0000248881 | 1 | 0 | EA | 101000000134686 |  | 102000000030811 | 01-Road |  | 3-In Transit |  | WorkPackLink | INLEC-CAGE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-14 | GRST-5000369038_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000053996 | 1020 | 2025-06-28 | 2 |  | 2025-01-22 | 4900216206_2025_0001 | 2025-03-01 | 1KT2430 | 5000369038_2025_0001 | 0 | 2 | 0 | 90025113 | 2 | 0 | 180117369 | 1 | 0 | 0 | X | L | 4900216206 | 2025 |  | 5000369038 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 2024-11-14 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90025113_0010/9026115_0010 |  |  | DG2 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ | 1000004874 | AU1072 | 1000245303 | S002 | 30 | 30 | 5300017912 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-22 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240706 | 2024-07-06 | 248881 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 200144771 | 0010 | 0020 | 200144771 | 2Y Harm Filter Vesda Check 60JB870 | AA53.60JB870 | JB,NON I.S. JUNCTION BOX | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10026494 | TESTER;SMK DETECT,AERO,PSA LIFLT711 | 1 | CAN | 2 | 0 | 1 | 1 | CAN | 19.02 - At KGP | Supply for Order 200144771, Item 2 cannot be changed 9026350 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016479 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | CAN |  |  |  | 180119978 | 9026350 | 05 | Preparation | 0000231921 | 2 | 0 | CAN | 102000000031870 |  | 107000000000399 |  |  |  |  | WorkPackLink | INLEC-CAGE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000379461_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  | 100000055482 | 1020 | 2025-10-15 | 1 |  | 2025-01-30 | 4900222651_2025_0001 | 2025-03-01 | 60JB870 | 5000379461_2025_0001 | 0 | 2 | 0 | 90025042 | 1 | 0 | 180119978 | 2 | 0 | 0 | X | L | 4900222651 | 2025 |  | 5000379461 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026494 | TESTER;SMK DETECT,AERO,PSA LIFLT711 | 2024-10-16 | W |  | 0010 | Function Test & Complete PRT / MITR | INT | Function Test & Complete PRT / MITR | 2 |  | 9026350_0020 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000229037 | S002 | 30 | 30 | 5300016479 | 20 |  |  | 0 | 1 | CAN | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231921 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | INLEC | 100087760 | 0010 | 0010 | 100087760 | Cyl Rod Drop Probes F/Test (4) 5K2001 | AA53.520XT11A | TXDCR,SENSOR PROX CYL 1 ROD DROP 5K2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10026563 | SENSOR,PROX;BENTLY 330704000050100205 | 4 | EA | 6 | 0 | 0 | 3 | EA | 02.03 - SOH @ AA02 | Supply for Order 100087760, Item 1 cannot be changed 90028435 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018538 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028435 | 05 | Preparation | 0000278368 | 1 | 0 | EA | 102000000030117 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-28 | ODST-0090028435_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5K2001 |  | 0 | 2 | 0 | 90028435 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026563 | SENSOR,PROX;BENTLY 330704000050100205 | 2024-11-28 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's |  |  | 90028435_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272777 | S002 | 30 | 30 | 5300018538 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-11-20 | 278368 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0030 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10026567 | PROBE;EX(IA),8MM,1MM,BENTLY 330105 | 18 | EA | 8 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA01/AA02 | Supply for Order 200089806, Item 3 cannot be changed 90024958 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003900 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024958 | 05 | Preparation | 0000128060 | 3 | 0 | EA | 102000000027506 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024958_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024958 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026567 | PROBE;EX(IA),8MM,1MM,BENTLY 330105 | 2024-01-02 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024958_0030 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127469 | S002 |  | 30 | 5300003900 | 30 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128060 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-16 | INLEC | 200089807 | 0010 | 0030 | 200089807 | 8Y Replace Vibration Probes (4) 1K1820 | AA53.118XT505A | TXDCR,1K1820 GEAR AXIAL DISPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10026567 | PROBE;EX(IA),8MM,1MM,BENTLY 330105 | 4 | EA | 8 | 0 | 0 | 0 |  | 02.10 - SOH @ AA01/AA02 | Supply for Order 200089807, Item 3 cannot be changed 90024959 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003901 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024959 | 05 | Preparation | 0000128101 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024959_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024959 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026567 | PROBE;EX(IA),8MM,1MM,BENTLY 330105 | 2024-01-02 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024959_0010 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127470 | S002 |  | 30 | 5300003901 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128101 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-02-07 | 2025-01-31 | 2025-02-07 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0020 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(07.02.2025) | 10026960 | VALVE,TRIP;0.25",FISHER 377571169138 | 2 | EA | 4 | 0 | 0 | 2 | EA | 09.02 - SOH @ AA02 | Supply for Order 600001473, Item 2 cannot be changed 90030516 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020972 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030516 | 05 | Preparation | 0000084391 | 2 | 0 | EA | 102000000034077 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030516_0020 | 0 | 12 | 0 | 0 |  | 2025-01-29 | AA53 | 2025-05-08 |  |  | 2025-02-12 |  |  |  |  | 2025-12-15 | 0 |  | 2025-02-07 |  | 2025-02-12 | 4V1302 |  | 0 | 2 | 0 | 90030516 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-07 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026960 | VALVE,TRIP;0.25",FISHER 377571169138 | 2025-02-07 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90030516_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083795 | S002 |  | 30 | 5300020972 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-07 |  | Engineering Query/Management of Change |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84391 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1900 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10026963 | VALVE,CONTR;0.5",30GPM,DENISON R2V12333 | 2 | EA | 6 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 264 cannot be changed 90028419 item 2030 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2060 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 264 | 0 | EA | 102000000031288 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026963 | VALVE,CONTR;0.5",30GPM,DENISON R2V12333 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2030 |  |  | DG1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 264 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2060 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-11-15 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100042172 | 0020 | 0010 | 100042172 | 3 Way Pilot Valve Replace 414UV122 | AA53.414UV122 | VALVE,CTRL EXIST HW TO E1409 | AA01 | 20 | Del to Maintenance after Reqmt Date | 10027101 | VALVE:PILOT,0.500"NPT,3 WAY,SS316L | 1 | EA | 3 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 100042172, Item 1 cannot be changed 90029070 item 10 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300017923 | 10 | CPT | 7 | 1000023276 | 1 | 30000103 | ROTORK AUSTRALIA PTY LTD | 4500037868 | 10 | 1 | EA | 2025-03-07 |  | 180128194/ |  | 90025115 | 05 | Preparation | 0000140693 | 1 | 0 | EA | 101000000148506 |  | 101000000148916 | 01-Road |  | 5-Completed |  | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2025-03-05 | 2025-02-28 | Y | 1001 | 2024-11-15 | ODST-0090025115_0010 | 0 | 9 | 0 | 9 | 2025-02-10 | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-10 | 2025-02-12 | 2025-03-05 |  |  | 2022-07-07 | 0 | 5000414599_2025_0001 | 2025-02-24 |  | 2025-02-24 | 414UV122 |  | 0 | 2 | 2 | 90025115 | 0 | 1 |  | 1 | 0 | 0 | X | L |  | 0 | 5000414599 |  | 0 | 2025 | 180128194 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10027101 | VALVE:PILOT,0.500"NPT,3 WAY,SS316L | 2024-11-14 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025115_0010 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-12-17 | 20 | 6000011666 | 2025-02-12 | 1 |  | 0 |  | 25SDLN4 | MJ | 20005363 | AU1072 | 1000140122 | S002 | 30 | 30 | 5300017923 | 10 |  | 5300017924 | 10 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-26 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140693 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-11-15 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100042173 | 0020 | 0010 | 100042173 | 3 Way Pilot Valve Replace 414UV125 | AA53.414UV125 | VALVE,CTRL 4V1405 HW RETURN | AA01 | 20 | Del to Maintenance after Reqmt Date | 10027101 | VALVE:PILOT,0.500"NPT,3 WAY,SS316L | 1 | EA | 3 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 100042173, Item 1 cannot be changed 90029072 item 10 already exists | Material is received @AA01 | SP97 | Direct Multi-base | 48 | AA02 | 5300017927 | 10 | CPT | 7 | 1000023278 | 1 | 30000103 | ROTORK AUSTRALIA PTY LTD | 4500037868 | 30 | 1 | EA | 2025-03-07 |  | 180128194/ |  | 90025117 | 05 | Preparation | 0000140694 | 1 | 0 | EA | 101000000148508 |  | 101000000148916 | 01-Road |  | 5-Completed |  | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2025-03-05 | 2025-02-28 | Y | 1001 | 2024-11-15 | ODST-0090025117_0010 | 0 | 9 | 0 | 9 | 2025-02-10 | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-10 | 2025-02-12 | 2025-03-05 |  |  | 2022-07-07 | 0 | 5000414630_2025_0001 | 2025-02-24 |  | 2025-02-24 | 414UV125 |  | 0 | 2 | 2 | 90025117 | 0 | 1 |  | 1 | 0 | 0 | X | L |  | 0 | 5000414630 |  | 0 | 2025 | 180128194 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10027101 | VALVE:PILOT,0.500"NPT,3 WAY,SS316L | 2024-11-14 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025117_0010 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-12-17 | 20 | 6000011666 | 2025-02-12 | 1 |  | 0 |  | 25SDLN4 | MJ | 20005363 | AU1072 | 1000140123 | S002 | 30 | 30 | 5300017927 | 10 |  | 5300017928 | 10 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-26 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140694 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-11-15 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100042174 | 0020 | 0010 | 100042174 | 3 Way Pilot Valve Replace 414UV373 | AA53.414UV373 | VALVE,CTRL 4V1404 HW RETURN | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.11.2024) | 10027101 | VALVE:PILOT,0.500"NPT,3 WAY,SS316L | 1 | EA | 3 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 100042174, Item 1 cannot be changed 90029071 item 10 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 48 | AA02 | 5300017925 | 10 | CPT | 7 | 1000023277 | 1 | 30000103 | ROTORK AUSTRALIA PTY LTD | 4500037868 | 20 | 1 | EA | 2025-03-07 |  | 180128194/ |  | 90025116 | 05 | Preparation | 0000140695 | 1 | 0 | EA | 101000000148507 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-15 | ODST-0090025116_0010 | 0 | 9 | 0 | 9 | 2025-02-10 | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-10 | 2025-02-12 | 2025-03-05 |  |  | 2022-07-07 | 0 | 5000414578_2025_0001 | 2025-02-24 |  | 2025-02-24 | 414UV373 |  | 0 | 2 | 2 | 90025116 | 0 | 1 |  | 2 | 0 | 0 | X | L |  | 0 | 5000414578 |  | 0 | 2025 | 180128194 | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10027101 | VALVE:PILOT,0.500"NPT,3 WAY,SS316L | 2024-11-14 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025116_0010 |  |  | LN4 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA53 | 2024-12-17 | 20 | 6000011666 | 2025-02-12 | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000140124 | S002 | 30 | 30 | 5300017925 | 10 |  | 5300017926 | 10 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140695 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100080816 | 0050 | 0010 | 100080816 | MOC-117208 Repl Accumulators (2) 1A1491 | AA53.1A1491 | PKG EQ,HYD PWR PACK | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.11.2024) | 10027265 | SWITCH,PROX,5-25VDC,RG 1.5MM,18GM-ND,IND | 2 | EA | 6 | 0 | 3 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 100080816, Item 1 cannot be changed 90025102 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017708 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025102 | 05 | Preparation | 0000251583 | 1 | 0 | EA | 102000000032011 | 102000000031705 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-11 | ODST-0090025102_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1A1491 |  | 0 | 2 | 0 | 90025102 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10027265 | SWITCH,PROX,5-25VDC,RG 1.5MM,18GM-ND,IND | 2024-11-11 | W |  | 0050 | Remove & Replace Proxys | INT | Remove & Replace Proxys |  |  | 90025102_0010 |  |  | LN1 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000247849 | S002 |  | 30 | 5300017708 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPR07 | 2024-07-19 | 251583 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100080816 | 0050 | 0010 | 100080816 | MOC-117208 Repl Accumulators (2) 1A1491 | AA53.1A1491 | PKG EQ,HYD PWR PACK | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.11.2024) | 10027265 | SWITCH,PROX,5-25VDC,RG 1.5MM,18GM-ND,IND | 2 | EA | 6 | 0 | 3 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 100080816, Item 1 cannot be changed 90025102 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017708 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025102 | 05 | Preparation | 0000251583 | 1 | 0 | EA | 102000000032011 | 102000000025968 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-11 | ODST-0090025102_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1A1491 |  | 0 | 2 | 0 | 90025102 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10027265 | SWITCH,PROX,5-25VDC,RG 1.5MM,18GM-ND,IND | 2024-11-11 | W |  | 0050 | Remove & Replace Proxys | INT | Remove & Replace Proxys |  |  | 90025102_0010 |  |  | LN1 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000247849 | S002 |  | 30 | 5300017708 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPR07 | 2024-07-19 | 251583 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100080929 | 0050 | 0010 | 100080929 | MOC-117208 Repl Accumulators (3) 1A1190 | AA53.1A1190 | PKG EQ,PWR PACK FOR HYD VALVES (SEE P1) | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.11.2024) | 10027265 | SWITCH,PROX,5-25VDC,RG 1.5MM,18GM-ND,IND | 3 | EA | 6 | 0 | 3 | 3 | EA | 02.03 - SOH @ AA02 | Supply for Order 100080929, Item 1 cannot be changed 90025103 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017709 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025103 | 05 | Preparation | 0000251550 | 1 | 0 | EA | 102000000032001 | 102000000031706 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-11 | ODST-0090025103_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1A1190 |  | 0 | 2 | 0 | 90025103 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10027265 | SWITCH,PROX,5-25VDC,RG 1.5MM,18GM-ND,IND | 2024-11-11 | W |  | 0050 | Remove & Replace Proxys | INT | Remove & Replace Proxys |  |  | 90025103_0010 |  |  | LN1 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000247889 | S002 |  | 30 | 5300017709 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPR07 | 2024-07-19 | 251550 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Error in cost calculation | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100086264 | 0020 | 0030 | 100086264 | Start Clutch/UV Purge Sol OH (3) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10027962 | VALVE,SLND;2 WAY,0.5",125PSI,125VDC | 1 | EA | 15 | 1 | 1 | 1 | EA | 18.11 - SOH @ AA02 | Supply for Order 100086264, Item 3 cannot be changed 90025091 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017153 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124193 | 9027127 | 05 | Preparation | 0000272423 | 3 | 0 | EA | 102000000032149 | 102000000029580 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-31 | IDST-0180124193 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 1 |  | 2025-02-11 | 4900234099_2025_0005 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025091 | 0 | 0 | 180124193 | 2 | 0 | 0 | X | L | 4900234099 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10027962 | VALVE,SLND;2 WAY,0.5",125PSI,125VDC | 2024-10-29 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  |  | 9027127_0040 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267123 | S002 | 30 | 30 | 5300017153 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272423 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10027962 | VALVE,SLND;2 WAY,0.5",125PSI,125VDC | 1 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 581 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | UV purge |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10027962 | VALVE,SLND;2 WAY,0.5",125PSI,125VDC |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD4401 | Released | 2024-11-05 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0020 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2 | EA | 21 | 8 | 6 | 2 | EA | 29.01 - At KGP | Supply for Order 100039665, Item 14 cannot be changed 180092338 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180092338 | 9019265 | 05 | Preparation | 0000138169 | 14 | 0 | EA | 102000000023614 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000276551_2024 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000040088 | 1020 | 2024-03-07 | 2 |  | 2024-11-12 | 4900170489_2024_0001 | 2024-12-01 | 144PT504 | 5000276551_2024_0001 | 0 | 2 | 0 | 90023592 | 2 | 0 | 180092338/180122921 | 2 | 0 | 0 | X | L | 4900170489 | 2024 |  | 5000276551 | 2024 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2024-11-05 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9019265_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 14 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 |  | 30 | 5300017367 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0020 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2 | EA | 21 | 8 | 6 | 2 | EA | 29.01 - At KGP | Supply for Order 100039666, Item 1 cannot be changed 180100946 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100946 | 9021452 | 05 | Preparation | 0000138170 | 1 | 0 | EA | 102000000025718 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 | 5400002279 | 10 | 2 | EA | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000305846_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000044761 | 1020 | 2024-03-07 | 2 |  | 2024-12-04 | 4900185006_2024_0001 | 2025-03-01 | 144PT60 | 5000305846_2024_0001 | 0 | 2 | 0 | 90024949 | 2 | 0 | 180100946/180122911 | 2 | 0 | 0 | X | L | 4900185006 | 2024 |  | 5000305846 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9021452_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 |  | 30 | 5300002037 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0030 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2 | EA | 21 | 8 | 6 | 2 | EA | 19.02 - At KGP | Supply for Order 100039671, Item 3 cannot be changed 9026894 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122884 | 9026894 | 05 | Preparation | 0000138175 | 3 | 0 | EA | 102000000027384 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 | 5400002277 | 10 | 2 | EA | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391239_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056488 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900230007_2025_0003 | 2025-03-01 | 244PT60 | 5000391239_2025_0002 | 0 | 2 | 0 | 90024950 | 2 | 0 | 180122884 | 2 | 0 | 0 | X | L | 4900230007 | 2025 |  | 5000391239 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 9026894_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 |  | 30 | 5300002039 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0030 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2 | EA | 21 | 8 | 6 | 2 | EA | 19.02 - At KGP | Supply for Order 100039740, Item 3 cannot be changed 9026897 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122888 | 9026897 | 05 | Preparation | 0000138264 | 3 | 0 | EA | 102000000027383 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 | 5400002280 | 10 | 2 | EA | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391270_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056491 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900230032_2025_0001 | 2025-03-01 | 344PT501 | 5000391270_2025_0001 | 0 | 2 | 0 | 90024951 | 2 | 0 | 180122920/180122888 | 2 | 0 | 0 | X | L | 4900230032 | 2025 |  | 5000391270 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026897_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 |  | 30 | 5300002053 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0010 | 0050 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2 | EA | 21 | 8 | 6 | 2 | EA | 19.02 - At KGP | Supply for Order 100039741, Item 3 cannot be changed 9026899 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122896 | 9026899 | 05 | Preparation | 0000138265 | 3 | 0 | EA | 102000000027382 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AU01P08-UT | 0 | 5400002281 | 10 | 2 | EA | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391272_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056493 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900229979_2025_0001 | 2025-03-01 | 344PT504 | 5000391272_2025_0001 | 0 | 2 | 0 | 90024952 | 2 | 0 | 180122896 | 2 | 0 | 0 | X | L | 4900229979 | 2025 |  | 5000391272 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Management of Change | 9026899_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 |  | 30 | 5300002054 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2024-03-01 | 2025-05-31 | 2025-06-01 | QMI | 100047965 | 0010 | 0020 | 100047965 | MOC-141289 Transmitter Replace 144FT84 | AA53.144FT84 | METER,DP FLOW,1V4450 OUTLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10028105 | CONNECTOR,0.250",SS316,FILLING | 3 | EA | 21 | 8 | 6 | 3 | EA | 19.12 - Material Consumed | Supply for Order 100047965, Item 2 cannot be changed 180009111 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300001827 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180009111 | 90001493 | 05 | Preparation | 0000146486 | 2 | 0 | EA |  |  | 102000000002681 | 01-Road |  | 3-In Transit |  | WorkPackLink | QMP08CAGE | KCM-LNG | 0 |  | 0 | 0 |  | 1 | 2 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2025-05-31 |  |  | 2025-03-01 |  |  | 100000002887 | 1020 | 2024-12-30 | 3 |  | 2024-03-06 | 4900035070_2024_0003 | 2024-03-04 | 144FT84 | 5000030950_2024_0002 | 0 | 2 | 0 | 90001493 | 3 | 0 | 180009111 | 2 | 0 | 0 | X | L | 4900035070 | 2024 |  | 5000030950 | 2024 | 0 |  | 2024-03-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Engineering Query/Management of Change | 90001493_0020 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 | 4900193788_2024 | 25SDLN1 | MJ | 1000000809 | AU1072 | 1000145855 | S002 |  | 30 | 5300001827 | 20 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-03-01 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146486 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-06-01 | 2025-05-31 | 2025-05-31 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091128 | 0060 | 0130 | 200091128 | 6Y Motor Bearing Insp - 1KM2301 | AA53.1KM2301 | MOTOR,HV,REGENERATION GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(26.09.2024) | 10029478 | BEARING,SHELL;GARBE LAHMEYER DRGE286772> | 1 | EA | 0 | 0 | 1 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091128, Item 9 cannot be changed 90024963 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004360 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180133963 | 9028683 | 05 | Preparation | 0000129422 | 9 | 0 | EA |  |  | 101000000144004 | 01-Road |  | 5-Completed |  | WorkPackLink | P99PICKUPFROMWHSE | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 0 | 2025-02-16 | 2025-02-14 | Y | 1001 | 2024-01-02 | GRST-5000434486_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060902 | 1020 | 2023-04-01 | 1 |  | 2025-03-10 | 4900263280_2025_0001 | 2025-03-01 | 2200576286 | 5000434486_2025_0001 | 0 | 2 | 0 | 90024963 | 1 | 0 | 180133963 | 2 | 0 | 0 | X | L | 4900263280 | 2025 |  | 5000434486 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10029478 | BEARING,SHELL;GARBE LAHMEYER DRGE286772> | 2024-09-26 | W |  | 0060 | Inspect Motor NDE Bearing | ENON | Inspect Motor NDE Bearing | 5 |  | 9028683_0080 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SD2301 | MJ | 20005294 | AU1072 | 1000128791 | S002 |  | 30 | 5300004360 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-12 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0431 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10029482 | BEARING,SHELL,DE;TOSHIBA 2KE000283ITEM3> | 1 | EA | 0 | 0 | 0 | 0 |  | 06.02 - ETA 18.04.25 PO 4500044752 ex Toshiba Expediting Exhausted | Supply for Order 200091505, Item 83 cannot be changed 90025019 item 800 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 83 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0800 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | MainMtrDE |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10029482 | BEARING,SHELL,DE;TOSHIBA 2KE000283ITEM3> | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0800 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 83 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 800 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0440 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10029483 | BEARING,TOSHIBA TIKE-FCCNW MTR,NDE,SHELL | 1 | EA | 0 | 0 | 1 | 1 | EA | 29.01 - At KGP | Supply for Order 200091505, Item 54 cannot be changed 9025806 item 530 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 530 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117299 | 9025806 | 05 | Preparation | 0000129754 | 54 | 0 | EA |  |  | 101000000039253 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R3FL | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000368760_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000054015 | 1020 | 2025-06-05 | 1 |  | 2025-01-22 | 4900216122_2025_0001 | 2025-03-01 | MainMtrNDE | 5000368760_2025_0001 | 0 | 2 | 0 | 90025019 | 1 | 0 | 180117299 | 2 | 0 | 0 | X | L | 4900216122 | 2025 |  | 5000368760 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10029483 | BEARING,TOSHIBA TIKE-FCCNW MTR,NDE,SHELL | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 9025806_0530 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 54 |  | 0 |  | 25SDFR1 | MJ | 1000004848 | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 530 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-24 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091128 | 0060 | 0100 | 200091128 | 6Y Motor Bearing Insp - 1KM2301 | AA53.1KM2301 | MOTOR,HV,REGENERATION GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10029579 | RING,OIL;GARBE LAHMEYER 99000119003 | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091128, Item 5 cannot be changed 90024963 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004360 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024963 | 05 | Preparation | 0000129422 | 5 | 0 | EA | 102000000027509 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024963_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200576286 |  | 0 | 2 | 0 | 90024963 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10029579 | RING,OIL;GARBE LAHMEYER 99000119003 | 2024-01-02 | W |  | 0060 | Inspect Motor NDE Bearing | ENON | Inspect Motor NDE Bearing | 5 |  | 90024963_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128791 | S002 |  | 30 | 5300004360 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-07-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146424 | 0010 | 0040 | 200146424 | 5Y SVC 5KM2001 MOTOR MAJOR MATERIAL 2HF1 | AA53.5KM2001 | MOTOR,HV,MAIN,STABILIZER COMP,5K2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.07.2024) | 10029582 | RING,OIL;SIEMENS DRG2D30110340771REVC | 1 | EA | 1 | 0 | 0 | 1 | EA | 18.12 - SOH @ AA02 | Supply for Order 200146424, Item 4 cannot be changed 90024989 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013117 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024989 | 05 | Preparation | 0000234301 | 4 | 0 | EA | 102000000031789 | 102000000027510 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-23 | ODST-0090024989_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-04 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024989 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10029582 | RING,OIL;SIEMENS DRG2D30110340771REVC | 2024-07-22 | W |  | 0010 | MOTOR MAJOR MATERIALS 2HF1 | INT | MOTOR MAJOR MATERIALS 2HF1 | 5 |  | 90024989_0030 |  |  | ST5 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231257 | S002 |  |  | 5300013117 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-22 | 234301 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091128 | 0060 | 0110 | 200091128 | 6Y Motor Bearing Insp - 1KM2301 | AA53.1KM2301 | MOTOR,HV,REGENERATION GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10029616 | SEAL,LABYTH;GARBE LAHMEYER 99000119004 | 1 | EA | 1 | 0 | 0 | 0 |  | 03.10 - SOH @ AA02 | Supply for Order 200091128, Item 6 cannot be changed 90024963 item 50 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004360 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024963 | 05 | Preparation | 0000129422 | 6 | 0 | [8 empty] | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024963_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200576286 |  | 0 | 2 | 0 | 90024963 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10029616 | SEAL,LABYTH;GARBE LAHMEYER 99000119004 | 2024-01-02 | W |  | 0060 | Inspect Motor NDE Bearing | ENON | Inspect Motor NDE Bearing | 5 |  | 90024963_0050 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128791 | S002 |  | 30 | 5300004360 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-07-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146424 | 0010 | 0050 | 200146424 | 5Y SVC 5KM2001 MOTOR MAJOR MATERIAL 2HF1 | AA53.5KM2001 | MOTOR,HV,MAIN,STABILIZER COMP,5K2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.07.2024) | 10029717 | GLASS,SIGHT;SIEMENS DVN63307A50 | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200146424, Item 5 cannot be changed 90024989 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013117 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024989 | 05 | Preparation | 0000234301 | 5 | 0 | EA | 102000000031789 | 101000000135511 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-23 | ODST-0090024989_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-04 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024989 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10029717 | GLASS,SIGHT;SIEMENS DVN63307A50 | 2024-07-22 | W |  | 0010 | MOTOR MAJOR MATERIALS 2HF1 | INT | MOTOR MAJOR MATERIALS 2HF1 | 5 |  | 90024989_0040 |  |  | ST5 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231257 | S002 |  |  | 5300013117 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-22 | 234301 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147116 | 0020 | 0010 | 200147116 | 3Y Vibration Probe Replace (7) 1KT2420 | AA53.124YE031 | TXDCR,ALARM VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10031344 | PROXIMITOR;TXDCR,8MM,-26VDC,5M SYS | 7 | EA | 1 | 7 | 0 | 7 | EA | 18.11 - SOH @ AA02 | Supply for Order 200147116, Item 1 cannot be changed 9027115 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017864 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027115 | 05 | Preparation | 0000235387 | 1 | 0 | EA | 102000000032160 | 102000000027409 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-14 | GIST-4900234130_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 7 |  | 2025-02-11 | 4900234130_2025_0001 | 2025-03-01 | 1K2420 |  | 0 | 2 | 0 | 90025108 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234130 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10031344 | PROXIMITOR;TXDCR,8MM,-26VDC,5M SYS | 2024-11-13 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027115_0010 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232430 | S002 | 30 | 30 | 5300017864 | 10 |  |  | 0 | 7 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235387 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-02-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100036896 | 0020 | 0010 | 100036896 | MOC-150074 Hand Switch Replace 520HS087 | AA53.520HS087 | SW,HAND P/BUTTON MAN RESET 520UZ191 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.02.2025) | 10032259 | SWITCH,PB;EX,STAHL 8040/1178X01L03SA05 | 1 | EA | 5 | 0 | 0 | 1 | EA | 09.02 - SOH @ AA02 | Supply for Order 100036896, Item 1 cannot be changed 90030518 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020980 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030518 | 05 | Preparation | 0000135400 | 1 | 0 | EA | 102000000033433 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030518_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-02-12 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030518 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10032259 | SWITCH,PB;EX,STAHL 8040/1178X01L03SA05 | 2025-02-07 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030518_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000134831 | S002 | 30 | 30 | 5300020980 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 135400 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-02-27 | 2025-03-04 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0090 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10032707 | RELAY,PLUG-IN;IZUMI RH1BU | 2 | EA | 1 | 0 | 2 | 1 | EA | DEL: 80033611 | Supply for Order 600001363, Item 16 cannot be changed 90032183 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032183 | 05 | Preparation | 0000084301 | 16 | 0 | EA | 101000000152698 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-27 | ODST-0090032183_0040 | 0 | 10 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-27 |  |  | 2025-03-09 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-04 |  | 2025-03-09 | Scott Kinloc |  | 0 | 2 | 0 | 90032183 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10032707 | RELAY,PLUG-IN;IZUMI RH1BU | 2025-03-04 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90032183_0040 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 16 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 |  | 30 | 5300018438 | 110 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDSTB5 | Released | 2025-02-08 | 2025-02-27 | 2025-03-04 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0070 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10032968 | CONTACTOR,ELEC;240VAC,S+S CA73000240VAC | 2 | EA | 1 | 0 | 6 | 0 |  | 07.03 - PR 2000283489 RFQ | Supply for Order 600001363, Item 14 cannot be changed 90032183 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032183 | 05 | Preparation | 0000084301 | 14 | 0 | [8 empty] | WorkPackLink |  | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-27 | ODST-0090032183_0020 | 0 | 10 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-27 |  |  | 2025-03-09 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-04 |  | 2025-03-09 | Scott Kinloc |  | 0 | 2 | 0 | 90032183 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10032968 | CONTACTOR,ELEC;240VAC,S+S CA73000240VAC | 2025-03-04 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90032183_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 14 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 |  | 30 | 5300018438 | 90 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDFLR | Released | 2024-11-08 | 2025-02-08 | 2025-04-26 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0250 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Del to Maintenance after Reqmt Date | 10033993 | CABLE,INST;CU,1PR,1.5MM²,SWA,XLPE,BK,PVC | 330 | M | 660 | 0 | 50 | 330 | M | 20.02 - SOH @ AA01 | Supply for Order 600001815, Item 35 cannot be changed 180130291 item 20 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 30 | AA02 | 5300007843 | 260 | CPT | 14 | 1000029658 | 35 | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD | 4500046279 | 20 | 330 | M | 2025-02-28 |  | /180127155 |  | 90031517 | 07 | Execution | 0000084731 | 35 | 0 | M |  |  | 101000000147193 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-02-80B | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 330 | 2025-03-01 | 2025-02-28 | Y | 1001 | 2024-03-13 | ODST-0090031517_0020 | 0 | 82 | 0 | 0 | 2025-04-09 | 2025-04-29 | AA53 | 2025-02-08 |  |  | 2025-07-22 | 2025-04-11 | 2025-03-01 |  |  | 2024-08-30 | 0 | 5000409416_2025_0001 | 2025-04-26 |  | 2025-02-20 | 37PT40/41 |  | 0 | 2 | 2 | 90031517 | 0 | 330 |  | 1 | 0 | 0 | X | L |  | 0 | 5000409416 |  | 0 | 2025 | /018012715 | 2025-04-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10033993 | CABLE,INST;CU,1PR,1.5MM²,SWA,XLPE,BK,PVC | 2025-02-10 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90031517_0020 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-28 | 10 | 6000015203 | 2025-04-11 | 35 |  | 0 |  | 25SDFLR | MJ | 20005368 | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 260 |  | 5300011702 | 120 | 330 | M | 2001 | AA02 | 2025-04-26 |  |  | 2025-02-26 | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-02-08 | 2025-04-11 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0260 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Planned delivery after Reqmt Date | 10033993 | CABLE,INST;CU,1PR,1.5MM²,SWA,XLPE,BK,PVC | 330 | M | 660 | 0 | 660 | 0 |  | 16.02 - ETA 06.03.25 PO 4500046279 MACLEANS CPT | Supply for Order 600001815, Item 36 cannot be changed – 4500046279 already exists | Vendor PO raised | SP97 | Direct Multi-base | 30 | AA01 | 5300011702 | 130 | CPT | 7 | 1000029658 | 36 | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD | 4500046279 | 30 | 330 | M | 2025-04-25 |  |  |  |  | 07 | Execution | 0000084731 | 36 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 330 |  |  | Y | 1001 | 2024-06-18 | POPO-4500046279_00030 | 0 | 82 | 0 | 0 | 2025-04-09 | 2025-04-24 | AA53 | 2025-02-08 |  |  | 2025-07-22 | 2025-04-11 | 2025-04-26 |  |  | 2024-08-30 | 0 |  | 2025-04-11 |  | 2025-04-26 | 37TT40/41 |  | 0 | 2 | 2 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-04-11 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10033993 | CABLE,INST;CU,1PR,1.5MM²,SWA,XLPE,BK,PVC | 2025-02-10 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour | [5 empty] | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-28 | 10 | 6000015203 | 2025-04-11 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 | 30 | 30 | 5300007843 | 270 |  | 5300011702 | 130 | 330 | M | 1001 | AA02 | 2025-04-11 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-02-08 | 2025-04-11 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0270 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Planned delivery after Reqmt Date | 10033993 | CABLE,INST;CU,1PR,1.5MM²,SWA,XLPE,BK,PVC | 330 | M | 660 | 0 | 660 | 0 |  | 16.02 - ETA 06.03.25 PO 4500046279 MACLEANS CPT | Supply for Order 600001815, Item 37 cannot be changed – 4500046279 already exists | Vendor PO raised | SP97 | Direct Multi-base | 30 | AA01 | 5300011702 | 140 | CPT | 7 | 1000029658 | 37 | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD | 4500046279 | 40 | 330 | M | 2025-04-25 |  |  |  |  | 07 | Execution | 0000084731 | 37 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 330 |  |  | Y | 1001 | 2024-06-18 | POPO-4500046279_00040 | 0 | 82 | 0 | 0 | 2025-04-09 | 2025-04-24 | AA53 | 2025-02-08 |  |  | 2025-07-22 | 2025-04-11 | 2025-04-26 |  |  | 2024-08-30 | 0 |  | 2025-04-11 |  | 2025-04-26 | 37TT40/41 |  | 0 | 2 | 2 |  | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-04-11 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10033993 | CABLE,INST;CU,1PR,1.5MM²,SWA,XLPE,BK,PVC | 2025-02-10 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour | [5 empty] | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA02 | 2025-02-28 | 10 | 6000015203 | 2025-04-11 | 0 |  | 0 |  | 25SDFLR | MJ |  | AU1009 | 1000084145 | S001 | 30 | 30 | 5300007843 | 280 |  | 5300011702 | 140 | 330 | M | 1001 | AA02 | 2025-04-11 |  |  |  | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-02-08 | 2025-04-26 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0240 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Del to Maintenance after Reqmt Date | 10033993 | CABLE,INST;CU,1PR,1.5MM²,SWA,XLPE,BK,PVC | 330 | M | 660 | 0 | 50 | 330 | M | 20.02 - SOH @ AA01 | Supply for Order 600001815, Item 34 cannot be changed 180130291 item 10 already exists | Material work-packed @AA02 | SP97 | Direct Multi-base | 30 | AA02 | 5300007843 | 250 | CPT | 14 | 1000029658 | 34 | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD | 4500046279 | 10 | 330 | M | 2025-02-28 |  | /180127155 |  | 90031517 | 07 | Execution | 0000084731 | 34 | 0 | M |  |  | 101000000147194 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-02-80B | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 330 | 2025-03-01 | 2025-02-28 | Y | 1001 | 2024-03-13 | ODST-0090031517_0010 | 0 | 82 | 0 | 0 | 2025-04-09 | 2025-04-29 | AA53 | 2025-02-08 |  |  | 2025-07-22 | 2025-04-11 | 2025-03-01 |  |  | 2024-08-30 | 0 | 5000409399_2025_0001 | 2025-04-26 |  | 2025-02-20 | 37PT40/41 |  | 0 | 2 | 2 | 90031517 | 0 | 330 |  | 1 | 0 | 0 | X | L |  | 0 | 5000409399 |  | 0 | 2025 | /018012715 | 2025-04-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10033993 | CABLE,INST;CU,1PR,1.5MM²,SWA,XLPE,BK,PVC | 2025-02-10 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90031517_0010 |  |  | SL0 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 104 | Proj & Brownfields | AU00 | 0 | AA53 | 2025-02-28 | 10 | 6000015203 | 2025-04-11 | 34 |  | 0 |  | 25SDFLR | MJ | 20005368 | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 250 |  | 5300011702 | 110 | 330 | M | 2001 | AA02 | 2025-04-26 |  |  | 2025-02-26 | AU00 | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDSTB5 | Released | 2024-08-09 | 2025-03-01 | 2024-09-30 | 2025-03-01 | 2025-03-01 | INLEC | 100038870 | 1000 | 0060 | 100038870 | MOC-123206 Replace JB 5PM2001BJ | AA53.5PM2001BJ | JB,MOTOR,RCU STABLI HEATER PUMP,5P2001B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.08.2024) | 10034179 | LUG,COMP;35MM2,10MM SCR | 3 | EA | 32 | 0 | 0 | 3 | EA | 29.01 - At KGP | Supply for Order 100038870, Item 6 cannot be changed 180073873 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300013766 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180073873 | 9014200 | 06 | Scheduling | 0000137402 | 6 | 0 | EA | 102000000016236 | 102000000016146 | 102000000016159 | 01-Road |  | 4-Arrived | LP-NWS-14 | WorkPackLink | P08WHSFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 | 2024-09-26 |  | Y | 1001 | 2024-08-09 | GRST-5000295875_2024 | 0 | 0 | 0 | 0 |  | 2024-10-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000031264 | 1020 | 2025-07-31 | 3 |  | 2024-09-25 | 4900139136_2024_0005 | 2024-10-03 | 5PM2001BJ | 5000295875_2024_0003 | 0 | 2 | 0 | 90017620 | 3 | 0 | 180073887/180073873 | 2 | 0 | 0 | X | L | 4900139136 | 2024 |  | 5000295875 | 2024 | 0 |  | 2024-09-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034179 | LUG,COMP;35MM2,10MM SCR | 2024-08-09 | W |  | 1000 | Function Test & Complete ITR/MITR | INT | Function Test & Complete ITR/MITR |  | Management of Change | 9014200_0060 |  |  | ST5 |  | C3 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ | 20002965 | AU1072 | 1000136732 | S002 |  | 30 | 5300013766 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-09-30 |  | Management of Change | 2024-09-26 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-08-09 | 2025-03-01 | 2024-09-30 | 2025-03-01 | 2025-03-01 | INLEC | 100038870 | 1000 | 0050 | 100038870 | MOC-123206 Replace JB 5PM2001BJ | AA53.5PM2001BJ | JB,MOTOR,RCU STABLI HEATER PUMP,5P2001B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.08.2024) | 10034185 | LUG,COMP;70MM2,10MM STUD | 1 | BOX | 5 | 1 | 2 | 1 | BOX | 25.09 - At KGP | Supply for Order 100038870, Item 5 cannot be changed 180071767 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300013766 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  | 180071767 | 9013652 | 06 | Scheduling | 0000137402 | 5 | 0 | BOX |  |  | 102000000017739 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-KGP-RUNNER-SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 | 2024-09-19 |  | Y | 1001 | 2024-08-09 | GRST-5000213267_2024 | 0 | 0 | 0 | 0 |  | 2024-10-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000030340 | 1020 | 2025-07-31 | 1 |  | 2024-09-19 | 4900134631_2024_0001 | 2024-10-03 | 5PM2001BJ | 5000213267_2024_0001 | 0 | 2 | 0 | 90017620 | 1 | 0 | 180071767/180073887 | 2 | 0 | 0 | X | L | 4900134631 | 2024 |  | 5000213267 | 2024 | 0 |  | 2024-09-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034185 | LUG,COMP;70MM2,10MM STUD | 2024-08-09 | W |  | 1000 | Function Test & Complete ITR/MITR | INT | Function Test & Complete ITR/MITR |  | Management of Change | 9013652_0050 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ | 1000003367 | AU1072 | 1000136732 | S002 | 30 | 30 | 5300013766 | 50 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2024-09-30 |  | Management of Change | 2024-09-19 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-08-09 | 2025-03-01 | 2024-09-30 | 2025-03-01 | 2025-03-01 | INLEC | 100038870 | 1000 | 0070 | 100038870 | MOC-123206 Replace JB 5PM2001BJ | AA53.5PM2001BJ | JB,MOTOR,RCU STABLI HEATER PUMP,5P2001B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.08.2024) | 10034191 | LUG,COMP;HYLUG,120MM2,10MM,CU,PLTD | 6 | EA | 132 | 0 | 0 | 6 | EA | 29.01 - At KGP | Supply for Order 100038870, Item 7 cannot be changed 180073873 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300013766 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180073873 | 9014200 | 06 | Scheduling | 0000137402 | 7 | 0 | EA | 102000000016236 | 102000000016147 | 102000000016159 | 01-Road |  | 4-Arrived | LP-NWS-14 | WorkPackLink | P08WHSFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 | 2024-09-26 |  | Y | 1001 | 2024-08-09 | GRST-5000295875_2024 | 0 | 0 | 0 | 0 |  | 2024-10-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000031264 | 1020 | 2025-07-31 | 6 |  | 2024-09-25 | 4900139136_2024_0007 | 2024-10-03 | 5PM2001BJ | 5000295875_2024_0004 | 0 | 2 | 0 | 90017620 | 6 | 0 | 180073887/180073873 | 2 | 0 | 0 | X | L | 4900139136 | 2024 |  | 5000295875 | 2024 | 0 |  | 2024-09-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034191 | LUG,COMP;HYLUG,120MM2,10MM,CU,PLTD | 2024-08-09 | W |  | 1000 | Function Test & Complete ITR/MITR | INT | Function Test & Complete ITR/MITR |  | Management of Change | 9014200_0070 |  |  | ST5 |  | C3 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ | 20002965 | AU1072 | 1000136732 | S002 |  | 30 | 5300013766 | 70 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-09-30 |  | Management of Change | 2024-09-26 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-02-27 | 2025-03-04 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0020 | 0100 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10034255 | STRIP,TERM;CABAC BLP250 | 3 | PAC | 2 | 0 | 3 | 0 |  | DEL: 80033367 | Supply for Order 600001363, Item 17 cannot be changed 90032183 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAC |  |  |  |  | 90032183 | 05 | Preparation | 0000084301 | 17 | 0 | [8 empty] | WorkPackLink |  | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-27 | ODST-0090032183_0050 | 0 | 10 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-27 |  |  | 2025-03-09 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-04 |  | 2025-03-09 | Scott Kinloc |  | 0 | 2 | 0 | 90032183 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034255 | STRIP,TERM;CABAC BLP250 | 2025-03-04 | W |  | 0020 | Inlec materials sort&deliver to job site | INT | Inlec materials sort&deliver to job site |  |  | 90032183_0050 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 17 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 | 30 | 30 | 5300018438 | 120 |  |  | 0 | 3 | PAC | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0130 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10034453 | GLAND,CABLE;EXDE,UNIV,B,25MM THD | 6 | EA | 34 | 6 | 47 | 6 | EA | 06.02 - SOH @ AA02 | Supply for Order 600001815, Item 19 cannot be changed 9027608 item 110 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180126078 | 9027608 | 07 | Execution | 0000084731 | 19 | 0 | EA |  |  | 102000000033070 |  |  |  |  | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-03-13 | IDST-0180126078 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  | 100000057701 | 1020 | 2024-08-30 | 6 |  | 2025-02-17 | 4900239182_2025_0003 | 2025-03-01 | 37FQI40/41 |  | 0 | 2 | 0 | 90030415 | 0 | 0 | 180126078 | 2 | 0 | 0 | X | L | 4900239182 | 2025 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034453 | GLAND,CABLE;EXDE,UNIV,B,25MM THD | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 9027608_0110 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 19 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0120 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10034456 | GLAND,CABLE;EXDE,UNIV,O,WXYZ,20MM | 14 | EA | 0 | 5 | 28 | 14 | EA | 20.02 - SOH @ AA02 | Supply for Order 600001815, Item 18 cannot be changed 90030415 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132827 | 9028650 | 07 | Execution | 0000084731 | 18 | 0 | EA |  |  | 101000000146772 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-03-13 | GRST-5000429438_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  | 100000060147 | 1020 | 2024-08-30 | 14 |  | 2025-03-06 | 4900259004_2025_0001 | 2025-03-01 | 37FQI40/41 | 5000429438_2025_0001 | 0 | 2 | 0 | 90030415 | 14 | 0 | 180132827 | 2 | 0 | 0 | X | L | 4900259004 | 2025 |  | 5000429438 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034456 | GLAND,CABLE;EXDE,UNIV,O,WXYZ,20MM | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 9028650_0100 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 18 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 130 |  |  | 0 | 14 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0060 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10034647 | TIE,CABLE;186X4.8MM,BLK,PA 6.6 | 10 | PKT | 42 | 8 | 39 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500004676, Item 6 cannot be changed 90031855 item 60 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | PKT |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 6 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0060 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034647 | TIE,CABLE;186X4.8MM,BLK,PA 6.6 | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0060 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 60 |  |  | 0 | 10 | PKT | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 3 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0300 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10034648 | TIE,CABLE;295X4.8MM,PA,BLK,100PK | 8 | PKT | 76 | 21 | 66 | 8 | PKT | 23.01 - SOH @ AA02 | Supply for Order 100087648, Item 31 cannot be changed 90028417 item 290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | PKT |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 31 | 0 | PKT | 102000000031912 | 102000000031742 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034648 | TIE,CABLE;295X4.8MM,PA,BLK,100PK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0290 |  |  | ST5 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 31 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 300 |  |  | 0 | 8 | PKT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0020 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10034648 | TIE,CABLE;295X4.8MM,PA,BLK,100PK | 2 | PKT | 76 | 21 | 66 | 2 | PKT | Workpacked at KGP | Supply for Order 200089373, Item 2 cannot be changed 180091768 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | PKT |  |  |  | 180091768 | 9019016 | 07 | Execution | 0000127667 | 2 | 0 | PKT |  |  | 102000000023515 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-KGP-RUNNER-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000275117_2024 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000040386 | 1020 | 2025-12-15 | 2 |  | 2024-11-11 | 4900169565_2024_0003 | 2024-11-10 | Troy Mac | 5000275117_2024_0001 | 0 | 2 | 0 | 90023594 | 2 | 0 | 180091768 | 2 | 0 | 0 | X | L | 4900169565 | 2024 |  | 5000275117 | 2024 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034648 | TIE,CABLE;295X4.8MM,PA,BLK,100PK | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9019016_0020 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDFR2 | MJ | 1000004072 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 20 |  |  | 0 | 2 | PKT | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 3 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0090 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10034649 | TIE,CABLE;UV,6.9X343MM,PA,BLK | 20 | PKT | 0 | 0 | 17 | 0 |  | 10.03 - DEL: 80005434 | Supply for Order 100090053, Item 9 cannot be changed 90032376 item 90 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | PKT |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 9 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0090 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034649 | TIE,CABLE;UV,6.9X343MM,PA,BLK | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0090 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 9 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 90 |  |  | 0 | 20 | PKT | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | INLEC | 200067823 | 0020 | 0030 | 200067823 | 6Y SIF Exhaust TC Replace (18) 1KT2420 | AA53.124TE301 | TXDCR,1KT2420 TURB EXH DUCT TEMP | AA01 | 10 | Shipped qty below requirement qty | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W | 100 | EA | 150 | 16 | 42 | 16 | EA | 31.01 - SOH @ AA02 | Supply for Order 200067823, Item 3 cannot be changed 90025073 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016758 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027125 | 05 | Preparation | 0000102098 | 3 | 0 | EA | 102000000032159 | 102000000027583 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 84 |  |  | Y | 1001 | 2024-10-23 | GIST-4900234109_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2024-07-25 | 16 |  | 2025-02-11 | 4900234109_2025_0003 | 2025-03-01 | 124TE301-318 |  | 0 | 2 | 0 | 90025073 | 0 | 0 |  | 1 | 0 | 0 | X | L | 4900234109 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W | 2024-10-23 | W |  | 0020 | Complete Replacement of Cable & TC's | INT | Complete Replacement of Cable & TC's |  | Order Requires Replanning | 90025073_0030/9027125_0030 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000101542 | S002 | 30 | 70 | 5300016758 | 30 |  |  | 0 | 100 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 102098 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | INLEC | 200067823 | 0020 | 0030 | 200067823 | 6Y SIF Exhaust TC Replace (18) 1KT2420 | AA53.124TE301 | TXDCR,1KT2420 TURB EXH DUCT TEMP | AA01 | 10 | Shipped qty below requirement qty | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W | 100 | EA | 150 | 16 | 42 | 40 | EA | 31.01 - SOH @ AA02 | Supply for Order 200067823, Item 3 cannot be changed 90025073 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016758 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027125 | 05 | Preparation | 0000102098 | 3 | 0 | EA | 101000000139302 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 84 |  |  | Y | 1001 | 2024-10-23 | GIST-4900234109_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2024-07-25 | 16 |  | 2025-02-11 | 4900234109_2025_0003 | 2025-03-01 | 124TE301-318 |  | 0 | 2 | 0 | 90025073 | 0 | 0 |  | 1 | 0 | 0 | X | L | 4900234109 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W | 2024-10-23 | W |  | 0020 | Complete Replacement of Cable & TC's | INT | Complete Replacement of Cable & TC's |  | Order Requires Replanning | 90025073_0030/9027125_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000101542 | S002 | 30 | 70 | 5300016758 | 30 |  |  | 0 | 100 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 102098 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | INLEC | 200067823 | 0020 | 0030 | 200067823 | 6Y SIF Exhaust TC Replace (18) 1KT2420 | AA53.124TE301 | TXDCR,1KT2420 TURB EXH DUCT TEMP | AA01 | 10 | Shipped qty below requirement qty | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W | 100 | EA | 150 | 16 | 42 | 44 | EA | 31.01 - SOH @ AA02 | Supply for Order 200067823, Item 3 cannot be changed 90025073 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016758 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027125 | 05 | Preparation | 0000102098 | 3 | 0 | EA | 102000000033130 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 84 |  |  | Y | 1001 | 2024-10-23 | GIST-4900234109_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2024-07-25 | 16 |  | 2025-02-11 | 4900234109_2025_0003 | 2025-03-01 | 124TE301-318 |  | 0 | 2 | 0 | 90025073 | 0 | 0 |  | 1 | 0 | 0 | X | L | 4900234109 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W | 2024-10-23 | W |  | 0020 | Complete Replacement of Cable & TC's | INT | Complete Replacement of Cable & TC's |  | Order Requires Replanning | 90025073_0030/9027125_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000101542 | S002 | 30 | 70 | 5300016758 | 30 |  |  | 0 | 100 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 102098 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2870 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W | 30 | EA | 150 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 565 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 70 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | INLEC | 200067823 | 0020 | 0040 | 200067823 | 6Y SIF Exhaust TC Replace (18) 1KT2420 | AA53.124TE301 | TXDCR,1KT2420 TURB EXH DUCT TEMP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10034853 | TAPE,GLASS,PLAIN,12MM X 20M,HT | 10 | ROL | 14 | 0 | 19 | 10 | ROL | 29.01 - At KGP | Supply for Order 200067823, Item 4 cannot be changed 180111664 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016758 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180111664 | 9023967 | 05 | Preparation | 0000102098 | 4 | 0 | ROL | 102000000027917 |  | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-23 | GRST-5000345144_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000050172 | 1020 | 2024-07-25 | 10 |  | 2025-01-06 | 4900203665_2025_0001 | 2025-03-01 | 124TE301-318 | 5000345144_2025_0001 | 0 | 2 | 0 | 90025073 | 10 | 0 | 180111664 | 2 | 0 | 0 | X | L | 4900203665 | 2025 |  | 5000345144 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034853 | TAPE,GLASS,PLAIN,12MM X 20M,HT | 2024-10-23 | W |  | 0020 | Complete Replacement of Cable & TC's | INT | Complete Replacement of Cable & TC's |  | Order Requires Replanning | 9023967_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000101542 | S002 |  | 30 | 5300016758 | 40 |  |  | 0 | 10 | ROL | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 102098 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-02-07 | 2025-02-17 | 2025-02-13 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0060 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.02.2025) | 10035382 | CONDUIT;ELEC,THD,40X1.8MM,GLAV ST,HD | 10 | EA | 1 | 0 | 2 | 0 |  | 21.02 - ETA 14.03.25 PO 4500046920 MM CPT | Supply for Order 600001473, Item 6 cannot be changed 90030804 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020972 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030804 | 05 | Preparation | 0000084391 | 6 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-07 | ODST-0090030804_0010 | 0 | 1 | 0 | 0 |  | 2025-02-15 | AA53 | 2025-05-08 |  |  | 2025-02-18 |  |  |  |  | 2025-12-15 | 0 |  | 2025-02-13 |  | 2025-02-18 | 4V1302 |  | 0 | 2 | 0 | 90030804 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-13 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10035382 | CONDUIT;ELEC,THD,40X1.8MM,GLAV ST,HD | 2025-02-13 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90030804_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083795 | S002 | 30 | 30 | 5300020972 | 60 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-13 |  | Engineering Query/Management of Change |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84391 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2025-02-06 | 2025-02-06 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0190 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.02.2025) | 10035383 | CONDUIT;THD,ST,HD,GALV,32MM | 15 | EA | 0 | 0 | 0 | 0 |  | 09.02 - ETA 27.02.25 PO 4500045285 MCLEANS CPT | Supply for Order 600001815, Item 25 cannot be changed 90030416 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030416 | 07 | Execution | 0000084731 | 25 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 15 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030416_0020 | 0 | 5 | 0 | 0 |  | 2025-02-04 | AA53 | 2025-02-08 |  |  | 2025-02-11 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-06 |  | 2025-02-11 | 37FQI40/41 |  | 0 | 2 | 0 | 90030416 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-06 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10035383 | CONDUIT;THD,ST,HD,GALV,32MM | 2025-02-06 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030416_0020 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 25 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 200 |  |  | 0 | 15 | EA | 2001 | AA02 | 2025-02-06 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-02-06 | 2025-02-06 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0180 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.02.2025) | 10035384 | CONDUIT,25MM,THD,ST,HDG,25MM | 15 | EA | 0 | 0 | 13 | 0 |  | 09.02 - ETA 27.02.25 PO 4500045285 MCLEANS CPT | Supply for Order 600001815, Item 24 cannot be changed 90030416 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030416 | 07 | Execution | 0000084731 | 24 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 15 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030416_0010 | 0 | 5 | 0 | 0 |  | 2025-02-04 | AA53 | 2025-02-08 |  |  | 2025-02-11 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-06 |  | 2025-02-11 | 37FQI40/41 |  | 0 | 2 | 0 | 90030416 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-06 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10035384 | CONDUIT,25MM,THD,ST,HDG,25MM | 2025-02-06 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030416_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 24 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 190 |  |  | 0 | 15 | EA | 2001 | AA02 | 2025-02-06 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0040 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue detected, please check message in derivation or orchestration log | 10035440 | REDUCER,CDUIT;EX,1.25"M,1"F,RDU113231 | 10 | EA | 10 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 500005166, Item 57 cannot be changed 90032306 item 30 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 520 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 57 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0030 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Inlec Contai |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10035440 | REDUCER,CDUIT;EX,1.25"M,1"F,RDU113231 | 2025-03-03 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0030 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 57 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 520 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | ROTAT | 100036025 | 0010 | 0010 | 100036025 | Replace Quick Connect Fitting - 520HYD72 | AA53.520HYD72 | VALVE,5P2002B SUCTION | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10037479 | COUPLING,HALF;M,BSP,PARKER SM5028FBS3 | 1 | EA | 4 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 | Supply for Order 100036025, Item 1 cannot be changed 90025009 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015698 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025009 | 05 | Preparation | 0000134549 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025009_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025009 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10037479 | COUPLING,HALF;M,BSP,PARKER SM5028FBS3 | 2024-09-23 | W |  | 0010 | Replace monoblock quick connect fitting | INT | Replace monoblock quick connect fitting |  |  | 90025009_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000133880 | S002 |  | 30 | 5300015698 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134549 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0010 | 0010 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10037747 | PIPE:SML,25MM,CS,A106 GR B,SCH 80 | 6 | M | 6 | 6 | 6 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 100087299, Item 5 cannot be changed 90028581 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020055 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028581 | 05 | Preparation | 0000277133 | 5 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028581_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-12-18 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100087299 |  | 0 | 2 | 0 | 90028581 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10037747 | PIPE:SML,25MM,CS,A106 GR B,SCH 80 | 2025-01-14 | W |  | 0010 | Fabricate Spool | INT | Fabricate Spool |  | Management of Change | 90028581_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271703 | S002 | 30 | 30 | 5300020055 | 10 |  |  | 0 | 6 | M | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277133 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0040 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10037846 | PIPE,SML;50MM,LTCS,SCH40 | 3 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10037846 | PIPE,SML;50MM,LTCS,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0170 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10037846 | PIPE,SML;50MM,LTCS,SCH40 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 16 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10037846 | PIPE,SML;50MM,LTCS,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0320 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10037846 | PIPE,SML;50MM,LTCS,SCH40 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 30 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10037846 | PIPE,SML;50MM,LTCS,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
X | 25SDSTB5 | Created |  | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 100042784 | 0010 | 0030 | 100042784 | MOC-114890 N2 Rotameter Repl - 5K2001 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 1 | EA | 47 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000141305 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-12-06 | 0 |  |  |  |  | 520FI32 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  | Engineering Query/Management of Change |  |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000140674 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Created/Pre-costed/Object created/Date set by external system/Material committed/Order Approval Required | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0090 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 10 | EA | 47 | 0 | 27 | 0 |  | 17.02 - SOH @ AA02 | Supply for Order 100085072, Item 11 cannot be changed 90029953 item 60 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029953 | 05 | Preparation | 0000267773 | 11 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029953_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 2025-01-30 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029953_0060 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 |  | 30 | 5300019757 | 110 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-05-18 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0040 | 0030 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Shipped qty below requirement qty | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 8 | EA | 47 | 0 | 27 | 4 | EA | 24.02 - SOH @ AA02 | Supply for Order 600001290, Item 4 cannot be changed 180032292 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180032292 | 9004554 | 05 | Preparation | 0000084206 | 4 | 0 | EA |  |  | 102000000008603 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P08-CAMP-LRG | AA53-PO8-LN | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-02-12 | GRST-5000102817_2024 | 0 | 0 | 0 | 0 |  | 2024-05-19 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000011290 | 1020 | 2024-05-13 | 4 |  | 2024-06-06 | 4900070365_2024_0001 | 2024-05-21 |  | 5000102817_2024_0001 | 0 | 2 | 0 | 90006510 | 4 | 0 | 180032292/180101031 | 1 | 0 | 0 | X | L | 4900070365 | 2024 |  | 5000102817 | 2024 | 0 |  | 2024-05-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 2024-02-29 | W |  | 0040 | MOC-113604 Install BD 4KT1410V6A/B | INT | MOC-113604 Install BD 4KT1410V6A/B |  | Management of Change | 9004554_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDLN4 | MJ | 1000001968 | AU1072 | 1000083560 | S002 |  | 30 | 5300006479 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-05-18 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0060 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 10 | EA | 47 | 0 | 27 | 0 |  | 17.02 - SOH @ AA02 | Supply for Order 600001416, Item 6 cannot be changed 90030040 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 6 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 |  | 30 | 5300004566 | 20 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0030 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 10 | EA | 47 | 0 | 27 | 10 | EA | 24.02 - SOH @ AA02 | Supply for Order 600001416, Item 3 cannot be changed 90024964 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024964 | 05 | Preparation | 0000084298 | 3 | 0 | EA |  |  | 102000000031357 |  |  |  |  | WorkPackLink | PACKING | T23-W2 LN1-SJI | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024964_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90024964 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 2024-01-02 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024964_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 |  | 30 | 5300004566 | 10 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0100 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 20 | EA | 126 | 0 | 43 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 100085072, Item 12 cannot be changed 90029953 item 70 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029953 | 05 | Preparation | 0000267773 | 12 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029953_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 2025-01-30 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029953_0070 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 12 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 | 30 | 30 | 5300019757 | 120 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-11-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100085143 | 0020 | 0010 | 100085143 | Replace Non-Spec Inst Tube 1K2420 | AA53.124PT20A | TX,PRESS DISCHARGE 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 6 | EA | 126 | 0 | 43 | 6 | EA | 24.02 - SOH @ AA02 | Supply for Order 100085143, Item 1 cannot be changed 90028284 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018586 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028284 | 05 | Preparation | 0000267807 | 1 | 0 | EA |  |  | 102000000031723 |  |  |  |  | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028284_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124PT20A/B |  | 0 | 2 | 0 | 90028284 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 2024-11-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90028284_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000262866 | S002 | 30 | 30 | 5300018586 | 10 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267807 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0035 | 0010 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 5 | EA | 126 | 0 | 43 | 5 | EA | 29.01 - At KGP | Supply for Order 600001792, Item 4 cannot be changed 180105579 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004604 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180105579 | 9022716 | 05 | Preparation | 0000084710 | 4 | 0 | EA |  |  | 102000000027014 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-LRG | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000320192_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000047050 | 1020 | 2025-07-31 | 5 |  | 2024-12-15 | 4900191553_2024_0001 | 2025-03-01 | 118UCV112 | 5000320192_2024_0001 | 0 | 2 | 0 | 90024967 | 5 | 0 | 180105579 | 2 | 0 | 0 | X | L | 4900191553 | 2024 |  | 5000320192 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 2024-01-02 | W |  | 0035 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 9022716_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDFR1 | MJ | 1000004540 | AU1072 | 1000084094 | S002 | 30 | 30 | 5300004604 | 10 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2024-12-19 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84710 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0090 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 8 | EA | 126 | 0 | 43 | 8 | EA | 09.02 - SOH @ AA02 | Supply for Order 600001815, Item 15 cannot be changed 9027675 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180129284 | 9027675 | 07 | Execution | 0000084731 | 15 | 0 | EA | 102000000033738 |  | 107000000000114 |  |  |  | P07YRDBY28 | WorkPackLink | P07YRDBY28 | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-03-13 | GRST-5000416495_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  | 100000058595 | 1020 | 2024-08-30 | 8 |  | 2025-02-25 | 4900248427_2025_0001 | 2025-03-01 | 37PT40/41 | 5000416495_2025_0001 | 0 | 2 | 0 | 90030415 | 8 | 0 | 180129284 | 2 | 0 | 0 | X | L | 4900248427 | 2025 |  | 5000416495 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 9027675_0070 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 100 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0050 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10038447 | VALVE:NON-RTRN,0.25in,NPT,316L SS,NITRIL | 1 | EA | 1 | 0 | 0 | 1 | EA | DEL: 80031513 | Supply for Order 100085072, Item 7 cannot be changed 90029953 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029953 | 05 | Preparation | 0000267773 | 7 | 0 | EA | 101000000152142 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-08 | ODST-0090029953_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90029953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038447 | VALVE:NON-RTRN,0.25in,NPT,316L SS,NITRIL | 2025-01-30 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90029953_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 | 30 | 30 | 5300019757 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0110 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10038470 | VALVE,NDL,AGCO,15MM,6000LB,SCRD NPT | 1 | EA | 4 | 0 | 0 | 0 |  | 25.02 - SOH @ AA02 | Supply for Order 200091513, Item 613 cannot be changed 90028419 item 4170 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 613 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038470 | VALVE,NDL,AGCO,15MM,6000LB,SCRD NPT | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4170 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 613 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4200 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-04 | INLEC | 100039355 | 0020 | 0010 | 100039355 | MOC-77046 Isolation VLV Install 408LT506 | AA53.408LT506 | TX,LEVEL STARTING OIL TANK GT4008V | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10038810 | VALVE,NDL;HOKE 3812G6Y | 1 | EA | 23 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 100039355, Item 1 cannot be changed 90024948 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300001979 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024948 | 05 | Preparation | 0000137887 | 1 | 0 | EA | 102000000029229 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024948_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-11-22 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408LT506 |  | 0 | 2 | 0 | 90024948 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038810 | VALVE,NDL;HOKE 3812G6Y | 2024-01-01 | W |  | 0020 | Install Isolation Valve | INT | Install Isolation Valve | 5 |  | 90024948_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000137277 | S002 |  | 30 | 5300001979 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137887 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-10-17 | 2025-01-01 | 2024-12-27 | 2025-05-08 | 2025-05-08 | INLEC | 100044565 | 0020 | 0010 | 100044565 | MOC-151119 Press Switch Rpl (4) 4KT1410 | AA53.460PZ471A | SW,PRESS 4KT1410V5 CO2 STORAGE TNK HIHI | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(26.11.2024) | 10038826 | VALVE,BALL;0.25",6000PSIG,GYROLOCK,SS316 | 4 | EA | 12 | 0 | 8 | 4 | EA | 23.01 - SOH @ AA02 | Supply for Order 100044565, Item 2 cannot be changed 90026157 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016507 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90026157 | 05 | Preparation | 0000143069 | 2 | 0 | EA | 102000000034121 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090026157_0010 | 0 | 0 | 0 | 0 |  | 2024-12-30 | AA53 | 2025-05-08 |  |  | 2025-01-01 |  |  |  |  | 2020-11-01 | 0 |  | 2024-12-27 |  | 2025-01-01 | 4KT1410 |  | 0 | 2 | 0 | 90026157 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-12-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038826 | VALVE,BALL;0.25",6000PSIG,GYROLOCK,SS316 | 2024-11-26 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  | Engineering Query/Management of Change/Order Requires Replanning | 90026157_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000142440 | S002 | 30 | 30 | 5300016507 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-12-27 |  | Engineering Query/Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143069 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0740 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10042299 | PLUG;0.750",NPT,HEX,A105N | 1 | EA | 8 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 475 cannot be changed 90028419 item 3340 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 475 | 0 | EA | 102000000030481 | 102000000030908 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3340 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10042299 | PLUG;0.750",NPT,HEX,A105N | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3340 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 475 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 3370 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0070 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue detected, please check message in derivation or orchestration log | 10042392 | BUSH:HEX,1.000"X 0.750",NPT,SS316 | 20 | EA | 0 | 0 | 0 | 0 |  | 07.03 - ETA 03.04.25 PO 4500027944 POCHEM CPT | Supply for Order 500005166, Item 61 cannot be changed 90032306 item 60 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 61 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0060 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Inlec Contai |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10042392 | BUSH:HEX,1.000"X 0.750",NPT,SS316 | 2025-03-03 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0060 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 61 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 550 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0010 | 0020 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10043006 | ELBOW:90 DEG,25MM,BW,LR,A234-WPB,SCH 80 | 2 | EA | 2 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA01 | Supply for Order 100087299, Item 6 cannot be changed 90028581 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020055 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028581 | 05 | Preparation | 0000277133 | 6 | 0 | EA | 101000000136031 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028581_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-12-18 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100087299 |  | 0 | 2 | 0 | 90028581 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10043006 | ELBOW:90 DEG,25MM,BW,LR,A234-WPB,SCH 80 | 2025-01-14 | W |  | 0010 | Fabricate Spool | INT | Fabricate Spool |  | Management of Change | 90028581_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271703 | S002 |  |  | 5300020055 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277133 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0010 | 0050 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10043753 | TEE:RED,25 X 15MM,BW,CS,A234-WPB,SCH 80 | 1 | EA | 0 | 0 | 0 | 0 |  | 02.03 - SOH @ AA02 | Supply for Order 100087299, Item 11 cannot be changed 90028581 item 40 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020055 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028581 | 05 | Preparation | 0000277133 | 11 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028581_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-12-18 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100087299 |  | 0 | 2 | 0 | 90028581 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10043753 | TEE:RED,25 X 15MM,BW,CS,A234-WPB,SCH 80 | 2025-01-14 | W |  | 0010 | Fabricate Spool | INT | Fabricate Spool |  | Management of Change | 90028581_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271703 | S002 |  |  | 5300020055 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277133 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0050 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10044183 | ELBOW,90DEG,BW,LR,25MM,LTCS,SCH80 | 1 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10044183 | ELBOW,90DEG,BW,LR,25MM,LTCS,SCH80 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0330 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10044183 | ELBOW,90DEG,BW,LR,25MM,LTCS,SCH80 | 1 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 31 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10044183 | ELBOW,90DEG,BW,LR,25MM,LTCS,SCH80 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0080 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10044314 | REDUCER,CONC,BW,50X25MM,LTCS,40/80 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10044314 | REDUCER,CONC,BW,50X25MM,LTCS,40/80 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0350 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10044314 | REDUCER,CONC,BW,50X25MM,LTCS,40/80 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 33 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10044314 | REDUCER,CONC,BW,50X25MM,LTCS,40/80 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0210 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10044613 | REDUCER,ECC,BW,50X25MM,LTCS,SCH40/80 | 2 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 20 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10044613 | REDUCER,ECC,BW,50X25MM,LTCS,SCH40/80 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0190 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10044919 | TEE,EQUAL,BW,50MM,LTCS,A420-WPL6,SCH40 | 1 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 18 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10044919 | TEE,EQUAL,BW,50MM,LTCS,A420-WPL6,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0070 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10044919 | TEE,EQUAL,BW,50MM,LTCS,A420-WPL6,SCH40 | 1 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10044919 | TEE,EQUAL,BW,50MM,LTCS,A420-WPL6,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0200 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10045034 | TEE,RED,50 X 25MM,BW,LTCS,SCH 40/80 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 19 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10045034 | TEE,RED,50 X 25MM,BW,LTCS,SCH 40/80 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDGT7 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100034776 | 0040 | 0060 | 100034776 | MOC-145870-PV CM G4007V3 Passing Fill Va | AA53.G4007V3 | VE,CO2 LOW PRESSURE,GT4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.01.2025) | 10045499 | ELBOW,90 DEG,15MM,BW,LR,316L,SCH 40S | 1 | EA | 0 | 0 | 0 | 0 |  | 20.01 - ETA 24.02.25 PO 4500043239 PPP CPT | Supply for Order 100034776, Item 7 cannot be changed 90030057 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020137 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030057 | 05 | Preparation | 0000133257 | 7 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-17 | ODST-0090030057_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100034776 |  | 0 | 2 | 0 | 90030057 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10045499 | ELBOW,90 DEG,15MM,BW,LR,316L,SCH 40S | 2025-01-17 | W |  | 0040 | Fabricate Spool ( site inspection ) | INT | Fabricate Spool ( site inspection ) |  | Engineering Query/Management of Change | 90030057_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000132686 | S002 | 30 | 30 | 5300020137 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133257 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0030 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10045499 | ELBOW,90 DEG,15MM,BW,LR,316L,SCH 40S | 1 | EA | 0 | 0 | 0 | 0 |  | 17.12 - ETA 14.02.25 PO 4500039496 PCHEM CPT | Supply for Order 100041844, Item 5 cannot be changed 90028427 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000601 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028427 | 05 | Preparation | 0000140308 | 5 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028427_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100041844 |  | 0 | 2 | 0 | 90028427 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10045499 | ELBOW,90 DEG,15MM,BW,LR,316L,SCH 40S | 2024-12-16 | W |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change | 90028427_0030 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139679 | S002 | 30 | 30 | 5300000601 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140308 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0040 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10045504 | ELBOW,PIPE;25MM,SSTP316L,SMLS,SCH40S | 1 | EA | 1 | 0 | 0 | 1 | EA | 17.01 - SOH @ AA01 | Supply for Order 100041844, Item 6 cannot be changed 90028427 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300000601 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028427 | 05 | Preparation | 0000140308 | 6 | 0 | EA | 101000000139074 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028427_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100041844 |  | 0 | 2 | 0 | 90028427 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10045504 | ELBOW,PIPE;25MM,SSTP316L,SMLS,SCH40S | 2024-12-16 | W |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change | 90028427_0040 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139679 | S002 | 30 | 30 | 5300000601 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140308 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0050 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10045803 | REDUCER,CONC,25 X 15MM,BW,SS316L,SCH 40S | 1 | EA | 1 | 0 | 0 | 1 | EA | 20.01 - SOH @ AA01 | Supply for Order 100041844, Item 7 cannot be changed 90028427 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300000601 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028427 | 05 | Preparation | 0000140308 | 7 | 0 | EA | 101000000142892 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028427_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100041844 |  | 0 | 2 | 0 | 90028427 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10045803 | REDUCER,CONC,25 X 15MM,BW,SS316L,SCH 40S | 2024-12-16 | W |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change | 90028427_0050 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139679 | S002 |  | 30 | 5300000601 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140308 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
X | 25SDSTB5 | Created |  | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 100042784 | 0010 | 0010 | 100042784 | MOC-114890 N2 Rotameter Repl - 5K2001 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10047892 | CONNECTOR,M;316SS,0.250",GYRO 4CM4316 | 1 | EA | 72 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000141305 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-12-06 | 0 |  |  |  |  | 520FI32 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047892 | CONNECTOR,M;316SS,0.250",GYRO 4CM4316 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  | Engineering Query/Management of Change |  |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000140674 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Created/Pre-costed/Object created/Date set by external system/Material committed/Order Approval Required | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2025-03-04 | 2025-03-01 | 2025-03-04 | 2025-03-01 | 2025-03-01 | ROTAT | 100079772 | 0010 | 0010 | 100079772 | Replace Hose with Tube G4009XM1 | AA53.G4009XM1 | MOTOR,G4009 BARRING GEAR | AA01 | 30 | Issue detected, please check message in derivation or orchestration log | 10047892 | CONNECTOR,M;316SS,0.250",GYRO 4CM4316 | 2 | EA | 72 | 0 | 70 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100079772, Item 1 cannot be changed 90032194 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022016 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032194 | 05 | Preparation | 0000246944 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032194_0010 | 0 | 8 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-09 |  |  |  |  | 2025-06-27 | 0 |  | 2025-03-04 |  | 2025-03-09 |  |  | 0 | 2 | 0 | 90032194 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047892 | CONNECTOR,M;316SS,0.250",GYRO 4CM4316 | 2025-03-04 | W |  | 0010 | Replace Flexi Hose with hard tubing | INT | Replace Flexi Hose with hard tubing |  |  | 90032194_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000243502 | S002 | 30 | 30 | 5300022016 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246944 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-04-05 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0060 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.03.2024) | 10047892 | CONNECTOR,M;316SS,0.250",GYRO 4CM4316 | 4 | EA | 72 | 0 | 70 | 4 | EA | 02.10 - At KGP | Supply for Order 600001290, Item 9 cannot be changed 180029563 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180029563 | 9004207 | 05 | Preparation | 0000084206 | 9 | 0 | EA | 102000000006931 | 102000000007205 | 102000000007333 |  |  |  | LP-NWS-01 | WorkPackLink | P08YRDBAY6 | AA53-P08-LN | 0 |  | 0 | 0 |  | 4 | 0 |  |  | Y | 1001 | 2024-02-12 |  | 0 | 0 | 0 | 0 |  | 2024-04-06 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000013638 | 1020 | 2024-05-13 | 4 |  | 2024-06-19 | 4900076368_2024_0003/4900076235_2024_0003/4900066729_2024_0003 | 2024-04-08 |  | 5000122775_2024_0002 | 0 | 2 | 0 | 90006964 | 4 | 0 | 180029563/180099822 | 2 | 0 | 0 | X | L | 4900076368 | 2024 |  | 5000122775 | 2024 | 0 |  | 2024-04-05 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047892 | CONNECTOR,M;316SS,0.250",GYRO 4CM4316 | 2024-03-25 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9004207_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083560 | S002 | 30 | 30 | 5300006479 | 70 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-04-05 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SD4401 | Released | 2024-11-05 | 2024-12-01 | 2024-11-26 | 2025-03-01 | 2025-03-02 | INLEC | 100039665 | 0010 | 0030 | 100039665 | MOC-141049 Pressure TX Replace 144PT504 | AA53.144PT504 | TX,PRESS K4401A LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2 | EA | 113 | 76 | 83 | 2 | EA | 19.02 - At KGP | Supply for Order 100039665, Item 15 cannot be changed 90023592 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017367 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122922 | 9027007 | 05 | Preparation | 0000138169 | 15 | 0 | EA | 102000000025836 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000391237_2025 | 0 | 0 | 0 | 0 |  | 2024-11-29 | AA53 | 2025-03-01 |  |  | 2024-12-01 |  |  | 100000056804 | 1020 | 2024-03-07 | 2 |  | 2025-02-07 | 4900229998_2025_0001 | 2024-12-01 | 144PT504 | 5000391237_2025_0001 | 0 | 2 | 0 | 90023592 | 2 | 0 | 180122922/180122921 | 2 | 0 | 0 | X | L | 4900229998 | 2025 |  | 5000391237 | 2025 | 0 |  | 2024-11-26 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2024-11-05 | W |  | 0010 | TX Pre Works | INT | TX Pre Works |  | Management of Change | 9027007_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 15 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137540 | S002 | 30 | 30 | 5300017367 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-11-26 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138169 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039666 | 0020 | 0050 | 100039666 | MOC 113249 - EEHA Tx Replace 144PT60 | AA53.144PT60 | TX,PRESS K4401A DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2 | EA | 113 | 76 | 83 | 2 | EA | 19.02 - At KGP | Supply for Order 100039666, Item 4 cannot be changed 90024949 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002037 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122880 | 9026892 | 05 | Preparation | 0000138170 | 4 | 0 | EA | 102000000030039 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391253_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056486 | 1020 | 2024-03-07 | 2 |  | 2025-02-07 | 4900230015_2025_0003 | 2025-03-01 | 144PT60 | 5000391253_2025_0002 | 0 | 2 | 0 | 90024949 | 2 | 0 | 180122911/180122880 | 2 | 0 | 0 | X | L | 4900230015 | 2025 |  | 5000391253 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026892_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137581 | S002 | 30 | 30 | 5300002037 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138170 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039671 | 0020 | 0040 | 100039671 | MOC 113250 - EEHA Tx Replace 244PT60 | AA53.244PT60 | TX,PRESS K4401B DISCHARGE | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2 | EA | 113 | 76 | 83 | 2 | EA | 19.02 - At KGP | Supply for Order 100039671, Item 4 cannot be changed 9026894 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002039 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122884 | 9026894 | 05 | Preparation | 0000138175 | 4 | 0 | EA | 102000000030043 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391239_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056488 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900230007_2025_0005 | 2025-03-01 | 244PT60 | 5000391239_2025_0003 | 0 | 2 | 0 | 90024950 | 2 | 0 | 180122884 | 2 | 0 | 0 | X | L | 4900230007 | 2025 |  | 5000391239 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query/Management of Change | 9026894_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137586 | S002 | 30 | 30 | 5300002039 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138175 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Part printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039740 | 0020 | 0040 | 100039740 | MOC 113252 - EEHA Tx Replace 344PT501 | AA53.344PT501 | TX,PRESS K4401C-P2A/B LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2 | EA | 113 | 76 | 83 | 2 | EA | 19.02 - At KGP | Supply for Order 100039740, Item 4 cannot be changed 9026895 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002053 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122885 | 9026895 | 05 | Preparation | 0000138264 | 4 | 0 | EA | 102000000030042 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391238_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056489 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900229989_2025_0003 | 2025-03-01 | 344PT501 | 5000391238_2025_0002 | 0 | 2 | 0 | 90024951 | 2 | 0 | 180122920/180122885 | 2 | 0 | 0 | X | L | 4900229989 | 2025 |  | 5000391238 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2024-01-01 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 9026895_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137595 | S002 | 30 | 30 | 5300002053 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138264 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-02-26 | 2025-03-01 | INLEC | 100039741 | 0010 | 0060 | 100039741 | MOC 113253 - EEHA Tx Replace 344PT504 | AA53.344PT504 | TX,PRESS K4401C LUBE OIL HEADER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2 | EA | 113 | 76 | 83 | 2 | EA | 19.02 - At KGP | Supply for Order 100039741, Item 4 cannot be changed 9026898 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002054 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122893 | 9026898 | 05 | Preparation | 0000138265 | 4 | 0 | EA | 102000000030040 |  | 107000000000791 |  |  |  |  | WorkPackLink | P07-INLEC ROOM | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000391263_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056492 | 1020 | 2024-03-08 | 2 |  | 2025-02-07 | 4900230033_2025_0003 | 2025-03-01 | 344PT504 | 5000391263_2025_0002 | 0 | 2 | 0 | 90024952 | 2 | 0 | 180122893 | 2 | 0 | 0 | X | L | 4900230033 | 2025 |  | 5000391263 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Management of Change | 9026898_0040 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000137596 | S002 | 30 | 30 | 5300002054 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138265 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-02-26 | 2025-02-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0035 | 0030 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 5 | EA | 113 | 76 | 83 | 5 | EA | 23.01 - SOH @ AA02 | Supply for Order 600001792, Item 6 cannot be changed 90024967 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004604 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024967 | 05 | Preparation | 0000084710 | 6 | 0 | EA | 102000000032121 | 102000000030041 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024967_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118UCV112 |  | 0 | 2 | 0 | 90024967 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2024-01-02 | W |  | 0035 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90024967_0030 |  |  | FR1 |  | C3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000084094 | S002 | 30 | 30 | 5300004604 | 30 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84710 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0110 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10047900 | CONNECTOR,TUBE;M COMP,0.375"X0.50",NPT | 20 | EA | 7 | 24 | 0 | 7 | EA | 18.02 - SOH @ AA01 | Supply for Order 600001815, Item 17 cannot be changed 90030415 item 90 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180126078 | 9027608 | 07 | Execution | 0000084731 | 17 | 0 | EA |  |  | 102000000033933 |  |  |  |  | WorkPackLink | SW3R02B02A | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-03-13 | IDST-0180126078 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  | 100000057701 | 1020 | 2024-08-30 | 12 |  | 2025-02-17 | 4900239182_2025_0001 | 2025-03-01 | 37PT40/41 |  | 0 | 2 | 0 | 90030415 | 0 | 0 | 180126078 | 2 | 0 | 0 | X | L | 4900239182 | 2025 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047900 | CONNECTOR,TUBE;M COMP,0.375"X0.50",NPT | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030415_0090/9027608_0090 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 17 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 120 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0110 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10047900 | CONNECTOR,TUBE;M COMP,0.375"X0.50",NPT | 20 | EA | 7 | 24 | 0 | 12 | EA | 18.02 - SOH @ AA01 | Supply for Order 600001815, Item 17 cannot be changed 90030415 item 90 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180126078 | 9027608 | 07 | Execution | 0000084731 | 17 | 0 | EA |  |  | 102000000033070 |  |  |  |  | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-03-13 | IDST-0180126078 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  | 100000057701 | 1020 | 2024-08-30 | 12 |  | 2025-02-17 | 4900239182_2025_0001 | 2025-03-01 | 37PT40/41 |  | 0 | 2 | 0 | 90030415 | 0 | 0 | 180126078 | 2 | 0 | 0 | X | L | 4900239182 | 2025 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047900 | CONNECTOR,TUBE;M COMP,0.375"X0.50",NPT | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030415_0090/9027608_0090 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 17 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 120 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0100 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10047920 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 20 | EA | 0 | 0 | 0 | 0 |  | 25.02 - SOH @ AA01 | Supply for Order 600001815, Item 16 cannot be changed 90030415 item 80 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030415 | 07 | Execution | 0000084731 | 16 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030415_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 37PT40/41 |  | 0 | 2 | 0 | 90030415 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047920 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030415_0080 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 16 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 |  | 30 | 5300007843 | 110 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDGT9 | Released | 2025-03-04 | 2025-03-01 | 2025-03-04 | 2025-03-01 | 2025-03-01 | ROTAT | 100079772 | 0010 | 0020 | 100079772 | Replace Hose with Tube G4009XM1 | AA53.G4009XM1 | MOTOR,G4009 BARRING GEAR | AA01 | 30 | Issue detected, please check message in derivation or orchestration log | 10047929 | CONNECTOR,TBG;0.25",NPTF X COMP,SS | 2 | EA | 4 | 0 | 12 | 0 |  | DEL: 80033378 | Supply for Order 100079772, Item 2 cannot be changed 90032194 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022016 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032194 | 05 | Preparation | 0000246944 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032194_0020 | 0 | 8 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-09 |  |  |  |  | 2025-06-27 | 0 |  | 2025-03-04 |  | 2025-03-09 |  |  | 0 | 2 | 0 | 90032194 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047929 | CONNECTOR,TBG;0.25",NPTF X COMP,SS | 2025-03-04 | W |  | 0010 | Replace Flexi Hose with hard tubing | INT | Replace Flexi Hose with hard tubing |  |  | 90032194_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000243502 | S002 | 30 | 30 | 5300022016 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246944 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-04-05 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0050 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.03.2024) | 10047929 | CONNECTOR,TBG;0.25",NPTF X COMP,SS | 4 | EA | 4 | 0 | 12 | 4 | EA | 02.10 - At KGP | Supply for Order 600001290, Item 8 cannot be changed 180029563 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180029563 | 9004207 | 05 | Preparation | 0000084206 | 8 | 0 | EA | 102000000006931 | 102000000007114 | 102000000007333 |  |  |  | LP-NWS-01 | WorkPackLink | P08YRDBAY6 | AA53-P08-LN | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-12 | GRST-5000122775_2024 | 0 | 0 | 0 | 0 |  | 2024-04-06 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000013638 | 1020 | 2024-05-13 | 4 |  | 2024-06-19 | 4900076368_2024_0001/4900076235_2024_0001/4900066729_2024_0001 | 2024-04-08 |  | 5000122775_2024_0001 | 0 | 2 | 0 | 90006964 | 4 | 0 | 180029563/180099822 | 2 | 0 | 0 | X | L | 4900076368 | 2024 |  | 5000122775 | 2024 | 0 |  | 2024-04-05 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047929 | CONNECTOR,TBG;0.25",NPTF X COMP,SS | 2024-03-25 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9004207_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083560 | S002 | 30 | 30 | 5300006479 | 60 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-04-05 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
X | 25SDSTB5 | Created |  | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 100042784 | 0010 | 0020 | 100042784 | MOC-114890 N2 Rotameter Repl - 5K2001 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10047970 | ELBOW,0.25X0.25",NPT,90DEG,COMP/M,SS | 1 | EA | 60 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000141305 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-12-06 | 0 |  |  |  |  | 520FI32 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047970 | ELBOW,0.25X0.25",NPT,90DEG,COMP/M,SS |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  | Engineering Query/Management of Change |  |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000140674 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Created/Pre-costed/Object created/Date set by external system/Material committed/Order Approval Required | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0080 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10048024 | NUT & FERRULE,TUBE,0.250"OD,SCNF,SS316 | 6 | SET | 14 | 0 | 0 | 6 | SET | 28.01 - qty 22 SOH @ AA02 | Supply for Order 600001416, Item 8 cannot be changed 90030040 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 8 | 0 | SET | 102000000034125 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048024 | NUT & FERRULE,TUBE,0.250"OD,SCNF,SS316 | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0030 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 |  | 30 | 5300004566 | 40 |  |  | 0 | 6 | SET | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
X | 25SDSTB5 | Created |  | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 100042784 | 0010 | 0040 | 100042784 | MOC-114890 N2 Rotameter Repl - 5K2001 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10048154 | UNION,COMP,STR;PROCHEM 4U316 | 1 | EA | 66 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000141305 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-12-06 | 0 |  |  |  |  | 520FI32 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048154 | UNION,COMP,STR;PROCHEM 4U316 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  | Engineering Query/Management of Change |  |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000140674 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Created/Pre-costed/Object created/Date set by external system/Material committed/Order Approval Required | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0035 | 0020 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10048155 | UNION,COMP,STR;GYRO 6U316 | 5 | EA | 38 | 12 | 71 | 5 | EA | 23.01 - SOH @ AA02 | Supply for Order 600001792, Item 5 cannot be changed 90024967 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004604 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024967 | 05 | Preparation | 0000084710 | 5 | 0 | EA | 102000000032121 | 102000000030038 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024967_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118UCV112 |  | 0 | 2 | 0 | 90024967 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048155 | UNION,COMP,STR;GYRO 6U316 | 2024-01-02 | W |  | 0035 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90024967_0020 |  |  | FR1 |  | C3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000084094 | S002 | 30 | 30 | 5300004604 | 20 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84710 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0140 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10048155 | UNION,COMP,STR;GYRO 6U316 | 20 | EA | 38 | 12 | 71 | 20 | EA | 09.02 - SOH @ AA02 | Supply for Order 600001815, Item 20 cannot be changed 90030415 item 120 already exists | Material picked; currently at SW3R02B02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030415 | 07 | Execution | 0000084731 | 20 | 0 | EA |  |  | 102000000033914 |  |  |  |  | WorkPackLink | SW3R02B02A | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030415_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 37PT40/41 |  | 0 | 2 | 0 | 90030415 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048155 | UNION,COMP,STR;GYRO 6U316 | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030415_0120 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 20 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 150 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100032677 | 0020 | 0080 | 100032677 | CV-OH 3" 300# 118TCV501 | AA53.118TCV501 | VALVE,1K1820E1 L/O COOL BYPASS TEMP CTRL | AA01 | 20 | WO item has not been released yet | 10048526 | FLANGE,BLIND;80MM,CL300,RF,LTCS | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131169 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032677 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048526 | FLANGE,BLIND;80MM,CL300,RF,LTCS |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130519 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-05-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100047394 | 0030 | 0050 | 100047394 | CV-OH 1" 600# 124PCV54 | AA53.124PCV54 | VALVE,CONT SEAL OIL BACK PRESS 1K2420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(19.09.2024) | 10048539 | FLANGE,BLIND;25MM,CL600,RF,LTCS | 2 | EA | 0 | 0 | 2 | 2 | EA | 29.01 - At KGP | Supply for Order 100047394, Item 7 cannot be changed 90024986 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300011592 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117452 | 9026017 | 07 | Execution | 0000145926 | 7 | 0 | EA | 102000000030526 | 101000000134376 | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-06-14 | GRST-5000369214_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000054483 | 1020 | 2018-10-31 | 2 |  | 2025-01-22 | 4900216400_2025_0001 | 2025-03-01 | 100047394 | 5000369214_2025_0001 | 0 | 2 | 0 | 90024986 | 2 | 0 | 180117452 | 2 | 0 | 0 | X | L | 4900216400 | 2025 |  | 5000369214 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048539 | FLANGE,BLIND;25MM,CL600,RF,LTCS | 2024-09-19 | W |  | 0030 | Remove Valve 124PCV54 & Fit Blinds | INT | Remove Valve 124PCV54 & Fit Blinds | 5 |  | 9026017_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000145296 | S002 | 30 | 30 | 5300011592 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2024-05-23 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145926 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material shortage/Printed/Partially confirmed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-05-13 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0010 | 0060 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10048748 | FLANGE,WN;15MM,CL300,RF,A105N,SCH 80 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 100087299, Item 14 cannot be changed 90028582 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020055 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028582 | 05 | Preparation | 0000277133 | 14 | 0 | EA | 102000000031658 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028582_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-05-13 |  |  |  |  | 2026-12-18 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100087299 |  | 0 | 2 | 0 | 90028582 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048748 | FLANGE,WN;15MM,CL300,RF,A105N,SCH 80 | 2025-01-14 | W |  | 0010 | Fabricate Spool | INT | Fabricate Spool |  | Management of Change | 90028582_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 14 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271703 | S002 | 30 | 30 | 5300020055 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277133 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0010 | 0040 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10048750 | FLANGE,WN;25MM,CL300,RF,A105N,SCH 80 | 2 | EA | 2 | 0 | 0 | 2 | EA | 25.02 - SOH @ AA02 | Supply for Order 100087299, Item 8 cannot be changed 90028581 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020055 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028581 | 05 | Preparation | 0000277133 | 8 | 0 | EA | 101000000148353 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028581_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-12-18 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100087299 |  | 0 | 2 | 0 | 90028581 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048750 | FLANGE,WN;25MM,CL300,RF,A105N,SCH 80 | 2025-01-14 | W |  | 0010 | Fabricate Spool | INT | Fabricate Spool |  | Management of Change | 90028581_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271703 | S002 | 30 | 30 | 5300020055 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277133 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0090 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10048910 | FLANGE,WN,50MM,CL150,RF,LTCS,SCH 160 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048910 | FLANGE,WN,50MM,CL150,RF,LTCS,SCH 160 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0370 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10048922 | FLANGE,WN;50MM,CL300,RF,LTCSLF2C1,SCH40 | 3 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 35 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048922 | FLANGE,WN;50MM,CL300,RF,LTCSLF2C1,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0100 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10048922 | FLANGE,WN;50MM,CL300,RF,LTCSLF2C1,SCH40 | 8 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 9 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048922 | FLANGE,WN;50MM,CL300,RF,LTCSLF2C1,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0230 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10048922 | FLANGE,WN;50MM,CL300,RF,LTCSLF2C1,SCH40 | 9 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 22 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048922 | FLANGE,WN;50MM,CL300,RF,LTCSLF2C1,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0220 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10048934 | FLANGE,WN;25MM,CL300,RF,LTCS,SCH 80 | 3 | EA | 10 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 21 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048934 | FLANGE,WN;25MM,CL300,RF,LTCS,SCH 80 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0360 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10048950 | FLANGE,WN;25MM,CL600,RF,LTCS,SCH 80 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 34 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048950 | FLANGE,WN;25MM,CL600,RF,LTCS,SCH 80 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDFLR | Released | 2024-01-24 | 2025-04-30 |  | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0140 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | WO item has not been released yet | 10049269 | FLANGE,BLIND;25MM,CL150,RF,SS316 | 6 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000084653 | 20 | 0 | [8 empty] | WorkPackLink |  | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  |  |  |  | 600001757 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049269 | FLANGE,BLIND;25MM,CL150,RF,SS316 |  |  |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning |  |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDFLR | MJ |  |  | 1000084067 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
1 | 25SDFLR | Released | 2024-01-24 | 2025-04-30 |  | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0150 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | WO item has not been released yet | 10049270 | FLANGE,BLIND;40MM,CL150,RF,SS316 | 6 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000084653 | 21 | 0 | [8 empty] | WorkPackLink |  | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  |  |  |  | 600001757 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049270 | FLANGE,BLIND;40MM,CL150,RF,SS316 |  |  |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning |  |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDFLR | MJ |  |  | 1000084067 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2025-04-30 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0030 | 0020 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.12.2024) | 10049272 | FLG:BLIND,80MM,CL150,RF,SS316 | 4 | EA | 4 | 0 | 1 | 4 | EA | 23.01 - SOH @ AA02 | Supply for Order 600001815, Item 5 cannot be changed 90028267 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028267 | 07 | Execution | 0000084731 | 5 | 0 | EA | 101000000133529 |  | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-03-13 | ODST-0090028267_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 37FQI40/41 |  | 0 | 2 | 0 | 90028267 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049272 | FLG:BLIND,80MM,CL150,RF,SS316 | 2024-12-10 | W |  | 0030 | Provision of Flow Computers (MOC-119247) | ESRV | Provision of Flow Computers (MOC-119247) |  |  | 90028267_0010 |  |  | SL0 |  | C2 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0490 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10049276 | FLANGE,BLIND;250MM,CL150,RF,SS316 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 49 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049276 | FLANGE,BLIND;250MM,CL150,RF,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-02-28 | 2025-03-01 | VALVE | 100032675 | 0020 | 0080 | 100032675 | CV-OH 1" 300# 118PCV505 | AA53.118PCV505 | VALVE,1K1820 BUFFER GAS SUPPL PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10049287 | FLANGE,BLIND;25MM,CL300,RF,SS316 | 2 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131167 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032675 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049287 | FLANGE,BLIND;25MM,CL300,RF,SS316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130517 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR0 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | MECH | 100044226 | 0060 | 0030 | 100044226 | Offline Repair - P18032 HPV | AA53.EPFRAC6 | PIPE,ZONE FRAC TRAIN 3 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(14.11.2024) | 10049287 | FLANGE,BLIND;25MM,CL300,RF,SS316 | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 100044226, Item 3 cannot be changed 90025112 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017899 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025112 | 05 | Preparation | 0000142678 | 3 | 0 | EA | 102000000030521 | 101000000134377 | 102000000032105 |  |  |  |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025112_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-12-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100044226 |  | 0 | 2 | 0 | 90025112 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049287 | FLANGE,BLIND;25MM,CL300,RF,SS316 | 2024-11-14 | W |  | 0060 | Replace HPV Fittings (Bolt up scope) | INT | Replace HPV Fittings (Bolt up scope) |  |  | 90025112_0010 |  |  | FR3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000142148 | S002 | 30 | 30 | 5300017899 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142678 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0470 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10049291 | FLANGE,BLIND;100MM,CL300,RF,SS316 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 47 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049291 | FLANGE,BLIND;100MM,CL300,RF,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0480 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10049314 | FLANGE,BLIND;250MM,CL600,RF,SS316 | 4 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 48 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049314 | FLANGE,BLIND;250MM,CL600,RF,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0460 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10049315 | FLANGE,BLIND;300MM,CL600,RF,SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 46 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049315 | FLANGE,BLIND;300MM,CL600,RF,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0510 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10049320 | FLANGE,BLIND;600MM,CL600,RF,SS316 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 51 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 | [7 empty] | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049320 | FLANGE,BLIND;600MM,CL600,RF,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100034776 | 0040 | 0020 | 100034776 | MOC-145870-PV CM G4007V3 Passing Fill Va | AA53.G4007V3 | VE,CO2 LOW PRESSURE,GT4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.01.2025) | 10049455 | FLANGE,WN,15MM,CL300,RF,SS316L,SCH 40S | 3 | EA | 4 | 0 | 0 | 3 | EA | 19.02 - SOH @ AA02 | Supply for Order 100034776, Item 3 cannot be changed 90030057 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020137 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030057 | 05 | Preparation | 0000133257 | 3 | 0 | EA | 101000000143243 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2025-01-17 | ODST-0090030057_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100034776 |  | 0 | 2 | 0 | 90030057 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049455 | FLANGE,WN,15MM,CL300,RF,SS316L,SCH 40S | 2025-01-17 | W |  | 0040 | Fabricate Spool ( site inspection ) | INT | Fabricate Spool ( site inspection ) |  | Engineering Query/Management of Change | 90030057_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000132686 | S002 |  | 30 | 5300020137 | 20 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133257 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0060 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10049455 | FLANGE,WN,15MM,CL300,RF,SS316L,SCH 40S | 1 | EA | 4 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 100041844, Item 8 cannot be changed 90028427 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300000601 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028427 | 05 | Preparation | 0000140308 | 8 | 0 | EA | 101000000141983 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028427_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100041844 |  | 0 | 2 | 0 | 90028427 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049455 | FLANGE,WN,15MM,CL300,RF,SS316L,SCH 40S | 2024-12-16 | W |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change | 90028427_0060 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139679 | S002 |  | 30 | 5300000601 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140308 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0070 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10049521 | FLANGE,WN;25MM,CL600,RF,SSTP316L,SCH40S | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 100041844, Item 9 cannot be changed 90028427 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300000601 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028427 | 05 | Preparation | 0000140308 | 9 | 0 | EA | 101000000143588 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028427_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100041844 |  | 0 | 2 | 0 | 90028427 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049521 | FLANGE,WN;25MM,CL600,RF,SSTP316L,SCH40S | 2024-12-16 | W |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change | 90028427_0070 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139679 | S002 |  | 30 | 5300000601 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140308 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0520 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10053032 | SPADE BLIND:250MM,CL150,SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 52 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 | [7 empty] | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10053032 | SPADE BLIND:250MM,CL150,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0440 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10053051 | SPADE BLIND;300MM,CL600,SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 44 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 | [7 empty] | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10053051 | SPADE BLIND;300MM,CL600,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-01 | 2024-03-31 | 2024-03-28 | 2025-03-02 | 2025-05-09 | INLEC | 100035833 | 0020 | 0030 | 100035833 | OPSD - Replace 414FV055A/65A feedback ar | AA53.414FV055A | VALVE,FLOW CTRL GT1420A HVY MR TO E1450A | AA01 | 20 | Del to Maintenance after Reqmt Date | 10054068 | VALVE,BALL;2000PSI,FB,PROCHEM 7510F8YRH+ | 2 | EA | 0 | 0 | 6 | 2 | EA | 10.03 - AT AA53 | Supply for Order 100035833, Item 3 cannot be changed 180014652 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300007533 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180014652 | 9001419 | 07 | Execution | 0000134354 | 3 | 0 | EA |  |  | 102000000003934 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-KGP-RUNNER-SML | P19 FL INLEC | 0 |  | 0 | 0 |  | 2 | 0 | 2024-04-09 |  | Y | 1001 | 2024-03-06 |  | 0 | 0 | 0 | 0 |  | 2024-03-29 | AA53 | 2025-03-02 |  |  | 2024-03-31 |  |  | 100000005175 | 1020 | 2023-12-30 | 2 |  | 2024-04-01 | 4900041857_2024_0001 | 2024-03-31 |  | 5000048901_2024_0001 | 0 | 2 | 0 | 90004428 | 2 | 0 | 180014652/180083312 | 1 | 0 | 0 | X | L | 4900041857 | 2024 |  | 5000048901 | 2024 | 0 |  | 2024-03-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10054068 | VALVE,BALL;2000PSI,FB,PROCHEM 7510F8YRH+ | 2024-03-06 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 | Opportune Shutdown | 9001419_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ | 1000001159 | AU1072 | 1000133783 | S002 | 30 | 30 | 5300007533 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-03-28 |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134354 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-09 | 2025-03-02 | 2025-03-02 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Goods movement posted/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-10-22 | 2025-05-01 | 2025-04-26 | 2025-03-01 | 2025-05-15 | VALVE | 100045269 | 0015 | 0010 | 100045269 | Replace Pressure Gauge - 118PG11 | AA53.118PG11 | GAUGE,PRESS E1801 DE-ETH REBOILER | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(22.10.2024) | 10055197 | VALVE,GATE,15MM,CL600,RF,SS,S6GE | 1 | EA | 4 | 0 | 0 | 1 | EA | 23.10 - SOH @ AA02 | Supply for Order 100045269, Item 2 cannot be changed 90025072 item 10 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016694 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025072 | 05 | Preparation | 0000143781 | 2 | 0 | EA | 102000000027653 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-22 | ODST-0090025072_0010 | 0 | 0 | 0 | 0 |  | 2025-04-29 | AA53 | 2025-03-01 |  |  | 2025-05-01 |  |  |  |  | 2021-04-04 | 0 |  | 2025-04-26 |  | 2025-05-01 | 100045269 |  | 0 | 2 | 0 | 90025072 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-04-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10055197 | VALVE,GATE,15MM,CL600,RF,SS,S6GE | 2024-10-22 | W |  | 0015 | Remove & Replace Valve > | INT | Remove & Replace Valve > |  |  | 90025072_0010 |  |  | FR1 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000143151 | S002 |  | 30 | 5300016694 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-04-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143781 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-08-08 | 2025-03-01 | 2025-02-03 | 2025-03-01 | 2025-03-01 | VALVE | 100031838 | 0010 | 0020 | 100031838 | MV-RE 6" 600# 520GAV1667 | AA53.520HCV10A | VALVE,COMP O/H VAP TO DOMGAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.08.2024) | 10055204 | VALVE,GATE,150MM,CL600,RF,SS,S6GE | 1 | EA | 1 | 0 | 1 | 0 |  | 06.01 - ETA 28.03.25 PO 4500028998 SCORE FCA | Supply for Order 100031838, Item 2 cannot be changed – 4500028998 already exists | Vendor PO raised | SP97 | Direct Multi-base | 266 | AA01 | 5300013747 | 10 | FCA | 7 | 1000016811 | 2 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500028998 | 10 | 1 | EA | 2025-03-28 |  |  |  | 90028400 | 05 | Preparation | 0000130239 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-08 | ODST-0090028400_0010 | 0 | 96 | 96 | 96 | 2025-05-08 | 2025-02-06 | AA53 | 2025-03-01 |  |  | 2025-05-18 | 2025-05-10 | 2025-05-15 |  |  | 2024-05-05 | 0 |  | 2025-02-03 |  | 2025-02-08 | 100031838 |  | 0 | 2 | 2 | 90028400 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10055204 | VALVE,GATE,150MM,CL600,RF,SS,S6GE | 2024-08-08 | W |  | 0010 | Remove & Replace Valve | INT | Remove & Replace Valve |  |  | 90028400_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-08-08 | 20 | 6000008117 | 2025-05-10 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000129668 | S001 | 30 | 30 | 5300013746 | 10 |  | 5300013747 | 10 | 1 | EA | 1001 | AA02 | 2025-02-03 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-01-02 | 2025-01-01 | 2024-12-27 | 2025-03-01 | 2025-05-16 | INLEC | 600001530 | 0010 | 0090 | 600001530 | MOC-107654/88803 Pre SD Scope 118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10057741 | CLAMP,BEAM;C,50X63MM,M12,316SS | 20 | EA | 0 | 0 | 20 | 20 | EA | 29.01 - At KGP | Supply for Order 600001530, Item 5 cannot be changed 180101078 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300004570 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180101078 | 9021459 | 05 | Preparation | 0000084445 | 5 | 0 | EA | 101000000116112 |  | 107000000000750 |  |  |  |  | WorkPackLink | P07-WAREHOUSE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000306426_2024 | 0 | 0 | 0 | 0 |  | 2024-12-30 | AA53 | 2025-03-01 |  |  | 2025-01-01 |  |  | 100000044900 | 1020 | 2025-07-31 | 20 |  | 2024-12-04 | 4900185201_2024_0001 | 2025-01-01 | 118UCV112 | 5000306426_2024_0001 | 0 | 2 | 0 | 90024965 | 20 | 0 | 180101078 | 2 | 0 | 0 | X | L | 4900185201 | 2024 |  | 5000306426 | 2024 | 0 |  | 2024-12-27 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10057741 | CLAMP,BEAM;C,50X63MM,M12,316SS | 2024-09-30 | W |  | 0010 | MOC-88803 Frac 1 Pre Works | INT | MOC-88803 Frac 1 Pre Works | 0 |  | 9021459_0030 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000083862 | S002 | 30 | 30 | 5300004570 | 40 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-12-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84445 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM06 | Capital
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0130 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10057805 | WIRE,SS316,RND,ANNEALED,20SWG (0.9MM) | 1 | ROL | 5 | 0 | 1 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 33 cannot be changed 90031501 item 150 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 33 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0150 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10057805 | WIRE,SS316,RND,ANNEALED,20SWG (0.9MM) | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0150 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 33 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 290 |  |  | 0 | 1 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0050 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10057848 | ROPE,FIB;SISAL,3STR,PLN LAID,RHL,12MM | 2 | CX | 1 | 1 | 1 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500004676, Item 5 cannot be changed 90031855 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | CX |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 5 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0050 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10057848 | ROPE,FIB;SISAL,3STR,PLN LAID,RHL,12MM | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0050 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 50 |  |  | 0 | 2 | CX | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 3 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0100 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10058017 | BOLT ASY;HEX HD,M6X65MM,SS316,A4-80,NUT | 1 | EA | 0 | 0 | 0 | 0 |  | 20.02 - SOH @ AA01 | Supply for Order 600001416, Item 10 cannot be changed 90030040 item 50 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 10 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058017 | BOLT ASY;HEX HD,M6X65MM,SS316,A4-80,NUT | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0050 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 | 30 | 30 | 5300004566 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0120 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10058032 | BOLT;HEX HD,M10X30MM,A480,ISO 3506,W/NUT | 1 | BOX | 5 | 0 | 0 | 1 | BOX | 27.01 - SOH @ AA02 | Supply for Order 600001416, Item 12 cannot be changed 90030040 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 12 | 0 | BOX | 102000000033975 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058032 | BOLT;HEX HD,M10X30MM,A480,ISO 3506,W/NUT | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0070 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 12 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 | 30 | 30 | 5300004566 | 80 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0130 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10058038 | BOLT ASY;HEX HD,M10X65MM,SS316,A4-80,NUT | 1 | EA | 1 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 | Supply for Order 600001416, Item 13 cannot be changed 90030040 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 13 | 0 | EA | 101000000143778 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058038 | BOLT ASY;HEX HD,M10X65MM,SS316,A4-80,NUT | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0080 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 13 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 | 30 | 30 | 5300004566 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2410 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10058147 | BOLT;HEX HD,0.625" X 45MM,GR 8,11UNC | 12 | EA | 13 | 0 | 0 | 12 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 353 cannot be changed 90028419 item 2730 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 353 | 0 | EA | 102000000030495 | 102000000030825 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058147 | BOLT;HEX HD,0.625" X 45MM,GR 8,11UNC | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2730 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 353 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2760 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2540 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10058150 | BOLT,HEX;0.375"X20MM,CS,GDE 5,16UNC | 52 | EA | 360 | 0 | 0 | 52 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 716 cannot be changed 90028419 item 4790 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 716 | 0 | EA | 102000000030499 | 102000000030252 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 52 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4790 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058150 | BOLT,HEX;0.375"X20MM,CS,GDE 5,16UNC | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_4790 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 716 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4830 |  |  | 0 | 52 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1970 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10058150 | BOLT,HEX;0.375"X20MM,CS,GDE 5,16UNC | 20 | EA | 360 | 0 | 0 | 20 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 518 cannot be changed 90028419 item 3730 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 518 | 0 | EA | 102000000030389 | 102000000030251 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058150 | BOLT,HEX;0.375"X20MM,CS,GDE 5,16UNC | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_3730 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 518 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3760 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1990 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10058151 | BOLT,HEX;0.250"X12MM,10.9,20UNC | 2 | EA | 29 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 702 cannot be changed 90028419 item 4670 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4710 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 702 | 0 | EA | 102000000030389 | 102000000030831 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058151 | BOLT,HEX;0.250"X12MM,10.9,20UNC | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_4670 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 702 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4710 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1310 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10058151 | BOLT,HEX;0.250"X12MM,10.9,20UNC | 18 | EA | 29 | 0 | 0 | 18 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 154 cannot be changed 90028419 item 1180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 154 | 0 | EA | 102000000030480 | 102000000030829 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058151 | BOLT,HEX;0.250"X12MM,10.9,20UNC | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1180 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 154 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1200 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-05-18 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0020 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2024) | 10058181 | ROD,THD;CONT,M12 X 1M,316SS | 4 | EA | 2 | 0 | 3 | 2 | EA | 20.11 - SOH @ AA01 | Supply for Order 600001290, Item 5 cannot be changed 180029529 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180101032 | 9021091 | 05 | Preparation | 0000084206 | 5 | 0 | EA | 102000000007116 |  | 102000000007333 |  |  |  | LP-NWS-01 | WorkPackLink | P08YRDBAY6 | AA53-P08-LN | 0 | 5400000757 | 10 | 2 | EA | 1 | 3 |  |  | Y | 1001 | 2024-02-12 |  | 0 | 0 | 0 | 0 |  | 2024-05-19 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000044351 | 1020 | 2024-05-13 | 4 |  | 2024-12-04 | 4900185059_2024_0001/4900154867_2024_0001/4900076307_2024_0001/4900076149_2024_0001/4900066750_2024_0001 | 2024-05-21 |  | 5000306192_2024_0001/5000248725_2024_0001/5000122818_2024_0001 | 0 | 2 | 0 | 90006510 | 4 | 0 | 180101032/180083288/180029529/180101031 | 2 | 0 | 0 | X | L | 4900185059 | 2024 |  | 5000306192 | 2024 | 0 |  | 2024-05-18 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058181 | ROD,THD;CONT,M12 X 1M,316SS | 2024-03-06 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9021091_0030/9016687_0030/9004205_0030 |  |  | LN4 |  | C3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083560 | S002 |  | 30 | 5300006479 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-05-18 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-05-18 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0020 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2024) | 10058181 | ROD,THD;CONT,M12 X 1M,316SS | 4 | EA | 2 | 0 | 3 | 1 | EA | 20.11 - SOH @ AA01 | Supply for Order 600001290, Item 5 cannot be changed 180029529 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180101032 | 9021091 | 05 | Preparation | 0000084206 | 5 | 0 | EA | 102000000021303 |  | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | AA53-P08-LN | 0 | 5400000757 | 10 | 2 | EA | 1 | 3 |  |  | Y | 1001 | 2024-02-12 |  | 0 | 0 | 0 | 0 |  | 2024-05-19 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000044351 | 1020 | 2024-05-13 | 4 |  | 2024-12-04 | 4900185059_2024_0001/4900154867_2024_0001/4900076307_2024_0001/4900076149_2024_0001/4900066750_2024_0001 | 2024-05-21 |  | 5000306192_2024_0001/5000248725_2024_0001/5000122818_2024_0001 | 0 | 2 | 0 | 90006510 | 4 | 0 | 180101032/180083288/180029529/180101031 | 2 | 0 | 0 | X | L | 4900185059 | 2024 |  | 5000306192 | 2024 | 0 |  | 2024-05-18 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058181 | ROD,THD;CONT,M12 X 1M,316SS | 2024-03-06 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9021091_0030/9016687_0030/9004205_0030 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083560 | S002 |  | 30 | 5300006479 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-05-18 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-05-18 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0020 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2024) | 10058181 | ROD,THD;CONT,M12 X 1M,316SS | 4 | EA | 2 | 0 | 3 | 1 | EA | 20.11 - SOH @ AA01 | Supply for Order 600001290, Item 5 cannot be changed 180029529 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180101032 | 9021091 | 05 | Preparation | 0000084206 | 5 | 0 | EA |  |  | 102000000025732 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07-WAREHOUSE | AA53-P08-LN | 0 | 5400000757 | 10 | 2 | EA | 1 | 3 |  |  | Y | 1001 | 2024-02-12 |  | 0 | 0 | 0 | 0 |  | 2024-05-19 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000044351 | 1020 | 2024-05-13 | 4 |  | 2024-12-04 | 4900185059_2024_0001/4900154867_2024_0001/4900076307_2024_0001/4900076149_2024_0001/4900066750_2024_0001 | 2024-05-21 |  | 5000306192_2024_0001/5000248725_2024_0001/5000122818_2024_0001 | 0 | 2 | 0 | 90006510 | 4 | 0 | 180101032/180083288/180029529/180101031 | 2 | 0 | 0 | X | L | 4900185059 | 2024 |  | 5000306192 | 2024 | 0 |  | 2024-05-18 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058181 | ROD,THD;CONT,M12 X 1M,316SS | 2024-03-06 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9021091_0030/9016687_0030/9004205_0030 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ | 1000004390 | AU1072 | 1000083560 | S002 |  | 30 | 5300006479 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-05-18 |  | Management of Change | 2024-12-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
1 | 25SD4403 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 100031878 | 0020 | 0020 | 100031878 | Replace Flow Tx - 44FIT521 | AA53.44FIT521 | METER,FLOW K4403 SEALGAS PRIM VENT | AA01 | 30 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 8 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130319 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-11-08 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0020 | Replace Flow Meter | INT | Replace Flow Meter | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD4403 | MJ |  |  | 1000129688 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
1 | 25SDGT7 | Released | 2024-10-25 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100034776 | 0040 | 0050 | 100034776 | MOC-145870-PV CM G4007V3 Passing Fill Va | AA53.G4007V3 | VE,CO2 LOW PRESSURE,GT4007 | AA01 | 20 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 12 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000133257 | 6 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-06 | 0 |  |  |  |  | 100034776 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0040 | Fabricate Spool ( site inspection ) | INT | Fabricate Spool ( site inspection ) |  | Engineering Query/Management of Change |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000132686 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0100 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 8 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140308 | 12 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  |  |  |  | 100041844 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000139679 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD4403 | Released | 2024-01-30 | 2024-05-07 | 2024-12-18 | 2024-05-07 | 2024-05-07 | INLEC | 100042451 | 0090 | 0030 | 100042451 | Replace Flow Tx - 44FIT520 | AA53.44FIT520 | METER,FLOW K4403 SEALGAS PRIM VENT | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.12.2024) | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 4 | EA | 18 | 0 | 0 | 0 |  | 21.02 - SOH @ AA01 | Supply for Order 100042451, Item 5 cannot be changed 90027139 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300005745 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90027139 | 05 | Preparation | 0000140972 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-30 | ODST-0090027139_0020 | 0 | 230 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-12-23 |  |  |  |  | 2021-12-26 | 0 |  | 2024-12-18 |  | 2024-12-23 | 100042451 |  | 0 | 2 | 0 | 90027139 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-12-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 2024-12-17 | W |  | 0090 | Replace Flow Meter | INT | Replace Flow Meter | 5 |  | 90027139_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SD4403 | MJ |  | AU1072 | 1000140401 | S002 | 30 | 30 | 5300005745 | 40 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-12-18 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140972 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD4401 | Released | 2024-10-04 | 2025-03-01 |  | 2025-03-01 | 2025-04-29 | VALVE | 100076445 | 0010 | 0010 | 100076445 | MV-RE 1/2" 300# 244LT512 | AA53.244LT512 | TX,LEVEL DRAIN POT 2K4401V5A | AA01 | 20 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 16 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000232991 | 1 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD4401 | MJ |  |  | 1000230114 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-04-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-08-08 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200069587 | 0010 | 0020 | 200069587 | 8Y FG HOSE REPL FURNACE 5F2001 | AA53.520XE042HOSE01 | HOSE,FG 520XE042 B FLAME DET 5F2001 | AA01 | 20 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 4 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000103910 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 200069587 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0010 | Replace Hose 520XE042HOSE01 | INT | Replace Hose 520XE042HOSE01 | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000103326 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Ready For Scheduling/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | ROTAT | 200081172 | 0020 | 0040 | 200081172 | 4Y CO2 System Replace Hoses (3) 4KT1410 | AA53.HOSE40645 | HOSE,CO2 4KT1410V5 TO 414RV409 | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 24 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000115761 | 3 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 2200682034 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0020 | CO2 System Replace Hoses | INT | CO2 System Replace Hoses | 5 | Ready for Release |  |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000115091 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | ROTAT | 200081173 | 0020 | 0040 | 200081173 | 4Y CO2 System Replace Hoses (3) 4KT1430 | AA53.HOSE40648 | HOSE,CO2 4KT1430V5 TO 414RV509 | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 24 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000115762 | 3 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 2200682037 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0020 | CO2 System Replace Hoses | INT | CO2 System Replace Hoses | 5 | Ready for Release |  |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000115092 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT7 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0130 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 8 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235945 | 13 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147533 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000232951 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT9 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200147535 | 0110 | 0100 | 200147535 | 12Y INSP INT FIN FAN G4009E1 | AA53.G4009E1 | EXCH,HEAT G4009 SYNTH/MIN OIL AIR COOLER | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 8 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235947 | 10 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147535 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0110 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000232953 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT8 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200160323 | 0100 | 0110 | 200160323 | 12Y INSP INT FIN FAN G4008E1 | AA53.G4008E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4008 | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 8 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255582 | 11 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-14 | 0 |  |  |  |  | 200160323 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000251671 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0100 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 8 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 28 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0120 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 12 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 30 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0060 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 28 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 19 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 28 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0070 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 40 | EA | 18 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 20 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0120 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 200 | EA | 18 | 0 | 0 | 6 | EA | 21.02 - SOH @ AA01 | Supply for Order 600001757, Item 18 cannot be changed 90024970 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 18 | 0 | EA | 102000000032100 | 101000000139308 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0040 |  |  | SL0 |  | C4 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 18 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 170 |  |  | 0 | 200 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0120 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 200 | EA | 18 | 0 | 0 | 4 | EA | 21.02 - SOH @ AA01 | Supply for Order 600001757, Item 18 cannot be changed 90024970 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 18 | 0 | EA | 102000000032100 | 102000000028539 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0040 |  |  | SL0 |  | C4 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 18 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 170 |  |  | 0 | 200 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0120 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 200 | EA | 18 | 0 | 0 | 8 | EA | 21.02 - SOH @ AA01 | Supply for Order 600001757, Item 18 cannot be changed 90024970 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 18 | 0 | EA | 102000000032100 | 101000000139289 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0040 |  |  | SL0 |  | C4 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 18 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 170 |  |  | 0 | 200 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
1 | 25SDFR1 | Released | 2024-10-22 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | VALVE | 100045269 | 0015 | 0030 | 100045269 | Replace Pressure Gauge - 118PG11 | AA53.118PG11 | GAUGE,PRESS E1801 DE-ETH REBOILER | AA01 | 255 | WO item has not been released yet | 10058195 | BOLT STUD:0.500" X 90MM, B8M CL2 | 8 | EA | 40 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000143781 | 4 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-04-04 | 0 |  |  |  |  | 100045269 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058195 | BOLT STUD:0.500" X 90MM, B8M CL2 |  |  |  | 0015 | Remove & Replace Valve > | INT | Remove & Replace Valve > | [5 empty] | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000143151 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-02-28 | 2025-03-01 | VALVE | 100032675 | 0020 | 0060 | 100032675 | CV-OH 1" 300# 118PCV505 | AA53.118PCV505 | VALVE,1K1820 BUFFER GAS SUPPL PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 8 | EA | 201 | 0 | 0 | 0 |  | 15.01 - 244 SOH @ AA02, WO at Created Stage |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131167 | 6 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032675 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130517 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-25 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039501 | 0020 | 0010 | 100039501 | Replace - Asbestos gaskets 1K1820V5 | AA53.1K1820V5 | TANK,EMERG LUBE OIL RUNDOWN 1K1820 | AA01 | 30 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 8 | EA | 201 | 0 | 0 | 0 |  | 18.01 - At PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000137955 | 1 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-08-01 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0020 | Remove & Replace Gaskets (x3) | INT | Remove & Replace Gaskets (x3) | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137357 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039735 | 0010 | 0070 | 100039735 | Replace Flange Bolting 1K1820V7A/B | AA53.1K1820V7A | VE,DRAIN POT & MIST ELIMIN SEAL OIL | AA01 | 30 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 8 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000138236 | 7 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-08-11 | 0 |  |  |  |  | 100039735 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0010 | Replace 1K1820V7A - Gasket & Studs | INT | Replace 1K1820V7A - Gasket & Studs | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137645 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0110 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 4 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140308 | 13 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  |  |  |  | 100041844 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000139679 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR0 | Released | 2024-11-14 | 2025-03-01 |  | 2025-02-28 | 2025-03-01 | MECH | 100044226 | 0060 | 0020 | 100044226 | Offline Repair - P18032 HPV | AA53.EPFRAC6 | PIPE,ZONE FRAC TRAIN 3 | AA01 | 30 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 4 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142678 | 2 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-12-12 | 0 |  |  |  |  | 100044226 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0060 | Replace HPV Fittings (Bolt up scope) | INT | Replace HPV Fittings (Bolt up scope) | [5 empty] | FR3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR0 | MJ |  |  | 1000142148 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0630 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 8 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 63 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDGT7 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200144873 | 0100 | 0040 | 200144873 | 12Y INSP INT FIN FAN GT4007E1 | AA53.GT4007E1 | EXCH,HEAT SYNTHETIC OIL COOLER,GT4007 | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 16 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000232068 | 6 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200144873 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000229155 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0160 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 20 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 34 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0140 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 36 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 32 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 36 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0110 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 4 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 29 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0150 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 4 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 33 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0090 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 56 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 22 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 56 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0100 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 4 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 23 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0130 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 48 | EA | 201 | 0 | 67 | 48 | EA | 09.01 - Picked @ KSF | Supply for Order 600001757, Item 19 cannot be changed 90024970 item 50 already exists | Material picked; currently at SW3R01B01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 19 | 0 | EA | 102000000028581 |  | 102000000026658 |  |  |  |  | WorkPackLink | SW3R01B01A | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0050 |  |  | SL0 |  | C3 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 19 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 180 |  |  | 0 | 48 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
1 | 25SDFLR | Released | 2024-11-08 | 2025-04-30 |  | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0030 | 0050 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 64 | EA | 201 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000084731 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 64 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2024-08-30 | 0 |  |  |  |  | 37FQI40/41 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  |  |  | 0030 | Provision of Flow Computers (MOC-119247) | ESRV | Provision of Flow Computers (MOC-119247) | [5 empty] | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDFLR | MJ |  |  | 1000084145 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0540 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058204 | STUDBOLT;0.625" X 125MM,A193 B8M CL2 | 120 | EA | 36 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 54 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 120 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058204 | STUDBOLT;0.625" X 125MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SD4403 | Released | 2025-02-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | INLEC | 100031876 | 0030 | 0030 | 100031876 | Replace Needle Manifold - 44FV540 | AA53.44PDT531 | TX,PRESS K4403 SEALGAS PRIM VNT TO FLRE | AA01 | 30 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 8 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130317 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-11-08 | 0 |  |  |  |  | 100031876/77 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0030 | Complete Replacement | INT | Complete Replacement | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD4403 | MJ |  |  | 1000129686 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Material shortage/Order Approved/Released/Settlement rule created/Part printed | AM01 | Reactive Maintenance
1 | 25SD4403 | Released | 2025-02-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | INLEC | 100031877 | 0020 | 0020 | 100031877 | Replace Needle Manifold - 44FV539 | AA53.44PDT530 | TX,PRESS K4403 SEALGAS PRIM VNT TO FLRE | AA01 | 30 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 8 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130318 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-11-08 | 0 |  |  |  |  | 100031877 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD4403 | MJ |  |  | 1000129687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Settlement rule created/Part printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-25 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039501 | 0020 | 0020 | 100039501 | Replace - Asbestos gaskets 1K1820V5 | AA53.1K1820V5 | TANK,EMERG LUBE OIL RUNDOWN 1K1820 | AA01 | 30 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 8 | EA | 16 | 0 | 0 | 0 |  | 18.01 - At PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000137955 | 2 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-08-01 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0020 | Remove & Replace Gaskets (x3) | INT | Remove & Replace Gaskets (x3) | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137357 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
1 | 25SDDG1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-04-28 | VALVE | 100043452 | 0010 | 0020 | 100043452 | MV-IS 124MOV4 drain valve | AA53.124MOV04 | VALVE,MOV,TRANSMISSION GAS TO U2700 | AA01 | 20 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 1 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141984 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-25 | 0 |  |  |  |  | 100043452 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0010 | Repair Leaking Drain Point | INT | Repair Leaking Drain Point | 3 |  |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000141334 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance
1 | 25SD2301 | Released | 2024-10-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100084995 | 0010 | 0020 | 100084995 | REPLACE CS GASKET - NOZZLE K5 | AA53.1V2401 | SEP,HP FEED 1V2401 | AA01 | 30 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 4 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000267392 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-08 | 0 |  |  |  |  | 100084995 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0010 | Replace CS Gasket - Nozzle K5 | INT | Replace CS Gasket - Nozzle K5 | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000262826 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0600 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 16 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 60 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDGT7 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200144873 | 0100 | 0030 | 200144873 | 12Y INSP INT FIN FAN GT4007E1 | AA53.GT4007E1 | EXCH,HEAT SYNTHETIC OIL COOLER,GT4007 | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 8 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000232068 | 5 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200144873 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000229155 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200146986 | 0060 | 0050 | 200146986 | MOC-149553 EX/SH INSP TUB/RVDI BONREM | AA53.1E2402 | EXCH,HEAT FEED GAS LIQUID FIXED | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 8 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235448 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0060 | Remove Bonnet and Vent/Drain Blinds | INT | Remove Bonnet and Vent/Drain Blinds | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232419 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-02 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
1 | 25SDGT7 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0110 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 16 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235945 | 11 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147533 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000232951 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT9 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200147535 | 0110 | 0080 | 200147535 | 12Y INSP INT FIN FAN G4009E1 | AA53.G4009E1 | EXCH,HEAT G4009 SYNTH/MIN OIL AIR COOLER | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 16 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235947 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147535 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0110 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000232953 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT8 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200160323 | 0100 | 0090 | 200160323 | 12Y INSP INT FIN FAN G4008E1 | AA53.G4008E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4008 | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 16 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255582 | 9 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-14 | 0 |  |  |  |  | 200160323 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000251671 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0180 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 8 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 36 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0130 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 4 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 31 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0170 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 16 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 35 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0080 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 | 20 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 21 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058214 | STUDBOLT;0.750" X 110MM,A193 B8M CL2 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039735 | 0010 | 0040 | 100039735 | Replace Flange Bolting 1K1820V7A/B | AA53.1K1820V7A | VE,DRAIN POT & MIST ELIMIN SEAL OIL | AA01 | 30 | WO item has not been released yet | 10058216 | STUDBOLT;0.750" X 120MM,A193 B8M CL2 | 8 | EA | 20 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000138236 | 4 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-08-11 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058216 | STUDBOLT;0.750" X 120MM,A193 B8M CL2 |  |  |  | 0010 | Replace 1K1820V7A - Gasket & Studs | INT | Replace 1K1820V7A - Gasket & Studs | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137645 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0652 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10058217 | STUDBOLT;0.750" X 125MM,A193 B8M CL2 | 16 | EA | 16 | 0 | 0 | 16 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 89 cannot be changed 90025019 item 860 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 89 | 0 | EA | 102000000027650 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0860 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058217 | STUDBOLT;0.750" X 125MM,A193 B8M CL2 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0860 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 89 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 860 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0550 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058220 | STUDBOLT;0.750" X 150MM,A193 B8M CL2 | 80 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 55 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058220 | STUDBOLT;0.750" X 150MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0620 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058230 | STUDBOLT;0.875" X 125MM,A193 B8M CL2 | 24 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 62 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058230 | STUDBOLT;0.875" X 125MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0530 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058236 | STUDBOLT;0.875" X 170MM,A193 B8M CL2 | 32 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 53 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058236 | STUDBOLT;0.875" X 170MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-08-08 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100031838 | 0010 | 0030 | 100031838 | MV-RE 6" 600# 520GAV1667 | AA53.520HCV10A | VALVE,COMP O/H VAP TO DOMGAS | AA01 | 20 | WO item has not been released yet | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 | 12 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130239 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-05-05 | 0 |  |  |  |  | 100031838 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058249 | STUDBOLT;1.000"X170MM,B8M CL2 |  |  |  | 0010 | Remove & Replace Valve | INT | Remove & Replace Valve | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000129668 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-08-08 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100031838 | 0010 | 0050 | 100031838 | MV-RE 6" 600# 520GAV1667 | AA53.520HCV10A | VALVE,COMP O/H VAP TO DOMGAS | AA01 | 20 | WO item has not been released yet | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 12 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130239 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-05-05 | 0 |  |  |  |  | 100031838 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 |  |  |  | 0010 | Remove & Replace Valve | INT | Remove & Replace Valve | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000129668 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0570 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 12 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 57 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SD2301 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200146986 | 0060 | 0060 | 200146986 | MOC-149553 EX/SH INSP TUB/RVDI BONREM | AA53.1E2402 | EXCH,HEAT FEED GAS LIQUID FIXED | AA01 | 10 | WO item has not been released yet | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 | 12 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235448 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058252 | STUDBOLT;1.000" X 200MM,A193 B8M CL2 |  |  |  | 0060 | Remove Bonnet and Vent/Drain Blinds | INT | Remove Bonnet and Vent/Drain Blinds | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232419 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-02 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200146986 | 0060 | 0070 | 200146986 | MOC-149553 EX/SH INSP TUB/RVDI BONREM | AA53.1E2402 | EXCH,HEAT FEED GAS LIQUID FIXED | AA01 | 10 | WO item has not been released yet | 10058272 | STUDBOLT;1.125" X 230MM,A193 B8M CL2 | 12 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235448 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058272 | STUDBOLT;1.125" X 230MM,A193 B8M CL2 |  |  |  | 0060 | Remove Bonnet and Vent/Drain Blinds | INT | Remove Bonnet and Vent/Drain Blinds | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232419 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-02 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0610 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058287 | STUDBOLT;1.250" X 230MM,A193 B8M CL2 | 64 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 61 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 64 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058287 | STUDBOLT;1.250" X 230MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0590 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058287 | STUDBOLT;1.250" X 230MM,A193 B8M CL2 | 20 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 59 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058287 | STUDBOLT;1.250" X 230MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0560 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058292 | STUDBOLT;1.250" X 280MM,A193 B8M CL2 | 20 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 56 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058292 | STUDBOLT;1.250" X 280MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1320 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10058355 | STUDBOLT;1.750" X 370MM,A193 B8M2 CL2B | 20 | EA | 326 | 0 | 110 | 20 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 155 cannot be changed 90028419 item 1190 already exists | Material picked; currently at SW3R02F01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 155 | 0 | EA |  |  | 102000000031352 |  |  |  |  | WorkPackLink | SW3R02F01A |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058355 | STUDBOLT;1.750" X 370MM,A193 B8M2 CL2B | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1190 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 155 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1210 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-25 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0060 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Shipped qty below requirement qty | 10058355 | STUDBOLT;1.750" X 370MM,A193 B8M2 CL2B | 208 | EA | 326 | 0 | 110 | 110 | EA | 29.01 - At KGP | Supply for Order 600001757, Item 12 cannot be changed 90024969 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117300 | 9025807 | 07 | Execution | 0000084653 | 12 | 0 | EA |  |  | 101000000099241 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07YRDBY13 | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 98 |  |  | Y | 1001 | 2024-01-24 | GRST-5000368752_2025 | 0 | 0 | 0 | 0 |  | 2025-02-26 | AA53 | 2025-04-30 |  |  | 2025-02-28 |  |  | 100000054016 | 1020 | 2025-08-30 | 110 |  | 2025-01-22 | 4900216180_2025_0001 | 2025-02-28 | A3711B | 5000368752_2025_0001 | 0 | 2 | 0 | 90024969 | 110 | 0 | 180117300 | 1 | 0 | 0 | X | L | 4900216180 | 2025 |  | 5000368752 | 2025 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058355 | STUDBOLT;1.750" X 370MM,A193 B8M2 CL2B | 2024-07-22 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024969_0040/9025807_0040 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 12 |  | 0 |  | 25SDFLR | MJ | 1000004848 | AU1072 | 1000084067 | S002 |  | 30 | 5300005523 | 110 |  |  | 0 | 208 | EA | 2001 | AA02 | 2025-02-25 |  | Management of Change/Order Requires Replanning | 2025-01-24 |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-25 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0050 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.07.2024) | 10058355 | STUDBOLT;1.750" X 370MM,A193 B8M2 CL2B | 208 | EA | 326 | 0 | 110 | 146 | EA | 23.01 - SOH @ AA02 | Supply for Order 600001757, Item 11 cannot be changed 90024969 item 30 already exists | Material picked; currently at 30-03-06-81A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024969 | 07 | Execution | 0000084653 | 11 | 0 | EA |  |  | 101000000099242 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-06-81A | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 208 | 2025-01-18 | 2025-01-18 | Y | 1001 | 2024-01-24 | ODST-0090024969_0030 | 0 | 0 | 0 | 0 |  | 2025-02-26 | AA53 | 2025-04-30 |  |  | 2025-02-28 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-25 |  | 2025-02-28 | A3711A |  | 0 | 2 | 0 | 90024969 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058355 | STUDBOLT;1.750" X 370MM,A193 B8M2 CL2B | 2024-07-22 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024969_0030 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 11 |  | 0 |  | 25SDFLR | MJ | 20004585 | AU1072 | 1000084067 | S002 |  | 30 | 5300005523 | 100 |  |  | 0 | 208 | EA | 2001 | AA02 | 2025-02-25 |  | Management of Change/Order Requires Replanning | 2025-01-16 |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-25 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0050 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.07.2024) | 10058355 | STUDBOLT;1.750" X 370MM,A193 B8M2 CL2B | 208 | EA | 326 | 0 | 110 | 20 | EA | 23.01 - SOH @ AA02 | Supply for Order 600001757, Item 11 cannot be changed 90024969 item 30 already exists | Material picked; currently at SW3R02H01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024969 | 07 | Execution | 0000084653 | 11 | 0 | EA |  |  | 102000000030691 |  |  |  |  | WorkPackLink | SW3R02H01B | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 208 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024969_0030 | 0 | 0 | 0 | 0 |  | 2025-02-26 | AA53 | 2025-04-30 |  |  | 2025-02-28 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-25 |  | 2025-02-28 | A3711A |  | 0 | 2 | 0 | 90024969 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058355 | STUDBOLT;1.750" X 370MM,A193 B8M2 CL2B | 2024-07-22 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024969_0030 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 11 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 |  | 30 | 5300005523 | 100 |  |  | 0 | 208 | EA | 2001 | AA02 | 2025-02-25 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0640 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10058357 | STUDBOLT;1.875" X 330MM,A193 B8M2 CL2B | 48 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 64 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058357 | STUDBOLT;1.875" X 330MM,A193 B8M2 CL2B |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SD2301 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200146986 | 0060 | 0080 | 200146986 | MOC-149553 EX/SH INSP TUB/RVDI BONREM | AA53.1E2402 | EXCH,HEAT FEED GAS LIQUID FIXED | AA01 | 10 | WO item has not been released yet | 10058375 | STUDBOLT;2.500" X 575MM,A193 B8M2 CL2B | 24 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235448 | 8 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058375 | STUDBOLT;2.500" X 575MM,A193 B8M2 CL2B |  |  |  | 0060 | Remove Bonnet and Vent/Drain Blinds | INT | Remove Bonnet and Vent/Drain Blinds | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232419 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-02 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0080 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058668 | STUDBOLT;0.500"X70MM,L7,BLK | 8 | EA | 143 | 16 | 32 | 8 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 9 cannot be changed 90028417 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 9 | 0 | EA | 102000000031912 | 102000000033899 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058668 | STUDBOLT;0.500"X70MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0080 |  |  | ST5 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 80 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SDGT8 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | WORK | 200089335 | 0020 | 0040 | 200089335 | 10Y RECERTIFY PSV ROTABLE | AA53.408RV521 | PSV,CO2 DISCH LINE GT4008A CO2 | AA01 | 10 | WO item has not been released yet | 10058672 | STUDBOLT;0.500" X 90MM,L7,BLK | 4 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000127593 | 4 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 2200633290 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058672 | STUDBOLT;0.500" X 90MM,L7,BLK |  |  |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000127004 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200090677 | 0100 | 0030 | 200090677 | 4Y INT INSP EXCHANGER 5P2002AE | AA53.5P2002AE | EXCH,SEAL OIL COOLER P2002A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 8 | EA | 72 | 0 | 0 | 8 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090677, Item 2 cannot be changed 90028421 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019786 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028421 | 05 | Preparation | 0000128955 | 2 | 0 | EA | 102000000032844 | 102000000033895 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2027 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028421_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090677 |  | 0 | 2 | 0 | 90028421 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 2025-01-08 | W |  | 0100 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028421_0020 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128366 | S002 | 30 | 30 | 5300019786 | 20 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128955 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200090677 | 0100 | 0070 | 200090677 | 4Y INT INSP EXCHANGER 5P2002AE | AA53.5P2002AE | EXCH,SEAL OIL COOLER P2002A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 4 | EA | 72 | 0 | 0 | 4 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090677, Item 6 cannot be changed 90028421 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019786 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028421 | 05 | Preparation | 0000128955 | 6 | 0 | EA | 102000000032844 | 102000000033896 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2031 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028421_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090677 |  | 0 | 2 | 0 | 90028421 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 2025-01-08 | W |  | 0100 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028421_0060 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128366 | S002 | 30 | 30 | 5300019786 | 60 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128955 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-02-25 | 2025-03-01 | MECH | 200090678 | 0080 | 0090 | 200090678 | 4Y INT INSP EXCHANGER 5P2002BE | AA53.5P2002BE | EXCH,SEAL OIL COOLER P2002B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 8 | EA | 72 | 0 | 0 | 8 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090678, Item 2 cannot be changed 90028422 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019787 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028422 | 05 | Preparation | 0000128956 | 2 | 0 | EA | 102000000031911 | 102000000033897 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2026 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028422_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090678 |  | 0 | 2 | 0 | 90028422 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 2025-01-08 | W |  | 0080 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028422_0020 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128367 | S002 | 30 | 30 | 5300019787 | 20 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128956 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-02-25 | 2025-03-01 | MECH | 200090678 | 0080 | 0130 | 200090678 | 4Y INT INSP EXCHANGER 5P2002BE | AA53.5P2002BE | EXCH,SEAL OIL COOLER P2002B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 4 | EA | 72 | 0 | 0 | 4 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090678, Item 6 cannot be changed 90028422 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019787 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028422 | 05 | Preparation | 0000128956 | 6 | 0 | EA | 102000000031911 | 102000000033898 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2030 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028422_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090678 |  | 0 | 2 | 0 | 90028422 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 2025-01-08 | W |  | 0080 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028422_0060 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128367 | S002 | 30 | 30 | 5300019787 | 60 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128956 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200090882 | 0040 | 0040 | 200090882 | 12Y INT INSP EXCHANGER 1K1820E1A | AA53.1K1820E1A | EXCH,HEAT LUBE OIL FRAC T1 1K1820 | AA01 | 10 | WO item has not been released yet | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 8 | EA | 72 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000129132 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200090882 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK |  |  |  | 0040 | Remove Fin Fan Plugs (16) | INT | Remove Fin Fan Plugs (16) | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000128534 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Ready For Scheduling/Material committed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0660 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 12 | EA | 72 | 0 | 0 | 12 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 73 cannot be changed 90025019 item 710 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 710 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 73 | 0 | EA | 102000000032113 | 102000000028505 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0710 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058678 | STUDBOLT;0.625" X 80MM,L7,BLK | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0710 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 73 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 710 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDLN4 | Released | 2024-11-19 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | VALVE | 100042223 | 0020 | 0010 | 100042223 | CV-RE 2" 600# 414UV356 | AA53.414UV356 | VALVE,CTRL 4V1404 HW TO SUPPLY | AA01 | 10 | WO item has not been released yet | 10058684 | STUDBOLT;0.625" X 115MM,L7,BLK | 16 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140764 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 100042223 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058684 | STUDBOLT;0.625" X 115MM,L7,BLK |  |  |  | 0020 | Remove & Replace Valve, Reuse Actuator | INT | Remove & Replace Valve, Reuse Actuator | [5 empty] | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000140133 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0010 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058692 | STUDBOLT;0.625" X 105MM,L7,BLK | 130 | EA | 169 | 0 | 0 | 48 | EA | 02.03 - SOH @ AA02 | Supply for Order 200073951, Item 1 cannot be changed 90028585 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 1 | 0 | EA | 102000000033905 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 130 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058692 | STUDBOLT;0.625" X 105MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0010 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 |  | 30 | 5300020031 | 10 |  |  | 0 | 130 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0010 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058692 | STUDBOLT;0.625" X 105MM,L7,BLK | 130 | EA | 169 | 0 | 0 | 25 | EA | 02.03 - SOH @ AA02 | Supply for Order 200073951, Item 1 cannot be changed 90028585 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 1 | 0 | EA | 102000000033906 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 130 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058692 | STUDBOLT;0.625" X 105MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0010 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 |  | 30 | 5300020031 | 10 |  |  | 0 | 130 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-13 | MECH | 200152144 | 0010 | 0020 | 200152144 | 12Y INSP INT EXCHANGER 5E2005 | AA53.5E2005 | HTR,SUCTION ELEC 5K2001 | AA01 | 10 | WO item has not been released yet | 10058692 | STUDBOLT;0.625" X 105MM,L7,BLK | 8 | EA | 169 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000242789 | 2 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-08 | 0 |  |  |  |  | 200152144 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058692 | STUDBOLT;0.625" X 105MM,L7,BLK |  |  |  | 0010 | Operator Assist - Heat Trace Isolation | INT | Operator Assist - Heat Trace Isolation | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000239484 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-06-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-13 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-03-05 | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0030 | 0020 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | No issue identified | 10058692 | STUDBOLT;0.625" X 105MM,L7,BLK | 4 | EA | 169 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004588 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032272 | 05 | Preparation | 0000084596 | 48 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090032272_0020 | 0 | 9 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-10 |  |  |  |  | 2025-09-29 | 0 |  | 2025-03-05 |  | 2025-03-10 |  |  | 0 | 2 | 0 | 90032272 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058692 | STUDBOLT;0.625" X 105MM,L7,BLK |  |  |  | 0030 | Fabricate spool1 as per:L2000.DM0010.001 | INT | Fabricate spool1 as per:L2000.DM0010.001 |  |  | 90032272_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 20 |  |  | 48 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000084000 | S002 |  | 30 | 5300004588 | 60 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-03-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84596 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0120 | 0020 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10058694 | STUDBOLT;0.750"X100MM,L7,BLK | 20 | EA | 98 | 0 | 30 | 20 | EA | 23.01 - SOH @ AA02 | Supply for Order 100079012, Item 12 cannot be changed 90028429 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018551 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028429 | 05 | Preparation | 0000243763 | 12 | 0 | EA | 102000000031901 | 102000000033893 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028429_0080 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079012 |  | 0 | 2 | 0 | 90028429 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058694 | STUDBOLT;0.750"X100MM,L7,BLK | 2024-11-29 | W |  | 0120 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028429_0080 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 12 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240421 | S002 | 30 | 30 | 5300018551 | 80 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243763 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0140 | 0020 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10058694 | STUDBOLT;0.750"X100MM,L7,BLK | 20 | EA | 98 | 0 | 30 | 20 | EA | 23.01 - SOH @ AA02 | Supply for Order 100079106, Item 12 cannot be changed 90028430 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018552 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028430 | 05 | Preparation | 0000243730 | 12 | 0 | EA | 102000000031891 | 102000000033894 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028430_0070 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079106 |  | 0 | 2 | 0 | 90028430 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058694 | STUDBOLT;0.750"X100MM,L7,BLK | 2024-11-29 | W |  | 0140 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028430_0070 |  |  | ST5 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 12 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240357 | S002 | 30 | 30 | 5300018552 | 70 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0130 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058698 | STUDBOLT;0.750" X 125MM,L7,BLK | 12 | EA | 57 | 24 | 0 | 12 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 14 cannot be changed 90028417 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 14 | 0 | EA | 102000000031912 | 102000000033903 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058698 | STUDBOLT;0.750" X 125MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0130 |  |  | ST5 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 14 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 130 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0120 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058702 | STUDBOLT;0.750" X 150MM,L7,BLK | 12 | EA | 50 | 0 | 0 | 12 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 13 cannot be changed 90028417 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 13 | 0 | EA | 102000000033890 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058702 | STUDBOLT;0.750" X 150MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0120 |  |  | ST5 |  | C5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 13 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 |  | 30 | 5300018296 | 120 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0050 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058702 | STUDBOLT;0.750" X 150MM,L7,BLK | 25 | EA | 50 | 0 | 0 | 12 | EA | 09.02 - SOH @ AA01 | Supply for Order 200073951, Item 5 cannot be changed 90028585 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 5 | 0 | EA | 102000000033892 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 25 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058702 | STUDBOLT;0.750" X 150MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0050 |  |  | ST5 |  | C5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 |  | 30 | 5300020031 | 50 |  |  | 0 | 25 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0050 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058702 | STUDBOLT;0.750" X 150MM,L7,BLK | 25 | EA | 50 | 0 | 0 | 2 | EA | 09.02 - SOH @ AA01 | Supply for Order 200073951, Item 5 cannot be changed 90028585 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 5 | 0 | EA | 102000000031896 | 102000000033891 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 25 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058702 | STUDBOLT;0.750" X 150MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0050 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 |  | 30 | 5300020031 | 50 |  |  | 0 | 25 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDDG1 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200174926 | 0030 | 0040 | 200174926 | Replace Exchanger - 1KKT2430E3 | AA53.1KKT2430E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2430 | AA01 | 10 | WO item has not been released yet | 10058702 | STUDBOLT;0.750" X 150MM,L7,BLK | 12 | EA | 50 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000277561 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-07-09 | 0 |  |  |  |  | 200174926 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058702 | STUDBOLT;0.750" X 150MM,L7,BLK |  |  |  | 0030 | Remove Bonnet / Spools & Structure | INT | Remove Bonnet / Spools & Structure | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000272048 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0110 | 0040 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058720 | STUDBOLT;0.875" X 180MM,L7,BLK | 48 | EA | 48 | 0 | 0 | 16 | EA | 24.02 - SOH @ AA02 | Supply for Order 200088516, Item 4 cannot be changed 90028586 item 40 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020032 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028586 | 05 | Preparation | 0000126825 | 4 | 0 | EA | 101000000145936 |  | 101000000148055 | 01-Road |  | 5-Completed |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 48 | 2025-02-27 | 2025-02-26 | Y | 1001 | 2025-01-14 | ODST-0090028586_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028586 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058720 | STUDBOLT;0.875" X 180MM,L7,BLK | 2025-01-14 | W |  | 0110 | Punchlist & Closeout WP200088516MET001 | ENON | Punchlist & Closeout WP200088516MET001 | 5 | Ready for Release | 90028586_0040 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ | 20005551 | AU1072 | 1000126175 | S002 |  | 30 | 5300020032 | 40 |  |  | 0 | 48 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-24 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126825 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0110 | 0040 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058720 | STUDBOLT;0.875" X 180MM,L7,BLK | 48 | EA | 48 | 0 | 0 | 16 | EA | 24.02 - SOH @ AA02 | Supply for Order 200088516, Item 4 cannot be changed 90028586 item 40 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020032 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028586 | 05 | Preparation | 0000126825 | 4 | 0 | EA | 101000000145881 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A |  | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028586_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028586 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058720 | STUDBOLT;0.875" X 180MM,L7,BLK | 2025-01-14 | W |  | 0110 | Punchlist & Closeout WP200088516MET001 | ENON | Punchlist & Closeout WP200088516MET001 | 5 | Ready for Release | 90028586_0040 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126175 | S002 |  | 30 | 5300020032 | 40 |  |  | 0 | 48 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126825 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0110 | 0040 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058720 | STUDBOLT;0.875" X 180MM,L7,BLK | 48 | EA | 48 | 0 | 0 | 16 | EA | 24.02 - SOH @ AA02 | Supply for Order 200088516, Item 4 cannot be changed 90028586 item 40 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020032 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028586 | 05 | Preparation | 0000126825 | 4 | 0 | EA | 101000000147963 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A |  | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028586_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028586 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058720 | STUDBOLT;0.875" X 180MM,L7,BLK | 2025-01-14 | W |  | 0110 | Punchlist & Closeout WP200088516MET001 | ENON | Punchlist & Closeout WP200088516MET001 | 5 | Ready for Release | 90028586_0040 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126175 | S002 |  | 30 | 5300020032 | 40 |  |  | 0 | 48 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126825 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0050 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058731 | STUDBOLT;1.000" X 145MM,L7,BLK | 12 | EA | 0 | 0 | 12 | 12 | EA | 19.02 - SOH @ AA02 | Supply for Order 100087648, Item 6 cannot be changed 9028800 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132451 | 9028800 | 05 | Preparation | 0000278190 | 6 | 0 | EA |  |  | 102000000034224 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07YRDBY13 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-22 | GRST-5000428147_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060060 | 1020 | 2025-12-02 | 12 |  | 2025-03-05 | 4900257839_2025_0005 | 2025-03-01 | 5E2001 | 5000428147_2025_0003 | 0 | 2 | 0 | 90028417 | 12 | 0 | 180132451 | 2 | 0 | 0 | X | L | 4900257839 | 2025 |  | 5000428147 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058731 | STUDBOLT;1.000" X 145MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 9028800_0050 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ | 1000005325 | AU1072 | 1000272706 | S002 |  | 30 | 5300018296 | 50 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-03-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SDLN1 | Released | 2024-08-15 | 2025-03-01 |  | 2025-02-19 | 2025-03-03 | MECH | 600003215 | 0020 | 0050 | 600003215 | MOC-117109 1E1303 Exchanger Replacement | AA53.1E1303 | EXCH,HEAT AIR COOL REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10058737 | STUDBOLT;1.000" X 200MM,L7,BLK | 24 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000254308 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058737 | STUDBOLT;1.000" X 200MM,L7,BLK |  |  |  | 0020 | Remove blanks For Inspection Access | INT | Remove blanks For Inspection Access |  | Management of Change |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000250524 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W35069 | 2024-08-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-02-19 | 2025-02-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0030 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058744 | STUDBOLT;1.125"X125MM,GDE L7,BLK | 20 | EA | 20 | 0 | 0 | 10 | EA | 13.02 - SOH @ AA02 | Supply for Order 100087648, Item 4 cannot be changed 90028417 item 30 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 4 | 0 | EA | 101000000143908 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058744 | STUDBOLT;1.125"X125MM,GDE L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 30 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0030 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058744 | STUDBOLT;1.125"X125MM,GDE L7,BLK | 20 | EA | 20 | 0 | 0 | 10 | EA | 13.02 - SOH @ AA02 | Supply for Order 100087648, Item 4 cannot be changed 90028417 item 30 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 4 | 0 | EA | 101000000144065 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058744 | STUDBOLT;1.125"X125MM,GDE L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 30 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0060 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058751 | BLT STUD:1.125in,8-UNtpi,220mm,CARBON ST | 20 | EA | 0 | 0 | 20 | 20 | EA | 19.02 - SOH @ AA02 | Supply for Order 100087648, Item 7 cannot be changed 9028800 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132451 | 9028800 | 05 | Preparation | 0000278190 | 7 | 0 | EA |  |  | 102000000034224 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07YRDBY13 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-22 | GRST-5000428147_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060060 | 1020 | 2025-12-02 | 20 |  | 2025-03-05 | 4900257839_2025_0007 | 2025-03-01 | 5E2001 | 5000428147_2025_0004 | 0 | 2 | 0 | 90028417 | 20 | 0 | 180132451 | 2 | 0 | 0 | X | L | 4900257839 | 2025 |  | 5000428147 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058751 | BLT STUD:1.125in,8-UNtpi,220mm,CARBON ST | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 9028800_0060 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ | 1000005325 | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 60 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-03-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0030 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 24 | EA | 24 | 0 | 0 | 6 | EA | 19.02 - SOH @ AA02 | Supply for Order 200082188, Item 3 cannot be changed 90028591 item 30 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020023 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028591 | 05 | Preparation | 0000117838 | 3 | 0 | EA | 101000000142450 |  | 101000000144157 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 24 |  | 2025-02-15 | Y | 1001 | 2025-01-14 | ODST-0090028591_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200082188 |  | 0 | 2 | 0 | 90028591 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 2025-01-14 | W |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools |  |  | 90028591_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SD2301 | MJ | 20005086 | AU1072 | 1000117251 | S002 |  | 30 | 5300020023 | 30 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117838 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0030 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 24 | EA | 24 | 0 | 0 | 6 | EA | 19.02 - SOH @ AA02 | Supply for Order 200082188, Item 3 cannot be changed 90028591 item 30 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020023 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028591 | 05 | Preparation | 0000117838 | 3 | 0 | EA | 101000000142428 |  | 101000000144679 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 24 |  | 2025-02-16 | Y | 1001 | 2025-01-14 | ODST-0090028591_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200082188 |  | 0 | 2 | 0 | 90028591 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 2025-01-14 | W |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools |  |  | 90028591_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SD2301 | MJ | 20005300 | AU1072 | 1000117251 | S002 |  | 30 | 5300020023 | 30 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-14 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117838 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0030 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 24 | EA | 24 | 0 | 0 | 6 | EA | 19.02 - SOH @ AA02 | Supply for Order 200082188, Item 3 cannot be changed 90028591 item 30 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020023 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028591 | 05 | Preparation | 0000117838 | 3 | 0 | EA | 101000000142459 |  | 101000000144679 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 24 |  | 2025-02-16 | Y | 1001 | 2025-01-14 | ODST-0090028591_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200082188 |  | 0 | 2 | 0 | 90028591 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 2025-01-14 | W |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools |  |  | 90028591_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SD2301 | MJ | 20005300 | AU1072 | 1000117251 | S002 |  | 30 | 5300020023 | 30 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-14 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117838 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0030 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 24 | EA | 24 | 0 | 0 | 6 | EA | 19.02 - SOH @ AA02 | Supply for Order 200082188, Item 3 cannot be changed 90028591 item 30 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020023 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028591 | 05 | Preparation | 0000117838 | 3 | 0 | EA | 101000000142429 |  | 101000000144157 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 24 |  | 2025-02-15 | Y | 1001 | 2025-01-14 | ODST-0090028591_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200082188 |  | 0 | 2 | 0 | 90028591 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 2025-01-14 | W |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools |  |  | 90028591_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SD2301 | MJ | 20005086 | AU1072 | 1000117251 | S002 |  | 30 | 5300020023 | 30 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117838 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDDG1 | Released | 2024-10-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200160316 | 0030 | 0020 | 200160316 | 10Y INSPECT 8" 600# 44CHV1107 | AA53.44CHV1107 | VALVE,CHECK HP FG TO K2430 | AA01 | 10 | WO item has not been released yet | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK | 12 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255550 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-SD-UT1 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  |  |  |  | 200160316 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058759 | STUDBOLT;1.125" X 370MM,L7,BLK |  |  |  | 0030 | Install NRV | INT | Install NRV | 5 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000251639 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0040 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058761 | STUDBOLT;1.125" X 410MM,L7,BLK | 72 | EA | 0 | 0 | 72 | 72 | EA | 19.02 - SOH @ AA02 | Supply for Order 100087648, Item 5 cannot be changed 9028800 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132451 | 9028800 | 05 | Preparation | 0000278190 | 5 | 0 | EA |  |  | 102000000034224 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07YRDBY13 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-22 | GRST-5000428147_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060060 | 1020 | 2025-12-02 | 72 |  | 2025-03-05 | 4900257839_2025_0003 | 2025-03-01 | 5E2001 | 5000428147_2025_0002 | 0 | 2 | 0 | 90028417 | 72 | 0 | 180132451 | 2 | 0 | 0 | X | L | 4900257839 | 2025 |  | 5000428147 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058761 | STUDBOLT;1.125" X 410MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 9028800_0040 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ | 1000005325 | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 40 |  |  | 0 | 72 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-03-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0090 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Shipped qty below requirement qty | 10058762 | STUDBOLT;1.125" X 470MM,L7,BLK | 64 | EA | 3 | 0 | 62 | 62 | EA | 19.02 - SOH @ AA02 | Supply for Order 100087648, Item 10 cannot be changed 90028417 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132451 | 9028800 | 05 | Preparation | 0000278190 | 10 | 0 | EA |  |  | 102000000034224 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07YRDBY13 |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-22 | GRST-5000428147_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060060 | 1020 | 2025-12-02 | 62 |  | 2025-03-05 | 4900257839_2025_0011 | 2025-03-01 | 5E2001 | 5000428147_2025_0006 | 0 | 2 | 0 | 90028417 | 62 | 0 | 180132451 | 1 | 0 | 0 | X | L | 4900257839 | 2025 |  | 5000428147 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058762 | STUDBOLT;1.125" X 470MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0090/9028800_0090 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ | 1000005325 | AU1072 | 1000272706 | S002 |  | 30 | 5300018296 | 90 |  |  | 0 | 64 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-03-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0090 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Shipped qty below requirement qty | 10058762 | STUDBOLT;1.125" X 470MM,L7,BLK | 64 | EA | 3 | 0 | 62 | 2 | EA | 19.02 - SOH @ AA02 | Supply for Order 100087648, Item 10 cannot be changed 90028417 item 90 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132451 | 9028800 | 05 | Preparation | 0000278190 | 10 | 0 | EA | 102000000033970 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-22 | GRST-5000428147 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060060 | 1020 | 2025-12-02 | 62 |  | 2025-03-05 | 4900257839_2025_0011 | 2025-03-01 | 5E2001 | 5000428147_2025_0006 | 0 | 2 | 0 | 90028417 | 62 | 0 | 180132451 | 1 | 0 | 0 | X | L | 4900257839 | 2025 |  | 5000428147 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058762 | STUDBOLT;1.125" X 470MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0090/9028800_0090 |  |  | ST5 |  | C5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 |  | 30 | 5300018296 | 90 |  |  | 0 | 64 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0020 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058764 | STUDBOLT;1.125" X 550MM,L7,BLK | 56 | EA | 0 | 0 | 56 | 56 | EA | 19.02 - SOH @ AA02 | Supply for Order 100087648, Item 3 cannot be changed 9028800 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132451 | 9028800 | 05 | Preparation | 0000278190 | 3 | 0 | EA |  |  | 102000000034224 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07YRDBY13 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-22 | GRST-5000428147_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060060 | 1020 | 2025-12-02 | 56 |  | 2025-03-05 | 4900257839_2025_0001 | 2025-03-01 | 5E2001 | 5000428147_2025_0001 | 0 | 2 | 0 | 90028417 | 56 | 0 | 180132451 | 2 | 0 | 0 | X | L | 4900257839 | 2025 |  | 5000428147 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058764 | STUDBOLT;1.125" X 550MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 9028800_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ | 1000005325 | AU1072 | 1000272706 | S002 |  | 30 | 5300018296 | 20 |  |  | 0 | 56 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-03-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0100 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058769 | STUDBOLT;1.250"X230MM,L7,BLK | 20 | EA | 45 | 0 | 0 | 20 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 11 cannot be changed 90028417 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 11 | 0 | EA | 102000000031912 | 102000000033901 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058769 | STUDBOLT;1.250"X230MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0100 |  |  | ST5 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 100 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0020 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058772 | STUDBOLT;1.250" X 250MM,L7,BLK | 45 | EA | 40 | 0 | 7 | 4 | EA | 20.02 - SOH @ AA01 | Supply for Order 200073951, Item 2 cannot be changed 90028585 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 2 | 0 | EA | 102000000033847 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 45 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058772 | STUDBOLT;1.250" X 250MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0020 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 |  | 30 | 5300020031 | 20 |  |  | 0 | 45 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0020 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058772 | STUDBOLT;1.250" X 250MM,L7,BLK | 45 | EA | 40 | 0 | 7 | 6 | EA | 20.02 - SOH @ AA01 | Supply for Order 200073951, Item 2 cannot be changed 90028585 item 20 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 2 | 0 | EA | 101000000145941 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 45 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058772 | STUDBOLT;1.250" X 250MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0020 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 |  | 30 | 5300020031 | 20 |  |  | 0 | 45 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0110 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | WO item has not been released yet | 10058776 | STUDBOLT;1.250" X 280MM,L7,BLK | 24 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139208 | 13 | 0 | [8 empty] | WorkPackLink |  | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-08-01 | 0 |  |  |  |  | 100040704 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058776 | STUDBOLT;1.250" X 280MM,L7,BLK |  |  |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000138559 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0070 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058777 | STUDBOLT;1.250" X 290MM,L7,BLK | 24 | EA | 0 | 0 | 24 | 24 | EA | 19.02 - SOH @ AA02 | Supply for Order 100087648, Item 8 cannot be changed 9028800 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132451 | 9028800 | 05 | Preparation | 0000278190 | 8 | 0 | EA |  |  | 102000000034224 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07YRDBY13 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-22 | GRST-5000428147_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000060060 | 1020 | 2025-12-02 | 24 |  | 2025-03-05 | 4900257839_2025_0009 | 2025-03-01 | 5E2001 | 5000428147_2025_0005 | 0 | 2 | 0 | 90028417 | 24 | 0 | 180132451 | 2 | 0 | 0 | X | L | 4900257839 | 2025 |  | 5000428147 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058777 | STUDBOLT;1.250" X 290MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 9028800_0070 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ | 1000005325 | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 70 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-03-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0070 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | WO item has not been released yet | 10058807 | STUDBOLT;1.500"X310MM,L7,BLK | 27 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139208 | 9 | 0 | [8 empty] | WorkPackLink |  | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 27 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-08-01 | 0 |  |  |  |  | 100040704 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058807 | STUDBOLT;1.500"X310MM,L7,BLK |  |  |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000138559 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100043807 | 0010 | 0042 | 100043807 | Repair/replace faulty N2 flow indicator | AA53.118FI503 | IND,N2 PURGE GAS TO RESERVOIR 1K1820V6 | AA01 | 20 | WO item has not been released yet | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 4 | EA | 90 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000142308 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-01-14 | 0 |  |  |  |  | 100043807 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK |  |  |  | 0010 | Remove & Replace Flowmeter | INT | Remove & Replace Flowmeter | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000141677 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material shortage | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-05-15 | MECH | 100044203 | 0010 | 0030 | 100044203 | Repair/replace faulty N2 flow indicator | AA53.118FI502 | IND,N2 PURGE GAS TO RESERVOIR 1K1820V2 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 8 | EA | 90 | 0 | 0 | 8 | EA | 02.10 - SOH @ AA02 | Supply for Order 100044203, Item 2 cannot be changed 90024953 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002290 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024953 | 06 | Scheduling | 0000142657 | 2 | 0 | EA | 102000000032094 | 102000000028503 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024953_0020 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2021-01-14 | 0 |  | 2025-03-26 |  | 2025-03-31 | 118FI502 |  | 0 | 2 | 0 | 90024953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 2024-01-02 | W |  | 0010 | Remove & Replace Flowmeter | INT | Remove & Replace Flowmeter | 5 |  | 90024953_0020 |  |  | FR1 |  | A4 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000142019 | S002 | 30 | 30 | 5300002290 | 20 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142657 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200090677 | 0100 | 0050 | 200090677 | 4Y INT INSP EXCHANGER 5P2002AE | AA53.5P2002AE | EXCH,SEAL OIL COOLER P2002A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 8 | EA | 90 | 0 | 0 | 8 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090677, Item 4 cannot be changed 90028421 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019786 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028421 | 05 | Preparation | 0000128955 | 4 | 0 | EA | 102000000032844 | 102000000033848 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2029 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028421_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090677 |  | 0 | 2 | 0 | 90028421 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 2025-01-08 | W |  | 0100 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028421_0040 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128366 | S002 | 30 | 30 | 5300019786 | 40 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128955 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-02-25 | 2025-03-01 | MECH | 200090678 | 0080 | 0110 | 200090678 | 4Y INT INSP EXCHANGER 5P2002BE | AA53.5P2002BE | EXCH,SEAL OIL COOLER P2002B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 8 | EA | 90 | 0 | 0 | 8 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090678, Item 4 cannot be changed 90028422 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019787 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028422 | 05 | Preparation | 0000128956 | 4 | 0 | EA | 102000000031911 | 102000000033849 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2028 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028422_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090678 |  | 0 | 2 | 0 | 90028422 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 2025-01-08 | W |  | 0080 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028422_0040 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128367 | S002 | 30 | 30 | 5300019787 | 40 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128956 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0670 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 20 | EA | 90 | 0 | 0 | 20 | EA | 15.10 - SOH @ AA02 | Supply for Order 200091505, Item 74 cannot be changed 90025019 item 720 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 720 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 74 | 0 | EA | 102000000032113 | 102000000028502 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0720 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058983 | STUDBOLT;0.500" X 65MM,L7,BLK | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0720 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 74 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 720 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0100 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 8 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139208 | 12 | 0 | [8 empty] | WorkPackLink |  | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-08-01 | 0 |  |  |  |  | 100040704 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  |  |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000138559 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100048154 | 0010 | 0030 | 100048154 | Repair - B&P Sight Glasses 1K1820V3 | AA53.1K1820V3 | TANK,FRAC 1 LUBE OIL RESERVOIR | AA01 | 20 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 16 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000146666 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-12-01 | 0 |  |  |  |  | 100048154 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  |  |  | 0010 | Remove Sight Glasses, Cover Flanges | INT | Remove Sight Glasses, Cover Flanges | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000146076 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed/Printed | AM01 | Reactive Maintenance
1 | 25SDGT9 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0170 | 0040 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 4 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000277133 | 13 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-12-18 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  |  |  | 0170 | Replace Spool (Bolt up scope) | INT | Replace Spool (Bolt up scope) |  | Management of Change |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000271703 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0030 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 35 | EA | 43 | 0 | 0 | 21 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 3 cannot be changed 90028585 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 3 | 0 | EA | 102000000033073 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 35 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0030 |  |  | ST5 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 30 |  |  | 0 | 35 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0030 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 35 | EA | 43 | 0 | 0 | 6 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 3 cannot be changed 90028585 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 3 | 0 | EA | 102000000031896 | 102000000033435 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 35 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0030 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 30 |  |  | 0 | 35 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0030 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 35 | EA | 43 | 0 | 0 | 8 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 3 cannot be changed 90028585 item 30 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 3 | 0 | EA | 102000000031074 | 101000000136293 | 102000000031896 |  |  |  |  | WorkPackLink |  | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 35 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0030 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 30 |  |  | 0 | 35 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDGT8 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | WORK | 200089335 | 0020 | 0050 | 200089335 | 10Y RECERTIFY PSV ROTABLE | AA53.408RV521 | PSV,CO2 DISCH LINE GT4008A CO2 | AA01 | 10 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 4 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000127593 | 5 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 2200633290 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  |  |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000127004 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-05-01 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200147055 | 0015 | 0020 | 200147055 | 2Y Depress Valve F/Test (5) 1V2401 | AA53.124HCV051 | VALVE,CTRL PRESS DEPRESS 1V2401 | AA01 | 10 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 4 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235216 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-20 | 0 |  |  |  |  | 200147055 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  |  |  | 0015 | Remove & Re-Instate Blind | INT | Remove & Re-Instate Blind | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232270 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-05-01 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200147056 | 0015 | 0020 | 200147056 | 2Y Depress Valve F/Test (4) 1C2401 | AA53.124HCV141 | VALVE,CTRL HAND 1C2401 DEPRESS | AA01 | 10 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 4 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235217 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-20 | 0 |  |  |  |  | 200147056 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  |  |  | 0015 | Remove & Re-Instate Blind | INT | Remove & Re-Instate Blind | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232271 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDDG1 | Released | 2024-05-01 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200147059 | 0020 | 0020 | 200147059 | 2Y FUNCT TEST 124HCV68 | AA53.124HCV68 | VALVE,CTRL 1K2430 DEPRESS | AA01 | 10 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 4 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235220 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147059 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  |  |  | 0020 | Remove & Re-Instate Blind | INT | Remove & Re-Instate Blind |  | Ready for Release |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000232274 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0140 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10058992 | STUDBOLT;0.625"X90MM,L7,BLK | 24 | EA | 82 | 0 | 0 | 24 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 15 cannot be changed 90028417 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 15 | 0 | EA | 102000000033846 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058992 | STUDBOLT;0.625"X90MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0140 |  |  | ST5 |  | C5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 140 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0120 | 0010 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10059000 | STUDBOLT;0.750" X 90MM,L7,BLK | 20 | EA | 40 | 0 | 0 | 11 | EA | 19.02 - SOH @ AA02 | Supply for Order 100079012, Item 11 cannot be changed 90028429 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018551 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028429 | 05 | Preparation | 0000243763 | 11 | 0 | EA | 102000000031901 | 101000000008908 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028429_0070 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079012 |  | 0 | 2 | 0 | 90028429 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059000 | STUDBOLT;0.750" X 90MM,L7,BLK | 2024-11-29 | W |  | 0120 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028429_0070 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240421 | S002 | 30 | 30 | 5300018551 | 70 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243763 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0120 | 0010 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10059000 | STUDBOLT;0.750" X 90MM,L7,BLK | 20 | EA | 40 | 0 | 0 | 9 | EA | 19.02 - SOH @ AA02 | Supply for Order 100079012, Item 11 cannot be changed 90028429 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018551 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028429 | 05 | Preparation | 0000243763 | 11 | 0 | EA | 102000000031901 | 102000000033381 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028429_0070 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079012 |  | 0 | 2 | 0 | 90028429 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059000 | STUDBOLT;0.750" X 90MM,L7,BLK | 2024-11-29 | W |  | 0120 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028429_0070 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240421 | S002 | 30 | 30 | 5300018551 | 70 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243763 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0140 | 0010 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10059000 | STUDBOLT;0.750" X 90MM,L7,BLK | 20 | EA | 40 | 0 | 0 | 20 | EA | 19.02 - SOH @ AA02 | Supply for Order 100079106, Item 11 cannot be changed 90028430 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018552 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028430 | 05 | Preparation | 0000243730 | 11 | 0 | EA | 102000000033382 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028430_0060 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079106 |  | 0 | 2 | 0 | 90028430 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059000 | STUDBOLT;0.750" X 90MM,L7,BLK | 2024-11-29 | W |  | 0140 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028430_0060 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240357 | S002 | 30 | 30 | 5300018552 | 60 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0120 | 0030 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10059002 | STUDBOLT;0.750"X110MM,L7,BLK | 20 | EA | 325 | 24 | 0 | 20 | EA | 02.12 - SOH @ AA02 | Supply for Order 100079012, Item 13 cannot be changed 90028429 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018551 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028429 | 05 | Preparation | 0000243763 | 13 | 0 | EA | 102000000031901 | 102000000033977 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028429_0090 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079012 |  | 0 | 2 | 0 | 90028429 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059002 | STUDBOLT;0.750"X110MM,L7,BLK | 2024-11-29 | W |  | 0120 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028429_0090 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 13 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240421 | S002 | 30 | 30 | 5300018551 | 90 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243763 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0140 | 0030 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10059002 | STUDBOLT;0.750"X110MM,L7,BLK | 20 | EA | 325 | 24 | 0 | 20 | EA | 02.12 - SOH @ AA02 | Supply for Order 100079106, Item 13 cannot be changed 90028430 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018552 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028430 | 05 | Preparation | 0000243730 | 13 | 0 | EA | 102000000033978 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028430_0080 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079106 |  | 0 | 2 | 0 | 90028430 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059002 | STUDBOLT;0.750"X110MM,L7,BLK | 2024-11-29 | W |  | 0140 | Install Return Header Covers | INT | Install Return Header Covers |  |  | 90028430_0080 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 13 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240357 | S002 | 30 | 30 | 5300018552 | 80 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0110 | 0020 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059002 | STUDBOLT;0.750"X110MM,L7,BLK | 32 | EA | 325 | 24 | 0 | 32 | EA | 15.01 - SOH @ AA02 | Supply for Order 200088516, Item 2 cannot be changed 90028586 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020032 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028586 | 05 | Preparation | 0000126825 | 2 | 0 | EA | 102000000033979 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028586_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028586 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059002 | STUDBOLT;0.750"X110MM,L7,BLK | 2025-01-14 | W |  | 0110 | Punchlist & Closeout WP200088516MET001 | ENON | Punchlist & Closeout WP200088516MET001 | 5 | Ready for Release | 90028586_0020 |  |  | ST5 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126175 | S002 | 30 | 30 | 5300020032 | 20 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126825 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0110 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10059011 | STUDBOLT;0.875"X140MM,L7,BLK | 12 | EA | 0 | 0 | 12 | 12 | EA | 29.01 - At KGP | Supply for Order 100087648, Item 12 cannot be changed 9026016 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180117451 | 9026016 | 05 | Preparation | 0000278190 | 12 | 0 | EA | 101000000134657 |  | 102000000030810 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-MATERIALS |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-22 | GRST-5000369231_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000054482 | 1020 | 2025-12-02 | 12 |  | 2025-01-22 | 4900216369_2025_0001 | 2025-03-01 | 5E2001 | 5000369231_2025_0001 | 0 | 2 | 0 | 90028417 | 12 | 0 | 180117451 | 2 | 0 | 0 | X | L | 4900216369 | 2025 |  | 5000369231 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059011 | STUDBOLT;0.875"X140MM,L7,BLK | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 9026016_0110 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 12 |  | 0 |  | 25SDSTB5 | MJ | 1000004846 | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 110 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-23 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0150 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10059014 | BLT STUD:0.875in,UNC,170mm,CARBON STEEL | 24 | EA | 39 | 0 | 2 | 24 | EA | 15.01 - SOH @ AA02 | Supply for Order 100087648, Item 16 cannot be changed 90028417 item 150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 16 | 0 | EA | 102000000030710 | 101000000134783 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059014 | BLT STUD:0.875in,UNC,170mm,CARBON STEEL | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0150 |  |  | ST5 |  | C2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 16 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 150 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0040 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059014 | BLT STUD:0.875in,UNC,170mm,CARBON STEEL | 15 | EA | 39 | 0 | 2 | 15 | EA | 20.02 - SOH @ AA01 | Supply for Order 200073951, Item 4 cannot be changed 90028585 item 40 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 4 | 0 | EA | 101000000145679 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 15 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059014 | BLT STUD:0.875in,UNC,170mm,CARBON STEEL | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0040 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 40 |  |  | 0 | 15 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0110 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059028 | STUDBOLT;1.125"X170MM,L7,BLK | 20 | EA | 73 | 0 | 32 | 20 | EA | 15.01 - SOH @ AA02 | Supply for Order 200073951, Item 11 cannot be changed 90028585 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 11 | 0 | EA | 102000000033902 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059028 | STUDBOLT;1.125"X170MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0110 |  |  | ST5 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 110 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0060 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059030 | STUDBOLT;1.125" X 200MM,L7,BLK | 33 | EA | 57 | 0 | 0 | 8 | EA | 24.02 - SOH @ AA02 | Supply for Order 200073951, Item 6 cannot be changed 90028585 item 60 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 6 | 0 | EA | 101000000147605 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 33 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059030 | STUDBOLT;1.125" X 200MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0060 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 |  | 5300020031 | 60 |  |  | 0 | 33 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0060 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059030 | STUDBOLT;1.125" X 200MM,L7,BLK | 33 | EA | 57 | 0 | 0 | 8 | EA | 24.02 - SOH @ AA02 | Supply for Order 200073951, Item 6 cannot be changed 90028585 item 60 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 6 | 0 | EA | 101000000142340 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 33 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059030 | STUDBOLT;1.125" X 200MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0060 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 |  | 5300020031 | 60 |  |  | 0 | 33 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0060 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059030 | STUDBOLT;1.125" X 200MM,L7,BLK | 33 | EA | 57 | 0 | 0 | 8 | EA | 24.02 - SOH @ AA02 | Supply for Order 200073951, Item 6 cannot be changed 90028585 item 60 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 6 | 0 | EA | 101000000147605 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 33 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059030 | STUDBOLT;1.125" X 200MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0060 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 |  | 5300020031 | 60 |  |  | 0 | 33 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0060 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059030 | STUDBOLT;1.125" X 200MM,L7,BLK | 33 | EA | 57 | 0 | 0 | 8 | EA | 24.02 - SOH @ AA02 | Supply for Order 200073951, Item 6 cannot be changed 90028585 item 60 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 6 | 0 | EA | 101000000142314 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 33 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059030 | STUDBOLT;1.125" X 200MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0060 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 |  | 5300020031 | 60 |  |  | 0 | 33 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0080 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | WO item has not been released yet | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 20 | EA | 55 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139208 | 10 | 0 | [8 empty] | WorkPackLink |  | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-08-01 | 0 |  |  |  |  | 100040704 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK |  |  |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000138559 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0070 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 55 | EA | 55 | 0 | 0 | 10 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 7 cannot be changed 90028585 item 70 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 7 | 0 | EA | 101000000142245 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 55 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 70 |  |  | 0 | 55 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0070 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 55 | EA | 55 | 0 | 0 | 10 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 7 cannot be changed 90028585 item 70 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 7 | 0 | EA | 101000000142246 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 55 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 70 |  |  | 0 | 55 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0070 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 55 | EA | 55 | 0 | 0 | 10 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 7 cannot be changed 90028585 item 70 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 7 | 0 | EA | 101000000142344 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 55 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 70 |  |  | 0 | 55 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0070 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 55 | EA | 55 | 0 | 0 | 10 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 7 cannot be changed 90028585 item 70 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 7 | 0 | EA | 101000000142347 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 55 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 70 |  |  | 0 | 55 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0070 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 55 | EA | 55 | 0 | 0 | 5 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 7 cannot be changed 90028585 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 7 | 0 | EA | 101000000142249 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 55 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0070 |  |  | ST5 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 70 |  |  | 0 | 55 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0070 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 55 | EA | 55 | 0 | 0 | 10 | EA | 19.02 - SOH @ AA02 | Supply for Order 200073951, Item 7 cannot be changed 90028585 item 70 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 7 | 0 | EA | 101000000142247 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 55 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0070 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 70 |  |  | 0 | 55 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-08-15 | 2025-03-01 |  | 2025-02-19 | 2025-03-03 | MECH | 600003215 | 0020 | 0060 | 600003215 | MOC-117109 1E1303 Exchanger Replacement | AA53.1E1303 | EXCH,HEAT AIR COOL REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK | 12 | EA | 55 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000254308 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059031 | STUDBOLT;1.125" X 230MM,L7,BLK |  |  |  | 0020 | Remove blanks For Inspection Access | INT | Remove blanks For Inspection Access |  | Management of Change |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000250524 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W35069 | 2024-08-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-02-19 | 2025-02-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0080 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 80 | EA | 40 | 0 | 0 | 5 | EA | 18.02 - SOH @ AA01 | Supply for Order 200073951, Item 8 cannot be changed 90028585 item 80 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 8 | 0 | EA | 101000000146104 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 80 |  |  | 0 | 80 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0080 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 80 | EA | 40 | 0 | 0 | 5 | EA | 18.02 - SOH @ AA01 | Supply for Order 200073951, Item 8 cannot be changed 90028585 item 80 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 8 | 0 | EA | 101000000145950 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 80 |  |  | 0 | 80 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0080 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 80 | EA | 40 | 0 | 0 | 5 | EA | 18.02 - SOH @ AA01 | Supply for Order 200073951, Item 8 cannot be changed 90028585 item 80 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 8 | 0 | EA | 101000000146036 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 80 |  |  | 0 | 80 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0080 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 80 | EA | 40 | 0 | 0 | 5 | EA | 18.02 - SOH @ AA01 | Supply for Order 200073951, Item 8 cannot be changed 90028585 item 80 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 8 | 0 | EA | 101000000145956 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 80 |  |  | 0 | 80 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0080 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 80 | EA | 40 | 0 | 0 | 5 | EA | 18.02 - SOH @ AA01 | Supply for Order 200073951, Item 8 cannot be changed 90028585 item 80 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 8 | 0 | EA | 101000000152493 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 80 |  |  | 0 | 80 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0080 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 80 | EA | 40 | 0 | 0 | 5 | EA | 18.02 - SOH @ AA01 | Supply for Order 200073951, Item 8 cannot be changed 90028585 item 80 already exists | Material picked; currently at SW3R01C03A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 8 | 0 | EA | 101000000145957 |  | 102000000034358 |  |  |  |  | WorkPackLink | SW3R01C03A | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 80 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 80 |  |  | 0 | 80 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0080 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 80 | EA | 40 | 0 | 0 | 5 | EA | 18.02 - SOH @ AA01 | Supply for Order 200073951, Item 8 cannot be changed 90028585 item 80 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 8 | 0 | EA | 101000000145953 |  | 101000000148055 | 01-Road |  | 5-Completed |  | WorkPackLink |  | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 80 | 2025-02-27 | 2025-02-26 | Y | 1001 | 2025-01-14 | ODST-0090028585_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059045 | STUDBOLT;1.500" X 230MM,L7,BLK | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0080 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ | 20005551 | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 80 |  |  | 0 | 80 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-24 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDDG1 | Released | 2024-10-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200160315 | 0050 | 0040 | 200160315 | 10Y INSPECT 16" 600# 124CHV0792 | AA53.124CHV0792 | VALVE,CHECK U2401 3RD STG COMP BYPASS | AA01 | 10 | WO item has not been released yet | 10059051 | STUDBOLT;1.625" X 290MM,L7,BLK | 40 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255547 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  |  |  |  | 200160315 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059051 | STUDBOLT;1.625" X 290MM,L7,BLK |  |  |  | 0050 | Install NRV | INT | Install NRV | 5 | Ready for Release |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000251636 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2540 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10059143 | NUT,HEX,0.500",SS410,13 UNC | 56 | EA | 68 | 0 | 0 | 56 | EA | 10.01 - SOH @ AA02 | Supply for Order 200091513, Item 560 cannot be changed 90028419 item 4050 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4080 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 560 | 0 | EA | 102000000030385 | 102000000030193 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 56 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059143 | NUT,HEX,0.500",SS410,13 UNC | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_4050 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 560 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4080 |  |  | 0 | 56 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0170 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10059176 | NUT;HEX,M6,ISO,MTR,SS316 | 1 | BOX | 1 | 0 | 1 | 1 | BOX | 19.02 - SOH @ AA02 | Supply for Order 600001416, Item 17 cannot be changed 90030040 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 17 | 0 | BOX | 101000000143777 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059176 | NUT;HEX,M6,ISO,MTR,SS316 | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0120 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 17 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 |  | 30 | 5300004566 | 130 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0160 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10059178 | NUT,HEX,M10,ISO MTR,SS316,1.5MM PITCH | 1 | BOX | 3 | 0 | 1 | 1 | BOX | 28.01 - ETA 14.02.25 PO 4500043860 ex Konnect | Supply for Order 600001416, Item 16 cannot be changed 90030040 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 16 | 0 | BOX | 102000000034126 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059178 | NUT,HEX,M10,ISO MTR,SS316,1.5MM PITCH | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0110 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 16 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 | 30 | 30 | 5300004566 | 120 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-05-18 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0040 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2024) | 10059179 | NUT,HEX;M12,ISO MTR,SS316 | 1 | BOX | 1 | 0 | 3 | 1 | BOX | 02.10 - At KGP | Supply for Order 600001290, Item 7 cannot be changed 180032088 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  | 180032088 | 9004359 | 05 | Preparation | 0000084206 | 7 | 0 | BOX |  |  | 101000000043529 |  |  |  |  | WorkPackLink | P08C06C2 | AA53-P08-LN | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-02-12 | GRST-5000103099_2024 | 0 | 0 | 0 | 0 |  | 2024-05-19 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000011643 | 1020 | 2024-05-13 | 1 |  | 2024-06-05 | 4900070136_2024_0001 | 2024-05-21 |  | 5000103099_2024_0001 | 0 | 2 | 0 | 90006510 | 1 | 0 | 180032088/180101031 | 2 | 0 | 0 | X | L | 4900070136 | 2024 |  | 5000103099 | 2024 | 0 |  | 2024-05-18 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059179 | NUT,HEX;M12,ISO MTR,SS316 | 2024-03-06 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9004359_0050 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083560 | S002 |  | 30 | 5300006479 | 50 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2024-05-18 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0090 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10059204 | SCREW,MACH,M6 X 30MM,SS,SLOTTED,CSK HD | 1 | EA | 1 | 0 | 0 | 1 | EA | 25.02 - SOH @ AA02 | Supply for Order 600001416, Item 9 cannot be changed 90030040 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 9 | 0 | EA | 101000000148354 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059204 | SCREW,MACH,M6 X 30MM,SS,SLOTTED,CSK HD | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0040 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 | 30 | 30 | 5300004566 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0310 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10059298 | SCREW,MACH,HEX,M20 X 40MM,1.5MM,CS | 16 | EA | 116 | 0 | 0 | 16 | EA | 24.09 - SOH at AA02 | Supply for Order 200147980, Item 131 cannot be changed 90028418 item 460 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 131 | 0 | EA | 102000000030531 | 102000000030945 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0460 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059298 | SCREW,MACH,HEX,M20 X 40MM,1.5MM,CS | 2024-09-23 | W |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  | 90028418_0460 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 131 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 470 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0110 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10059312 | SCREW,SELF TAP,NO.10 X 13MM,PAN,PHIL,SS | 5 | BOX | 477 | 10 | 70 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 11 cannot be changed 90032376 item 110 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 11 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0110 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059312 | SCREW,SELF TAP,NO.10 X 13MM,PAN,PHIL,SS | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0110 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 11 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 |  | 30 | 5300022012 | 110 |  |  | 0 | 5 | BOX | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0120 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10059315 | SCREW,SELF TAP,NO.10 X 19MM,PAN,PHIL,SS | 5 | BOX | 2 | 1 | 0 | 0 |  | DEL: 80033610 | Supply for Order 100090053, Item 12 cannot be changed 90032376 item 120 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 12 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0120 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059315 | SCREW,SELF TAP,NO.10 X 19MM,PAN,PHIL,SS | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0120 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 12 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 120 |  |  | 0 | 5 | BOX | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0270 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10059315 | SCREW,SELF TAP,NO.10 X 19MM,PAN,PHIL,SS | 2 | BOX | 2 | 1 | 0 | 2 | BOX | 02.03 - SOH @ AA02 | Supply for Order 500005166, Item 47 cannot be changed 90031501 item 280 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 430 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 47 | 0 | BOX | 101000000150345 |  | 101000000150366 | 01-Road |  | 5-Completed |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 | 2025-03-04 | 2025-03-02 | Y | 1001 | 2025-02-13 | ODST-0090031501_0280 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059315 | SCREW,SELF TAP,NO.10 X 19MM,PAN,PHIL,SS | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0280 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 47 |  | 0 |  | 25SDENA1 | MJ | 20005471 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 430 |  |  | 0 | 2 | BOX | 2001 | AA02 | 2025-03-27 |  |  | 2025-02-28 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0110 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10059411 | WASHER,FLAT,RND,6MM,NORM,SS316 | 1 | BOX | 1 | 0 | 1 | 1 | BOX | 19.02 - SOH @ AA02 | Supply for Order 600001416, Item 11 cannot be changed 90030040 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 11 | 0 | BOX | 101000000143230 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059411 | WASHER,FLAT,RND,6MM,NORM,SS316 | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0060 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 11 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 |  | 30 | 5300004566 | 70 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0140 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10059413 | WASHER,FLAT;RND,10MM,NORM,SS316 | 1 | BOX | 1 | 0 | 0 | 0 |  | 28.01 - qty 1 SOH @ AA02 | Supply for Order 600001416, Item 14 cannot be changed 90030040 item 90 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 14 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059413 | WASHER,FLAT;RND,10MM,NORM,SS316 | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0090 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 14 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 | 30 | 30 | 5300004566 | 100 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-01-02 | 2024-09-23 | 2024-05-19 | 2025-05-08 | 2025-05-08 | ROTAT | 600001290 | 0010 | 0030 | 600001290 | MOC-113604 Install BD LNG4 Turbines | AA53.4KT1410V6A | ACC,VESSEL HYD OIL 4KT1410 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.03.2024) | 10059414 | WASHER,FLAT;RND,12MM,NORM,SS316 | 1 | BOX | 1 | 0 | 1 | 1 | BOX | 02.10 - At KGP | Supply for Order 600001290, Item 6 cannot be changed 180029529 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006479 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  | 180029529 | 9004205 | 05 | Preparation | 0000084206 | 6 | 0 | BOX | 102000000006931 | 102000000007113 | 102000000007333 |  |  |  | LP-NWS-01 | WorkPackLink | P08YRDBAY6 | AA53-P08-LN | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-02-12 |  | 0 | 0 | 0 | 0 |  | 2024-05-19 | AA53 | 2025-05-08 |  |  | 2024-09-23 |  |  | 100000013638 | 1020 | 2024-05-13 | 1 |  | 2024-06-19 | 4900076307_2024_0003/4900076149_2024_0003/4900066750_2024_0003 | 2024-05-21 |  | 5000122818_2024_0002 | 0 | 2 | 0 | 90006510 | 1 | 0 | 180029529/180101031 | 2 | 0 | 0 | X | L | 4900076307 | 2024 |  | 5000122818 | 2024 | 0 |  | 2024-05-19 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059414 | WASHER,FLAT;RND,12MM,NORM,SS316 | 2024-03-06 | W |  | 0010 | Fabricate Brackets | INT | Fabricate Brackets |  | Management of Change | 9004205_0040 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000083560 | S002 | 30 | 30 | 5300006479 | 40 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2024-05-19 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84206 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 2 | Very High | RC00018003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-31 | INLEC | 600001416 | 0020 | 0150 | 600001416 | MOC-117240 Replace Gas Det (6) 1KT1410 | AA53.160QE501A | DET,GAS IR,1KT1410 TURBINE AIR INLET | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10059435 | WASHER,SPRG;SNGL COIL,10MM,SS316 | 1 | BOX | 4 | 0 | 2 | 1 | BOX | 28.01 - qty 2 SOH @ AA02 | Supply for Order 600001416, Item 15 cannot be changed 90030040 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004566 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  |  | 90030040 | 05 | Preparation | 0000084298 | 15 | 0 | BOX | 102000000032264 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030040_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT1410 |  | 0 | 2 | 0 | 90030040 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059435 | WASHER,SPRG;SNGL COIL,10MM,SS316 | 2025-01-23 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030040_0100 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000083768 | S002 | 30 | 30 | 5300004566 | 110 |  |  | 0 | 1 | BOX | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM06 | Capital
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10059442 | WASHER,FLAT;RND,0.500",NARROW,LTCS | 68 | EA | 1 | 0 | 0 | 1 | EA | 15.10 - ETA 19.03.25 PO 4500031012 BH | Supply for Order 200091513, Item 354 cannot be changed 90028419 item 2740 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2770 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 354 | 0 | EA | 102000000030495 | 102000000030366 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 68 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059442 | WASHER,FLAT;RND,0.500",NARROW,LTCS | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2740 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 354 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2770 |  |  | 0 | 68 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1370 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10059443 | WASHER,FLAT,RND,0.750" X 0.125"THK,C45 | 32 | EA | 108 | 0 | 0 | 32 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 179 cannot be changed 90028419 item 1350 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 179 | 0 | EA | 102000000030498 | 102000000030364 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1350 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059443 | WASHER,FLAT,RND,0.750" X 0.125"THK,C45 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1350 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 179 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1380 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0050 | 0330 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10059458 | WASHER,FLAT,RND,21 X 37 X 3MM THK,CS | 8 | EA | 24 | 0 | 0 | 8 | EA | 15.10 - SOH @ AA02 | Supply for Order 200147980, Item 133 cannot be changed 90028418 item 470 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 480 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 133 | 0 | EA | 102000000030531 | 102000000030286 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0470 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059458 | WASHER,FLAT,RND,21 X 37 X 3MM THK,CS | 2024-09-23 | W |  | 0050 | CROSSHEAD RH/LH | INT | CROSSHEAD RH/LH | 5 |  | 90028418_0470 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 133 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 480 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0035 | 0040 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10059550 | CLAMP,TUBE;SNGL,9.5MM,PA,SS316 | 6 | EA | 70 | 0 | 8 | 6 | EA | 02.10 - SOH @ AA02 | Supply for Order 600001792, Item 7 cannot be changed 90024967 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004604 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024967 | 05 | Preparation | 0000084710 | 7 | 0 | EA | 102000000032121 | 102000000029697 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024967_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118UCV112 |  | 0 | 2 | 0 | 90024967 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059550 | CLAMP,TUBE;SNGL,9.5MM,PA,SS316 | 2024-01-02 | W |  | 0035 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90024967_0040 |  |  | FR1 |  | C3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000084094 | S002 |  | 30 | 5300004604 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84710 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1120 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10059585 | HELICOIL,0.25"UNC X 1.5 DIA LG,INCON,LK | 31 | EA | 110 | 0 | 0 | 31 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 135 cannot be changed 90028419 item 1090 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 135 | 0 | EA | 102000000030480 | 102000000030069 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059585 | HELICOIL,0.25"UNC X 1.5 DIA LG,INCON,LK | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1090 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 135 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1100 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0100 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10059875 | TAPE:SS THD SEAL,6.5mm,PTFE/NI | 40 | ROL | 52 | 1 | 135 | 40 | ROL | 20.02 - SOH @ AA02 | Supply for Order 500004676, Item 10 cannot be changed 9028889 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180134056 | 9028889 | 07 | Execution | 0000278102 | 10 | 0 | ROL |  |  | 102000000034474 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-12 | GRST-5000434885_2025 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060557 | 1020 | 2025-12-31 | 40 |  | 2025-03-10 | 4900263464_2025_0001 | 2025-04-01 | TA OPS/BAILS | 5000434885_2025_0001 | 0 | 2 | 0 | 90031855 | 40 | 0 | 180134056 | 2 | 0 | 0 | X | L | 4900263464 | 2025 |  | 5000434885 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059875 | TAPE:SS THD SEAL,6.5mm,PTFE/NI | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 9028889_0090 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 100 |  |  | 0 | 40 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 1040 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10059944 | SHEET;1200X1.5MM,RBR,BLK | 2 | M | 10 | 0 | 5 | 0 |  | 27.09 - qty 15 SOH at AA01 | Supply for Order 200147980, Item 104 cannot be changed 90028418 item 260 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 104 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059944 | SHEET;1200X1.5MM,RBR,BLK | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0260 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 104 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 270 |  |  | 0 | 2 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 1060 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10059944 | SHEET;1200X1.5MM,RBR,BLK | 18 | M | 10 | 0 | 5 | 10 | M | 17.02 - SOH @ AA01 | Supply for Order 200147980, Item 191 cannot be changed 90030872 item 10 already exists | Material picked; currently at 30-03-05-80A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 950 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90030872 | 05 | Preparation | 0000236589 | 191 | 0 | M |  |  | 101000000050857 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-05-80A |  | 0 |  | 0 | 0 |  | 0 | 18 | 2025-02-27 | 2025-02-27 | Y | 1001 | 2024-09-24 | ODST-0090030872_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030872 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059944 | SHEET;1200X1.5MM,RBR,BLK | 2025-02-14 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90030872_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 191 |  | 0 |  | 25SDSTB5 | MJ | 20005559 | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 950 |  |  | 0 | 18 | M | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-25 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-03-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005190 | 0010 | 0010 | 500005190 | KGP 2025 Rotating Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 30 | No Issue identified | 10059945 | RUBBER,NATURAL,1200MMX3.2MM THK,10M ROLL | 10 | M | 40 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022062 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90032308 | 05 | Preparation | 0000299465 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-03-05 | ODST-0090032308_0010 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-12 | 0 |  | 2025-03-27 |  | 2025-04-01 |  |  | 0 | 2 | 0 | 90032308 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059945 | RUBBER,NATURAL,1200MMX3.2MM THK,10M ROLL |  |  |  | 0010 | KGP 2025 Rotating Consumables | NCNF | KGP 2025 Rotating Consumables |  |  | 90032308_0010 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000292874 | S002 |  | 30 | 5300022062 | 10 |  |  | 0 | 10 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2025-03-05 | 299465 | 0 | 0 |  | 1020 | 3 |  |  | 5 | Low | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0070 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10059951 | JOINTING,1.5M X 2M X 1.50MM,C4500,CNAF | 1 | SHT | 2 | 0 | 0 | 1 | SHT | 24.09 - qty 1 SOH at AA01 | Supply for Order 200091108, Item 112 cannot be changed 90028420 item 750 already exists | Material picked; currently at SW3R02F01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 780 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 112 | 0 | SHT |  |  | 101000000113773 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R02F01A |  | 0 |  | 0 | 0 |  | 0 | 1 | 2025-01-24 | 2025-01-24 | Y | 1001 | 2024-07-20 | ODST-0090028420_0750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | E2 SO Tank |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059951 | JOINTING,1.5M X 2M X 1.50MM,C4500,CNAF | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0750 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 112 |  | 0 |  | 25SD2420 | MJ | 20005251 | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 780 |  |  | 0 | 1 | SHT | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-22 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-14 | 2025-02-28 | 2025-02-23 | 2025-02-28 | 2025-03-02 | MECH | 200147113 | 0030 | 0010 | 200147113 | 16Y VE/SH INSP RVI 1K2420E2 | AA53.1K2420E2 | TANK,SEAL OIL RESERVOIR FOR 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.01.2025) | 10059951 | JOINTING,1.5M X 2M X 1.50MM,C4500,CNAF | 1 | SHT | 2 | 0 | 0 | 1 | SHT | 10.03 - SOH @ AA02 | Supply for Order 200147113, Item 1 cannot be changed 90030015 item 10 already exists | Material picked; currently at 30-03-05-80A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300020231 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  |  | 90030015 | 05 | Preparation | 0000235384 | 1 | 0 | SHT |  |  | 101000000148056 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-05-80A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2025-02-27 | 2025-02-27 | Y | 1001 | 2025-01-20 | ODST-0090030015_0010 | 0 | 0 | 0 | 0 |  | 2025-02-26 | AA53 | 2025-02-28 |  |  | 2025-02-28 |  |  |  |  | 2025-07-15 | 0 |  | 2025-02-23 |  | 2025-02-28 | 200147113 |  | 0 | 2 | 0 | 90030015 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-23 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059951 | JOINTING,1.5M X 2M X 1.50MM,C4500,CNAF | 2025-01-20 | W |  | 0030 | Open Lid Access | INT | Open Lid Access |  |  | 90030015_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ | 20005556 | AU1072 | 1000232427 | S002 |  | 30 | 5300020231 | 10 |  |  | 0 | 1 | SHT | 2001 | AA02 | 2025-02-23 |  |  | 2025-02-25 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235384 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0152 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10060109 | GASKET;572 X 650 X 1.6MM,FF,CTD,C4400 | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 104 cannot be changed 90023534 item 560 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 104 | 0 | EA | 102000000030053 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | crkseal ring |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060109 | GASKET;572 X 650 X 1.6MM,FF,CTD,C4400 | 2024-05-11 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 90023534_0560 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 104 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 830 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2270 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060176 | GASKET:CNAF,250 X 310 X 1.5MM,RF,C4430 | 1 | EA | 4 | 0 | 0 | 1 | EA | 10.01 - SOH @ AA02 | Supply for Order 200091513, Item 306 cannot be changed 90028419 item 2390 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 306 | 0 | EA | 102000000030651 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2390 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060176 | GASKET:CNAF,250 X 310 X 1.5MM,RF,C4430 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2390 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 306 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2420 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060176 | GASKET:CNAF,250 X 310 X 1.5MM,RF,C4430 | 2 | EA | 4 | 0 | 0 | 2 | EA | 10.01 - SOH @ AA02 | Supply for Order 200091513, Item 611 cannot be changed 90028419 item 4150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 611 | 0 | EA | 102000000030652 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060176 | GASKET:CNAF,250 X 310 X 1.5MM,RF,C4430 | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4150 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 611 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4180 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0210 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060187 | GASKET;CNAF,49 X 85.5 X 1.5MM,RF,C4400 | 2 | EA | 4 | 0 | 0 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 200147980, Item 180 cannot be changed 90028418 item 870 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 900 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 180 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0870 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Crosshead |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060187 | GASKET;CNAF,49 X 85.5 X 1.5MM,RF,C4400 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0870 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 180 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 900 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0100 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060187 | GASKET;CNAF,49 X 85.5 X 1.5MM,RF,C4400 | 1 | EA | 4 | 0 | 0 | 1 | EA | 24.02 - SOH @ AA02 | Supply for Order 200147980, Item 169 cannot be changed 90028418 item 760 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 169 | 0 | EA | 102000000030535 | 102000000033498 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0760 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | frame gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060187 | GASKET;CNAF,49 X 85.5 X 1.5MM,RF,C4400 | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0760 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 169 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 790 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0020 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060193 | GASKET;150MM,168MM,279MM,CNAF,RF | 2 | EA | 13 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 604 cannot be changed 90028419 item 4110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 604 | 0 | EA | 102000000030387 | 102000000030354 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060193 | GASKET;150MM,168MM,279MM,CNAF,RF | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4110 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 604 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4140 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-14 | 2025-02-27 | 2025-02-22 | 2025-02-25 | 2025-03-13 | MECH | 200147078 | 0040 | 0010 | 200147078 | MOC-104398 4Y INSP INT EXCH 1K2420E4 | AA53.1K2420E4 | EXCH,HEAT SEAL OIL COOLER 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.01.2025) | 10060239 | GASKET,CNAF,305 X 338,1.5MM,CNTR BAR 6MM | 1 | EA | 7 | 5 | 0 | 1 | EA | 28.01 - qty 12 SOH @ AA02 | Supply for Order 200147078, Item 1 cannot be changed 90029997 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300020333 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027117 | 05 | Preparation | 0000235349 | 1 | 0 | EA | 102000000032238 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-22 | GIST-4900234111_2025 | 0 | 0 | 0 | 0 |  | 2025-02-25 | AA53 | 2025-02-27 |  |  | 2025-02-27 |  |  | 100000056763 | 1020 | 2025-09-16 | 1 |  | 2025-02-11 | 4900234111_2025_0001 | 2025-02-27 |  |  | 0 | 2 | 0 | 90029997 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234111 | 2025 |  |  | 0 | 0 |  | 2025-02-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060239 | GASKET,CNAF,305 X 338,1.5MM,CNTR BAR 6MM | 2025-01-22 | W |  | 0040 | Remove Bonnet / Spools & Install Blinds | INT | Remove Bonnet / Spools & Install Blinds |  |  | 9027117_0010 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232392 | S002 |  | 30 | 5300020333 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235349 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-13 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 4 | EA | 8 | 1 | 0 | 3 | EA | 02.03 - SOH @ AA02 | Supply for Order 200091513, Item 606 cannot be changed 90028419 item 4130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 606 | 0 | EA | 102000000030353 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4130 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 606 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4160 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 2 | EA | 8 | 1 | 0 | 2 | EA | 15.10 - SOH @ AA02 | Supply for Order 200091513, Item 534 cannot be changed 90028419 item 3870 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3900 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 534 | 0 | EA |  |  | 102000000030352 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3870 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_3870 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 534 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3900 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 4 | EA | 8 | 1 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 200091513, Item 606 cannot be changed 90028419 item 4130 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 606 | 0 | EA |  |  | 102000000031279 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4130 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 606 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4160 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-02 | MECH | 200147079 | 0030 | 0010 | 200147079 | 4Y INSP INT EXCHANGER 1KKT2420E3 | AA53.1KKT2420E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2420 | AA01 | 10 | Shipped qty below requirement qty | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 2 | EA | 8 | 1 | 0 | 1 | EA | 20.01 - SOH @ AA02 | Supply for Order 200147079, Item 1 cannot be changed 90030058 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300020191 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027119 | 05 | Preparation | 0000235350 | 1 | 0 | EA | 102000000032234 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-20 | GIST-4900234121_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-28 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-09-16 | 1 |  | 2025-02-11 | 4900234121_2025_0001 | 2025-03-01 | 200147079 |  | 0 | 2 | 0 | 90030058 | 0 | 0 |  | 1 | 0 | 0 | X | L | 4900234121 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 2025-01-19 | W |  | 0030 | Remove Bonnet / Spools & Install Blinds | INT | Remove Bonnet / Spools & Install Blinds |  |  | 90030058_0010/9027119_0010 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232393 | S002 |  | 30 | 5300020191 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235350 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200174926 | 0030 | 0010 | 200174926 | Replace Exchanger - 1KKT2430E3 | AA53.1KKT2430E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2430 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 2 | EA | 8 | 1 | 0 | 2 | EA | 15.10 - SOH @ AA02 | Supply for Order 200174926, Item 2 cannot be changed 90028606 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020026 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028606 | 05 | Preparation | 0000277561 | 2 | 0 | EA |  |  | 102000000031278 |  |  |  |  | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028606_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-07-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174926 |  | 0 | 2 | 0 | 90028606 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060240 | GASKET,CNAF,441 X 478 X 2.0MM,BAR | 2025-01-14 | W |  | 0030 | Remove Bonnet / Spools & Structure | INT | Remove Bonnet / Spools & Structure |  |  | 90028606_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000272048 | S002 |  | 30 | 5300020026 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277561 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146436 | 0010 | 0020 | 200146436 | 1Y Cond Prod Pump Service - 5P2002B | AA53.5P2002B | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10060263 | GASKET,CNAF,35.5 X 48 X 1.5MM | 4 | EA | 16 | 0 | 0 | 4 | EA | 16.12 - qty 32 SOH @ AA02 | Supply for Order 200146436, Item 2 cannot be changed 90025016 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015715 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025016 | 05 | Preparation | 0000234313 | 2 | 0 | EA | 102000000031887 | 102000000031696 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025016_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025016 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060263 | GASKET,CNAF,35.5 X 48 X 1.5MM | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025016_0020 |  |  | ST5 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231369 | S002 |  | 30 | 5300015715 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234313 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146437 | 0010 | 0020 | 200146437 | 1Y Cond Prod Pump Service - 5P2002A | AA53.5P2002A | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10060263 | GASKET,CNAF,35.5 X 48 X 1.5MM | 4 | EA | 16 | 0 | 0 | 4 | EA | 16.12 - qty 32 SOH @ AA02 | Supply for Order 200146437, Item 2 cannot be changed 90025015 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015714 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025015 | 05 | Preparation | 0000234314 | 2 | 0 | EA | 102000000031890 | 102000000031698 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025015_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025015 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060263 | GASKET,CNAF,35.5 X 48 X 1.5MM | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025015_0020 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231370 | S002 |  | 30 | 5300015714 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234314 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146438 | 0010 | 0020 | 200146438 | 1Y Cond Heater Pump Service - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10060263 | GASKET,CNAF,35.5 X 48 X 1.5MM | 4 | EA | 16 | 0 | 0 | 4 | EA | 16.12 - qty 32 SOH @ AA02 | Supply for Order 200146438, Item 2 cannot be changed 90025014 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015713 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025014 | 05 | Preparation | 0000234315 | 2 | 0 | EA | 102000000031900 | 102000000031697 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025014_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025014 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060263 | GASKET,CNAF,35.5 X 48 X 1.5MM | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 | Ready for Release | 90025014_0020 |  |  | ST5 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231371 | S002 |  | 30 | 5300015713 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234315 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146439 | 0010 | 0020 | 200146439 | 1Y Cond Heater Pump Service - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10060263 | GASKET,CNAF,35.5 X 48 X 1.5MM | 4 | EA | 16 | 0 | 0 | 4 | EA | 16.12 - qty 32 SOH @ AA02 | Supply for Order 200146439, Item 2 cannot be changed 90025013 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015712 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025013 | 05 | Preparation | 0000234316 | 2 | 0 | EA | 102000000031907 | 102000000031699 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025013_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025013 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060263 | GASKET,CNAF,35.5 X 48 X 1.5MM | 2024-09-24 | W |  | 0010 | Annual PM Stab Heater Pump | INT | Annual PM Stab Heater Pump | 5 |  | 90025013_0020 |  |  | ST5 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231372 | S002 |  | 30 | 5300015712 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234316 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0040 | 0082 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10060289 | GASKET;118MM,145MM,KLINGERSIL - C4430 | 2 | EA | 8 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 25 cannot be changed 90023534 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 25 | 0 | EA | 102000000030454 | 102000000031091 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060289 | GASKET;118MM,145MM,KLINGERSIL - C4430 | 2024-01-02 | W |  | 0040 | CONROD SUB-ASSEMBLY | INT | CONROD SUB-ASSEMBLY | 5 |  | 90023534_0170 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 25 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 240 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0020 | 0082 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10060289 | GASKET;118MM,145MM,KLINGERSIL - C4430 | 4 | EA | 8 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 8 cannot be changed 90023534 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 8 | 0 | EA | 102000000030435 | 102000000031102 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060289 | GASKET;118MM,145MM,KLINGERSIL - C4430 | 2024-01-02 | W |  | 0020 | FRAME SUB-ASSEMBLY | INT | FRAME SUB-ASSEMBLY | 5 |  | 90023534_0010 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 80 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0130 | 0012 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10060289 | GASKET;118MM,145MM,KLINGERSIL - C4430 | 2 | EA | 8 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 49 cannot be changed 90023534 item 210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 49 | 0 | EA | 102000000030453 | 102000000031100 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060289 | GASKET;118MM,145MM,KLINGERSIL - C4430 | 2024-01-02 | W |  | 0130 | PRIMARY, INTER & OIL SCRAPER SEALS | INT | PRIMARY, INTER & OIL SCRAPER SEALS |  |  | 90023534_0210 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 49 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 390 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060350 | GASKET;CNAF,25MM,CL300,RF,1.5MM,1.0% PSM | 8 | EA | 17 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 378 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060350 | GASKET;CNAF,25MM,CL300,RF,1.5MM,1.0% PSM |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0030 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060355 | GASKET;CNAF,100MM,CL300,RF,1.5MM,1.0% P+ | 2 | EA | 5 | 0 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 10 cannot be changed 90028583 item 100 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 10 | 0 | EA | 102000000031259 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060355 | GASKET;CNAF,100MM,CL300,RF,1.5MM,1.0% P+ | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0100 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 |  | 30 | 5300020057 | 100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0030 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060355 | GASKET;CNAF,100MM,CL300,RF,1.5MM,1.0% P+ | 2 | EA | 5 | 0 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 3 cannot be changed 90028584 item 30 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 3 | 0 | EA | 102000000031258 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060355 | GASKET;CNAF,100MM,CL300,RF,1.5MM,1.0% P+ | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0030 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 |  | 30 | 5300020058 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0020 | 0040 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 4 | EA | 63 | 0 | 28 | 4 | EA | 27.09 - qty 75 SOH at AA02 | Supply for Order 200089884, Item 4 cannot be changed 90024984 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024984 | 05 | Preparation | 0000128153 | 4 | 0 | EA | 102000000026931 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-05-08 | ODST-0090024984_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-16 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024984 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 2024-05-08 | W |  | 0020 | Install Spades | INT | Install Spades | 5 | Order Requires Replanning | 90024984_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 40 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0130 | 0020 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 8 | EA | 63 | 0 | 28 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089887, Item 7 cannot be changed 90025037 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 7 | 0 | EA | 102000000031999 | 102000000026935 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | BleedAirPipe |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 2024-10-16 | W |  | 0130 | Mechanical Preparation for Waterwash | INT | Mechanical Preparation for Waterwash | 5 | Ready for Release | 90025037_0070 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 70 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0120 | 0020 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 8 | EA | 63 | 0 | 28 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089888, Item 10 cannot be changed 90025038 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025038 | 05 | Preparation | 0000128157 | 10 | 0 | EA | 102000000032002 | 102000000026936 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025038_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025038 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025038_0040 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 40 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0120 | 0010 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 8 | EA | 63 | 0 | 28 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089889, Item 10 cannot be changed 90025039 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 10 | 0 | EA | 102000000032028 | 102000000026932 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025039_0040 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 40 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-06-01 | 2025-05-27 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0120 | 0030 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 8 | EA | 63 | 0 | 28 | 8 | EA | 18.10 - SOH @ AA02 | Supply for Order 200089890, Item 19 cannot be changed 90025060 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025060 | 05 | Preparation | 0000128159 | 19 | 0 | EA | 102000000032017 | 102000000026934 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025060_0020 | 0 | 0 | 0 | 0 |  | 2025-05-30 | AA53 | 2025-03-01 |  |  | 2025-06-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-05-27 |  | 2025-06-01 | Isolations |  | 0 | 2 | 0 | 90025060 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025060_0020 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 19 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 50 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-05-27 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0120 | 0030 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 8 | EA | 63 | 0 | 28 | 8 | EA | 18.10 - SOH @ AA02 | Supply for Order 200089891, Item 13 cannot be changed 90025062 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025062 | 05 | Preparation | 0000128160 | 13 | 0 | EA | 102000000032020 | 102000000026933 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025062_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060384 | GASKET;CNAF,100MM,CL150,RF,1.5MM,1.0%PSM | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025062_0060 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 60 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0040 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060386 | GASKET;CNAF,150MM,CL150,1.5MM,RF,1.0%PSM | 8 | EA | 50 | 0 | 8 | 8 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 11 cannot be changed 90028583 item 110 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 11 | 0 | EA | 102000000031583 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060386 | GASKET;CNAF,150MM,CL150,1.5MM,RF,1.0%PSM | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0110 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 |  | 30 | 5300020057 | 110 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0040 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060386 | GASKET;CNAF,150MM,CL150,1.5MM,RF,1.0%PSM | 8 | EA | 50 | 0 | 8 | 8 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 4 cannot be changed 90028584 item 40 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 4 | 0 | EA | 102000000031582 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060386 | GASKET;CNAF,150MM,CL150,1.5MM,RF,1.0%PSM | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0040 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 |  | 30 | 5300020058 | 40 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200088517 | 0100 | 0070 | 200088517 | 8Y P01 INT INSP PRESS VESSEL 5V2004 | AA53.5V2004 | VE,FUEL GAS KNOCK OUT DRUM | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060391 | GASKET;CNAF,450MM,CL150,1.5MM,RF,1.0%PSM | 1 | EA | 8 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200088517, Item 8 cannot be changed 90028592 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020030 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028592 | 05 | Preparation | 0000126826 | 8 | 0 | EA | 102000000033543 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028592_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200088517 |  | 0 | 2 | 0 | 90028592 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060391 | GASKET;CNAF,450MM,CL150,1.5MM,RF,1.0%PSM | 2025-01-14 | W |  | 0100 | Re-instate Vessel head / Spools | INT | Re-instate Vessel head / Spools |  |  | 90028592_0020 |  |  | ST5 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126176 | S002 | 30 | 30 | 5300020030 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126826 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-05-01 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147107 | 0010 | 0010 | 200147107 | 1Y F06 SIF ESD F/TEST (4) 1K2430 | AA53.124HE22 | SW,ROTARY 1K2430 EMERG TRIP CCR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(30.04.2024) | 10060397 | GASKET;CNAF,25MM,CL150,1.5MM,RF,1.0% PSM | 1 | EA | 62 | 2 | 0 | 1 | EA | 02.10 - SOH @ AA02 | Supply for Order 200147107, Item 1 cannot be changed 90024978 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300009667 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124187 | 90024978 | 05 | Preparation | 0000235358 | 1 | 0 | EA | 102000000032158 | 102000000027095 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-01 | IDST-0180124187 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-06-16 | 1 |  | 2025-02-11 | 4900234105_2025_0001 | 2025-03-01 |  |  | 0 | 2 | 0 | 90024978 | 0 | 0 | 180124187 | 2 | 0 | 0 | X | L | 4900234105 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060397 | GASKET;CNAF,25MM,CL150,1.5MM,RF,1.0% PSM | 2024-04-30 | W |  | 0010 | Operations Assistance | INT | Operations Assistance | 5 |  | 90024978_0010 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232421 | S002 | 30 | 30 | 5300009667 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235358 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Material shortage/Printed/Released/Settlement rule created/Pre-costed/Object created/Date set by external system | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2520 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060400 | GASKET;CNAF,65MM,CL150,1.5MM,RF,1.0% PSM | 10 | EA | 31 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 379 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060400 | GASKET;CNAF,65MM,CL150,1.5MM,RF,1.0% PSM |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 1030 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060449 | GASKET;220MM,240MM,KLINGERSIL - C4500 | 1 | EA | 7 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 103 cannot be changed 90028418 item 250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 103 | 0 | EA | 102000000030539 | 102000000030880 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060449 | GASKET;220MM,240MM,KLINGERSIL - C4500 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0250 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 103 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0080 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060451 | GASKET;CNAF,19.5 X 30.0 X 1.6MM,GR | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 16.04.25 PO 4500043754 Flowserve CPT | Supply for Order 100079771, Item 8 cannot be changed 90028600 item 60 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060451 | GASKET;CNAF,19.5 X 30.0 X 1.6MM,GR | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0060 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 |  | 30 | 5300020063 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0200 | 0810 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060458 | GASKET,METALLIC;21.0 X 29.0 X 0.9MM,AL | 24 | EA | 101 | 0 | 0 | 24 | EA | 24.09 - SOH at AA02 | Supply for Order 200147980, Item 117 cannot be changed 90028418 item 360 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 117 | 0 | EA | 102000000030549 | 102000000030889 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0360 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060458 | GASKET,METALLIC;21.0 X 29.0 X 0.9MM,AL | 2024-09-23 | W |  | 0200 | SUCTION VALVE ASSY | INT | SUCTION VALVE ASSY | 5 |  | 90028418_0360 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 117 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 370 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0070 | 0360 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060458 | GASKET,METALLIC;21.0 X 29.0 X 0.9MM,AL | 24 | EA | 101 | 0 | 0 | 24 | EA | 24.09 - SOH at AA02 | Supply for Order 200147980, Item 108 cannot be changed 90028418 item 300 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 108 | 0 | EA | 102000000030542 | 102000000030888 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0300 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060458 | GASKET,METALLIC;21.0 X 29.0 X 0.9MM,AL | 2024-09-23 | W |  | 0070 | DISCHARGE VALVE ASSY | INT | DISCHARGE VALVE ASSY | 5 |  | 90028418_0300 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 108 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 310 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0060 | 0050 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060459 | GASKET,METALLIC;23.0 X 30.0 X 2.0MM,AL | 4 | EA | 8 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 185 cannot be changed 90028418 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 185 | 0 | EA | 102000000030532 | 102000000030883 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060459 | GASKET,METALLIC;23.0 X 30.0 X 2.0MM,AL | 2024-09-23 | W |  | 0060 | CYLINDER | INT | CYLINDER | 5 |  | 90028418_0040 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 185 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 50 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0130 | 0610 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060465 | GASKET,METALLIC;165.05 X 178.95 X 3.5MM | 2 | EA | 8 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 156 cannot be changed 90028418 item 640 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 156 | 0 | EA | 102000000030540 | 102000000030882 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0640 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060465 | GASKET,METALLIC;165.05 X 178.95 X 3.5MM | 2024-09-23 | W |  | 0130 | INTERMEDIATE PACKING | INT | INTERMEDIATE PACKING | 5 |  | 90028418_0640 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 156 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 670 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0840 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060465 | GASKET,METALLIC;165.05 X 178.95 X 3.5MM | 2 | EA | 8 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 154 cannot be changed 90028418 item 620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 154 | 0 | EA | 102000000030538 | 102000000030881 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060465 | GASKET,METALLIC;165.05 X 178.95 X 3.5MM | 2024-09-23 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90028418_0620 |  |  | ST5 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 154 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 650 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0070 | 0370 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060471 | GASKET,METALLIC;261.0 X 271.0 X 2.0MM,AL | 4 | EA | 44 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 109 cannot be changed 90028418 item 310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 109 | 0 | EA | 102000000030542 | 102000000030807 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060471 | GASKET,METALLIC;261.0 X 271.0 X 2.0MM,AL | 2024-09-23 | W |  | 0070 | DISCHARGE VALVE ASSY | INT | DISCHARGE VALVE ASSY | 5 |  | 90028418_0310 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 109 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 320 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0200 | 0820 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060471 | GASKET,METALLIC;261.0 X 271.0 X 2.0MM,AL | 4 | EA | 44 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 118 cannot be changed 90028418 item 370 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 118 | 0 | EA | 102000000030549 | 102000000030806 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0370 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Cov Gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060471 | GASKET,METALLIC;261.0 X 271.0 X 2.0MM,AL | 2024-09-23 | W |  | 0200 | SUCTION VALVE ASSY | INT | SUCTION VALVE ASSY | 5 |  | 90028418_0370 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 118 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 380 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2260 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060481 | GASKET,JACKETED,135 X 154,3.2MM | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - 1 SOH @ AA02 | Supply for Order 200091513, Item 331 cannot be changed 90028419 item 2580 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2610 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 331 | 0 | EA | 102000000030482 | 102000000030660 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2580 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060481 | GASKET,JACKETED,135 X 154,3.2MM | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2580 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 331 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2610 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200090882 | 0040 | 0050 | 200090882 | 12Y INT INSP EXCHANGER 1K1820E1A | AA53.1K1820E1A | EXCH,HEAT LUBE OIL FRAC T1 1K1820 | AA01 | 10 | WO item has not been released yet | 10060562 | GASKET;FLAT,29.0 X 36.0 X 3.0MM,IRON | 16 | EA | 300 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000129132 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200090882 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060562 | GASKET;FLAT,29.0 X 36.0 X 3.0MM,IRON |  |  |  | 0040 | Remove Fin Fan Plugs (16) | INT | Remove Fin Fan Plugs (16) | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000128534 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Ready For Scheduling/Material committed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0182 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10060576 | GASKET;FLAT,190 X 200 X 3MM,IRON | 8 | EA | 9 | 0 | 0 | 7 | EA | 25.02 - SOH @ AA02 | Supply for Order 200091126, Item 130 cannot be changed 90023534 item 780 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1070 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 130 | 0 | EA | 102000000030448 | 102000000031106 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | suction |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060576 | GASKET;FLAT,190 X 200 X 3MM,IRON | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0780 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 130 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1070 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0040 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10060594 | GASKET,JKTD,404 X 430 X 3.2MM,316/G | 2 | EA | 2 | 0 | 0 | 0 |  | 20.12 - ETA 29.04.25 PO 4500036351 KLINGER CPT | Supply for Order 100040704, Item 4 cannot be changed 90025105 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017859 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025105 | 05 | Preparation | 0000139208 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025105_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-08-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100040704 |  | 0 | 2 | 0 | 90025105 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060594 | GASKET,JKTD,404 X 430 X 3.2MM,316/G | 2024-11-13 | W |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection |  |  | 90025105_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000138559 | S002 | 30 | 30 | 5300017859 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139208 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0230 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10060594 | GASKET,JKTD,404 X 430 X 3.2MM,316/G | 2 | EA | 2 | 0 | 0 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 100087648, Item 24 cannot be changed 90028417 item 230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 24 | 0 | EA | 102000000030614 | 101000000134820 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060594 | GASKET,JKTD,404 X 430 X 3.2MM,316/G | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0230 |  |  | ST5 |  | C4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 24 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 230 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0120 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | Issue detected, please check message in derivation or orchestration log | 10060595 | GASKET | 3 | EA | 0 | 0 | 0 | 0 |  | 03.02 - Needs purchase req | Linked PR creation failed for Order 14 Item |  | SP97 | Direct Multi-base | 0 | AA01 | 5300017860 | 20 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029757 | 05 | Preparation | 0000139208 | 14 | 0 | [8 empty] | WorkPackLink |  | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-14 |  | 0 | 0 | 0 | 0 |  | 2025-02-22 | AA53 | 2025-03-01 | [7 empty] | 2021-08-01 | 0 |  | 2025-02-12 |  | 2025-02-24 | 100040704 |  | 0 | 2 | 0 | 90029757 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060595 | GASKET | 2024-12-15 | E |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection |  |  | 90029757_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA02 |  | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000138559 | S001 | 71 | 71 | 5300017859 | 40 |  | 5300017860 | 20 | 3 | EA | 1001 | AA02 | 2025-02-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0320 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060595 | GASKET | 3 | EA | 0 | 0 | 0 | 0 |  | 03.02 - Needs purchase req | Linked PR creation failed for Order 33 Item |  | SP97 | Direct Multi-base | 0 | AA01 | 5300018313 | 30 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029758 | 05 | Preparation | 0000278190 | 33 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-23 |  | 0 | 0 | 0 | 0 |  | 2025-02-22 | AA53 | 2025-03-01 | [7 empty] | 2025-12-02 | 0 |  | 2025-02-12 |  | 2025-02-24 | 5E2001 |  | 0 | 2 | 0 | 90029758 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060595 | GASKET | 2025-01-19 | E |  | 0001 | Materials | INT | Materials |  |  | 90029758_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA02 |  | 10 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000272706 | S001 | 71 | 71 | 5300018296 | 320 |  | 5300018313 | 30 | 3 | EA | 1001 | AA02 | 2025-02-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 0 | 0 | 0 |  | 1010 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0210 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10060600 | GASKET,JKTD,1331 X 1357 X 3.2MM,SS/GR | 4 | EA | 4 | 0 | 0 | 4 | EA | 19.02 - SOH @ AA02 | Supply for Order 100087648, Item 22 cannot be changed 90028417 item 210 already exists | Material picked; currently at 30-03-05-81A/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 22 | 0 | EA |  |  | 101000000133882 | 01-Road |  | 5-Completed |  | WorkPackLink | 30-03-05-81A |  | 0 |  | 0 | 0 |  | 0 | 4 | 2025-01-23 | 2025-01-23 | Y | 1001 | 2024-11-22 | ODST-0090028417_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060600 | GASKET,JKTD,1331 X 1357 X 3.2MM,SS/GR | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0210 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 22 |  | 0 |  | 25SDSTB5 | MJ | 20005202 | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 210 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-21 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2025-01-15 | 2025-03-01 | 2025-02-26 | 2025-03-01 | 2025-03-03 | MECH | 200146986 | 0060 | 0010 | 200146986 | MOC-149553 EX/SH INSP TUB/RVDI BONREM | AA53.1E2402 | EXCH,HEAT FEED GAS LIQUID FIXED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060742 | GASKET;SWR,956 X 1004 X 6.4MM,316L/GR | 2 | EA | 0 | 0 | 2 | 2 | EA | 24.02 - SOH @ AA02 | Supply for Order 200146986, Item 1 cannot be changed 90028607 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020054 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180133208 | 90028607 | 05 | Preparation | 0000235448 | 1 | 0 | EA |  |  | 101000000146818 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07YRDBY14 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000430614_2025 | 0 | 2 | 0 | 0 |  | 2025-03-01 | AA53 | 2025-03-01 |  |  | 2025-03-03 |  |  | 100000060074 | 1020 | 2025-12-03 | 2 |  | 2025-03-07 | 4900259895_2025_0001 | 2025-03-03 | HIGH | 5000430614_2025_0001 | 0 | 2 | 0 | 90028607 | 2 | 0 | 180133208 | 2 | 0 | 0 | X | L | 4900259895 | 2025 |  | 5000430614 | 2025 | 0 |  | 2025-02-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060742 | GASKET;SWR,956 X 1004 X 6.4MM,316L/GR | 2025-01-14 | W |  | 0060 | Remove Bonnet and Vent/Drain Blinds | INT | Remove Bonnet and Vent/Drain Blinds |  |  | 90028607_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2301 | MJ | 1000005251 | AU1072 | 1000232419 | S002 |  | 30 | 5300020054 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-26 |  |  | 2025-02-27 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-02 | 235448 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0090 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10060761 | GASKET,SW;33.5 X 42.8 X 4.5MM,316L/GR | 2 | EA | 0 | 2 | 0 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091108, Item 114 cannot be changed 9027124 item 770 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027124 | 05 | Preparation | 0000129406 | 114 | 0 | EA | 102000000030156 | 101000000134321 | 102000000030441 |  |  |  |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-20 | GIST-4900234150_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-04-28 | 2 |  | 2025-02-11 | 4900234150_2025_0103 | 2025-03-01 | SOFilter |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234150 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060761 | GASKET,SW;33.5 X 42.8 X 4.5MM,316L/GR | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 9027124_0770 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 114 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 800 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0480 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060772 | GASKET,SW;398.8MM,417.3MM | 6 | EA | 18 | 0 | 0 | 6 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 48 cannot be changed 90028419 item 400 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 48 | 0 | EA |  |  | 102000000030906 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0400 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060772 | GASKET,SW;398.8MM,417.3MM | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0400 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 48 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 410 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0410 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060773 | GASKET,SW;424.2MM,435.4MM | 12 | EA | 20 | 0 | 0 | 9 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 41 cannot be changed 90028419 item 330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 41 | 0 | EA | 102000000030589 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060773 | GASKET,SW;424.2MM,435.4MM | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0330 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 41 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 340 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0410 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060773 | GASKET,SW;424.2MM,435.4MM | 12 | EA | 20 | 0 | 0 | 3 | EA | 19.02 - SOH @ AA02 | Supply for Order 200091513, Item 41 cannot be changed 90028419 item 330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 41 | 0 | EA | 102000000033628 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060773 | GASKET,SW;424.2MM,435.4MM | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0330 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 41 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 340 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100043807 | 0010 | 0052 | 100043807 | Repair/replace faulty N2 flow indicator | AA53.118FI503 | IND,N2 PURGE GAS TO RESERVOIR 1K1820V6 | AA01 | 20 | WO item has not been released yet | 10060881 | GASKET:SWCI,15MM,CL150,316L/GR/316 | 1 | EA | 23 | 0 | 0 | 0 |  | 02.10 - SOH @ AA02 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000142308 | 5 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-01-14 | 0 |  |  |  |  | 100043807 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060881 | GASKET:SWCI,15MM,CL150,316L/GR/316 |  |  |  | 0010 | Remove & Replace Flowmeter | INT | Remove & Replace Flowmeter | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000141677 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material shortage | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-05-15 | MECH | 100044203 | 0010 | 0020 | 100044203 | Repair/replace faulty N2 flow indicator | AA53.118FI502 | IND,N2 PURGE GAS TO RESERVOIR 1K1820V2 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10060881 | GASKET:SWCI,15MM,CL150,316L/GR/316 | 2 | EA | 23 | 2 | 85 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 100044203, Item 1 cannot be changed 90024953 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002290 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024953 | 06 | Scheduling | 0000142657 | 1 | 0 | EA | 102000000032094 | 102000000026950 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024953_0010 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2021-01-14 | 0 |  | 2025-03-26 |  | 2025-03-31 | 118FI502 |  | 0 | 2 | 0 | 90024953 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060881 | GASKET:SWCI,15MM,CL150,316L/GR/316 | 2024-01-02 | W |  | 0010 | Remove & Replace Flowmeter | INT | Remove & Replace Flowmeter | 5 |  | 90024953_0010 |  |  | FR1 |  | A4 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000142019 | S002 | 30 | 30 | 5300002290 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142657 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-08-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200069587 | 0010 | 0010 | 200069587 | 8Y FG HOSE REPL FURNACE 5F2001 | AA53.520XE042HOSE01 | HOSE,FG 520XE042 B FLAME DET 5F2001 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(18.12.2024) | 10060881 | GASKET:SWCI,15MM,CL150,316L/GR/316 | 1 | EA | 23 | 2 | 85 | 1 | EA | 19.12- SOH @ AA02 | Supply for Order 200069587, Item 3 cannot be changed 90028437 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013756 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028437 | 06 | Scheduling | 0000103910 | 3 | 0 | EA | 102000000031902 | 102000000030223 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-09 | ODST-0090028437_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200069587 |  | 0 | 2 | 0 | 90028437 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060881 | GASKET:SWCI,15MM,CL150,316L/GR/316 | 2024-12-18 | W |  | 0010 | Replace Hose 520XE042HOSE01 | INT | Replace Hose 520XE042HOSE01 | 5 |  | 90028437_0010 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000103326 | S002 | 30 | 30 | 5300013756 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 103910 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Ready For Scheduling/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0010 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10060881 | GASKET:SWCI,15MM,CL150,316L/GR/316 | 7 | EA | 23 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 14 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 7 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060881 | GASKET:SWCI,15MM,CL150,316L/GR/316 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SD4401 | Released | 2024-01-01 | 2025-03-01 | 2025-02-28 | 2025-02-28 | 2025-04-29 | MECH | 100040077 | 0030 | 0050 | 100040077 | Investigate Blocked Seal Pot Drain 344LC | AA53.344LCV509 | VALVE,CTRL LEVEL DRAIN POT 3K4401V5B | AA01 | 20 | No issue identified | 10060882 | GASKET:SWCI,20MM,CL150,316L/GR/316 | 10 | EA | 53 | 16 | 119 | 10 | EA | 28.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021904 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031989 | 05 | Preparation | 0000138598 | 5 | 0 | EA | 102000000034493 |  | 102000000034357 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-28 | ODST-0090031989_0020 | 0 | 4 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-05 |  |  |  |  | 2025-09-30 | 0 |  | 2025-02-28 |  | 2025-03-05 |  |  | 0 | 2 | 0 | 90031989 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060882 | GASKET:SWCI,20MM,CL150,316L/GR/316 |  |  |  | 0030 | Investigate & Clear Blockages | INT | Investigate & Clear Blockages | 3 |  | 90031989_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000138027 | S002 | 30 | 30 | 5300021904 | 20 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138598 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100048154 | 0010 | 0020 | 100048154 | Repair - B&P Sight Glasses 1K1820V3 | AA53.1K1820V3 | TANK,FRAC 1 LUBE OIL RESERVOIR | AA01 | 20 | WO item has not been released yet | 10060882 | GASKET:SWCI,20MM,CL150,316L/GR/316 | 8 | EA | 53 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000146666 | 2 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2022-12-01 | 0 |  |  |  |  | 100048154 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060882 | GASKET:SWCI,20MM,CL150,316L/GR/316 |  |  |  | 0010 | Remove Sight Glasses, Cover Flanges | INT | Remove Sight Glasses, Cover Flanges | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000146076 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0010 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10060882 | GASKET:SWCI,20MM,CL150,316L/GR/316 | 2 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 19 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060882 | GASKET:SWCI,20MM,CL150,316L/GR/316 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD4403 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | INLEC | 100031878 | 0020 | 0010 | 100031878 | Replace Flow Tx - 44FIT521 | AA53.44FIT521 | METER,FLOW K4403 SEALGAS PRIM VENT | AA01 | 30 | WO item has not been released yet | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130319 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-11-08 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR |  |  |  | 0020 | Replace Flow Meter | INT | Replace Flow Meter | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD4403 | MJ |  |  | 1000129688 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SD4403 | Released | 2024-01-30 | 2024-05-07 | 2024-12-18 | 2024-05-07 | 2024-05-07 | INLEC | 100042451 | 0090 | 0020 | 100042451 | Replace Flow Tx - 44FIT520 | AA53.44FIT520 | METER,FLOW K4403 SEALGAS PRIM VENT | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.12.2024) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2 | EA | 53 | 0 | 553 | 2 | EA | 10.01 - Picked @ KSF | Supply for Order 100042451, Item 4 cannot be changed 90027139 item 10 already exists | Material picked; currently at SW3R01B01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005745 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90027139 | 05 | Preparation | 0000140972 | 4 | 0 | EA | 102000000029298 |  | 102000000026658 |  |  |  |  | WorkPackLink | SW3R01B01A | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-30 | ODST-0090027139_0010 | 0 | 230 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-12-23 |  |  |  |  | 2021-12-26 | 0 |  | 2024-12-18 |  | 2024-12-23 | 100042451 |  | 0 | 2 | 0 | 90027139 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-12-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2024-12-17 | W |  | 0090 | Replace Flow Meter | INT | Replace Flow Meter | 5 |  | 90027139_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SD4403 | MJ |  | AU1072 | 1000140401 | S002 | 30 | 30 | 5300005745 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-12-18 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140972 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | ROTAT | 200081172 | 0020 | 0030 | 200081172 | 4Y CO2 System Replace Hoses (3) 4KT1410 | AA53.HOSE40645 | HOSE,CO2 4KT1410V5 TO 414RV409 | AA01 | 10 | WO item has not been released yet | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 6 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000115761 | 2 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 2200682034 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR |  |  |  | 0020 | CO2 System Replace Hoses | INT | CO2 System Replace Hoses | 5 | Ready for Release |  |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000115091 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | ROTAT | 200081173 | 0020 | 0030 | 200081173 | 4Y CO2 System Replace Hoses (3) 4KT1430 | AA53.HOSE40648 | HOSE,CO2 4KT1430V5 TO 414RV509 | AA01 | 10 | WO item has not been released yet | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 6 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000115762 | 2 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 2200682037 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR |  |  |  | 0020 | CO2 System Replace Hoses | INT | CO2 System Replace Hoses | 5 | Ready for Release |  |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000115092 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | WORK | 200089335 | 0020 | 0010 | 200089335 | 10Y RECERTIFY PSV ROTABLE | AA53.408RV521 | PSV,CO2 DISCH LINE GT4008A CO2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 1 | EA | 53 | 0 | 553 | 0 |  | 02.10 - SOH @ AA01 | Supply for Order 200089335, Item 2 cannot be changed 90024961 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004145 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024961 | 07 | Execution | 0000127593 | 2 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024961_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200633290 |  | 0 | 2 | 0 | 90024961 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2024-01-02 | W |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | Ready for Release | 90024961_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000127004 | S002 | 30 | 30 | 5300004145 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127593 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-05-01 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200147055 | 0015 | 0010 | 200147055 | 2Y Depress Valve F/Test (5) 1V2401 | AA53.124HCV051 | VALVE,CTRL PRESS DEPRESS 1V2401 | AA01 | 10 | WO item has not been released yet | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 1 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235216 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-20 | 0 |  |  |  |  | 200147055 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR |  |  |  | 0015 | Remove & Re-Instate Blind | INT | Remove & Re-Instate Blind | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232270 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2024-05-01 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200147056 | 0015 | 0010 | 200147056 | 2Y Depress Valve F/Test (4) 1C2401 | AA53.124HCV141 | VALVE,CTRL HAND 1C2401 DEPRESS | AA01 | 10 | WO item has not been released yet | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 1 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235217 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-20 | 0 |  |  |  |  | 200147056 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR |  |  |  | 0015 | Remove & Re-Instate Blind | INT | Remove & Re-Instate Blind | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232271 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDDG1 | Released | 2024-05-01 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200147059 | 0020 | 0010 | 200147059 | 2Y FUNCT TEST 124HCV68 | AA53.124HCV68 | VALVE,CTRL 1K2430 DEPRESS | AA01 | 10 | WO item has not been released yet | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 1 | EA | 53 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235220 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147059 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR |  |  |  | 0020 | Remove & Re-Instate Blind | INT | Remove & Re-Instate Blind |  | Ready for Release |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000232274 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0010 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 53 | 0 | 553 | 0 |  | 15.01 - SOH @ AA01 | Supply for Order 200177498, Item 7 cannot be changed 90028588 item 70 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 7 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177498 |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028588_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 | 30 | 30 | 5300020059 | 70 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0030 | 0010 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 53 | 0 | 553 | 0 |  | 15.01 - SOH @ AA01 | Supply for Order 200177498, Item 1 cannot be changed 90028588 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 |  | 90028588_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 | 30 | 30 | 5300020059 | 10 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0010 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 53 | 0 | 553 | 0 |  | 15.01 - SOH @ AA01 | Supply for Order 200177499, Item 7 cannot be changed 90028589 item 70 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 7 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 | 30 | 30 | 5300020060 | 70 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0030 | 0010 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 53 | 0 | 553 | 0 |  | 15.01 - SOH @ AA01 | Supply for Order 200177499, Item 1 cannot be changed 90028589 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 |  | 90028589_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 | 30 | 30 | 5300020060 | 10 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0010 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 53 | 0 | 553 | 0 |  | 15.01 - SOH @ AA01 | Supply for Order 200177720, Item 7 cannot be changed 90028590 item 70 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 7 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177720 |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 90028590_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 | 30 | 30 | 5300020061 | 70 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0030 | 0010 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 53 | 0 | 553 | 0 |  | 15.01 - SOH @ AA01 | Supply for Order 200177720, Item 1 cannot be changed 90028590 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0030 | ConMon Inspections / ESD | ENON | ConMon Inspections / ESD | 3 | Ready for Release | 90028590_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 | 30 | 30 | 5300020061 | 10 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0090 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 30 | EA | 53 | 0 | 553 | 15 | EA | 18.10 - SOH @ AA01 | Supply for Order 600001757, Item 15 cannot be changed 90024970 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 15 | 0 | EA | 102000000032100 | 101000000150444 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0010 |  |  | SL0 |  | C4 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 140 |  |  | 0 | 30 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0090 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 30 | EA | 53 | 0 | 553 | 9 | EA | 18.10 - SOH @ AA01 | Supply for Order 600001757, Item 15 cannot be changed 90024970 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 15 | 0 | EA | 102000000032100 | 102000000030192 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0010 |  |  | SL0 |  | C4 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 140 |  |  | 0 | 30 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0090 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 30 | EA | 53 | 0 | 553 | 2 | EA | 18.10 - SOH @ AA01 | Supply for Order 600001757, Item 15 cannot be changed 90024970 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 15 | 0 | EA | 102000000032100 | 101000000149985 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0010 |  |  | SL0 |  | C4 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 140 |  |  | 0 | 30 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0090 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 30 | EA | 53 | 0 | 553 | 2 | EA | 18.10 - SOH @ AA01 | Supply for Order 600001757, Item 15 cannot be changed 90024970 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 15 | 0 | EA | 102000000032100 | 101000000149986 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET:SW;25MM,CL150,4.5MM,SS316L,GR | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0010 |  |  | SL0 |  | C4 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 140 |  |  | 0 | 30 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0010 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 10 | EA | 34 | 17 | 102 | 4 | EA | 24.02 - SOH @ AA02 | Supply for Order 200089472, Item 8 cannot be changed 90028583 item 80 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 8 | 0 | EA |  |  | 102000000033267 |  |  |  |  | WorkPackLink | PACKING | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0080 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 80 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0010 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 10 | EA | 34 | 17 | 102 | 2 | EA | 02.03 - SOH @ AA02 | Supply for Order 200089473, Item 1 cannot be changed 90028584 item 10 already exists | Material picked; currently at WH2-PACK-SD-1A/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 1 | 0 | EA | 102000000031708 |  | 102000000031644 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1A | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 10 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0010 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 10 | EA | 34 | 17 | 102 | 8 | EA | 02.03 - SOH @ AA02 | Supply for Order 200089473, Item 1 cannot be changed 90028584 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 1 | 0 | EA |  |  | 102000000033269 |  |  |  |  | WorkPackLink | PACKING | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 10 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2530 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 10 | EA | 34 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 380 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT7 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0120 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | WO item has not been released yet | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 2 | EA | 34 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235945 | 12 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147533 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000232951 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT9 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200147535 | 0110 | 0090 | 200147535 | 12Y INSP INT FIN FAN G4009E1 | AA53.G4009E1 | EXCH,HEAT G4009 SYNTH/MIN OIL AIR COOLER | AA01 | 10 | WO item has not been released yet | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 2 | EA | 34 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235947 | 9 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147535 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR |  |  |  | 0110 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000232953 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT8 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200160323 | 0100 | 0100 | 200160323 | 12Y INSP INT FIN FAN G4008E1 | AA53.G4008E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4008 | AA01 | 10 | WO item has not been released yet | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 2 | EA | 34 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255582 | 10 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-14 | 0 |  |  |  |  | 200160323 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000251671 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0030 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 3 | EA | 34 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 21 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0020 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 10 | EA | 34 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 15 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0110 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Shipped qty below requirement qty | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 24 | EA | 34 | 17 | 102 | 13 | EA | 09.01 - @ KGP | Supply for Order 600001757, Item 17 cannot be changed 180105568 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180105568 | 9022429 | 07 | Execution | 0000084653 | 17 | 0 | EA |  |  | 101000000121479 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 11 |  |  | Y | 1001 | 2024-01-24 | GRST-5000320153_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  | 100000047251 | 1020 | 2025-08-30 | 13 |  | 2024-12-15 | 4900191624_2024_0001 | 2025-03-01 | 600001757 | 5000320153_2024_0001 | 0 | 2 | 0 | 90024970 | 13 | 0 | 180105568 | 1 | 0 | 0 | X | L | 4900191624 | 2024 |  | 5000320153 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0030/9022429_0030 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 17 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 160 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0110 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Shipped qty below requirement qty | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 24 | EA | 34 | 17 | 102 | 11 | EA | 09.01 - @ KGP | Supply for Order 600001757, Item 17 cannot be changed 180105568 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180105568 | 9022429 | 07 | Execution | 0000084653 | 17 | 0 | EA | 102000000028856 | 101000000131259 | 102000000032100 |  |  |  |  | WorkPackLink |  | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 11 |  |  | Y | 1001 | 2024-01-24 | GRST-5000320153 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  | 100000047251 | 1020 | 2025-08-30 | 13 |  | 2024-12-15 | 4900191624_2024_0001 | 2025-03-01 | 600001757 | 5000320153_2024_0001 | 0 | 2 | 0 | 90024970 | 13 | 0 | 180105568 | 1 | 0 | 0 | X | L | 4900191624 | 2024 |  | 5000320153 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET:SW;40MM,CL150,4.5MM,SS316L,GR | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0030/9022429_0030 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 17 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 160 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
1 | 25SDFR1 | Released | 2024-01-25 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039501 | 0020 | 0040 | 100039501 | Replace - Asbestos gaskets 1K1820V5 | AA53.1K1820V5 | TANK,EMERG LUBE OIL RUNDOWN 1K1820 | AA01 | 30 | WO item has not been released yet | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 2 | EA | 29 | 0 | 0 | 0 |  | 18.01 - At PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000137955 | 4 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-08-01 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 |  |  |  | 0020 | Remove & Replace Gaskets (x3) | INT | Remove & Replace Gaskets (x3) | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137357 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | WORK | 200055989 | 0020 | 0030 | 200055989 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.118RV13 | PSV,1V1805 ON 2" LINE 1W41534 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 1 | EA | 29 | 16 | 177 | 1 | EA | 18.12 - SOH @ AA02 | Supply for Order 200055989, Item 3 cannot be changed 90024941 item 20 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000272 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024941 | 07 | Execution | 0000090304 | 3 | 0 | EA | 102000000027100 |  | 102000000032114 |  |  |  |  | WorkPackLink | PACKING | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024941_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200055989 |  | 0 | 2 | 0 | 90024941 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 2024-01-01 | W |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV |  | Ready for Release | 90024941_0020 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000089708 | S002 | 30 | 30 | 5300000272 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 90304 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200088517 | 0100 | 0010 | 200088517 | 8Y P01 INT INSP PRESS VESSEL 5V2004 | AA53.5V2004 | VE,FUEL GAS KNOCK OUT DRUM | AA01 | 10 | WO item has not been released yet | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 1 | EA | 29 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000126826 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 |  |  |  | 0100 | Re-instate Vessel head / Spools | INT | Re-instate Vessel head / Spools | [5 empty] | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000126176 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2540 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 30 | EA | 29 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 381 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 1020 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 4 | EA | 29 | 16 | 177 | 4 | EA | 23.01 - SOH @ AA02 | Supply for Order 200147980, Item 102 cannot be changed 90028418 item 240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 102 | 0 | EA | 102000000030539 | 102000000030228 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0240 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 102 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 250 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0050 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 9 | EA | 29 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 23 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 9 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0040 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 14 | EA | 29 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 17 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 14 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDFLR | Released | 2024-11-08 | 2025-04-30 |  | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0030 | 0040 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | WO item has not been released yet | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 | 16 | EA | 29 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000084731 | 7 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2024-08-30 | 0 |  |  |  |  | 37FQI40/41 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET:SWCI,50MM,CL150,316L/GR/316 |  |  |  | 0030 | Provision of Flow Computers (MOC-119247) | ESRV | Provision of Flow Computers (MOC-119247) | [5 empty] | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDFLR | MJ |  |  | 1000084145 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2550 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 | 30 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 382 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2025-01-14 | 2025-02-28 |  | 2025-02-28 | 2025-03-02 | MECH | 200147112 | 0030 | 0010 | 200147112 | 16Y VE/SH INSP RVI 1K2420E1 | AA53.1K2420E1 | TANK,DEGASSING FOR SEAL OIL ON 1K2420 | AA01 | 10 | WO item has not been released yet | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 | 2 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235383 | 1 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-02-28 |  |  | 2025-02-28 |  |  |  |  | 2025-07-14 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 |  |  |  | 0030 | Remove Heater for Vessel Inspection | INT | Remove Heater for Vessel Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000232426 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0070 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 | 5 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 25 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0050 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 | 1 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 18 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDFLR | Released | 2024-11-08 | 2025-02-08 |  | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0020 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | WO item has not been released yet | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 | 4 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000084731 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-02-08 |  |  | 2025-02-08 |  |  |  |  | 2024-08-30 | 0 |  |  |  |  | 37FQI40/41 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060886 | GASKET:SWCI,80MM,CL150,316L/GR/316 |  |  |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour | [5 empty] | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDFLR | MJ |  |  | 1000084145 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0390 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 6 | EA | 71 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 39 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | WORK | 200059456 | 0030 | 0020 | 200059456 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.520RV02 | PSV,5P20040 FROM 5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 71 | 0 | 102 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200059456, Item 2 cannot be changed 90024947 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300001576 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024947 | 05 | Preparation | 0000093805 | 2 | 0 | EA | 102000000031880 | 102000000029925 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024947_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024947 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-01-01 | W |  | 0030 | Remove / Install PSV | INT | Remove / Install PSV |  | Ready for Release | 90024947_0010 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000093175 | S002 | 30 | 30 | 5300001576 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  | 2025-01-15 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 93805 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed/Partially confirmed | AM02 | Proactive Maintenance
1 | 25SDGT8 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200061977 | 0030 | 0010 | 200061977 | 12Y INT INSP PRESS VESSEL GT4008V2 | AA53.GT4008V2 | VE,ONLINE WATER WASH TANK,GT4008 | AA01 | 10 | WO item has not been released yet | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 71 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000096332 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-UT-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200061977 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 |  |  |  | 0030 | Isolate & Disconnect Instrumentation | INT | Isolate & Disconnect Instrumentation | [5 empty] | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000095696 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200088517 | 0100 | 0030 | 200088517 | 8Y P01 INT INSP PRESS VESSEL 5V2004 | AA53.5V2004 | VE,FUEL GAS KNOCK OUT DRUM | AA01 | 10 | WO item has not been released yet | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 71 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000126826 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-09 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 |  |  |  | 0100 | Re-instate Vessel head / Spools | INT | Re-instate Vessel head / Spools | [5 empty] | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000126176 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0050 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 71 | 0 | 102 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 12 cannot be changed 90028583 item 120 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 12 | 0 | EA | 102000000031587 |  | 102000000029604 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0120 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0050 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 71 | 0 | 102 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 5 cannot be changed 90028584 item 50 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 5 | 0 | EA | 102000000031584 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0050 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0050 | 0080 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Shipped qty below requirement qty | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 4 | EA | 71 | 0 | 102 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089884, Item 8 cannot be changed 180105563 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180108646 | 9023062 | 05 | Preparation | 0000128153 | 8 | 0 | EA | 102000000029920 |  | 102000000029606 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-05-08 | GRST-5000330368 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000049400 | 1020 | 2024-07-16 | 2 |  | 2024-12-23 | 4900196398_2024_0001/4900191574_2024_0001 | 2025-03-01 |  | 5000330368_2024_0001/5000320133_2024_0001 | 0 | 2 | 0 | 90024984 | 2 | 0 | 180105563/180108646 | 1 | 0 | 0 | X | L | 4900196398 | 2024 |  | 5000330368 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-05-08 | W |  | 0050 | Remove Spades | INT | Remove Spades | 5 | Order Requires Replanning | 90024984_0030/9023062_0030/9022425_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 80 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0050 | 0080 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Shipped qty below requirement qty | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 4 | EA | 71 | 0 | 102 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089884, Item 8 cannot be changed 180105563 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180108646 | 9023062 | 05 | Preparation | 0000128153 | 8 | 0 | EA | 101000000121646 |  | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-05-08 | GRST-5000330368_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000049400 | 1020 | 2024-07-16 | 2 |  | 2024-12-23 | 4900196398_2024_0001/4900191574_2024_0001 | 2025-03-01 |  | 5000330368_2024_0001/5000320133_2024_0001 | 0 | 2 | 0 | 90024984 | 2 | 0 | 180105563/180108646 | 1 | 0 | 0 | X | L | 4900196398 | 2024 |  | 5000330368 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-05-08 | W |  | 0050 | Remove Spades | INT | Remove Spades | 5 | Order Requires Replanning | 90024984_0030/9023062_0030/9022425_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 80 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0050 | 0080 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Shipped qty below requirement qty | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 4 | EA | 71 | 0 | 102 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089884, Item 8 cannot be changed 180105563 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180108646 | 9023062 | 05 | Preparation | 0000128153 | 8 | 0 | EA |  |  | 101000000121812 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-05-08 | GRST-5000330368_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000049400 | 1020 | 2024-07-16 | 2 |  | 2024-12-23 | 4900196398_2024_0001/4900191574_2024_0001 | 2025-03-01 |  | 5000330368_2024_0001/5000320133_2024_0001 | 0 | 2 | 0 | 90024984 | 2 | 0 | 180105563/180108646 | 1 | 0 | 0 | X | L | 4900196398 | 2024 |  | 5000330368 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-05-08 | W |  | 0050 | Remove Spades | INT | Remove Spades | 5 | Order Requires Replanning | 90024984_0030/9023062_0030/9022425_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 80 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0130 | 0030 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 71 | 0 | 102 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089887, Item 8 cannot be changed 90025037 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 8 | 0 | EA | 102000000031999 | 102000000029928 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | OCW Drain |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-16 | W |  | 0130 | Mechanical Preparation for Waterwash | INT | Mechanical Preparation for Waterwash | 5 | Ready for Release | 90025037_0080 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0150 | 0040 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 71 | 0 | 102 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089887, Item 13 cannot be changed 90025037 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 13 | 0 | EA | 102000000031995 | 102000000029927 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | OCW Drain |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-16 | W |  | 0150 | Mechanical Restoration Post Waterwash | INT | Mechanical Restoration Post Waterwash | 5 | Ready for Release | 90025037_0130 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 130 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0150 | 0010 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 4 | EA | 71 | 0 | 102 | 4 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089887, Item 10 cannot be changed 90025037 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 10 | 0 | EA | 102000000031995 | 102000000029926 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | BleedAirPipe |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-16 | W |  | 0150 | Mechanical Restoration Post Waterwash | INT | Mechanical Restoration Post Waterwash | 5 | Ready for Release | 90025037_0100 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 100 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0120 | 0030 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 6 | EA | 71 | 0 | 102 | 6 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089888, Item 11 cannot be changed 90025038 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025038 | 05 | Preparation | 0000128157 | 11 | 0 | EA | 102000000032002 | 102000000029930 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025038_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025038 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025038_0050 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 50 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0120 | 0040 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 5 | EA | 71 | 0 | 102 | 1 | EA | 17.10 - SOH @ AA01 | Supply for Order 200089888, Item 12 cannot be changed 90025038 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025038 | 05 | Preparation | 0000128157 | 12 | 0 | EA | 102000000032002 | 102000000029929 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025038_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025038 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025038_0060 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 60 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0120 | 0030 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 5 | EA | 71 | 0 | 102 | 5 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089889, Item 12 cannot be changed 90025039 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 12 | 0 | EA | 102000000032028 | 102000000029921 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025039_0060 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 60 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0120 | 0020 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 6 | EA | 71 | 0 | 102 | 3 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089889, Item 11 cannot be changed 90025039 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 11 | 0 | EA | 102000000032028 | 102000000028274 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025039_0050 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 50 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0120 | 0020 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 6 | EA | 71 | 0 | 102 | 3 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089889, Item 11 cannot be changed 90025039 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 11 | 0 | EA | 102000000032028 | 102000000029922 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025039_0050 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 50 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-06-01 | 2025-05-27 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0120 | 0040 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 6 | EA | 71 | 0 | 102 | 3 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089890, Item 20 cannot be changed 90025060 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025060 | 05 | Preparation | 0000128159 | 20 | 0 | EA | 102000000032017 | 101000000105574 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025060_0030 | 0 | 0 | 0 | 0 |  | 2025-05-30 | AA53 | 2025-03-01 |  |  | 2025-06-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-05-27 |  | 2025-06-01 | Isolations |  | 0 | 2 | 0 | 90025060 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025060_0030 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 20 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 60 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-05-27 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-06-01 | 2025-05-27 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0120 | 0050 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 5 | EA | 71 | 0 | 102 | 0 |  | 23.01 - SOH @ AA02 | Supply for Order 200089890, Item 21 cannot be changed 90025060 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025060 | 05 | Preparation | 0000128159 | 21 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025060_0040 | 0 | 0 | 0 | 0 |  | 2025-05-30 | AA53 | 2025-03-01 |  |  | 2025-06-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-05-27 |  | 2025-06-01 | Isolations |  | 0 | 2 | 0 | 90025060 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025060_0040 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 21 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 70 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-05-27 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0120 | 0040 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 6 | EA | 71 | 0 | 102 | 6 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089891, Item 14 cannot be changed 90025062 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025062 | 05 | Preparation | 0000128160 | 14 | 0 | EA | 102000000032020 | 102000000029924 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025062_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025062_0070 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 70 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0120 | 0050 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 5 | EA | 71 | 0 | 102 | 5 | EA | 23.01 - SOH @ AA02 | Supply for Order 200089891, Item 15 cannot be changed 90025062 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025062 | 05 | Preparation | 0000128160 | 15 | 0 | EA | 102000000032020 | 102000000029923 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025062_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025062_0080 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 80 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT9 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200147536 | 0030 | 0010 | 200147536 | 12Y INSP INT PRESS VESSEL GT4009V2 | AA53.GT4009V2 | VE,GT4009 ONLINE WATER WASH TANK | AA01 | 10 | WO item has not been released yet | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 71 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235948 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147536 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET:SWCI,100MM,CL150,316L/GR/316 |  |  |  | 0030 | Isolate & Disconnect Instrumentation | INT | Isolate & Disconnect Instrumentation | [5 empty] | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000232954 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDGT8 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200061977 | 0030 | 0020 | 200061977 | 12Y INT INSP PRESS VESSEL GT4008V2 | AA53.GT4008V2 | VE,ONLINE WATER WASH TANK,GT4008 | AA01 | 10 | WO item has not been released yet | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 | 1 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000096332 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-UT-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200061977 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 |  |  |  | 0030 | Isolate & Disconnect Instrumentation | INT | Isolate & Disconnect Instrumentation | [5 empty] | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000095696 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2560 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 | 10 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 383 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT7 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0100 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | WO item has not been released yet | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 | 2 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235945 | 10 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147533 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000232951 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT9 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200147535 | 0110 | 0070 | 200147535 | 12Y INSP INT FIN FAN G4009E1 | AA53.G4009E1 | EXCH,HEAT G4009 SYNTH/MIN OIL AIR COOLER | AA01 | 10 | WO item has not been released yet | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 | 2 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235947 | 7 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147535 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 |  |  |  | 0110 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000232953 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT9 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200147536 | 0030 | 0020 | 200147536 | 12Y INSP INT PRESS VESSEL GT4009V2 | AA53.GT4009V2 | VE,GT4009 ONLINE WATER WASH TANK | AA01 | 10 | WO item has not been released yet | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 | 1 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235948 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200147536 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 |  |  |  | 0030 | Isolate & Disconnect Instrumentation | INT | Isolate & Disconnect Instrumentation | [5 empty] | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000232954 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDGT8 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | MECH | 200160323 | 0100 | 0080 | 200160323 | 12Y INSP INT FIN FAN G4008E1 | AA53.G4008E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4008 | AA01 | 10 | WO item has not been released yet | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 | 2 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255582 | 8 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-14 | 0 |  |  |  |  | 200160323 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000251671 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0090 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 | 1 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 27 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060888 | GASKET:SWCI,150MM,CL150,316L/GR/316 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 1010 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060889 | GASKET:SWCI,200MM,CL150,316L/GR/316 | 12 | EA | 37 | 1 | 3 | 12 | EA | 23.01 - SOH @ AA02 | Supply for Order 200147980, Item 101 cannot be changed 90028418 item 230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 101 | 0 | EA | 102000000030539 | 102000000030214 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060889 | GASKET:SWCI,200MM,CL150,316L/GR/316 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0230 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 101 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 240 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0020 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060889 | GASKET:SWCI,200MM,CL150,316L/GR/316 | 2 | EA | 37 | 1 | 3 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 8 cannot be changed 90028588 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 8 | 0 | EA | 102000000031570 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177498 |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060889 | GASKET:SWCI,200MM,CL150,316L/GR/316 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028588_0080 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 | 30 | 30 | 5300020059 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0020 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060889 | GASKET:SWCI,200MM,CL150,316L/GR/316 | 2 | EA | 37 | 1 | 3 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 8 cannot be changed 90028589 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 8 | 0 | EA | 102000000031571 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060889 | GASKET:SWCI,200MM,CL150,316L/GR/316 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0080 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 | 30 | 30 | 5300020060 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0020 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060889 | GASKET:SWCI,200MM,CL150,316L/GR/316 | 2 | EA | 37 | 1 | 3 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177720, Item 8 cannot be changed 90028590 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 8 | 0 | EA | 102000000031569 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177720 |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060889 | GASKET:SWCI,200MM,CL150,316L/GR/316 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 90028590_0080 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 | 30 | 30 | 5300020061 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0360 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060890 | GASKET:SWCI,250MM,CL150,316L/GR/316 | 6 | EA | 7 | 2 | 11 | 0 |  | DEL: 80033609 | Supply for Order 100090053, Item 36 cannot be changed 90032376 item 340 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 36 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0340 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060890 | GASKET:SWCI,250MM,CL150,316L/GR/316 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0340 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 36 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 360 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0140 | 0040 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | WO item has not been released yet | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 | 2 | EA | 71 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000243763 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-12 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 |  |  |  | 0140 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000240421 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0160 | 0040 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | WO item has not been released yet | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 | 2 | EA | 71 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000243730 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-12 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 |  |  |  | 0160 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000240357 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-11-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | VALVE | 100087379 | 0080 | 0020 | 100087379 | MV-OH 4" 300# 960BAV2400 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 255 | No issue identified | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 | 2 | EA | 71 | 5 | 38 | 2 | EA | 27.11 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018141 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028278 | 05 | Preparation | 0000277207 | 4 | 0 | EA | 102000000029916 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-20 | ODST-0090028278_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-11-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100087379 |  | 0 | 2 | 0 | 90028278 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 |  |  |  | 0080 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve |  |  | 90028278_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000271762 | S002 | 30 | 30 | 5300018141 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 277207 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0060 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 | 5 | EA | 71 | 5 | 38 | 5 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 13 cannot be changed 90028583 item 130 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 13 | 0 | EA | 102000000031567 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0130 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 130 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0060 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 | 5 | EA | 71 | 5 | 38 | 5 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 6 cannot be changed 90028584 item 60 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 6 | 0 | EA | 102000000031566 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060901 | GASKET:SWCI,100MM,CL300,SS316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0060 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 60 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0020 | 0010 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 1 | EA | 55 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132018 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033564 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131400 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0020 | 0010 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 1 | EA | 55 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132019 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033565 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131501 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0180 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 6 | EA | 55 | 0 | 23 | 0 |  | 02.03 - SOH @ AA02 | Supply for Order 100087648, Item 19 cannot be changed 90028417 item 180 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 19 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0180 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 19 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 180 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0120 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 4 | EA | 55 | 0 | 23 | 4 | EA | 02.03 - SOH @ AA02 | Supply for Order 200073951, Item 12 cannot be changed 90028585 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 12 | 0 | EA | 101000000150106 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0120 |  |  | ST5 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 12 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 120 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0070 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 5 | EA | 55 | 0 | 23 | 0 |  | 02.03 - SOH @ AA02 | Supply for Order 200089472, Item 14 cannot be changed 90028583 item 140 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 14 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0140 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 140 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0070 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 5 | EA | 55 | 0 | 23 | 2 | EA | 02.03 - SOH @ AA02 | Supply for Order 200089473, Item 7 cannot be changed 90028584 item 70 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 7 | 0 | EA |  |  | 101000000150110 | 01-Road |  | 5-Completed |  | WorkPackLink | PACKING | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 5 | 2025-03-04 | 2025-03-02 | Y | 1001 | 2025-01-15 | ODST-0090028584_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0070 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDLN4 | MJ | 20005471 | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 70 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-28 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0070 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 5 | EA | 55 | 0 | 23 | 3 | EA | 02.03 - SOH @ AA02 | Supply for Order 200089473, Item 7 cannot be changed 90028584 item 70 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 7 | 0 | EA | 101000000141663 |  | 101000000141502 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 5 |  | 2025-02-07 | Y | 1001 | 2025-01-15 | ODST-0090028584_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0070 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDLN4 | MJ | 20005067 | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 70 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0020 | 0020 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2 | EA | 55 | 0 | 23 | 2 | EA | 18.12 - SOH @ AA02 | Supply for Order 200089884, Item 2 cannot be changed 90024984 item 10 already exists | Material picked; currently at SW3R01B01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024984 | 05 | Preparation | 0000128153 | 2 | 0 | EA | 102000000027357 | 102000000028273 | 102000000026658 |  |  |  |  | WorkPackLink | SW3R01B01A |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-05-08 | ODST-0090024984_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-16 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024984 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2024-05-08 | W |  | 0020 | Install Spades | INT | Install Spades | 5 | Order Requires Replanning | 90024984_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2024-07-22 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0050 | 0070 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2 | EA | 55 | 0 | 23 | 2 | EA | P08C11L4 | Supply for Order 200089884, Item 7 cannot be changed 180045616 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180045616 | 9007601 | 05 | Preparation | 0000128153 | 7 | 0 | EA |  |  | 102000000011278 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08C11L2 |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-08 | GRST-5000139808_2024 | 0 | 0 | 0 | 0 |  | 2024-07-23 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000017337 | 1020 | 2024-07-16 | 2 |  | 2024-07-15 | 4900091928_2024_0001 | 2024-07-25 |  | 5000139808_2024_0001 | 0 | 2 | 0 | 90011070 | 2 | 0 | 180045616/180071488 | 2 | 0 | 0 | X | L | 4900091928 | 2024 |  | 5000139808 | 2024 | 0 |  | 2024-07-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2024-05-08 | W |  | 0050 | Remove Spades | INT | Remove Spades | 5 | Order Requires Replanning | 9007601_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDDG1 | MJ | 1000002393 | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 70 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-07-22 |  | Order Requires Replanning | 2024-07-16 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0020 | 0020 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | WO item has not been released yet | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 | 2 | EA | 55 | 0 | 0 | 0 |  | 23.01 - PR Never line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084710 | 2 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET:SWCI,150MM,CL300,316L/GR/316 |  |  |  | 0020 | Install 118UCV112 | INT | Install 118UCV112 | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000084094 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0020 | 0020 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10060903 | GASKET:SWCI,200MM,CL300,316L/GR/316 | 1 | EA | 54 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132018 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033564 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060903 | GASKET:SWCI,200MM,CL300,316L/GR/316 |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131400 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0020 | 0020 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10060903 | GASKET:SWCI,200MM,CL300,316L/GR/316 | 1 | EA | 54 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132019 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033565 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060903 | GASKET:SWCI,200MM,CL300,316L/GR/316 |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131501 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0160 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10060903 | GASKET:SWCI,200MM,CL300,316L/GR/316 | 14 | EA | 54 | 1 | 15 | 14 | EA | 23.01 - SOH @ AA02 | Supply for Order 100087648, Item 17 cannot be changed 90028417 item 160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 17 | 0 | EA | 102000000030215 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 14 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060903 | GASKET:SWCI,200MM,CL300,316L/GR/316 | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0160 |  |  | ST5 |  | C2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 17 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 160 |  |  | 0 | 14 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0130 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060903 | GASKET:SWCI,200MM,CL300,316L/GR/316 | 6 | EA | 54 | 1 | 15 | 6 | EA | 15.01 - SOH @ AA02 | Supply for Order 200073951, Item 13 cannot be changed 90028585 item 130 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 13 | 0 | EA | 102000000031896 | 102000000031589 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060903 | GASKET:SWCI,200MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0130 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 13 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 130 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0350 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 12 | EA | 21 | 0 | 9 | 2 | EA | 07.03 - ETA 31.01.25 PO 4500041049 KLINGER CPT | Supply for Order 100090053, Item 35 cannot be changed 90032376 item 330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 35 | 0 | EA | 101000000152585 |  | 102000000033278 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0330 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0330 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 35 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 350 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0350 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 12 | EA | 21 | 0 | 9 | 8 | EA | 07.03 - ETA 31.01.25 PO 4500041049 KLINGER CPT | Supply for Order 100090053, Item 35 cannot be changed 90032376 item 330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 35 | 0 | EA | 101000000152584 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0330 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0330 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 35 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 350 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146436 | 0020 | 0040 | 200146436 | 1Y Cond Prod Pump Service - 5P2002B | AA53.5P2002B | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 1 | EA | 21 | 0 | 9 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200146436, Item 4 cannot be changed 90025016 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015715 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025016 | 05 | Preparation | 0000234313 | 4 | 0 | EA | 102000000026937 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025016_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200146436 |  | 0 | 2 | 0 | 90025016 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 2024-09-24 | W |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  | 90025016_0040 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231369 | S002 | 30 | 30 | 5300015715 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234313 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146437 | 0020 | 0040 | 200146437 | 1Y Cond Prod Pump Service - 5P2002A | AA53.5P2002A | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 1 | EA | 21 | 0 | 9 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200146437, Item 4 cannot be changed 90025015 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015714 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025015 | 05 | Preparation | 0000234314 | 4 | 0 | EA | 102000000026938 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025015_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200146437 |  | 0 | 2 | 0 | 90025015 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 2024-09-24 | W |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  | 90025015_0040 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231370 | S002 | 30 | 30 | 5300015714 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234314 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 1000 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 4 | EA | 21 | 0 | 9 | 4 | EA | 23.01 - SOH @ AA02 | Supply for Order 200147980, Item 100 cannot be changed 90028418 item 220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 100 | 0 | EA | 102000000030057 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060904 | GASKET:SWCI,250MM,CL300,316L/GR/316 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0220 |  |  | ST5 |  | C5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 100 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 230 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0140 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060905 | GASKET:SWCI,300MM,CL300,316L/GR/316 | 10 | EA | 14 | 0 | 11 | 2 | EA | 10.01 - ETA 28.02.25 PO 4500041284 KLINGER CPT | Supply for Order 200073951, Item 14 cannot be changed 90028585 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 14 | 0 | EA | 101000000137179 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060905 | GASKET:SWCI,300MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0140 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 14 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 140 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146438 | 0020 | 0040 | 200146438 | 1Y Cond Heater Pump Service - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10060905 | GASKET:SWCI,300MM,CL300,316L/GR/316 | 1 | EA | 14 | 0 | 11 | 0 |  | 10.01 - ETA 28.02.25 PO 4500041284 KLINGER CPT | Supply for Order 200146438, Item 4 cannot be changed 90025014 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015713 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025014 | 05 | Preparation | 0000234315 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025014_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200146438 |  | 0 | 2 | 0 | 90025014 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060905 | GASKET:SWCI,300MM,CL300,316L/GR/316 | 2024-09-24 | W |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 | Ready for Release | 90025014_0040 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231371 | S002 | 30 | 30 | 5300015713 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234315 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200146439 | 0020 | 0040 | 200146439 | 1Y Cond Heater Pump Service - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(24.09.2024) | 10060905 | GASKET:SWCI,300MM,CL300,316L/GR/316 | 1 | EA | 14 | 0 | 11 | 0 |  | 16.12 - qty 6 SOH @ AA02 | Supply for Order 200146439, Item 4 cannot be changed 90025013 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015712 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025013 | 05 | Preparation | 0000234316 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090025013_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200146439 |  | 0 | 2 | 0 | 90025013 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060905 | GASKET:SWCI,300MM,CL300,316L/GR/316 | 2024-09-24 | W |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  | 90025013_0040 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231372 | S002 | 30 | 30 | 5300015712 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234316 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0010 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10060906 | GASKET:SWCI,350MM,CL300,316L/GR/316 | 2 | EA | 26 | 0 | 8 | 2 | EA | 18.11 - SOH @ AA02 | Supply for Order 100040704, Item 1 cannot be changed 90025105 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017859 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025105 | 05 | Preparation | 0000139208 | 1 | 0 | EA | 102000000027403 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025105_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-08-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100040704 |  | 0 | 2 | 0 | 90025105 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060906 | GASKET:SWCI,350MM,CL300,316L/GR/316 | 2024-11-13 | W |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection |  |  | 90025105_0010 |  |  | ST5 |  | C4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000138559 | S002 | 30 | 30 | 5300017859 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139208 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0190 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10060906 | GASKET:SWCI,350MM,CL300,316L/GR/316 | 8 | EA | 26 | 0 | 8 | 0 |  | 15.01 - SOH @ AA02 | Supply for Order 100087648, Item 20 cannot be changed 90028417 item 190 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 20 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060906 | GASKET:SWCI,350MM,CL300,316L/GR/316 | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0190 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 20 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 190 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0150 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060906 | GASKET:SWCI,350MM,CL300,316L/GR/316 | 2 | EA | 26 | 0 | 8 | 0 |  | 15.01 - SOH @ AA02 | Supply for Order 200073951, Item 15 cannot be changed 90028585 item 150 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 15 | 0 | [8 empty] | WorkPackLink |  | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060906 | GASKET:SWCI,350MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0150 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 15 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 150 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0170 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10060907 | GASKET:SWCI,400MM,CL300,SS316L/GR/316 | 4 | EA | 12 | 0 | 14 | 4 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 18 cannot be changed 90028417 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 18 | 0 | EA | 102000000033629 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060907 | GASKET:SWCI,400MM,CL300,SS316L/GR/316 | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0170 |  |  | ST5 |  | C1 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 18 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 170 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0160 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060910 | GASKET:SWCI,600MM,CL300,316L/GR/316 | 6 | EA | 8 | 0 | 2 | 0 |  | 15.01 - SOH @ AA02 | Supply for Order 200073951, Item 16 cannot be changed 90028585 item 160 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 16 | 0 | [8 empty] | WorkPackLink |  | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060910 | GASKET:SWCI,600MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0160 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 16 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 160 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
1 | 25SDGT7 | Released | 2024-10-25 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100034776 | 0040 | 0040 | 100034776 | MOC-145870-PV CM G4007V3 Passing Fill Va | AA53.G4007V3 | VE,CO2 LOW PRESSURE,GT4007 | AA01 | 20 | WO item has not been released yet | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 3 | EA | 210 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000133257 | 5 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-06 | 0 |  |  |  |  | 100034776 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 |  |  |  | 0040 | Fabricate Spool ( site inspection ) | INT | Fabricate Spool ( site inspection ) |  | Engineering Query/Management of Change |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000132686 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-01 | 2025-03-01 | 2025-02-28 | 2025-02-28 | 2025-04-29 | MECH | 100040077 | 0030 | 0040 | 100040077 | Investigate Blocked Seal Pot Drain 344LC | AA53.344LCV509 | VALVE,CTRL LEVEL DRAIN POT 3K4401V5B | AA01 | 20 | No issue identified | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 10 | EA | 210 | 10 | 117 | 0 |  | 28.02 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021904 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031989 | 05 | Preparation | 0000138598 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-28 | ODST-0090031989_0010 | 0 | 4 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-05 |  |  |  |  | 2025-09-30 | 0 |  | 2025-02-28 |  | 2025-03-05 |  |  | 0 | 2 | 0 | 90031989 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 |  |  |  | 0030 | Investigate & Clear Blockages | INT | Investigate & Clear Blockages | 3 |  | 90031989_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000138027 | S002 | 30 | 30 | 5300021904 | 10 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138598 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-11-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100040704 | 0010 | 0090 | 100040704 | BOLT REMOVAL - INSPECTION OF NOZZLE N6 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 30 | WO item has not been released yet | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2 | EA | 210 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139208 | 11 | 0 | [8 empty] | WorkPackLink |  | T25-SD-STB5 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-08-01 | 0 |  |  |  |  | 100040704 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Hot Bolt Flanged Connection | INT | Hot Bolt Flanged Connection | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000138559 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0080 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | WO item has not been released yet | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2 | EA | 210 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140308 | 10 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  |  |  |  | 100041844 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000139679 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-10-22 | 2025-02-15 |  | 2025-03-01 | 2025-05-15 | VALVE | 100045269 | 0015 | 0020 | 100045269 | Replace Pressure Gauge - 118PG11 | AA53.118PG11 | GAUGE,PRESS E1801 DE-ETH REBOILER | AA01 | 255 | WO item has not been released yet | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2 | EA | 210 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000143781 | 3 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-02-15 |  |  |  |  | 2021-04-04 | 0 |  |  |  |  | 100045269 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 |  |  |  | 0015 | Remove & Replace Valve > | INT | Remove & Replace Valve > | [5 empty] | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000143151 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD4401 | Released | 2024-10-04 | 2025-03-01 |  | 2025-03-01 | 2025-04-29 | VALVE | 100076445 | 0010 | 0020 | 100076445 | MV-RE 1/2" 300# 244LT512 | AA53.244LT512 | TX,LEVEL DRAIN POT 2K4401V5A | AA01 | 20 | WO item has not been released yet | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 4 | EA | 210 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000232991 | 2 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD4401 | MJ |  |  | 1000230114 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-04-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDGT9 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0170 | 0030 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | WO item has not been released yet | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 1 | EA | 210 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000277133 | 12 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-12-18 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 |  |  |  | 0170 | Replace Spool (Bolt up scope) | INT | Replace Spool (Bolt up scope) |  | Management of Change |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000271703 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0250 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 4 | EA | 210 | 10 | 117 | 4 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 26 cannot be changed 90028417 item 240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 26 | 0 | EA | 102000000031912 | 102000000030217 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0240 |  |  | ST5 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 26 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 250 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0170 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 30 | EA | 210 | 10 | 117 | 30 | EA | 15.01 - SOH @ AA02 | Supply for Order 200073951, Item 17 cannot be changed 90028585 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 17 | 0 | EA | 102000000031896 | 102000000031572 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0170 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 17 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 170 |  |  | 0 | 30 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | WORK | 200089335 | 0020 | 0020 | 200089335 | 10Y RECERTIFY PSV ROTABLE | AA53.408RV521 | PSV,CO2 DISCH LINE GT4008A CO2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 1 | EA | 210 | 10 | 117 | 1 | EA | 18.12 - SOH @ AA02 | Supply for Order 200089335, Item 3 cannot be changed 90024961 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004145 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024961 | 07 | Execution | 0000127593 | 3 | 0 | EA | 102000000026946 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024961_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200633290 |  | 0 | 2 | 0 | 90024961 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-01-02 | W |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | Ready for Release | 90024961_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000127004 | S002 | 30 | 30 | 5300004145 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127593 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0120 | 0020 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 4 | EA | 210 | 10 | 117 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089887, Item 4 cannot be changed 90025037 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 4 | 0 | EA | 102000000031990 | 102000000029859 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | CO2 Spading |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash | 5 | Ready for Release | 90025037_0040 |  |  | LN1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 40 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0120 | 0020 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 4 | EA | 210 | 10 | 117 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089887, Item 4 cannot be changed 90025037 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 4 | 0 | EA | 102000000031990 | 102000000025803 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | CO2 Spading |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash | 5 | Ready for Release | 90025037_0040 |  |  | LN1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 40 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0160 | 0020 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 4 | EA | 210 | 10 | 117 | 4 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089887, Item 15 cannot be changed 90025037 item 150 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 15 | 0 | EA | 102000000032005 | 102000000026952 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | CO2 Spading |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0160 | Remove Positive Isolations | INT | Remove Positive Isolations | 5 | Ready for Release | 90025037_0150 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 150 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0120 | 0050 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 8 | EA | 210 | 10 | 117 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089888, Item 13 cannot be changed 90025038 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025038 | 05 | Preparation | 0000128157 | 13 | 0 | EA | 102000000032002 | 102000000026947 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025038_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025038 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025038_0070 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 70 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0120 | 0040 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 8 | EA | 210 | 10 | 117 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089889, Item 13 cannot be changed 90025039 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 13 | 0 | EA | 102000000032028 | 102000000026942 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025039_0070 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 70 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-06-01 | 2025-05-27 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0120 | 0060 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 8 | EA | 210 | 10 | 117 | 8 | EA | 18.10 - SOH @ AA02 | Supply for Order 200089890, Item 22 cannot be changed 90025060 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025060 | 05 | Preparation | 0000128159 | 22 | 0 | EA | 102000000032017 | 102000000026945 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025060_0050 | 0 | 0 | 0 | 0 |  | 2025-05-30 | AA53 | 2025-03-01 |  |  | 2025-06-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-05-27 |  | 2025-06-01 | Isolations |  | 0 | 2 | 0 | 90025060 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025060_0050 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 22 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 80 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-05-27 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0120 | 0060 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 8 | EA | 210 | 10 | 117 | 8 | EA | 18.10 - SOH @ AA02 | Supply for Order 200089891, Item 16 cannot be changed 90025062 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025062 | 05 | Preparation | 0000128160 | 16 | 0 | EA | 102000000032020 | 102000000026944 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025062_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025062_0090 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 90 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200090677 | 0100 | 0040 | 200090677 | 4Y INT INSP EXCHANGER 5P2002AE | AA53.5P2002AE | EXCH,SEAL OIL COOLER P2002A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2 | EA | 210 | 10 | 117 | 2 | EA | 23.01 - SOH @ AA02 | Supply for Order 200090677, Item 3 cannot be changed 90028421 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019786 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028421 | 05 | Preparation | 0000128955 | 3 | 0 | EA | 102000000031915 | 102000000030218 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2028 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028421_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090677 |  | 0 | 2 | 0 | 90028421 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2025-01-08 | W |  | 0100 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028421_0030 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128366 | S002 | 30 | 30 | 5300019786 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128955 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-02-25 | 2025-03-01 | MECH | 200090678 | 0080 | 0100 | 200090678 | 4Y INT INSP EXCHANGER 5P2002BE | AA53.5P2002BE | EXCH,SEAL OIL COOLER P2002B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2 | EA | 210 | 10 | 117 | 2 | EA | 10.01 - SOH @ AA01 | Supply for Order 200090678, Item 3 cannot be changed 90028422 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019787 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028422 | 05 | Preparation | 0000128956 | 3 | 0 | EA | 102000000031906 | 102000000030219 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2027 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028422_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090678 |  | 0 | 2 | 0 | 90028422 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2025-01-08 | W |  | 0080 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028422_0030 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128367 | S002 | 30 | 30 | 5300019787 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128956 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0580 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 12 | EA | 210 | 10 | 117 | 12 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 66 cannot be changed 90025019 item 640 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 640 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 66 | 0 | EA | 102000000032113 | 102000000026943 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0640 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET:SWCI,15MM,CL300/600,316L/GR/316 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0640 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 66 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 640 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033564 | 0020 | 0030 | 100033564 | Replace Drive Coupling - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 1 | EA | 111 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132018 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033564 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131400 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-04 | ROTAT | 100033565 | 0020 | 0030 | 100033565 | Replace Drive Coupling - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 1 | EA | 111 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132019 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-12 | 0 |  |  |  |  | 100033565 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR |  |  |  | 0020 | Remove Pump | INT | Remove Pump | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000131501 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | MECH | 100039735 | 0010 | 0060 | 100039735 | Replace Flange Bolting 1K1820V7A/B | AA53.1K1820V7A | VE,DRAIN POT & MIST ELIMIN SEAL OIL | AA01 | 30 | WO item has not been released yet | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2 | EA | 111 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000138236 | 6 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-08-11 | 0 |  |  |  |  | 100039735 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR |  |  |  | 0010 | Replace 1K1820V7A - Gasket & Studs | INT | Replace 1K1820V7A - Gasket & Studs | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000137645 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0080 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 10 | EA | 111 | 2 | 96 | 8 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 15 cannot be changed 90028583 item 150 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 15 | 0 | EA | 102000000031574 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0150 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 150 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0080 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 10 | EA | 111 | 2 | 96 | 10 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 8 cannot be changed 90028584 item 80 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 8 | 0 | EA | 102000000031573 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0080 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 80 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200090677 | 0100 | 0020 | 200090677 | 4Y INT INSP EXCHANGER 5P2002AE | AA53.5P2002AE | EXCH,SEAL OIL COOLER P2002A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2 | EA | 111 | 2 | 96 | 2 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090677, Item 1 cannot be changed 90028421 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019786 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028421 | 05 | Preparation | 0000128955 | 1 | 0 | EA | 102000000031915 | 102000000030220 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2026 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028421_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090677 |  | 0 | 2 | 0 | 90028421 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2025-01-08 | W |  | 0100 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028421_0010 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128366 | S002 | 30 | 30 | 5300019786 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128955 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-02-25 | 2025-03-01 | MECH | 200090678 | 0080 | 0140 | 200090678 | 4Y INT INSP EXCHANGER 5P2002BE | AA53.5P2002BE | EXCH,SEAL OIL COOLER P2002B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2 | EA | 111 | 2 | 96 | 2 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090678, Item 1 cannot be changed 90028422 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019787 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028422 | 05 | Preparation | 0000128956 | 1 | 0 | EA | 102000000031906 | 102000000030221 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2031 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028422_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090678 |  | 0 | 2 | 0 | 90028422 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2025-01-08 | W |  | 0080 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028422_0010 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128367 | S002 | 30 | 30 | 5300019787 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128956 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200090882 | 0040 | 0030 | 200090882 | 12Y INT INSP EXCHANGER 1K1820E1A | AA53.1K1820E1A | EXCH,HEAT LUBE OIL FRAC T1 1K1820 | AA01 | 10 | WO item has not been released yet | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2 | EA | 111 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000129132 | 2 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200090882 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR |  |  |  | 0040 | Remove Fin Fan Plugs (16) | INT | Remove Fin Fan Plugs (16) | 5 |  |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000128534 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Ready For Scheduling/Material committed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0590 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 12 | EA | 111 | 2 | 96 | 12 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 67 cannot be changed 90025019 item 650 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 67 | 0 | EA | 102000000032113 | 102000000026948 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0650 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0650 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 67 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 650 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2200 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 4 | EA | 111 | 2 | 96 | 4 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 325 cannot be changed 90028419 item 2520 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 325 | 0 | EA | 102000000030482 | 102000000030222 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2520 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2520 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 325 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2550 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0080 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | WO item has not been released yet | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2 | EA | 111 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235400 | 8 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR |  |  |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232443 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDFR1 | Released | 2024-12-12 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | VALVE | 100032671 | 0080 | 0030 | 100032671 | CV-OH 1" 300# 118TCV503 | AA53.118TCV503 | VALVE,K1820E1 S/OIL COOLER BYPASS TEMP | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | 18.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131163 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-02 | 0 |  |  |  |  | 100032671 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0080 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130513 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | VALVE | 100032672 | 0020 | 0050 | 100032672 | CV-OH 1" 300# 118LCV505 | AA53.118LCV505 | VALVE,S/OIL O/H TK 1K1820V1 LVL CTRL | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131164 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 118LCV505 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130514 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2025-01-07 | 2025-03-01 |  | 2025-03-01 | 2025-05-14 | VALVE | 100032673 | 0020 | 0010 | 100032673 | CV-OH 1" 300# 118LCV508 | AA53.118LCV508 | VALVE,S/OIL DRN POT K1820V4A LOCAL LVL | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131165 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-02 | 0 |  |  |  |  | 100032673 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130515 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-15 | VALVE | 100032674 | 0020 | 0050 | 100032674 | CV-OH 1" 300# 118LCV510 | AA53.118LCV510 | VALVE,S/OIL DRN POT K1820V4B LOCAL LVL | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131166 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032674 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130516 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-02-28 | 2025-03-01 | VALVE | 100032675 | 0020 | 0070 | 100032675 | CV-OH 1" 300# 118PCV505 | AA53.118PCV505 | VALVE,1K1820 BUFFER GAS SUPPL PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 4 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131167 | 7 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032675 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130517 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-17 | VALVE | 100032678 | 0020 | 0130 | 100032678 | CV-OH 1" 300# 118PDCV506 | AA53.118PDCV506 | VALVE,1K1820E1 S/OIL PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | 31.01 - 432 SOH @ AA02 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131170 | 13 | 0 | [8 empty] | WorkPackLink |  | T25-TA-FRC-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  |  |  |  | 100032678 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130520 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT9 | Released | 2024-05-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100033225 | 0020 | 0030 | 100033225 | CV-RE 1" 300# 960UZ652 | AA53.960UZ652 | VALVE,GT4009V6 GAS TURB CO2 EXT DISCH | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 7 | 530 | 2 | EA | 02.12 - SOH @ AA02 | Supply for Order 100033225, Item 3 cannot be changed 90028270 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300010228 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028270 | 07 | Execution | 0000131737 | 3 | 0 | EA | 102000000031600 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-05-15 | ODST-0090028270_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028270 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-11-29 | W |  | 0020 | Punchlist & Closeout WP100033225MET001 | ENON | Punchlist & Closeout WP100033225MET001 |  |  | 90028270_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000131147 | S002 | 30 | 30 | 5300010228 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2024-10-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131737 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Partially confirmed/Job In Process/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2024-03-31 | 2024-03-28 | 2025-03-01 | 2025-03-01 | VALVE | 100034634 | 0030 | 0010 | 100034634 | OPSD 1" 600# unblock bypass 113LCV09 | AA53.113LICA09 | LOOP,LEVEL 1V1301 REGEN GAS WTR KO DRUM | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 7 | 530 | 2 | EA | AT KGP | Supply for Order 100034634, Item 1 cannot be changed 180014650 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300000146 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180014650 | 90004250 | 05 | Preparation | 0000133166 | 1 | 0 | EA |  |  | 102000000003932 | 01-Road |  | 3-In Transit |  | WorkPackLink | HVP08C05 | T25-TA-P07 | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2024-03-29 | AA53 | 2025-03-01 |  |  | 2024-03-31 |  |  | 100000004943 | 1020 | 2024-11-20 | 2 |  | 2024-04-01 | 4900041927_2024_0001 | 2024-03-31 | 100034634 | 5000048890_2024_0001 | 0 | 2 | 0 | 90004250 | 2 | 0 | 180014650 | 2 | 0 | 0 | X | L | 4900041927 | 2024 |  | 5000048890 | 2024 | 0 |  | 2024-03-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-01-01 | W |  | 0030 | Remove Blinds & Install Valve | INT | Remove Blinds & Install Valve |  | Opportune Shutdown | 90004250_0010 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDLN1 | MJ | 1000001154 | AU1072 | 1000132536 | S002 | 30 | 30 | 5300000146 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-03-28 |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133166 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Part printed/Material shortage | AM01 | Reactive Maintenance
| 25SD4401 | Released | 2024-01-01 | 2025-03-01 | 2025-02-28 | 2025-02-28 | 2025-04-29 | MECH | 100040077 | 0030 | 0060 | 100040077 | Investigate Blocked Seal Pot Drain 344LC | AA53.344LCV509 | VALVE,CTRL LEVEL DRAIN POT 3K4401V5B | AA01 | 20 | No issue identified | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 10 | EA | 262 | 7 | 530 | 0 |  | 28.02 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021904 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031989 | 05 | Preparation | 0000138598 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-02-28 | ODST-0090031989_0030 | 0 | 4 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-05 |  |  |  |  | 2025-09-30 | 0 |  | 2025-02-28 |  | 2025-03-05 | HIGH |  | 0 | 2 | 0 | 90031989 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0030 | Investigate & Clear Blockages | INT | Investigate & Clear Blockages | 3 |  | 90031989_0030 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000138027 | S002 | 30 | 30 | 5300021904 | 30 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138598 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SDLN4 | Released | 2024-01-02 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0090 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140308 | 11 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  |  |  |  | 100041844 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000139679 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR0 | Released | 2024-11-14 | 2025-03-01 |  | 2025-02-28 | 2025-03-01 | MECH | 100044226 | 0060 | 0010 | 100044226 | Offline Repair - P18032 HPV | AA53.EPFRAC6 | PIPE,ZONE FRAC TRAIN 3 | AA01 | 30 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142678 | 1 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-12-12 | 0 |  |  |  |  | 100044226 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0060 | Replace HPV Fittings (Bolt up scope) | INT | Replace HPV Fittings (Bolt up scope) | [5 empty] | FR3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR0 | MJ |  |  | 1000142148 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDLN1 | Released | 2024-10-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | VALVE | 100078477 | 0020 | 0020 | 100078477 | CV-OH 1" 600# 113LCV09 | AA53.113LCV09 | VALVE,1V1301 REGEN GAS WTR KO DRUM | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 4 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000241492 | 2 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-16 | 0 |  |  |  |  | 100078477 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000238214 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-05-31 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-06 | VALVE | 100079171 | 0020 | 0020 | 100079171 | CV-OH 1" 600# 124PCV52 | AA53.124PCV52 | VALVE,CTRL PRESS BUFF GAS 1K2420 | AA01 | 255 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000244737 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000241416 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2025-01-07 | 2025-03-01 |  | 2025-03-01 | 2025-04-29 | VALVE | 100079184 | 0020 | 0010 | 100079184 | CV-OH 1" 600# 124LCV26 | AA53.124LCV26 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000244787 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000241339 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2025-01-07 | 2025-03-01 |  | 2025-03-01 | 2025-04-30 | VALVE | 100079185 | 0020 | 0010 | 100079185 | CV-OH 1" 600# 124LCV27 | AA53.124LCV27 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000244788 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000241340 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-30 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100079244 | 0010 | 0050 | 100079244 | CV-OH 1' 600# 124LCV23 | AA53.124LCV23 | VALVE,CTRL LEVEL S/O FILTER OUT 1K2420 | AA01 | 255 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000244777 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000241462 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDGT9 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0170 | 0010 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000277133 | 9 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-12-18 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0170 | Replace Spool (Bolt up scope) | INT | Replace Spool (Bolt up scope) |  | Management of Change |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000271703 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDGT9 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100087351 | 0020 | 0020 | 100087351 | CV Reverse 1" 300# Act BAV - 960UZ653 | AA53.960UZ653 | VALVE,GT4009V6 GEARBOX CO2 INIT DISCH | AA01 | 255 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000277149 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-11-04 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove & Replace Valve/Correct Direction | INT | Remove & Replace Valve/Correct Direction | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDGT9 | MJ |  |  | 1000271668 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | WORK | 200055989 | 0020 | 0020 | 200055989 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.118RV13 | PSV,1V1805 ON 2" LINE 1W41534 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 7 | 530 | 1 | EA | 02.10 - SOH @ AA01 | Supply for Order 200055989, Item 2 cannot be changed 90024941 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000272 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024941 | 07 | Execution | 0000090304 | 2 | 0 | EA | 102000000031595 |  | 102000000032114 |  |  |  |  | WorkPackLink | PACKING | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024941_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200055989 |  | 0 | 2 | 0 | 90024941 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-01-01 | W |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV |  | Ready for Release | 90024941_0010 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000089708 | S002 | 30 | 30 | 5300000272 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 90304 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0090 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 10 | EA | 262 | 7 | 530 | 10 | EA | 15.01 -SOH @ AA01 | Supply for Order 200089472, Item 16 cannot be changed 90028583 item 160 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 16 | 0 | EA | 102000000031603 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0160 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 160 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0090 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 10 | EA | 262 | 7 | 530 | 10 | EA | 15.01 -SOH @ AA01 | Supply for Order 200089473, Item 9 cannot be changed 90028584 item 90 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 9 | 0 | EA | 102000000031601 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0090 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 90 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2024-07-19 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0020 | 0010 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 7 | 530 | 1 | EA | 25.09 - At KGP | Supply for Order 200089884, Item 1 cannot be changed 180066696 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180066696 | 9011773 | 05 | Preparation | 0000128153 | 1 | 0 | EA |  |  | 102000000007221 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-08 | GRST-5000197845_2024 | 0 | 0 | 0 | 0 |  | 2024-07-20 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000026766 | 1020 | 2024-07-16 | 1 |  | 2024-09-05 | 4900126368_2024_0001 | 2024-07-22 |  | 5000197845_2024_0001 | 0 | 2 | 0 | 90011068 | 1 | 0 | 180066696/180071501 | 2 | 0 | 0 | X | L | 4900126368 | 2024 |  | 5000197845 | 2024 | 0 |  | 2024-07-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-05-08 | W |  | 0020 | Install Spades | INT | Install Spades | 5 | Order Requires Replanning | 9011773_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ | 1000003125 | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-07-19 |  | Order Requires Replanning | 2024-09-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2024-07-22 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0050 | 0090 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 7 | 530 | 1 | EA | 25.09 - At KGP | Supply for Order 200089884, Item 9 cannot be changed 180066697 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180066697 | 9011774 | 05 | Preparation | 0000128153 | 9 | 0 | EA |  |  | 102000000007109 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07-WAREHOUSE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-08 | GRST-5000197838_2024 | 0 | 0 | 0 | 0 |  | 2024-07-23 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000026767 | 1020 | 2024-07-16 | 1 |  | 2024-09-05 | 4900126369_2024_0003 | 2024-07-25 |  | 5000197838_2024_0002 | 0 | 2 | 0 | 90011070 | 1 | 0 | 180066697/180071488 | 2 | 0 | 0 | X | L | 4900126369 | 2024 |  | 5000197838 | 2024 | 0 |  | 2024-07-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-05-08 | W |  | 0050 | Remove Spades | INT | Remove Spades | 5 | Order Requires Replanning | 9011774_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDDG1 | MJ | 1000003125 | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-07-22 |  | Order Requires Replanning | 2024-09-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200090677 | 0100 | 0060 | 200090677 | 4Y INT INSP EXCHANGER 5P2002AE | AA53.5P2002AE | EXCH,SEAL OIL COOLER P2002A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 7 | 530 | 1 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090677, Item 5 cannot be changed 90028421 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019786 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028421 | 05 | Preparation | 0000128955 | 5 | 0 | EA | 102000000032844 | 102000000031590 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2030 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028421_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090677 |  | 0 | 2 | 0 | 90028421 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2025-01-08 | W |  | 0100 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028421_0050 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128366 | S002 | 30 | 30 | 5300019786 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128955 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-09 | 2025-03-01 | 2025-02-24 | 2025-02-25 | 2025-03-01 | MECH | 200090678 | 0080 | 0120 | 200090678 | 4Y INT INSP EXCHANGER 5P2002BE | AA53.5P2002BE | EXCH,SEAL OIL COOLER P2002B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 7 | 530 | 1 | EA | 10.01 - SOH @ AA02 | Supply for Order 200090678, Item 5 cannot be changed 90028422 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019787 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028422 | 05 | Preparation | 0000128956 | 5 | 0 | EA | 102000000031906 | 102000000031591 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2029 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-09 | ODST-0090028422_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-02-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200090678 |  | 0 | 2 | 0 | 90028422 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2025-01-08 | W |  | 0080 | NEW - Install Seal Oil Cooler | INT | NEW - Install Seal Oil Cooler |  |  | 90028422_0050 |  |  | ST5 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000128367 | S002 | 30 | 30 | 5300019787 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128956 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0600 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 6 | EA | 262 | 7 | 530 | 6 | EA | 31.01 - 432 SOH @ AA02 | Supply for Order 200091505, Item 68 cannot be changed 90025019 item 660 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 68 | 0 | EA | 102000000032113 | 102000000031594 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0660 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0660 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 68 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 660 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2570 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 40 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 384 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2430 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 262 | 7 | 530 | 2 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 711 cannot be changed 90028419 item 4750 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 711 | 0 | EA | 102000000030482 | 102000000031593 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_4750 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 711 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4790 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146436 | 0020 | 0050 | 200146436 | 1Y Cond Prod Pump Service - 5P2002B | AA53.5P2002B | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234313 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146436 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231369 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146437 | 0020 | 0050 | 200146437 | 1Y Cond Prod Pump Service - 5P2002A | AA53.5P2002A | PUMP,CONDENSATE PRODUCT 5C2001 TO 5E2001 | AA01 | 30 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234314 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146437 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231370 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146438 | 0020 | 0050 | 200146438 | 1Y Cond Heater Pump Service - 5P2001A | AA53.5P2001A | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234315 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146438 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 | Ready for Release |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231371 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200146439 | 0020 | 0050 | 200146439 | 1Y Cond Heater Pump Service - 5P2001B | AA53.5P2001B | PUMP,CONDENSATE STAB HEATER,C2001 -F2001 | AA01 | 30 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000234316 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  |  |  |  | 200146439 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Clean Pump Suction Strainer | INT | Clean Pump Suction Strainer | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000231372 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0040 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235400 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232443 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0990 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 8 | EA | 262 | 7 | 530 | 8 | EA | 24.09 - SOH at AA02 | Supply for Order 200147980, Item 99 cannot be changed 90028418 item 210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 99 | 0 | EA | 102000000030539 | 102000000031592 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0210 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 99 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 220 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0020 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 20 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0240 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 3 | EA | 262 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 23 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-04-30 | 2025-02-24 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0100 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 12 | EA | 262 | 7 | 530 | 12 | EA | 18.10 - SOH @ AA01 | Supply for Order 600001757, Item 16 cannot be changed 90024970 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024970 | 07 | Execution | 0000084653 | 16 | 0 | EA | 102000000032100 | 102000000031596 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024970_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-04-30 |  |  | 2025-04-30 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600001757 |  | 0 | 2 | 0 | 90024970 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET:SWCI,25MM,CL300/600,316L/GR/316 | 2024-10-14 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024970_0020 |  |  | SL0 |  | C4 |  |  |  | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 16 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 150 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
1 | 25SDDG1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-04-28 | VALVE | 100043452 | 0010 | 0040 | 100043452 | MV-IS 124MOV4 drain valve | AA53.124MOV04 | VALVE,MOV,TRANSMISSION GAS TO U2700 | AA01 | 20 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 1 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141984 | 6 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-25 | 0 |  |  |  |  | 100043452 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Repair Leaking Drain Point | INT | Repair Leaking Drain Point | 3 |  |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000141334 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0140 | 0020 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 8 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000243763 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-12 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0140 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000240421 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-11-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0160 | 0020 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 8 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000243730 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-12 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0160 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000240357 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-07 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | VALVE | 100079243 | 0010 | 0010 | 100079243 | MV-RE 1.5" 300# 124GLV1110 | AA53.124LCV26 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.10.2024) | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2 | EA | 160 | 4 | 34 | 2 | EA | 08.10 - SOH at AA02 | Supply for Order 100079243, Item 1 cannot be changed 90025024 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016132 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124192 | 9027121 | 05 | Preparation | 0000244776 | 1 | 0 | EA | 102000000031669 | 102000000027099 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-07 | IDST-0180124192 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2026-06-04 | 2 |  | 2025-02-11 | 4900234049_2025_0001 | 2025-03-01 | 100079243 |  | 0 | 2 | 0 | 90025024 | 0 | 0 | 180124192 | 2 | 0 | 0 | X | L | 4900234049 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2024-10-07 | W |  | 0010 | Replace Passing Bypass Valve 124GAV1305 | INT | Replace Passing Bypass Valve 124GAV1305 |  |  | 9027121_0010 |  |  | DG1 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000241461 | S002 | 30 | 30 | 5300016132 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 244776 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 |  | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0120 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000246943 | 12 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  |  |  |  | 100079771 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000243501 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
1 | 25SD2301 | Released | 2024-10-29 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 100084995 | 0010 | 0010 | 100084995 | REPLACE CS GASKET - NOZZLE K5 | AA53.1V2401 | SEP,HP FEED 1V2401 | AA01 | 30 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 1 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000267392 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-08 | 0 |  |  |  |  | 100084995 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Replace CS Gasket - Nozzle K5 | INT | Replace CS Gasket - Nozzle K5 | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000262826 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-05-05 | ROTAT | 200066255 | 0010 | 0040 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 6 | EA | 160 | 4 | 34 | 6 | EA | 02.10 - At KGP | Supply for Order 200066255, Item 4 cannot be changed 180004302 item 30 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004302 | 9000019 | 05 | Preparation | 0000100557 | 4 | 0 | EA | 102000000000283 | 102000000000217 | 102000000000282 | 01-Road |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017884 | 0 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000002054 | 1020 | 2025-07-31 | 6 |  | 2024-02-12 | 4900030517_2024_0005 | 2024-05-03 | GT4008 | 5000017884_2024_0001 | 0 | 2 | 0 | 90000272 | 6 | 0 | 180004302/180017134 | 2 | 0 | 0 | X | L | 4900030517 | 2024 |  | 5000017884 | 2024 | 0 |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2024-01-02 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 | Ready for Release | 9000019_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ | 1000000499 | AU1072 | 1000099994 | S002 | 30 | 30 | 5300004178 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed/Part printed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0080 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117838 | 10 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200082188 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000117251 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0110 | 0010 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 10 | EA | 160 | 4 | 34 | 10 | EA | 15.01 - SOH @ AA02 | Supply for Order 200088516, Item 1 cannot be changed 90028586 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020032 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028586 | 05 | Preparation | 0000126825 | 1 | 0 | EA | 102000000031899 | 102000000031580 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028586_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028586 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0110 | Punchlist & Closeout WP200088516MET001 | ENON | Punchlist & Closeout WP200088516MET001 | 5 | Ready for Release | 90028586_0010 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126175 | S002 | 30 | 30 | 5300020032 | 10 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126825 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0100 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 10 | EA | 160 | 4 | 34 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 17 cannot be changed 90028583 item 170 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180126076 | 9027606 | 05 | Preparation | 0000127730 | 17 | 0 | EA |  |  | 102000000033071 |  |  |  |  | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-15 | IDST-0180126076 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000057099 | 1020 | 2024-09-06 | 2 |  | 2025-02-17 | 4900239135_2025_0001 | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 | 180126076 | 2 | 0 | 0 | X | L | 4900239135 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0170/9027606_0170 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 170 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0100 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 10 | EA | 160 | 4 | 34 | 10 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 10 cannot be changed 90028584 item 100 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 10 | 0 | EA | 102000000031579 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0100 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 100 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0610 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 12 | EA | 160 | 4 | 34 | 12 | EA | 18.12 - SOH @ AA02 | Supply for Order 200091505, Item 69 cannot be changed 90025019 item 670 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 69 | 0 | EA | 102000000032113 | 102000000027097 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0670 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0670 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 69 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 670 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2580 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 12 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 385 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT7 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200144873 | 0100 | 0010 | 200144873 | 12Y INSP INT FIN FAN GT4007E1 | AA53.GT4007E1 | EXCH,HEAT SYNTHETIC OIL COOLER,GT4007 | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000232068 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200144873 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000229155 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200146986 | 0060 | 0040 | 200146986 | MOC-149553 EX/SH INSP TUB/RVDI BONREM | AA53.1E2402 | EXCH,HEAT FEED GAS LIQUID FIXED | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235448 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0060 | Remove Bonnet and Vent/Drain Blinds | INT | Remove Bonnet and Vent/Drain Blinds | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232419 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-02 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147452 | 0010 | 0010 | 200147452 | 6Y INSP TURB F/HOSE REPL GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 6 | EA | 160 | 4 | 34 | 6 | EA | 18.12 - SOH @ AA02 | Supply for Order 200147452, Item 1 cannot be changed 90025002 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015679 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025002 | 05 | Preparation | 0000235862 | 1 | 0 | EA | 102000000027098 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025002_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025002 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2024-09-22 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 3 | Ready for Release | 90025002_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232868 | S002 | 30 | 30 | 5300015679 | 10 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235862 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0980 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 12 | EA | 160 | 4 | 34 | 12 | EA | 24.09 - SOH at AA02 | Supply for Order 200147980, Item 98 cannot be changed 90028418 item 200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 98 | 0 | EA | 102000000030539 | 102000000030212 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0200 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 98 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 210 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0040 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 1 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 22 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
1 | 25SD2301 | Released | 2024-08-07 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 600001365 | 0030 | 0030 | 600001365 | MOC-77357 1K2301 Install Aux Lube Oil Pu | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 5 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084303 | 16 | 0 | [8 empty] | WorkPackLink |  | 1K-2301 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001365 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0030 | Mechanical Tie In & Supports | INT | Mechanical Tie In & Supports |  | Order Requires Replanning |  |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000083687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDLN1 | Released | 2024-08-15 | 2025-03-01 |  | 2025-02-19 | 2025-03-03 | MECH | 600003215 | 0020 | 0020 | 600003215 | MOC-117109 1E1303 Exchanger Replacement | AA53.1E1303 | EXCH,HEAT AIR COOL REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 4 | EA | 160 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000254308 | 2 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove blanks For Inspection Access | INT | Remove blanks For Inspection Access |  | Management of Change |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000250524 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W35069 | 2024-08-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-02-19 | 2025-02-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital | M0-000001-99-02
1 | 25SDFR1 | Released | 2024-12-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-16 | VALVE | 100032676 | 0010 | 0100 | 100032676 | CV-OH 2" 300# 118PCV507 | AA53.118PCV507 | VALVE,1K1820E1 L/O PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2 | EA | 428 | 0 | 0 | 0 |  | 19.01 - PR Never Line item, 391 SOH @ AA02 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131168 | 10 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  |  |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000130518 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDLN4 | Released | 2024-11-19 | 2025-05-08 |  | 2025-05-08 | 2025-05-08 | VALVE | 100042223 | 0020 | 0020 | 100042223 | CV-RE 2" 600# 414UV356 | AA53.414UV356 | VALVE,CTRL 4V1404 HW TO SUPPLY | AA01 | 10 | WO item has not been released yet | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2 | EA | 428 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140764 | 5 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 100042223 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 |  |  |  | 0020 | Remove & Replace Valve, Reuse Actuator | INT | Remove & Replace Valve, Reuse Actuator | [5 empty] | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000140133 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDFR0 | Released | 2024-11-18 | 2025-05-24 |  | 2025-02-28 | 2025-05-25 | MECH | 100044631 | 0060 | 0010 | 100044631 | Replace Gasket - 3P18075 | AA53.EPFRAC6 | PIPE,ZONE FRAC TRAIN 3 | AA01 | 30 | WO item has not been released yet | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 1 | EA | 428 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000143185 | 1 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-24 |  |  | 2025-05-24 |  |  |  |  | 2023-12-29 | 0 |  |  |  |  | 2100299310 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 |  |  |  | 0060 | Replace HPV Fittings (Bolt up scope) | INT | Replace HPV Fittings (Bolt up scope) | 7 |  |  |  |  | FR3 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR0 | MJ |  |  | 1000142567 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-25 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0260 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 5 | EA | 428 | 14 | 539 | 5 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 27 cannot be changed 90028417 item 250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 27 | 0 | EA | 102000000031912 | 102000000030224 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-11-22 | ODST-0090028417_0250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0250 |  |  | ST5 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 27 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 260 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0290 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 40 | EA | 428 | 14 | 539 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 29 cannot be changed 90032376 item 270 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 29 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0270 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0270 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 29 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 290 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0180 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 50 | EA | 428 | 14 | 539 | 50 | EA | 15.01 - SOH @ AA02 | Supply for Order 200073951, Item 18 cannot be changed 90028585 item 180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 18 | 0 | EA | 102000000031576 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0180 |  |  | ST5 |  | CC |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 18 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 | 30 | 30 | 5300020031 | 180 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0110 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 10 | EA | 428 | 14 | 539 | 10 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 18 cannot be changed 90028583 item 180 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 18 | 0 | EA | 102000000031578 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0180 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 18 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 180 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0110 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 10 | EA | 428 | 14 | 539 | 10 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 11 cannot be changed 90028584 item 110 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 11 | 0 | EA | 102000000031575 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0110 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 110 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2024-07-19 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0020 | 0030 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 1 | EA | 428 | 14 | 539 | 1 | EA | 25.09 - At KGP | Supply for Order 200089884, Item 3 cannot be changed 180066696 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180066696 | 9011773 | 05 | Preparation | 0000128153 | 3 | 0 | EA | 102000000007138 |  | 107000000000399 |  |  |  |  | WorkPackLink | INLEC-CAGE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-08 | GRST-5000197845_2024 | 0 | 0 | 0 | 0 |  | 2024-07-20 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000026766 | 1020 | 2024-07-16 | 1 |  | 2024-09-05 | 4900126368_2024_0003 | 2024-07-22 |  | 5000197845_2024_0002 | 0 | 2 | 0 | 90011068 | 1 | 0 | 180066696/180071501 | 2 | 0 | 0 | X | L | 4900126368 | 2024 |  | 5000197845 | 2024 | 0 |  | 2024-07-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-05-08 | W |  | 0020 | Install Spades | INT | Install Spades | 5 | Order Requires Replanning | 9011773_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-07-19 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2024-07-22 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0050 | 0060 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 1 | EA | 428 | 14 | 539 | 1 | EA | 25.09 - At KGP | Supply for Order 200089884, Item 6 cannot be changed 180066697 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180066697 | 9011774 | 05 | Preparation | 0000128153 | 6 | 0 | EA | 102000000007731 |  | 107000000000399 |  |  |  |  | WorkPackLink | INLEC-CAGE |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-08 | GRST-5000197838_2024 | 0 | 0 | 0 | 0 |  | 2024-07-23 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000026767 | 1020 | 2024-07-16 | 1 |  | 2024-09-05 | 4900126369_2024_0001 | 2024-07-25 |  | 5000197838_2024_0001 | 0 | 2 | 0 | 90011070 | 1 | 0 | 180066697/180071488 | 2 | 0 | 0 | X | L | 4900126369 | 2024 |  | 5000197838 | 2024 | 0 |  | 2024-07-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-05-08 | W |  | 0050 | Remove Spades | INT | Remove Spades | 5 | Order Requires Replanning | 9011774_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-07-22 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0120 | 0030 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 4 | EA | 428 | 14 | 539 | 4 | EA | 10.01 - Picked @ KSF | Supply for Order 200089887, Item 5 cannot be changed 90025037 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 5 | 0 | EA | 102000000031990 | 102000000026929 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | CO2 Spading |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash | 5 | Ready for Release | 90025037_0050 |  |  | LN1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 50 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0160 | 0030 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 4 | EA | 428 | 14 | 539 | 4 | EA | 10.01 - Picked @ KSF | Supply for Order 200089887, Item 16 cannot be changed 90025037 item 160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 16 | 0 | EA | 102000000032005 | 102000000026951 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | CO2 Spading |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0160 | Remove Positive Isolations | INT | Remove Positive Isolations | 5 | Ready for Release | 90025037_0160 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 160 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0120 | 0060 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 8 | EA | 428 | 14 | 539 | 8 | EA | 10.01 - Picked @ KSF | Supply for Order 200089888, Item 14 cannot be changed 90025038 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025038 | 05 | Preparation | 0000128157 | 14 | 0 | EA | 102000000032002 | 102000000026930 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025038_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025038 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025038_0080 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 80 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0120 | 0050 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 8 | EA | 428 | 14 | 539 | 8 | EA | 10.01 - Picked @ KSF | Supply for Order 200089889, Item 14 cannot be changed 90025039 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 14 | 0 | EA | 102000000032028 | 102000000026925 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025039_0080 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 14 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 80 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-06-01 | 2025-05-27 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0120 | 0070 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 8 | EA | 428 | 14 | 539 | 8 | EA | 10.01 - Picked @ KSF | Supply for Order 200089890, Item 23 cannot be changed 90025060 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025060 | 05 | Preparation | 0000128159 | 23 | 0 | EA | 102000000032017 | 102000000026928 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025060_0060 | 0 | 0 | 0 | 0 |  | 2025-05-30 | AA53 | 2025-03-01 |  |  | 2025-06-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-05-27 |  | 2025-06-01 | Isolations |  | 0 | 2 | 0 | 90025060 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025060_0060 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 23 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 90 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-05-27 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0120 | 0070 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 8 | EA | 428 | 14 | 539 | 8 | EA | 10.01 - Picked @ KSF | Supply for Order 200089891, Item 17 cannot be changed 90025062 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025062 | 05 | Preparation | 0000128160 | 17 | 0 | EA | 102000000032020 | 102000000026927 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025062_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025062_0100 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 17 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 100 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0620 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 12 | EA | 428 | 14 | 539 | 12 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 70 cannot be changed 90025019 item 680 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 680 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 70 | 0 | EA | 102000000032113 | 102000000026926 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0680 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0680 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 70 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 680 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT7 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 200144873 | 0100 | 0020 | 200144873 | 12Y INSP INT FIN FAN GT4007E1 | AA53.GT4007E1 | EXCH,HEAT SYNTHETIC OIL COOLER,GT4007 | AA01 | 10 | WO item has not been released yet | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2 | EA | 428 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000232068 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200144873 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 |  |  |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDGT7 | MJ |  |  | 1000229155 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240413 | 2024-04-13 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-13 | MECH | 200152144 | 0010 | 0010 | 200152144 | 12Y INSP INT EXCHANGER 5E2005 | AA53.5E2005 | HTR,SUCTION ELEC 5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(24.01.2025) | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 1 | EA | 428 | 14 | 539 | 1 | EA | 28.01 - ETA 15.04.25 PO 4500043595 ex KLINGER | Supply for Order 200152144, Item 1 cannot be changed 90030060 item 10 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020429 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030060 | 05 | Preparation | 0000242789 | 1 | 0 | EA |  |  | 102000000032392 |  |  |  |  | WorkPackLink | PACKING | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-24 | ODST-0090030060_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-08 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200152144 |  | 0 | 2 | 0 | 90030060 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 2025-01-24 | W |  | 0010 | Operator Assist - Heat Trace Isolation | INT | Operator Assist - Heat Trace Isolation | 5 |  | 90030060_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000239484 | S002 | 30 | 30 | 5300020429 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-06-07 | 242789 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-13 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0390 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 4 | EA | 428 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 37 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0250 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 8 | EA | 428 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 24 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0120 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 | 4 | EA | 428 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 11 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET:SWCI,50MM,CL300/600,316L/GR/316 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0050 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | WO item has not been released yet | 10060923 | GASKET:SW;150MM,CL900,RF,316L/GR/316 | 6 | EA | 17 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235400 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 |  |  |  |  | 200147128 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060923 | GASKET:SW;150MM,CL900,RF,316L/GR/316 |  |  |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232443 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD4403 | Released | 2025-02-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | INLEC | 100031876 | 0030 | 0020 | 100031876 | Replace Needle Manifold - 44FV540 | AA53.44PDT531 | TX,PRESS K4403 SEALGAS PRIM VNT TO FLRE | AA01 | 30 | WO item has not been released yet | 10060927 | GASKET:SWCI,15MM,CL1500,316L/GR/316 | 2 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130317 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-11-08 | 0 |  |  |  |  | 100031876/77 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060927 | GASKET:SWCI,15MM,CL1500,316L/GR/316 |  |  |  | 0030 | Complete Replacement | INT | Complete Replacement | [5 empty] | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD4403 | MJ |  |  | 1000129686 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Material shortage/Order Approved/Released/Settlement rule created/Part printed | AM01 | Reactive Maintenance
1 | 25SD4403 | Released | 2025-02-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | INLEC | 100031877 | 0020 | 0010 | 100031877 | Replace Needle Manifold - 44FV539 | AA53.44PDT530 | TX,PRESS K4403 SEALGAS PRIM VNT TO FLRE | AA01 | 30 | WO item has not been released yet | 10060927 | GASKET:SWCI,15MM,CL1500,316L/GR/316 | 2 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130318 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-11-08 | 0 |  |  |  |  | 100031877 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060927 | GASKET:SWCI,15MM,CL1500,316L/GR/316 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Engineering Query |  |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SD4403 | MJ |  |  | 1000129687 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Engineering Query |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Settlement rule created/Part printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2590 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060927 | GASKET:SWCI,15MM,CL1500,316L/GR/316 | 10 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 386 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060927 | GASKET:SWCI,15MM,CL1500,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2600 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060929 | GASKET:SWCI,25MM,CL1500,316L/GR/316 | 10 | EA | 28 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 387 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060929 | GASKET:SWCI,25MM,CL1500,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2280 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060930 | GASKET:SWCI,40MM,CL1500,316L/GR/316 | 2 | EA | 66 | 4 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 333 cannot be changed 90028419 item 2590 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2620 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 333 | 0 | EA | 102000000030482 | 102000000030211 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2590 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060930 | GASKET:SWCI,40MM,CL1500,316L/GR/316 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2590 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 333 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2620 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDDG1 | Released | 2025-02-11 | 2025-03-12 |  | 2025-03-01 | 2025-06-06 | MECH | 100086858 | 0130 | 0010 | 100086858 | 1E2406 externally corroded tube ends | AA53.1E2406 | EXCH,HEAT AFTER COOLER FOR COMPR | AA01 | 10 | WO item has not been released yet | 10060931 | GASKET:SWCI,50MM,CL1500,316L/GR/316 | 36 | EA | 30 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000275554 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 36 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-12 |  |  | 2025-03-12 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 100086858 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060931 | GASKET:SWCI,50MM,CL1500,316L/GR/316 |  |  |  | 0130 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000270168 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-06 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-06-06 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2025-02-11 | 2025-05-09 |  | 2025-03-01 | 2025-05-11 | MECH | 100086859 | 0130 | 0010 | 100086859 | 1E2405 externally corroded tube ends | AA53.1E2405 | EXCH,HEAT AFTER COOLER FOR COMPR | AA01 | 10 | WO item has not been released yet | 10060931 | GASKET:SWCI,50MM,CL1500,316L/GR/316 | 16 | EA | 30 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000275555 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-09 |  |  | 2025-05-09 |  |  |  |  | 2025-10-31 | 0 |  |  |  |  | 100086859 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060931 | GASKET:SWCI,50MM,CL1500,316L/GR/316 |  |  |  | 0130 | Refit Drain and Vent Flanges | INT | Refit Drain and Vent Flanges | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000270169 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-06 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-11 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0310 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 10 | EA | 66 | 0 | 101 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 31 cannot be changed 90032376 item 290 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 31 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0290 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0290 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 31 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 310 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-03-01 | 2025-03-11 | MECH | 200082188 | 0140 | 0060 | 200082188 | 6Y P02 INT INSP EXCHANGER 1E2407 | AA53.1E2407 | EXCH,HEAT RE INJ VAPOURISER 1E2407 | AA01 | 10 | WO item has not been released yet | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 1 | EA | 66 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117838 | 7 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 200082188 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  |  |  | 0140 | Re-instate Bonnet & Spools | INT | Re-instate Bonnet & Spools | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000117251 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-05 | MECH | 200088516 | 0110 | 0030 | 200088516 | 8Y P02 INT INSP FIN FAN 5E2003 | AA53.5E2003 | EXCH,HEAT COMPRESSOR DISCHARGE COOL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 8 | EA | 66 | 0 | 101 | 8 | EA | 15.01 - SOH @ AA02 | Supply for Order 200088516, Item 3 cannot be changed 90028586 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020032 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028586 | 05 | Preparation | 0000126825 | 3 | 0 | EA | 102000000031899 | 102000000031568 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028586_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028586 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2025-01-14 | W |  | 0110 | Punchlist & Closeout WP200088516MET001 | ENON | Punchlist & Closeout WP200088516MET001 | 5 | Ready for Release | 90028586_0030 |  |  | ST5 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126175 | S002 | 30 | 30 | 5300020032 | 30 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 126825 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-08-08 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 100031838 | 0010 | 0040 | 100031838 | MV-RE 6" 600# 520GAV1667 | AA53.520HCV10A | VALVE,COMP O/H VAP TO DOMGAS | AA01 | 20 | WO item has not been released yet | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 | 2 | EA | 50 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000130239 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-05-05 | 0 |  |  |  |  | 100031838 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 |  |  |  | 0010 | Remove & Replace Valve | INT | Remove & Replace Valve | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000129668 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Settlement rule created | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0330 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 | 10 | EA | 50 | 0 | 4 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 33 cannot be changed 90032376 item 310 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 33 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0310 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0310 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 33 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 330 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SD2301 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200146986 | 0060 | 0030 | 200146986 | MOC-149553 EX/SH INSP TUB/RVDI BONREM | AA53.1E2402 | EXCH,HEAT FEED GAS LIQUID FIXED | AA01 | 10 | WO item has not been released yet | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 | 2 | EA | 50 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235448 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 |  |  |  | 0060 | Remove Bonnet and Vent/Drain Blinds | INT | Remove Bonnet and Vent/Drain Blinds | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232419 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-02 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0070 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | WO item has not been released yet | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 | 3 | EA | 50 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235400 | 7 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 |  |  |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232443 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0970 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 | 8 | EA | 50 | 0 | 4 | 8 | EA | 24.09 - SOH at AA02 | Supply for Order 200147980, Item 97 cannot be changed 90028418 item 190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 97 | 0 | EA | 102000000030539 | 102000000030216 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0190 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 97 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 200 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDLN1 | Released | 2024-08-15 | 2025-03-01 |  | 2025-02-19 | 2025-03-03 | MECH | 600003215 | 0020 | 0030 | 600003215 | MOC-117109 1E1303 Exchanger Replacement | AA53.1E1303 | EXCH,HEAT AIR COOL REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 | 8 | EA | 50 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000254308 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060933 | GASKET;SWCI,150MM,CL600,316L/GR/316 |  |  |  | 0020 | Remove blanks For Inspection Access | INT | Remove blanks For Inspection Access |  | Management of Change |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000250524 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W35069 | 2024-08-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-02-19 | 2025-02-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital | M0-000001-99-02
1 | 25SD2301 | Released | 2025-01-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | MECH | 200146986 | 0060 | 0020 | 200146986 | MOC-149553 EX/SH INSP TUB/RVDI BONREM | AA53.1E2402 | EXCH,HEAT FEED GAS LIQUID FIXED | AA01 | 10 | WO item has not been released yet | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 2 | EA | 14 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235448 | 2 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 |  |  |  | 0060 | Remove Bonnet and Vent/Drain Blinds | INT | Remove Bonnet and Vent/Drain Blinds | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232419 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-02 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance
1 | 25SDDG1 | Released | 2024-10-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200160316 | 0030 | 0010 | 200160316 | 10Y INSPECT 8" 600# 44CHV1107 | AA53.44CHV1107 | VALVE,CHECK HP FG TO K2430 | AA01 | 10 | WO item has not been released yet | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 2 | EA | 14 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255550 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-SD-UT1 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  |  |  |  | 200160316 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 |  |  |  | 0030 | Install NRV | INT | Install NRV | 5 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000251639 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-08-15 | 2025-03-01 |  | 2025-02-19 | 2025-03-03 | MECH | 600003215 | 0020 | 0040 | 600003215 | MOC-117109 1E1303 Exchanger Replacement | AA53.1E1303 | EXCH,HEAT AIR COOL REGENERATION GAS | AA01 | 10 | WO item has not been released yet | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 4 | EA | 14 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000254308 | 4 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 |  |  |  | 0020 | Remove blanks For Inspection Access | INT | Remove blanks For Inspection Access |  | Management of Change |  |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0065 | Ready for Execution (Order) | ZBPM0006 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000250524 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W35069 | 2024-08-01 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-03 | 2025-02-19 | 2025-02-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM06 | Capital | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0320 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 | 6 | EA | 47 | 0 | 6 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 32 cannot be changed 90032376 item 300 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 32 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0300 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0300 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 32 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 |  | 30 | 5300022012 | 320 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN1 | Released | 2024-11-19 | 2025-03-01 |  | 2025-03-01 | 2025-03-02 | VALVE | 600003361 | 0020 | 0010 | 600003361 | MOC-120323 - CV-RE 10" 600# 141FCV01 | AA53.141FCV01 | VALVE,H/W FLOW TO 1E4101 CV | AA01 | 20 | WO item has not been released yet | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 | 2 | EA | 47 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000266685 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-23 | 0 |  |  |  |  | 600003361 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 |  |  |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0035 | In Planning (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000261577 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-09-24 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Material shortage/Printed | AM06 | Capital
| 25SDLN1 | Released | 2024-11-19 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 600003400 | 0020 | 0040 | 600003400 | MOC-120323 - CV-RE 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 | 2 | EA | 47 | 0 | 6 | 2 | EA | 22.11 - SOH @ AA02 | Supply for Order 600003400, Item 4 cannot be changed 90025120 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018070 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025120 | 03 | Planning | 0000266702 | 4 | 0 | EA | 102000000032030 | 102000000027398 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-19 | ODST-0090025120_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-09-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | 600003400 |  | 0 | 2 | 0 | 90025120 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 | 2024-11-20 | W |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve |  |  | 90025120_0020 |  |  | LN1 |  | C3 |  |  |  | Z1 | WEG Priority | 0035 | In Planning (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000261698 | S002 |  | 30 | 5300018070 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-09-24 | 266702 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00018003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Material shortage/Printed | AM06 | Capital
1 | 25SDLN1 | Released | 2024-11-12 | 2025-03-01 |  | 2025-03-01 | 2025-06-09 | VALVE | 100034564 | 0020 | 0020 | 100034564 | CV-OH 12" 600# 111UCV032 | AA53.111UCV032 | VALVE,CTRL REFLUX C1101 | AA01 | 10 | WO item has not been released yet | 10060936 | GASKET;SWCI,300MM,CL600,316L/GR/316 | 2 | EA | 6 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000133016 | 3 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2027-10-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060936 | GASKET;SWCI,300MM,CL600,316L/GR/316 |  |  |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [5 empty] | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000132426 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-06-09 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0340 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10060936 | GASKET;SWCI,300MM,CL600,316L/GR/316 | 10 | EA | 6 | 0 | 6 | 0 |  | 07.03 - ETA 26.03.25 PO 4500048413 KLINGER CPT | Supply for Order 100090053, Item 34 cannot be changed 90032376 item 320 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 34 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0320 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060936 | GASKET;SWCI,300MM,CL600,316L/GR/316 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0320 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 34 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 340 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDDG1 | Released | 2024-10-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200160315 | 0050 | 0010 | 200160315 | 10Y INSPECT 16" 600# 124CHV0792 | AA53.124CHV0792 | VALVE,CHECK U2401 3RD STG COMP BYPASS | AA01 | 10 | WO item has not been released yet | 10060938 | GASKET;SWCI,400MM,CL600,316L/GR/316 | 2 | EA | 8 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255547 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  |  |  |  | 200160315 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060938 | GASKET;SWCI,400MM,CL600,316L/GR/316 |  |  |  | 0050 | Install NRV | INT | Install NRV | 5 | Ready for Release |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000251636 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0400 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 | 4 | EA | 25 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 40 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060941 | GASKET;SWCI,600MM,CL600,316L/GR/316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDDG1 | Released | 2024-10-15 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | VALVE | 200160315 | 0050 | 0030 | 200160315 | 10Y INSPECT 16" 600# 124CHV0792 | AA53.124CHV0792 | VALVE,CHECK U2401 3RD STG COMP BYPASS | AA01 | 10 | WO item has not been released yet | 10060947 | GASKET:SWCI,400MM,CL900,316L/GR/316 | 2 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000255547 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-SD-DG | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  |  |  |  | 200160315 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060947 | GASKET:SWCI,400MM,CL900,316L/GR/316 |  |  |  | 0050 | Install NRV | INT | Install NRV | 5 | Ready for Release |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDDG1 | MJ |  |  | 1000251636 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2610 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060956 | GASKET;32MM,RF,316LSS,GR,CL150 | 10 | EA | 10 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 388 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060956 | GASKET;32MM,RF,316LSS,GR,CL150 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2620 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060961 | GASKET;SWCI,65MM,CL150,316L/GR/316 | 10 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 389 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060961 | GASKET;SWCI,65MM,CL150,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 |  | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0530 | 0060 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | WO item has not been released yet | 10060961 | GASKET;SWCI,65MM,CL150,316L/GR/316 | 1 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084301 | 24 | 0 | [8 empty] | WorkPackLink |  | 5K-2001 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 600001363 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060961 | GASKET;SWCI,65MM,CL150,316L/GR/316 |  |  |  | 0530 | Mechanical Tie in | INT | Mechanical Tie in | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000083685 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0500 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060983 | GASKET;SWCI,90MM,CL150,316L/GR/316 | 10 | EA | 14 | 0 | 0 | 10 | EA | 13.01 - SOH @ AA02 | Supply for Order 200091513, Item 50 cannot be changed 90028419 item 420 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 50 | 0 | EA | 102000000030481 | 102000000030905 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0420 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060983 | GASKET;SWCI,90MM,CL150,316L/GR/316 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0420 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 50 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 430 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2630 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10060983 | GASKET;SWCI,90MM,CL150,316L/GR/316 | 10 | EA | 14 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 390 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060983 | GASKET;SWCI,90MM,CL150,316L/GR/316 |  |  |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2210 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10060984 | GASKET,SWCI;125MM,CL300,316L,125MM | 2 | EA | 26 | 0 | 4 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 326 cannot be changed 90028419 item 2530 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 326 | 0 | EA | 102000000030482 | 102000000030225 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2530 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060984 | GASKET,SWCI;125MM,CL300,316L,125MM | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2530 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 326 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2560 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-25 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0030 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.05.2024) | 10060985 | GASKET;SWCI,1500MM,CL150,316L/GR/316 | 10 | EA | 12 | 0 | 0 | 8 | EA | 21.02 - SOH @ AA02 | Supply for Order 600001757, Item 9 cannot be changed 90024969 item 10 already exists | Material picked; currently at 30-03-06-80B/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 80 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024969 | 07 | Execution | 0000084653 | 9 | 0 | EA |  |  | 102000000031484 |  |  |  |  | WorkPackLink | 30-03-06-80B | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024969_0010 | 0 | 0 | 0 | 0 |  | 2025-02-26 | AA53 | 2025-04-30 |  |  | 2025-02-28 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-25 |  | 2025-02-28 | 600001757600 |  | 0 | 2 | 0 | 90024969 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060985 | GASKET;SWCI,1500MM,CL150,316L/GR/316 | 2024-05-29 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024969_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 9 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 80 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-25 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDFLR | Released | 2024-01-24 | 2025-02-28 | 2025-02-25 | 2024-11-26 | 2025-05-13 | MECH | 600001757 | 0015 | 0030 | 600001757 | MOC-48081 - Replace S&L Flare Tip A3711A | AA53.A3711A | STACK,FLARE TIP FOR A RISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.05.2024) | 10060985 | GASKET;SWCI,1500MM,CL150,316L/GR/316 | 10 | EA | 12 | 0 | 0 | 2 | EA | 21.02 - SOH @ AA02 | Supply for Order 600001757, Item 9 cannot be changed 90024969 item 10 already exists | Material picked; currently at 30-03-06-80B/Z830 @A | SP12 | Stock at Base | 0 | AA02 | 5300005523 | 80 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024969 | 07 | Execution | 0000084653 | 9 | 0 | EA |  |  | 102000000031483 |  |  |  |  | WorkPackLink | 30-03-06-80B | T25-SL0-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-24 | ODST-0090024969_0010 | 0 | 0 | 0 | 0 |  | 2025-02-26 | AA53 | 2025-04-30 |  |  | 2025-02-28 |  |  |  |  | 2025-08-30 | 0 |  | 2025-02-25 |  | 2025-02-28 | 600001757600 |  | 0 | 2 | 0 | 90024969 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-25 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060985 | GASKET;SWCI,1500MM,CL150,316L/GR/316 | 2024-05-29 | W |  | 0015 | LL_Replace Flare Tip - A3711A | INT | LL_Replace Flare Tip - A3711A |  | Management of Change/Order Requires Replanning | 90024969_0010 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 9 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084067 | S002 | 30 | 30 | 5300005523 | 80 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-25 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  | 2024-11-26 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84653 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-13 | 2024-11-26 | 2024-11-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Partially confirmed/Material shortage | AM06 | Capital
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0200 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10061033 | GASKET;SWCI,1370 X 1510,4.5MM,SS/GRAP/SS | 6 | EA | 6 | 0 | 0 | 3 | EA | 30.12 - SOH @ AA01 | Supply for Order 100087648, Item 21 cannot be changed 90028417 item 200 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 21 | 0 | EA | 101000000026140 |  | 101000000136865 | 01-Road |  | 5-Completed |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 | 2025-01-23 | 2025-01-23 | Y | 1001 | 2024-11-22 | ODST-0090028417_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061033 | GASKET;SWCI,1370 X 1510,4.5MM,SS/GRAP/SS | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0200 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 21 |  | 0 |  | 25SDSTB5 | MJ | 20005202 | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 200 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-21 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0200 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10061033 | GASKET;SWCI,1370 X 1510,4.5MM,SS/GRAP/SS | 6 | EA | 6 | 0 | 0 | 3 | EA | 30.12 - SOH @ AA01 | Supply for Order 100087648, Item 21 cannot be changed 90028417 item 200 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 21 | 0 | EA | 101000000130270 |  | 101000000136865 | 01-Road |  | 5-Completed |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 | 2025-01-23 | 2025-01-23 | Y | 1001 | 2024-11-22 | ODST-0090028417_0200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061033 | GASKET;SWCI,1370 X 1510,4.5MM,SS/GRAP/SS | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0200 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 21 |  | 0 |  | 25SDSTB5 | MJ | 20005202 | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 200 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-21 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0220 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10061035 | GASKET,SWCI,1510 X 1660,4.5MM,SS/GRAP/SS | 2 | EA | 2 | 0 | 0 | 2 | EA | 02.03 - SOH @ AA02 | Supply for Order 100087648, Item 23 cannot be changed 90028417 item 220 already exists | Material picked; currently at KSF-PACK-SD-LRG/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028417 | 05 | Preparation | 0000278190 | 23 | 0 | EA |  |  | 101000000130271 | 01-Road |  | 5-Completed |  | WorkPackLink | KSF-PACK-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 2 | 2025-01-26 | 2025-01-23 | Y | 1001 | 2024-11-22 | ODST-0090028417_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5E2001 |  | 0 | 2 | 0 | 90028417 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061035 | GASKET,SWCI,1510 X 1660,4.5MM,SS/GRAP/SS | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 90028417_0220 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 23 |  | 0 |  | 25SDSTB5 | MJ | 20005203 | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 220 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-21 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0090 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10061094 | GASKET,SW;271 X 288.5 X 4.5MM,316L/GR | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 03.04.25 PO 4500043754 exFlowserve | Supply for Order 100079771, Item 9 cannot be changed 90028600 item 70 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 9 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061094 | GASKET,SW;271 X 288.5 X 4.5MM,316L/GR | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0070 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 |  | 30 | 5300020063 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1980 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10061145 | GASKET;SWI,148 X 180,4.5MM,316L/GR/316 | 2 | EA | 17 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 278 cannot be changed 90028419 item 2170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 278 | 0 | EA | 102000000030501 | 102000000030904 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ONCONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061145 | GASKET;SWI,148 X 180,4.5MM,316L/GR/316 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_2170 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 278 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2200 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0100 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10061279 | GASKET,MET,76 X 91 X 4.0MM,SS/GR | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 16.04.25 PO 4500043754 Flowserve CPT | Supply for Order 100079771, Item 10 cannot be changed 90028600 item 80 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 10 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061279 | GASKET,MET,76 X 91 X 4.0MM,SS/GR | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0080 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 |  | 30 | 5300020063 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-02-20 | 2025-03-01 | ROTAT | 100079771 | 0040 | 0110 | 100079771 | RE MOTOR & OH PUMP - 1.5" 300# -5K2001P3 | AA53.5K2001PM3 | MOTOR,CHILLED WATER PUMP STABILISER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10061280 | GASKET,MET,8 X 32 X 1.6MM,SS/GR | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 14.04.25 PO 4500043754 exFlowserve | Supply for Order 100079771, Item 11 cannot be changed 90028600 item 90 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020063 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028600 | 07 | Execution | 0000246943 | 11 | 0 | [8 empty] | WorkPackLink |  | T25-W1-ST5-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028600_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-27 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100079771 |  | 0 | 2 | 0 | 90028600 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061280 | GASKET,MET,8 X 32 X 1.6MM,SS/GR | 2025-01-14 | W |  | 0040 | Install Pump From 4K2001P3 | INT | Install Pump From 4K2001P3 |  |  | 90028600_0090 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000243501 | S002 |  | 30 | 5300020063 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-20 | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246943 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-02-20 | 2025-02-20 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Date set by external system/Partially confirmed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0030 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.01.2025) | 10061281 | GASKET,FLAT,642 X 668 X 2.5MM,SS316 | 2 | EA | 2 | 0 | 0 | 2 | EA | 18.02 - SOH @ AA02 | Supply for Order 200147128, Item 3 cannot be changed 90030059 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020226 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030059 | 05 | Preparation | 0000235400 | 3 | 0 | EA | 101000000145612 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-20 | ODST-0090030059_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147128 |  | 0 | 2 | 0 | 90030059 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061281 | GASKET,FLAT,642 X 668 X 2.5MM,SS316 | 2025-01-20 | W |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection |  |  | 90030059_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000232443 | S002 |  | 30 | 5300020226 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235400 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0292 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10061312 | GASKET,METALLIC,22.5 X 26.5 X 1.0MM,CU | 2 | EA | 3 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091126, Item 125 cannot be changed 90023534 item 730 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1020 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 125 | 0 | EA | 102000000030443 | 102000000031105 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061312 | GASKET,METALLIC,22.5 X 26.5 X 1.0MM,CU | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0730 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 125 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1020 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2280 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10061324 | GASKET;150MM,NTRL GR T,ORN STRIPE | 2 | EA | 12 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 307 cannot be changed 90028419 item 2400 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 307 | 0 | EA | 102000000030491 | 102000000030357 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2400 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061324 | GASKET;150MM,NTRL GR T,ORN STRIPE | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2400 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 307 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2430 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-02 | MECH | 200147079 | 0030 | 0030 | 200147079 | 4Y INSP INT EXCHANGER 1KKT2420E3 | AA53.1KKT2420E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.01.2025) | 10061324 | GASKET;150MM,NTRL GR T,ORN STRIPE | 4 | EA | 12 | 0 | 0 | 4 | EA | 18.02 - SOH @ AA02 | Supply for Order 200147079, Item 3 cannot be changed 90030058 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020191 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030058 | 05 | Preparation | 0000235350 | 3 | 0 | EA | 101000000145614 |  | 102000000034100 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-01-20 | ODST-0090030058_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-28 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147079 |  | 0 | 2 | 0 | 90030058 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061324 | GASKET;150MM,NTRL GR T,ORN STRIPE | 2025-01-20 | W |  | 0030 | Remove Bonnet / Spools & Install Blinds | INT | Remove Bonnet / Spools & Install Blinds |  |  | 90030058_0030 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232393 | S002 | 30 | 30 | 5300020191 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235350 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200174926 | 0030 | 0020 | 200174926 | Replace Exchanger - 1KKT2430E3 | AA53.1KKT2430E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2430 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10061324 | GASKET;150MM,NTRL GR T,ORN STRIPE | 4 | EA | 12 | 0 | 0 | 2 | EA | 18.02 - SOH @ AA02 | Supply for Order 200174926, Item 3 cannot be changed 90028606 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020026 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028606 | 05 | Preparation | 0000277561 | 3 | 0 | EA | 102000000031381 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028606_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-07-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174926 |  | 0 | 2 | 0 | 90028606 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061324 | GASKET;150MM,NTRL GR T,ORN STRIPE | 2025-01-14 | W |  | 0030 | Remove Bonnet / Spools & Structure | INT | Remove Bonnet / Spools & Structure |  |  | 90028606_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000272048 | S002 | 30 | 30 | 5300020026 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277561 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200174926 | 0030 | 0020 | 200174926 | Replace Exchanger - 1KKT2430E3 | AA53.1KKT2430E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2430 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10061324 | GASKET;150MM,NTRL GR T,ORN STRIPE | 4 | EA | 12 | 0 | 0 | 2 | EA | 18.02 - SOH @ AA02 | Supply for Order 200174926, Item 3 cannot be changed 90028606 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020026 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028606 | 05 | Preparation | 0000277561 | 3 | 0 | EA | 102000000034005 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028606_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-07-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174926 |  | 0 | 2 | 0 | 90028606 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061324 | GASKET;150MM,NTRL GR T,ORN STRIPE | 2025-01-14 | W |  | 0030 | Remove Bonnet / Spools & Structure | INT | Remove Bonnet / Spools & Structure |  |  | 90028606_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000272048 | S002 | 30 | 30 | 5300020026 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277561 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0040 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061334 | GASKET,NON-M;330 X 440 X 4.0MM,NEOP | 1 | EA | 0 | 0 | 0 | 0 |  | 15.10 - ETA 18.03.25 PO 4500031473 BH | Supply for Order 200147980, Item 163 cannot be changed 90028418 item 700 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 163 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0700 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Cov Gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061334 | GASKET,NON-M;330 X 440 X 4.0MM,NEOP | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0700 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 163 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 730 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0110 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061350 | GASKET;80MM,90MM,136MM,CNAF,FF | 1 | EA | 7 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 170 cannot be changed 90028418 item 770 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 800 |  | 7 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 170 | 0 | EA | 102000000030535 | 102000000030088 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | frame gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061350 | GASKET;80MM,90MM,136MM,CNAF,FF | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0770 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 170 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 800 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0960 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061352 | GASKET;CNAF,220 X 240 X 2.0MM,MIN FIB | 1 | EA | 6 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 96 cannot be changed 90028418 item 180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 96 | 0 | EA | 102000000030539 | 102000000030280 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061352 | GASKET;CNAF,220 X 240 X 2.0MM,MIN FIB | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0180 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 96 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0060 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061355 | GASKET;CNAF,111 X 200 X 1MM,MIN FIB | 1 | EA | 6 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 165 cannot be changed 90028418 item 720 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 165 | 0 | EA | 102000000030535 | 102000000030886 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0720 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Cov gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061355 | GASKET;CNAF,111 X 200 X 1MM,MIN FIB | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0720 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 165 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 750 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0180 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061355 | GASKET;CNAF,111 X 200 X 1MM,MIN FIB | 1 | EA | 6 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 177 cannot be changed 90028418 item 840 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 177 | 0 | EA | 102000000030535 | 102000000030887 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | NDE Shield |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061355 | GASKET;CNAF,111 X 200 X 1MM,MIN FIB | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0840 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 177 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 870 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0120 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061358 | GASKET;CNAF,100 X 178 X 2MM,MIN FIB | 1 | EA | 6 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 171 cannot be changed 90028418 item 780 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 171 | 0 | EA | 102000000030535 | 102000000030885 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | frame gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061358 | GASKET;CNAF,100 X 178 X 2MM,MIN FIB | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0780 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 171 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 810 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | ROTAT | 200088840 | 0060 | 0010 | 200088840 | 5Y P03 SD 5K2001 CRANKCASE RELIEF INSP | AA53.520RV502 | VALVE,CRANKCASE EXPLOSION 5K2001 | AA01 | 10 | No issue identified | 10061359 | GASKET;CNAF,350 X 410 X 2MM,MIN FIB | 1 | EA | 3 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015695 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025007 | 05 | Preparation | 0000127070 | 1 | 0 | EA | 102000000027808 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025007_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025007 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061359 | GASKET;CNAF,350 X 410 X 2MM,MIN FIB |  |  |  | 0060 | REINSTALL 520RV502 | INT | REINSTALL 520RV502 |  |  | 90025007_0010 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000126472 | S002 |  | 30 | 5300015695 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127070 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0130 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061360 | GASKET;102MM,190.5MM,CNAF | 1 | EA | 3 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 172 cannot be changed 90028418 item 790 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 172 | 0 | EA | 102000000030535 | 102000000030809 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0790 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | frame gasket |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061360 | GASKET;102MM,190.5MM,CNAF | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0790 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 172 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 820 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0030 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10061368 | GASKET;CNAF,470 X 490 X 1.5MM,MIN FIB | 2 | EA | 11 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 605 cannot be changed 90028419 item 4120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 605 | 0 | EA | 102000000030356 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061368 | GASKET;CNAF,470 X 490 X 1.5MM,MIN FIB | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4120 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 605 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4150 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2290 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 2 | EA | 12 | 0 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200091513, Item 308 cannot be changed 90028419 item 2410 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 308 | 0 | EA | 102000000033637 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2410 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2410 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 308 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2440 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0190 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 3 | EA | 12 | 0 | 0 | 0 |  | 15.01 - SOH @ AA02 | Supply for Order 200091513, Item 640 cannot be changed 90028419 item 4260 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 640 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4260 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 640 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4290 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0270 | 0050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 4 | EA | 12 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 607 cannot be changed 90028419 item 4140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 607 | 0 | EA |  |  | 102000000033638 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 2024-07-21 | W |  | 0270 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028419_4140 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 607 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4170 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-02 | MECH | 200147079 | 0030 | 0020 | 200147079 | 4Y INSP INT EXCHANGER 1KKT2420E3 | AA53.1KKT2420E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(19.01.2025) | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 2 | EA | 12 | 0 | 0 | 0 |  | 21.01 - ETA 14.02.25 PO 4500043420 KLINGER CPT | Supply for Order 200147079, Item 2 cannot be changed 90030058 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020191 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030058 | 05 | Preparation | 0000235350 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-20 | ODST-0090030058_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-28 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147079 |  | 0 | 2 | 0 | 90030058 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 2025-01-19 | W |  | 0030 | Remove Bonnet / Spools & Install Blinds | INT | Remove Bonnet / Spools & Install Blinds |  |  | 90030058_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232393 | S002 | 30 | 30 | 5300020191 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235350 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-02 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 200174926 | 0030 | 0030 | 200174926 | Replace Exchanger - 1KKT2430E3 | AA53.1KKT2430E3 | EXCH,HEAT LUBE OIL COOLER 1KKT2430 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 2 | EA | 12 | 0 | 0 | 0 |  | 15.01 - SOH @ AA02 | Supply for Order 200174926, Item 4 cannot be changed 90028606 item 30 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020026 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028606 | 05 | Preparation | 0000277561 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028606_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-07-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174926 |  | 0 | 2 | 0 | 90028606 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061416 | GASKET;CNAF,441 X 478 X 2MM,C4500,CTD | 2025-01-14 | W |  | 0030 | Remove Bonnet / Spools & Structure | INT | Remove Bonnet / Spools & Structure |  |  | 90028606_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000272048 | S002 | 30 | 30 | 5300020026 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277561 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0020 | 0160 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061419 | GASKET,NON-M;330 X 380 X 16MM,FELT | 1 | EA | 3 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 175 cannot be changed 90028418 item 820 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 175 | 0 | EA | 102000000030535 | 102000000030359 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0820 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE Shield |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061419 | GASKET,NON-M;330 X 380 X 16MM,FELT | 2024-09-23 | W |  | 0020 | FRAME ASSY | ENON | FRAME ASSY | 5 |  | 90028418_0820 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 175 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 850 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0010 | 0020 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10061521 | GASKET,NON-METALLIC;FLOWSV 001886925000 | 2 | EA | 3 | 1 | 4 | 2 | EA | 18.02 - SOH @ AA02 | Supply for Order 100085072, Item 2 cannot be changed 90028434 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028434 | 05 | Preparation | 0000267773 | 2 | 0 | EA | 101000000143123 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-08 | ODST-0090028434_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028434 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061521 | GASKET,NON-METALLIC;FLOWSV 001886925000 | 2025-01-08 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  | Management of Change/Order Requires Replanning | 90028434_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 |  | 30 | 5300019757 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-11-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 100085092 | 0010 | 0020 | 100085092 | ACT-IS 123FCV03 | AA53.123FCV03 | VALVE,CTRL FLOW REGEN GAS TO 1E2302 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(14.11.2024) | 10061521 | GASKET,NON-METALLIC;FLOWSV 001886925000 | 2 | EA | 3 | 1 | 4 | 1 | EA | 18.02 - SOH @ AA02 | Supply for Order 100085092, Item 2 cannot be changed 90025111 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017886 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025111 | 05 | Preparation | 0000267720 | 2 | 0 | EA | 102000000029800 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025111_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-24 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025111 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061521 | GASKET,NON-METALLIC;FLOWSV 001886925000 | 2024-11-14 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve |  |  | 90025111_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000262780 | S002 |  | 30 | 5300017886 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267720 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0950 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10061844 | O-RING;BUNAN,0.139",3.234"ID,70,BS236 | 2 | EA | 0 | 0 | 0 | 0 |  | 16.12 - qty 2 SOH @ AA01 | Supply for Order 200147980, Item 95 cannot be changed 90028418 item 170 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 95 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10061844 | O-RING;BUNAN,0.139",3.234"ID,70,BS236 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0170 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 95 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 | 30 | 30 | 5300015696 | 180 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0170 | 0850 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10062030 | O-RING;VITONA,0.070",0.250"ID,75,BS010 | 34 | EA | 44 | 0 | 0 | 34 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 155 cannot be changed 90028418 item 630 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 155 | 0 | EA |  |  | 102000000030379 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 34 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0630 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062030 | O-RING;VITONA,0.070",0.250"ID,75,BS010 | 2024-09-23 | W |  | 0170 | PISTON ROD PACKING Stuffing Box | INT | PISTON ROD PACKING Stuffing Box | 5 |  | 90028418_0630 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 155 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 660 |  |  | 0 | 34 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-07 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0090 | 0342 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10062058 | O-RING;VITONA,0.103",0.812"ID,70,BS117 | 1 | EA | 1 | 0 | 0 | 0 |  | 31.01 - SOH @ AA02 | Supply for Order 200091126, Item 73 cannot be changed 90028438 item 10 already exists | Awaiting work-packing @AA03 | SP12 | Stock at Base | 0 | AA03 | 5300010137 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028438 | 05 | Preparation | 0000129360 | 73 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-05-11 | ODST-0090028438_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-07 |  | 2025-03-01 | LO Pump |  | 0 | 2 | 0 | 90028438 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062058 | O-RING;VITONA,0.103",0.812"ID,70,BS117 | 2024-05-11 | W |  | 0090 | LUBE OIL | INT | LUBE OIL | 5 |  | 90028438_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 73 |  | 0 |  | 25SD2301 | MJ |  | AU1098 | 1000128789 | S003 | 30 |  | 5300010137 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2025-02-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1190 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2300 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10062088 | O-RING;VITONA,0.139",1.171"ID,70,BS217 | 8 | EA | 8 | 0 | 0 | 8 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 309 cannot be changed 90028419 item 2420 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2450 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 309 | 0 | EA | 102000000030491 | 101000000135973 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2420 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062088 | O-RING;VITONA,0.139",1.171"ID,70,BS217 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2420 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 309 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2450 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2900 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10062094 | O-RING;VITONA,0.139",1.875"ID,70,BS225 | 2 | EA | 14 | 0 | 2 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 419 cannot be changed 90028419 item 2910 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2940 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 419 | 0 | EA | 102000000030494 | 102000000030297 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2910 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062094 | O-RING;VITONA,0.139",1.875"ID,70,BS225 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2910 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 419 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2940 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3150 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10062094 | O-RING;VITONA,0.139",1.875"ID,70,BS225 | 2 | EA | 14 | 0 | 2 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 602 cannot be changed 90028419 item 4090 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 602 | 0 | EA | 102000000030496 | 102000000030378 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062094 | O-RING;VITONA,0.139",1.875"ID,70,BS225 | 2024-07-21 | W |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  | 90028419_4090 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 602 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4120 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0230 | 0940 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10062098 | O-RING;VITONA,0.139",2.359"ID,70,BS229 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 94 cannot be changed 90028418 item 160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 94 | 0 | EA | 102000000030539 | 102000000030296 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062098 | O-RING;VITONA,0.139",2.359"ID,70,BS229 | 2024-09-23 | W |  | 0230 | CONSUMABLES | INT | CONSUMABLES | 5 |  | 90028418_0160 |  |  | ST5 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 94 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 170 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0690 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10062114 | O-RING;VITONA,0.139",4.734"ID,70,BS248 | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 76 cannot be changed 90025019 item 730 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 730 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 76 | 0 | EA | 102000000032113 | 102000000027255 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0730 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062114 | O-RING;VITONA,0.139",4.734"ID,70,BS248 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0730 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 76 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 730 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2910 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10062126 | O-RING;VITONA,0.139",10.984"ID,70,BS276 | 2 | EA | 3 | 0 | 0 | 1 | EA | 20.12 - SOH @ AA01 | Supply for Order 200091513, Item 420 cannot be changed 90028419 item 2920 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2950 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 420 | 0 | EA | 102000000030502 | 102000000030374 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2920 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062126 | O-RING;VITONA,0.139",10.984"ID,70,BS276 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2920 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 420 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2950 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2390 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10062138 | O-RING;VITONA,0.210",3.600"ID,70,BS342 | 4 | EA | 43 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 536 cannot be changed 90028419 item 3890 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3920 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 536 | 0 | EA | 102000000030482 | 102000000030373 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3890 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062138 | O-RING;VITONA,0.210",3.600"ID,70,BS342 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_3890 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 536 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3920 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0700 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10062144 | O-RING;VITONA,0.210",4.475"ID,70,BS349 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - 4 SOH @ AA02 | Supply for Order 200091505, Item 77 cannot be changed 90025019 item 740 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 740 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 77 | 0 | EA | 102000000032113 | 102000000027250 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0740 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062144 | O-RING;VITONA,0.210",4.475"ID,70,BS349 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0740 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 77 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 740 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2310 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10062147 | O-RING;VITONA,0.210",12.975"ID,70,BS382 | 2 | EA | 8 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 310 cannot be changed 90028419 item 2430 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 310 | 0 | EA | 102000000030491 | 102000000030640 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2430 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062147 | O-RING;VITONA,0.210",12.975"ID,70,BS382 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2430 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 310 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2460 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0242 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10062153 | O-RING;VITONA,0.275",7.475"ID,70,BS443 | 8 | EA | 9 | 0 | 0 | 7 | EA | 02.03 - SOH @ AA02 | Supply for Order 200091126, Item 136 cannot be changed 90023534 item 840 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 136 | 0 | EA | 102000000030448 | 102000000029830 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062153 | O-RING;VITONA,0.275",7.475"ID,70,BS443 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0840 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 136 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1130 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0060 | 0242 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10062153 | O-RING;VITONA,0.275",7.475"ID,70,BS443 | 8 | EA | 9 | 0 | 0 | 1 | EA | 02.03 - SOH @ AA02 | Supply for Order 200091126, Item 136 cannot be changed 90023534 item 840 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 136 | 0 | EA | 102000000030448 | 102000000033156 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0840 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062153 | O-RING;VITONA,0.275",7.475"ID,70,BS443 | 2024-05-11 | W |  | 0060 | SUCTION VALVE & UNLOADER SPARES | INT | SUCTION VALVE & UNLOADER SPARES | 5 |  | 90023534_0840 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 136 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 1130 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 100041806 | 0030 | 0010 | 100041806 | OPER-12982- Aux door seals Repl-4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10062317 | SEALING MAT,P GKT,BETWEEN P | 30 | M | 146 | 0 | 0 | 30 | M | 18.10 - SOH @ AA02 | Supply for Order 100041806, Item 1 cannot be changed 90025058 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016540 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90025058 | 05 | Preparation | 0000140298 | 1 | 0 | M | 102000000033125 |  | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | P08 - FL Mech | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025058_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-06-26 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2100337744 |  | 0 | 2 | 0 | 90025058 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062317 | SEALING MAT,P GKT,BETWEEN P | 2024-10-17 | W |  | 0030 | Remove & Replace Door Seals | INT | Remove & Replace Door Seals |  |  | 90025058_0010 |  |  | LN4 |  | A3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139708 | S002 |  | 30 | 5300016540 | 10 |  |  | 0 | 30 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140298 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2320 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10062317 | SEALING MAT,P GKT,BETWEEN P | 4 | M | 146 | 0 | 0 | 0 |  | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 337 cannot be changed 90028419 item 2610 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2640 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 337 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2610 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062317 | SEALING MAT,P GKT,BETWEEN P | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2610 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 337 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2640 |  |  | 0 | 4 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-03-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005190 | 0010 | 0060 | 500005190 | KGP 2025 Rotating Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 30 | No Issue identified | 10062537 | KEROSINE,REG GRADE,20L | 5 | DR | 2 | 0 | 2 | 0 |  | 07.03 - PR 2000283559 |  | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022062 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90032308 | 05 | Preparation | 0000299465 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-03-05 | ODST-0090032308_0060 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-12 | 0 |  | 2025-03-27 |  | 2025-04-01 |  |  | 0 | 2 | 0 | 90032308 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062537 | KEROSINE,REG GRADE,20L |  |  |  | 0010 | KGP 2025 Rotating Consumables | NCNF | KGP 2025 Rotating Consumables |  |  | 90032308_0060 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 6 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000292874 | S002 | 30 | 30 | 5300022062 | 60 |  |  | 0 | 5 | DR | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2025-03-05 | 299465 | 0 | 0 |  | 1020 | 3 |  |  | 5 | Low | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0040 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC |  | 10 | Issue detected, please check message in derivation or orchestration log | 10062555 | GAS:LPG,SNG9,9 KG,CYL | 4 | CYL | 6 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 4 cannot be changed 90032376 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | CYL |  | 0000001694 |  |  | 90032376 | 05 | Preparation | 0000289018 | 4 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0040 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405 |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062555 | GAS:LPG,SNG9,9 KG,CYL | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0040 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 40 |  |  | 0 | 4 | CYL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0050 | 0020 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 5 | DR | 2 | 0 | 29 | 4 | DR | 24.02 - SOH @ AA02 | Supply for Order 200089472, Item 2 cannot be changed 9027935 item 900010 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180130011 | 9027935 | 05 | Preparation | 0000127730 | 2 | 0 | DR | 102000000033774 |  | 107000000000120 |  |  |  | P07YRDBY34 | WorkPackLink | P07YRDBY34 | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000419185_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000058977 | 1020 | 2024-09-06 | 5 |  | 2025-02-27 | 4900250561_2025_0001/4900250561_2025_0003 | 2025-03-01 | 200089472 | 5000419185_2025_0002/5000419185_2025_0001 | 0 | 2 | 0 | 90028583 | 5 | 0 | 180130011/180130011/180130011 | 2 | 0 | 0 | X | L | 4900250561 | 2025 |  | 5000419185 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 9027935_0090_0020/9027935_0090_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 20 |  |  | 0 | 5 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0050 | 0020 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 5 | DR | 2 | 0 | 29 | 1 | DR | 24.02 - SOH @ AA02 | Supply for Order 200089472, Item 2 cannot be changed 9027935 item 900010 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180130011 | 9027935 | 05 | Preparation | 0000127730 | 2 | 0 | DR | 102000000033773 |  | 107000000000120 |  |  |  | P07YRDBY34 | WorkPackLink | P07YRDBY34 | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000419185_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000058977 | 1020 | 2024-09-06 | 5 |  | 2025-02-27 | 4900250561_2025_0001/4900250561_2025_0003 | 2025-03-01 | 200089472 | 5000419185_2025_0002/5000419185_2025_0001 | 0 | 2 | 0 | 90028583 | 5 | 0 | 180130011/180130011/180130011 | 2 | 0 | 0 | X | L | 4900250561 | 2025 |  | 5000419185 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 9027935_0090_0020/9027935_0090_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 20 |  |  | 0 | 5 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0020 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 5 | DR | 2 | 0 | 29 | 8 | EA | 03.02 - SOH @ AA01 | Supply for Order 200089473, Item 13 cannot be changed 9025790 item 900010 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180130009 | 9027934 | 05 | Preparation | 0000127731 | 13 | 0 | EA |  |  | 102000000033540 |  |  |  |  | WorkPackLink | SW3R01F02A | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000419175 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000058976 | 1020 | 2024-09-06 | 5 |  | 2025-02-27 | 4900250572_2025_0001/4900220572_2025_0001 | 2025-03-01 | 200089473 | 5000419175_2025_0001/5000375807_2025_0001 | 0 | 2 | 0 | 90028584 | 5 | 0 | 180118851/180118851/180130009/180130009 | 2 | 0 | 0 | X | L | 4900250572 | 2025 |  | 5000419175 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 9027934_0090_0020/9025790_0090_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 13 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 130 |  |  | 0 | 5 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2024-07-21 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0040 | 0050 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 3 | DR | 2 | 0 | 29 | 1 | DR | 25.09 - At KGP | Supply for Order 200089884, Item 5 cannot be changed 90011069 item 900010 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180068285 | 90011069 | 05 | Preparation | 0000128153 | 5 | 0 | DR |  |  | 102000000016831 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-08 | GRST-5000202879_2024 | 0 | 0 | 0 | 0 |  | 2024-07-22 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000027959 | 1020 | 2024-07-16 | 3 |  | 2024-09-10 | 4900128869_2024_0001/4900128869_2024_0003 | 2024-07-24 |  | 5000202940_2024_0001/5000202922_2024_0001/5000202879_2024_0001 | 0 | 2 | 0 | 90011069 | 3 | 0 | 180068285/180068285/180068285 | 2 | 0 | 0 | X | L | 4900128869 | 2024 |  | 5000202879 | 2024 | 0 |  | 2024-07-21 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2024-05-08 | W |  | 0040 | Water Wash Turbine | INT | Water Wash Turbine | 5 | Order Requires Replanning | 90011069_0090_0010/90011069_0090_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ | 1000003209 | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 50 |  |  | 0 | 3 | DR | 2001 | AA02 | 2024-07-21 |  | Order Requires Replanning | 2024-09-10 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2024-07-21 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0040 | 0050 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 3 | DR | 2 | 0 | 29 | 1 | DR | 25.09 - At KGP | Supply for Order 200089884, Item 5 cannot be changed 90011069 item 900010 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180068285 | 90011069 | 05 | Preparation | 0000128153 | 5 | 0 | DR |  |  | 102000000016833 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-08 | GRST-5000202879_2024 | 0 | 0 | 0 | 0 |  | 2024-07-22 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000027959 | 1020 | 2024-07-16 | 3 |  | 2024-09-10 | 4900128869_2024_0001/4900128869_2024_0003 | 2024-07-24 |  | 5000202940_2024_0001/5000202922_2024_0001/5000202879_2024_0001 | 0 | 2 | 0 | 90011069 | 3 | 0 | 180068285/180068285/180068285 | 2 | 0 | 0 | X | L | 4900128869 | 2024 |  | 5000202879 | 2024 | 0 |  | 2024-07-21 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2024-05-08 | W |  | 0040 | Water Wash Turbine | INT | Water Wash Turbine | 5 | Order Requires Replanning | 90011069_0090_0010/90011069_0090_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ | 1000003209 | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 50 |  |  | 0 | 3 | DR | 2001 | AA02 | 2024-07-21 |  | Order Requires Replanning | 2024-09-10 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDDG1 | Released | 2024-05-08 | 2025-03-01 | 2024-07-21 | 2025-03-01 | 2025-03-01 | ROTAT | 200089884 | 0040 | 0050 | 200089884 | 2Y 1KT2430 TURB FR5 WATER WASH | AA53.1KT2430 | TURB,GAS FOR 3RD STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(08.05.2024) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 3 | DR | 2 | 0 | 29 | 1 | DR | 25.09 - At KGP | Supply for Order 200089884, Item 5 cannot be changed 90011069 item 900010 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300009986 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180068285 | 90011069 | 05 | Preparation | 0000128153 | 5 | 0 | DR |  |  | 102000000016832 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-05-08 | GRST-5000202879_2024 | 0 | 0 | 0 | 0 |  | 2024-07-22 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000027959 | 1020 | 2024-07-16 | 3 |  | 2024-09-10 | 4900128869_2024_0001/4900128869_2024_0003 | 2024-07-24 |  | 5000202940_2024_0001/5000202922_2024_0001/5000202879_2024_0001 | 0 | 2 | 0 | 90011069 | 3 | 0 | 180068285/180068285/180068285 | 2 | 0 | 0 | X | L | 4900128869 | 2024 |  | 5000202879 | 2024 | 0 |  | 2024-07-21 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2024-05-08 | W |  | 0040 | Water Wash Turbine | INT | Water Wash Turbine | 5 | Order Requires Replanning | 90011069_0090_0010/90011069_0090_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDDG1 | MJ | 1000003209 | AU1072 | 1000127563 | S002 | 30 | 30 | 5300009986 | 50 |  |  | 0 | 3 | DR | 2001 | AA02 | 2024-07-21 |  | Order Requires Replanning | 2024-09-10 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128153 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0140 | 0010 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 3 | DR | 2 | 0 | 29 | 3 | DR | 17.10 - SOH @ AA01/AA02 | Supply for Order 200089887, Item 9 cannot be changed 9025793 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180118853 | 9025793 | 05 | Preparation | 0000128156 | 9 | 0 | DR | 102000000031642 | 102000000031638 | 107000000000120 |  |  |  | P07YRDBY34 | WorkPackLink | P07YRDBY34 | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000375813_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055277 | 1020 | 2024-07-12 | 3 |  | 2025-01-28 | 4900220552_2025_0001 | 2025-03-01 | Waterwash | 5000375813_2025_0001 | 0 | 2 | 0 | 90025037 | 3 | 0 | 180118853 | 2 | 0 | 0 | X | L | 4900220552 | 2025 |  | 5000375813 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2024-10-16 | W |  | 0140 | Water Wash Turbine | INT | Water Wash Turbine | 5 | Ready for Release | 9025793_0090 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 90 |  |  | 0 | 3 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0140 | 0010 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 3 | DR | 2 | 0 | 29 | 3 | DR | 08.12- SOH @ AA02/AA01 | Supply for Order 200089888, Item 2 cannot be changed 9025794 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180118850 | 9025794 | 05 | Preparation | 0000128157 | 2 | 0 | DR | 102000000031642 | 102000000031639 | 107000000000120 |  |  |  | P07YRDBY34 | WorkPackLink | P07YRDBY34 | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000375831_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055277 | 1020 | 2024-07-12 | 3 |  | 2025-01-28 | 4900220565_2025_0001 | 2025-03-01 | Waterwash | 5000375831_2025_0001 | 0 | 2 | 0 | 90025038 | 3 | 0 | 180118850 | 2 | 0 | 0 | X | L | 4900220565 | 2025 |  | 5000375831 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2024-10-16 | W |  | 0140 | Water Wash Turbine | INT | Water Wash Turbine |  | Ready for Release | 9025794_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 10 |  |  | 0 | 3 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0140 | 0010 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 3 | DR | 2 | 0 | 29 | 195 | EA | 08.12- SOH @ AA02/AA01 | Supply for Order 200089889, Item 2 cannot be changed 9025789 item 900010 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180118848 | 9025789 | 05 | Preparation | 0000128158 | 2 | 0 | EA |  |  | 102000000028342 |  |  |  |  | WorkPackLink | KSF-PACK-SD-LRG | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000375809 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055277 | 1020 | 2024-07-12 | 3 |  | 2025-01-28 | 4900220543_2025_0005/4900220543_2025_0003/4900220543_2025_0001 | 2025-03-01 | Waterwash | 5000375809_2025_0001/5000375809_2025_0002/5000375809_2025_0003 | 0 | 2 | 0 | 90025039 | 3 | 0 | 180118848/180118848/180118848/180118848 | 2 | 0 | 0 | X | L | 4900220543 | 2025 |  | 5000375809 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2024-10-16 | W |  | 0140 | Water Wash Turbine | INT | Water Wash Turbine |  | Ready for Release | 9025789_0090_0030/9025789_0090_0010/9025789_0090_0020 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 10 |  |  | 0 | 3 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0140 | 0010 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 3 | DR | 2 | 0 | 29 | 3 | DR | 08.12- SOH @ AA02/AA01 | Supply for Order 200089890, Item 24 cannot be changed 9025792 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180118847 | 9025792 | 05 | Preparation | 0000128159 | 24 | 0 | DR | 102000000031642 | 102000000031637 | 107000000000120 |  |  |  | P07YRDBY34 | WorkPackLink | P07YRDBY34 | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000375840_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055277 | 1020 | 2024-07-12 | 3 |  | 2025-01-28 | 4900220571_2025_0001 | 2025-03-01 | Waterwash | 5000375840_2025_0001 | 0 | 2 | 0 | 90025059 | 3 | 0 | 180118847 | 2 | 0 | 0 | X | L | 4900220571 | 2025 |  | 5000375840 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2024-10-17 | W |  | 0140 | Water Wash Turbine | INT | Water Wash Turbine |  | Ready for Release | 9025792_0030 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 24 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 100 |  |  | 0 | 3 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0140 | 0010 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 3 | DR | 2 | 0 | 29 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 200089891, Item 10 cannot be changed 9025791 item 900010 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180118849 | 9025791 | 05 | Preparation | 0000128160 | 10 | 0 | [8 empty] | WorkPackLink |  | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-17 | GRST-5000375793 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055277 | 1020 | 2024-07-12 | 3 |  | 2025-01-28 | 4900220551_2025_0001/4900220551_2025_0003 | 2025-03-01 | Waterwash | 5000375793_2025_0001/5000375793_2025_0002 | 0 | 2 | 0 | 90025062 | 3 | 0 | 180118849/180118849/180118849 | 2 | 0 | 0 | X | L | 4900220551 | 2025 |  | 5000375793 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062818 | DETERGENT;TURCO BONDERITE C-MC,5884,20L | 2024-10-17 | W |  | 0140 | Water Wash Turbine | INT | Water Wash Turbine |  | Ready for Release | 9025791_0090_0020/9025791_0090_0010 |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 30 |  |  | 0 | 3 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0050 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Shipped qty below requirement qty | 10062910 | SEALANT,SILASTIC,RTV732,CLEAR,CART | 8 | CQ | 163 | 86 | 620 | 4 | CQ | 02.12 - SOH @ AA02 | Supply for Order 200089373, Item 5 cannot be changed 90023594 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  | 180091768 | 9019016 | 07 | Execution | 0000127667 | 5 | 0 | CQ |  |  | 102000000023518 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-KGP-RUNNER-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-05 | GRST-5000275094_2024 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000040386 | 1020 | 2025-12-15 | 4 |  | 2024-11-11 | 4900169565_2024_0011 | 2024-11-10 | Troy Mac | 5000275094_2024_0001 | 0 | 2 | 0 | 90023594 | 4 | 0 | 180091768/180091768 | 1 | 0 | 0 | X | L | 4900169565 | 2024 |  | 5000275094 | 2024 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062910 | SEALANT,SILASTIC,RTV732,CLEAR,CART | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 90023594_0050/9019016_0090_0010 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDFR2 | MJ | 1000004072 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 50 |  |  | 0 | 8 | CQ | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0190 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Shipped qty below requirement qty | 10062910 | SEALANT,SILASTIC,RTV732,CLEAR,CART | 100 | CQ | 163 | 86 | 620 | 16 | CQ | 20.02 - SOH @ AA01 | Supply for Order 500005166, Item 39 cannot be changed 90031501 item 210 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  | 180132204 | 9028446 | 05 | Preparation | 0000294187 | 39 | 0 | CQ |  |  | 102000000033939 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 84 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427504_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060207 | 1020 |  | 16 |  | 2025-03-05 | 4900257428_2025_0011 | 2025-04-01 | TA LAG_VORN | 5000427504_2025_0006 | 0 | 2 | 0 | 90031501 | 16 | 0 | 180132204/180132204 | 1 | 0 | 0 | X | L | 4900257428 | 2025 |  | 5000427504 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062910 | SEALANT,SILASTIC,RTV732,CLEAR,CART | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0210/9028446_0090_0020 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 39 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 350 |  |  | 0 | 100 | CQ | 2001 | AA02 | 2025-03-27 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0110 | 0060 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10062939 | COMPOUND,JOINTING;HYLOMAR,100GM TUBE | 10 | TB | 36 | 0 | 0 | 0 |  | 10.01 - SOH @ AA02 | Supply for Order 100079012, Item 10 cannot be changed 90028429 item 60 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018551 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  |  | 90028429 | 05 | Preparation | 0000243763 | 10 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028429_0090_0010/90028429_0090_0020 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079012 |  | 0 | 2 | 0 | 90028429 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062939 | COMPOUND,JOINTING;HYLOMAR,100GM TUBE | 2024-11-28 | W |  | 0110 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028429_0090_0010/90028429_0090_0020 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240421 | S002 | 30 | 30 | 5300018551 | 60 |  |  | 0 | 10 | TB | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243763 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0130 | 0060 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10062939 | COMPOUND,JOINTING;HYLOMAR,100GM TUBE | 10 | TB | 36 | 0 | 0 | 10 | TB | 10.01 - SOH @ AA02 | Supply for Order 100079106, Item 10 cannot be changed 90028430 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018552 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  |  | 90028430 | 05 | Preparation | 0000243730 | 10 | 0 | TB | 102000000033580 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028430_0050 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079106 |  | 0 | 2 | 0 | 90028430 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062939 | COMPOUND,JOINTING;HYLOMAR,100GM TUBE | 2024-11-28 | W |  | 0130 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028430_0050 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240357 | S002 | 30 | 30 | 5300018552 | 50 |  |  | 0 | 10 | TB | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243730 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 2890 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10062941 | SEALANT;GKT/FLG,LOCTITE 573,250ML | 5 | TB | 29 | 0 | 0 | 5 | TB | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 418 cannot be changed 90028419 item 2900 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2930 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 418 | 0 | TB | 102000000030494 | 102000000030134 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2900 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062941 | SEALANT;GKT/FLG,LOCTITE 573,250ML | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_2900 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 418 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2930 |  |  | 0 | 5 | TB | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091128 | 0060 | 0060 | 200091128 | 6Y Motor Bearing Insp - 1KM2301 | AA53.1KM2301 | MOTOR,HV,REGENERATION GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10062957 | COMPOUND,LOCTITE GKT ELIMINATOR,SEALING | 3 | TB | 8 | 0 | 5 | 3 | TB | 03.10 - SOH @ AA02 | Supply for Order 200091128, Item 2 cannot be changed 90024963 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004360 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  |  | 90024963 | 05 | Preparation | 0000129422 | 2 | 0 | TB | 102000000029984 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024963_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 2200576286 |  | 0 | 2 | 0 | 90024963 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062957 | COMPOUND,LOCTITE GKT ELIMINATOR,SEALING | 2024-01-02 | W |  | 0060 | Inspect Motor NDE Bearing | ENON | Inspect Motor NDE Bearing | 5 |  | 90024963_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128791 | S002 | 30 | 30 | 5300004360 | 20 |  |  | 0 | 3 | TB | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147110 | 0010 | 0010 | 200147110 | 1Y CO2 F/Test (79) 1KT2420 | AA53.160GA1212A | TXDCR,1KT2420 CO2 CYL WEIGHT LOW |  | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.11.2024) | 10062981 | AIR,INSTR GRADE,G SIZE CYL,13700 KPA | 1 | CYL | 5 | 0 | 3 | 0 |  | 20.11 - SOH @ AA02 | Supply for Order 200147110, Item 1 cannot be changed 90025100 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017680 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CYL |  |  |  |  | 90025100 | 05 | Preparation | 0000235381 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-11 | ODST-0090025100_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025100 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062981 | AIR,INSTR GRADE,G SIZE CYL,13700 KPA | 2024-11-10 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 3 |  | 90025100_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232424 | S002 | 30 | 30 | 5300017680 | 10 |  |  | 0 | 1 | CYL | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235381 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147173 | 0010 | 0010 | 200147173 | 1Y CO2 Function Test (105) 1KT2430 | AA53.160GA1312A | TXDCR,1KT2430 CO2 CYL WEIGHT LOW |  | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(10.11.2024) | 10062981 | AIR,INSTR GRADE,G SIZE CYL,13700 KPA | 2 | CYL | 5 | 0 | 3 | 0 |  | 23.01 - SOH @ AA02 | Supply for Order 200147173, Item 2 cannot be changed 90025101 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017681 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CYL |  |  |  |  | 90025101 | 05 | Preparation | 0000235474 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-11 | ODST-0090025101_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-08-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1KT2430 |  | 0 | 2 | 0 | 90025101 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062981 | AIR,INSTR GRADE,G SIZE CYL,13700 KPA | 2024-11-10 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 3 |  | 90025101_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000232528 | S002 | 30 | 30 | 5300017681 | 10 |  |  | 0 | 2 | CYL | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-01 | 235474 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0040 | 0030 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(02.03.2025) | 10063308 | ETHYLENE GLYCOL,20L DRM | 1 | DR | 4 | 0 | 13 | 0 |  | 02.03 - SOH @ AA02 | Supply for Order 500005166, Item 56 cannot be changed 90032306 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 510 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90032306 | 05 | Preparation | 0000294187 | 56 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090032306_0020 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | Inlec Contai |  | 0 | 2 | 0 | 90032306 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10063308 | ETHYLENE GLYCOL,20L DRM | 2025-03-02 | W |  | 0040 | 2025 - Consumables Inlec | NCNF | 2025 - Consumables Inlec |  |  | 90032306_0020 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 56 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 510 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200144742 | 0020 | 0010 | 200144742 | 2Y SVC ACCUMULATOR N2 PRESSURE | AA53.4K1410V6 | ACC,FOR IGV SYSTEM,4K1410 |  | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10063423 | GAS COMPRESSED:N2,D2,CYL,15000kPa,99.5% | 1 | CYL | 2 | 0 | 10 | 0 |  | 13.01 - SOH @ AA02 | Supply for Order 200144742, Item 1 cannot be changed 90025061 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016542 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CYL |  |  |  |  | 90025061 | 05 | Preparation | 0000231832 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-LN4-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025061_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200144742 |  | 0 | 2 | 0 | 90025061 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10063423 | GAS COMPRESSED:N2,D2,CYL,15000kPa,99.5% | 2024-10-17 | W |  | 0020 | Top Up As Required | INT | Top Up As Required |  | Ready for Release | 90025061_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000228988 | S002 | 30 | 30 | 5300016542 | 10 |  |  | 0 | 1 | CYL | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231832 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-10-21 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200144743 | 0020 | 0010 | 200144743 | 2Y SVC ACCUMULATOR N2 PRESS | AA53.4K1450V3 | ACC,VESSEL 4K1450 |  | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(21.10.2024) | 10063423 | GAS COMPRESSED:N2,D2,CYL,15000kPa,99.5% | 1 | CYL | 2 | 0 | 10 | 0 |  | 13.01 - SOH @ AA02 | Supply for Order 200144743, Item 1 cannot be changed 90025070 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016674 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CYL |  |  |  |  | 90025070 | 05 | Preparation | 0000231833 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-LN4-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-21 | ODST-0090025070_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-07-22 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200144743 |  | 0 | 2 | 0 | 90025070 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10063423 | GAS COMPRESSED:N2,D2,CYL,15000kPa,99.5% | 2024-10-21 | W |  | 0020 | Top Up As Required | INT | Top Up As Required |  | Ready for Release | 90025070_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000228989 | S002 | 30 | 30 | 5300016674 | 10 |  |  | 0 | 1 | CYL | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231833 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0040 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10063472 | SOLU:SOAP,GAS LEAK DETECT,5L BOT | 2 | BT | 8 | 0 | 8 | 40 | EA | 21.02 - SOH @ AA02 | Supply for Order 500004676, Item 4 cannot be changed 9028889 item 900010 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | BT |  |  |  | 180134056 | 9028889 | 07 | Execution | 0000278102 | 4 | 0 | EA | 101000000149760 |  | 101000000149860 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2025-03-02 | Y | 1001 | 2025-02-12 | GRST-5000434885 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060557 | 1020 | 2025-12-31 | 2 |  | 2025-03-10 | 4900263464_2025_0005/4900263464_2025_0007 | 2025-04-01 | TA OPS/BAILS | 5000434885_2025_0004/5000434885_2025_0003 | 0 | 2 | 0 | 90031855 | 2 | 0 | 180134056/180134056/180134056 | 2 | 0 | 0 | X | L | 4900263464 | 2025 |  | 5000434885 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10063472 | SOLU:SOAP,GAS LEAK DETECT,5L BOT | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 9028889_0090_0020/9028889_0090_0010 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 4 |  | 0 |  | 25SDENA1 | MJ | 20005413 | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 40 |  |  | 0 | 2 | BT | 2001 | AA02 | 2025-03-27 |  |  | 2025-02-28 |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091128 | 0060 | 0082 | 200091128 | 6Y Motor Bearing Insp - 1KM2301 | AA53.1KM2301 | MOTOR,HV,REGENERATION GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10063552 | BOTTLE,SAMPLE,125ML,PL,C/W SCR TOP | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091128, Item 7 cannot be changed 90024963 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004360 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024963 | 05 | Preparation | 0000129422 | 7 | 0 | EA | 102000000027655 |  | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024963_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-01 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200091128 |  | 0 | 2 | 0 | 90024963 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10063552 | BOTTLE,SAMPLE,125ML,PL,C/W SCR TOP | 2024-01-02 | W |  | 0060 | Inspect Motor NDE Bearing | ENON | Inspect Motor NDE Bearing | 5 |  | 90024963_0060 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128791 | S002 | 30 | 30 | 5300004360 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0080 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10064375 | BAG:SAMPLE,OPEN TOP,900X600MM,150UM,GRN | 2 | EA | 1287 | 0 | 720 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500004676, Item 8 cannot be changed 90031855 item 70 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 8 | 0 | [8 empty] | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-12 | ODST-0090031855_0070 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10064375 | BAG:SAMPLE,OPEN TOP,900X600MM,150UM,GRN | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0070 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 8 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDENA1 | Released | 2025-03-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005190 | 0010 | 0030 | 500005190 | KGP 2025 Rotating Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 30 | No Issue identified | 10064387 | WIPER:DISP,BLUE,70MX49CM | 50 | ROL | 97 | 0 | 3 | 0 |  | 07.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022062 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90032308 | 05 | Preparation | 0000299465 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-03-05 | ODST-0090032308_0030 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-12 | 0 |  | 2025-03-27 |  | 2025-04-01 |  |  | 0 | 2 | 0 | 90032308 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10064387 | WIPER:DISP,BLUE,70MX49CM |  |  |  | 0010 | KGP 2025 Rotating Consumables | NCNF | KGP 2025 Rotating Consumables |  |  | 90032308_0030 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000292874 | S002 | 30 | 30 | 5300022062 | 30 |  |  | 0 | 50 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2025-03-05 | 299465 | 0 | 0 |  | 1020 | 3 |  |  | 5 | Low | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0030 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Shipped qty below requirement qty | 10065556 | TUBE,GAS,DETECT,DRAEGER,WATER VAPOUR | 20 | BOX | 0 | 0 | 13 | 12 | BOX | 13.02 - ETA 18.03.25 PO 4500046017 ex ARA Marine | Supply for Order 500004676, Item 3 cannot be changed 90031855 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  | 180134056 | 9028889 | 07 | Execution | 0000278102 | 3 | 0 | BOX |  |  | 102000000034471 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 7 |  |  | Y | 1001 | 2025-02-12 | GRST-5000434885_2025 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060557 | 1020 | 2025-12-31 | 13 |  | 2025-03-10 | 4900263464_2025_0009/4900263464_2025_0011 | 2025-04-01 | TA OPS/BAILS | 5000434885_2025_0005/5000434885_2025_0006 | 0 | 2 | 0 | 90031855 | 13 | 0 | 180134056/180134056/180134056 | 1 | 0 | 0 | X | L | 4900263464 | 2025 |  | 5000434885 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10065556 | TUBE,GAS,DETECT,DRAEGER,WATER VAPOUR | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0030/9028889_0090_0040/9028889_0090_0030 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 30 |  |  | 0 | 20 | BOX | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0030 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Shipped qty below requirement qty | 10065556 | TUBE,GAS,DETECT,DRAEGER,WATER VAPOUR | 20 | BOX | 0 | 0 | 13 | 1 | BOX | 13.02 - ETA 18.03.25 PO 4500046017 ex ARA Marine | Supply for Order 500004676, Item 3 cannot be changed 90031855 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  | 180134056 | 9028889 | 07 | Execution | 0000278102 | 3 | 0 | BOX |  |  | 102000000034473 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 7 |  |  | Y | 1001 | 2025-02-12 | GRST-5000434885_2025 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  | 100000060557 | 1020 | 2025-12-31 | 13 |  | 2025-03-10 | 4900263464_2025_0009/4900263464_2025_0011 | 2025-04-01 | TA OPS/BAILS | 5000434885_2025_0005/5000434885_2025_0006 | 0 | 2 | 0 | 90031855 | 13 | 0 | 180134056/180134056/180134056 | 1 | 0 | 0 | X | L | 4900263464 | 2025 |  | 5000434885 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10065556 | TUBE,GAS,DETECT,DRAEGER,WATER VAPOUR | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0030/9028889_0090_0040/9028889_0090_0030 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 3 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 30 |  |  | 0 | 20 | BOX | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SDENA1 | Released | 2025-03-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005190 | 0010 | 0070 | 500005190 | KGP 2025 Rotating Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 30 | No Issue identified | 10065676 | PAD;SORBENT,43X48X0.5CM,HP156 | 10 | PAC | 61 | 0 | 0 | 0 |  | 07.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022062 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAC |  |  |  |  | 90032308 | 05 | Preparation | 0000299465 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-03-05 | ODST-0090032308_0070 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-12 | 0 |  | 2025-03-27 |  | 2025-04-01 |  |  | 0 | 2 | 0 | 90032308 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10065676 | PAD;SORBENT,43X48X0.5CM,HP156 |  |  |  | 0010 | KGP 2025 Rotating Consumables | NCNF | KGP 2025 Rotating Consumables |  |  | 90032308_0070 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 7 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000292874 | S002 | 30 | 30 | 5300022062 | 70 |  |  | 0 | 10 | PAC | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2025-03-05 | 299465 | 0 | 0 |  | 1020 | 3 |  |  | 5 | Low | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10065700 | GASKET,SEALING;NP HFZ286050473 | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 369 cannot be changed 90028419 item 2770 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2800 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 369 | 0 | EA | 102000000030499 | 102000000030291 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2770 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10065700 | GASKET,SEALING;NP HFZ286050473 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_2770 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 369 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2800 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2430 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10065701 | GASKET;NP MAN200348 | 4 | M | 12 | 0 | 0 | 4 | M | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 370 cannot be changed 90028419 item 2780 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2810 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 370 | 0 | M | 102000000030499 | 102000000030371 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10065701 | GASKET;NP MAN200348 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_2780 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 370 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2810 |  |  | 0 | 4 | M | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2440 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10065702 | GASKET;NP KFZ314360474 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 371 cannot be changed 90028419 item 2790 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 371 | 0 | EA | 102000000034071 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2790 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10065702 | GASKET;NP KFZ314360474 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_2790 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 371 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2820 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0020 | 0330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10065702 | GASKET;NP KFZ314360474 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 669 cannot be changed 90028419 item 4470 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4500 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 669 | 0 | EA | 102000000034129 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4470 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10065702 | GASKET;NP KFZ314360474 | 2024-07-21 | W |  | 0020 | BELLMOUTH NO 1 BEARING & HP THRUST | INT | BELLMOUTH NO 1 BEARING & HP THRUST | 5 |  | 90028419_4470 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 669 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4500 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0310 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Shipped qty below requirement qty | 10149809 | SEALANT,736 RED,HEAT RES,CART,300ML | 40 | CQ | 4 | 0 | 4 | 3 | CQ | DEL; 80032706 | Supply for Order 500005166, Item 51 cannot be changed 90031501 item 320 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 470 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  | 180132204 | 9028446 | 05 | Preparation | 0000294187 | 51 | 0 | CQ |  |  | 102000000033923 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 37 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427504_2025 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060207 | 1020 |  | 3 |  | 2025-03-05 | 4900257428_2025_0009 | 2025-04-01 | TA LAG_VORN | 5000427504_2025_0005 | 0 | 2 | 0 | 90031501 | 3 | 0 | 180132204/180132204 | 1 | 0 | 0 | X | L | 4900257428 | 2025 |  | 5000427504 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10149809 | SEALANT,736 RED,HEAT RES,CART,300ML | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0320/9028446_0090_0010 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 51 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 470 |  |  | 0 | 40 | CQ | 2001 | AA02 | 2025-03-27 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0180 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10202407 | ELBOW,90DEG,BW,LR,50MM,LTCS,A420WP,SCH40 | 2 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 17 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202407 | ELBOW,90DEG,BW,LR,50MM,LTCS,A420WP,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0340 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10202407 | ELBOW,90DEG,BW,LR,50MM,LTCS,A420WP,SCH40 | 4 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 32 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202407 | ELBOW,90DEG,BW,LR,50MM,LTCS,A420WP,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0060 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10202407 | ELBOW,90DEG,BW,LR,50MM,LTCS,A420WP,SCH40 | 8 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 5 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202407 | ELBOW,90DEG,BW,LR,50MM,LTCS,A420WP,SCH40 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0020 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10202422 | PIPE;25MM,6M,SSTP316L,SMLS,SCH40S | 6 | M | 0 | 0 | 0 | 0 |  | 13.01 - ETA 10.01.25 PO 4500040603 MRC CPT | Supply for Order 100041844, Item 4 cannot be changed 90028427 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000601 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028427 | 05 | Preparation | 0000140308 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028427_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100041844 |  | 0 | 2 | 0 | 90028427 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202422 | PIPE;25MM,6M,SSTP316L,SMLS,SCH40S | 2024-12-16 | W |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change | 90028427_0020 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139679 | S002 | 30 | 30 | 5300000601 | 40 |  |  | 0 | 6 | M | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140308 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2025-01-14 | 2025-03-04 | 2025-02-24 | 2025-02-28 | 2025-04-07 | MECH | 200073951 | 0190 | 0190 | 200073951 | 6Y P01 INT INSP PRESS VESSEL 5C2001 | AA53.5C2001 | VE,COLUMN STABILISER MODIFIED | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10203052 | GASKET;SWCI,400MM,CL300,316L/GR/316 | 5 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200073951, Item 19 cannot be changed 90028585 item 190 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020031 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028585 | 05 | Preparation | 0000108267 | 19 | 0 | [8 empty] | WorkPackLink |  | P07 - KGP - W1 25 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028585_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-04 |  |  | 2025-03-04 |  |  |  |  | 2025-11-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5C2001 |  | 0 | 2 | 0 | 90028585 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10203052 | GASKET;SWCI,400MM,CL300,316L/GR/316 | 2025-01-14 | W |  | 0190 | Inspect & Mark Up Areas to be Buffed A3 | INT | Inspect & Mark Up Areas to be Buffed A3 |  |  | 90028585_0190 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 19 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000107670 | S002 |  | 30 | 5300020031 | 190 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108267 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-04-07 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0001 | 0270 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.11.2024) | 10204140 | BAG,PL;1200X900MM,200UM | 100 | EA | 690 | 200 | 1559 | 100 | EA | 25.11 - SOH @ AA02 | Supply for Order 100087648, Item 28 cannot be changed 9025974 item 260 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300018296 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180120041 | 9025974 | 05 | Preparation | 0000278190 | 28 | 0 | EA | 102000000030229 |  | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-22 | GRST-5000380286_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055365 | 1020 | 2025-12-02 | 100 |  | 2025-01-30 | 4900222786_2025_0001 | 2025-03-01 | 5E2001 | 5000380286_2025_0001 | 0 | 2 | 0 | 90028417 | 100 | 0 | 180120041 | 2 | 0 | 0 | X | L | 4900222786 | 2025 |  | 5000380286 | 2025 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204140 | BAG,PL;1200X900MM,200UM | 2024-11-23 | W |  | 0001 | Materials | INT | Materials |  |  | 9025974_0260 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 28 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000272706 | S002 | 30 | 30 | 5300018296 | 270 |  |  | 0 | 100 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 278190 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0280 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10204140 | BAG,PL;1200X900MM,200UM | 300 | EA | 690 | 200 | 1559 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 28 cannot be changed 90032376 item 260 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 28 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 300 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0260 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204140 | BAG,PL;1200X900MM,200UM | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0260 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 28 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 280 |  |  | 0 | 300 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0010 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10204140 | BAG,PL;1200X900MM,200UM | 50 | EA | 690 | 200 | 1559 | 50 | EA | Workpacked at KGP | Supply for Order 200089373, Item 1 cannot be changed 180091768 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180091768 | 9019016 | 07 | Execution | 0000127667 | 1 | 0 | EA |  |  | 102000000023514 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-KGP-RUNNER-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000275123_2024 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000040386 | 1020 | 2025-12-15 | 50 |  | 2024-11-11 | 4900169565_2024_0001 | 2024-11-10 | Troy Mac | 5000275123_2024_0001 | 0 | 2 | 0 | 90023594 | 50 | 0 | 180091768 | 2 | 0 | 0 | X | L | 4900169565 | 2024 |  | 5000275123 | 2024 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204140 | BAG,PL;1200X900MM,200UM | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9019016_0010 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDFR2 | MJ | 1000004072 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 10 |  |  | 0 | 50 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0020 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10204140 | BAG,PL;1200X900MM,200UM | 500 | EA | 690 | 200 | 1559 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 3 cannot be changed 90031023 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031023 | 05 | Preparation | 0000294187 | 3 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 500 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031023_0020 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 | [5 empty] | 0 |  | 2025-03-06 |  | 2025-03-11 | TA LAG_VORN |  | 0 | 2 | 0 | 90031023 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204140 | BAG,PL;1200X900MM,200UM | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0020 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 3 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 30 |  |  | 0 | 500 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-03-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005190 | 0010 | 0040 | 500005190 | KGP 2025 Rotating Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 30 | No Issue identified | 10204140 | BAG,PL;1200X900MM,200UM | 10 | EA | 690 | 200 | 1559 | 0 |  | 07.03 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022062 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032308 | 05 | Preparation | 0000299465 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2025-03-05 | ODST-0090032308_0040 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  |  |  | 2025-12-12 | 0 |  | 2025-03-27 |  | 2025-04-01 |  |  | 0 | 2 | 0 | 90032308 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204140 | BAG,PL;1200X900MM,200UM |  |  |  | 0010 | KGP 2025 Rotating Consumables | NCNF | KGP 2025 Rotating Consumables |  |  | 90032308_0040 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 4 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000292874 | S002 | 30 | 30 | 5300022062 | 40 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52923 | 2025-03-05 | 299465 | 0 | 0 |  | 1020 | 3 |  |  | 5 | Low | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1880 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204183 | SEAL KIT;NP IRA0109911 | 2 | KIT | 11 | 0 | 0 | 2 | KIT | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 262 cannot be changed 90028419 item 2010 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2040 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 262 | 0 | KIT | 102000000030504 | 102000000030469 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204183 | SEAL KIT;NP IRA0109911 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2010 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 262 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2040 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3090 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204189 | VALVE,FOOT;1500KPA MAX,NP RVO10165 | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 445 cannot be changed 90028419 item 3100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 445 | 0 | EA | 102000000030496 | 102000000030125 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ON CONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204189 | VALVE,FOOT;1500KPA MAX,NP RVO10165 | 2024-07-21 | W |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  | 90028419_3100 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 445 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3130 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204190 | JOINT,EXPN;NP RGO27923 | 1 | EA | 1 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 540 cannot be changed 90028419 item 3920 already exists | Material picked; currently at SW3R02B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3950 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 540 | 0 | EA |  |  | 101000000010415 | 01-Road |  | 5-Completed |  | WorkPackLink | SW3R02B01B |  | 0 |  | 0 | 0 |  | 0 | 1 | 2025-01-21 | 2025-01-19 | Y | 1001 | 2024-07-22 | ODST-0090028419_3920 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204190 | JOINT,EXPN;NP RGO27923 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_3920 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 540 |  | 0 |  | 25SD2420 | MJ | 20004701 | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3950 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-01-17 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0060 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10204192 | SEALANT,SILICONE,ADVANTAGE 780,300G TUBE | 100 | TB | 162 | 2 | 78 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 6 cannot be changed 90032376 item 60 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 6 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0060 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204192 | SEALANT,SILICONE,ADVANTAGE 780,300G TUBE | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0060 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 6 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 60 |  |  | 0 | 100 | TB | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0050 | 0040 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10204236 | GASKET,RING;C4430,KLINGER 0W0010204236 | 1 | EA | 4 | 0 | 0 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 200089472, Item 4 cannot be changed 90028583 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 4 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204236 | GASKET,RING;C4430,KLINGER 0W0010204236 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028583_0040 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 |  | 30 | 5300020057 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0040 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10204236 | GASKET,RING;C4430,KLINGER 0W0010204236 | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 15 cannot be changed 90028584 item 150 already exists | Material picked; currently at WH2-PACK-SD-2B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 15 | 0 | EA | 102000000031257 |  | 102000000031300 |  |  |  |  | WorkPackLink | WH2-PACK-SD-2B | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204236 | GASKET,RING;C4430,KLINGER 0W0010204236 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028584_0150 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 |  | 30 | 5300020058 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2410 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204236 | GASKET,RING;C4430,KLINGER 0W0010204236 | 1 | EA | 4 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 628 cannot be changed 90028419 item 4190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 628 | 0 | EA | 102000000030482 | 102000000030358 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204236 | GASKET,RING;C4430,KLINGER 0W0010204236 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_4190 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 628 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4220 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0050 | 0050 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10204237 | GASKET,RING;C4430,KLINGER 0W0010204237 | 1 | EA | 3 | 0 | 4 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 200089472, Item 5 cannot be changed 90028583 item 50 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 5 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204237 | GASKET,RING;C4430,KLINGER 0W0010204237 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028583_0050 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 |  | 30 | 5300020057 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0050 | 0050 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10204237 | GASKET,RING;C4430,KLINGER 0W0010204237 | 1 | EA | 3 | 0 | 4 | 1 | EA | 19.02 - SOH @AA02 | Supply for Order 200089473, Item 16 cannot be changed 90028584 item 160 already exists | Material picked; currently at WH2-PACK-SD-1A/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 16 | 0 | EA | 101000000135510 |  | 102000000031644 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1A | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204237 | GASKET,RING;C4430,KLINGER 0W0010204237 | 2025-01-14 | W |  | 0050 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 5 | Ready for Release | 90028584_0160 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 |  | 30 | 5300020058 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2420 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204237 | GASKET,RING;C4430,KLINGER 0W0010204237 | 1 | EA | 3 | 0 | 4 | 1 | EA | 24.02 - SOH @ AA02 | Supply for Order 200091513, Item 629 cannot be changed 90028419 item 4200 already exists | Material picked; currently at SW3R01F02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 629 | 0 | EA |  |  | 102000000034498 |  |  |  |  | WorkPackLink | SW3R01F02A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204237 | GASKET,RING;C4430,KLINGER 0W0010204237 | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_4200 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 629 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4230 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0260 | 3080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204264 | RING,SEALING;NP 2001102601CUSTOMRUBBER | 1 | EA | 2 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 444 cannot be changed 90028419 item 3090 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 444 | 0 | EA | 102000000030496 | 102000000030467 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204264 | RING,SEALING;NP 2001102601CUSTOMRUBBER | 2024-07-21 | W |  | 0260 | TORQUE CONVERTER | INT | TORQUE CONVERTER | 5 |  | 90028419_3090 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 444 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0750 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204266 | GASKET;NP E194621RICHARDKLINGER | 2 | EA | 3 | 0 | 0 | 1 | EA | 20.02 - SOH @ AA02 | Supply for Order 200091513, Item 476 cannot be changed 90028419 item 3350 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 476 | 0 | EA | 102000000030481 | 102000000030602 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3350 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204266 | GASKET;NP E194621RICHARDKLINGER | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_3350 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 476 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3380 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2060 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204312 | BUSH,1ST STEP,RATIO VV;NP SMR25967 | 1 | EA | 5 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 526 cannot be changed 90028419 item 3810 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 526 | 0 | EA | 102000000030501 | 102000000030558 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3810 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204312 | BUSH,1ST STEP,RATIO VV;NP SMR25967 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3810 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 526 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3840 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2070 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204313 | BUSH,2ND STEP,RATIO VV;NP SMR25968 | 1 | EA | 4 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 527 cannot be changed 90028419 item 3820 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3850 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 527 | 0 | EA | 102000000030501 | 102000000030643 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3820 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204313 | BUSH,2ND STEP,RATIO VV;NP SMR25968 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3820 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 527 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3850 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2080 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204314 | BUSH,3RD STEP,RATIO VV;NP SMR25969 | 1 | EA | 4 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 528 cannot be changed 90028419 item 3830 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3860 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 528 | 0 | EA | 102000000030501 | 102000000030644 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3830 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204314 | BUSH,3RD STEP,RATIO VV;NP SMR25969 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3830 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 528 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3860 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091128 | 0060 | 0070 | 200091128 | 6Y Motor Bearing Insp - 1KM2301 | AA53.1KM2301 | MOTOR,HV,REGENERATION GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10204333 | PRIMER,LOCTITE 7649,52ML BOTTLE | 1 | BT | 29 | 1 | 7 | 1 | BT | 03.10 - SOH @ AA02 | Supply for Order 200091128, Item 3 cannot be changed 9027120 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300004360 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | BT |  |  |  |  | 9027120 | 05 | Preparation | 0000129422 | 3 | 0 | BT | 102000000029963 | 102000000029787 | 102000000032141 |  |  |  |  | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GIST-4900234122_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2023-04-01 | 1 |  | 2025-02-11 | 4900234122_2025_0001 | 2025-03-01 | 2200576286 |  | 0 | 2 | 0 | 90024963 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234122 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204333 | PRIMER,LOCTITE 7649,52ML BOTTLE | 2024-01-02 | W |  | 0060 | Inspect Motor NDE Bearing | ENON | Inspect Motor NDE Bearing | 5 |  | 9027120_0030 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128791 | S002 | 30 | 30 | 5300004360 | 30 |  |  | 0 | 1 | BT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129422 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-12-05 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100046238 | 0020 | 0010 | 100046238 | EEHA - Replace Glands - 414PDT608A | AA53.414PDT608A | TX,DIFF PRESS S/GAS REF 4K1450LP | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(10.02.2025) | 10204540 | ADAPTOR,CABLE GLAND;EX,CCG AN012M020E | 6 | EA | 25 | 0 | 16 | 0 |  | 26.02 - SOH @ AA02 | Supply for Order 100046238, Item 1 cannot be changed 90030598 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021048 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030598 | 05 | Preparation | 0000144782 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-02-10 | ODST-0090030598_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2020-12-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414PDT608A |  | 0 | 2 | 0 | 90030598 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204540 | ADAPTOR,CABLE GLAND;EX,CCG AN012M020E | 2025-02-10 | W |  | 0020 | Replace Glands | INT | Replace Glands |  | Engineering Query | 90030598_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000144153 | S002 |  | 30 | 5300021048 | 10 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  | Engineering Query |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144782 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-08-09 | 2025-03-01 | 2024-09-30 | 2025-03-01 | 2025-03-01 | INLEC | 100038870 | 1000 | 0020 | 100038870 | MOC-123206 Replace JB 5PM2001BJ | AA53.5PM2001BJ | JB,MOTOR,RCU STABLI HEATER PUMP,5P2001B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.08.2024) | 10204729 | GLAND,CABLE;EX,CCG 054703 | 2 | EA | 41 | 0 | 5 | 2 | EA | 29.01 - At KGP | Supply for Order 100038870, Item 2 cannot be changed 180073873 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300013766 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180073873 | 9014200 | 06 | Scheduling | 0000137402 | 2 | 0 | EA | 102000000016236 | 102000000015173 | 102000000016159 | 01-Road |  | 4-Arrived | LP-NWS-14 | WorkPackLink | P08WHSFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 | 2024-09-26 |  | Y | 1001 | 2024-08-09 | GRST-5000295875_2024 | 0 | 0 | 0 | 0 |  | 2024-10-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000031264 | 1020 | 2025-07-31 | 2 |  | 2024-09-25 | 4900139136_2024_0003 | 2024-10-03 | 5PM2001BJ | 5000295875_2024_0002 | 0 | 2 | 0 | 90017620 | 2 | 0 | 180073887/180073873 | 2 | 0 | 0 | X | L | 4900139136 | 2024 |  | 5000295875 | 2024 | 0 |  | 2024-09-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204729 | GLAND,CABLE;EX,CCG 054703 | 2024-08-09 | W |  | 1000 | Function Test & Complete ITR/MITR | INT | Function Test & Complete ITR/MITR |  | Management of Change | 9014200_0020 |  |  | ST5 |  | C3 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ | 20002965 | AU1072 | 1000136732 | S002 | 30 | 30 | 5300013766 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-09-30 |  | Management of Change | 2024-09-26 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-08-09 | 2025-03-01 | 2024-09-30 | 2025-03-01 | 2025-03-01 | INLEC | 100038870 | 1000 | 0010 | 100038870 | MOC-123206 Replace JB 5PM2001BJ | AA53.5PM2001BJ | JB,MOTOR,RCU STABLI HEATER PUMP,5P2001B | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.08.2024) | 10204731 | GLAND,CABLE;EEX,M50,CCG 054705 | 2 | EA | 3 | 0 | 0 | 2 | EA | 29.01 - At KGP | Supply for Order 100038870, Item 1 cannot be changed 180073873 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300013766 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180073873 | 9014200 | 06 | Scheduling | 0000137402 | 1 | 0 | EA | 102000000016236 | 102000000016148 | 102000000016159 | 01-Road |  | 4-Arrived | LP-NWS-14 | WorkPackLink | P08WHSFLR | AA53-TA-P07 | 0 | 5400002054 | 10 | 2 | EA | 0 | 0 | 2024-09-26 |  | Y | 1001 | 2024-08-09 | GRST-5000295875_2024 | 0 | 0 | 0 | 0 |  | 2024-10-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000031264 | 1020 | 2025-07-31 | 2 |  | 2024-09-25 | 4900139136_2024_0001 | 2024-10-03 | 5PM2001BJ | 5000295875_2024_0001 | 0 | 2 | 0 | 90017620 | 2 | 0 | 180073887/180073873 | 2 | 0 | 0 | X | L | 4900139136 | 2024 |  | 5000295875 | 2024 | 0 |  | 2024-09-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204731 | GLAND,CABLE;EEX,M50,CCG 054705 | 2024-08-09 | W |  | 1000 | Function Test & Complete ITR/MITR | INT | Function Test & Complete ITR/MITR |  | Management of Change | 9014200_0010 |  |  | ST5 |  | C3 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ | 20002965 | AU1072 | 1000136732 | S002 | 30 | 30 | 5300013766 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-09-30 |  | Management of Change | 2024-09-26 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137402 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0040 | 0140 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10204839 | BOLT;NP SRQ95318 | 4 | EA | 8 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000236589 | 113 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  |  |  |  | Tie Bolt |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204839 | BOLT;NP SRQ95318 |  |  |  | 0040 | CONNECTING ROD | INT | CONNECTING ROD | 5 |  |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000233553 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0040 | 0150 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10204840 | NUT ASY,CONROD;NP SQQ08744 | 4 | EA | 12 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 114 cannot be changed 90028418 item 330 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 114 | 0 | EA | 102000000030533 | 102000000030946 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0330 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Nut |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204840 | NUT ASY,CONROD;NP SQQ08744 | 2024-09-23 | W |  | 0040 | CONNECTING ROD | INT | CONNECTING ROD | 5 |  | 90028418_0330 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 114 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 340 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0040 | 0160 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10204841 | NUT,COUNTER;NP SQQ08745 | 4 | EA | 13 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 115 cannot be changed 90028418 item 340 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 115 | 0 | EA | 102000000030533 | 102000000030947 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0340 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Counter Nut |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204841 | NUT,COUNTER;NP SQQ08745 | 2024-09-23 | W |  | 0040 | CONNECTING ROD | INT | CONNECTING ROD | 5 |  | 90028418_0340 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 115 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 350 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-09-24 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147980 | 0040 | 0170 | 200147980 | 5Y SVC RE SD 5K2001 COMPR GSM MATR 2HF1 | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.09.2024) | 10204842 | WASHER;NP RRP39247 | 4 | EA | 10 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147980, Item 116 cannot be changed 90028418 item 350 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015696 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028418 | 05 | Preparation | 0000236589 | 116 | 0 | EA | 102000000030533 | 102000000030289 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | KGP TA PO7 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-24 | ODST-0090028418_0350 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-12-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | Washer |  | 0 | 2 | 0 | 90028418 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204842 | WASHER;NP RRP39247 | 2024-09-23 | W |  | 0040 | CONNECTING ROD | INT | CONNECTING ROD | 5 |  | 90028418_0350 |  |  | ST5 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 116 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000233553 | S002 |  | 30 | 5300015696 | 360 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-07 | 236589 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0030 | 0190 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204998 | GASKET;CNAF,110 X 217 X 2MM,FF,C4430 | 2 | EA | 5 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 20 cannot be changed 90028419 item 190 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 20 | 0 | EA | 102000000030386 | 102000000030087 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204998 | GASKET;CNAF,110 X 217 X 2MM,FF,C4430 | 2024-07-21 | W |  | 0030 | COMPRESSOR DISCHARGE CASE | INT | COMPRESSOR DISCHARGE CASE | 5 |  | 90028419_0190 |  |  | DG1 |  | A5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 20 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 200 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1540 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10204998 | GASKET;CNAF,110 X 217 X 2MM,FF,C4430 | 1 | EA | 5 | 0 | 0 | 1 | EA | 19.02 - SOH @AA02 | Supply for Order 200091513, Item 512 cannot be changed 90028419 item 3680 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3710 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 512 | 0 | EA | 102000000030488 | 102000000034004 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3680 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204998 | GASKET;CNAF,110 X 217 X 2MM,FF,C4430 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 90028419_3680 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 512 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3710 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2320 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10205061 | O-RING;NP KHA083008001 | 2 | EA | 12 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 311 cannot be changed 90028419 item 2440 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2470 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 311 | 0 | EA | 102000000030491 | 102000000030642 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2440 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205061 | O-RING;NP KHA083008001 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_2440 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 311 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2470 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3050 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10205247 | GASKET;NP KFZ253940604 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 434 cannot be changed 90028419 item 3050 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3080 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 434 | 0 | EA | 102000000030494 | 102000000030355 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205247 | GASKET;NP KFZ253940604 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 90028419_3050 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 434 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3080 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1060 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10205249 | WASHER;NP FLD032010025 | 18 | EA | 36 | 0 | 0 | 18 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 129 cannot be changed 90028419 item 1030 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1040 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 129 | 0 | EA | 102000000030480 | 102000000030285 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205249 | WASHER;NP FLD032010025 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1030 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 129 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1040 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1010 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10205258 | PIN,RAD,AIR;NP SMO80058 | 4 | EA | 7 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 116 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205258 | PIN,RAD,AIR;NP SMO80058 |  |  |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1020 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10205259 | PIN,RAD,AIR;NP ISM268121056 | 2 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 117 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205259 | PIN,RAD,AIR;NP ISM268121056 |  |  |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0780 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10205293 | BOLT;NP RVQ22139 | 6 | EA | 12 | 0 | 0 | 6 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 635 cannot be changed 90028419 item 4220 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 635 | 0 | EA |  |  | 102000000031934 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205293 | BOLT;NP RVQ22139 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_4220 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 635 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4250 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1460 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10205293 | BOLT;NP RVQ22139 | 6 | EA | 12 | 0 | 0 | 6 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 693 cannot be changed 90028419 item 4610 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 693 | 0 | EA | 102000000031935 | 102000000030997 | 102000000030480 |  |  |  |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4610 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205293 | BOLT;NP RVQ22139 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_4610 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 693 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4650 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0080 | 0052 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10205874 | SEALANT,PIPE,HP;LOCTITE 577 | 4 | TB | 5 | 1 | 0 | 1 | TB | 23.01 - SOH @ AA02 | Supply for Order 200091126, Item 36 cannot be changed 90023534 item 900020 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 36 | 0 | TB | 102000000031643 | 102000000031174 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0190/90023534_0090_0010/90023534_0090_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205874 | SEALANT,PIPE,HP;LOCTITE 577 | 2024-01-02 | W |  | 0080 | LUBRICATOR SPARES | INT | LUBRICATOR SPARES | 5 |  | 90023534_0190/90023534_0090_0010/90023534_0090_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 36 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 330 |  |  | 0 | 4 | TB | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0080 | 0052 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10205874 | SEALANT,PIPE,HP;LOCTITE 577 | 4 | TB | 5 | 1 | 0 | 1 | TB | 23.01 - SOH @ AA02 | Supply for Order 200091126, Item 36 cannot be changed 90023534 item 900020 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 36 | 0 | TB | 102000000031643 | 102000000031173 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0190/90023534_0090_0010/90023534_0090_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205874 | SEALANT,PIPE,HP;LOCTITE 577 | 2024-01-02 | W |  | 0080 | LUBRICATOR SPARES | INT | LUBRICATOR SPARES | 5 |  | 90023534_0190/90023534_0090_0010/90023534_0090_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 36 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 330 |  |  | 0 | 4 | TB | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0080 | 0052 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10205874 | SEALANT,PIPE,HP;LOCTITE 577 | 4 | TB | 5 | 1 | 0 | 2 | TB | 23.01 - SOH @ AA02 | Supply for Order 200091126, Item 36 cannot be changed 90023534 item 900020 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 36 | 0 | TB | 102000000031643 | 102000000031037 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0190/90023534_0090_0010/90023534_0090_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10205874 | SEALANT,PIPE,HP;LOCTITE 577 | 2024-01-02 | W |  | 0080 | LUBRICATOR SPARES | INT | LUBRICATOR SPARES | 5 |  | 90023534_0190/90023534_0090_0010/90023534_0090_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 36 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 330 |  |  | 0 | 4 | TB | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-01-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | VALVE | 100085072 | 0025 | 0010 | 100085072 | MOC-151012: ACT-IS 520PCV012 | AA53.520PCV012 | VALVE,C2001 OVERHEAD VAP TO FLARE | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(08.01.2025) | 10206163 | BOOSTER,FLOW,VALTEK 8" CL2500 MK1 CV | 2 | EA | 2 | 0 | 1 | 2 | EA | 08.01 - SOH 2 AA02 | Supply for Order 100085072, Item 3 cannot be changed 90028434 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019757 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028434 | 05 | Preparation | 0000267773 | 3 | 0 | EA | 102000000030120 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-08 | ODST-0090028434_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PCV012 |  | 0 | 2 | 0 | 90028434 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10206163 | BOOSTER,FLOW,VALTEK 8" CL2500 MK1 CV | 2025-01-08 | W |  | 0025 | Replace Auxillaries | INT | Replace Auxillaries |  | Management of Change/Order Requires Replanning | 90028434_0030 |  |  | ST5 |  | C1 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262813 | S002 |  | 30 | 5300019757 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change/Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267773 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
1 | 25SDFR0 | Released | 2024-11-18 | 2025-05-24 |  | 2025-02-28 | 2025-05-25 | MECH | 100044631 | 0060 | 0020 | 100044631 | Replace Gasket - 3P18075 | AA53.EPFRAC6 | PIPE,ZONE FRAC TRAIN 3 | AA01 | 30 | WO item has not been released yet | 10206406 | STUDBOLT;0.625" X 105MM,A193 B8M CL2 | 8 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000143185 | 2 | 0 | [8 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-24 |  |  | 2025-05-24 |  |  |  |  | 2023-12-29 | 0 |  |  |  |  | HIGH |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10206406 | STUDBOLT;0.625" X 105MM,A193 B8M CL2 |  |  |  | 0060 | Replace HPV Fittings (Bolt up scope) | INT | Replace HPV Fittings (Bolt up scope) | 7 |  |  |  |  | FR3 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDFR0 | MJ |  |  | 1000142567 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-25 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091108 | 0090 | 0100 | 200091108 | 12Y RE SD 1K2420 COMPR BSR MATERIALS | AA53.1K2420 | COMPR,CENTRIFUGAL U2400 2ND STAGE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10206825 | GASKET;305MM,338MM,KLINGERSIL C4430 | 2 | EA | 9 | 4 | 0 | 2 | EA | 18.02 - SOH @ AA02 | Supply for Order 200091108, Item 115 cannot be changed 90028420 item 780 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013062 | 810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028420 | 05 | Preparation | 0000129406 | 115 | 0 | EA | 102000000033937 |  | 102000000034100 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-20 | ODST-0090028420_0780 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-04-28 | 0 |  | 2025-02-24 |  | 2025-03-01 | SOFilter |  | 0 | 2 | 0 | 90028420 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10206825 | GASKET;305MM,338MM,KLINGERSIL C4430 | 2024-07-20 | W |  | 0090 | SEAL OIL | INT | SEAL OIL |  |  | 90028420_0780 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 115 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000128737 | S002 |  | 30 | 5300013062 | 810 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129406 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-14 | 2025-02-27 | 2025-02-22 | 2025-02-25 | 2025-03-13 | MECH | 200147078 | 0040 | 0020 | 200147078 | MOC-104398 4Y INSP INT EXCH 1K2420E4 | AA53.1K2420E4 | EXCH,HEAT SEAL OIL COOLER 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.01.2025) | 10206825 | GASKET;305MM,338MM,KLINGERSIL C4430 | 1 | EA | 9 | 4 | 0 | 1 | EA | 18.02 - SOH @ AA02 | Supply for Order 200147078, Item 2 cannot be changed 90029997 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020333 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90029997 | 05 | Preparation | 0000235349 | 2 | 0 | EA | 101000000144007 |  | 102000000034100 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-22 | ODST-0090029997_0020 | 0 | 0 | 0 | 0 |  | 2025-02-25 | AA53 | 2025-02-27 |  |  | 2025-02-27 |  |  |  |  | 2025-09-16 | 0 |  | 2025-02-22 |  | 2025-02-27 |  |  | 0 | 2 | 0 | 90029997 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10206825 | GASKET;305MM,338MM,KLINGERSIL C4430 | 2025-01-22 | W |  | 0040 | Remove Bonnet / Spools & Install Blinds | INT | Remove Bonnet / Spools & Install Blinds |  |  | 90029997_0020 |  |  | DG1 |  | C3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232392 | S002 |  | 30 | 5300020333 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235349 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-13 | 2025-02-25 | 2025-02-25 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0740 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10206839 | BAR,LKG;NP SMP5952078 | 2 | EA | 2 | 0 | 0 | 2 | EA | 13.01 - SOH @ AA02 | Supply for Order 200091513, Item 87 cannot be changed 90028419 item 700 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 710 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 87 | 0 | EA | 102000000030492 | 102000000030653 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0700 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10206839 | BAR,LKG;NP SMP5952078 | 2024-07-21 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_0700 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 87 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 710 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0160 | 2450 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10207323 | RING,PKG;VIT,THOMASSEN 30380012012 | 4 | EA | 9 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 631 cannot be changed 90028419 item 4210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 631 | 0 | EA | 102000000030491 | 102000000030621 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10207323 | RING,PKG;VIT,THOMASSEN 30380012012 | 2024-07-21 | W |  | 0160 | X-OVER VALVES & DRESSER COUPLINGS | INT | X-OVER VALVES & DRESSER COUPLINGS | 5 |  | 90028419_4210 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 631 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4240 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2810 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10207675 | HOSE,0.375" X 300MM,PTFE/SS316 BRAID | 2 | ASY | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000129822 | 409 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10207675 | HOSE,0.375" X 300MM,PTFE/SS316 BRAID |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2820 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10207676 | HOSE,0.375" x 500MM,PTFE/SS316 BRAID | 4 | ASY | 9 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000129822 | 410 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10207676 | HOSE,0.375" x 500MM,PTFE/SS316 BRAID |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2830 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10207677 | HOSE,0.375" X 750MM,PTFE/SS316 BRAID | 6 | ASY | 37 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000129822 | 411 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10207677 | HOSE,0.375" X 750MM,PTFE/SS316 BRAID |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2025-01-31 | 2025-03-01 | 2025-02-24 | 2025-05-11 | 2025-05-13 | INLEC | 100090545 | 0010 | 0010 | 100090545 | FAR4IPS1 - Tricon Card Replacement | AA53.FAR4IPS1 | PANEL,SYSTEM CABINET,IPS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(31.01.2025) | 10210526 | MODULE,IF;0.7A,24VDC,TRICONEX 3624 | 2 | EA | 18 | 0 | 0 | 2 | EA | 03.02 - SOH @ AA02 | Supply for Order 100090545, Item 1 cannot be changed 90030062 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020702 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030062 | 05 | Preparation | 0000291004 | 1 | 0 | EA | 102000000032209 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-31 | ODST-0090030062_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-11 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | FAR4IPS1 |  | 0 | 2 | 0 | 90030062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10210526 | MODULE,IF;0.7A,24VDC,TRICONEX 3624 | 2025-01-31 | W |  | 0010 | Inlec Assistance | INT | Inlec Assistance |  |  | 90030062_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000284798 | S002 | 30 | 30 | 5300020702 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W43601 | 2025-01-17 | 291004 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-13 | 2025-05-11 | 2025-05-11 | Pre-costed/Object created/Order Approved/Released/Material shortage/Settlement rule created/Date set by external system/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-03-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200065935 | 0010 | 0070 | 200065935 | 6Y Vib/Speed Probe Repl (7) 1K2420 | AA53.124GE026 | TXDCR,TRIP VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.02.2025) | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 8 | EA | 32 | 0 | 0 | 3 | EA | 05.02 - SOH @ AA02 | Supply for Order 200065935, Item 8 cannot be changed 90030135 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300008306 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030135 | 05 | Preparation | 0000100270 | 8 | 0 | EA | 101000000143389 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-03-25 | ODST-0090030135_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 124SE002A |  | 0 | 2 | 0 | 90030135 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 2025-02-02 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90030135_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000099654 | S002 |  | 30 | 5300008306 | 80 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100270 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-03-12 | 2025-03-01 | 2024-07-19 | 2025-03-01 | 2025-03-01 | INLEC | 200065935 | 0010 | 0020 | 200065935 | 6Y Vib/Speed Probe Repl (7) 1K2420 | AA53.124GE026 | TXDCR,TRIP VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.03.2024) | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 8 | EA | 32 | 0 | 0 | 8 | EA | 29.01 - Consumed | Supply for Order 200065935, Item 2 cannot be changed 180073882 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300008306 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180073882 | 9014218 | 05 | Preparation | 0000100270 | 2 | 0 | EA | 102000000007255 |  | 102000000016159 | 01-Road |  | 4-Arrived | LP-NWS-14 | WorkPackLink | P08WHSFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 8 | 0 | 2024-09-26 |  | Y | 1001 | 2024-03-25 |  | 0 | 0 | 0 | 0 |  | 2024-07-20 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000031264 | 1020 | 2025-07-31 | 8 |  | 2024-09-25 | 4900139146_2024_0001 | 2024-07-22 | 200065935 | 5000295873_2024_0001 | 0 | 2 | 0 | 90011040 | 8 | 0 | 180073882/180073889 | 2 | 0 | 0 | X | L | 4900139146 | 2024 |  | 5000295873 | 2024 | 0 |  | 2024-07-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 2024-03-25 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 9014218_0020 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SD2420 | MJ | 20002965 | AU1072 | 1000099654 | S002 |  | 30 | 5300008306 | 20 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-07-19 |  |  | 2024-09-26 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100270 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-17 | INLEC | 200089806 | 0010 | 0010 | 200089806 | 8Y Repl Vibration Probes (18) 1K1820 | AA53.118XT508X | TXDCR,1K1820 COMPR INBOARD COUPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 18 | EA | 32 | 0 | 0 | 18 | EA | 02.10 - SOH @ AA02 | Supply for Order 200089806, Item 1 cannot be changed 90024958 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003900 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024958 | 05 | Preparation | 0000128060 | 1 | 0 | EA | 102000000029852 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024958_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024958 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 2024-01-02 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024958_0010 |  |  | FR1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127469 | S002 |  | 30 | 5300003900 | 10 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128060 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-17 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-16 | INLEC | 200089807 | 0010 | 0010 | 200089807 | 8Y Replace Vibration Probes (4) 1K1820 | AA53.118XT505A | TXDCR,1K1820 GEAR AXIAL DISPL | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.10.2024) | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 4 | EA | 32 | 0 | 0 | 4 | EA | 24.10 - SOH @ AA02 | Supply for Order 200089807, Item 1 cannot be changed 90024959 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300003901 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024959 | 05 | Preparation | 0000128101 | 1 | 0 | EA | 102000000029854 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024959_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K1820 |  | 0 | 2 | 0 | 90024959 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 2024-10-14 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90024959_0020 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000127470 | S002 |  | 30 | 5300003901 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128101 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-16 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147116 | 0020 | 0020 | 200147116 | 3Y Vibration Probe Replace (7) 1KT2420 | AA53.124YE031 | TXDCR,ALARM VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 4 | EA | 32 | 0 | 0 | 4 | EA | 18.11 - SOH @ AA02 | Supply for Order 200147116, Item 2 cannot be changed 90025108 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017864 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025108 | 05 | Preparation | 0000235387 | 2 | 0 | EA | 102000000029853 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025108_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K2420 |  | 0 | 2 | 0 | 90025108 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 2024-11-13 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025108_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232430 | S002 |  | 30 | 5300017864 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235387 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147116 | 0020 | 0080 | 200147116 | 3Y Vibration Probe Replace (7) 1KT2420 | AA53.124YE031 | TXDCR,ALARM VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(19.11.2024) | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 3 | EA | 32 | 0 | 0 | 3 | EA | 20.11 - SOH @ AA02 | Supply for Order 200147116, Item 8 cannot be changed 90025108 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017864 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025108 | 05 | Preparation | 0000235387 | 8 | 0 | EA | 102000000029855 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-11-14 | ODST-0090025108_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 1K2420 |  | 0 | 2 | 0 | 90025108 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10210800 | CABLE,EXTN;EX,BENTLY 3301300400005 | 2024-11-19 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025108_0060 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232430 | S002 |  | 30 | 5300017864 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235387 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2025-02-08 | 2025-03-01 | 2025-02-09 | 2025-02-27 | 2025-03-11 | ROTAT | 600001363 | 0010 | 0030 | 600001363 | MOC-77357 5K2001 Install Aux LO Pump | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(09.02.2025) | 10212960 | MOTOR,AC;415V,1450RPM,7.5KW,EX(N),FOOT | 1 | EA | 2 | 0 | 0 | 1 | EA | 09.02 - SOH @ AA02 | Supply for Order 600001363, Item 9 cannot be changed 90030542 item 10 already exists | Material picked; currently at SW3R02D01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018438 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90030542 | 05 | Preparation | 0000084301 | 9 | 0 | EA |  |  | 102000000034074 |  |  |  |  | WorkPackLink | SW3R02D01A | AA53-P07-LO | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-27 | ODST-0090030542_0010 | 0 | 0 | 0 | 0 |  | 2025-02-10 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-09 |  | 2025-02-14 | Scott Kinloc |  | 0 | 2 | 0 | 90030542 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-09 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10212960 | MOTOR,AC;415V,1450RPM,7.5KW,EX(N),FOOT | 2025-02-09 | W |  | 0010 | 5K2001 - Install Auxiliary Lube Oil Pump | INT | 5K2001 - Install Auxiliary Lube Oil Pump |  |  | 90030542_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000083685 | S002 | 30 | 30 | 5300018438 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-09 |  |  |  |  | 1070 |  | 2025-02-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84301 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-11 | 2025-02-27 | 2025-02-27 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released/Partially confirmed/Part printed | AM06 | Capital | C0-000678-6B-01-02-02-EX
| 25SDGT7 | Released | 2024-10-25 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 100034776 | 0040 | 0010 | 100034776 | MOC-145870-PV CM G4007V3 Passing Fill Va | AA53.G4007V3 | VE,CO2 LOW PRESSURE,GT4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.01.2025) | 10215279 | PIPE,SML,15MM,SS316L,SCH40S | 6 | M | 0 | 0 | 0 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 100034776, Item 2 cannot be changed 90030057 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020137 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90030057 | 05 | Preparation | 0000133257 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2025-01-17 | ODST-0090030057_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-03-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100034776 |  | 0 | 2 | 0 | 90030057 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10215279 | PIPE,SML,15MM,SS316L,SCH40S | 2025-01-17 | W |  | 0040 | Fabricate Spool ( site inspection ) | INT | Fabricate Spool ( site inspection ) |  | Engineering Query/Management of Change | 90030057_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000132686 | S002 | 30 | 30 | 5300020137 | 10 |  |  | 0 | 6 | M | 2001 | AA02 | 2025-02-24 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133257 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100041844 | 0020 | 0010 | 100041844 | MOC-110460 Replace 414FT702 | AA53.4GT1410 | TURB,LNG HYDRAULIC | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.12.2024) | 10215279 | PIPE,SML,15MM,SS316L,SCH40S | 6 | M | 0 | 0 | 0 | 0 |  | 17.12 - ETA 12.02.25 PO 4500039500 AUS FITTINGS CPT | Supply for Order 100041844, Item 3 cannot be changed 90028427 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000601 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90028427 | 05 | Preparation | 0000140308 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028427_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2022-01-21 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100041844 |  | 0 | 2 | 0 | 90028427 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10215279 | PIPE,SML,15MM,SS316L,SCH40S | 2024-12-16 | W |  | 0020 | Remove & Replace Flow Transmitter | INT | Remove & Replace Flow Transmitter |  | Management of Change | 90028427_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000139679 | S002 | 30 | 30 | 5300000601 | 30 |  |  | 0 | 6 | M | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140308 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0130 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10218611 | STUDBOLT;0.625"X90MM,L7,CAD+XYLAN | 4 | EA | 56 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 12 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218611 | STUDBOLT;0.625"X90MM,L7,CAD+XYLAN |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0400 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10218611 | STUDBOLT;0.625"X90MM,L7,CAD+XYLAN | 4 | EA | 56 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 38 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218611 | STUDBOLT;0.625"X90MM,L7,CAD+XYLAN |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0260 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10218611 | STUDBOLT;0.625"X90MM,L7,CAD+XYLAN | 12 | EA | 56 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 25 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218611 | STUDBOLT;0.625"X90MM,L7,CAD+XYLAN |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0140 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10218612 | STUDBOLT;0.625"X100MM,L7,CAD+XYLAN | 32 | EA | 40 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 13 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218612 | STUDBOLT;0.625"X100MM,L7,CAD+XYLAN |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0270 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10218612 | STUDBOLT;0.625"X100MM,L7,CAD+XYLAN | 24 | EA | 40 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 26 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218612 | STUDBOLT;0.625"X100MM,L7,CAD+XYLAN |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0410 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10218612 | STUDBOLT;0.625"X100MM,L7,CAD+XYLAN | 16 | EA | 40 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 39 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218612 | STUDBOLT;0.625"X100MM,L7,CAD+XYLAN |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0280 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10218617 | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN | 16 | EA | 24 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 27 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10218617 | STUDBOLT;0.625"X120MM,L7,CAD+XYLAN |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2880 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10219152 | BOLT,HEX;0.250"X22MM,NP GRA06022 | 10 | EA | 31 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 566 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219152 | BOLT,HEX;0.250"X22MM,NP GRA06022 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1110 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10219152 | BOLT,HEX;0.250"X22MM,NP GRA06022 | 31 | EA | 31 | 0 | 0 | 31 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 134 cannot be changed 90028419 item 1080 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1090 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 134 | 0 | EA | 102000000030480 | 102000000030250 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219152 | BOLT,HEX;0.250"X22MM,NP GRA06022 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1080 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 134 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1090 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1040 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10219155 | BOLT,HEX;0.375"X31MM,NP GRA09031 | 18 | EA | 22 | 0 | 0 | 18 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 127 cannot be changed 90028419 item 1010 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1020 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 127 | 0 | EA | 102000000030480 | 102000000030238 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10219155 | BOLT,HEX;0.375"X31MM,NP GRA09031 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1010 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 127 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1020 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-08-02 | 2024-08-04 | 2024-08-29 | 2024-08-16 | 2025-05-08 | INLEC | 100082105 | 0010 | 0010 | 100082105 | OPSD 4KM1410KM2A investigate fan trip | AA53.4KM1410KM2A | MOTOR,START/HELP MOTOR COOL FAN,4KM1410 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(04.08.2024) | 10220301 | RELAY,O/L;ABB 1SAZ211201R1033 | 3 | EA | 0 | 0 | 0 | 3 | EA | 20.02 - AT KGP | Supply for Order 100082105, Item 1 cannot be changed 180095297 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300013562 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180095297 | 90017050 | 07 | Execution | 0000254730 | 1 | 0 | EA |  |  | 101000000089429 | 06-Air Passenger |  | 3-In Transit |  | WorkPackLink | P99PICKUPFROMWHSE | P19 FL Inlec | 0 |  | 0 | 0 |  | 3 | 0 |  | 2024-09-13 | Y | 1001 | 2024-08-04 |  | 0 | 28 | 0 | 0 |  | 2024-08-30 | AA53 | 2024-08-04 |  |  | 2024-09-01 |  |  | 100000041785 | 1020 | 2025-07-28 | 3 |  | 2024-11-19 | 4900175184_2024_0001 | 2024-09-01 | 4KM1410KM2A | 5000285164_2024_0001 | 0 | 2 | 0 | 90017050 | 3 | 0 | 180095297 | 2 | 0 | 0 | X | L | 4900175184 | 2024 |  | 5000285164 | 2024 | 0 |  | 2024-08-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10220301 | RELAY,O/L;ABB 1SAZ211201R1033 | 2024-08-04 | W |  | 0010 | FL 4KM1410KM2A investigate fan trip | INT | FL 4KM1410KM2A investigate fan trip |  | Opportune Shutdown | 90017050_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ | 1000003300 | AU1072 | 1000250885 | S002 | 30 | 30 | 5300013562 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-08-29 |  | Opportune Shutdown | 2024-09-12 |  | 1070 |  | 2024-08-04 | 1001 | Woodside Energy Ltd | W001 | W41088 | 2024-08-02 | 254730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-08 | 2024-08-16 | 2024-08-16 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Goods movement posted/Material committed/Partially confirmed/Date set by external system | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-05-23 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0580 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10220454 | STUDBOLT;0.875" X 150MM,A193 B8M CL2 | 12 | EA | 36 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 58 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-05-23 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10220454 | STUDBOLT;0.875" X 150MM,A193 B8M CL2 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-30 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100086264 | 0020 | 0020 | 100086264 | Start Clutch/UV Purge Sol OH (3) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10221899 | VALVE,SLND;EX,1400KPA,ASCO EAHTB262A134 | 1 | EA | 1 | 1 | 0 | 1 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086264, Item 2 cannot be changed 90025091 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017153 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124193 | 9027127 | 05 | Preparation | 0000272423 | 2 | 0 | EA | 102000000032149 | 102000000029233 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-31 | IDST-0180124193 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 1 |  | 2025-02-11 | 4900234099_2025_0003 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025091 | 0 | 0 | 180124193 | 2 | 0 | 0 | X | L | 4900234099 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10221899 | VALVE,SLND;EX,1400KPA,ASCO EAHTB262A134 | 2024-10-29 | W |  | 0020 | Complete Replacements | INT | Complete Replacements |  |  | 9027127_0030 |  |  | DG1 |  | B4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267123 | S002 |  | 30 | 5300017153 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272423 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2890 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10221899 | VALVE,SLND;EX,1400KPA,ASCO EAHTB262A134 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 567 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | UV purge |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10221899 | VALVE,SLND;EX,1400KPA,ASCO EAHTB262A134 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0300 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10222953 | SPADE BLIND,50MM,CL300,RF,A516-60/70 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 28 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10222953 | SPADE BLIND,50MM,CL300,RF,A516-60/70 |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SD2301 | Released | 2025-01-14 | 2025-03-01 |  | 2025-02-27 | 2025-03-01 | MECH | 200147128 | 0080 | 0110 | 200147128 | 2Y EX/SH INSP CSE/RVI 1E2302 | AA53.1E2302 | EXCH,HEAT REGENERATION GAS SHELL | AA01 | 10 | WO item has not been released yet | 10223375 | STUDBOLT;1.125" X 200MM,A193 B8M CL2 | 60 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235400 | 12 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 60 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-16 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223375 | STUDBOLT;1.125" X 200MM,A193 B8M CL2 |  |  |  | 0080 | Remove Bonnet/Spools for Inspection | INT | Remove Bonnet/Spools for Inspection | [5 empty] | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SD2301 | MJ |  |  | 1000232443 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-02-27 | 2025-02-27 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1480 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10223756 | SHIELD,CASE,INNER HEAT;NP SMR24371 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  |  |  | 05 | Preparation | 0000129822 | 745 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223756 | SHIELD,CASE,INNER HEAT;NP SMR24371 |  |  |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10223756 | SHIELD,CASE,INNER HEAT;NP SMR24371 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  |  |  | 05 | Preparation | 0000129822 | 744 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223756 | SHIELD,CASE,INNER HEAT;NP SMR24371 |  |  |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223759 | PIN,STR;0.125"X12MM,NP FJV03012 | 4 | EA | 16 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 156 cannot be changed 90028419 item 1200 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 156 | 0 | EA | 102000000030480 | 102000000030164 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1200 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223759 | PIN,STR;0.125"X12MM,NP FJV03012 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1200 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 156 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1220 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0880 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223763 | PACK,INS,OUTER CASE;NP SMQ49326 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 103 cannot be changed 90028419 item 810 already exists | Material picked; currently at KSF-PACK-SD-LRG/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 820 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 103 | 0 | EA |  |  | 102000000031285 |  |  |  |  | WorkPackLink | KSF-PACK-SD-LRG |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0810 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223763 | PACK,INS,OUTER CASE;NP SMQ49326 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0810 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 103 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 820 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0890 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223765 | PACK,INS,OUTER CASE;NP SMQ49325 | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 104 cannot be changed 90028419 item 820 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 830 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 104 | 0 | EA |  |  | 102000000031286 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0820 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223765 | PACK,INS,OUTER CASE;NP SMQ49325 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0820 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 104 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 830 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0900 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223767 | PACK,INS,OUTER CASE;NP SMQ49327 | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 105 cannot be changed 90028419 item 830 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 840 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 105 | 0 | EA |  |  | 102000000031287 |  |  |  |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0830 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223767 | PACK,INS,OUTER CASE;NP SMQ49327 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0830 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 105 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 840 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 1100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223788 | BOLT,HEX;NP GTJ09044 | 16 | EA | 36 | 0 | 0 | 16 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 125 cannot be changed 90028419 item 990 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1000 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 125 | 0 | EA | 102000000030487 | 102000000030248 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0990 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223788 | BOLT,HEX;NP GTJ09044 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0990 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 125 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1000 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0940 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223804 | SEAL,STRIP;NP SMR45670 | 28 | EA | 58 | 0 | 0 | 28 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 109 cannot be changed 90028419 item 860 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 870 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 109 | 0 | EA | 102000000030487 | 102000000030475 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 28 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0860 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223804 | SEAL,STRIP;NP SMR45670 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0860 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 109 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 870 |  |  | 0 | 28 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1370 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223823 | INSULATION,THERM;NP ICF000043798 | 1 | EA | 0 | 0 | 0 | 0 |  | 21.10 - ETA 11.03.25 PO 4500031678 BH | Supply for Order 200091513, Item 160 cannot be changed 90028419 item 1230 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 160 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223823 | INSULATION,THERM;NP ICF000043798 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1230 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 160 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1340 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223827 | BOLT,HEX;ALLOY ST,NP GQF06019 | 31 | EA | 31 | 0 | 0 | 7 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 157 cannot be changed 90028419 item 1210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 157 | 0 | EA | 102000000030480 | 101000000146591 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223827 | BOLT,HEX;ALLOY ST,NP GQF06019 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1210 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 157 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1230 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1340 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223827 | BOLT,HEX;ALLOY ST,NP GQF06019 | 31 | EA | 31 | 0 | 0 | 24 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 157 cannot be changed 90028419 item 1210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 157 | 0 | EA | 102000000030480 | 102000000030254 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223827 | BOLT,HEX;ALLOY ST,NP GQF06019 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1210 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 157 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1230 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1350 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223851 | BOLT,HEX;NP GTJ06031 | 31 | EA | 477 | 0 | 0 | 31 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 158 cannot be changed 90028419 item 1220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 158 | 0 | EA | 102000000030480 | 102000000030244 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 31 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223851 | BOLT,HEX;NP GTJ06031 | 2024-07-21 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_1220 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 158 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1240 |  |  | 0 | 31 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2430 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223917 | NUT,HEX;0.500" 13 UNC,NP FFF14612 | 12 | EA | 50 | 0 | 0 | 12 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 355 cannot be changed 90028419 item 2750 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2780 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 355 | 0 | EA | 102000000030495 | 102000000030195 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223917 | NUT,HEX;0.500" 13 UNC,NP FFF14612 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_2750 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 355 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  |  | 5300013090 | 2780 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1790 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10223926 | BOLT,HEX;ALLOY ST,NP GTH12028 | 6 | EA | 16 | 0 | 0 | 6 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 246 cannot be changed 90028419 item 1880 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1910 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 246 | 0 | EA | 102000000030389 | 102000000030242 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1880 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223926 | BOLT,HEX;ALLOY ST,NP GTH12028 | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1880 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 246 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1910 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0070 | 0950 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10224650 | SEAL,STRIP;NP SMR45672 | 2 | EA | 6 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 110 cannot be changed 90028419 item 870 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 110 | 0 | EA | 102000000030487 | 102000000030474 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0870 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10224650 | SEAL,STRIP;NP SMR45672 | 2024-07-21 | W |  | 0070 | TURBINE CASE | INT | TURBINE CASE | 5 |  | 90028419_0870 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 110 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 880 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-12-23 | 2025-05-08 | 2025-05-03 | 2025-05-08 | 2025-05-09 | INLEC | 100089412 | 0010 | 0020 | 100089412 | OPSD 414HV851 Replace Reg / stroke | AA53.414HV851 | VALVE,MANUAL 4V1431 HC LIQ TO E1423 | AA01 | 30 | No Issue identified | 10229092 | GAUGE,PRESS;BOURDON MEP5460D24 | 1 | EA | 0 | 0 | 0 | 0 |  | 10.03 - PR 2000285465 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300019450 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000285921 | 2 | 0 | [8 empty] | WorkPackLink |  | P19 OPSD | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-24 | STST-5300019450_00020 | 0 | 0 | 0 | 0 |  | 2025-05-06 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-12-18 | 0 |  | 2025-05-03 |  | 2025-05-08 | 414HV851 |  | 0 | 2 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229092 | GAUGE,PRESS;BOURDON MEP5460D24 |  |  |  | 0010 | Replace air reg / Stroke cal valve | INT | Replace air reg / Stroke cal valve |  | Opportune Shutdown |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000280084 | S002 | 30 | 30 | 5300019450 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-05-03 |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPFN4 | 2024-12-23 | 285921 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-09 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Goods movement posted/Material shortage | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | INLEC | 200067823 | 0020 | 0010 | 200067823 | 6Y SIF Exhaust TC Replace (18) 1KT2420 | AA53.124TE301 | TXDCR,1KT2420 TURB EXH DUCT TEMP | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.10.2024) | 10229571 | INSTRUMENT,TC,K;NP RTO68245 | 18 | EA | 61 | 18 | 2 | 18 | EA | 24.10 - SOH @ AA02 | Supply for Order 200067823, Item 1 cannot be changed 90025073 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300016758 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027125 | 05 | Preparation | 0000102098 | 1 | 0 | EA | 102000000029961 |  | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-23 | GIST-4900234109_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2024-07-25 | 18 |  | 2025-02-11 | 4900234109_2025_0001 | 2025-03-01 | 124TE301-318 |  | 0 | 2 | 0 | 90025073 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234109 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229571 | INSTRUMENT,TC,K;NP RTO68245 | 2024-10-23 | W |  | 0020 | Complete Replacement of Cable & TC's | INT | Complete Replacement of Cable & TC's |  | Order Requires Replanning | 9027125_0010 |  |  | DG1 |  | C2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000101542 | S002 | 30 | 30 | 5300016758 | 10 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 102098 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2670 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10229571 | INSTRUMENT,TC,K;NP RTO68245 | 20 | EA | 61 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 395 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | 124T301-318 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229571 | INSTRUMENT,TC,K;NP RTO68245 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0010 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10229640 | ADHESIVE;3 PART KIT,FOSTER 8277 | 1 | KIT | 8 | 0 | 1 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 20 cannot be changed 90031501 item 30 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 20 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0030 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229640 | ADHESIVE;3 PART KIT,FOSTER 8277 | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0030 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 20 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 170 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0020 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10229641 | ADHESIVE;CRY,FOSTER 9066 | 2 | KIT | 8 | 0 | 0 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 21 cannot be changed 90031501 item 40 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 21 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0040 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229641 | ADHESIVE;CRY,FOSTER 9066 | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0040 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 21 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 |  | 30 | 5300021227 | 180 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0240 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10229643 | SEALANT,FOSTER FLEXTRA 95-50,18.9L PAIL | 1 | DR | 0 | 0 | 1 | 0 |  | 07.03 - ETA 27.03.25 PO 4500047066 ARMACEL CPT | Supply for Order 100090053, Item 24 cannot be changed 90032376 item 240 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 24 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0240 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229643 | SEALANT,FOSTER FLEXTRA 95-50,18.9L PAIL | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0240 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 24 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 |  | 30 | 5300022012 | 240 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0220 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10229643 | SEALANT,FOSTER FLEXTRA 95-50,18.9L PAIL | 1 | DR | 0 | 0 | 1 | 0 |  | 20.02 - PR 2000180721 RFQ | Supply for Order 500005166, Item 42 cannot be changed 90031501 item 240 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 42 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0240 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229643 | SEALANT,FOSTER FLEXTRA 95-50,18.9L PAIL | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0240 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 42 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 |  | 30 | 5300021227 | 380 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN4 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 200144771 | 0010 | 0010 | 200144771 | 2Y Harm Filter Vesda Check 60JB870 | AA53.60JB870 | JB,NON I.S. JUNCTION BOX | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10229661 | FILTER ASY,AIR;VISION SYS VSP005 | 1 | EA | 16 | 0 | 1 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200144771, Item 1 cannot be changed 90025042 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016479 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025042 | 05 | Preparation | 0000231921 | 1 | 0 | EA | 102000000027968 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025042_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-10-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | 60JB870 |  | 0 | 2 | 0 | 90025042 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229661 | FILTER ASY,AIR;VISION SYS VSP005 | 2024-10-16 | W |  | 0010 | Function Test & Complete PRT / MITR | INT | Function Test & Complete PRT / MITR | 2 |  | 90025042_0010 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000229037 | S002 |  | 30 | 5300016479 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 231921 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0420 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10229941 | SPADE BLIND,50MM,CL600,SS316 | 15 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 42 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 15 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229941 | SPADE BLIND,50MM,CL600,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0410 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10229942 | SPADE BLIND,100MM,CL600,SS316 | 4 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 41 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229942 | SPADE BLIND,100MM,CL600,SS316 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-10-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100086238 | 0020 | 0050 | 100086238 | Ignitors, Trans & Cable O/H (4) 1KT2420 | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(29.10.2024) | 10230215 | GASKET;KLINGER 0WOO10007838 | 4 | EA | 12 | 4 | 0 | 4 | EA | 31.10 - SOH @ AA02 | Supply for Order 100086238, Item 5 cannot be changed 90025087 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017068 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124191 | 9027113 | 05 | Preparation | 0000272412 | 5 | 0 | EA | 102000000032145 | 102000000027258 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-29 | IDST-0180124191 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-11-05 | 4 |  | 2025-02-11 | 4900234106_2025_0005 | 2025-03-01 | 1KT2420 |  | 0 | 2 | 0 | 90025087 | 0 | 0 | 180124191 | 2 | 0 | 0 | X | L | 4900234106 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10230215 | GASKET;KLINGER 0WOO10007838 | 2024-10-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027113_0050 |  |  | DG1 |  | A2 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 5 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000267111 | S002 |  | 30 | 5300017068 | 50 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-10-22 | 272412 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 3250 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10230215 | GASKET;KLINGER 0WOO10007838 | 6 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 627 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | SPARKPLUG |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10230215 | GASKET;KLINGER 0WOO10007838 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0240 | 2840 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10230215 | GASKET;KLINGER 0WOO10007838 | 6 | EA | 12 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 412 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10230215 | GASKET;KLINGER 0WOO10007838 |  |  |  | 0240 | INLEC MATERIALS | INT | INLEC MATERIALS | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2024-01-02 | 2025-03-01 | 2024-05-24 | 2025-05-08 | 2025-05-08 | INLEC | 100044402 | 0020 | 0010 | 100044402 | LOC Needle Valve Replace (2) 414PDT022 | AA53.414PDT022A | TX,DIFF PRESS COMP SURGE CNT 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2 | EA | 21 | 4 | 6 | 2 | EA | 25.09 - At KGP | Supply for Order 100044402, Item 1 cannot be changed 180029516 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300002364 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180029516 | 90006485 | 06 | Scheduling | 0000142926 | 1 | 0 | EA | 102000000007342 | 102000000003996 | 102000000007333 |  |  |  | LP-NWS-01 | WorkPackLink | P08YRDBAY6 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 2 | 0 |  |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2024-05-25 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  | 100000013638 | 1020 | 2020-09-04 | 2 |  | 2024-06-19 | 4900076349_2024_0001/4900076188_2024_0001/4900066697_2024_0001 | 2024-05-27 | 414PDT022A | 5000122800_2024_0001 | 0 | 2 | 0 | 90006485 | 2 | 0 | 180029516 | 2 | 0 | 0 | X | L | 4900076349 | 2024 |  | 5000122800 | 2024 | 0 |  | 2024-05-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2024-01-02 | W |  | 0020 | Complete Replacement Needle Valves | INT | Complete Replacement Needle Valves | 2 |  | 90006485_0010 |  |  | LN4 |  | A2 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000142277 | S002 | 30 | 30 | 5300002364 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142926 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100044402 | 0020 | 0030 | 100044402 | LOC Needle Valve Replace (2) 414PDT022 | AA53.414PDT022A | TX,DIFF PRESS COMP SURGE CNT 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2 | EA | 21 | 4 | 6 | 2 | EA | 07.03 - SOH @ AA02 | Supply for Order 100044402, Item 3 cannot be changed 90028428 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002364 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028428 | 06 | Scheduling | 0000142926 | 3 | 0 | EA | 102000000031671 |  | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090028428_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2020-09-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414PDT022A |  | 0 | 2 | 0 | 90028428 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2024-12-13 | W |  | 0020 | Complete Replacement Needle Valves | INT | Complete Replacement Needle Valves | 2 |  | 90028428_0010 |  |  | LN4 |  | C2 |  |  |  | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000142277 | S002 | 30 | 30 | 5300002364 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142926 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDLN1 | Released | 2024-01-02 | 2025-03-01 | 2024-03-01 | 2025-05-31 | 2025-06-01 | QMI | 100047965 | 0010 | 0070 | 100047965 | MOC-141289 Transmitter Replace 144FT84 | AA53.144FT84 | METER,DP FLOW,1V4450 OUTLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 1 | EA | 21 | 4 | 6 | 1 | EA | 29.01 - At KGP | Supply for Order 100047965, Item 7 cannot be changed 180009111 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300001827 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180009111 | 90001493 | 05 | Preparation | 0000146486 | 7 | 0 | EA |  |  | 102000000002682 | 01-Road |  | 3-In Transit |  | WorkPackLink | QMP08CAGE | KCM-LNG | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000030926_2024 | 0 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2025-05-31 |  |  | 2025-03-01 |  |  | 100000002887 | 1020 | 2024-12-30 | 1 |  | 2024-03-06 | 4900035070_2024_0013 | 2024-03-04 | 144FT84 | 5000030926_2024_0001 | 0 | 2 | 0 | 90001493 | 1 | 0 | 180009111 | 2 | 0 | 0 | X | L | 4900035070 | 2024 |  | 5000030926 | 2024 | 0 |  | 2024-03-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2024-01-01 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 2 | Engineering Query/Management of Change | 90001493_0070 |  |  | LN1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 7 |  | 0 | 4900193788_2024 | 25SDLN1 | MJ | 1000000809 | AU1072 | 1000145855 | S002 | 30 | 30 | 5300001827 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-03-01 |  | Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 146486 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-06-01 | 2025-05-31 | 2025-05-31 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Goods movement posted/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100084996 | 0020 | 0010 | 100084996 | Vent Valve Replace 520PT507 | AA53.520PT507 | TX,PRESS HYDRAULIC UNIT OIL SUPPLY | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 1 | EA | 21 | 4 | 6 | 1 | EA | 29.01 - At KGP | Supply for Order 100084996, Item 1 cannot be changed 180100948 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300016552 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180100948 | 90025067 | 05 | Preparation | 0000267393 | 1 | 0 | EA | 102000000025719 |  | 107000000000750 |  |  |  |  | WorkPackLink | P07-WAREHOUSE | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-10-18 | GRST-5000305857_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000044763 | 1020 | 2025-07-31 | 1 |  | 2024-12-04 | 4900185015_2024_0001 | 2025-03-01 | 520PT507 | 5000305857_2024_0001 | 0 | 2 | 0 | 90025067 | 1 | 0 | 180100948 | 2 | 0 | 0 | X | L | 4900185015 | 2024 |  | 5000305857 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025067_0010 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262827 | S002 | 30 | 30 | 5300016552 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267393 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 100084996 | 0020 | 0020 | 100084996 | Vent Valve Replace 520PT507 | AA53.520PT507 | TX,PRESS HYDRAULIC UNIT OIL SUPPLY | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 1 | EA | 21 | 4 | 6 | 1 | EA | 16.12 - SOH @ AA01/AA02 | Supply for Order 100084996, Item 2 cannot be changed 90028433 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016552 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028433 | 05 | Preparation | 0000267393 | 2 | 0 | EA | 102000000031656 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090028433_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520PT507 |  | 0 | 2 | 0 | 90028433 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2024-12-13 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90028433_0010 |  |  | ST5 |  | C1 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000262827 | S002 | 30 | 30 | 5300016552 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267393 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Printed | AM01 | Reactive Maintenance
| 25SDDG1 | Released | 2025-02-08 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | INLEC | 100085112 | 0020 | 0010 | 100085112 | MOC-150252: Flow TX's Repl (2) 44FT21L/H | AA53.44FT21L | TX,FLOW LP FUEL GAS TO HEADER | AA01 | 20 | No issue identified | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2 | EA | 21 | 4 | 6 | 2 | EA | 09.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021006 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030534 | 05 | Preparation | 0000267756 | 1 | 0 | EA | 102000000034140 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-08 | ODST-0090030534_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 44FT21L/H |  | 0 | 2 | 0 | 90030534 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  | Management of Change | 90030534_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000262795 | S002 | 30 | 30 | 5300021006 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W47020 | 2024-09-30 | 267756 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Pre-costed/Object created/Date set by external system/Material committed/Order Approved/Released/Settlement rule created/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1390 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10236512 | ROLLER;NP SMS43028 | 6 | EA | 20 | 0 | 0 | 6 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 181 cannot be changed 90028419 item 1370 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 181 | 0 | EA | 102000000030498 | 102000000030730 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1370 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10236512 | ROLLER;NP SMS43028 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1370 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 181 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1400 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0940 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(10.11.2024) | 10236792 | SEAL,DPM;NP SMR45831 | 52 | EA | 224 | 0 | 0 | 52 | EA | 12.11 - SOH @ AA02 | Supply for Order 200091513, Item 773 cannot be changed 90028419 item 4930 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4970 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 773 | 0 | EA | 102000000030492 | 102000000030122 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 52 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4930 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10236792 | SEAL,DPM;NP SMR45831 | 2024-11-10 | W |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  | 90028419_4930 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 773 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4970 |  |  | 0 | 52 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1500 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(10.11.2024) | 10236792 | SEAL,DPM;NP SMR45831 | 70 | EA | 224 | 0 | 0 | 70 | EA | 12.11 - SOH @ AA02 | Supply for Order 200091513, Item 774 cannot be changed 90028419 item 4940 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4980 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 774 | 0 | EA | 102000000030480 | 102000000030092 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4940 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10236792 | SEAL,DPM;NP SMR45831 | 2024-11-10 | W |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  | 90028419_4940 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 774 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4980 |  |  | 0 | 70 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10237917 | ELEMENT,FLT;HYD,PALL HC9400FRS13Z | 1 | EA | 8 | 0 | 4 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 323 cannot be changed 90028419 item 2510 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2540 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 323 | 0 | EA | 102000000030482 | 102000000030098 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2510 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10237917 | ELEMENT,FLT;HYD,PALL HC9400FRS13Z | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2510 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 323 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2540 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0460 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10238898 | ELEMENT,FLT;OIL,PALL HC0101FRS18H | 4 | EA | 32 | 0 | 0 | 4 | EA | 15.01 - 29 SOH @ AA02 | Supply for Order 200091505, Item 56 cannot be changed 90025019 item 550 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 550 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 56 | 0 | EA | 102000000026766 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealOilFilt |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10238898 | ELEMENT,FLT;OIL,PALL HC0101FRS18H | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0550 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 56 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 | 30 | 30 | 5300015903 | 550 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2370 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10238898 | ELEMENT,FLT;OIL,PALL HC0101FRS18H | 10 | EA | 32 | 0 | 0 | 10 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 341 cannot be changed 90028419 item 2640 already exists | Material picked; currently at SW3R04D02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2670 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 341 | 0 | EA |  |  | 102000000030091 |  |  |  |  | WorkPackLink | SW3R04D02B |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2640 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10238898 | ELEMENT,FLT;OIL,PALL HC0101FRS18H | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2640 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 341 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2670 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-01-21 | 2025-01-31 | 2025-01-26 | 2025-05-19 | 2025-05-19 | MECH | 100090020 | 0010 | 0010 | 100090020 | OPSD 3K10 Water wash leak in compartment | AA53.3KT1410 | TURB,DRIVER FOR 3K1410 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(09.01.2025) | 10240426 | TEE,TUBE;3/8",316SS,SWAG SS6003 | 5 | EA | 4 | 0 | 5 | 1 | EA | 10.03 - AT AA53 | Supply for Order 100090020, Item 1 cannot be changed 180114595 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300019871 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180133419 | 9028832 | 05 | Preparation | 0000288931 | 1 | 0 | EA |  |  | 102000000034364 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P08-CAMP-SML | AA53-P08-OPSD | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-10 | GRST-5000431698_2025 | 0 | 0 | 0 | 0 |  | 2025-01-29 | AA53 | 2025-05-19 |  |  | 2025-01-31 |  |  | 100000060513 | 1020 | 2025-12-31 | 5 |  | 2025-03-07 | 4900260342_2025_0001/4900209822_2025_0001 | 2025-01-31 | 100090020 | 5000431698_2025_0001/5000357297_2025_0001 | 0 | 2 | 0 | 90028341 | 5 | 0 | 180133419/180114595/180133418 | 2 | 0 | 0 | X | L | 4900260342 | 2025 |  | 5000431698 | 2025 | 0 |  | 2025-01-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10240426 | TEE,TUBE;3/8",316SS,SWAG SS6003 | 2025-01-09 | W |  | 0010 | OPSD 3K10 Water wash leak in compartment | INT | OPSD 3K10 Water wash leak in compartment |  | Opportune Shutdown | 9028832_0010/9024352_0010 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDLN3 | MJ | 1000005344 | AU1072 | 1000282915 | S002 | 30 | 30 | 5300019871 | 10 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-01-26 |  | Opportune Shutdown | 2025-03-10 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41088 | 2025-01-05 | 288931 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-19 | 2025-05-19 | 2025-05-19 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-01-21 | 2025-01-31 | 2025-01-26 | 2025-05-19 | 2025-05-19 | MECH | 100090020 | 0010 | 0010 | 100090020 | OPSD 3K10 Water wash leak in compartment | AA53.3KT1410 | TURB,DRIVER FOR 3K1410 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(09.01.2025) | 10240426 | TEE,TUBE;3/8",316SS,SWAG SS6003 | 5 | EA | 4 | 0 | 5 | 4 | EA | 10.03 - AT AA53 | Supply for Order 100090020, Item 1 cannot be changed 180114595 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300019871 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180133419 | 9028832 | 05 | Preparation | 0000288931 | 1 | 0 | EA |  |  | 102000000030037 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P08-CAMP-SML | AA53-P08-OPSD | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-10 | GRST-5000431698_2025 | 0 | 0 | 0 | 0 |  | 2025-01-29 | AA53 | 2025-05-19 |  |  | 2025-01-31 |  |  | 100000060513 | 1020 | 2025-12-31 | 5 |  | 2025-03-07 | 4900260342_2025_0001/4900209822_2025_0001 | 2025-01-31 | 100090020 | 5000431698_2025_0001/5000357297_2025_0001 | 0 | 2 | 0 | 90028341 | 5 | 0 | 180133419/180114595/180133418 | 2 | 0 | 0 | X | L | 4900260342 | 2025 |  | 5000431698 | 2025 | 0 |  | 2025-01-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10240426 | TEE,TUBE;3/8",316SS,SWAG SS6003 | 2025-01-09 | W |  | 0010 | OPSD 3K10 Water wash leak in compartment | INT | OPSD 3K10 Water wash leak in compartment |  | Opportune Shutdown | 9028832_0010/9024352_0010 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDLN3 | MJ | 1000004722 | AU1072 | 1000282915 | S002 | 30 | 30 | 5300019871 | 10 |  |  | 0 | 5 | EA | 2001 | AA02 | 2025-01-26 |  | Opportune Shutdown | 2025-01-14 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41088 | 2025-01-05 | 288931 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-19 | 2025-05-19 | 2025-05-19 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material committed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-11 | 2025-02-24 | 2025-03-27 | 2025-02-24 | 2025-04-17 | NOMAINT | 500004676 | 0070 | 0020 | 500004676 | 25SD SITE LOGISITICS & HIRE GEAR WIN1 | AA53.1000 | KGP Non-Maintenance | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(12.02.2025) | 10241039 | WHIPCHECK;HOSE CPLG,23/90,10-32MM,SML | 40 | EA | 40 | 0 | 0 | 40 | EA | 02.03 - SOH @ AA02 | Supply for Order 500004676, Item 2 cannot be changed 90031855 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021195 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031855 | 07 | Execution | 0000278102 | 2 | 0 | EA | 101000000149760 |  | 101000000149860 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | KGP P-07 | 0 |  | 0 | 0 |  | 0 | 40 |  | 2025-03-02 | Y | 1001 | 2025-02-12 | ODST-0090031855_0020 | 0 | 36 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-02-24 |  |  | 2025-04-01 |  |  |  |  | 2025-12-31 | 0 |  | 2025-03-27 |  | 2025-04-01 | TA OPS/BAILS |  | 0 | 2 | 0 | 90031855 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241039 | WHIPCHECK;HOSE CPLG,23/90,10-32MM,SML | 2025-02-12 | W |  | 0070 | Crane support maintenance team | INT | Crane support maintenance team |  |  | 90031855_0020 | [8 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 2 |  | 0 |  | 25SDENA1 | MJ | 20005413 | AU1072 | 1000272560 | S002 | 30 | 30 | 5300021195 | 20 |  |  | 0 | 40 | EA | 2001 | AA02 | 2025-03-27 |  |  | 2025-02-28 |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-17 | 278102 | 0 | 0 |  | 1020 | 1 |  |  | 3 | High | RC00025003 | 2025-04-17 | 2025-02-24 | 2025-02-24 | Pre-costed/Object created/Date set by external system/Released/Settlement rule created/Material shortage/Partially confirmed | AM05 | Non-Execution | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0180 | 2490 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241080 | SCREW,CAP;0.375"X50MM,NP HEF09050 | 10 | EA | 10 | 0 | 0 | 10 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 538 cannot be changed 90028419 item 3900 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3930 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 538 | 0 | EA | 102000000030495 | 102000000030200 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3900 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241080 | SCREW,CAP;0.375"X50MM,NP HEF09050 | 2024-07-21 | W |  | 0180 | LOAD & ACCESSORY COUPLING GUARDS | INT | LOAD & ACCESSORY COUPLING GUARDS | 5 |  | 90028419_3900 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 538 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3930 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0090 | 1570 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241087 | SPACER;NP SMP40046 | 32 | EA | 32 | 0 | 0 | 32 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 199 cannot be changed 90028419 item 1550 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1580 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 199 | 0 | EA | 102000000030498 | 102000000030667 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1550 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241087 | SPACER;NP SMP40046 | 2024-07-21 | W |  | 0090 | 2ND STAGE NOZZLE | INT | 2ND STAGE NOZZLE | 5 |  | 90028419_1550 |  |  | DG1 |  | A3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 199 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 1580 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100043726 | 0010 | 0020 | 100043726 | Accelerometer Replace 123XT105 1K2301 | AA53.123XT105 | TXDCR,ACCELEROMETER 1K2301 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR | 1 | EA | 2 | 0 | 0 | 0 |  | 31.01 - SOH @ AA02 | Supply for Order 100043726, Item 1 cannot be changed 90024944 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001396 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024944 | 05 | Preparation | 0000142227 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024944_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123XT105 |  | 0 | 2 | 0 | 90024944 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR | 2024-01-01 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90024944_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000141596 | S002 |  | 30 | 5300001396 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100043726 | 0010 | 0050 | 100043726 | Accelerometer Replace 123XT105 1K2301 | AA53.123XT105 | TXDCR,ACCELEROMETER 1K2301 | AA01 | 30 | No issue identified | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR | 2 | EA | 2 | 0 | 0 | 0 |  | 30.01 - ETA 10.03.25 PO 4500043644 ex NSK |  | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001396 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030038 | 05 | Preparation | 0000142227 | 5 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030038_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123XT105 |  | 0 | 2 | 0 | 90030038 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90030038_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 5 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000141596 | S002 |  | 30 | 5300001396 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-03 | INLEC | 200146425 | 0020 | 0020 | 200146425 | 5Y SVC 5KM2001 MOTOR MAJOR LABOUR 2HF1 | AA53.5KM2001 | MOTOR,HV,MAIN,STABILIZER COMP,5K2001 | AA01 | 20 | No issue identified | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR | 1 | EA | 2 | 0 | 0 | 0 |  | 03.02 - ETA 07.03.25 PO 4500043502 NSK CPT |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020687 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030061 | 05 | Preparation | 0000234302 | 2 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-31 | ODST-0090030061_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-28 |  |  | 2025-03-01 |  |  |  |  | 2025-12-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520XT105 |  | 0 | 2 | 0 | 90030061 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90030061_0020 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231258 | S002 |  | 30 | 5300020687 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-22 | 234302 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146445 | 0020 | 0030 | 200146445 | 6Y Vibration Probes Replace (4) - 5K2001 | AA53.520XT101 | TXDCR,ACCELEROMETER CYL 1 IMPACT 5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR | 1 | EA | 2 | 0 | 0 | 0 |  | 03.02 - ETA 07.03.25 PO 4500043502 NSK CPT | Supply for Order 200146445, Item 3 cannot be changed 90030048 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017922 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030048 | 05 | Preparation | 0000234322 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-15 | ODST-0090030048_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5K2001 |  | 0 | 2 | 0 | 90030048 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR | 2025-01-30 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90030048_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231378 | S002 |  | 30 | 5300017922 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234322 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146445 | 0010 | 0010 | 200146445 | 6Y Vibration Probes Replace (4) - 5K2001 | AA53.520XT101 | TXDCR,ACCELEROMETER CYL 1 IMPACT 5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.11.2024) | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR | 1 | EA | 2 | 0 | 0 | 1 | EA | 18.11 - SOH @ AA02 | Supply for Order 200146445, Item 1 cannot be changed 90025114 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017922 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025114 | 05 | Preparation | 0000234322 | 1 | 0 | EA | 102000000028899 | 101000000131630 | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-15 | ODST-0090025114_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5K2001 |  | 0 | 2 | 0 | 90025114 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241112 | AMPLIFIER;CHARGE,5704 ACLRMTR | 2024-11-14 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90025114_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231378 | S002 |  | 30 | 5300017922 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234322 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100043726 | 0010 | 0012 | 100043726 | Accelerometer Replace 123XT105 1K2301 | AA53.123XT105 | TXDCR,ACCELEROMETER 1K2301 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 | 1 | EA | 2 | 0 | 0 | 0 |  | 30.01 - ETA 28.02.25 PO 4500041546 x qty 1 ex NSK | Supply for Order 100043726, Item 3 cannot be changed 90024944 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001396 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024944 | 05 | Preparation | 0000142227 | 3 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024944_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123XT105 |  | 0 | 2 | 0 | 90024944 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 | 2024-01-01 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90024944_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 3 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000141596 | S002 | 30 | 30 | 5300001396 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 100043726 | 0010 | 0060 | 100043726 | Accelerometer Replace 123XT105 1K2301 | AA53.123XT105 | TXDCR,ACCELEROMETER 1K2301 | AA01 | 30 | No issue identified | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 | 2 | EA | 2 | 0 | 0 | 0 |  | 03.02 - ETA 11.04.25 PO 4500044573 NSK CPT |  | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001396 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030038 | 05 | Preparation | 0000142227 | 6 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030038_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2021-12-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 123XT105 |  | 0 | 2 | 0 | 90030038 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90030038_0020 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 6 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000141596 | S002 | 30 | 30 | 5300001396 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Part printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-03 | INLEC | 200146425 | 0020 | 0010 | 200146425 | 5Y SVC 5KM2001 MOTOR MAJOR LABOUR 2HF1 | AA53.5KM2001 | MOTOR,HV,MAIN,STABILIZER COMP,5K2001 | AA01 | 20 | No issue identified | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 | 1 | EA | 2 | 0 | 0 | 0 |  | 18.02 - SOH @ AA02 |  | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020687 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030061 | 05 | Preparation | 0000234302 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-31 | ODST-0090030061_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-28 |  |  | 2025-03-01 |  |  |  |  | 2025-12-04 | 0 |  | 2025-02-24 |  | 2025-03-01 | 520XT105 |  | 0 | 2 | 0 | 90030061 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90030061_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231258 | S002 | 30 | 30 | 5300020687 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-22 | 234302 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146445 | 0020 | 0020 | 200146445 | 6Y Vibration Probes Replace (4) - 5K2001 | AA53.520XT101 | TXDCR,ACCELEROMETER CYL 1 IMPACT 5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.11.2024) | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 | 1 | EA | 2 | 0 | 0 | 2 | EA | 18.02 - SOH @ AA02 | Supply for Order 200146445, Item 2 cannot be changed 90025114 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017922 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025114 | 05 | Preparation | 0000234322 | 2 | 0 | EA | 101000000142718 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-15 | ODST-0090025114_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5K2001 |  | 0 | 2 | 0 | 90025114 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 | 2024-11-14 | W |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90025114_0020 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231378 | S002 | 30 | 30 | 5300017922 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234322 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200146445 | 0010 | 0020 | 200146445 | 6Y Vibration Probes Replace (4) - 5K2001 | AA53.520XT101 | TXDCR,ACCELEROMETER CYL 1 IMPACT 5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(30.01.2025) | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 | 1 | EA | 2 | 0 | 0 | 0 |  | 03.02 - ETA 11.04.25 PO 4500044573 NSK CPT | Supply for Order 200146445, Item 4 cannot be changed 90030048 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017922 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030048 | 05 | Preparation | 0000234322 | 4 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-15 | ODST-0090030048_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | 5K2001 |  | 0 | 2 | 0 | 90030048 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241113 | ACCELEROMETER;EEX,BRUEL 5704W1402A0100 | 2025-01-30 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90030048_0020 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231378 | S002 | 30 | 30 | 5300017922 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234322 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-06 | ROTAT | 100046308 | 0040 | 0020 | 100046308 | MOC-52386 - Tank Min Oil Replace - G4008 | AA53.G4008V1 | TANK,MINERAL OIL RESERVOIR G4008 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10241666 | ELEMENT,FLT;OIL,3UM,PALL HC8400FRP16Z | 2 | EA | 12 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 100046308, Item 2 cannot be changed 90024955 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300002735 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024955 | 05 | Preparation | 0000144829 | 2 | 0 | EA | 102000000026763 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024955_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2020-06-25 | 0 |  | 2025-02-24 |  | 2025-03-01 | MLO FILTER |  | 0 | 2 | 0 | 90024955 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241666 | ELEMENT,FLT;OIL,3UM,PALL HC8400FRP16Z | 2024-01-02 | W |  | 0040 | Fill MLO tank & carry out flush-3 micron | INT | Fill MLO tank & carry out flush-3 micron | 5 |  | 90024955_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000144178 | S002 | 30 | 30 | 5300002735 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144829 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-06 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Estimated costs | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0730 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 1 | EA | 19 | 0 | 1 | 1 | EA | 29.01 - At KGP | Supply for Order 200091505, Item 79 cannot be changed 180096108 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 760 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096108 | 9019486 | 05 | Preparation | 0000129754 | 79 | 0 | EA | 102000000024268 |  | 107000000000760 |  |  |  |  | WorkPackLink | 2025-SD-MATERIALS | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000287602_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000041869 | 1020 | 2025-06-05 | 1 |  | 2024-11-21 | 4900176193_2024_0001 | 2025-03-01 | LOFilter | 5000287602_2024_0001 | 0 | 2 | 0 | 90025019 | 1 | 0 | 180096108 | 2 | 0 | 0 | X | L | 4900176193 | 2024 |  | 5000287602 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 9019486_0760 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 79 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 760 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0470 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 4 | EA | 19 | 0 | 1 | 4 | EA | 15.01 - KSF Work-packed | Supply for Order 200091505, Item 57 cannot be changed 90025019 item 560 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 560 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 57 | 0 | EA | 102000000028379 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0560 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | SealOilFilt |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0560 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 57 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 560 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0720 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 3 | EA | 19 | 0 | 1 | 3 | EA | 15.01 - KSF Work-packed | Supply for Order 200091505, Item 78 cannot be changed 90025019 item 750 already exists | Material picked; currently at SW3R01B01B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 78 | 0 | EA | 102000000028470 |  | 102000000026659 |  |  |  |  | WorkPackLink | SW3R01B01B | P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0750 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | LOFilter |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0750 |  |  | FR1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 78 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 750 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 10 | EA | 19 | 0 | 1 | 4 | EA | 15.01 - SOH @ AA02 | Supply for Order 200091513, Item 338 cannot be changed 90028419 item 2620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 338 | 0 | EA | 101000000136722 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2620 |  |  | DG1 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 338 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2650 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 10 | EA | 19 | 0 | 1 | 3 | EA | 15.01 - SOH @ AA02 | Supply for Order 200091513, Item 338 cannot be changed 90028419 item 2620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 338 | 0 | EA | 102000000032937 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2620 |  |  | DG1 |  | C1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 338 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2650 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 10 | EA | 19 | 0 | 1 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200091513, Item 338 cannot be changed 90028419 item 2620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 338 | 0 | EA | 101000000136856 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2620 |  |  | DG1 |  | A1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 338 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2650 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0170 | 2330 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 10 | EA | 19 | 0 | 1 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200091513, Item 338 cannot be changed 90028419 item 2620 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2650 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 338 | 0 | EA | 102000000030093 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2620 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241667 | ELEMENT,FLT;OIL,PALL HC0101FRP18Z | 2024-07-21 | W |  | 0170 | FILTERS | INT | FILTERS | 5 |  | 90028419_2620 |  |  | DG1 |  | C5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 338 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2650 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0220 | 2550 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241837 | TAPE,GASKET,INS,75MM X 3MM X 30M,CER FIB | 2 | ROL | 4 | 0 | 0 | 2 | ROL | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 561 cannot be changed 90028419 item 4060 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4090 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 561 | 0 | ROL | 102000000030900 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241837 | TAPE,GASKET,INS,75MM X 3MM X 30M,CER FIB | 2024-07-21 | W |  | 0220 | EXHAUST PLENUM ASSEMBLY | INT | EXHAUST PLENUM ASSEMBLY | 5 |  | 90028419_4060 |  |  | DG1 |  | B1 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 561 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4090 |  |  | 0 | 2 | ROL | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1750 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241838 | GASKET;TAPE,60X3MM,30M RL,CER FIB,INS | 2 | ROL | 8 | 0 | 0 | 2 | ROL | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 242 cannot be changed 90028419 item 1850 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 1880 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 242 | 0 | ROL | 102000000030213 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_1850 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241838 | GASKET;TAPE,60X3MM,30M RL,CER FIB,INS | 2024-07-21 | W |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  | 90028419_1850 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 242 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 1880 |  |  | 0 | 2 | ROL | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241914 | ELEMENT,FLT;HYD,PALL HC9021FDP4H | 1 | EA | 10 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 706 cannot be changed 90028419 item 4710 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4750 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 706 | 0 | EA | 102000000030501 | 102000000030673 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_4710 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241914 | ELEMENT,FLT;HYD,PALL HC9021FDP4H | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_4710 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 706 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 4750 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 1920 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10241915 | STEM,VV;CMA 9500A017P0W1 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 272 cannot be changed 90028419 item 2110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 272 | 0 | EA | 102000000030971 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | ONCONDITION |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10241915 | STEM,VV;CMA 9500A017P0W1 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_2110 |  |  | DG1 |  | B3 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 272 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2140 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-03-01 | MECH | 100087299 | 0230 | 0010 | 100087299 | MOC-123256 Repl Spool section - GT4009V6 | AA53.GT4009V6 | VE,GT4009 CO2 LOW PRESSURE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10242462 | INSULATION;PIPE SECTION,NILFLAM PIR | 2 | EA | 0 | 0 | 0 | 0 |  | 13.02 - ETA 28.02.25 PO 4500045300 ex Pyrotek | Supply for Order 100087299, Item 15 cannot be changed 90029086 item 10 already exists | Shipping notification from Vendor received | SP97 | Direct Multi-base | 30 | AA01 | 5300020056 | 10 | CPT | 7 | 1000027871 | 15 | 30003074 | PYROTEK PTY LTD ROBBINS INDUSTRIAL SERVICES | 4500045300 | 30 | 2 | EA | 2025-02-28 |  | 180132942/ |  | 90029086 | 05 | Preparation | 0000277133 | 15 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090029086_0010 | 0 | 10 | 10 | 10 | 2025-02-20 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-03-11 | 2025-02-22 | 2025-03-06 |  |  | 2026-12-18 | 0 |  | 2025-02-12 |  | 2025-02-24 | TA LAG _ SUP |  | 0 | 2 | 2 | 90029086 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 | 180132942 | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242462 | INSULATION;PIPE SECTION,NILFLAM PIR | 2025-01-14 | W |  | 0230 | Install Insulation/Toughskin | INT | Install Insulation/Toughskin |  | Management of Change | 90029086_0010 |  |  | UT1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-01-15 | 5 | 6000014459 | 2025-02-22 | 0 |  | 0 |  | 25SDGT9 | MJ |  | AU1009 | 1000271703 | S001 | 30 | 30 | 5300020055 | 60 |  | 5300020056 | 10 | 2 | EA | 1001 | AA02 | 2025-02-12 |  | Management of Change |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-14 | 0 | 0 | 0 |  | 1010 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0200 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10242467 | FOAM;LIQ ISOCYANATE;250KG,ARIEL B9001 | 750 | KG | 0 | 0 | 1000 | 0 |  | 24.02 - ETA 20.03.25 PO 4500047054 ERA FCA | Supply for Order 100090053, Item 20 cannot be changed 90032376 item 200 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | KG |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 20 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 750 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0200 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242467 | FOAM;LIQ ISOCYANATE;250KG,ARIEL B9001 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0200 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 20 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 200 |  |  | 0 | 750 | KG | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0050 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10242467 | FOAM;LIQ ISOCYANATE;250KG,ARIEL B9001 | 920 | KG | 0 | 0 | 1000 | 0 |  | 24.02 - ETA 31.03.25 PO 4500047054 ERA FCA | Supply for Order 500005166, Item 24 cannot be changed 90031501 item 70 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | KG |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 24 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 920 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0070 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242467 | FOAM;LIQ ISOCYANATE;250KG,ARIEL B9001 | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0070 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 24 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 210 |  |  | 0 | 920 | KG | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0190 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10242468 | FOAM,POLYOL;230KG DRM,ARIEL DP9505POLYOL | 690 | KG | 0 | 0 | 230 | 0 |  | 07.03 - PR 2000283129 | Supply for Order 100090053, Item 19 cannot be changed 90032376 item 190 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | KG |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 19 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 690 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0190 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242468 | FOAM,POLYOL;230KG DRM,ARIEL DP9505POLYOL | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0190 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 19 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 190 |  |  | 0 | 690 | KG | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0150 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10242497 | TAPE:ADHESIVE,INS,50X3X9.14MM,ARMACELL | 5 | ROL | 11 | 0 | 56 | 0 |  | 07.03 - SOH @ AA02 | Supply for Order 100090053, Item 15 cannot be changed 90032376 item 150 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 15 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0150 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242497 | TAPE:ADHESIVE,INS,50X3X9.14MM,ARMACELL | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0150 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 15 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 |  | 30 | 5300022012 | 150 |  |  | 0 | 5 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0090 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10242497 | TAPE:ADHESIVE,INS,50X3X9.14MM,ARMACELL | 20 | ROL | 11 | 0 | 56 | 20 | ROL | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 29 cannot be changed 9028446 item 110 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132204 | 9028446 | 05 | Preparation | 0000294187 | 29 | 0 | ROL |  |  | 102000000034142 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427504 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 |  |  | 100000060207 | 1020 |  | 20 |  | 2025-03-05 | 4900257428_2025_0005 | 2025-04-01 | TA LAG_VORN | 5000427504_2025_0003 | 0 | 2 | 0 | 90031501 | 20 | 0 | 180132204 | 2 | 0 | 0 | X | L | 4900257428 | 2025 |  | 5000427504 | 2025 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242497 | TAPE:ADHESIVE,INS,50X3X9.14MM,ARMACELL | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 9028446_0110 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 29 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 |  | 30 | 5300021227 | 250 |  |  | 0 | 20 | ROL | 2001 | AA02 | 2025-03-27 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0150 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10242498 | BANDING,SS316,12MM X 0.55MM THK | 52 | KG | 64 | 0 | 20 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 35 cannot be changed 90031501 item 170 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | KG |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 35 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 52 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0170 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242498 | BANDING,SS316,12MM X 0.55MM THK | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0170 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 35 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 |  | 30 | 5300021227 | 310 |  |  | 0 | 52 | KG | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0160 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10242500 | SEAL,BANDING,SS316,12MM | 1000 | EA | 1699 | 0 | 821 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 36 cannot be changed 90031501 item 180 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 36 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1000 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0180 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242500 | SEAL,BANDING,SS316,12MM | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0180 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 36 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 320 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0140 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10242501 | SEAL,BANDING;INS,SS316L,19MM | 1000 | EA | 3040 | 600 | 1916 | 0 |  | 06.03 - SOH @ AA02 | Supply for Order 100090053, Item 14 cannot be changed 90032376 item 140 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 14 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1000 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0140 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242501 | SEAL,BANDING;INS,SS316L,19MM | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0140 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 14 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 140 |  |  | 0 | 1000 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0040 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10242501 | SEAL,BANDING;INS,SS316L,19MM | 200 | EA | 3040 | 600 | 1916 | 200 | EA | Workpacked at KGP | Supply for Order 200089373, Item 4 cannot be changed 180091768 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180091768 | 9019016 | 07 | Execution | 0000127667 | 4 | 0 | EA |  |  | 102000000023517 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-KGP-RUNNER-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000275115_2024 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000040386 | 1020 | 2025-12-15 | 200 |  | 2024-11-11 | 4900169565_2024_0007 | 2024-11-10 | Troy Mac | 5000275115_2024_0001 | 0 | 2 | 0 | 90023594 | 200 | 0 | 180091768 | 2 | 0 | 0 | X | L | 4900169565 | 2024 |  | 5000275115 | 2024 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242501 | SEAL,BANDING;INS,SS316L,19MM | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9019016_0040 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDFR2 | MJ | 1000004072 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 40 |  |  | 0 | 200 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0180 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10242501 | SEAL,BANDING;INS,SS316L,19MM | 1500 | EA | 3040 | 600 | 1916 | 0 |  | 20.02 - SOH @ AA02 | Supply for Order 500005166, Item 38 cannot be changed 90031501 item 200 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 38 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1500 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0200 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242501 | SEAL,BANDING;INS,SS316L,19MM | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0200 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 38 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 340 |  |  | 0 | 1500 | EA | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1940 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10242957 | PIN,CYL,HYD;NP DRAWINGSM01726372ITEM43 | 2 | EA | 2 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 268 cannot be changed 90028419 item 2070 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 268 | 0 | EA | 102000000030504 | 102000000030167 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242957 | PIN,CYL,HYD;NP DRAWINGSM01726372ITEM43 | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2070 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 268 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 2100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR0 | Released | 2024-11-20 | 2025-03-01 | 2025-05-09 | 2025-05-14 | 2025-05-18 | VALVE | 200085979 | 0010 | 0070 | 200085979 | 2Y HYD Package F/Test - A1890 | AA53.A1890 | PANEL,PWR PK FOR 3 HYD VLVS EX V1800 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(20.11.2024) | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 | 1 | EA | 6 | 0 | 4 | 1 | EA | 21.11 - SOH @ AA02 | Supply for Order 200085979, Item 7 cannot be changed 90025121 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018160 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025121 | 05 | Preparation | 0000124257 | 7 | 0 | EA | 102000000032090 | 102000000025267 | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-20 | ODST-0090025121_0070 | 0 | 74 | 0 | 0 |  | 2025-05-12 | AA53 | 2025-05-14 |  |  | 2025-05-14 |  |  |  |  | 2025-06-30 | 0 |  | 2025-05-09 |  | 2025-05-14 |  |  | 0 | 2 | 0 | 90025121 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 | 2024-11-20 | W |  | 0010 | Function Test & Complete PRT | INT | Function Test & Complete PRT | 5 | Ready for Release | 90025121_0070 |  |  | FR0 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDFR0 | MJ |  | AU1072 | 1000123668 | S002 | 30 | 30 | 5300018160 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-05-09 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124257 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-18 | 2025-05-14 | 2025-05-14 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 200146440 | 0010 | 0110 | 200146440 | 1Y HYD PKG F/Test - 5A2090 | AA53.5A2090 | PKG EQ,PWR PK ESD VLV 520HYD71/2/3/4/80 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(08.11.2024) | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 | 1 | EA | 6 | 0 | 4 | 1 | EA | 12.11 - SOH @ AA02 | Supply for Order 200146440, Item 11 cannot be changed 90025098 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300017633 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025098 | 05 | Preparation | 0000234317 | 11 | 0 | EA | 102000000026764 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-08 | ODST-0090025098_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-11-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025098 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 | 2024-11-08 | W |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | Ready for Release | 90025098_0110 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 11 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000231373 | S002 | 30 | 30 | 5300017633 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-23 | 234317 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0060 | 0930 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10244172 | RING,SUPP;NP SM01734348 | 1 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  |  |  | 05 | Preparation | 0000129822 | 743 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10244172 | RING,SUPP;NP SM01734348 |  |  |  | 0060 | 1ST STAGE NOZZLE & SUPPORT RING | INT | 1ST STAGE NOZZLE & SUPPORT RING | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-12-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | VALVE | 100032671 | 0010 | 0010 | 100032671 | CV-OH 1" 300# 118TCV503 | AA53.118TCV503 | VALVE,K1820E1 S/OIL COOLER BYPASS TEMP | AA01 | 20 | No issue identified | 10245403 | MAINT KIT;FISHER RGLX0000012 | 1 | KIT | 4 | 0 | 0 | 1 | KIT | 18.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019089 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028287 | 05 | Preparation | 0000131163 | 1 | 0 | KIT | 102000000033430 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-12 | ODST-0090028287_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032671 |  | 0 | 2 | 0 | 90028287 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245403 | MAINT KIT;FISHER RGLX0000012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028287_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130513 | S002 |  | 30 | 5300019089 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131163 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-31 | 2025-03-26 | 2025-03-01 | 2025-05-15 | VALVE | 100032672 | 0010 | 0010 | 100032672 | CV-OH 1" 300# 118LCV505 | AA53.118LCV505 | VALVE,S/OIL O/H TK 1K1820V1 LVL CTRL | AA01 | 20 | No Issue identified | 10245403 | MAINT KIT;FISHER RGLX0000012 | 1 | KIT | 4 | 0 | 0 | 1 | KIT | 25.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019173 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028288 | 05 | Preparation | 0000131164 | 1 | 0 | KIT | 102000000033491 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028288_0010 | 0 | 0 | 0 | 0 |  | 2025-03-29 | AA53 | 2025-03-01 |  |  | 2025-03-31 |  |  |  |  | 2025-06-02 | 0 |  | 2025-03-26 |  | 2025-03-31 | 118LCV505 |  | 0 | 2 | 0 | 90028288 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-26 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245403 | MAINT KIT;FISHER RGLX0000012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028288_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130514 | S002 |  | 30 | 5300019173 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-03-26 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131164 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | VALVE | 100032674 | 0010 | 0010 | 100032674 | CV-OH 1" 300# 118LCV510 | AA53.118LCV510 | VALVE,S/OIL DRN POT K1820V4B LOCAL LVL | AA01 | 20 | No issue identified | 10245403 | MAINT KIT;FISHER RGLX0000012 | 1 | KIT | 4 | 0 | 0 | 1 | KIT | 19.02 - SOH @AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019174 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028290 | 05 | Preparation | 0000131166 | 1 | 0 | KIT | 101000000146140 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028290_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032674 |  | 0 | 2 | 0 | 90028290 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245403 | MAINT KIT;FISHER RGLX0000012 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028290_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130516 | S002 |  | 30 | 5300019174 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131166 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-02-28 | 2025-03-01 | VALVE | 100032675 | 0010 | 0050 | 100032675 | CV-OH 1" 300# 118PCV505 | AA53.118PCV505 | VALVE,1K1820 BUFFER GAS SUPPL PRESS CTRL | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(15.12.2024) | 10245403 | MAINT KIT;FISHER RGLX0000012 | 1 | KIT | 4 | 0 | 0 | 1 | KIT | 18.02 - SOH @ AA02 | Supply for Order 100032675, Item 9 cannot be changed 90028291 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019175 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90028291 | 05 | Preparation | 0000131167 | 9 | 0 | KIT | 101000000147036 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028291_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100032675 |  | 0 | 2 | 0 | 90028291 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245403 | MAINT KIT;FISHER RGLX0000012 | 2024-12-15 | W |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028291_0030 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130517 | S002 |  | 30 | 5300019175 | 30 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131167 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | WORK | 200059456 | 0080 | 0010 | 200059456 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.520RV02 | PSV,5P20040 FROM 5K2001 |  | 10 | No issue identified | 10245534 | VALVE RLF:CONVENTIONAL | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 05 | Preparation | 0000093805 | 4 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-31 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 30POST | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245534 | VALVE RLF:CONVENTIONAL |  |  |  | 0080 | Return PSV To Warehouse | INT | Return PSV To Warehouse |  | Ready for Release |  |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000093175 |  | 30 |  |  | 0 |  |  | 0 | 0 | [5 empty] | Ready for Release |  |  | 1070 |  | 2025-01-15 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed/Partially confirmed | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-01-02 | 2025-01-15 | 2025-02-07 | 2025-03-01 | 2025-03-01 | WORK | 200059456 | 0010 | 0010 | 200059456 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.520RV02 | PSV,5P20040 FROM 5K2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.01.2024) | 10245534 | VALVE RLF:CONVENTIONAL | 1 | EA | 0 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA03 | Supply for Order 200059456, Item 5 cannot be changed 90025123 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA03 | 5300004999 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  | 180116045 | 90025123 | 05 | Preparation | 0000093805 | 5 | 0 | EA |  |  | 119000000003827 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08WHSFLR |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-01-17 |  | 0 | 45 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-01-15 |  |  | 2025-03-01 |  |  | 100000011969 | 1190 | 2025-07-31 | 1 |  | 2025-01-17 | 4900212587_2025_0001 | 2025-03-01 |  | 5000376025_2025_0001 | 0 | 2 | 0 | 90025123 | 1 | 0 | 180116045 | 2 | 0 | 0 | X | L | 4900212587 | 2025 |  | 5000376025 | 2025 | 0 |  | 2025-02-07 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245534 | VALVE RLF:CONVENTIONAL | 2024-01-17 | W |  | 0010 | Certify PSV | INT | Certify PSV |  | Ready for Release | 90025123_0010 |  |  | ST5 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDSTB5 | MJ | 20004268 | AU1098 | 1000093175 | S003 | 30 | 30 | 5300004999 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2025-02-07 |  | Ready for Release |  |  | 1070 |  | 2025-01-15 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 93805 | 0 | 0 |  | 1190 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed/Partially confirmed | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-01-29 | 2025-02-07 | 2025-03-01 | 2025-03-01 | WORK | 200055989 | 0010 | 0010 | 200055989 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.118RV13 | PSV,1V1805 ON 2" LINE 1W41534 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.01.2024) | 10245543 | VALVE,REL,FUKUI,REC371-(A)1D2,4000-5000 | 1 | EA | 2 | 0 | 0 | 1 | EA | 02.10 - SOH @ AA03 | Supply for Order 200055989, Item 5 cannot be changed 180115174 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA03 | 5300004967 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  | 180115174 | 90025122 | 07 | Execution | 0000090304 | 5 | 0 | EA |  |  | 119000000002033 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08WHSFLR |  | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-01-17 |  | 0 | 31 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-01-29 |  |  | 2025-03-01 |  |  | 100000011833 | 1190 | 2025-07-31 | 1 |  | 2025-01-15 | 4900210899_2025_0001 | 2025-03-01 |  | 5000382268_2025_0001 | 0 | 2 | 0 | 90025122 | 1 | 0 | 180115174 | 2 | 0 | 0 | X | L | 4900210899 | 2025 |  | 5000382268 | 2025 | 0 |  | 2025-02-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245543 | VALVE,REL,FUKUI,REC371-(A)1D2,4000-5000 | 2024-01-17 | W |  | 0010 | Certify PSV | ENON | Certify PSV |  | Ready for Release | 90025122_0010 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDFR1 | MJ | 20004472 | AU1098 | 1000089708 | S003 | 30 | 30 | 5300004967 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2025-02-07 |  | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 90304 | 0 | 0 |  | 1190 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | WORK | 200055989 | 0060 | 0010 | 200055989 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.118RV13 | PSV,1V1805 ON 2" LINE 1W41534 |  | 10 | No issue identified | 10245543 | VALVE,REL,FUKUI,REC371-(A)1D2,4000-5000 | -1 | EA | 0 | 0 | 0 | 0 |  | Refurb |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | DAMAGED |  |  |  | 07 | Execution | 0000090304 | 4 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2025-07-31 | 0 |  |  |  |  | 200055989 |  | 0 | 0 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245543 | VALVE,REL,FUKUI,REC371-(A)1D2,4000-5000 |  |  |  | 0060 | Return PSV To Stock | ENON | Return PSV To Stock |  | Ready for Release |  |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) | ZBPM0002 | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDFR1 | MJ |  |  | 1000089708 |  | 30 |  |  | 0 |  |  | 0 | 0 | [5 empty] | Ready for Release |  |  | 1070 |  | 2025-01-29 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0100 | 1560 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10245896 | BEARING,STD;NP SM01515100 | 1 | EA | 0 | 0 | 1 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 652 cannot be changed 9027132 item 4380 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124220 | 9027132 | 05 | Preparation | 0000129822 | 652 | 0 | EA |  |  | 102000000030735 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000396403_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056767 | 1020 | 2025-07-03 | 1 |  | 2025-02-11 | 4900234166_2025_0003 | 2025-03-01 |  | 5000396403_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180124220 | 2 | 0 | 0 | X | L | 4900234166 | 2025 |  | 5000396403 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245896 | BEARING,STD;NP SM01515100 | 2024-07-21 | W |  | 0100 | NO 2 BEARING | INT | NO 2 BEARING | 5 |  | 9027132_4380 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 652 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4410 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0110 | 1620 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10245898 | BEARING,STD;NP SMP3756705 | 1 | EA | 1 | 0 | 1 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 653 cannot be changed 9027132 item 4390 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124220 | 9027132 | 05 | Preparation | 0000129822 | 653 | 0 | EA |  |  | 102000000030771 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000396388_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056767 | 1020 | 2025-07-03 | 1 |  | 2025-02-11 | 4900234166_2025_0005 | 2025-03-01 |  | 5000396388_2025_0001 | 0 | 2 | 0 | 90028419 | 1 | 0 | 180124220 | 2 | 0 | 0 | X | L | 4900234166 | 2025 |  | 5000396388 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245898 | BEARING,STD;NP SMP3756705 | 2024-07-21 | W |  | 0110 | NO 3 BEARING | INT | NO 3 BEARING | 5 |  | 9027132_4390 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 653 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4420 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN4 | Released | 2025-02-07 | 2025-05-08 | 2025-05-03 | 2025-05-08 | 2025-05-17 | INLEC | 600001473 | 0010 | 0090 | 600001473 | MOC-54689 4V1302 HH Pressure Trip | AA53.413LT003 | TX,LEVEL 4V1303 FEED GAS SEPARATOR | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10247511 | VALVE,SLND;EX,HERION 2401112426002400 | 2 | ASY | 29 | 0 | 3 | 0 |  | 16.02 - SOH @ AA02 | Supply for Order 600001473, Item 10 cannot be changed 90031856 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020972 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90031856 | 05 | Preparation | 0000084391 | 10 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-02-07 | ODST-0090031856_0010 | 0 | 0 | 0 | 0 |  | 2025-05-06 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2025-12-15 | 0 |  | 2025-05-03 |  | 2025-05-08 | Contingency |  | 0 | 2 | 0 | 90031856 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-03 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10247511 | VALVE,SLND;EX,HERION 2401112426002400 | 2025-02-14 | W |  | 0010 | MOC-97485 Pre Works | INT | MOC-97485 Pre Works |  | Engineering Query/Management of Change | 90031856_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0006 | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000083795 | S002 | 30 | 30 | 5300020972 | 90 |  |  | 0 | 2 | ASY | 2001 | AA02 | 2025-05-03 |  | Engineering Query/Management of Change |  |  | 1070 |  | 2025-02-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84391 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-05-17 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Date set by external system/Released/Material shortage/Settlement rule created/Partially confirmed | AM06 | Capital
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0140 | 1950 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10248822 | RING,BASE,ACC;31.70X34X2.45MM,MILD ST | 4 | EA | 19 | 0 | 0 | 4 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 269 cannot be changed 90028419 item 2080 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 269 | 0 | EA | 102000000030504 | 102000000030301 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10248822 | RING,BASE,ACC;31.70X34X2.45MM,MILD ST | 2024-07-21 | W |  | 0140 | HYDRAULIC ACCUMULATOR & CONTRO SYS | INT | HYDRAULIC ACCUMULATOR & CONTRO SYS | 5 |  | 90028419_2080 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 269 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2110 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0170 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10248914 | TAPE,FIL;CROSS WEAVE,170UM,19MM | 30 | ROL | 20 | 0 | 20 | 0 |  | 07.03 - ETA 27.03.25 PO 4500047066 ARMACEL CPT | Supply for Order 100090053, Item 17 cannot be changed 90032376 item 170 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 17 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0170 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10248914 | TAPE,FIL;CROSS WEAVE,170UM,19MM | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0170 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 17 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 |  | 30 | 5300022012 | 170 |  |  | 0 | 30 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0140 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10248914 | TAPE,FIL;CROSS WEAVE,170UM,19MM | 60 | ROL | 20 | 0 | 20 | 0 |  | 02.03 - ETA 27.03.25 PO 4500047066 ARMACELL CPT | Supply for Order 500005166, Item 34 cannot be changed 90031501 item 160 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 34 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 60 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0160 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10248914 | TAPE,FIL;CROSS WEAVE,170UM,19MM | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0160 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 34 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 |  | 30 | 5300021227 | 300 |  |  | 0 | 60 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN4 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-08 | INLEC | 100043970 | 0010 | 0010 | 100043970 | CCC Replace FTA Cards 414PT084A | AA53.414PT084A | TX,PRESS 4V1440 TO 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(01.01.2024) | 10248945 | MODULE,IF;ANAL 1/0,CCC FTA20REVB | 2 | ASY | 5 | 0 | 0 | 2 | ASY | 02.10 - SOH @ AA02 | Supply for Order 100043970, Item 1 cannot be changed 90024946 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300001451 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90024946 | 05 | Preparation | 0000142474 | 1 | 0 | ASY | 102000000029975 |  | 102000000033276 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024946_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2022-09-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414PT084A |  | 0 | 2 | 0 | 90024946 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10248945 | MODULE,IF;ANAL 1/0,CCC FTA20REVB | 2024-01-01 | W |  | 0010 | Replace FTA Cards | INT | Replace FTA Cards | 5 |  | 90024946_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000141885 | S002 | 30 | 30 | 5300001451 | 10 |  |  | 0 | 2 | ASY | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142474 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1130 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10249753 | COVER,HEAT SHIELD;NP SMR35839 | 1 | EA | 3 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 136 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10249753 | COVER,HEAT SHIELD;NP SMR35839 |  |  |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1140 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10249754 | COVER,HEAT SHIELD;NP SMR35840 | 1 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 137 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10249754 | COVER,HEAT SHIELD;NP SMR35840 |  |  |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1150 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10249755 | COVER,HEAT SHIELD;NP SMR35835 | 1 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 138 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10249755 | COVER,HEAT SHIELD;NP SMR35835 |  |  |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1160 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10249756 | COVER,HEAT SHIELD;NP SMR35834 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 139 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10249756 | COVER,HEAT SHIELD;NP SMR35834 |  |  |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1170 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10249757 | COVER,HEAT SHIELD;NP SMR35836 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 140 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10249757 | COVER,HEAT SHIELD;NP SMR35836 |  |  |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0080 | 1180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10249758 | COVER,HEAT SHIELD;NP SMR35837 | 1 | EA | 1 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 141 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10249758 | COVER,HEAT SHIELD;NP SMR35837 |  |  |  | 0080 | INNER TURBINE CASE | INT | INNER TURBINE CASE | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 3150 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10250242 | HELICOIL;LCK TYPE,MTR,M16,2X1.5D,SS304 | 20 | EA | 43 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 543 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10250242 | HELICOIL;LCK TYPE,MTR,M16,2X1.5D,SS304 |  |  |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 3160 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10251133 | HELICOIL;NP RFR331450000 | 6 | EA | 40 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 544 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251133 | HELICOIL;NP RFR331450000 |  |  |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0200 | 3100 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10251133 | HELICOIL;NP RFR331450000 | 20 | EA | 40 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 546 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251133 | HELICOIL;NP RFR331450000 |  |  |  | 0200 | LP ROTOR ASSEMBLY | INT | LP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0095 | 0020 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10251510 | GLYCOL;MONOETHYLENE,230KG,MAU | 5 | DR | 4 | 0 | 3 | 0 |  | 19.02 - SOH @AA02 | Supply for Order 200091126, Item 80 cannot be changed 90023534 item 370 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 620 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 80 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0370 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251510 | GLYCOL;MONOETHYLENE,230KG,MAU | 2024-05-11 | W |  | 0095 | COOLING WATER | INT | COOLING WATER |  |  | 90023534_0370 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 80 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 620 |  |  | 0 | 5 | DR | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-09-10 | 2025-05-08 | 2024-09-10 | 2025-05-08 | 2025-05-09 | INLEC | 100084190 | 0010 | 0010 | 100084190 | OPSD - SUB2 Annunciator Panel Alarm | AA53.LN4.E0211540 | LN4 DISTR XFMR SUB 02 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(09.09.2024) | 10251568 | POWER SUPP;PWRBX PB15C24X | 1 | EA | 1 | 0 | 0 | 1 | EA | 10.03 - AT AA53 | Supply for Order 100084190, Item 1 cannot be changed 180068104 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300015224 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180068104 | 90019427 | 06 | Scheduling | 0000262127 | 1 | 0 | EA |  |  | 102000000016885 |  |  |  |  | WorkPackLink | P99PICKUPFROMWHSE | P19 FL Inlec | 0 | 5400000773 | 10 | 1 | EA | 0 | 0 |  |  | Y | 1001 | 2024-09-10 | GRST-5000202318_2024 | 0 | 0 | 0 | 0 |  | 2024-09-08 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  | 100000027837 | 1020 | 2025-03-08 | 1 |  | 2024-09-10 | 4900128692_2024_0001 | 2024-09-15 | P19 FL Inlec | 5000202318_2024_0001 | 0 | 2 | 0 | 90019427 | 1 | 0 | 180068104 | 2 | 0 | 0 | X | L | 4900128692 | 2024 |  | 5000202318 | 2024 | 0 |  | 2024-09-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251568 | POWER SUPP;PWRBX PB15C24X | 2024-09-09 | W |  | 0010 | SUB2 Annunciator Panel Alarm | INT | SUB2 Annunciator Panel Alarm |  | Opportune Shutdown | 90019427_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 | 4900131631_2024 | 25SDLN4 | MJ |  | AU1072 | 1000257739 | S002 |  | 30 | 5300015224 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-09-10 |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPFN4 | 2024-09-09 | 262127 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-09 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Ready For Scheduling/Goods movement posted/Material committed | AM01 | Reactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0280 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(19.02.2025) | 10251638 | INSULATION,SUPERWOOL PLUS BLANKET | 5 | PAC | 0 | 0 | 0 | 0 |  | 10.03 - ETA 27.03.25 PO 4500047066 ARMACELL CPT | Supply for Order 500005166, Item 48 cannot be changed 90031501 item 290 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 440 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAC |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 48 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0290 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251638 | INSULATION,SUPERWOOL PLUS BLANKET | 2025-02-19 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0290 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 48 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 |  | 30 | 5300021227 | 440 |  |  | 0 | 5 | PAC | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 3190 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10252020 | BUCKET,1ST STG HP;NP SMO1166120 | 1 | SET | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET |  | REFURB |  |  |  | 05 | Preparation | 0000129822 | 751 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10252020 | BUCKET,1ST STG HP;NP SMO1166120 |  |  |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0190 | 3180 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10252134 | PLATE,COV;NP SMO1166105 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  |  |  | 05 | Preparation | 0000129822 | 750 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  |  |  |  | ON CONDITION |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10252134 | PLATE,COV;NP SMO1166105 |  |  |  | 0190 | HP ROTOR ASSEMBLY | INT | HP ROTOR ASSEMBLY | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0150 | 0010 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(18.02.2025) | 10252137 | OIL,LAPPING;KEMLAP,2.5L | 5 | CON | 0 | 0 | 0 | 0 |  | 26.02 - ETA 31.03.25 PO 4500047528 BLACKWOODS CPT | Supply for Order 200091126, Item 153 cannot be changed 90031238 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 1290 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  |  |  |  | 90031238 | 05 | Preparation | 0000129360 | 153 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | ODST-0090031238_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | Deano |  | 0 | 2 | 0 | 90031238 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10252137 | OIL,LAPPING;KEMLAP,2.5L | 2025-02-18 | W |  | 0150 | CONSUMABLES | INT | CONSUMABLES |  |  | 90031238_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 153 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 | 30 | 30 | 5300004361 | 1290 |  |  | 0 | 5 | CON | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0160 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.02.2025) | 10252931 | STRIP,TERM;EX,WDU2.5,WEIDMULLER1020000> | 20 | EA | 22 | 0 | 0 | 20 | EA | 09.02 - SOH @ AA02 | Supply for Order 600001815, Item 22 cannot be changed 90030415 item 140 already exists | Material picked; currently at PACKING/Z830 @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030415 | 07 | Execution | 0000084731 | 22 | 0 | EA | 102000000033133 |  | 102000000032129 |  |  |  |  | WorkPackLink | PACKING | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030415_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | FAR12 |  | 0 | 2 | 0 | 90030415 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10252931 | STRIP,TERM;EX,WDU2.5,WEIDMULLER1020000> | 2025-02-05 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030415_0140 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 22 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 170 |  |  | 0 | 20 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDGT8 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147409 | 0010 | 0040 | 200147409 | 6Y CV-RE 2.5 600# Act BUV - 408XV575 | AA53.408XV575 | VALVE,FLOW CONT HPC BLEED | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10253545 | VALVE,BLEED;GE L47329PO5 | 1 | EA | 2 | 0 | 0 | 1 | EA | 24.02 - SOH @ AA02 | Supply for Order 200147409, Item 4 cannot be changed 90025018 item 10 already exists | Material picked; currently at WH2-PACK-SD-1B/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300015893 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90025018 | 05 | Preparation | 0000235814 | 4 | 0 | EA |  |  | 102000000029599 |  |  |  |  | WorkPackLink | WH2-PACK-SD-1B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025018_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | Valve |  | 0 | 2 | 0 | 90025018 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10253545 | VALVE,BLEED;GE L47329PO5 | 2024-09-30 | W |  | 0010 | Replace CDP Bleed Valve | INT | Replace CDP Bleed Valve | 3 | Ready for Release | 90025018_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232825 | S002 | 30 | 30 | 5300015893 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235814 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-12-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-13 | ROTAT | 200174928 | 0020 | 0030 | 200174928 | 6Y GT4009 GEOMETRY VALVE CDP BLEED | AA53.409XV575 | VALVE,GT4009 HP COMP BLEED ACTUATION | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(03.12.2024) | 10253545 | VALVE,BLEED;GE L47329PO5 | 1 | EA | 2 | 0 | 0 | 0 |  | 24.02 - SOH @ AA02 | Supply for Order 200174928, Item 3 cannot be changed 90028286 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018734 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90028286 | 05 | Preparation | 0000277563 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-03 | ODST-0090028286_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174928 |  | 0 | 2 | 0 | 90028286 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10253545 | VALVE,BLEED;GE L47329PO5 | 2024-12-03 | W |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | 3 | Ready for Release | 90028286_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000272050 | S002 | 30 | 30 | 5300018734 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277563 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-13 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
1 | 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0420 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | WO item has not been released yet | 10254900 | SPACER,RING,50MM,CL300,8MM,LTCS | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000084596 | 40 | 0 | [8 empty] | WorkPackLink |  | spacer ring | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254900 | SPACER,RING,50MM,CL300,8MM,LTCS |  |  |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify | [5 empty] | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDSTB5 | MJ |  |  | 1000084000 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0430 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10254979 | SPADE,BLIND,80MM,CL600,15MM,SS304 | 10 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 43 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254979 | SPADE,BLIND,80MM,CL600,15MM,SS304 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
1 | 25SDLN3 | Released | 2025-03-04 | 2025-04-02 |  | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0450 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | WO item has not been released yet | 10254984 | SPADE,BLIND,150MM,CL600,24MM,SS304 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000289018 | 45 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  |  |  |  | 3E1405/Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10254984 | SPADE,BLIND,150MM,CL600,24MM,SS304 |  |  |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 | [5 empty] | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN3 | MJ |  |  | 1000283045 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 0 | 0 | 0 |  |  | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-11-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-05 | INLEC | 100033543 | 0020 | 0010 | 100033543 | GT4008 T48 Harness Changeout | AA53.408TE519F | TXDCR,TEMP GT4008 LP COMPR INLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10255155 | PROBE,TEMP;GE 1696M81P13 | 1 | EA | 12 | 0 | 0 | 1 | EA | 23.01 - SOH @ AA02 | Supply for Order 100033543, Item 1 cannot be changed 90028283 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018584 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028283 | 05 | Preparation | 0000132064 | 1 | 0 | EA | 102000000029892 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028283_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028283 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255155 | PROBE,TEMP;GE 1696M81P13 | 2024-11-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90028283_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000131433 | S002 | 30 | 30 | 5300018584 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132064 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-05 | INLEC | 100076438 | 0020 | 0010 | 100076438 | Investigate Faulty Inlet T/C (1) GT4008 | AA53.408TE519G | TXDCR,TEMP GT4008 LP COMPR INLET | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255155 | PROBE,TEMP;GE 1696M81P13 | 1 | EA | 12 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 100076438, Item 1 cannot be changed 90025055 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016524 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025055 | 05 | Preparation | 0000233017 | 1 | 0 | EA | 102000000029890 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025055_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-02-18 | 0 |  | 2025-02-24 |  | 2025-03-01 | 408TE519G |  | 0 | 2 | 0 | 90025055 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255155 | PROBE,TEMP;GE 1696M81P13 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025055_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000230164 | S002 | 30 | 30 | 5300016524 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-04-18 | 233017 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0240 | 0310 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255155 | PROBE,TEMP;GE 1696M81P13 | 1 | EA | 12 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 31 cannot be changed 90025036 item 260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 31 | 0 | EA | 102000000029888 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | T48 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255155 | PROBE,TEMP;GE 1696M81P13 | 2024-10-16 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 | Ready for Release | 90025036_0260 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 31 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0240 | 0040 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255155 | PROBE,TEMP;GE 1696M81P13 | 1 | EA | 12 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 36 cannot be changed 90025043 item 320 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 36 | 0 | EA | 102000000029889 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255155 | PROBE,TEMP;GE 1696M81P13 | 2024-10-17 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 | Ready for Release | 90025043_0320 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 36 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 320 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0240 | 0020 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255155 | PROBE,TEMP;GE 1696M81P13 | 1 | EA | 12 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 29 cannot be changed 90025045 item 280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 29 | 0 | EA | 102000000029891 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255155 | PROBE,TEMP;GE 1696M81P13 | 2024-10-17 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 |  | 90025045_0280 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 29 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 280 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0090 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2 | EA | 5 | 2 | 4 | 2 | EA | KSF Work-Packed | Supply for Order 200147548, Item 9 cannot be changed 90025036 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 9 | 0 | EA | 101000000117613 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0080 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0060 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2 | EA | 5 | 2 | 4 | 2 | EA | KSF Work-Packed | Supply for Order 200147550, Item 8 cannot be changed 9022233 item 80 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180103949 | 9022233 | 05 | Preparation | 0000235962 | 8 | 0 | EA | 101000000117614 |  | 101000000117148 | 01-Road |  | 5-Completed |  | WorkPackLink | GR-ZONE |  | 0 |  | 0 | 0 |  | 0 | 0 | 2024-12-11 | 2024-12-04 | Y | 1001 | 2024-10-17 | IDST-0180103949 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000046024 | 1020 | 2025-05-15 | 2 |  | 2024-12-11 | 4900189446_2024_0001 | 2025-03-01 | Clutch gaske | 5000315873_2024_0001/5000315788_2024_0001 | 0 | 2 | 0 | 90025043 | 0 | 0 | 180103949 | 2 | 0 | 0 | X | L | 4900189446 | 2024 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 9022233_0080 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDGT8 | MJ | 20004260 | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2024-12-02 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0060 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2 | EA | 5 | 2 | 4 | 1 | EA | KSF Work-Packed | Supply for Order 200147552, Item 8 cannot be changed 90025045 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 8 | 0 | EA | 102000000027251 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0080 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0060 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2 | EA | 5 | 2 | 4 | 1 | EA | KSF Work-Packed | Supply for Order 200147552, Item 8 cannot be changed 90025045 item 80 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 8 | 0 | EA | 102000000029717 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0080 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147410 | 0010 | 0010 | 200147410 | 6Y CV-RE 6 600# Act BUV - 408XV576 | AA53.408XV576 | VALVE,FLOW CONT 8TH STAGE BLEED GT4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255178 | RING,BLEED;AIR,GE 2873600 | 2 | EA | 8 | 0 | 0 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147410, Item 1 cannot be changed 90025001 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015678 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025001 | 05 | Preparation | 0000235815 | 1 | 0 | EA | 102000000027567 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025001_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | Stg 8 gasket |  | 0 | 2 | 0 | 90025001 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255178 | RING,BLEED;AIR,GE 2873600 | 2024-09-22 | W |  | 0010 | REPLACE STG 8 BLEED VALVE | INT | REPLACE STG 8 BLEED VALVE | 3 | Ready for Release | 90025001_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232826 | S002 | 30 | 30 | 5300015678 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235815 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-12-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-13 | ROTAT | 200174929 | 0020 | 0020 | 200174929 | 6Y GT4009 GEOMETRY VALVE 8TH STAGE | AA53.409XV576 | VALVE,GT4009 8TH STAGE BLEED VLV ACTUAT | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(03.12.2024) | 10255178 | RING,BLEED;AIR,GE 2873600 | 2 | EA | 8 | 0 | 0 | 2 | EA | 02.12 - SOH @ AA02 | Supply for Order 200174929, Item 3 cannot be changed 90028285 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018650 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028285 | 05 | Preparation | 0000277564 | 3 | 0 | EA | 102000000029719 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-12-03 | ODST-0090028285_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174929 |  | 0 | 2 | 0 | 90028285 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255178 | RING,BLEED;AIR,GE 2873600 | 2024-12-03 | W |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | 3 | Ready for Release | 90028285_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000272051 | S002 | 30 | 30 | 5300018650 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277564 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-13 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0070 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255250 | GASKET;GE 9107M23P02 | 1 | EA | 7 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 7 cannot be changed 90025036 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 7 | 0 | EA | 102000000026609 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255250 | GASKET;GE 9107M23P02 | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0050 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255250 | GASKET;GE 9107M23P02 | 1 | EA | 7 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 7 cannot be changed 90025043 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 7 | 0 | EA | 102000000026610 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255250 | GASKET;GE 9107M23P02 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025043_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0050 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255250 | GASKET;GE 9107M23P02 | 1 | EA | 7 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 7 cannot be changed 90025045 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 7 | 0 | EA | 102000000026611 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch gaske |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255250 | GASKET;GE 9107M23P02 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-11-29 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-05 | INLEC | 100033543 | 0020 | 0020 | 100033543 | GT4008 T48 Harness Changeout | AA53.408TE519F | TXDCR,TEMP GT4008 LP COMPR INLET | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(29.11.2024) | 10255264 | GASKET;GE 9379M93P01 | 1 | EA | 25 | 0 | 2 | 0 |  | 19.02 - WO to be cancelled re Adrian G. | Supply for Order 100033543, Item 2 cannot be changed 90028283 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018584 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028283 | 05 | Preparation | 0000132064 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028283_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028283 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 | 2024-11-29 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90028283_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000131433 | S002 |  | 30 | 5300018584 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132064 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0240 | 0300 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 25 | 0 | 2 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 30 cannot be changed 90025036 item 250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 30 | 0 | EA | 102000000026602 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | T48 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 | 2024-10-16 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 | Ready for Release | 90025036_0250 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 30 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 250 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0240 | 0030 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 25 | 0 | 2 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 35 cannot be changed 90025043 item 310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 35 | 0 | EA | 102000000034494 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 | 2024-10-17 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 | Ready for Release | 90025043_0310 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 35 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 310 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0240 | 0030 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 25 | 0 | 2 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 35 cannot be changed 90025043 item 310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 35 | 0 | EA | 102000000032997 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 | 2024-10-17 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 | Ready for Release | 90025043_0310 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 35 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 310 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0240 | 0030 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 25 | 0 | 2 | 6 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 35 cannot be changed 90025043 item 310 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 35 | 0 | EA | 102000000026463 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0310 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 | 2024-10-17 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 | Ready for Release | 90025043_0310 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 35 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 310 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0240 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 25 | 0 | 2 | 1 | EA | 26.02 - SOH @ AA02 | Supply for Order 200147552, Item 28 cannot be changed 90025045 item 270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 28 | 0 | EA | 101000000147890 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 | 2024-10-17 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 |  | 90025045_0270 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 28 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 270 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0240 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 25 | 0 | 2 | 7 | EA | 26.02 - SOH @ AA02 | Supply for Order 200147552, Item 28 cannot be changed 90025045 item 270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 28 | 0 | EA | 102000000032996 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | T48 |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 | 2024-10-17 | W |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 3 |  | 90025045_0270 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 28 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 270 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0100 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255270 | GASKET;GE 9608M12P04 | 1 | EA | 1 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 35 cannot be changed 90025036 item 300 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 35 | 0 | EA | 102000000027252 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0300 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | AGB Clt Gask |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255270 | GASKET;GE 9608M12P04 | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0300 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 35 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 300 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0070 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255270 | GASKET;GE 9608M12P04 | 1 | EA | 1 | 0 | 0 | 0 |  | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 9 cannot be changed 90025043 item 90 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 9 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | AGB Clt Gask |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255270 | GASKET;GE 9608M12P04 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025043_0090 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0070 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255270 | GASKET;GE 9608M12P04 | 1 | EA | 1 | 0 | 0 | 0 |  | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 9 cannot be changed 90025045 item 90 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 9 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | AGB Clt Gask |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255270 | GASKET;GE 9608M12P04 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0090 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0210 | 0280 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 1 | EA | 4 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 28 cannot be changed 90025036 item 230 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 28 | 0 | EA | 102000000026774 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0230 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 2024-10-16 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 | Ready for Release | 90025036_0230 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 28 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 230 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0210 | 0030 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 1 | EA | 4 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 30 cannot be changed 90025043 item 280 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 30 | 0 | EA | 102000000026775 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0280 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 2024-10-17 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 | Ready for Release | 90025043_0280 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 30 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 280 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0210 | 0030 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 1 | EA | 4 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 26 cannot be changed 90025045 item 250 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 26 | 0 | EA | 102000000026776 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0250 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | HCU Filter |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 2024-10-17 | W |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 3 |  | 90025045_0250 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 26 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0180 | 0190 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255346 | GASKET;GE J219P04 | 1 | EA | 28 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 19 cannot be changed 90025036 item 160 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 19 | 0 | EA | 102000000026596 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0160 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | VBV RIG |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255346 | GASKET;GE J219P04 | 2024-10-16 | W |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 3 | Ready for Release | 90025036_0160 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 19 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0180 | 0020 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255346 | GASKET;GE J219P04 | 1 | EA | 28 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 23 cannot be changed 90025043 item 210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 23 | 0 | EA | 102000000026597 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | VBV RIG |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255346 | GASKET;GE J219P04 | 2024-10-17 | W |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 3 | Ready for Release | 90025043_0210 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 23 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 210 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0180 | 0020 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255346 | GASKET;GE J219P04 | 1 | EA | 28 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 23 cannot be changed 90025045 item 220 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 23 | 0 | EA | 102000000026598 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0220 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | VBV RIG |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255346 | GASKET;GE J219P04 | 2024-10-17 | W |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 3 |  | 90025045_0220 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 23 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 220 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0010 | 0020 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255347 | GASKET;GE J219P05 | 2 | EA | 13 | 0 | 8 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 2 cannot be changed 90025036 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 2 | 0 | EA | 102000000026603 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255347 | GASKET;GE J219P05 | 2024-10-16 | W |  | 0010 | P03 BORESCOPE INSPECTION | INT | P03 BORESCOPE INSPECTION | 3 | Ready for Release | 90025036_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0010 | 0020 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255347 | GASKET;GE J219P05 | 2 | EA | 13 | 0 | 8 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 2 cannot be changed 90025043 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 2 | 0 | EA | 102000000026604 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255347 | GASKET;GE J219P05 | 2024-10-17 | W |  | 0010 | P03 BORESCOPE INSPECTION | INT | P03 BORESCOPE INSPECTION | 3 | Ready for Release | 90025043_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0010 | 0020 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255347 | GASKET;GE J219P05 | 2 | EA | 13 | 0 | 8 | 2 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 2 cannot be changed 90025045 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 2 | 0 | EA | 102000000026605 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255347 | GASKET;GE J219P05 | 2024-10-17 | W |  | 0010 | P03 BORESCOPE INSPECTION | INT | P03 BORESCOPE INSPECTION |  |  | 90025045_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0010 | 0010 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 30 | 0 | 3 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 1 cannot be changed 90025036 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 1 | 0 | EA | 102000000029447 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 2024-10-16 | W |  | 0010 | P03 BORESCOPE INSPECTION | INT | P03 BORESCOPE INSPECTION | 3 | Ready for Release | 90025036_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0060 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 30 | 0 | 3 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 6 cannot be changed 90025036 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 6 | 0 | EA | 102000000032746 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | O ring |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0060 |  |  | UT1 |  | 10 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0040 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 30 | 0 | 3 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 6 cannot be changed 90025043 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 6 | 0 | EA | 102000000029452 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | O ring |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025043_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0010 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 30 | 0 | 3 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 1 cannot be changed 90025043 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 1 | 0 | EA | 102000000029448 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 2024-10-17 | W |  | 0010 | P03 BORESCOPE INSPECTION | INT | P03 BORESCOPE INSPECTION | 3 | Ready for Release | 90025043_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0040 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 30 | 0 | 3 | 0 |  | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 6 cannot be changed 90025045 item 60 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 6 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | O ring |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0010 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 30 | 0 | 3 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 1 cannot be changed 90025045 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 1 | 0 | EA | 102000000029449 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 2024-10-17 | W |  | 0010 | P03 BORESCOPE INSPECTION | INT | P03 BORESCOPE INSPECTION |  |  | 90025045_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0130 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255354 | PACKING,GBX,TFR;GE J221P138 | 1 | EA | 13 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 38 cannot be changed 90025036 item 320 already exists | Material picked; currently at SW3R01D01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 38 | 0 | EA | 102000000029593 | 102000000029440 | 102000000029625 |  |  |  |  | WorkPackLink | SW3R01D01A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0320 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Carbon Seal |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255354 | PACKING,GBX,TFR;GE J221P138 | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0320 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 38 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 | 30 | 30 | 5300016450 | 320 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0100 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255354 | PACKING,GBX,TFR;GE J221P138 | 1 | EA | 13 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 12 cannot be changed 90025043 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 12 | 0 | EA | 102000000029441 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Carbon Seal |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255354 | PACKING,GBX,TFR;GE J221P138 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025043_0110 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 12 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 | 30 | 30 | 5300016482 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0100 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255354 | PACKING,GBX,TFR;GE J221P138 | 1 | EA | 13 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 12 cannot be changed 90025045 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 12 | 0 | EA | 102000000029442 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Carbon Seal |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255354 | PACKING,GBX,TFR;GE J221P138 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0110 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 12 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 | 30 | 30 | 5300016487 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0050 | 0050 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 1 | EA | 339 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 5 cannot be changed 90025036 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 5 | 0 | EA | 102000000029159 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch O rin |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 2024-10-16 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025036_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0050 | 0030 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 1 | EA | 339 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 5 cannot be changed 90025043 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 5 | 0 | EA | 102000000029160 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch O rin |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 | Ready for Release | 90025043_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0050 | 0030 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 1 | EA | 339 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 5 cannot be changed 90025045 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 5 | 0 | EA | 102000000029161 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Clutch O rin |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 2024-10-17 | W |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 3 |  | 90025045_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0030 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255359 | FILTER,WASHING;ROCHEM FTSSWAG | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 9 cannot be changed 90028588 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 9 | 0 | EA | 102000000033621 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177498 |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255359 | FILTER,WASHING;ROCHEM FTSSWAG | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028588_0090 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0030 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255359 | FILTER,WASHING;ROCHEM FTSSWAG | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 9 cannot be changed 90028589 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 9 | 0 | EA | 102000000033622 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255359 | FILTER,WASHING;ROCHEM FTSSWAG | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0090 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0030 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255359 | FILTER,WASHING;ROCHEM FTSSWAG | 1 | EA | 4 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177720, Item 9 cannot be changed 90028590 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 9 | 0 | EA | 102000000033539 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177720 |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255359 | FILTER,WASHING;ROCHEM FTSSWAG | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 90028590_0090 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0090 | 0100 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255363 | PACKING,GBX,TFR;GE J221P905 | 3 | EA | 16 | 0 | 0 | 3 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 10 cannot be changed 90025036 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 10 | 0 | EA | 102000000029444 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255363 | PACKING,GBX,TFR;GE J221P905 | 2024-10-16 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 | Ready for Release | 90025036_0090 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 90 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0090 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255363 | PACKING,GBX,TFR;GE J221P905 | 3 | EA | 16 | 0 | 0 | 3 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 13 cannot be changed 90025043 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 13 | 0 | EA | 102000000029445 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255363 | PACKING,GBX,TFR;GE J221P905 | 2024-10-17 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 | Ready for Release | 90025043_0120 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 13 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 120 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0090 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255363 | PACKING,GBX,TFR;GE J221P905 | 3 | EA | 16 | 0 | 0 | 3 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 13 cannot be changed 90025045 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 13 | 0 | EA | 102000000029446 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255363 | PACKING,GBX,TFR;GE J221P905 | 2024-10-17 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 |  | 90025045_0120 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 13 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 120 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0040 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255397 | GASKET;GE L43073P01 | 2 | EA | 19 | 2 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 10 cannot be changed 90028588 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 10 | 0 | EA | 102000000031254 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177498 |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028588_0100 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0040 | 0040 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255397 | GASKET;GE L43073P01 | 2 | EA | 19 | 2 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 4 cannot be changed 90028588 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028588 | 05 | Preparation | 0000281227 | 4 | 0 | EA | 102000000031253 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028588_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028588 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 |  | 90028588_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000275664 | S002 |  | 30 | 5300020059 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0040 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255397 | GASKET;GE L43073P01 | 2 | EA | 19 | 2 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 10 cannot be changed 90028589 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 10 | 0 | EA | 102000000031256 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0100 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0040 | 0040 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255397 | GASKET;GE L43073P01 | 2 | EA | 19 | 2 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177499, Item 4 cannot be changed 90028589 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 4 | 0 | EA | 102000000031255 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 |  | 90028589_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 |  | 30 | 5300020060 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0040 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255397 | GASKET;GE L43073P01 | 2 | EA | 19 | 2 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177720, Item 10 cannot be changed 90028590 item 100 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 10 | 0 | EA | 102000000031251 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0100 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177720 |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 90028590_0100 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0040 | 0040 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10255397 | GASKET;GE L43073P01 | 2 | EA | 19 | 2 | 0 | 2 | EA | 15.01 - SOH @ AA02 | Supply for Order 200177720, Item 4 cannot be changed 90028590 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028590 | 05 | Preparation | 0000281240 | 4 | 0 | EA | 102000000031252 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028590_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028590 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 | Ready for Release | 90028590_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000275666 | S002 |  | 30 | 5300020061 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0090 | 0120 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10255427 | O-RING;0.924" ID,GE M832481912 | 3 | EA | 46 | 0 | 0 | 3 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 34 cannot be changed 90025036 item 290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 34 | 0 | EA | 102000000027584 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255427 | O-RING;0.924" ID,GE M832481912 | 2024-10-16 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 | Ready for Release | 90025036_0290 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 34 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 290 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0090 | 0030 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255427 | O-RING;0.924" ID,GE M832481912 | 3 | EA | 46 | 0 | 0 | 3 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 15 cannot be changed 90025043 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 15 | 0 | EA | 102000000027585 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255427 | O-RING;0.924" ID,GE M832481912 | 2024-10-17 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 | Ready for Release | 90025043_0140 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 15 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 140 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0090 | 0030 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255427 | O-RING;0.924" ID,GE M832481912 | 3 | EA | 46 | 0 | 0 | 3 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 15 cannot be changed 90025045 item 140 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 15 | 0 | EA | 102000000027586 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | Chip detecto |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255427 | O-RING;0.924" ID,GE M832481912 | 2024-10-17 | W |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 3 |  | 90025045_0140 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 15 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 140 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147564 | 0010 | 0010 | 200147564 | 2Y SVC G4007 AIR SYSTEM FLT CHANGE OUT | AA53.G4007S2 | FILT,GENERATOR INLET AIR G4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255442 | NUT,ELEM,FIXATION;DONALD P770920 | 32 | EA | 408 | 0 | 0 | 32 | EA | 03.10 - SOH @ AA02 | Supply for Order 200147564, Item 1 cannot be changed 90025005 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015683 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025005 | 05 | Preparation | 0000235976 | 1 | 0 | EA | 102000000028415 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025005_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025005 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255442 | NUT,ELEM,FIXATION;DONALD P770920 | 2024-09-22 | W |  | 0010 | Replace Generator Air Filters | INT | Replace Generator Air Filters | 3 | Ready for Release | 90025005_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232982 | S002 |  | 30 | 5300015683 | 10 |  |  | 0 | 32 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235976 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT8 | Released | 2024-08-13 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0070 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | WO item has not been released yet | 10255508 | GEAR SET;FLENDGRAF A10004T159 | 1 | SET | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000098185 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255508 | GEAR SET;FLENDGRAF A10004T159 |  |  |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000097602 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0220 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10255509 | BEARING,GBX;TURB,FLENDGRAF B11005K778 | 1 | EA | 0 | 0 | 0 | 0 |  | 30.12 - ETA 15.04.25 PO 4500034747 ENERGY CAPITAL CPT MID APRIL | Supply for Order 200063883, Item 22 cannot be changed 90024996 item 190 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 22 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090024996_0190 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255509 | BEARING,GBX;TURB,FLENDGRAF B11005K778 | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 90024996_0190 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 22 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0020 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10255510 | BEARING,GBX;FLENDGRAF B12005K777 | 1 | EA | 3 | 0 | 1 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200063883, Item 2 cannot be changed 9026956 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124312 | 9026956 | 05 | Preparation | 0000098185 | 2 | 0 | EA |  |  | 102000000032808 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R4FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-08-13 | GRST-5000396738_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000057061 | 1020 | 2024-10-06 | 1 |  | 2025-02-11 | 4900234305_2025_0001 | 2025-03-01 |  | 5000396738_2025_0001 | 0 | 2 | 0 | 90024996 | 1 | 0 | 180124312 | 2 | 0 | 0 | X | L | 4900234305 | 2025 |  | 5000396738 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255510 | BEARING,GBX;FLENDGRAF B12005K777 | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 9026956_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ | 1000005108 | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-12 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0030 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10255511 | BEARING,GBX;TURB,FLENDGRAF B21002D409 | 1 | EA | 0 | 0 | 1 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200063883, Item 3 cannot be changed 9027129 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124194 | 9027129 | 05 | Preparation | 0000098185 | 3 | 0 | EA |  |  | 102000000029511 |  |  |  |  | WorkPackLink | P07WH-R4FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-08-13 | GRST-5000396440_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056764 | 1020 | 2024-10-06 | 1 |  | 2025-02-11 | 4900234151_2025_0001 | 2025-03-01 |  | 5000396440_2025_0001 | 0 | 2 | 0 | 90024996 | 1 | 0 | 180124194 | 2 | 0 | 0 | X | L | 4900234151 | 2025 |  | 5000396440 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255511 | BEARING,GBX;TURB,FLENDGRAF B21002D409 | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 9027129_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0040 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10255512 | BEARING,GBX;TURB,FLENDGRAF B22005H174 | 1 | EA | 0 | 0 | 1 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200063883, Item 4 cannot be changed 9027130 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124197 | 9027130 | 05 | Preparation | 0000098185 | 4 | 0 | EA |  |  | 102000000029512 |  |  |  |  | WorkPackLink | P07WH-R4FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-08-13 | GRST-5000396441_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056765 | 1020 | 2024-10-06 | 1 |  | 2025-02-11 | 4900234152_2025_0001 | 2025-03-01 |  | 5000396441_2025_0001 | 0 | 2 | 0 | 90024996 | 1 | 0 | 180124197 | 2 | 0 | 0 | X | L | 4900234152 | 2025 |  | 5000396441 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255512 | BEARING,GBX;TURB,FLENDGRAF B22005H174 | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 9027130_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0150 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10255513 | SEAL,GBX;TURB,FLENDGRAF K11003AF377 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 200063883, Item 15 cannot be changed 90024996 item 130 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 15 | 0 | EA | 101000000001736 |  | 101000000142669 | 01-Road |  | 5-Completed |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 | 2025-02-09 | 2025-02-03 | Y | 1001 | 2024-08-13 | ODST-0090024996_0130 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255513 | SEAL,GBX;TURB,FLENDGRAF K11003AF377 | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 90024996_0130 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDGT8 | MJ | 20005186 | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 130 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-08 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0160 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10255514 | SEAL,GBX;TURB,FLENDGRAF K21003AF378 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 200063883, Item 16 cannot be changed 90024996 item 140 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 16 | 0 | EA | 101000000010728 |  | 101000000142669 | 01-Road |  | 5-Completed |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 | 2025-02-09 | 2025-02-03 | Y | 1001 | 2024-08-13 | ODST-0090024996_0140 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255514 | SEAL,GBX;TURB,FLENDGRAF K21003AF378 | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 90024996_0140 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 16 |  | 0 |  | 25SDGT8 | MJ | 20005186 | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-08 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0040 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.12.2024) | 10255516 | PROBE,VIB;FLENDGR RJO042070000A | 1 | EA | 4 | 0 | 0 | 0 |  | 30.12 - ETA 29.07.25 PO 4500040852 BH FCA | Supply for Order 200063883, Item 29 cannot be changed 90028271 item 30 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028271 | 05 | Preparation | 0000098185 | 29 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090028271_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | XE585 |  | 0 | 2 | 0 | 90028271 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255516 | PROBE,VIB;FLENDGR RJO042070000A | 2024-12-02 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90028271_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 29 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 240 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0020 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.12.2024) | 10255516 | PROBE,VIB;FLENDGR RJO042070000A | 10 | EA | 4 | 0 | 0 | 4 | EA | 30.12 - ETA 29.07.25 PO 4500040852 BH FCA | Supply for Order 200063883, Item 27 cannot be changed 90028271 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028271 | 05 | Preparation | 0000098185 | 27 | 0 | EA | 102000000029945 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-08-13 | ODST-0090028271_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | XE505-509XY |  | 0 | 2 | 0 | 90028271 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255516 | PROBE,VIB;FLENDGR RJO042070000A | 2024-12-02 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90028271_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 27 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 220 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200147376 | 0010 | 0010 | 200147376 | 2Y Flame Detector Replace (2) GT4007 | AA53.407XT513A | DET,FLAME COMB CHAMBER,GT4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255526 | SENSOR,FLAME;GE L44819P01 | 2 | EA | 5 | 0 | 0 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147376, Item 1 cannot be changed 90025044 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016486 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025044 | 05 | Preparation | 0000235781 | 1 | 0 | EA | 102000000027505 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025044_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | AA53-TA-P07 |  | 0 | 2 | 0 | 90025044 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255526 | SENSOR,FLAME;GE L44819P01 | 2024-10-17 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 3 |  | 90025044_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232792 | S002 |  | 30 | 5300016486 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235781 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-11-28 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200156131 | 0010 | 0010 | 200156131 | 3Y Flame Detector Replace (2) - GT4009 | AA53.409XT513A | DET,GT4009 COMBUSTION CHAMBERS FLAME | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10255526 | SENSOR,FLAME;GE L44819P01 | 2 | EA | 5 | 0 | 0 | 2 | EA | 02.12 - SOH @ AA02 | Supply for Order 200156131, Item 1 cannot be changed 90028282 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018545 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028282 | 05 | Preparation | 0000248730 | 1 | 0 | EA | 102000000029943 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-28 | ODST-0090028282_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-29 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028282 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255526 | SENSOR,FLAME;GE L44819P01 | 2024-11-28 | W |  | 0010 | Complete Replacement | INT | Complete Replacement | 3 |  | 90028282_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000245152 | S002 |  | 30 | 5300018545 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | IP1020240706 | 2024-07-06 | 248730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-04 | ROTAT | 100076545 | 0010 | 0010 | 100076545 | Replace GT4008 G/box Filters | AA53.G4008S3 | FILT,GEARBOX ENCL VENTILATION G4008 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10255580 | ELEMENT,FLT;ALARA F729F66F8 630X630MM | 16 | EA | 1 | 0 | 0 | 1 | EA | 18.11 - ETA 14.07.25 PO 4500035100 BH FCA | Supply for Order 100076545, Item 1 cannot be changed 90025046 item 10 already exists | Material picked; currently at KSF-PACK-SD-SML/Z830 | SP12 | Stock at Base | 0 | AA02 | 5300016491 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025046 | 05 | Preparation | 0000233290 | 1 | 0 | EA |  |  | 102000000032685 |  |  |  |  | WorkPackLink | KSF-PACK-SD-SML | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025046_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-09 | 0 |  | 2025-02-24 |  | 2025-03-01 | 100076545 |  | 0 | 2 | 0 | 90025046 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255580 | ELEMENT,FLT;ALARA F729F66F8 630X630MM | 2024-10-17 | W |  | 0010 | Replace GT4008 G/box Filters | INT | Replace GT4008 G/box Filters |  |  | 90025046_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000230395 | S002 | 30 | 30 | 5300016491 | 10 |  |  | 0 | 16 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-04-19 | 233290 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2460 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10255600 | GASKET;3.000" CL 150,NP KFZ269810144 | 10 | EA | 14 | 0 | 0 | 10 | EA | 10.01 - SOH @ AA02 | Supply for Order 200091513, Item 550 cannot be changed 90028419 item 3960 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3990 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 550 | 0 | EA | 102000000030499 | 102000000030656 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3960 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255600 | GASKET;3.000" CL 150,NP KFZ269810144 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_3960 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 550 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3990 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-05-05 | ROTAT | 200066255 | 0010 | 0050 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.02.2024) | 10255603 | GASKET,SW;2.000",NP KFZ269860144 | 3 | EA | 5 | 0 | 3 | 3 | EA | 29.01 - At KGP | Supply for Order 200066255, Item 5 cannot be changed 180017123 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017123 | 90006336 | 05 | Preparation | 0000100557 | 5 | 0 | EA | 102000000003513 | 102000000003509 | 102000000004398 | 01-Road |  | 3-In Transit | W1 - 24SDLN3 - CAGE | WorkPackLink | GT4008 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000058665_2024 | 0 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000005808 | 1020 | 2025-07-31 | 3 |  | 2024-04-11 | 4900045238_2024_0001 | 2024-05-03 | GT4008 | 5000058665_2024_0001 | 0 | 2 | 0 | 90006336 | 3 | 0 | 180017123 | 2 | 0 | 0 | X | L | 4900045238 | 2024 |  | 5000058665 | 2024 | 0 |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255603 | GASKET,SW;2.000",NP KFZ269860144 | 2024-02-23 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 | Ready for Release | 90006336_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT8 | MJ | 1000001236 | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 50 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed/Part printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147452 | 0010 | 0050 | 200147452 | 6Y INSP TURB F/HOSE REPL GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255603 | GASKET,SW;2.000",NP KFZ269860144 | 3 | EA | 5 | 0 | 3 | 2 | EA | 27.02 - SOH @ AA02 | Supply for Order 200147452, Item 5 cannot be changed 90025002 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015679 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025002 | 05 | Preparation | 0000235862 | 5 | 0 | EA | 102000000026599 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025002_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025002 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255603 | GASKET,SW;2.000",NP KFZ269860144 | 2024-09-22 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 3 | Ready for Release | 90025002_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232868 | S002 |  | 30 | 5300015679 | 50 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235862 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147452 | 0010 | 0050 | 200147452 | 6Y INSP TURB F/HOSE REPL GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255603 | GASKET,SW;2.000",NP KFZ269860144 | 3 | EA | 5 | 0 | 3 | 1 | EA | 27.02 - SOH @ AA02 | Supply for Order 200147452, Item 5 cannot be changed 90025002 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015679 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025002 | 05 | Preparation | 0000235862 | 5 | 0 | EA | 102000000031280 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025002_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025002 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255603 | GASKET,SW;2.000",NP KFZ269860144 | 2024-09-22 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 3 | Ready for Release | 90025002_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 5 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232868 | S002 |  | 30 | 5300015679 | 50 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235862 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-05-05 | ROTAT | 200066255 | 0010 | 0060 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(23.02.2024) | 10255604 | GASKET,RING;SS316GR,NP KFZ269880144 | 3 | EA | 9 | 0 | 3 | 3 | EA | 29.01 - At KGP | Supply for Order 200066255, Item 6 cannot be changed 180017123 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017123 | 90006336 | 05 | Preparation | 0000100557 | 6 | 0 | EA | 102000000003513 | 102000000003510 | 102000000004398 | 01-Road |  | 3-In Transit | W1 - 24SDLN3 - CAGE | WorkPackLink | GT4008 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000058665_2024 | 0 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000005808 | 1020 | 2025-07-31 | 3 |  | 2024-04-11 | 4900045238_2024_0003 | 2024-05-03 | GT4008 | 5000058665_2024_0002 | 0 | 2 | 0 | 90006336 | 3 | 0 | 180017123 | 2 | 0 | 0 | X | L | 4900045238 | 2024 |  | 5000058665 | 2024 | 0 |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255604 | GASKET,RING;SS316GR,NP KFZ269880144 | 2024-02-23 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 | Ready for Release | 90006336_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDGT8 | MJ | 1000001236 | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed/Part printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0150 | 2010 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10255604 | GASKET,RING;SS316GR,NP KFZ269880144 | 2 | EA | 9 | 0 | 3 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 521 cannot be changed 90028419 item 3760 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3790 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 521 | 0 | EA | 102000000030501 | 102000000030227 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3760 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255604 | GASKET,RING;SS316GR,NP KFZ269880144 | 2024-07-21 | W |  | 0150 | FUEL GAS RATIO VALVE | INT | FUEL GAS RATIO VALVE | 5 |  | 90028419_3760 |  |  | DG1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 521 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3790 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147452 | 0010 | 0060 | 200147452 | 6Y INSP TURB F/HOSE REPL GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255604 | GASKET,RING;SS316GR,NP KFZ269880144 | 3 | EA | 9 | 0 | 3 | 3 | EA | 18.12 - SOH @ AA02 | Supply for Order 200147452, Item 6 cannot be changed 90025002 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015679 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025002 | 05 | Preparation | 0000235862 | 6 | 0 | EA | 102000000027091 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025002_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025002 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255604 | GASKET,RING;SS316GR,NP KFZ269880144 | 2024-09-22 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 3 | Ready for Release | 90025002_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232868 | S002 |  | 30 | 5300015679 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235862 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2470 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10255607 | GASKET,SW;1.500",NP KFZ273110144 | 8 | EA | 6 | 0 | 0 | 6 | EA | 05.12 - ETA 01.03.25 PO 4500031675 ex BH MOT GS4953941 10kg 22x22x15 | Supply for Order 200091513, Item 551 cannot be changed 90028419 item 3970 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4000 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 551 | 0 | EA | 102000000030499 | 102000000030658 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3970 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255607 | GASKET,SW;1.500",NP KFZ273110144 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_3970 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 551 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4000 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0210 | 2480 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10255608 | GASKET;2.000" CL150,NP KFZ320300144 | 18 | EA | 20 | 0 | 0 | 18 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091513, Item 552 cannot be changed 90028419 item 3980 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 4010 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 552 | 0 | EA | 102000000030499 | 102000000030351 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_3980 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255608 | GASKET;2.000" CL150,NP KFZ320300144 | 2024-07-21 | W |  | 0210 | INLET PLENUM ASSEMBLY | INT | INLET PLENUM ASSEMBLY | 5 |  | 90028419_3980 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 552 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 4010 |  |  | 0 | 18 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0010 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(22.10.2024) | 10255634 | HEAD,TC;THERMO ENG PT100 | 24 | EA | 4 | 0 | 0 | 4 | EA | 05.03 - ETA 05.04.25 PO 4500033027 BH; in Trans MOTtba GS5052327 61.4kg 72x57x74 | Supply for Order 200063883, Item 26 cannot be changed 90024996 item 210 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 26 | 0 | EA | 102000000027096 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-08-13 | ODST-0090024996_0210 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4008 |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255634 | HEAD,TC;THERMO ENG PT100 | 2024-10-22 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90024996_0210 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 26 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 210 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0090 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(23.01.2025) | 10255634 | HEAD,TC;THERMO ENG PT100 | 4 | EA | 4 | 0 | 0 | 0 |  | 03.02 - ETA 01.07.25 PO 4500044485 BH FCA IN PACKING CHR to Collect | Supply for Order 200063883, Item 34 cannot be changed 90030043 item 10 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030043 | 05 | Preparation | 0000098185 | 34 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-08-13 | ODST-0090030043_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4008 |  | 0 | 2 | 0 | 90030043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255634 | HEAD,TC;THERMO ENG PT100 | 2025-01-23 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90030043_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 34 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 290 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-04 | ROTAT | 100079733 | 0010 | 0010 | 100079733 | Replace GT4008 Turbine Starter Hoses | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255665 | PIPE,SS;NP SMR7741047 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 100079733, Item 1 cannot be changed 90025004 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015682 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025004 | 05 | Preparation | 0000246850 | 1 | 0 | EA | 101000000001832 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025004_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-17 | 0 |  | 2025-02-24 |  | 2025-03-01 | Starter Hose |  | 0 | 2 | 0 | 90025004 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255665 | PIPE,SS;NP SMR7741047 | 2024-09-22 | W |  | 0010 | Replace GT4008 Turbine Starter Hoses | INT | Replace GT4008 Turbine Starter Hoses |  |  | 90025004_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000243462 | S002 |  | 30 | 5300015682 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246850 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-09-23 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-04 | ROTAT | 100079733 | 0010 | 0020 | 100079733 | Replace GT4008 Turbine Starter Hoses | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255666 | PIPE,SS;NP SMR7741048 | 1 | EA | 1 | 0 | 0 | 1 | EA | 13.02 - SOH @ AA02 | Supply for Order 100079733, Item 2 cannot be changed 90025004 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015682 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025004 | 05 | Preparation | 0000246850 | 2 | 0 | EA | 101000000001752 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-23 | ODST-0090025004_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-05-17 | 0 |  | 2025-02-24 |  | 2025-03-01 | Starter Hose |  | 0 | 2 | 0 | 90025004 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255666 | PIPE,SS;NP SMR7741048 | 2024-09-22 | W |  | 0010 | Replace GT4008 Turbine Starter Hoses | INT | Replace GT4008 Turbine Starter Hoses |  |  | 90025004_0020 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000243462 | S002 |  | 30 | 5300015682 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPN6M | 2024-06-28 | 246850 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-05-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-05-05 | ROTAT | 200066255 | 0010 | 0010 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10255671 | PIPE,FLEX;NP SMR7741895 | 1 | EA | 0 | 0 | 1 | 1 | EA | 25.09 - At KGP | Supply for Order 200066255, Item 1 cannot be changed 180004302 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004302 | 9000019 | 05 | Preparation | 0000100557 | 1 | 0 | EA |  |  | 102000000000216 | 01-Road |  | 5-Completed |  | WorkPackLink | P07WH-R3FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 1 | 0 | 2024-02-13 |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000002054 | 1020 | 2025-07-31 | 1 |  | 2024-02-12 | 4900030517_2024_0001 | 2024-05-03 | GT4008 | 5000017897_2024_0001 | 0 | 2 | 0 | 90000272 | 1 | 0 | 180004302/180017134 | 2 | 0 | 0 | X | L | 4900030517 | 2024 |  | 5000017897 | 2024 | 0 |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255671 | PIPE,FLEX;NP SMR7741895 | 2024-01-02 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 | Ready for Release | 9000019_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ | 1000000499 | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed/Part printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-05 | ROTAT | 200066255 | 0010 | 0070 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10255671 | PIPE,FLEX;NP SMR7741895 | 1 | EA | 0 | 0 | 1 | 0 |  | 05.02 - SOH @ AA53 PO TO COME THROUGH | Supply for Order 200066255, Item 7 cannot be changed 90030685 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030685 | 05 | Preparation | 0000100557 | 7 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030685_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030685 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255671 | PIPE,FLEX;NP SMR7741895 | 2025-02-11 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 | Ready for Release | 90030685_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed/Part printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147452 | 0010 | 0020 | 200147452 | 6Y INSP TURB F/HOSE REPL GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255671 | PIPE,FLEX;NP SMR7741895 | 1 | EA | 0 | 0 | 1 | 1 | EA | 29.01 - At KGP | Supply for Order 200147452, Item 2 cannot be changed 180096316 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015679 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096316 | 9019880 | 05 | Preparation | 0000235862 | 2 | 0 | EA | 102000000024318 |  | 107000000000045 |  |  |  | P07WH-R5FL | WorkPackLink | P07WH-R5FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-22 | GRST-5000288540_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000042602 | 1020 | 2025-09-30 | 1 |  | 2024-11-21 | 4900176548_2024_0001 | 2025-03-01 |  | 5000288540_2024_0001 | 0 | 2 | 0 | 90025002 | 1 | 0 | 180096316 | 2 | 0 | 0 | X | L | 4900176548 | 2024 |  | 5000288540 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255671 | PIPE,FLEX;NP SMR7741895 | 2024-09-22 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 3 | Ready for Release | 9019880_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232868 | S002 |  | 30 | 5300015679 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235862 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-05-05 | ROTAT | 200066255 | 0010 | 0020 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10255672 | PIPE,FLEX;NP SMR7741896 | 1 | EA | 2 | 0 | 0 | 1 | EA | 25.09 - At KGP | Supply for Order 200066255, Item 2 cannot be changed 180017144 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180017144 | 9001294 | 05 | Preparation | 0000100557 | 2 | 0 | EA |  |  | 102000000003502 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R3FL | AU01-TA-P07 | 0 | 5400000396 | 10 | 1 | EA | 0 | 0 |  |  | Y | 1001 | 2024-01-02 | GRST-5000058174_2024 | 0 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000005808 | 1020 | 2025-07-31 | 1 |  | 2024-04-11 | 4900045305_2024_0001 | 2024-05-03 | GT4008 | 5000058174_2024_0001 | 0 | 2 | 0 | 90000272 | 1 | 0 | 180017134/180017144 | 2 | 0 | 0 | X | L | 4900045305 | 2024 |  | 5000058174 | 2024 | 0 |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255672 | PIPE,FLEX;NP SMR7741896 | 2024-01-02 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 | Ready for Release | 9001294_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 | 4900072439_2024 | 25SDGT8 | MJ | 1000001236 | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed/Part printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147452 | 0010 | 0030 | 200147452 | 6Y INSP TURB F/HOSE REPL GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255672 | PIPE,FLEX;NP SMR7741896 | 1 | EA | 2 | 0 | 0 | 1 | EA | 24.10 - SOH @ AA02 | Supply for Order 200147452, Item 3 cannot be changed 90025002 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015679 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025002 | 05 | Preparation | 0000235862 | 3 | 0 | EA | 102000000032873 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-22 | ODST-0090025002_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025002 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255672 | PIPE,FLEX;NP SMR7741896 | 2024-09-22 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 3 | Ready for Release | 90025002_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232868 | S002 |  | 30 | 5300015679 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235862 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2024-04-30 | 2025-03-01 | 2025-05-05 | ROTAT | 200066255 | 0010 | 0030 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10255673 | PIPE,FLEX;NP SMR7741897 | 1 | EA | 0 | 0 | 1 | 1 | EA | 25.09 - At KGP | Supply for Order 200066255, Item 3 cannot be changed 180004302 item 20 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004302 | 9000019 | 05 | Preparation | 0000100557 | 3 | 0 | EA |  |  | 102000000000216 | 01-Road |  | 5-Completed |  | WorkPackLink | P07WH-R3FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 1 | 0 | 2024-02-13 |  | Y | 1001 | 2024-01-02 |  | 0 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000002054 | 1020 | 2025-07-31 | 1 |  | 2024-02-12 | 4900030517_2024_0003 | 2024-05-03 | GT4008 | 5000017897_2024_0002 | 0 | 2 | 0 | 90000272 | 1 | 0 | 180004302/180017134 | 2 | 0 | 0 | X | L | 4900030517 | 2024 |  | 5000017897 | 2024 | 0 |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255673 | PIPE,FLEX;NP SMR7741897 | 2024-01-02 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 | Ready for Release | 9000019_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ | 1000000499 | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed/Part printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-05 | ROTAT | 200066255 | 0010 | 0080 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(11.02.2025) | 10255673 | PIPE,FLEX;NP SMR7741897 | 1 | EA | 0 | 0 | 1 | 0 |  | 05.02 - SOH @ AA53 PO TO COME THROUGH | Supply for Order 200066255, Item 8 cannot be changed 90030685 item 20 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030685 | 05 | Preparation | 0000100557 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090030685_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90030685 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255673 | PIPE,FLEX;NP SMR7741897 | 2025-02-11 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 | Ready for Release | 90030685_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-05 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material committed/Part printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147452 | 0010 | 0040 | 200147452 | 6Y INSP TURB F/HOSE REPL GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(22.09.2024) | 10255673 | PIPE,FLEX;NP SMR7741897 | 1 | EA | 0 | 0 | 1 | 1 | EA | 29.01 - At KGP | Supply for Order 200147452, Item 4 cannot be changed 180096316 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015679 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180096316 | 9019880 | 05 | Preparation | 0000235862 | 4 | 0 | EA |  |  | 102000000024319 | 01-Road |  | 3-In Transit |  | WorkPackLink | P07WH-R4FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-22 | GRST-5000288540_2024 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000042602 | 1020 | 2025-09-30 | 1 |  | 2024-11-21 | 4900176548_2024_0003 | 2025-03-01 |  | 5000288540_2024_0002 | 0 | 2 | 0 | 90025002 | 1 | 0 | 180096316 | 2 | 0 | 0 | X | L | 4900176548 | 2024 |  | 5000288540 | 2024 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255673 | PIPE,FLEX;NP SMR7741897 | 2024-09-22 | W |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 3 | Ready for Release | 9019880_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT7 | MJ | 1000004156 | AU1072 | 1000232868 | S002 |  | 30 | 5300015679 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2024-11-22 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235862 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDLN4 | Released | 2025-02-12 | 2025-03-31 |  | 2025-05-08 | 2025-05-09 | INLEC | 100033091 | 0010 | 0010 | 100033091 | OPSD Server lost conn to controller | AA53.414UZV408 | VALVE,CTRL 4KT1410 TRANSFER SERVOVALVE | AA01 | 30 | WO item has not been released yet | 10255819 | VALVE,SERVO;EX,MOOG G771K226A | 1 | EA | 4 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131575 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-P08-OPSD | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 |  |  | 2025-03-31 |  |  |  |  | 2024-11-16 | 0 |  |  |  |  | 414UZV408 |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255819 | VALVE,SERVO;EX,MOOG G771K226A |  |  |  | 0010 | Investigate / Calibrate MOOG - 414UZV408 | INT | Investigate / Calibrate MOOG - 414UZV408 | 5 | Opportune Shutdown |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 30 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000131006 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Opportune Shutdown |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 5 | Low | RC00025003 | 2025-05-09 | 2025-05-08 | 2025-05-08 | Pre-costed/Object created/Order Approved/Material committed/Released/Settlement rule created | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0250 | 3060 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10255925 | BEARING,GBX;FLENDGRAF 75A0023 | 2 | EA | 3 | 0 | 2 | 2 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091513, Item 435 cannot be changed 9026847 item 3060 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 3090 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122106 | 9026847 | 05 | Preparation | 0000129822 | 435 | 0 | EA | 102000000030369 |  | 107000000000766 |  |  |  |  | WorkPackLink | P07WH-R7FL |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-07-22 | GRST-5000389475_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056466 | 1020 | 2025-07-03 | 2 |  | 2025-02-05 | 4900228037_2025_0005 | 2025-03-01 |  | 5000389475_2025_0001 | 0 | 2 | 0 | 90028419 | 2 | 0 | 180122106 | 2 | 0 | 0 | X | L | 4900228037 | 2025 |  | 5000389475 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255925 | BEARING,GBX;FLENDGRAF 75A0023 | 2024-07-21 | W |  | 0250 | GEARBOX | INT | GEARBOX | 5 |  | 9026847_3060 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 435 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 |  | 30 | 5300013090 | 3090 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDLN4 | Released | 2024-01-02 | 2024-07-15 |  | 2025-05-08 | 2025-05-08 | INLEC | 100040405 | 0010 | 0040 | 100040405 | MOC-151032 OPSD2 Acc Gear Vibration Alar | AA53.414XE415 | TXDCR,SEISMIC VIBR ACC GEAR 4KT1410 | AA01 | 10 | WO item has not been released yet | 10256236 | REPLACED BY 10416216 | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138897 | 1 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-05-08 | [7 empty] | 2022-08-25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256236 | REPLACED BY 10416216 |  |  |  | 0010 | Investigate 4KT1410 Acc Gear Vibration | INT | Investigate 4KT1410 Acc Gear Vibration |  | Opportune Shutdown/Engineering Query/Management of Change |  |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [8 empty] | 10 |  |  | 0 |  | 0 |  | 25SDLN4 | MJ |  |  | 1000138307 |  |  | 99 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Opportune Shutdown/Engineering Query/Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100083354 | 0020 | 0010 | 100083354 | Solenoid Replace 414UZV50G 4KT1430 | AA53.414UZV50G | SOL,TRIP W/WTR STOP VLV OFFLINE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10256241 | VALVE,SLND;EX,NP REO045050200 | 1 | EA | 0 | 1 | 0 | 0 |  | 19.02 - ETA 23.05.25 PO 4500032210 BH FCA To be SCRd' to 2026 | Supply for Order 100083354, Item 1 cannot be changed 90025065 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016549 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025065 | 05 | Preparation | 0000259347 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090025065_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414UZV50G |  | 0 | 2 | 0 | 90025065 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256241 | VALVE,SLND;EX,NP REO045050200 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025065_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000255202 | S002 | 30 | 30 | 5300016549 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-08-27 | 259347 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDLN4 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-05-08 | 2025-05-08 | INLEC | 100083365 | 0020 | 0010 | 100083365 | Solenoid Replace 414UZV40G | AA53.414UZV40G | SOL,W/WTR STOP VLV OFFLINE | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10256241 | VALVE,SLND;EX,NP REO045050200 | 1 | EA | 0 | 1 | 0 | 0 |  | 19.02 - ETA 23.05.25 PO 4500032210 BH FCA To be SCRd' to 2026 | Supply for Order 100083365, Item 1 cannot be changed 90025066 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300016550 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025066 | 05 | Preparation | 0000259381 | 1 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090025066_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-03-01 |  |  |  |  | 2025-10-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 414UZV40G |  | 0 | 2 | 0 | 90025066 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256241 | VALVE,SLND;EX,NP REO045050200 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025066_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000255125 | S002 | 30 | 30 | 5300016550 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-08-27 | 259381 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
1 | 25SD2420 | Released | 2024-07-21 | 2025-03-01 |  | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0130 | 1940 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | WO item has not been released yet | 10256244 | HELICOIL;NP RFR331090000 | 8 | EA | 64 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000129822 | 515 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256244 | HELICOIL;NP RFR331090000 |  |  |  | 0130 | EXHAUST FRAME & DIFFUSER | INT | EXHAUST FRAME & DIFFUSER | 5 |  |  |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SD2420 | MJ |  |  | 1000129172 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0060 | 0050 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 6 | 0 | 5 | 1 | DR | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 11 cannot be changed 9026411 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180120059 | 9026411 | 05 | Preparation | 0000281227 | 11 | 0 | DR |  |  | 102000000031954 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000379672_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055189 | 1020 | 2026-06-30 | 1 |  | 2025-01-30 | 4900222803_2025_0003 | 2025-03-01 | 200177498 | 5000379672_2025_0002 | 0 | 2 | 0 | 90028588 | 1 | 0 | 180120059 | 2 | 0 | 0 | X | L | 4900222803 | 2025 |  | 5000379672 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 9026411_0110 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDGT7 | MJ | 1000005037 | AU1072 | 1000275664 | S002 | 30 | 30 | 5300020059 | 110 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177498 | 0040 | 0050 | 200177498 | 1Y Turbine WW - GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 6 | 0 | 5 | 1 | DR | 15.01 - SOH @ AA02 | Supply for Order 200177498, Item 5 cannot be changed 9026411 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020059 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180120059 | 9026411 | 05 | Preparation | 0000281227 | 5 | 0 | DR |  |  | 102000000031953 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000379672_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055189 | 1020 | 2026-06-30 | 1 |  | 2025-01-30 | 4900222803_2025_0001 | 2025-03-01 |  | 5000379672_2025_0001 | 0 | 2 | 0 | 90028588 | 1 | 0 | 180120059 | 2 | 0 | 0 | X | L | 4900222803 | 2025 |  | 5000379672 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 |  | 9026411_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDGT7 | MJ | 1000005037 | AU1072 | 1000275664 | S002 | 30 | 30 | 5300020059 | 50 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281227 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0040 | 0050 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 6 | 0 | 5 | 0 |  | DEL: 90028589 | Supply for Order 200177499, Item 5 cannot be changed 90028589 item 50 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 5 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 |  | 90028589_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 | 30 | 30 | 5300020060 | 50 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177499 | 0060 | 0050 | 200177499 | 1Y Turbine WW - GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 6 | 0 | 5 | 0 |  | 07.03 - SOH @ AA53 | Supply for Order 200177499, Item 11 cannot be changed 90028589 item 110 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020060 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90028589 | 05 | Preparation | 0000281238 | 11 | 0 | [8 empty] | WorkPackLink |  | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028589_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200177499 |  | 0 | 2 | 0 | 90028589 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 |  | 90028589_0110 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000275665 | S002 | 30 | 30 | 5300020060 | 110 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281238 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0060 | 0050 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 6 | 0 | 5 | 1 | DR | 07.03 - SOH @ AA53 | Supply for Order 200177720, Item 11 cannot be changed 9026412 item 110 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180120064 | 9026412 | 05 | Preparation | 0000281240 | 11 | 0 | DR |  |  | 102000000031952 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000379619_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055190 | 1020 | 2025-06-30 | 1 |  | 2025-01-30 | 4900222777_2025_0003 | 2025-03-01 | 200177720 | 5000379619_2025_0002 | 0 | 2 | 0 | 90028590 | 1 | 0 | 180120064 | 2 | 0 | 0 | X | L | 4900222777 | 2025 |  | 5000379619 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 2025-01-14 | W |  | 0060 | Water Wash Soak/Rinse/Dry | INT | Water Wash Soak/Rinse/Dry | 3 | Ready for Release | 9026412_0110 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDGT9 | MJ | 1000005037 | AU1072 | 1000275666 | S002 | 30 | 30 | 5300020061 | 110 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-15 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200177720 | 0040 | 0050 | 200177720 | 1Y Turbine WW - GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 |  | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 6 | 0 | 5 | 1 | DR | 15.01 - Needs purchase req | Supply for Order 200177720, Item 5 cannot be changed 9026412 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300020061 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180120064 | 9026412 | 05 | Preparation | 0000281240 | 5 | 0 | DR |  |  | 102000000031951 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-01-15 | GRST-5000379619_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000055190 | 1020 | 2025-06-30 | 1 |  | 2025-01-30 | 4900222777_2025_0001 | 2025-03-01 |  | 5000379619_2025_0001 | 0 | 2 | 0 | 90028590 | 1 | 0 | 180120064 | 2 | 0 | 0 | X | L | 4900222777 | 2025 |  | 5000379619 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 2025-01-14 | W |  | 0040 | Lineup Permissive to Start WW | INT | Lineup Permissive to Start WW | 3 | Ready for Release | 9026412_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDGT9 | MJ | 1000005037 | AU1072 | 1000275666 | S002 | 30 | 30 | 5300020061 | 50 |  |  | 0 | 1 | DR | 2001 | AA02 | 2025-02-24 |  | Ready for Release | 2025-02-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-12-02 | 281240 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDDG1 | Released | 2025-02-11 | 2025-03-12 | 2025-03-07 | 2025-03-01 | 2025-06-06 | MECH | 100086858 | 0120 | 0010 | 100086858 | 1E2406 externally corroded tube ends | AA53.1E2406 | EXCH,HEAT AFTER COOLER FOR COMPR | AA01 | 10 | No Issue identified | 10257020 | GASKET;36X29X3MMTHK,HUDSON 36293SI | 1750 | EA | 10 | 0 | 0 | 10 | EA | 11.02 - qty 1,510 SOH @ AA01 |  | Material picked; currently at SW3R01E02B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300021137 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030839 | 05 | Preparation | 0000275554 | 3 | 0 | EA |  |  | 102000000034496 |  |  |  |  | WorkPackLink | SW3R01E02B | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 1750 |  |  | Y | 1001 | 2025-02-11 | ODST-0090030839_0010 | 0 | 0 | 0 | 0 |  | 2025-03-10 | AA53 | 2025-03-12 |  |  | 2025-03-12 |  |  |  |  | 2025-10-31 | 0 |  | 2025-03-07 |  | 2025-03-12 | 100086858 |  | 0 | 2 | 0 | 90030839 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-03-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257020 | GASKET;36X29X3MMTHK,HUDSON 36293SI |  |  |  | 0120 | Re-instate Plugs | INT | Re-instate Plugs |  |  | 90030839_0010 |  |  | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDDG1 | MJ |  | AU1072 | 1000270168 | S002 |  | 30 | 5300021137 | 10 |  |  | 0 | 1750 | EA | 2001 | AA02 | 2025-03-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-06 | 275554 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-06-06 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2025-02-11 | 2025-04-29 | 2025-04-24 | 2025-03-01 | 2025-05-11 | MECH | 100086859 | 0120 | 0010 | 100086859 | 1E2405 externally corroded tube ends | AA53.1E2405 | EXCH,HEAT AFTER COOLER FOR COMPR | AA01 | 10 | No Issue identified | 10257020 | GASKET;36X29X3MMTHK,HUDSON 36293SI | 880 | EA | 10 | 0 | 0 | 0 |  | 26.02 - ETA 18.04.25 PO 4500047665 JORD FCA |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300021138 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000275555 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-DG-P07 | 0 |  | 0 | 0 |  | 0 | 880 |  |  | Y | 1001 | 2025-02-11 | STST-5300021138_00010 | 0 | 0 | 0 | 0 |  | 2025-04-27 | AA53 | 2025-04-29 |  |  | 2025-04-29 |  |  |  |  | 2025-10-31 | 0 |  | 2025-04-24 |  | 2025-04-29 | 100086859 |  | 0 | 2 | 0 |  | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-04-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257020 | GASKET;36X29X3MMTHK,HUDSON 36293SI |  |  |  | 0120 | Re-instate Plugs | INT | Re-instate Plugs | [5 empty] | DG1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000270169 | S002 |  | 30 | 5300021138 | 10 |  |  | 0 | 880 | EA | 2001 | AA02 | 2025-04-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-11-06 | 275555 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-11 | 2025-03-01 | 2025-03-01 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | VALVE | 100032671 | 0010 | 0040 | 100032671 | CV-OH 1" 300# 118TCV503 | AA53.118TCV503 | VALVE,K1820E1 S/OIL COOLER BYPASS TEMP | AA01 | 20 | No issue identified | 10257416 | O-RING;NITRILE-DS52-1,FISHER 1E591406992 | 1 | EA | 3 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019089 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028287 | 05 | Preparation | 0000131163 | 6 | 0 | EA | 102000000033928 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-12 | ODST-0090028287_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028287 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257416 | O-RING;NITRILE-DS52-1,FISHER 1E591406992 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028287_0040 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130513 | S002 |  | 30 | 5300019089 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131163 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | VALVE | 100032672 | 0010 | 0030 | 100032672 | CV-OH 1" 300# 118LCV505 | AA53.118LCV505 | VALVE,S/OIL O/H TK 1K1820V1 LVL CTRL | AA01 | 20 | No issue identified | 10257416 | O-RING;NITRILE-DS52-1,FISHER 1E591406992 | 1 | EA | 3 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019173 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028289 | 05 | Preparation | 0000131164 | 7 | 0 | EA | 102000000033932 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028289_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028289 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257416 | O-RING;NITRILE-DS52-1,FISHER 1E591406992 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028289_0010 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 7 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130514 | S002 |  | 30 | 5300019173 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131164 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-12-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-15 | VALVE | 100032674 | 0010 | 0040 | 100032674 | CV-OH 1" 300# 118LCV510 | AA53.118LCV510 | VALVE,S/OIL DRN POT K1820V4B LOCAL LVL | AA01 | 20 | No issue identified | 10257416 | O-RING;NITRILE-DS52-1,FISHER 1E591406992 | 1 | EA | 3 | 0 | 0 | 1 | EA | 19.02 - SOH @ AA02 |  | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300019174 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028290 | 05 | Preparation | 0000131166 | 8 | 0 | EA | 102000000033930 |  | 102000000033277 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-12-16 | ODST-0090028290_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028290 | 0 | 0 |  | 3 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257416 | O-RING;NITRILE-DS52-1,FISHER 1E591406992 |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90028290_0040 |  |  | FR1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 8 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000130516 | S002 |  | 30 | 5300019174 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131166 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-15 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | VALVE | 600001792 | 0035 | 0050 | 600001792 | MOC-89054 Install New CV-118UCV112 | AA53.1E1801 | EXCH,HEAT DE-ETH REBOIL FRAC 1 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10257642 | GLAND,CABLE,E1EX-00,EX(DE),SIZE 00-20SS | 2 | EA | 9 | 0 | 16 | 2 | EA | 02.10 - SOH @ AA02 | Supply for Order 600001792, Item 8 cannot be changed 90024967 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004604 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024967 | 05 | Preparation | 0000084710 | 8 | 0 | EA | 102000000032121 | 102000000029217 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024967_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 118UCV112 |  | 0 | 2 | 0 | 90024967 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257642 | GLAND,CABLE,E1EX-00,EX(DE),SIZE 00-20SS | 2024-01-02 | W |  | 0035 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90024967_0050 |  |  | FR1 |  | C3 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000084094 | S002 | 30 | 30 | 5300004604 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84710 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM06 | Capital
| 25SDFLR | Released | 2024-11-08 | 2025-03-01 | 2025-02-24 | 2025-02-08 | 2025-05-04 | INLEC | 600001815 | 0010 | 0170 | 600001815 | MOC-119237 Replace Flare Flowmtr 37FQI40 | AA53.37FQI40 | LOOP,MASS FLOW TO FLARE A3711A | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(06.02.2025) | 10257695 | PLATE;END,WEIDMULLER 1050000000 | 10 | EA | 10 | 0 | 11 | 0 |  | 06.03 - SOH @ AA02 | Supply for Order 600001815, Item 23 cannot be changed 90030415 item 150 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007843 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90030415 | 07 | Execution | 0000084731 | 23 | 0 | [8 empty] | WorkPackLink |  | T25-W1-SL1-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-03-13 | ODST-0090030415_0150 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-02-08 |  |  | 2025-03-01 |  |  |  |  | 2024-08-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | FAR12 |  | 0 | 2 | 0 | 90030415 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257695 | PLATE;END,WEIDMULLER 1050000000 | 2025-02-06 | W |  | 0010 | MEA INLEC Pre TA Labour | INT | MEA INLEC Pre TA Labour |  |  | 90030415_0150 |  |  | SL0 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 10 |  |  | 23 |  | 0 |  | 25SDFLR | MJ |  | AU1072 | 1000084145 | S002 | 30 | 30 | 5300007843 | 180 |  |  | 0 | 10 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  | 2025-02-08 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84731 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00018003 | 2025-05-04 | 2025-02-08 | 2025-02-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Ready For Scheduling/Partially confirmed | AM06 | Capital | C0-001035-6A-08-01
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089472 | 0060 | 0020 | 200089472 | 2Y Turbine WW - 4KT1410 | AA53.4KT1410 | TURB,GAS FOR 4K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 8 | EA | 142 | 0 | 4 | 8 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089472, Item 9 cannot be changed 90028583 item 90 already exists | Material picked; currently at SW3R01F02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020057 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028583 | 05 | Preparation | 0000127730 | 9 | 0 | EA |  |  | 102000000033541 |  |  |  |  | WorkPackLink | SW3R01F02A | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028583_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089472 |  | 0 | 2 | 0 | 90028583 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028583_0090 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 9 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127141 | S002 | 30 | 30 | 5300020057 | 90 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2025-01-15 | 2025-05-08 | 2025-02-24 | 2025-05-08 | 2025-05-08 | ROTAT | 200089473 | 0060 | 0020 | 200089473 | 2Y Turbine WW - 4KT1430 | AA53.4KT1430 | TURB,GAS FOR 4K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 8 | EA | 142 | 0 | 4 | 8 | EA | 15.01 - SOH @ AA02 | Supply for Order 200089473, Item 2 cannot be changed 90028584 item 20 already exists | Material picked; currently at SW3R01F02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020058 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028584 | 05 | Preparation | 0000127731 | 2 | 0 | EA |  |  | 102000000033540 |  |  |  |  | WorkPackLink | SW3R01F02A | P07 TA ROT 2025 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2025-01-15 | ODST-0090028584_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-05-08 |  |  | 2025-05-08 |  |  |  |  | 2024-09-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200089473 |  | 0 | 2 | 0 | 90028584 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2025-01-14 | W |  | 0060 | Remove WW Spades | INT | Remove WW Spades | 5 | Ready for Release | 90028584_0020 |  |  | LN4 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDLN4 | MJ |  | AU1072 | 1000127142 | S002 | 30 | 30 | 5300020058 | 20 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127731 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0150 | 0020 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 142 | 0 | 4 | 4 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089887, Item 11 cannot be changed 90025037 item 110 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 11 | 0 | EA | 102000000031995 | 102000000027846 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0110 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Flame Eye |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2024-10-16 | W |  | 0150 | Mechanical Restoration Post Waterwash | INT | Mechanical Restoration Post Waterwash | 5 | Ready for Release | 90025037_0110 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 11 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 110 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089887 | 0130 | 0010 | 200089887 | 2Y Turbine WW & AF Change - 1KT1410 | AA53.1KT1410 | TURB,DRIVER FOR 1K1410 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 142 | 0 | 4 | 4 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089887, Item 6 cannot be changed 90025037 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016467 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025037 | 05 | Preparation | 0000128156 | 6 | 0 | EA | 102000000031999 | 102000000027845 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025037_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Flame Eye |  | 0 | 2 | 0 | 90025037 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2024-10-16 | W |  | 0130 | Mechanical Preparation for Waterwash | INT | Mechanical Preparation for Waterwash | 5 | Ready for Release | 90025037_0060 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127566 | S002 | 30 | 30 | 5300016467 | 60 |  |  | 0 | 4 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128156 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089888 | 0120 | 0070 | 200089888 | 2Y Turbine WW & AF Change - 1KT1420 | AA53.1KT1420 | TURB,DRIVER FOR 1K1420 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 8 | EA | 142 | 0 | 4 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089888, Item 15 cannot be changed 90025038 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016473 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025038 | 05 | Preparation | 0000128157 | 15 | 0 | EA | 102000000032002 | 102000000027847 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025038_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025038 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025038_0090 |  |  | LN1 |  | A2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127567 | S002 | 30 | 30 | 5300016473 | 90 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128157 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089889 | 0120 | 0060 | 200089889 | 2Y Turbine WW & AF Change - 1KT1430 | AA53.1KT1430 | TURB,DRIVER FOR 1K1430 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 8 | EA | 142 | 0 | 4 | 8 | EA | 17.10 - SOH @ AA02 | Supply for Order 200089889, Item 15 cannot be changed 90025039 item 90 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016474 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025039 | 05 | Preparation | 0000128158 | 15 | 0 | EA | 102000000032028 | 102000000027842 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025039_0090 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025039 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2024-10-16 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025039_0090 |  |  | LN1 |  | B5 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 15 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127568 | S002 | 30 | 30 | 5300016474 | 90 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128158 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-06-01 | 2025-05-27 | 2025-03-01 | 2025-03-02 | ROTAT | 200089890 | 0120 | 0020 | 200089890 | 2Y Turbine WW & AF Change - 1KT1440 | AA53.1KT1440 | TURB,DRIVER FOR 1K1440 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 8 | EA | 142 | 0 | 4 | 8 | EA | 18.10 - SOH @ AA02 | Supply for Order 200089890, Item 18 cannot be changed 90025060 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016541 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025060 | 05 | Preparation | 0000128159 | 18 | 0 | EA | 102000000032017 | 102000000027844 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025060_0010 | 0 | 0 | 0 | 0 |  | 2025-05-30 | AA53 | 2025-03-01 |  |  | 2025-06-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-05-27 |  | 2025-06-01 | Isolations |  | 0 | 2 | 0 | 90025060 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-05-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025060_0010 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 18 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127569 | S002 | 30 | 30 | 5300016541 | 40 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-05-27 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128159 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDLN1 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | ROTAT | 200089891 | 0120 | 0020 | 200089891 | 2Y Turbine WW & AF Change - 1KT1450 | AA53.1KT1450 | TURB,DRIVER FLASH GAS COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 8 | EA | 142 | 0 | 4 | 8 | EA | 18.10 - SOH @ AA02 | Supply for Order 200089891, Item 12 cannot be changed 90025062 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016543 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025062 | 05 | Preparation | 0000128160 | 12 | 0 | EA | 102000000032020 | 102000000027843 | 102000000032035 |  |  |  | LP-SD-C11 | WorkPackLink | PACKING-SD | T25-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025062_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-07-12 | 0 |  | 2025-02-24 |  | 2025-03-01 | Isolations |  | 0 | 2 | 0 | 90025062 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2024-10-17 | W |  | 0120 | Positively Isolate Turbine for Waterwash | INT | Positively Isolate Turbine for Waterwash |  | Ready for Release | 90025062_0050 |  |  | LN1 |  | B4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 12 |  | 0 |  | 25SDLN1 | MJ |  | AU1072 | 1000127570 | S002 | 30 | 30 | 5300016543 | 50 |  |  | 0 | 8 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128160 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0040 | 0510 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 24 | EA | 142 | 0 | 4 | 24 | EA | 24.09 - SOH at AA02 | Supply for Order 200091513, Item 51 cannot be changed 90028419 item 430 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 440 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 51 | 0 | EA | 102000000030481 | 102000000030657 | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_0430 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 2024-07-21 | W |  | 0040 | COMBUSTION COMPONENTS | INT | COMBUSTION COMPONENTS | 5 |  | 90028419_0430 |  |  | DG1 |  | A4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 51 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 440 |  |  | 0 | 24 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDLN1 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144602 | 0010 | 0020 | 200144602 | 2Y Flame Eyes F/Test/Repl (4) 1KT1410 | AA53.114XE306A | DET,FLAME LOSS IN CHAMBER 2 KT1410 | AA01 | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 142 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231727 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228874 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144603 | 0010 | 0020 | 200144603 | 2Y Flame Eyes F/Test/Repl (4) 1KT1420 | AA53.114XE406A | DET,FLAME LOSS IN CHAMBER 2 KT1420 | AA01 | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 142 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231728 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228875 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144604 | 0010 | 0020 | 200144604 | 2Y Flame Eyes F/Test/Repl (4) 1KT1430 | AA53.114XE506A | DET,FLAME LOSS IN CHAMBER 2 KT1430 | AA01 | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 142 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231729 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228876 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-10-16 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144605 | 0010 | 0020 | 200144605 | 2Y Flame Eyes F/Test/Repl (4) 1KT1440 | AA53.114XE606A | DET,FLAME LOSS IN CHAMBER 2 KT1440 | AA01 | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 142 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231730 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228877 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
1 | 25SDLN1 | Released | 2024-10-17 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | INLEC | 200144606 | 0010 | 0020 | 200144606 | 2Y Flame Eyes F/Test/Repl (4) 1KT1450 | AA53.114XE706A | DET,FLAME LOSS IN CHAMBER 1 KT1450 | AA01 | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 142 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000231731 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-10-30 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  |  |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  |  |  |  | LN1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 5 |  |  | 0 |  | 0 |  | 25SDLN1 | MJ |  |  | 1000228878 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-04-12 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0120 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Shipped qty below requirement qty | 10258204 | DRILL,PANEL,COBALT,TWIN POINT,NO.11 | 50 | EA | 59 | 0 | 13 | 13 | EA | 24.02 - SOH @ AA01 | Supply for Order 500005166, Item 14 cannot be changed 90031023 item 120 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180132201 | 9028444 | 05 | Preparation | 0000294187 | 14 | 0 | EA |  |  | 102000000033429 | 01-Road |  | 3-In Transit |  | WorkPackLink | KSF-P07-SD-SML | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 37 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427540_2025 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 |  |  | 100000060206 | 1020 |  | 13 |  | 2025-03-05 | 4900257474_2025_0005 | 2025-03-11 | TA LAG_VORN | 5000427540_2025_0003 | 0 | 2 | 0 | 90031023 | 13 | 0 | 180132201 | 1 | 0 | 0 | X | L | 4900257474 | 2025 |  | 5000427540 | 2025 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258204 | DRILL,PANEL,COBALT,TWIN POINT,NO.11 | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0120/9028444_0120 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 14 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 |  | 30 | 5300021227 | 130 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-03-06 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0080 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10258205 | DRILL,PANEL,COBALT,TWIN POINT,NO.30 | 50 | EA | 0 | 20 | 260 | 0 |  | 10.03 - DEL: 80015125 | Supply for Order 100090053, Item 8 cannot be changed 90032376 item 80 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90032376 | 05 | Preparation | 0000289018 | 8 | 0 | [8 empty] | WorkPackLink |  | P07 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-03-04 | ODST-0090032376_0080 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  |  |  | 2025-07-31 | 0 |  | 2025-03-28 |  | 2025-04-02 | 3E1405/Vorn |  | 0 | 2 | 0 | 90032376 | 0 | 0 |  | 1 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258205 | DRILL,PANEL,COBALT,TWIN POINT,NO.30 | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0080 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 8 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 |  | 30 | 5300022012 | 80 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0100 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10258205 | DRILL,PANEL,COBALT,TWIN POINT,NO.30 | 10 | EA | 0 | 20 | 260 | 0 |  | 13.02 - qty 60 SOH @ AA01 | Supply for Order 200089373, Item 10 cannot be changed 90023594 item 100 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023594 | 07 | Execution | 0000127667 | 10 | 0 | [8 empty] | WorkPackLink |  | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-11-05 | ODST-0090023594_0100 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  |  |  | 2025-12-15 | 0 |  | 2024-11-05 |  | 2024-11-10 | Troy Mac |  | 0 | 2 | 0 | 90023594 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258205 | DRILL,PANEL,COBALT,TWIN POINT,NO.30 | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 90023594_0100 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 10 |  | 0 |  | 25SDFR2 | MJ |  | AU1072 | 1000127056 | S002 |  | 30 | 5300017449 | 100 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0090 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Shipped qty below requirement qty | 10258205 | DRILL,PANEL,COBALT,TWIN POINT,NO.30 | 50 | EA | 0 | 20 | 260 | 30 | EA | 19.02 - SOH @ AA02 | Supply for Order 500005166, Item 11 cannot be changed 90031023 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180127512 | 9027345 | 05 | Preparation | 0000294187 | 11 | 0 | EA |  |  | 101000000143207 |  |  |  |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2025-02-13 | GRST-5000409627_2025 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 |  |  | 100000058189 | 1020 |  | 30 |  | 2025-02-20 | 4900242651_2025_0001 | 2025-03-11 | TA LAG_VORN | 5000409627_2025_0001 | 0 | 2 | 0 | 90031023 | 30 | 0 | 180127512 | 1 | 0 | 0 | X | L | 4900242651 | 2025 |  | 5000409627 | 2025 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258205 | DRILL,PANEL,COBALT,TWIN POINT,NO.30 | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 90031023_0090/9027345_0090 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 11 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 |  | 30 | 5300021227 | 100 |  |  | 0 | 50 | EA | 2001 | AA02 | 2025-03-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDLN3 | Released | 2025-03-04 | 2025-04-02 | 2025-03-28 | 2025-05-23 | 2025-08-13 | MECH | 100090053 | 0010 | 0100 | 100090053 | LNG3 MCHE Natural Gas Tube Leak Repairs | AA53.3E1405 | EXCH,HEAT MAIN CRYOGENIC | AA01 | 10 | Issue detected, please check message in derivation or orchestration log | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 50 | ROL | 139 | 43 | 612 | 24 | ROL | 10.03 - SOH @ AA02 | Supply for Order 100090053, Item 10 cannot be changed 90032376 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300022012 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180134141 | 9029112 | 05 | Preparation | 0000289018 | 10 | 0 | ROL |  |  | 101000000150540 |  |  |  |  | WorkPackLink | KSF-P07-SD-SML | P07 | 0 |  | 0 | 0 |  | 0 | 26 |  |  | Y | 1001 | 2025-03-04 | GRST-5000435313_2025 | 0 | 0 | 0 | 0 |  | 2025-03-31 | AA53 | 2025-05-23 |  |  | 2025-04-02 |  |  | 100000060593 | 1020 | 2025-07-31 | 24 |  | 2025-03-10 | 4900263706_2025_0001 | 2025-04-02 | 3E1405/Vorn | 5000435313_2025_0001 | 0 | 2 | 0 | 90032376 | 24 | 0 | 180134141 | 1 | 0 | 0 | X | L | 4900263706 | 2025 |  | 5000435313 | 2025 | 0 |  | 2025-03-28 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 2025-03-04 | W |  | 0010 | Pre Shut Scaffold 3E1405 | INT | Pre Shut Scaffold 3E1405 |  |  | 90032376_0100/9029112_0100 |  |  | LN3 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 10 |  |  | 10 |  | 0 |  | 25SDLN3 | MJ |  | AU1072 | 1000283045 | S002 | 30 | 30 | 5300022012 | 100 |  |  | 0 | 50 | ROL | 2001 | AA02 | 2025-03-28 |  |  |  |  | 1070 |  | 2025-02-21 | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2025-01-07 | 289018 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 3 | High | RC00025003 | 2025-08-13 | 2025-05-23 | 2025-05-23 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created/Partially confirmed/Printed | AM01 | Reactive Maintenance
| 25SDFR2 | Released | 2024-11-05 | 2025-03-09 | 2024-11-05 | 2024-11-03 | 2025-03-29 | INSP | 200089373 | 0020 | 0030 | 200089373 | 6Y P02 CVI-CUI EXCH INSP 2E1804 | AA53.2E1804 | EXCH,HEAT DEPROPANISER REBOIL FRAC2 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(05.11.2024) | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 6 | ROL | 139 | 43 | 612 | 6 | ROL | Workpacked at KGP | Supply for Order 200089373, Item 3 cannot be changed 180091768 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300017449 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180091768 | 9019016 | 07 | Execution | 0000127667 | 3 | 0 | ROL |  |  | 102000000023516 | 01-Road |  | 1-Not Started |  | WorkPackLink | KSF-KGP-RUNNER-SML | STONE HENGE | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-05 | GRST-5000275082_2024 | 0 | 0 | 0 | 0 |  | 2024-11-06 | AA53 | 2025-03-09 |  |  | 2025-03-09 |  |  | 100000040386 | 1020 | 2025-12-15 | 6 |  | 2024-11-11 | 4900169565_2024_0005 | 2024-11-10 | Troy Mac | 5000275082_2024_0001 | 0 | 2 | 0 | 90023594 | 6 | 0 | 180091768 | 2 | 0 | 0 | X | L | 4900169565 | 2024 |  | 5000275082 | 2024 | 0 |  | 2024-11-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 2024-11-05 | W |  | 0020 | REMOVE LAGGING / INSULATION | ENON | REMOVE LAGGING / INSULATION | 0 |  | 9019016_0030 |  |  | FR2 | [5 empty] | Z2 | WEG Proactive | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDFR2 | MJ | 1000004072 | AU1072 | 1000127056 | S002 | 30 | 30 | 5300017449 | 30 |  |  | 0 | 6 | ROL | 2001 | AA02 | 2024-11-05 |  |  |  |  | 1070 |  | 2024-11-27 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127667 | 0 | 0 |  | 1020 | 1 | PJ | Project | 1 | Critical Work | RC00025003 | 2025-03-29 | 2024-11-03 | 2024-11-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Partially confirmed/Material committed | AM02 | Proactive Maintenance
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0030 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 120 | ROL | 139 | 43 | 612 | 8 | ROL | 26.02 - SOH @ AA02 | Supply for Order 500005166, Item 4 cannot be changed 9028444 item 30 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132244 | 9028623 | 05 | Preparation | 0000294187 | 4 | 0 | ROL |  |  | 102000000034000 | 01-Road |  | 3-In Transit |  | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427669 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 |  |  | 100000060109 | 1020 |  | 120 |  | 2025-03-05 | 4900257512_2025_0001/4900257474_2025_0001 | 2025-03-11 | TA LAG_VORN | 5000427669_2025_0001/5000427540_2025_0001 | 0 | 2 | 0 | 90031023 | 120 | 0 | 180132201/180132244 | 2 | 0 | 0 | X | L | 4900257512 | 2025 |  | 5000427669 | 2025 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 9028623_0030/9028444_0030 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 40 |  |  | 0 | 120 | ROL | 2001 | AA02 | 2025-03-06 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0030 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 120 | ROL | 139 | 43 | 612 | 88 | ROL | 26.02 - SOH @ AA02 | Supply for Order 500005166, Item 4 cannot be changed 9028444 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132244 | 9028623 | 05 | Preparation | 0000294187 | 4 | 0 | ROL |  |  | 102000000033940 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427669_2025 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 |  |  | 100000060109 | 1020 |  | 120 |  | 2025-03-05 | 4900257512_2025_0001/4900257474_2025_0001 | 2025-03-11 | TA LAG_VORN | 5000427669_2025_0001/5000427540_2025_0001 | 0 | 2 | 0 | 90031023 | 120 | 0 | 180132201/180132244 | 2 | 0 | 0 | X | L | 4900257512 | 2025 |  | 5000427669 | 2025 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 9028623_0030/9028444_0030 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 40 |  |  | 0 | 120 | ROL | 2001 | AA02 | 2025-03-06 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-03-11 | 2025-03-06 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0030 | 0030 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(14.02.2025) | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 120 | ROL | 139 | 43 | 612 | 24 | ROL | 26.02 - SOH @ AA02 | Supply for Order 500005166, Item 4 cannot be changed 9028444 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180132244 | 9028623 | 05 | Preparation | 0000294187 | 4 | 0 | ROL |  |  | 102000000033482 | 01-Road |  | 3-In Transit |  | WorkPackLink | 2025-SD-INSULATION | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2025-02-13 | GRST-5000427669_2025 | 0 | 0 | 0 | 0 |  | 2025-03-09 | AA53 | 2025-04-01 |  |  | 2025-03-11 |  |  | 100000060109 | 1020 |  | 120 |  | 2025-03-05 | 4900257512_2025_0001/4900257474_2025_0001 | 2025-03-11 | TA LAG_VORN | 5000427669_2025_0001/5000427540_2025_0001 | 0 | 2 | 0 | 90031023 | 120 | 0 | 180132201/180132244 | 2 | 0 | 0 | X | L | 4900257512 | 2025 |  | 5000427669 | 2025 | 0 |  | 2025-03-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258207 | TAPE:CLOTH,48mmX25m,BLK | 2025-02-14 | W |  | 0030 | 2025 - Consumables - Insulation Bulk | NCNF | 2025 - Consumables - Insulation Bulk |  |  | 9028623_0030/9028444_0030 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 4 |  | 0 |  | 25SDENA1 | MJ | 1000005306 | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 40 |  |  | 0 | 120 | ROL | 2001 | AA02 | 2025-03-06 |  |  | 2025-03-05 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
| 25SDENA1 | Released | 2025-02-05 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 2025-04-01 | NOMAINT | 500005166 | 0020 | 0320 | 500005166 | 2025 - KGP Turnaround Consumables | AA53.1000 | KGP Non-Maintenance | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(21.02.2025) | 10258215 | INSLN:FIBERMESH;4MX1000MM,50MM | 50 | ROL | 28 | 0 | 6 | 0 |  | 24.02 - ETA 03.04.25 PO 4500047066 ARMACELL AUS CPT | Supply for Order 500005166, Item 54 cannot be changed 90031501 item 330 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300021227 | 490 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90031501 | 05 | Preparation | 0000294187 | 54 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2025-02-13 | ODST-0090031501_0330 | 0 | 0 | 0 | 0 |  | 2025-03-30 | AA53 | 2025-04-01 |  |  | 2025-04-01 | [5 empty] | 0 |  | 2025-03-27 |  | 2025-04-01 | TA LAG_VORN |  | 0 | 2 | 0 | 90031501 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-03-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258215 | INSLN:FIBERMESH;4MX1000MM,50MM | 2025-02-21 | W |  | 0020 | 2025 - Materials - Insulation Bulk | NCNF | 2025 - Materials - Insulation Bulk |  |  | 90031501_0330 | [8 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 99 |  |  | 54 |  | 0 |  | 25SDENA1 | MJ |  | AU1072 | 1000287811 | S002 | 30 | 30 | 5300021227 | 490 |  |  | 0 | 50 | ROL | 2001 | AA02 | 2025-03-27 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W39541 | 2025-02-04 | 294187 | 0 | 0 |  | 1020 | 1 | SD | Shutdown |  |  | RC00025003 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Pre-costed/Object created/Released/Settlement rule created/Error in cost calculation/Material shortage | AM05 | Non-Execution
1 | 25SDFR2 | Released | 2024-02-13 | 2025-03-01 |  | 2025-03-01 | 2025-05-31 | PROJ | 100041374 | 0090 | 0010 | 100041374 | KLE- Blast and Paint CL1801 | AA53.CL1801 | LOOP,CORR CL1801 | AA01 | 255 | WO item has not been released yet | 10258236 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX SPI | 2 | EA | 30 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139858 | 1 | 0 | [8 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 | [7 empty] | 2026-02-01 | 0 |  |  |  |  | TALag_B.Vorn |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  | 30POST | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258236 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX SPI |  |  |  | 0090 | Install Cladding at CL1801 | ENON | Install Cladding at CL1801 | 5 |  |  |  |  | LN0 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | [8 empty] | 99 |  |  | 0 |  | 0 |  | 25SDFR2 | MJ |  |  | 1000139289 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 2 |  |  | 2 | PJ | Project | 6 | Very Low | RC00025003 | 2025-05-31 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Ready For Scheduling Canceled/Material committed | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-22 | 2025-03-01 | 2025-02-18 | 2025-03-01 | 2025-03-07 | MECH | 100087648 | 0110 | 0010 | 100087648 | Replace Re-boiler Bundle 5E2001 | AA53.5E2001 | EXCH,VESSEL REBOIL STAB MODIFIED 5C2001 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(18.02.2025) | 10258236 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX SPI | 1 | EA | 30 | 0 | 30 | 0 |  | 24.02 - ETA 07.03.25 PO 4500047066 ARMACELL AUS CPT | Supply for Order 100087648, Item 34 cannot be changed 90031095 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 30 | AA01 | 5300018313 | 40 | DDP | 7 | 1000030203 | 34 | 30005435 | ARMACELL AUSTRALIA ENGINEERING PTY | 4500047066 | 10 | 1 | EA | 2025-03-27 |  |  |  | 90031095 | 05 | Preparation | 0000278190 | 34 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-11-23 | ODST-0090031095_0010 | 0 | 44 | 39 | 44 | 2025-03-27 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-04-14 | 2025-03-29 | 2025-04-09 |  |  | 2025-12-02 | 0 |  | 2025-02-18 |  | 2025-03-01 | TA LAG_VORN |  | 0 | 2 | 2 | 90031095 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258236 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX SPI | 2025-02-18 | W |  | 0110 | Replace insulation & cladding | INT | Replace insulation & cladding |  |  | 90031095_0010 |  |  | ST5 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2025-02-18 | 10 | 6000015614 | 2025-03-29 | 0 |  | 0 |  | 25SDSTB5 | MJ |  | AU1009 | 1000272706 | S001 | 30 | 30 | 5300018296 | 330 |  | 5300018313 | 40 | 1 | EA | 1001 | AA02 | 2025-02-18 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGKW | 2024-11-19 | 0 | 0 | 2 |  | 1010 | 3 | SD | Shutdown | 3 | High | RC00025003 | 2025-03-07 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | M0-000001-99-02
| 25SD2420 | Released | 2024-03-12 | 2025-03-01 | 2024-07-19 | 2025-03-01 | 2025-03-01 | INLEC | 200065935 | 0010 | 0040 | 200065935 | 6Y Vib/Speed Probe Repl (7) 1K2420 | AA53.124GE026 | TXDCR,TRIP VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.03.2024) | 10258304 | PROBE,VIB;EX,BENTLY 331010061100205 | 6 | EA | 8 | 0 | 0 | 6 | EA | 25.09 - At KGP | Supply for Order 200065935, Item 4 cannot be changed 180053095 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300008306 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180053095 | 9009209 | 05 | Preparation | 0000100270 | 4 | 0 | EA |  |  | 102000000007257 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08C11L2 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-03-25 | GRST-5000159428_2024 | 0 | 0 | 0 | 0 |  | 2024-07-20 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000021355 | 1020 | 2025-07-31 | 6 |  | 2024-08-02 | 4900103330_2024_0003 | 2024-07-22 | 200065935 | 5000159428_2024_0002 | 0 | 2 | 0 | 90011040 | 6 | 0 | 180053095/180073889 | 2 | 0 | 0 | X | L | 4900103330 | 2024 |  | 5000159428 | 2024 | 0 |  | 2024-07-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258304 | PROBE,VIB;EX,BENTLY 331010061100205 | 2024-03-25 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 9009209_0040 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SD2420 | MJ | 1000002619 | AU1072 | 1000099654 | S002 | 30 | 30 | 5300008306 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-07-19 |  |  | 2024-08-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100270 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-03-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200065935 | 0010 | 0060 | 200065935 | 6Y Vib/Speed Probe Repl (7) 1K2420 | AA53.124GE026 | TXDCR,TRIP VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10258304 | PROBE,VIB;EX,BENTLY 331010061100205 | 6 | EA | 8 | 0 | 0 | 0 |  | 16.12 - SOH @ AA02 | Supply for Order 200065935, Item 7 cannot be changed 90028268 item 20 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300008306 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028268 | 05 | Preparation | 0000100270 | 7 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-03-25 | ODST-0090028268_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200065935 |  | 0 | 2 | 0 | 90028268 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258304 | PROBE,VIB;EX,BENTLY 331010061100205 | 2024-12-13 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90028268_0020 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000099654 | S002 | 30 | 30 | 5300008306 | 70 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100270 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-09-22 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200147409 | 0010 | 0050 | 200147409 | 6Y CV-RE 2.5 600# Act BUV - 408XV575 | AA53.408XV575 | VALVE,FLOW CONT HPC BLEED | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(30.09.2024) | 10258551 | RING,BLEED;AIR,GE 0946 | 2 | EA | 2 | 0 | 0 | 2 | EA | 18.12 - SOH @ AA02 | Supply for Order 200147409, Item 5 cannot be changed 90025018 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015893 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025018 | 05 | Preparation | 0000235814 | 5 | 0 | EA | 102000000027579 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025018_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | CDP Gasket |  | 0 | 2 | 0 | 90025018 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258551 | RING,BLEED;AIR,GE 0946 | 2024-09-30 | W |  | 0010 | Replace CDP Bleed Valve | INT | Replace CDP Bleed Valve | 3 | Ready for Release | 90025018_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 5 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232825 | S002 |  | 30 | 5300015893 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235814 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-12-03 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-13 | ROTAT | 200174928 | 0020 | 0040 | 200174928 | 6Y GT4009 GEOMETRY VALVE CDP BLEED | AA53.409XV575 | VALVE,GT4009 HP COMP BLEED ACTUATION | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(03.12.2024) | 10258551 | RING,BLEED;AIR,GE 0946 | 2 | EA | 2 | 0 | 0 | 0 |  | 20.12 - ETA 02.09.25 PO 4500024443 NP FCA check LM workshop | Supply for Order 200174928, Item 4 cannot be changed 90028286 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300018734 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028286 | 05 | Preparation | 0000277563 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-12-03 | ODST-0090028286_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-30 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200174928 |  | 0 | 2 | 0 | 90028286 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258551 | RING,BLEED;AIR,GE 0946 | 2024-12-03 | W |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | 3 | Ready for Release | 90028286_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000272050 | S002 |  | 30 | 5300018734 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52958 | 2024-11-15 | 277563 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-13 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0230 | 0290 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10258555 | WASHER,PLN;GE 133A1624P37 | 1 | EA | 6 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 29 cannot be changed 90025036 item 240 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 29 | 0 | EA | 102000000026634 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0240 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258555 | WASHER,PLN;GE 133A1624P37 | 2024-10-16 | W |  | 0230 | IGNITER PLUG INSPECTION | INT | IGNITER PLUG INSPECTION | 3 | Ready for Release | 90025036_0240 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 29 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 240 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0230 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258555 | WASHER,PLN;GE 133A1624P37 | 1 | EA | 6 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 31 cannot be changed 90025043 item 290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 31 | 0 | EA | 102000000026635 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258555 | WASHER,PLN;GE 133A1624P37 | 2024-10-17 | W |  | 0230 | IGNITER PLUG INSPECTION | INT | IGNITER PLUG INSPECTION | 3 | Ready for Release | 90025043_0290 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 31 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 290 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0230 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258555 | WASHER,PLN;GE 133A1624P37 | 1 | EA | 6 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 27 cannot be changed 90025045 item 260 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 27 | 0 | EA | 102000000026636 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0260 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258555 | WASHER,PLN;GE 133A1624P37 | 2024-10-17 | W |  | 0230 | IGNITER PLUG INSPECTION | INT | IGNITER PLUG INSPECTION | 3 |  | 90025045_0260 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 27 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0260 | 0320 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10258557 | GASKET;GE 1538M42P01 | 2 | EA | 18 | 0 | 0 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 32 cannot be changed 90025036 item 270 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 32 | 0 | EA | 102000000026612 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | P48 Probe gasket | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0270 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | P48 gasket |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258557 | GASKET;GE 1538M42P01 | 2024-10-16 | W |  | 0260 | P48 INLET PROBE INSPECTION | INT | P48 INLET PROBE INSPECTION | 3 | Ready for Release | 90025036_0270 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 32 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 270 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0260 | 0010 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258557 | GASKET;GE 1538M42P01 | 2 | EA | 18 | 0 | 0 | 2 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 34 cannot be changed 90025043 item 300 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 34 | 0 | EA | 102000000026614 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0300 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | P48 gasket |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258557 | GASKET;GE 1538M42P01 | 2024-10-17 | W |  | 0260 | P48 INLET PROBE INSPECTION | INT | P48 INLET PROBE INSPECTION | 3 | Ready for Release | 90025043_0300 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 34 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 300 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0260 | 0010 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258557 | GASKET;GE 1538M42P01 | 2 | EA | 18 | 0 | 0 | 2 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 30 cannot be changed 90025045 item 290 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 30 | 0 | EA | 102000000026601 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0290 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | P48 gasket |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258557 | GASKET;GE 1538M42P01 | 2024-10-17 | W |  | 0260 | P48 INLET PROBE INSPECTION | INT | P48 INLET PROBE INSPECTION | 3 |  | 90025045_0290 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 30 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 290 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 100039340 | 0010 | 0020 | 100039340 | Replace - GT4007 Offline WW Relay Module | AA53.GT4007AP10 | PKG EQ,INSTRUMENT,GT4007 | AA01 | 30 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258598 | RELAY,IF;WOODWARD 5441413 | 1 | EA | 1 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 100039340, Item 2 cannot be changed 90025069 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016561 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90025069 | 05 | Preparation | 0000137832 | 2 | 0 | EA | 102000000027727 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090025069_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-11-18 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4007AP10 |  | 0 | 2 | 0 | 90025069 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258598 | RELAY,IF;WOODWARD 5441413 | 2024-10-17 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect |  |  | 90025069_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 30 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000137262 | S002 | 30 | 30 | 5300016561 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137832 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 5 | Low | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2024-10-16 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147548 | 0100 | 0140 | 200147548 | 1Y INSP GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(16.10.2024) | 10258644 | GASKET;GE 9608M08G48 | 1 | EA | 6 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147548, Item 14 cannot be changed 90025036 item 120 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016450 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025036 | 05 | Preparation | 0000235960 | 14 | 0 | EA | 102000000026600 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-16 | ODST-0090025036_0120 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE gasket |  | 0 | 2 | 0 | 90025036 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258644 | GASKET;GE 9608M08G48 | 2024-10-16 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 | Ready for Release | 90025036_0120 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 14 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232966 | S002 |  | 30 | 5300016450 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235960 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147550 | 0100 | 0040 | 200147550 | 1Y INSP GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258644 | GASKET;GE 9608M08G48 | 1 | EA | 6 | 0 | 0 | 1 | EA | 17.10 - SOH @ AA02 | Supply for Order 200147550, Item 19 cannot be changed 90025043 item 170 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016482 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025043 | 05 | Preparation | 0000235962 | 19 | 0 | EA | 102000000026613 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025043_0170 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-15 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE gasket |  | 0 | 2 | 0 | 90025043 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258644 | GASKET;GE 9608M08G48 | 2024-10-17 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 | Ready for Release | 90025043_0170 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 19 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000232968 | S002 |  | 30 | 5300016482 | 170 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235962 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-04 | ROTAT | 200147552 | 0100 | 0040 | 200147552 | 1Y Turbine Mechanical Maintenance GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258644 | GASKET;GE 9608M08G48 | 1 | EA | 6 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 200147552, Item 19 cannot be changed 90025045 item 180 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016487 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025045 | 05 | Preparation | 0000235964 | 19 | 0 | EA | 102000000026615 |  | 102000000034059 |  |  |  |  | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025045_0180 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-02 | 0 |  | 2025-02-24 |  | 2025-03-01 | DE gasket |  | 0 | 2 | 0 | 90025045 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258644 | GASKET;GE 9608M08G48 | 2024-10-17 | W |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 3 |  | 90025045_0180 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 19 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232970 | S002 |  | 30 | 5300016487 | 180 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235964 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-04 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-11 | INLEC | 100076454 | 0020 | 0010 | 100076454 | GT4009 SLO B Temp Sensor fail | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10258659 | MODULE,IF;WOODWARD 9905970 | 1 | EA | 11 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 100076454, Item 1 cannot be changed 90025056 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016525 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025056 | 05 | Preparation | 0000233101 | 1 | 0 | EA | 102000000029973 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025056_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-10 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4009 |  | 0 | 2 | 0 | 90025056 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258659 | MODULE,IF;WOODWARD 9905970 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025056_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000230184 | S002 | 30 | 30 | 5300016525 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-04-18 | 233101 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-11 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SD2420 | Released | 2024-07-21 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-08 | ROTAT | 200091513 | 0230 | 2650 | 200091513 | 6Y RE SD 1KT2420 TURB FR3 MAJOR MATERIAL | AA53.1KT2420 | TURB,GAS FOR 2ND STAGE COMPRESSOR | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(21.07.2024) | 10258662 | SEALANT;BIRKOSIT DICHTUNGSKITT,1KG TIN | 2 | EA | 1 | 0 | 0 | 1 | EA | 02.10 - qty 2 SOH at AA01 | Supply for Order 200091513, Item 392 cannot be changed 90028419 item 900010 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300013090 | 2880 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028419 | 05 | Preparation | 0000129822 | 392 | 0 | EA | 102000000033198 |  | 102000000030553 |  |  |  | LP-SD-C02 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-07-22 | ODST-0090028419_2850/90028419_0090_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-03 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90028419 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258662 | SEALANT;BIRKOSIT DICHTUNGSKITT,1KG TIN | 2024-07-21 | W |  | 0230 | MISCELLANEOUS GASKETS | INT | MISCELLANEOUS GASKETS | 5 |  | 90028419_2850/90028419_0090_0010 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 392 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000129172 | S002 | 30 | 30 | 5300013090 | 2880 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129822 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-08 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT8 | Released | 2024-09-22 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147409 | 0010 | 0030 | 200147409 | 6Y CV-RE 2.5 600# Act BUV - 408XV575 | AA53.408XV575 | VALVE,FLOW CONT HPC BLEED | AA01 | 20 | WO item has not been released yet | 10258664 | CLAMP,TBG;GE AS18951400 | 2 | EA | 7 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235814 | 3 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-10 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258664 | CLAMP,TBG;GE AS18951400 |  |  |  | 0010 | Replace CDP Bleed Valve | INT | Replace CDP Bleed Valve | 3 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000232825 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
1 | 25SDGT8 | Released | 2024-09-22 | 2025-03-01 |  | 2025-03-01 | 2025-03-01 | ROTAT | 200147410 | 0010 | 0020 | 200147410 | 6Y CV-RE 6 600# Act BUV - 408XV576 | AA53.408XV576 | VALVE,FLOW CONT 8TH STAGE BLEED GT4008 | AA01 | 20 | WO item has not been released yet | 10258665 | CLAMP,TBG;GE AS18951600 | 2 | EA | 2 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000235815 | 2 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-05-10 | 0 |  |  |  |  | Stg 8 clamp |  | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258665 | CLAMP,TBG;GE AS18951600 |  |  |  | 0010 | REPLACE STG 8 BLEED VALVE | INT | REPLACE STG 8 BLEED VALVE | 3 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000232826 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0210 | 0021 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(25.09.2024) | 10258679 | MOTOR,AC;45KW,415V,4P,TOSHIBA D225M | 1 | EA | 1 | 0 | 0 | 1 | EA | 25.09 - SOH at AA02 | Supply for Order 200063883, Item 25 cannot be changed 90024996 item 20 already exists | Material picked; currently at SW3R01H05B/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | REFURB |  |  | 90024996 | 05 | Preparation | 0000098185 | 25 | 0 | EA |  |  | 102000000034075 |  |  |  |  | WorkPackLink | SW3R01H05B |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090024996_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258679 | MOTOR,AC;45KW,415V,4P,TOSHIBA D225M | 2024-09-25 | W |  | 0210 | Install SS Clutch and Barring gear Motor | INT | Install SS Clutch and Barring gear Motor |  | Ready for Release | 90024996_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 25 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
1 | 25SDGT8 | Released | 2024-08-13 | 2025-03-01 |  | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0080 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | WO item has not been released yet | 10258718 | GEAR,BARRING;FLENDGRAF SN7233SN7234TG | 1 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000098185 | 8 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 | 0 |  |  | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 2 | 0 | 0 |  | L |  | 0 |  |  | 0 | 0 |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258718 | GEAR,BARRING;FLENDGRAF SN7233SN7234TG |  |  |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release |  |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [8 empty] | 20 |  |  | 0 |  | 0 |  | 25SDGT8 | MJ |  |  | 1000097602 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 | 0 |  |  | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0010 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258719 | GASKET;GR313,HUDSON T10837 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147533, Item 1 cannot be changed 90028595 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020027 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028595 | 05 | Preparation | 0000235945 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028595_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147533 |  | 0 | 2 | 0 | 90028595 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258719 | GASKET;GR313,HUDSON T10837 | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028595_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232951 | S002 |  | 30 | 5300020027 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235945 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147535 | 0110 | 0010 | 200147535 | 12Y INSP INT FIN FAN G4009E1 | AA53.G4009E1 | EXCH,HEAT G4009 SYNTH/MIN OIL AIR COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258719 | GASKET;GR313,HUDSON T10837 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147535, Item 1 cannot be changed 90028597 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020029 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028597 | 05 | Preparation | 0000235947 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028597_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147535 |  | 0 | 2 | 0 | 90028597 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258719 | GASKET;GR313,HUDSON T10837 | 2025-01-14 | W |  | 0110 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028597_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232953 | S002 |  | 30 | 5300020029 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235947 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200160323 | 0100 | 0010 | 200160323 | 12Y INSP INT FIN FAN G4008E1 | AA53.G4008E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258719 | GASKET;GR313,HUDSON T10837 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200160323, Item 1 cannot be changed 90028596 item 10 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020028 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028596 | 05 | Preparation | 0000255582 | 1 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028596_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200160323 |  | 0 | 2 | 0 | 90028596 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258719 | GASKET;GR313,HUDSON T10837 | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028596_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000251671 | S002 |  | 30 | 5300020028 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 255582 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0020 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258720 | GASKET;GR313,HUDSON T10838 | 1 | EA | 1 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147533, Item 2 cannot be changed 90028595 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020027 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028595 | 05 | Preparation | 0000235945 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028595_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147533 |  | 0 | 2 | 0 | 90028595 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258720 | GASKET;GR313,HUDSON T10838 | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028595_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232951 | S002 |  |  | 5300020027 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235945 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147535 | 0110 | 0020 | 200147535 | 12Y INSP INT FIN FAN G4009E1 | AA53.G4009E1 | EXCH,HEAT G4009 SYNTH/MIN OIL AIR COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258720 | GASKET;GR313,HUDSON T10838 | 1 | EA | 1 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147535, Item 2 cannot be changed 90028597 item 20 already exists | Awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020029 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028597 | 05 | Preparation | 0000235947 | 2 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028597_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147535 |  | 0 | 2 | 0 | 90028597 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258720 | GASKET;GR313,HUDSON T10838 | 2025-01-14 | W |  | 0110 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028597_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232953 | S002 |  |  | 5300020029 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235947 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200160323 | 0100 | 0020 | 200160323 | 12Y INSP INT FIN FAN G4008E1 | AA53.G4008E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258720 | GASKET;GR313,HUDSON T10838 | 1 | EA | 1 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200160323, Item 2 cannot be changed 90028596 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020028 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028596 | 05 | Preparation | 0000255582 | 2 | 0 | EA | 102000000034127 |  | 102000000034103 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028596_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200160323 |  | 0 | 2 | 0 | 90028596 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258720 | GASKET;GR313,HUDSON T10838 | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028596_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 2 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000251671 | S002 |  |  | 5300020028 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 255582 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0030 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258721 | GASKET;GR313,HUDSON T10877 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147533, Item 3 cannot be changed 90028595 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020027 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028595 | 05 | Preparation | 0000235945 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028595_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147533 |  | 0 | 2 | 0 | 90028595 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258721 | GASKET;GR313,HUDSON T10877 | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028595_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232951 | S002 |  | 30 | 5300020027 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235945 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147535 | 0110 | 0030 | 200147535 | 12Y INSP INT FIN FAN G4009E1 | AA53.G4009E1 | EXCH,HEAT G4009 SYNTH/MIN OIL AIR COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258721 | GASKET;GR313,HUDSON T10877 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147535, Item 3 cannot be changed 90028597 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020029 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028597 | 05 | Preparation | 0000235947 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028597_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147535 |  | 0 | 2 | 0 | 90028597 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258721 | GASKET;GR313,HUDSON T10877 | 2025-01-14 | W |  | 0110 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028597_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232953 | S002 |  | 30 | 5300020029 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235947 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200160323 | 0100 | 0030 | 200160323 | 12Y INSP INT FIN FAN G4008E1 | AA53.G4008E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258721 | GASKET;GR313,HUDSON T10877 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200160323, Item 3 cannot be changed 90028596 item 30 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020028 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028596 | 05 | Preparation | 0000255582 | 3 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028596_0030 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200160323 |  | 0 | 2 | 0 | 90028596 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258721 | GASKET;GR313,HUDSON T10877 | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028596_0030 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000251671 | S002 |  | 30 | 5300020028 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 255582 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT7 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0040 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258722 | GASKET;GR313,HUDSON T10878 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147533, Item 4 cannot be changed 90028595 item 40 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020027 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028595 | 05 | Preparation | 0000235945 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028595_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147533 |  | 0 | 2 | 0 | 90028595 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258722 | GASKET;GR313,HUDSON T10878 | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028595_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232951 | S002 |  | 30 | 5300020027 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235945 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT9 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147535 | 0110 | 0040 | 200147535 | 12Y INSP INT FIN FAN G4009E1 | AA53.G4009E1 | EXCH,HEAT G4009 SYNTH/MIN OIL AIR COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258722 | GASKET;GR313,HUDSON T10878 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200147535, Item 4 cannot be changed 90028597 item 40 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020029 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028597 | 05 | Preparation | 0000235947 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028597_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147535 |  | 0 | 2 | 0 | 90028597 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258722 | GASKET;GR313,HUDSON T10878 | 2025-01-14 | W |  | 0110 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028597_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT9 | MJ |  | AU1072 | 1000232953 | S002 |  | 30 | 5300020029 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235947 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDGT8 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200160323 | 0100 | 0040 | 200160323 | 12Y INSP INT FIN FAN G4008E1 | AA53.G4008E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4008 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10258722 | GASKET;GR313,HUDSON T10878 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.01 - ETA 28.02.25 PO 4500043445 ex Klinger | Supply for Order 200160323, Item 4 cannot be changed 90028596 item 40 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300020028 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028596 | 05 | Preparation | 0000255582 | 4 | 0 | [8 empty] | WorkPackLink |  | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028596_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2026-04-14 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200160323 |  | 0 | 2 | 0 | 90028596 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258722 | GASKET;GR313,HUDSON T10878 | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028596_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 4 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000251671 | S002 |  | 30 | 5300020028 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBB4 | 2024-08-08 | 255582 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-10-07 | 2025-03-01 | 2025-02-12 | 2025-03-01 | 2025-04-29 | VALVE | 100079243 | 0010 | 0030 | 100079243 | MV-RE 1.5" 300# 124GLV1110 | AA53.124LCV26 | VALVE,CTRL LEVEL S/O DRAIN TANK 1K2420 | AA01 | 255 | Issue Detected, please check Message log(Orchestration / Derivation)(07.10.2024) | 10259046 | VALVE GLB:40mm,ASME CL300,RF,CS,C3T | 1 | EA | 0 | 0 | 0 | 0 |  | 06.01 - ETA 12.02.25 PO 4500032380 SCORE CPT | Supply for Order 100079243, Item 3 cannot be changed – 4500032380 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300016133 | 10 | CPT | 7 | 1000020678 | 3 | 30000225 | SCORE AUSTRALASIA PTY LTD | 4500032380 | 10 | 1 | EA | 2025-02-28 |  |  |  | 90029068 | 05 | Preparation | 0000244776 | 3 | 0 | [8 empty] | WorkPackLink |  | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-07 | ODST-0090029068_0020 | 0 | 0 | 0 | 0 | 2025-02-10 | 2025-02-22 | AA53 | 2025-03-01 |  |  | 2025-03-01 | 2025-02-12 | 2025-02-24 |  |  | 2026-06-04 | 0 |  | 2025-02-12 |  | 2025-02-24 | 100079243 |  | 0 | 2 | 2 | 90029068 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259046 | VALVE GLB:40mm,ASME CL300,RF,CS,C3T | 2024-10-07 | W |  | 0010 | Replace Passing Bypass Valve 124GAV1305 | INT | Replace Passing Bypass Valve 124GAV1305 |  |  | 90029068_0020 |  |  | DG1 |  |  | 05 | Release Completed | X | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 2024-12-17 | 99 | 6000010058 | 2025-02-12 | 0 |  | 0 |  | 25SD2420 | MJ |  | AU1009 | 1000241461 | S001 | 30 | 30 | 5300016132 | 30 |  | 5300016133 | 10 | 1 | EA | 1001 | AA02 | 2025-02-12 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-06-17 | 0 | 0 | 0 |  | 1010 | 3 | SD | Shutdown | 6 | Very Low | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0030 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.12.2024) | 10259119 | TXDCR,VIB;EX,BENTLY 3304000105 | 2 | EA | 4 | 0 | 0 | 2 | EA | 03.12 - SOH @ AA02 | Supply for Order 200063883, Item 28 cannot be changed 90028271 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028271 | 05 | Preparation | 0000098185 | 28 | 0 | EA | 102000000029978 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-08-13 | ODST-0090028271_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | XE503/4 |  | 0 | 2 | 0 | 90028271 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259119 | TXDCR,VIB;EX,BENTLY 3304000105 | 2024-12-02 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90028271_0020 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 28 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 230 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0060 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.12.2024) | 10259139 | PROXIMITOR,BENTLY 330180-51-05 | 12 | EA | 19 | 0 | 0 | 3 | EA | 27.02 - SOH @ AA02 | Supply for Order 200063883, Item 31 cannot be changed 90028271 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028271 | 05 | Preparation | 0000098185 | 31 | 0 | EA | 101000000150188 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-08-13 | ODST-0090028271_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4008 |  | 0 | 2 | 0 | 90028271 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259139 | PROXIMITOR,BENTLY 330180-51-05 | 2024-12-02 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90028271_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 31 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 260 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0060 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.12.2024) | 10259139 | PROXIMITOR,BENTLY 330180-51-05 | 12 | EA | 19 | 0 | 0 | 4 | EA | 27.02 - SOH @ AA02 | Supply for Order 200063883, Item 31 cannot be changed 90028271 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028271 | 05 | Preparation | 0000098185 | 31 | 0 | EA | 102000000029848 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-08-13 | ODST-0090028271_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4008 |  | 0 | 2 | 0 | 90028271 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259139 | PROXIMITOR,BENTLY 330180-51-05 | 2024-12-02 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90028271_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 31 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 260 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0060 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.12.2024) | 10259139 | PROXIMITOR,BENTLY 330180-51-05 | 12 | EA | 19 | 0 | 0 | 3 | EA | 27.02 - SOH @ AA02 | Supply for Order 200063883, Item 31 cannot be changed 90028271 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028271 | 05 | Preparation | 0000098185 | 31 | 0 | EA | 101000000137406 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-08-13 | ODST-0090028271_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | GT4008 |  | 0 | 2 | 0 | 90028271 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259139 | PROXIMITOR,BENTLY 330180-51-05 | 2024-12-02 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90028271_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 31 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 260 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0080 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10259307 | TAPE,GRAPH,ADH,6MM X 12M,RIBBON | 1 | EA | 2 | 0 | 0 | 1 | EA | 15.01 - SOH @ AA02 | Supply for Order 200147533, Item 8 cannot be changed 90028595 item 60 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020027 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028595 | 05 | Preparation | 0000235945 | 8 | 0 | EA | 102000000031503 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028595_0060 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147533 |  | 0 | 2 | 0 | 90028595 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259307 | TAPE,GRAPH,ADH,6MM X 12M,RIBBON | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028595_0060 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232951 | S002 |  | 30 | 5300020027 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235945 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0110 | 0040 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10259308 | TAPE,GRAPH,ADH,10MM X 12M,RIBBON | 6 | EA | 20 | 0 | 0 | 6 | EA | 18.02 - SOH @ AA02 | Supply for Order 100079012, Item 8 cannot be changed 90028429 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018551 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028429 | 05 | Preparation | 0000243763 | 8 | 0 | EA | 102000000031787 | 102000000030100 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028429_0040 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079012 |  | 0 | 2 | 0 | 90028429 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259308 | TAPE,GRAPH,ADH,10MM X 12M,RIBBON | 2024-11-28 | W |  | 0110 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028429_0040 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240421 | S002 | 30 | 30 | 5300018551 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243763 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0130 | 0050 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10259308 | TAPE,GRAPH,ADH,10MM X 12M,RIBBON | 6 | EA | 20 | 0 | 0 | 1 | EA | 18.02 - SOH @ AA02 | Supply for Order 100079106, Item 9 cannot be changed 90028430 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018552 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028430 | 05 | Preparation | 0000243730 | 9 | 0 | EA | 102000000031904 | 102000000030101 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028430_0040 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079106 |  | 0 | 2 | 0 | 90028430 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259308 | TAPE,GRAPH,ADH,10MM X 12M,RIBBON | 2024-11-28 | W |  | 0130 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028430_0040 |  |  | ST5 |  | A4 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240357 | S002 | 30 | 30 | 5300018552 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0130 | 0050 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10259308 | TAPE,GRAPH,ADH,10MM X 12M,RIBBON | 6 | EA | 20 | 0 | 0 | 5 | EA | 18.02 - SOH @ AA02 | Supply for Order 100079106, Item 9 cannot be changed 90028430 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018552 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028430 | 05 | Preparation | 0000243730 | 9 | 0 | EA | 102000000033919 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028430_0040 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079106 |  | 0 | 2 | 0 | 90028430 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259308 | TAPE,GRAPH,ADH,10MM X 12M,RIBBON | 2024-11-28 | W |  | 0130 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028430_0040 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240357 | S002 | 30 | 30 | 5300018552 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0090 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10259308 | TAPE,GRAPH,ADH,10MM X 12M,RIBBON | 1 | EA | 20 | 0 | 0 | 1 | EA | 18.02 - SOH @ AA02 | Supply for Order 200147533, Item 9 cannot be changed 90028595 item 70 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020027 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028595 | 05 | Preparation | 0000235945 | 9 | 0 | EA | 101000000145374 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028595_0070 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147533 |  | 0 | 2 | 0 | 90028595 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259308 | TAPE,GRAPH,ADH,10MM X 12M,RIBBON | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028595_0070 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232951 | S002 | 30 | 30 | 5300020027 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235945 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0110 | 0050 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10259309 | TAPE,GRAPH,ADH,15MM X 12M,RIBBON | 2 | EA | 6 | 0 | 0 | 1 | EA | 18.02 - SOH @ AA02 | Supply for Order 100079012, Item 9 cannot be changed 90028429 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018551 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028429 | 05 | Preparation | 0000243763 | 9 | 0 | EA | 102000000031787 | 102000000033854 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028429_0050 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079012 |  | 0 | 2 | 0 | 90028429 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259309 | TAPE,GRAPH,ADH,15MM X 12M,RIBBON | 2024-11-28 | W |  | 0110 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028429_0050 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240421 | S002 | 30 | 30 | 5300018551 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243763 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-18 | MECH | 100079012 | 0110 | 0050 | 100079012 | Exch Insp - FF Tube IRIS - 5E2002B1 | AA53.5E2002B1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10259309 | TAPE,GRAPH,ADH,15MM X 12M,RIBBON | 2 | EA | 6 | 0 | 0 | 1 | EA | 18.02 - SOH @ AA02 | Supply for Order 100079012, Item 9 cannot be changed 90028429 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018551 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028429 | 05 | Preparation | 0000243763 | 9 | 0 | EA | 102000000031787 | 102000000029989 | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028429_0050 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079012 |  | 0 | 2 | 0 | 90028429 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259309 | TAPE,GRAPH,ADH,15MM X 12M,RIBBON | 2024-11-28 | W |  | 0110 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028429_0050 |  |  | ST5 |  | A5 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 9 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240421 | S002 | 30 | 30 | 5300018551 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243763 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-18 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDSTB5 | Released | 2024-11-29 | 2025-02-21 | 2025-02-16 | 2025-03-01 | 2025-03-03 | MECH | 100079106 | 0130 | 0040 | 100079106 | Exch Insp - FF Tube IRIS - 5E2002A1 | AA53.5E2002A1 | EXCH,VESSEL HC COND PRODUCT COOLER | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(28.11.2024) | 10259309 | TAPE,GRAPH,ADH,15MM X 12M,RIBBON | 2 | EA | 6 | 0 | 0 | 2 | EA | 18.02 - SOH @ AA02 | Supply for Order 100079106, Item 8 cannot be changed 90028430 item 30 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300018552 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028430 | 05 | Preparation | 0000243730 | 8 | 0 | EA | 102000000033855 |  | 102000000033275 |  |  |  |  | WorkPackLink | PACKING-SD | P07 TA MET 2025 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-11-29 | ODST-0090028430_0030 | 0 | 0 | 0 | 0 |  | 2025-02-19 | AA53 | 2025-03-01 |  |  | 2025-02-21 |  |  |  |  | 2025-12-12 | 0 |  | 2025-02-16 |  | 2025-02-21 | 100079106 |  | 0 | 2 | 0 | 90028430 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259309 | TAPE,GRAPH,ADH,15MM X 12M,RIBBON | 2024-11-28 | W |  | 0130 | Install Header Gaskets | INT | Install Header Gaskets |  |  | 90028430_0030 |  |  | ST5 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 8 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000240357 | S002 | 30 | 30 | 5300018552 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-06-12 | 243730 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance
| 25SDGT7 | Released | 2025-01-14 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | MECH | 200147533 | 0100 | 0070 | 200147533 | 12Y INSP INT FIN FAN G4007E1 | AA53.G4007E1 | EXCH,HEAT SYNTH/MIN LO COOLER G4007 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(14.01.2025) | 10259309 | TAPE,GRAPH,ADH,15MM X 12M,RIBBON | 1 | EA | 6 | 0 | 0 | 1 | EA | 18.02 - SOH @ AA02 | Supply for Order 200147533, Item 7 cannot be changed 90028595 item 50 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300020027 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028595 | 05 | Preparation | 0000235945 | 7 | 0 | EA | 101000000145372 |  | 102000000034102 |  |  |  |  | WorkPackLink | PACKING-SD | T25-W1-UT1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2025-01-14 | ODST-0090028595_0050 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200147533 |  | 0 | 2 | 0 | 90028595 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259309 | TAPE,GRAPH,ADH,15MM X 12M,RIBBON | 2025-01-14 | W |  | 0100 | Fit New Gasket & Header Plate | INT | Fit New Gasket & Header Plate | 5 |  | 90028595_0050 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 7 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000232951 | S002 | 30 | 30 | 5300020027 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-05-03 | 235945 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance
| 25SD4401 | Released | 2024-10-18 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-28 | INLEC | 100035121 | 0020 | 0010 | 100035121 | Vibration Probe Replace 244XE505X | AA53.FAR7CM6 | PANEL,SYSTEM CABINET,CPMS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10259931 | PROBE,VIB;EX,BENTLY 3301050212050205 | 1 | EA | 15 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 100035121, Item 1 cannot be changed 90025068 item 10 already exists | Material picked; currently at SW3R01D01A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016553 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025068 | 05 | Preparation | 0000133613 | 1 | 0 | EA | 102000000029593 | 102000000029435 | 102000000029625 |  |  |  |  | WorkPackLink | SW3R01D01A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-18 | ODST-0090025068_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-12-29 | 0 |  | 2025-02-24 |  | 2025-03-01 | K4401B |  | 0 | 2 | 0 | 90025068 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259931 | PROBE,VIB;EX,BENTLY 3301050212050205 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025068_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SD4401 | MJ |  | AU1072 | 1000133023 | S002 | 30 | 30 | 5300016553 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133613 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-28 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0240 | 0050 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.12.2024) | 10259931 | PROBE,VIB;EX,BENTLY 3301050212050205 | 1 | EA | 15 | 0 | 0 | 1 | EA | 03.12 - SOH @ AA02 | Supply for Order 200063883, Item 30 cannot be changed 90028271 item 40 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028271 | 05 | Preparation | 0000098185 | 30 | 0 | EA | 102000000029850 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090028271_0040 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 | XE617 |  | 0 | 2 | 0 | 90028271 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10259931 | PROBE,VIB;EX,BENTLY 3301050212050205 | 2024-12-02 | W |  | 0240 | Install Gearbox Instrumentation | INT | Install Gearbox Instrumentation |  | Ready for Release | 90028271_0040 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 30 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0100 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10260101 | PIN,FLENDER TX80 BARRING,CLUTCH,PAWLSTOP | 1 | SET | 0 | 0 | 0 | 0 |  | 05.03 - ETA 05.04.25 PO 4500032727 BH; In Trans MOT tba GS5049320 1.3kg 35x35x20 | Supply for Order 200063883, Item 10 cannot be changed 90024996 item 80 already exists | Awaiting picking (check stock levels) @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 10 | 0 | [8 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090024996_0080 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260101 | PIN,FLENDER TX80 BARRING,CLUTCH,PAWLSTOP | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 90024996_0080 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 10 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 |  | 30 | 5300014051 | 80 |  |  | 0 | 1 | SET | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDGT7 | Released | 2024-10-17 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-04-29 | INLEC | 100076521 | 0020 | 0010 | 100076521 | Investigate Faulty T/C (1) GT4007 | AA53.407TE518B | TXDCR,TEMP HP COMP DISCH GT4007 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(17.10.2024) | 10260110 | SENSOR,TEMP;GE L47314P03 | 1 | EA | 1 | 0 | 0 | 1 | EA | 18.10 - SOH @ AA02 | Supply for Order 100076521, Item 1 cannot be changed 90025057 item 10 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300016535 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90025057 | 05 | Preparation | 0000233040 | 1 | 0 | EA | 102000000027508 |  | 102000000034108 |  |  |  |  | WorkPackLink | PACKING-SD | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-10-17 | ODST-0090025057_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-09-08 | 0 |  | 2025-02-24 |  | 2025-03-01 | 407TE518B |  | 0 | 2 | 0 | 90025057 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260110 | SENSOR,TEMP;GE L47314P03 | 2024-10-17 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90025057_0010 |  |  | UT1 | [5 empty] | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDGT7 | MJ |  | AU1072 | 1000230205 | S002 |  | 30 | 5300016535 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W52788 | 2024-04-18 | 233040 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-04-29 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance
| 25SDGT8 | Released | 2024-08-13 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-03 | ROTAT | 200063883 | 0009 | 0060 | 200063883 | 12Y G4008 GEARBOX MAJOR OVERHAUL | AA53.G4008X1 | GBOX,FOR G4008 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(13.08.2024) | 10260117 | CLUTCH ASY;FLENDER/SSS GEARS SN7233SN72> | 1 | ASY | 2 | 0 | 0 | 1 | ASY | 03.10 - SOH @ AA02 | Supply for Order 200063883, Item 6 cannot be changed 90024996 item 10 already exists | Material picked; currently at SW3R05C02A/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300014051 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  |  | 90024996 | 05 | Preparation | 0000098185 | 6 | 0 | ASY |  |  | 102000000025801 |  |  |  |  | WorkPackLink | SW3R05C02A |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-08-13 | ODST-0090024996_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2024-10-06 | 0 |  | 2025-02-24 |  | 2025-03-01 |  |  | 0 | 2 | 0 | 90024996 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260117 | CLUTCH ASY;FLENDER/SSS GEARS SN7233SN72> | 2024-08-13 | W |  | 0009 | Gearbox Overhaul | INT | Gearbox Overhaul | 3 | Ready for Release | 90024996_0010 |  |  | UT1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 6 |  | 0 |  | 25SDGT8 | MJ |  | AU1072 | 1000097602 | S002 | 30 | 30 | 5300014051 | 10 |  |  | 0 | 1 | ASY | 2001 | AA02 | 2025-02-24 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98185 | 0 | 0 |  | 1020 | 2 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-03 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0520 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10260262 | BEARING,PAD,TILTING;RENK 4101 | 1 | EA | 2 | 0 | 1 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 61 cannot be changed 9026841 item 600 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 600 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180122097 | 9026841 | 05 | Preparation | 0000129754 | 61 | 0 | EA |  |  | 102000000029389 | 01-Road |  | 1-Not Started |  | WorkPackLink | P07WH-R3FL | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000389425_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056459 | 1020 | 2025-06-05 | 1 |  | 2025-02-05 | 4900228019_2025_0001 | 2025-03-01 | G/Box #1 | 5000389425_2025_0001 | 0 | 2 | 0 | 90025019 | 1 | 0 | 180122097 | 2 | 0 | 0 | X | L | 4900228019 | 2025 |  | 5000389425 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260262 | BEARING,PAD,TILTING;RENK 4101 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 9026841_0600 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 61 |  | 0 |  | 25SDFR1 | MJ | 1000004969 | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 600 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  | 2025-02-07 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0712 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10260263 | BEARING,PAD,TILTING;RENK 4102 | 1 | EA | 0 | 0 | 1 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 84 cannot be changed 9027108 item 810 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 810 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180124161 | 9027108 | 05 | Preparation | 0000129754 | 84 | 0 | EA |  |  | 102000000005580 |  |  |  |  | WorkPackLink | P07WH-R3FL | P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-09-30 | GRST-5000396283_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056759 | 1020 | 2025-06-05 | 1 |  | 2025-02-11 | 4900234056_2025_0001 | 2025-03-01 |  | 5000396283_2025_0001 | 0 | 2 | 0 | 90025019 | 1 | 0 | 180124161 | 2 | 0 | 0 | X | L | 4900234056 | 2025 |  | 5000396283 | 2025 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260263 | BEARING,PAD,TILTING;RENK 4102 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 9027108_0810 |  |  | FR1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 84 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  |  | 5300015903 | 810 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SD2301 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | ROTAT | 200091126 | 0030 | 0142 | 200091126 | 5Y RE SD 1K2301 COMPR MAJOR MATERIALS | AA53.1K2301 | COMPR,REGENERATION GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(11.05.2024) | 10262159 | NUT,LK;THOMASSEN 1441860142 | 12 | EA | 12 | 0 | 0 | 12 | EA | 23.01 - SOH @ AA02 | Supply for Order 200091126, Item 86 cannot be changed 90023534 item 410 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004361 | 660 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90023534 | 05 | Preparation | 0000129360 | 86 | 0 | EA | 102000000030443 | 102000000030459 | 102000000034105 |  |  |  |  | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | ODST-0090023534_0410 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2023-04-03 | 0 |  | 2025-02-24 |  | 2025-03-01 | CR-xhead |  | 0 | 2 | 0 | 90023534 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262159 | NUT,LK;THOMASSEN 1441860142 | 2024-05-11 | W |  | 0030 | CROSSHEAD GUIDE SUB-ASSEMBLY | INT | CROSSHEAD GUIDE SUB-ASSEMBLY | 5 |  | 90023534_0410 |  |  | DG1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 86 |  | 0 |  | 25SD2301 | MJ |  | AU1072 | 1000128789 | S002 |  | 30 | 5300004361 | 660 |  |  | 0 | 12 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129360 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance
| 25SDLN4 | Released | 2024-06-28 | 2024-07-11 | 2024-07-08 | 2025-05-08 | 2025-05-08 | INLEC | 100078578 | 0020 | 0010 | 100078578 | OPSD1 4KM1450KM1A Replace Motor | AA53.4KM1450KM1A | MOTOR,MAIN MOTOR COOLING FAN,4KM1450 | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(28.06.2024) | 10262242 | MOTOR,AC;EX,75KW,415V,2P,ABB M3JP280SMA2 | 1 | EA | 0 | 0 | 0 | 1 | EA | 10.03 - AT AA53 | Supply for Order 100078578, Item 1 cannot be changed 180103943 item 10 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300012165 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180103943 | 90014149 | 07 | Execution | 0000242087 | 1 | 0 | EA |  |  | 101000000034259 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08YRDBAY6 | AA53-P08-FL | 0 |  | 0 | 0 |  | 1 | 0 |  |  | Y | 1001 | 2024-06-28 |  | 0 | 0 | 0 | 0 |  | 2024-07-09 | AA53 | 2024-10-02 |  |  | 2024-07-11 |  |  | 100000045830 | 1020 | 2024-11-30 | 1 |  | 2024-12-11 | 4900189414_2024_0001 | 2024-07-11 |  | 5000315805_2024_0001 | 0 | 2 | 0 | 90014149 | 1 | 0 | 180103943 | 2 | 0 | 0 | X | L | 4900189414 | 2024 |  | 5000315805 | 2024 | 0 |  | 2024-07-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262242 | MOTOR,AC;EX,75KW,415V,2P,ABB M3JP280SMA2 | 2024-06-28 | W |  | 0020 | Replace Motor & Cooling fan assembly | INT | Replace Motor & Cooling fan assembly |  | Opportune Shutdown | 90014149_0010 |  |  | LN4 | [5 empty] | Z1 | WEG Priority | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 1 |  | 0 |  | 25SDLN4 | MJ | 1000004427 | AU1072 | 1000238808 | S002 | 30 | 30 | 5300012165 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-07-08 |  | Opportune Shutdown | 2024-12-12 |  | 1070 |  | 2024-10-02 | 1001 | Woodside Energy Ltd | W001 | W41088 | 2024-06-04 | 242087 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-08 | 2025-05-08 | 2025-05-08 | Released/Settlement rule created/Pre-costed/Object created/Order Approved/Goods movement posted/Partially confirmed/Job In Process/Material committed | AM01 | Reactive Maintenance
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0410 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10262328 | NUT KIT,BLT+LK;KAWASAKI DRGZRC74B0905 | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 52 cannot be changed 90025019 item 510 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 510 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 52 | 0 | KIT | 102000000032113 | 102000000029301 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0510 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | CplIsoltSlev |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262328 | NUT KIT,BLT+LK;KAWASAKI DRGZRC74B0905 | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0510 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 52 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 510 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDFR1 | Released | 2024-07-20 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-05-14 | ROTAT | 200091505 | 0030 | 0420 | 200091505 | 8Y Compressor BSR Materials - 1K1820 | AA53.1K1820 | COMPR,FRAC 1 CENTRIFUGAL PROPANE | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(20.07.2024) | 10262329 | NUT KIT,BLT+LK;KAWASAKI DRGZRC74B082BOL> | 1 | KIT | 2 | 0 | 0 | 1 | KIT | 03.10 - SOH @ AA02 | Supply for Order 200091505, Item 53 cannot be changed 90025019 item 520 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300015903 | 520 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90025019 | 05 | Preparation | 0000129754 | 53 | 0 | KIT | 102000000032113 | 102000000029308 | 102000000032082 |  |  |  | LP-SD-C07 | WorkPackLink | PACKING-SD | P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-09-30 | ODST-0090025019_0520 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-06-05 | 0 |  | 2025-02-24 |  | 2025-03-01 | CplgBoltNutL |  | 0 | 2 | 0 | 90025019 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262329 | NUT KIT,BLT+LK;KAWASAKI DRGZRC74B082BOL> | 2024-07-20 | W |  | 0030 | CONSUMABLES/G-BOX | INT | CONSUMABLES/G-BOX | 5 |  | 90025019_0520 |  |  | FR1 |  | C4 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 20 |  |  | 53 |  | 0 |  | 25SDFR1 | MJ |  | AU1072 | 1000129164 | S002 |  | 30 | 5300015903 | 520 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129754 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 4 | Medium | RC00025003 | 2025-05-14 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage | AM02 | Proactive Maintenance | M0-000001-99-02
| 25SDSTB5 | Released | 2024-01-02 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | MECH | 600001678 | 0010 | 0030 | 600001678 | MOC-81997 - 5K2001 Suction Drain Drum | AA53.5K2001 | COMPR,STABILISER GAS | AA01 | 20 | Issue Detected, please check Message log(Orchestration / Derivation)(02.01.2024) | 10262346 | VALVE,CHK;50MM,CL300,RF,LTCS,L3C2PNX | 1 | EA | 1 | 0 | 0 | 1 | EA | 03.10 - SOH @ AA02 | Supply for Order 600001678, Item 2 cannot be changed 90024966 item 20 already exists | Material picked; currently at PACKING-SD/Z830 @AA0 | SP12 | Stock at Base | 0 | AA02 | 5300004588 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90024966 | 05 | Preparation | 0000084596 | 2 | 0 | EA | 102000000028483 |  | 102000000031917 |  |  |  | LP-SD-C12 | WorkPackLink | PACKING-SD |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090024966_0020 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-09-29 | 0 |  | 2025-02-24 |  | 2025-03-01 | Critical |  | 0 | 2 | 0 | 90024966 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262346 | VALVE,CHK;50MM,CL300,RF,LTCS,L3C2PNX | 2024-01-02 | W |  | 0010 | Process Isolation & Verify | INT | Process Isolation & Verify |  |  | 90024966_0020 |  |  | ST5 |  | C1 |  |  |  | Z1 | WEG Priority | 0055 | In Preparation (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 |  | 20 |  |  | 2 |  | 0 |  | 25SDSTB5 | MJ |  | AU1072 | 1000084000 | S002 | 30 | 30 | 5300004588 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84596 | 0 | 0 |  | 1020 | 1 | SD | Shutdown | 4 | Medium | RC00018003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM06 | Capital
| 25SD2420 | Released | 2024-03-12 | 2025-03-01 | 2024-07-19 | 2025-03-01 | 2025-03-01 | INLEC | 200065935 | 0010 | 0010 | 200065935 | 6Y Vib/Speed Probe Repl (7) 1K2420 | AA53.124GE026 | TXDCR,TRIP VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(25.03.2024) | 10262583 | PROBE,VIB;EX,BENTLY 3301050212100205 | 2 | EA | 19 | 6 | 0 | 2 | EA | 25.09 - At KGP | Supply for Order 200065935, Item 1 cannot be changed 180053095 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300008306 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180053095 | 9009209 | 05 | Preparation | 0000100270 | 1 | 0 | EA |  |  | 102000000007254 | 01-Road |  | 3-In Transit |  | WorkPackLink | P08C11L2 | AA53-TA-P07 | 0 | 5400001281 | 10 | 2 | EA | 0 | 0 |  |  | Y | 1001 | 2024-03-25 | GRST-5000159428_2024 | 0 | 0 | 0 | 0 |  | 2024-07-20 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000021355 | 1020 | 2025-07-31 | 2 |  | 2024-08-02 | 4900103330_2024_0001 | 2024-07-22 | 200065935 | 5000159428_2024_0001 | 0 | 2 | 0 | 90011040 | 2 | 0 | 180053095/180073889 | 2 | 0 | 0 | X | L | 4900103330 | 2024 |  | 5000159428 | 2024 | 0 |  | 2024-07-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262583 | PROBE,VIB;EX,BENTLY 3301050212100205 | 2024-03-25 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 9009209_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 1 |  | 0 |  | 25SD2420 | MJ | 1000002619 | AU1072 | 1000099654 | S002 |  | 30 | 5300008306 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-07-19 |  |  | 2024-08-06 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100270 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-03-12 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-01 | INLEC | 200065935 | 0010 | 0050 | 200065935 | 6Y Vib/Speed Probe Repl (7) 1K2420 | AA53.124GE026 | TXDCR,TRIP VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.12.2024) | 10262583 | PROBE,VIB;EX,BENTLY 3301050212100205 | 2 | EA | 19 | 6 | 0 | 0 |  | 16.12 - SOH @ AA02 | Supply for Order 200065935, Item 6 cannot be changed 90028268 item 10 already exists | Awaiting picking @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300008306 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90028268 | 05 | Preparation | 0000100270 | 6 | 0 | [8 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-25 | ODST-0090028268_0010 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  |  |  | 2025-07-31 | 0 |  | 2025-02-24 |  | 2025-03-01 | 200065935 |  | 0 | 2 | 0 | 90028268 | 0 | 0 |  | 2 | 0 | 0 | X | L |  | 0 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262583 | PROBE,VIB;EX,BENTLY 3301050212100205 | 2024-12-13 | W |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 |  | 90028268_0010 |  |  | DG1 | [5 empty] | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 6 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000099654 | S002 |  | 30 | 5300008306 | 60 |  |  | 0 | 2 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100270 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-01 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Goods movement posted/Material shortage/Printed | AM02 | Proactive Maintenance
| 25SD2420 | Released | 2024-11-11 | 2025-03-01 | 2025-02-24 | 2025-03-01 | 2025-03-02 | INLEC | 200147116 | 0020 | 0030 | 200147116 | 3Y Vibration Probe Replace (7) 1KT2420 | AA53.124YE031 | TXDCR,ALARM VIBRATION 1K2420 | AA01 | 10 | Issue Detected, please check Message log(Orchestration / Derivation)(13.11.2024) | 10262583 | PROBE,VIB;EX,BENTLY 3301050212100205 | 6 | EA | 19 | 6 | 0 | 6 | EA | 18.11 - SOH @ AA02 | Supply for Order 200147116, Item 3 cannot be changed 9027115 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300017864 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 9027115 | 05 | Preparation | 0000235387 | 3 | 0 | EA | 102000000032160 | 102000000029436 | 102000000032166 |  |  |  | LP-SD-C03 | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y | 1001 | 2024-11-14 | GIST-4900234130_2025 | 0 | 0 | 0 | 0 |  | 2025-02-27 | AA53 | 2025-03-01 |  |  | 2025-03-01 |  |  | 100000056763 | 1020 | 2025-07-31 | 6 |  | 2025-02-11 | 4900234130_2025_0003 | 2025-03-01 | 1K2420 |  | 0 | 2 | 0 | 90025108 | 0 | 0 |  | 2 | 0 | 0 | X | L | 4900234130 | 2025 |  |  | 0 | 0 |  | 2025-02-24 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262583 | PROBE,VIB;EX,BENTLY 3301050212100205 | 2024-11-13 | W |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9027115_0030 |  |  | DG1 |  | B2 |  |  |  | Z2 | WEG Proactive | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  | 5 |  |  | 3 |  | 0 |  | 25SD2420 | MJ |  | AU1072 | 1000232430 | S002 |  | 30 | 5300017864 | 30 |  |  | 0 | 6 | EA | 2001 | AA02 | 2025-02-24 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPGXJ | 2024-04-30 | 235387 | 0 | 0 |  | 1020 | 3 | SD | Shutdown | 1 | Critical Work | RC00025003 | 2025-03-02 | 2025-03-01 | 2025-03-01 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance