## Colour coding
PR NEVER | BOTTOM Last | YEAR | 2024
CREATED | BOTTOM Second | EVENT | 2024 KGP WIN 1 TA
DELIVERED PRE S/4 | BOTTOM Third | START DATE | 2024-03-07
GOOD | BOTTOM Fourth | FINISH DATE | 2024-03-27
Inventory | BOTTOM Fifth | DAYS to TA START | -364
PURCHASE | TOP | MLC | GEOFF DYSON
Need to look at |  | Revision CODE | 24OKCM19 , 24OKCO19 , 24OKCM16 , 24OKCM13 , 24OKCO16 , 24OKCO13
|  | # DAYS in TA | 20
|  | # WO's: TOTAL | 377 | n
|  | TOTAL WO LINES | 514 | n
|  | # WO Lines: TOTAL PR NEVER | 0 | g
|  | # WO Lines: NOT RELEASED | 0
|  | # Created WO's: TOTAL | 1
|  | % WO Lines: In Transit ~ Rc'd at PBRC ~ STAGED ~ ON SITE | 30.42%
| (Delivered Pre S/4) + Stock on hand (released) + PR Never + | # WO Lines:In Transit ~ Rc'd at PBRC ~ STAGED ~ ON SITE | 0 | 0 | 0 | 0
|  | # WO LineS:(RFQ, PR, PO): To receive by Start Date | MRP NOT RUN
|  | # WO Lines:CRITICAL WILL NOT MEET START DATE | #REF!
# WO Lines: TO NOT MEET START DATE
# WO Lines: TO NOT MEET FINISH DATE
|  | # WO Lines: INT'L FREIGHT REMAINING | N/A

## Dashboard
KPI FOR OKHA 2410 MATERIALS
| PO Material Status | WO Description | Count of WO Revision
| On Time |  | 872
| Grand Total |  | 872
0
PR NEVER
201
TOTAL WO
872
TOTAL WO LINES
  © Reserved to WIL
866
RELEASED WO LINES
198
RELEASED WO
0
PR NEVER
3
CREATED WO
6
CREATED WO LINES
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Key Turnaround Dates
Year -
Days to Start -
Campaign start -
Campaign finish -
2024
-364
07-Mar-24
27-Mar-24
Material Analysis
Delivered Pre S4H -
Need Purchasing -
SOH -
Refurb -
359
326
187
3

## Sheet3
WO Status | (All) | [7 empty] | WO Status | (All) | WO Status | Created |  |  | WO Status | (All) |  |  | Supply status | (blank) | [9 empty] | WO Status | Released | WO Status | Released | WO Status | Released | 0
|  |  | Row Labels | Count of WO Revision | 23.05% | Sum of Unique WO number | Count of WO number | [9 empty] | Supply status | (blank) | Expediting Note / User Comment | UserCommentLink | Req Priority for Material/Component | (All) | WO Status | (All) |  |  | Row Labels | Count of WO Status | [10 empty] | Batch (of Material) | NEW | 3
Expediting Note / User Comment | Count of Expediting Note / User Comment |  | Delayed | 13 |  | 201 | 872 |  | Sum of Unique WO number | Count of WO Status | Sum of Unique WO number | Count of WO Status | [14 empty] | STO raised (through orchestration) | 6 | Available Inventory | Sum of Unique WO number | Count of WO Status | Expediting Note / User Comment | Count of Expediting Note / User Comment | Expediting Note / User Comment | Count of Expediting Note / User Comment |  | Row Labels | Count of Material Category
Grand Total |  |  | Missing Staging Date | 515 | 201 |  |  | 100% | 201 | 872 | 3 | 6 | 3 | 6 |  |  |  |  | Row Labels | Count of Requirement date (WO component) | Row Labels | Sum of Unique WO number | Sum of Unique WO number |  | Row Labels | Count of PO Material Status | Vendor PO raised | 28 | #REF! | 198 | 866 | Grand Total |  |  |  |  | Delivered Pre S4H | 359 | Row Labels | Count of Material Category
|  |  | ON TIME | 344 |  |  |  | 100% | [10 empty] | INLEC | 2 | 24OKCM19 | 45 | 201 |  | On Time | 872 | Missing Supply Status | 515 | 2 | [7 empty] | Need Purchasing | 326 | 200079587 | 1
|  |  | Grand Total | 872 | [14 empty] | MECH | 23 | 24OKCM16 | 60 |  |  |  |  | Material work-packed @AB50 | 74 | 0 | [7 empty] | SOH | 187 | 10507776 | 1
[19 empty] | PAINT | 32 | 24OKCM13 | 41 |  |  |  |  | Materials handed over to w/ Maintenance | 12 | -2 | [7 empty] | Grand Total | 872 | SOH | 1
[19 empty] | CRANE | 2 | 24OKCO16 | 39 |  |  |  |  | Material In-Transit on-04-Sea | 12
[21 empty] | 24OKCO13 | 6 |  |  |  |  | Material work-packed @AB01 | 16
[21 empty] | 24OKCO19 | 10 |  |  |  |  | Material In-Transit on-01-Road | 69 |  |  |  |  | 0
[27 empty] | Material avail; awaiting work-packing @AB01 | 102
[27 empty] | Shipping notification from Vendor received | 1
[27 empty] | PR approved; PO not issued | 2
[27 empty] | Material avail; awaiting work-packing @AB03 | 1
[27 empty] | Material avail; awaiting work-packing @AB02 | 2
[27 empty] | Material is received @AB01 | 18
[27 empty] | Workpack awaiting Shipment @AB01 | 2
#REF! | #REF! | [25 empty] | Material is received @AB50 | 11
j | [26 empty] | Material In-Transit on-06-Air Passenger | 1
0
WO Status | (All)
WO Revision |  | 24OKCM19, 24OKCM16, 24OKCM13, 24OKCO16, 24OKCO13, 24OKCO19
24OKCM19
24OKCM16
24OKCM13
24OKCO16
24OKCO13
24OKCO19

## 📊 Report
KGP WIN 1 Material
| WO creation date | #No. of WO
| Z | 843
| 2024-02-02 | 16
| 2024-01-11 | 5
| 2024-03-05 | 3
| 2024-03-27 | 2
| 2024-02-09 | 1
| 2024-02-07 | 1
| 2024-01-26 | 1
| Grand Total | 872
0
TOTAL WO CREATED
07-Mar-24
START DATE
27-Mar-24
FINISH DATE
0
PR NEVER
-364
DAYS TO START
2024
YEAR
TOTAL WO
377
TOTAL WO LINES
514
  © Reserved to Shutdown
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Working
[6 empty] | Average of ReservationItem | WO Status |  |  | WO Status | Count of WO Revision
Supply Status | # Count | WO Revision | Sum of Requirement quantity | WO Status | Sum of Requirement quantity | Req Priority for Material/Component | Created | Released | Grand Total | Created | 6
Shipping notification from Vendor received | 1 | 24OKCM13 | 2064 | Released | 6439 | 10 | 1.5 | 12.0084 | 11.8926 | Released | 866
Material avail; awaiting work-packing @AB03 | 1 | 24OKCM16 | 1969 | Created | 8 | 20 |  | 7.675 | 7.675 | Grand Total | 872
Material In-Transit on-06-Air Passenger | 1 | 24OKCM19 | 1859 | Grand Total | 6447 | 30 | 1.5 | 5.0396 | 4.9709
PR approved; PO not issued | 2 | 24OKCO16 | 450 |  |  | 255 |  | 1.3333 | 1.3333
Workpack awaiting Shipment @AB01 | 2 | 24OKCO19 | 90 |  |  | Grand Total | 1.5 | 9.1201 | 9.0677
Material avail; awaiting work-packing @AB02 | 2 | 24OKCO13 | 15
STO raised (through orchestration) | 6 | Grand Total | 6447
Material is received @AB50 | 11
Material In-Transit on-04-Sea | 12
Materials handed over to w/ Maintenance | 12
Material work-packed @AB01 | 16
Material is received @AB01 | 18
Vendor PO raised | 28
Material In-Transit on-01-Road | 69
Material work-packed @AB50 | 74
Material avail; awaiting work-packing @AB01 | 102
Unknown | 515
Total | 872

## OKHA 2410
WO Revision | Alert / Exception | WO Overall Status | WO Status | WO creation date | WO Actual Release date | Requirement date (WO component) | Material Staging date (STO) | WO basic Start date | WO basic Finish date | WO Main work centre | WO Priority | WO number | BOM item number | WO Description | Functional location | Operation / Activity | Demand Plant | ETA @ Demand plant | Procurement plant | ETA @ Procument plant | Supplying Plant | ETA @ Supply plant | Req Priority for Material/Component | Req Urgency for Material/Component | Material / Component | Material Description | Requirement quantity | Stock on-hand @ Base | Stock on-hand @ Remote | Expediting Note / User Comment | Planned Deliver Time (in days) (PR) | Supply status | SupplyProcess | Supplying Plant (STO) | Current STO | Current STO Item | Planned Deliver Time (in days) (STO) | PR Release Indicator | Purchase Requisition | Purchase Requisition Item | Release date (PR) | Delivery date (PR) | Vendor | Vendor PO | GR PO Document | Vendor PO item | PO qty | Requirement UOM | Delivery date (PO) | Batch (of Material) | IBD for PO | Latest Inbound Delivery Document | Campaign (Y/N) | Process Phase | Process Subphase | Reservation | ReservationItem | WO_OVERALL_STATUS_CODE | Status of Material (Demand Plant) | Status of Material (Supplying Plant) | Message log | Top HU | HU Quantity | HUUOM | Nested HU Lvl 2 | Nested HU Lvl 3 | ContainerID | Linked Work-pack/HU | Unloading Point | Arrival (plan) | Delay @ Supply plant | Delay@ Demand plant | Final Due Date | Incompletion indic. (Y/N) | Item deletion indicator | Requirements date (PR) | Return STO | Return STO Item | Return STO Qty | Shipping Type | Stock In-Transit into Remote | Voyage status | Voyage type | Voyage-id | WithdrawnQuantity | WO item number | Unique WO number | C-28 | Date Modified D-E | Actual C-D | CALC | Vendor PO2 | PO Material Status | Delivery date (PO)2 | Material Category | Key | Column1 | Logic | Any order which is ahead (Date) | Any order which is ahead (Qty) | SP Count
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0080 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10006659 | PLUG,SPARK;SOLAR 903316C1 | 1 | 0 | 8 | 8 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 8 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00000963414542110006659000200061999 | #N/A | 000009634110006659000200061999 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0010 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10006856 | O-RING;TURB,BS228,SOLAR 912642C1 | 1 | 0 | 70 | 70 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00000963414542110006856000200061999 | #N/A | 000009634110006856000200061999 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0020 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10006930 | GASKET;CU,SOLAR 1739421 | 1 | 0 | 14 | 14 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00000963414542110006930000200061999 | #N/A | 000009634110006930000200061999 |  |  | 1
24OKCO19 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0010 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | ELECTRICAL ISOLATE AU05.05P450001A (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10017194 | BEARING,BALL,RAD,65 X 140 X 33MM THK,C3 | 1 | 0 | 1 | 1 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 12 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001371064542110017194000100038602 | 00001371064542110017194000100038602 | 000013710610017194000100038602 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 |  | 2024-04-25 | 2024-04-28 | MECH |  | 100038807 | 0052 | MOC110643 EGC2 Upgrade ASV Act Stem (100038807) | VALVE,FIC042503,ANTI-SURGE CTRL (AB50.05FCV042503) | INSTALL NEW COMPONENTS IN 05FCV042508 (0090) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10021820 | DIAPHRAGM,ACT;NTRL,FISHER 2E859702202 | 1 | 1 | 4 | 4 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137308 | 6 | 4 | 30 |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001373084540710021820000100038807 | 00001373084540710021820000100038807 | 000013730810021820000100038807 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-10 |  | 2024-05-09 | 2024-05-12 | MECH |  | 100038806 | 0010 | MOC110643 LGC1 Upgrade ASV Act Stem (100038806) | VALVE,K043300,SURGE CTRL (AB50.05FCV043103) | INSTALL NEW COMPONENTS IN ACTUATOR (0040) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10021821 | DIAPHRAGM,ACT;FISHER 2E859502202 | 1 | 0 | 3 | 3 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137307 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001373074542210021821000100038806 | 00001373074542210021821000100038806 | 000013730710021821000100038806 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 |  | 2024-04-25 | 2024-04-28 | MECH |  | 100038807 | 0042 | MOC110643 EGC2 Upgrade ASV Act Stem (100038807) | VALVE,FIC042503,ANTI-SURGE CTRL (AB50.05FCV042503) | INSTALL NEW COMPONENTS IN ACTUATOR (0040) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10021822 | DIAPHRAGM,ACT;FISHER 2N126902202 | 1 | 1 | 1 | 1 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137308 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001373084540710021822000100038807 | 00001373084540710021822000100038807 | 000013730810021822000100038807 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0190 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10034184 | LUG,COMP;50MM2,12MM SCR | 20 | 0 | 30 | 25.03.24: OK - Available in Okha stock | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 14 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001334014537910034184000100034857 | 00001334014537910034184000100034857 | 000013340110034184000100034857 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-10 | MECH |  | 200064964 | 0010 | 7Y CALIBRATE RV DISPOSABLE (200064964) | PSV,REL POWER GEN-T1 PILOT GAS INSTR (AB50.05PSV400244-1) | CERTIFY PSV FROM STOCK (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10038987 | VALVE,REL;690KPAG,CIRSEAL 5159T13MP100 | 1 | 1 | 0 | 1 SOH @ AB01 | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003454 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000099266 | 1 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-21 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00000992664542110038987000200064964 | #N/A | 000009926610038987000200064964 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-13 | 2024-04-18 | 2024-04-19 | MECH |  | 100036757 | 0020 | FP8 MOC Install EGC2 Motor Bearing Press (100036757) | MOTOR,K042210,GAS COMP DRIVER (AB50.05KM042210) | Install EGC2 Motor Bearing Pressure Bala (0020) | AB50 | 2024-04-18 | AB01 |  | AB02 |  | 20 | 20 | 10047907 | CONNECTOR,COMP/M,0.50" X 0.75" NPT,SS | 2 | 0 | 0 | 2 SOH @ AB01 | 0 | Material avail; awaiting work-packing @AB02 | Stock at Base (SP12) | AB02 | 5300001259 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135291 | 1 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-21 | -23 | 5 | ON TIME |  | On Time | 0 | Need Purchasing | 00001352914540010047907000100036757 | 00001352914540010047907000100036757 | 000013529110047907000100036757 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-01 | 2024-04-29 | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0050 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING HC HEADER SPADES (0090) | AB50 | 2024-05-14 |  |  | AB01 |  | 10 | 5 | 10058077 | BOLT ASY,HEX HD;WITH NUT,1.125"X100MM | 32 | 0 | 0 | ETA 28.03.24 PO 4500004680 x 32 KONNECT | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006987 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 25 | 4 | 30 | 30 | Supply for Order 100072584, Item 25 cannot be changed 90003409 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 13 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-03 | -26 | 2 | ON TIME |  | After Turnround | 2024-03-28 | Need Purchasing | 00002185114541310058077000100072584 | 00002185114541310058077000100072584 | 000021851110058077000100072584 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-22 | 2024-04-29 |  | 2024-04-28 | 2024-05-02 | REFURB |  | 100037132 | 0040 | E/R - Replace Spool HVAC CSW1 CDR-30357 (100037132) | PUMP,A/C COOLING,DUTY (AB50.03P753002A) | replace spool (0030) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10058191 | STUDBOLT;0.500" X 65MM,A193 B8M CL2 | 4 | 0 | 17 | 17 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135616 | 4 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001356164541110058191000100037132 | 00001356164541110058191000100037132 | 000013561610058191000100037132 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-22 | 2024-04-29 |  | 2024-04-28 | 2024-05-02 | REFURB |  | 100037132 | 0030 | E/R - Replace Spool HVAC CSW1 CDR-30357 (100037132) | PUMP,A/C COOLING,DUTY (AB50.03P753002A) | replace spool (0030) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10058201 | STUDBOLT;0.625" X 100MM,A193 B8M CL2 | 8 | 0 | 26 | 26 SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135616 | 3 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001356164541110058201000100037132 | 00001356164541110058201000100037132 | 000013561610058201000100037132 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-22 | 2024-04-29 |  | 2024-04-28 | 2024-05-02 | REFURB |  | 100037132 | 0050 | E/R - Replace Spool HVAC CSW1 CDR-30357 (100037132) | PUMP,A/C COOLING,DUTY (AB50.03P753002A) | replace spool (0030) | AB50 |  | AB01 |  | AB02 |  | 20 | 20 | 10058213 | STUDBOLT;0.750"X100MM,A193 B8M CL2 | 8 | 0 | 18 | ETA 29.04.24 PO 4500003941 x 32 TRISTAR | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135616 | 5 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001356164541110058213000100037132 | 00001356164541110058213000100037132 | 000013561610058213000100037132 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-02 | 2024-05-01 | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0070 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING PURGE HEADER SPADES (0110) | AB50 | 2024-05-16 |  |  | AB01 |  | 10 | 5 | 10058535 | STUDBOLT;1.000"X 165MM,B7,CAD+XYLAN | 32 | 0 | 0 | ETA 29.04.24 PO 4500003941 x 32 TRISTAR | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006987 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 29 | 4 | 30 | 30 | Supply for Order 100072584, Item 29 cannot be changed 90003411 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 14 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-04 | -27 | 1 | ON TIME |  | After Turnround | 2024-04-29 | Need Purchasing | 00002185114541410058535000100072584 | 00002185114541410058535000100072584 | 000021851110058535000100072584 | 0 | #N/A | 0
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-22 |  | 2024-04-22 | 2024-04-22 | MECH |  | 100033093 | 0050 | CLASS Repl Bilge P/p X/ver Vlv MV643405 (100033093) | VALVE,SCREWDWN,BILGEWTR TRANSFER PUMP (AB50.03MV643405) | Replace valve 03MV643405 (0020) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10058872 | STUDBOLT;0.500"X65MM,B7,CAD+XYLAN | 16 | 48 | 33 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000131577 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-25 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001315774540410058872000100033093 | 00001315774540410058872000100033093 | 000013157710058872000100033093 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-27 | 2024-05-05 |  | 2024-05-04 | 2024-05-07 | REFURB |  | 100038184 | 0030 | E/R - Repl Spool Steam Cond CDR-28783 (100038184) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | replace 15-SW-3750718-EXA1X-P (0030) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10058872 | STUDBOLT;0.500"X65MM,B7,CAD+XYLAN | 20 | 48 | 33 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136688 | 3 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-07 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001366884541710058872000100038184 | 00001366884541710058872000100038184 | 000013668810058872000100038184 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-12 | 2024-04-22 |  | 2024-04-22 | 2024-04-26 | REFURB |  | 100039046 | 0020 | E/R - Repl 3x LP Steam Spools CDR-27187 (100039046) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | Repl 3x LP Steam DN80 Spools (0020) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10058872 | STUDBOLT;0.500"X65MM,B7,CAD+XYLAN | 12 | 48 | 33 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137520 | 2 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-25 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001375204540410058872000100039046 | 00001375204540410058872000100039046 | 000013752010058872000100039046 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100036830 | 0020 | Replace C/Medium Vlv 05MV460015 (100036830) | VALVE,A043300,CM INLET (AB50.05MV460015) | Replace valve 05MV460015 (0020) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10058877 | STUDBOLT;0.625"X90MM,B7,CAD+XYLAN | 8 | 0 | 96 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000135362 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001353624542110058877000100036830 | 00001353624542110058877000100036830 | 000013536210058877000100036830 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-26 | REFURB |  | 100037555 | 0040 | MOD7 - Repl Spool CG-5130339 CDR-29137 (100037555) | LOOP,CORROSION, DEHYDRATION (AB50.05B02-CG01) | replace spool (0020) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10058877 | STUDBOLT;0.625"X90MM,B7,CAD+XYLAN | 12 | 0 | 96 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136067 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001360674540610058877000100037555 | 00001360674540610058877000100037555 | 000013606710058877000100037555 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-12 | 2024-04-22 |  | 2024-04-22 | 2024-04-26 | REFURB |  | 100039046 | 0030 | E/R - Repl 3x LP Steam Spools CDR-27187 (100039046) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | Repl 3x LP Steam DN80 Spools (0020) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10058877 | STUDBOLT;0.625"X90MM,B7,CAD+XYLAN | 12 | 0 | 96 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137520 | 3 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-25 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001375204540410058877000100039046 | 00001375204540410058877000100039046 | 000013752010058877000100039046 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-03-27 | 2024-05-09 | 2024-05-07 | 2024-05-09 | 2024-05-10 | MECH |  | 100032996 | 0020 | Replace Vlv FG Scrub Vessel MV441022 (100032996) | VALVE,LG441113,MAN DRAIN (AB50.05MV441022) | Isolate 05MV441022 (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 30 | 30 | 10058878 | STUDBOLT;0.625"X95MM,B7,CAD+XYLAN | 8 | 0 | 0 | MAINT. - R. | 0 | STO raised (through orchestration) | Stock at Base (SP12) | AB01 | 5300008461 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131610 | 2 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | -26 | 2 | ON TIME |  | After Turnround | 2024-05-10 | Need Purchasing | 00001316104542110058878000100032996 | 00001316104542110058878000100032996 | 000013161010058878000100032996 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-12 | 2024-04-22 |  | 2024-04-22 | 2024-04-26 | REFURB |  | 100039046 | 0040 | E/R - Repl 3x LP Steam Spools CDR-27187 (100039046) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | Repl 3x LP Steam DN80 Spools (0020) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10058879 | STUDBOLT;0.625"X100MM,B7,CAD+XYLAN | 12 | 58 | 25 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137520 | 4 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-25 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001375204540410058879000100039046 | 00001375204540410058879000100039046 | 000013752010058879000100039046 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0070 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10058892 | STUDBOLT;0.750"X120MM,B7,CAD+XYLAN | 4 | 12 | 31 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 4 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001427824540910058892000100044230 | 00001427824540910058892000100044230 | 000014278210058892000100044230 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 |  | 2024-04-25 | 2024-04-25 | MECH |  | 100046259 | 0030 | "Replace monoflange @ 05MV042441, EGC2" (100046259) | VALVE,05MV042441,MAN ISOL (AB50.05MV042441) | Install Valve (0030) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10058892 | STUDBOLT;0.750"X120MM,B7,CAD+XYLAN | 4 | 12 | 31 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000144760 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2021-06-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001447604540710058892000100046259 | 00001447604540710058892000100046259 | 000014476010058892000100046259 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-03 | 2024-05-01 | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0090 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING COW SPADES (0120) | AB50 | 2024-05-16 |  |  | AB01 |  | 10 | 5 | 10058893 | STUDBOLT;0.750"X125MM,B7,CAD+XYLAN | 16 | 0 | 0 | ETA 29.04.24 PO 4500003941 x 16 TRISTAR | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006987 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 39 | 4 | 30 | 30 | Supply for Order 100072584, Item 39 cannot be changed 90003411 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 13 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-05 | -26 | 2 | ON TIME |  | After Turnround | 2024-04-29 | Need Purchasing | 00002185114541510058893000100072584 | 00002185114541510058893000100072584 | 000021851110058893000100072584 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0090 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10058907 | STUDBOLT;0.875"X170MM,B7,CAD+XYLAN | 24 | 35 | 9 | SOH @ AB01/AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 6 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 12 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001427824540910058907000100044230 | 00001427824540910058907000100044230 | 000014278210058907000100044230 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-19 | MECH |  | 100034735 | 0030 | CLASS Repl Steam Drain Vlv Stripping Pp (100034735) | VALVE,SP750434,MAN THROTTLE,INLET (AB50.03MV750338) | Perform Isolations 03MV750338 (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060881 | GASKET,SWCI;15MM,CL150,4.5MM,316L/GR/316 | 2 | 0 | 7 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133239 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-21 | 0 | 0 | Missing Staging Date | 4500005685 | After Turnround | 2024-04-02 | Need Purchasing | 00001332394540010060881000100034735 | 00001332394540010060881000100034735 | 000013323910060881000100034735 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-12 | 2024-04-22 |  | 2024-04-22 | 2024-04-26 | REFURB |  | 100039046 | 0070 | E/R - Repl 3x LP Steam Spools CDR-27187 (100039046) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | Repl 3x LP Steam DN80 Spools (0020) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10060881 | GASKET,SWCI;15MM,CL150,4.5MM,316L/GR/316 | 3 | 0 | 7 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137520 | 10 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-25 | 0 | 0 | Missing Staging Date | 4500005685 | After Turnround | 2024-04-02 | Need Purchasing | 00001375204540410060881000100039046 | 00001375204540410060881000100039046 | 000013752010060881000100039046 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-28 | MECH |  | 100043119 | 0040 | D - Replace EGC2 PDT Isol Valves (100043119) | VALVE,PDT460520,MAN ISOL (AB50.05MV460127) | Replace EGC2 PDT Isol Valves (0020) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 1 | 0 | 0 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000141703 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2022-10-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-05-09 | Need Purchasing | 00001417034540910060884000100043119 | 00001417034540910060884000100043119 | 000014170310060884000100043119 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100036830 | 0030 | Replace C/Medium Vlv 05MV460015 (100036830) | VALVE,A043300,CM INLET (AB50.05MV460015) | Replace valve 05MV460015 (0020) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 2 | 0 | 11 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000135362 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-31 | 0 | 0 |  |  | 0 | 0 |  | 9 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 0 | 0 | Missing Staging Date | 4500005685, 4500005685, 4500007919, 4500007919, 4500007919 | After Turnround | 2024-05-28 | Need Purchasing | 00001353624542110060886000100036830 | 00001353624542110060886000100036830 | 000013536210060886000100036830 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-12 | 2024-04-22 |  | 2024-04-22 | 2024-04-26 | REFURB |  | 100039046 | 0080 | E/R - Repl 3x LP Steam Spools CDR-27187 (100039046) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | Repl 3x LP Steam DN80 Spools (0020) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 9 | 0 | 11 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137520 | 11 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-05-27 | 0 | 0 |  |  | 0 | 0 |  | 9 |  |  |  | 0 | 0 | 0.125 | 2024-03-25 | 0 | 0 | Missing Staging Date | 4500005685, 4500005685, 4500007919, 4500007919, 4500007919 | After Turnround | 2024-05-28 | Need Purchasing | 00001375204540410060886000100039046 | 00001375204540410060886000100039046 | 000013752010060886000100039046 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-29 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0530 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | ISOLATE & SPADE (0030) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 4 | 0 | 11 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 6 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 9 |  |  |  | 0 | 0 | 0.019231 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-05-28 | Need Purchasing | 00001287344538010060886000200090465 | 00001287344538010060886000200090465 | 000012873410060886000200090465 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-02 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0550 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | ISOLATE & SPADE (0030) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060886 | GASKET;SWCI,80MM,CL150,316L/GR/316 | 4 | 0 | 11 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 6 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 9 |  |  |  | 0 | 0 | 0.019231 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-05-28 | Need Purchasing | 00001296914538410060886000200091461 | 00001296914538410060886000200091461 | 000012969110060886000200091461 |  |  | 1
24OKCO19 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0030 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | ELECTRICAL ISOLATE AU05.05P450001A (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10060889 | GASKET;SWCI,200MM,CL150,316L/GR/316 | 1 | 0 | 5 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 14 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001371064542110060889000100038602 | 00001371064542110060889000100038602 | 000013710610060889000100038602 |  |  | 1
24OKCO19 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0020 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | ELECTRICAL ISOLATE AU05.05P450001A (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10060890 | GASKET;SWCI,250MM,CL150,316L/GR/316 | 1 | 14 | 16 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 13 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001371064542110060890000100038602 | 00001371064542110060890000100038602 | 000013710610060890000100038602 |  |  | 1
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-08 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0020 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | MECHANICAL DEISOLATE COTS (0230) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060890 | GASKET;SWCI,250MM,CL150,316L/GR/316 | 4 | 14 | 16 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 42 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00002185114542010060890000100072584 | 00002185114542010060890000100072584 | 000021851110060890000100072584 |  |  | 1
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-08 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0060 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | MECHANICAL DEISOLATE COTS (0230) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060891 | GASKET;SWCI,300MM,CL150,316L/GR/316 | 4 | 0 | 6 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 46 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-10 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-16 | Need Purchasing | 00002185114542010060891000100072584 | 00002185114542010060891000100072584 | 000021851110060891000100072584 |  |  | 1
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-04-30 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0030 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING LOAD HEADER SPADES (0080) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060891 | GASKET;SWCI,300MM,CL150,316L/GR/316 | 4 | 0 | 6 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 23 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-02 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-16 | Need Purchasing | 00002185114541210060891000100072584 | 00002185114541210060891000100072584 | 000021851110060891000100072584 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-29 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0520 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | ISOLATE & SPADE (0030) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060903 | GASKET;SWCI,200MM,CL300,316L/GR/316 | 4 | 0 | 9 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 5 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001287344538010060903000200090465 | 00001287344538010060903000200090465 | 000012873410060903000200090465 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-02 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0540 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | ISOLATE & SPADE (0030) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060903 | GASKET;SWCI,200MM,CL300,316L/GR/316 | 4 | 0 | 9 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 5 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001296914538410060903000200091461 | 00001296914538410060903000200091461 | 000012969110060903000200091461 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-03-27 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 100032996 | 0030 | Replace Vlv FG Scrub Vessel MV441022 (100032996) | VALVE,LG441113,MAN DRAIN (AB50.05MV441022) | Isolate 05MV441022 (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 3 | 0 | 20 | MAINT. - R. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131610 | 3 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001316104542110060916000100032996 | 00001316104542110060916000100032996 | 000013161010060916000100032996 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-29 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0550 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | ISOLATE & SPADE (0030) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060917 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 4 | 2 | 11 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 7 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | Need Purchasing | 00001287344538010060917000200090465 | 00001287344538010060917000200090465 | 000012873410060917000200090465 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-02 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0570 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | ISOLATE & SPADE (0030) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10060917 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 4 | 2 | 11 | OK. - CAMPAIGN PICK PDC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 8 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | Need Purchasing | 00001296914538410060917000200091461 | 00001296914538410060917000200091461 | 000012969110060917000200091461 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100034425 | 0010 | Replace LGC1 Seal Sys Vlv HV043018 (100034425) | VALVE,K043300SEAL,MAN ISOL (AB50.05HV043018) | Replace LGC1 Seal Sys Vlv HV043018 (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10060929 | GASKET;SWCI,25MM,CL1500,316L/GR/316 | 2 | 0 | 22 | OK. - 2023 - Staged | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000132929 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001329294542110060929000100034425 | 00001329294542110060929000100034425 | 000013292910060929000100034425 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0400 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10061160 | GASKET;SWCI,25MM,PN10-40,316L/GR/316 | 19 | 0 | 6 | ETA. - PROC. INV. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 30 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | Need Purchasing | 00001287344539110061160000200090465 | 00001287344539110061160000200090465 | 000012873410061160000200090465 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0400 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10061160 | GASKET;SWCI,25MM,PN10-40,316L/GR/316 | 19 | 0 | 6 | ETA. - PROC. - INVENT. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 31 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | Need Purchasing | 00001296914539510061160000200091461 | 00001296914539510061160000200091461 | 000012969110061160000200091461 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0410 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10061164 | GASKET;SWCI,40MM,PN10-40,316L/GR/316 | 10 | 0 | 5 | ETA. - PROC. - INV. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 31 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | Need Purchasing | 00001287344539110061164000200090465 | 00001287344539110061164000200090465 | 000012873410061164000200090465 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0410 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10061164 | GASKET;SWCI,40MM,PN10-40,316L/GR/316 | 10 | 0 | 5 | ETA. - PROC. - INVENT. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 32 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | Need Purchasing | 00001296914539510061164000200091461 | 00001296914539510061164000200091461 | 000012969110061164000200091461 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0420 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10061172 | GASKET;SWCI,80MM,PN10-40,316L/GR/316 | 13 | 0 | 4 | PR 2000030884 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 32 | 2 | 30 |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001287344539110061172000200090465 | 00001287344539110061172000200090465 | 000012873410061172000200090465 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0420 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10061172 | GASKET;SWCI,80MM,PN10-40,316L/GR/316 | 13 | 0 | 4 | PR 2000030884 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 33 | 2 | 30 |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001296914539510061172000200091461 | 00001296914539510061172000200091461 | 000012969110061172000200091461 |  |  | 1
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-21 | MECH |  | 100039000 | 0010 | Paint Prod/W Pump-B Base (100039000) | MOTOR,P450001B,PROD WTR PUMP DRIVER (AB50.05PM450001B) | PMIC Isolations (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10062327 | TAPE;COR INH,50MM,10MRL,DENSO 600050 | 1 | 7 | 3 | OK. - PDC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137452 | 8 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-21 | 0 | 0 | Missing Staging Date | 4500007962 | During Turnaround | 2024-03-24 | SOH | 00001374524540010062327000100039000 | 00001374524540010062327000100039000 | 000013745210062327000100039000 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0020 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10062849 | COMPOUND,ANTI-CORROSION;HENKEL 209758 | 1 | 0 | 9 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CAN |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT1 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001380454542110062849000100039544 | 00001380454542110062849000100039544 | 000013804510062849000100039544 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-13 | MECH |  | 100034866 | 0020 | Install GT3 HDF Seals & Bolts (100034866) | DAMP,B400003,INLET (AB50.05HDF400003-1) | Isolate Vent Fans (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10062910 | SEALANT,SILASTIC,RTV732,CLEAR,CART | 3 | 5 | 4 | OK. - PDC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133318 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001333184542110062910000100034866 | 00001333184542110062910000100034866 | 000013331810062910000100034866 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-13 | MECH |  | 100034867 | 0020 | Install GT4 HDF Seals & Bolts (100034867) | DAMP,B400004,INLET (AB50.05HDF400004-1) | Isolate Vent Fans (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10062910 | SEALANT,SILASTIC,RTV732,CLEAR,CART | 3 | 5 | 4 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133319 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001333194542110062910000100034867 | 00001333194542110062910000100034867 | 000013331910062910000100034867 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-03-13 | 2024-04-18 | 2024-04-13 | 2024-04-18 | 2024-04-19 | MECH |  | 100033044 |  | Repl N2 Backup Cyl & Reg Fittings MOC (100033044) | PKG EQ,NITROGEN BOTTLE RACK (AB50.03A481004) | Repl N2 Backup Cylinders (0010) | AB50 | 2024-04-18 |  |  | AB02 |  | 20 | 20 | 10063416 | GAS,COMP;N2,EHP,99.9%,CYL G | 6 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB02 | Stock at Base (SP12) | AB02 | 5300007835 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | CYL |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131525 | 1 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | -23 | 5 | ON TIME |  | On Time | 0 | Need Purchasing | 00001315254540010063416000100033044 | 00001315254540010063416000100033044 | 000013152510063416000100033044 | 0 | #N/A | 0
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-05 |  | 2024-05-05 | 2024-05-06 | MECH |  | 200083040 | 0032 | 6M P05 INSP/LUBE OF TURRET SWIVEL UNITS (200083040) | TURRET,PRODUCTION SWIVEL 1 (AB50.04V020001) | INSPECT & LUBRICATE TURRET SWIVEL (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10063466 | SILICA GEL,DESICCANT,PERMEABLE SACHET | 1 | 1 | 1 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | PAC |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000119827 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-07 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001198274541710063466000200083040 | 00001198274541710063466000200083040 | 000011982710063466000200083040 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 200072354 | 0010 | 2M M3/M5/M7/FWD SECT OIL SAMPLING ROUTE (200072354) | ENG,A600011A,FIRE WTR PUMP (AB50.03G600011) | CARRY OUT OIL SAMPLING (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10063554 | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP | 15 | 60 | 31 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000106783 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-31 | 0 | 0 |  |  | 0 | 0 |  | 21 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-06-18 | SOH | 00001067834542110063554000200072354 | 00001067834542110063554000200072354 | 000010678310063554000200072354 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 200072355 | 0010 | 2M ENG ROOM OIL SAMPLING ROUTE 2 (200072355) | ENG,A600001A,FIRE WTR PUMP (AB50.03G600001) | CARRY OUT OIL SAMPLING (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10063554 | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP | 15 | 60 | 31 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000106784 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-31 | 0 | 0 |  |  | 0 | 0 |  | 21 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-06-18 | SOH | 00001067844542110063554000200072355 | 00001067844542110063554000200072355 | 000010678410063554000200072355 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-08 |  | 2024-04-08 | 2024-04-16 | MECH |  | 200083035 | 0010 | 1Y F15 FIRE WATER HYDRANT INSP & TEST (200083035) | HYDT,FZ03,MAIN DECK,PORT (AB50.03SP602001) | INSPECT & TEST FIRE WATER HYDRANT (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10064932 | WASHER;65MM,MOULDED RBR,BS 336 | 79 | 0 | 100 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000119900 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-13 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-19 | Need Purchasing | 00001199004539010064932000200083035 | 00001199004539010064932000200083035 | 000011990010064932000200083035 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-02-09 | 2024-03-29 |  | 2024-03-29 | 2024-03-29 | PAINT |  | 100032520 | 0010 | 072 - Apply Cladding Sealant TEG Reboilr (100032520) | VE,A130010,GLYCOL REBOILER (AB50.05V130003) | FAF - Apply Cladding Sealant TEG Reboilr (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10149809 | SEALANT,736 RED,HEAT RES,CART,300ML | 4 | 5 | 0 | OK. - PDC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000131024 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001310244538010149809000100032520 | 00001310244538010149809000100032520 | 000013102410149809000100032520 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-08 | 2024-05-07 | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0010 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | MECHANICAL DEISOLATE COTS (0230) | AB50 | 2024-05-22 |  |  | AB01 |  | 10 | 5 | 10204117 | GASKET,FLG;125MM,1.5MM THK,CNAF,CL150 | 4 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006987 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 41 | 4 | 30 | 30 | Supply for Order 100072584, Item 41 cannot be changed 90003412 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 14 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-10 | -27 | 1 | ON TIME |  | After Turnround | 2024-05-07 | Need Purchasing | 00002185114542010204117000100072584 | 00002185114542010204117000100072584 | 000021851110204117000100072584 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-03 | 2024-05-01 | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0100 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING COW SPADES (0120) | AB50 | 2024-05-16 |  |  | AB01 |  | 10 | 5 | 10204117 | GASKET,FLG;125MM,1.5MM THK,CNAF,CL150 | 4 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006987 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 40 | 4 | 30 | 30 | Supply for Order 100072584, Item 40 cannot be changed 90003411 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 13 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-05 | -26 | 2 | ON TIME |  | After Turnround | 2024-05-07 | Need Purchasing | 00002185114541510204117000100072584 | 00002185114541510204117000100072584 | 000021851110204117000100072584 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-01 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0060 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING HC HEADER SPADES (0090) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10204124 | GASKET;450MM,CNAF,RF,KLINGER 864431171 | 4 | 2 | 16 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 26 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00002185114541310204124000100072584 | 00002185114541310204124000100072584 | 000021851110204124000100072584 |  |  | 1
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-08 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0050 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | MECHANICAL DEISOLATE COTS (0230) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10204124 | GASKET;450MM,CNAF,RF,KLINGER 864431171 | 4 | 2 | 16 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 45 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00002185114542010204124000100072584 | 00002185114542010204124000100072584 | 000021851110204124000100072584 |  |  | 1
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-08 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0040 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | MECHANICAL DEISOLATE COTS (0230) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10205990 | GASKET;250MM,273MM,FF,KLINGER 864434131 | 6 | 2 | 14 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 44 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00002185114542010205990000100072584 | 00002185114542010205990000100072584 | 000021851110205990000100072584 |  |  | 1
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-02 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0050 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING IG HEADER SPADES (0100) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10205990 | GASKET;250MM,273MM,FF,KLINGER 864434131 | 4 | 2 | 14 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 27 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00002185114541410205990000100072584 | 00002185114541410205990000100072584 | 000021851110205990000100072584 |  |  | 1
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-02 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0080 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING PURGE HEADER SPADES (0110) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10205993 | GASKET;400MM,406MM,FF,KLINGER 864434161 | 4 | 13 | 19 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 30 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-29 | SOH | 00002185114541410205993000100072584 | 00002185114541410205993000100072584 | 000021851110205993000100072584 |  |  | 1
24OKCM16 |  |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-08 |  | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0030 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | MECHANICAL DEISOLATE COTS (0230) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10205993 | GASKET;400MM,406MM,FF,KLINGER 864434161 | 4 | 13 | 19 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 43 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-10 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-29 | SOH | 00002185114542010205993000100072584 | 00002185114542010205993000100072584 | 000021851110205993000100072584 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-05-02 | OPS |  | 200082353 | 0020 | 1Y TEST PV VACUUM VALVE (200082353) | VALVE,OKHA9021,VACUUM (AB50.03A480012A) | Install IG header spades - OPEN (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10205993 | GASKET;400MM,406MM,FF,KLINGER 864434161 | 28 | 13 | 19 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118257 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-01 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-29 | Need Purchasing | 00001182574540910205993000200082353 | 00001182574540910205993000200082353 | 000011825710205993000200082353 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-22 | 2024-04-29 | 2024-04-04 | 2024-04-28 | 2024-05-02 | REFURB |  | 100037132 | 0020 | E/R - Replace Spool HVAC CSW1 CDR-30357 (100037132) | PUMP,A/C COOLING,DUTY (AB50.03P753002A) | replace spool (0030) | AB50 | 2024-04-29 |  |  | AB01 |  | 20 | 20 | 10206291 | GASKET;CNAF,20MM,CL150,1.5MM,FF,C4430 | 1 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006988 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135616 | 2 | 1 | 30 | 30 | Supply for Order 100037132, Item 2 cannot be changed 90003413 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-01 | -3 | 25 | ON TIME | 4500003832 | After Turnround | 2024-04-04 | Need Purchasing | 00001356164541110206291000100037132 | 00001356164541110206291000100037132 | 000013561610206291000100037132 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-22 | 2024-04-29 | 2024-04-04 | 2024-04-28 | 2024-05-02 | REFURB |  | 100037132 | 0010 | E/R - Replace Spool HVAC CSW1 CDR-30357 (100037132) | PUMP,A/C COOLING,DUTY (AB50.03P753002A) | replace spool (0030) | AB50 | 2024-04-29 |  |  | AB01 |  | 20 | 20 | 10206298 | GASKET,CNAF,150MM,CL150,1.5MM,FF,C4430 | 1 | 0 | 1 | OK - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006988 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135616 | 1 | 1 | 30 | 30 | Supply for Order 100037132, Item 1 cannot be changed 90003413 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-01 | -3 | 25 | ON TIME | 4500004017 | FALSE | 2024-03-09 | Need Purchasing | 00001356164541110206298000100037132 | 00001356164541110206298000100037132 | 000013561610206298000100037132 | 0 | #N/A | 0
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0030 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10209468 | GASKET;SS,SOLAR 304649100 | 2 | 0 | 14 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-06-25 | Need Purchasing | 00000963414542110209468000200061999 | #N/A | 000009634110209468000200061999 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | INLEC |  | 100035477 | 0010 | Upgrade GT1 I/O Modules (100035477) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Upgrade GT1 I/O Modules (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10218797 | MODULE,IF;8-INPUT,AB 1794IRT8XT | 3 | 0 | 15 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134011 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date | 4500005822 | After Turnround | 2024-06-25 | Need Purchasing | 00001340114542110218797000100035477 | 00001340114542110218797000100035477 | 000013401110218797000100035477 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | INLEC |  | 100035479 | 0010 | Upgrade GT3 I/O Modules (100035479) | PKG EQ,MAIN GEN 3 (AB50.05A400003) | Upgrade GT3 I/O Modules (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10218797 | MODULE,IF;8-INPUT,AB 1794IRT8XT | 7 | 0 | 15 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134013 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date | 4500005822 | After Turnround | 2024-06-25 | Need Purchasing | 00001340134542110218797000100035479 | 00001340134542110218797000100035479 | 000013401310218797000100035479 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | INLEC |  | 100035560 | 0010 | Upgrade GT4 I/O Modules (100035560) | PKG EQ,MAIN GEN 4 (AB50.05A400004) | Upgrade GT4 I/O Modules (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10218797 | MODULE,IF;8-INPUT,AB 1794IRT8XT | 6 | 0 | 15 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134014 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date | 4500005822 | After Turnround | 2024-06-25 | Need Purchasing | 00001340144542110218797000100035560 | 00001340144542110218797000100035560 | 000013401410218797000100035560 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-03-27 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-10 | MECH |  | 100032996 | 0060 | Replace Vlv FG Scrub Vessel MV441022 (100032996) | VALVE,LG441113,MAN DRAIN (AB50.05MV441022) | Isolate 05MV441022 (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 30 | 30 | 10227240 | VALVE,BALL;20MM,CL300,RF,CS,C3B1F | 1 | 0 | 0 | ETA - ISSUE. | 0 | STO raised (through orchestration) | Stock at Base (SP12) | AB01 | 5300008461 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131610 | 6 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | -12 | 16 | ON TIME | 4500009019 | After Turnround | 2024-06-19 | Need Purchasing | 00001316104542110227240000100032996 | 00001316104542110227240000100032996 | 000013161010227240000100032996 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0010 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10227715 | VALVE;MONOFLG,15MM,CL600,SS,S6M1L | 1 | 0 | 1 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-10-14 | Need Purchasing | 00001427824540910227715000100044230 | 00001427824540910227715000100044230 | 000014278210227715000100044230 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-13 | MECH |  | 100034866 | 0012 | Install GT3 HDF Seals & Bolts (100034866) | DAMP,B400003,INLET (AB50.05HDF400003-1) | Isolate Vent Fans (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10228855 | KIT,REP;SEAL,FIRE DAMP,SOALR 1042202 | 2 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000191 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133318 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001333184542110228855000100034866 | 00001333184542110228855000100034866 | 000013331810228855000100034866 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-13 | MECH |  | 100034867 | 0012 | Install GT4 HDF Seals & Bolts (100034867) | DAMP,B400004,INLET (AB50.05HDF400004-1) | Isolate Vent Fans (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10228855 | KIT,REP;SEAL,FIRE DAMP,SOALR 1042202 | 2 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000192 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133319 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | OKHAEC |  | 0 | 0 | 2024-06-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001333194542110228855000100034867 | 00001333194542110228855000100034867 | 000013331910228855000100034867 | 0 | #N/A | 0
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-02 |  | 2024-03-29 | 2024-04-03 | PAINT |  | 100038880 | 0070 | CT2 - 2WBT STBD FWD Ramp Blast & Replace (100038880) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10233767 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 4 | 0 | 36 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137381 | 7 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-05 | 0 | 0 | Missing Staging Date | 4500001554, 4500001554, 4500001554 | During Turnaround | 2024-03-15 | Need Purchasing | 00001373814538410233767000100038880 | 00001373814538410233767000100038880 | 000013738110233767000100038880 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-11 | 2024-04-16 | PAINT |  | 100038883 | 0030 | CT4 - 4WBT PORT AFT Ramp Blast & Replace (100038883) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10233767 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 4 | 0 | 36 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137384 | 8 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-18 | 0 | 0 | Missing Staging Date | 4500001554, 4500001554, 4500001554 | During Turnaround | 2024-03-15 | Need Purchasing | 00001373844539710233767000100038883 | 00001373844539710233767000100038883 | 000013738410233767000100038883 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-11 |  | 2024-04-06 | 2024-04-12 | PAINT |  | 100038887 | 0020 | CT2 - 2COT PORT X-Over Ramp Blst&Replace (100038887) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10233767 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 4 | 0 | 36 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137388 | 7 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-14 | 0 | 0 | Missing Staging Date | 4500001554, 4500001554, 4500001554 | During Turnaround | 2024-03-15 | Need Purchasing | 00001373884539310233767000100038887 | 00001373884539310233767000100038887 | 000013738810233767000100038887 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-04 | 2024-04-09 | PAINT |  | 100038888 | 0030 | CT2 - 2COT STBD X-Over Ramp Blst&Replace (100038888) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10233767 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 4 | 0 | 36 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137389 | 8 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-11 | 0 | 0 | Missing Staging Date | 4500001554, 4500001554, 4500001554 | During Turnaround | 2024-03-15 | Need Purchasing | 00001373894539010233767000100038888 | 00001373894539010233767000100038888 | 000013738910233767000100038888 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-31 |  | 2024-03-29 | 2024-04-02 | PAINT |  | 100038890 | 0030 | CT4 - 4WBT PORT FWD Ramp Blast & Replace (100038890) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10233767 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 4 | 0 | 36 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137391 | 8 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-03 | 0 | 0 | Missing Staging Date | 4500001554, 4500001554, 4500001554 | During Turnaround | 2024-03-15 | Need Purchasing | 00001373914538210233767000100038890 | 00001373914538210233767000100038890 | 000013739110233767000100038890 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-17 |  | 2024-04-13 | 2024-04-19 | PAINT |  | 100038891 | 0020 | CT5 - 5COT PORT X-Over Ramp Blst&Replace (100038891) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10233767 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 4 | 0 | 36 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137392 | 7 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-20 | 0 | 0 | Missing Staging Date | 4500001554, 4500001554, 4500001554 | During Turnaround | 2024-03-15 | Need Purchasing | 00001373924539910233767000100038891 | 00001373924539910233767000100038891 | 000013739210233767000100038891 |  |  | 1
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-05 | 2024-03-13 | 2024-04-05 | 2024-04-08 | MECH |  | 200083257 | 0030 | 5Y PORTABLE FIRE EXT REPLACEMENT (200083257) | EXT FIRE,DP,9KG,B DECK FWD (AB50.05EXP017) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | 2024-04-05 |  |  | AB01 |  | 10 | 5 | 10236513 | EXTINGUISHER,FIRE;FOAM,FOAM,ARC,9L,PORT | 1 | 0 | 0 | ISSUE. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003915 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120455 | 3 | 3 | 30 | 30 | Supply for Order 200083257, Item 3 cannot be changed 90001664 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-08 | -5 | 23 | ON TIME |  | On Time | 2023-09-14 | Need Purchasing | 00001204554538710236513000200083257 | 00001204554538710236513000200083257 | 000012045510236513000200083257 | 0 | #N/A | 0
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-13 | CRANE |  | 100038739 | 0052 | Replace HPU level sight glass (100038739) | GAUGE,X790001-AMD2023, LEVEL (AB50.05X790001-YMD8790) | Replace hyd tank level sight glass - aft (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10241131 | PAD;ABSORBENT,OIL/FUEL,SPILL,100/PK | 1 | 0 | 21 | UserCommentLink | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | PAC |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137260 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001372604542110241131000100038739 | 00001372604542110241131000100038739 | 000013726010241131000100038739 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0030 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10243755 | NUT,LK;SOLAR 903112C1 | 12 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002004 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT1 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 2024-03-01 | Need Purchasing | 00001380454542110243755000100039544 | 00001380454542110243755000100039544 | 000013804510243755000100039544 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-03-28 | 2024-03-30 | MECH |  | 100037795 | 0022 | CLASS Repl 4SWBT Draft Gauge Vlv (100037795) | VALVE,CP850370B,WBT 4 SB,DRAFT GAUGE (AB50.03SP752429) | Empty 4S WBT (0010) | AB50 | 2024-03-28 |  |  | AB01 |  | 10 | 5 | 10245447 | GASKET;CNAF,JIS10K,80MM,1.5MM,FF,C4430 | 2 | 2 | 0 | OK PDC TO PICK. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001629 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000136296 | 2 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2026-05-27 | 0 | 0 |  |  | 0 | 0 |  | 4 |  |  |  | 0 | 0 | 0.33333 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001362964537910245447000100037795 | 00001362964537910245447000100037795 | 000013629610245447000100037795 | 0 | #N/A | 0
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 |  | 2024-04-04 | 2024-04-04 | INLEC |  | 200084031 | 0010 | 1Y RADAR MAGNETRON REPLACEMENT (200084031) | ANTENNA,S BAND ANTENNA (AB50.03CARD612806) | REMOVE & REPLACE RADAR MAGNETRON (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10249942 | MAGNETRON,X-BAND;EEV MG5424 | 3 | 0 | 5 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122040 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-07 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001220404538610249942000200084031 | 00001220404538610249942000200084031 | 000012204010249942000200084031 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-09 | INLEC |  | 100033881 | 0010 | Repl EM Light Batteries & Diffuser MOD5 (100033881) | LIGHT,FLUOR,BTE1074-05-005 (AB50.05LT400102W6513) | Isolate Lighting 05LT400302B24 & R25 (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10251722 | DIFFUSER;CHALMIT SPROT100295 | 1 | 11 | 0 | OK . - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004741 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132353 | 1 | 4 | 30 | 30 | Supply for Order 100033881, Item 1 cannot be changed 90003360 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001323534542110251722000100033881 | 00001323534542110251722000100033881 | 000013235310251722000100033881 | 0 | #N/A | 0
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-04-09 | 2024-04-09 | MECH |  | 200086029 | 0012 | 5Y F15 LAYFLAT HOSE REPL CARG DECK (200086029) | HOSE,WTR,UPPER DECK (AB50.03FHR060) | LAYFLAT HOSE RECIRTIFICATION (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10288499 | HOSE ASY;WTR/FOAM,RED,38MMX18M LG | 32 | 32 | 1 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000124287 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-15 | SOH | 00001242874539110288499000200086029 | 00001242874539110288499000200086029 | 000012428710288499000200086029 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | MECH |  | 100034055 | 0010 | Inspect EGC2 Discharge Cooler TCV042574 (100034055) | VALVE,TIC042574,CONTR COOL MED OUTLET (AB50.05TCV042574) | Inspect EGC2 Discharge Cooler TCV042574 (0020) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10294417 | GASKET;FISHER RGASKETX392 | 1 | 1 | 7 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132609 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001326094540010294417000100034055 | 00001326094540010294417000100034055 | 000013260910294417000100034055 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-05-15 | 2024-05-09 | 2024-05-13 | CRANE |  | 100038739 | 0030 | Replace HPU level sight glass (100038739) | GAUGE,X790001-AMD2023, LEVEL (AB50.05X790001-YMD8790) | Replace hyd tank level sight glass - aft (0010) | AB50 | 2024-05-30 |  |  | AB01 |  | 20 | 20 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 1 | 1 | 1 | UserCommentLink | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001746 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137260 | 2 | 4 | 30 | 30 | Supply for Order 100038739, Item 2 cannot be changed 90003273 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 21 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | -34 | -6 | Delayed |  | On Time | 0 | SOH | 00001372604542110300759000100038739 | 00001372604542110300759000100038739 | 000013726010300759000100038739 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-04 |  | 2024-05-04 | 2024-05-05 | INLEC |  | 100033739 | 0010 | Replace EM Light Batteries MOD12 (9off) (100033739) | LIGHT,EMERG, MOD 12,PROCESS DECK (AB50.05LT400302B4505) | Conduct Lighting cct iso's x3 as req'd (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 9 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132271 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-06 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001322714541610304033000100033739 | 00001322714541610304033000100033739 | 000013227110304033000100033739 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-05 |  | 2024-05-05 | 2024-05-05 | INLEC |  | 100033781 | 0010 | Repl EM Batteries MOD3 (6off) (100033781) | LIGHT,EMERG MOD 3 LEVEL 2 (AB50.05LT400302B1811) | Isolate Lighting CCT's as Required (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 6 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132273 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-07 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001322734541710304033000100033781 | 00001322734541710304033000100033781 | 000013227310304033000100033781 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-06 |  | 2024-05-06 | 2024-05-06 | INLEC |  | 100033782 | 0010 | Repl EM Light Batteries MOD13 (4off) (100033782) | LIGHT,EMERG MOD 13 UPPER DECK (AB50.05LT400302W4712) | Isolate Lighting CCT's as Required (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 4 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132274 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-08 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001322744541810304033000100033782 | 00001322744541810304033000100033782 | 000013227410304033000100033782 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-06 |  | 2024-05-06 | 2024-05-06 | INLEC |  | 100033783 | 0010 | Replace EM Light Batteries MOD11 (5off) (100033783) | LIGHT,EMERG MOD 11 PROCESS DECK (AB50.05LT400302R4007) | Isolate Lighting CCT's as Required (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 5 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132275 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-08 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001322754541810304033000100033783 | 00001322754541810304033000100033783 | 000013227510304033000100033783 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-07 |  | 2024-05-07 | 2024-05-07 | INLEC |  | 100033784 | 0020 | Replace EM & Exit Light Batteries LER (6 (100033784) | LIGHT,EMERG EXIT MOD 13 INTERNAL (AB50.05LT400302R0113) | Replace 6x Em Batteries & Ex Inspection (0020) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 5 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132276 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-09 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001322764541910304033000100033784 | 00001322764541910304033000100033784 | 000013227610304033000100033784 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-04-17 |  | 2024-04-17 | 2024-04-17 | INLEC |  | 100033785 | 0010 | Replace LT400302B3605 Battery MOD8 (100033785) | LIGHT,EMERG MOD 8 UPPER DECK (AB50.05LT400302B3605) | Isolate Lt CCT LT400302B36 (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 1 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000132277 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-20 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001322774539910304033000100033785 | 00001322774539910304033000100033785 | 000013227710304033000100033785 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-03-28 |  | 2024-03-28 | 2024-03-28 | INLEC |  | 100033786 | 0010 | Replace EM LT400302R0110 Batt Battery RM (100033786) | LIGHT,EMERG MOD 13 INTERNAL (AB50.05LT400302R0110) | Isolate Lighting CCT LT400302R01 (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 1 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000132278 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-02-29 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001322784537910304033000100033786 | 00001322784537910304033000100033786 | 000013227810304033000100033786 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-03-28 |  | 2024-03-28 | 2024-03-28 | INLEC |  | 100033880 | 0010 | Repl MOD6 G/Tray & EM Light Bat (2off) (100033880) | LIGHT,FLUOR,JN413-5102 (AB50.05LT400102W7106) | Isolate Lt cct's 05LT400102W71 & B27 (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 1 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000132352 | 1 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-29 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001323524537910304033000100033880 | 00001323524537910304033000100033880 | 000013235210304033000100033880 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | INLEC |  | 100033881 | 0020 | Repl EM Light Batteries & Diffuser MOD5 (100033881) | LIGHT,FLUOR,BTE1074-05-005 (AB50.05LT400102W6513) | Isolate Lighting 05LT400302B24 & R25 (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10304033 | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 4 | 0 | 54 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132353 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date | 4500005690, W451778135, W451780469 | After Turnround | 2024-05-10 | Need Purchasing | 00001323534542110304033000100033881 | 00001323534542110304033000100033881 | 000013235310304033000100033881 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-10 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100032535 | 0020 | Repl TEG Transmitter 05LT130112 (100032535) | TX,LIC130112,LEVEL (AB50.05LT130112) | 05LC130112 in Man. Isolate & Disconnect (0010) | AB50 | [5 empty] | 20 | 20 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 4 | 0 | 0 | ETA. - ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131039 | 2 | 3 | 30 |  | Supply Process could not be determined for item 2, material 10305744 Plant AB50, check config. |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-06-04 | Need Purchasing | 00001310394540010305744000100032535 | 00001310394540010305744000100032535 | 000013103910305744000100032535 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0150 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10355246 | VALVE,GLOBE;DN40,PN25,LAVAL AG9685005747 | 1 | 2 | 2 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 90 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 21 | 2 | 30 | 30 | Supply for Order 200091461, Item 21 cannot be changed 90002702 item 90 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510355246000200091461 | 00001296914539510355246000200091461 | 000012969110355246000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0130 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10355246 | VALVE,GLOBE;DN40,PN25,LAVAL AG9685005747 | 1 | 2 | 2 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 80 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 19 | 2 | 30 | 30 | Supply for Order 200091461, Item 19 cannot be changed 90002702 item 80 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510355246000200091461 | 00001296914539510355246000200091461 | 000012969110355246000200091461 | 0 | #N/A | 0
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0050 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10402509 | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 | 2 | 0 | 8 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | DR |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 5 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-15 | Need Purchasing | 00000963414542110402509000200061999 | #N/A | 000009634110402509000200061999 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 100033628 | 0030 | Repl Swivel HPU Bursting Disc & Bladder (100033628) | ACC,A098200,HYDR OIL BACK-UP (AB50.04V098000A) | Repl Swivel HPU Bursting Disc & Bladder (0020) | AB50 |  |  |  | AB02 |  | 20 | 20 | 10423729 | GAS,COMP;N2,IND GDE,EHP 99.5%,G2,MOP16 | 1 | 0 | 0 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | SET |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132149 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-02 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001321494542110423729000100033628 | 00001321494542110423729000100033628 | 000013214910423729000100033628 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0060 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10424330 | FILTER KIT,ELEM,LUBE OIL;SOLAR 10647286 | 1 | 0 | 2 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 6 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 2 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-03-30 | Need Purchasing | 00000963414542110424330000200061999 | #N/A | 000009634110424330000200061999 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | INLEC |  | 200067754 | 0010 | 5Y HPU HP ESD B SOLENOID REPLACEMENT (200067754) | SOL,02A758001 ESD HYD OIL HP-B SUPPLY (AB50.02XZV758053B) | REPLACE HP ESD SOLENOID (0020) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10430531 | VALVE,SLND;BIFOLD FP15S30632S78A155 | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000102123 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-10-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-19 | Need Purchasing | 00001021234542110430531000200067754 | 00001021234542110430531000200067754 | 000010212310430531000200067754 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 200078320 | 0042 | 1Y LUBE OIL PURIFIER OVERHAUL A (200078320) | PKG EQ,LO PURIFIER A (AB50.03A755790) | ISOLATIONS OF LUBE OIL PURIFIER (0020) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10438411 | SERV KIT;MAJOR,PURIFIER,LAVAL 54815301 | 1 | 1 | 1 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000112609 | 4 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-26 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001126094542110438411000200078320 | 00001126094542110438411000200078320 | 000011260910438411000200078320 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 200064912 | 0012 | 1Y LUBE OIL PURIFIER OVERHAUL B (200064912) | PKG EQ,LO PURIFIER B (AB50.03A755890) | ISOLATIONS OF LUBE OIL PURIFIER (0020) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10438413 | PLATE,ELS;LAVAL 6057100 | 1 | 1 | 11 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000099214 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-26 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00000992144542110438413000200064912 | #N/A | 000009921410438413000200064912 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 200064912 | 0032 | 1Y LUBE OIL PURIFIER OVERHAUL B (200064912) | PKG EQ,LO PURIFIER B (AB50.03A755890) | ISOLATIONS OF LUBE OIL PURIFIER (0020) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10438563 | NOZZLE;LAVAL 54233604 | 2 | 2 | 12 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000099214 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-26 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00000992144542110438563000200064912 | #N/A | 000009921410438563000200064912 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-04-03 | 2024-04-24 | 2024-04-24 | MECH |  | 100039936 | 0010 | CLASS Replace ER Draft Gauge Vlv Potenti (100039936) | VALVE,CP850370C,ENG ROOM HYD HAND VALVE (AB50.03SP752427) | ROV Scope Awareness (0010) | AB50 | 2024-04-24 |  |  | AB01 |  | 10 | 5 | 10439222 | VALVE,COMPL;SHIPHAM DM991209E | 1 | 0 | 2 | 0216 - Gr'd -STO5000014700 | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002106 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138437 | 1 | 3 | 30 | 30 | Supply for Order 100039936, Item 1 cannot be changed 90003285 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2026-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-27 | -7 | 21 | ON TIME |  | During Turnaround | 2024-03-27 | Need Purchasing | 00001384374540610439222000100039936 | 00001384374540610439222000100039936 | 000013843710439222000100039936 | 0 | #N/A | 0
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 100033628 | 0020 | Repl Swivel HPU Bursting Disc & Bladder (100033628) | ACC,A098200,HYDR OIL BACK-UP (AB50.04V098000A) | Repl Swivel HPU Bursting Disc & Bladder (0020) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10440971 | BLADDER KIT,ACC;OLAER 19034200225 | 2 | 0 | 1 | ETA. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132149 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-02 | 0 | 0 |  |  | 0 | 0 |  | 1 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001321494542110440971000100033628 | 00001321494542110440971000100033628 | 000013214910440971000100033628 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 |  | 2024-05-01 | 2024-05-03 | MECH |  | 200082368 | 0070 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200082368) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10443257 | KIT,FILTER ELM;JOHN CRANE 89689834 | 1 | 0 | 2 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | SET |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118281 | 5 | 4 |  | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-09-16 | Need Purchasing | 00001182814541410443257000200082368 | 00001182814541410443257000200082368 | 000011828110443257000200082368 |  |  | 1
24OKCO13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-05 |  | 2024-04-05 | 2024-04-05 | MECH |  | 200084013 | 0010 | 3M MAINT OF START/EMER AIR COMPRESSOR (200084013) | COMPR,A470004,STARTING AIR NO 4 (AB50.03K470004) | CONDUCT 3M MAINT ON START/EMER COMP (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10444408 | FILTER,OIL;SPERRE 3722 | 2 | 4 | 5 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122114 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-12 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001221144538710444408000200084013 | 00001221144538710444408000200084013 | 000012211410444408000200084013 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 |  | 2024-05-01 | 2024-05-03 | MECH |  | 200082368 | 0060 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200082368) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10445237 | ELEMENT ASY,FLT;SIEMENS 64441565 | 1 | 4 | 3 | OK - PDC. | 0 |  | Stock at Base and Remote (SP11) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118281 | 4 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-11-21 | SOH | 00001182814541410445237000200082368 | 00001182814541410445237000200082368 | 000011828110445237000200082368 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-02-20 | 2024-05-09 | 2024-05-09 | MECH |  | 100034425 | 0020 | Replace LGC1 Seal Sys Vlv HV043018 (100034425) | VALVE,K043300SEAL,MAN ISOL (AB50.05HV043018) | Replace LGC1 Seal Sys Vlv HV043018 (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10445243 | VALVE,GATE;25MM,CL1500,SIEMENS 11788565 | 1 | 0 | 0 | ETA. - Y. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000124 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000132929 | 2 | 4 | 30 | 30 | Supply for Order 100034425, Item 2 cannot be changed 90001630 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 51 | 79 | ON TIME | W451777676 | After Turnround | 2024-04-12 | Need Purchasing | 00001329294542110445243000100034425 | 00001329294542110445243000100034425 | 000013292910445243000100034425 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0180 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447452 | VALVE,GLOBE;25MM,ARI 23006RPN25DN25C08B | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 140 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 23 | 2 | 30 | 30 | Supply for Order 200090465, Item 23 cannot be changed 90002701 item 130 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447452000200090465 | 00001287344539110447452000200090465 | 000012873410447452000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0140 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447453 | VALVE,GLOBE;40MM,ARI 23006RPN25DN40C11B | 1 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 100 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 19 | 2 | 30 | 30 | Supply for Order 200090465, Item 19 cannot be changed 90002701 item 90 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447453000200090465 | 00001287344539110447453000200090465 | 000012873410447453000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0160 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447453 | VALVE,GLOBE;40MM,ARI 23006RPN25DN40C11B | 1 | 2 | 0 | OK - PDC Pick. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 120 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 21 | 2 | 30 | 30 | Supply for Order 200090465, Item 21 cannot be changed 90002701 item 110 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447453000200090465 | 00001287344539110447453000200090465 | 000012873410447453000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0220 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447458 | VALVE,GLOBE;80MM,ARI 23006PN25DN80C07A | 1 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 180 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 27 | 2 | 30 | 30 | Supply for Order 200090465, Item 27 cannot be changed 90002701 item 170 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447458000200090465 | 00001287344539110447458000200090465 | 000012873410447458000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0190 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447458 | VALVE,GLOBE;80MM,ARI 23006PN25DN80C07A | 1 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 150 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 24 | 2 | 30 | 30 | Supply for Order 200090465, Item 24 cannot be changed 90002701 item 140 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447458000200090465 | 00001287344539110447458000200090465 | 000012873410447458000200090465 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-30 | 2024-05-09 | 2024-05-10 | MECH |  | 200063469 | 0020 | CALIBRATE RV ROTABLE (200063469) | PSV,PCV750030A,PCV FAIL (AB50.03PSV750061) | CERTIFY PSV FROM STOCK (0010) | AB50 | 2024-05-09 | AB01 |  | AB03 |  | 20 | 20 | 10447827 | VALVE,REL,BROADY 3511N-CN-021,566-614KPA | 1 | 1 | 0 | OK. - PDC. | 0 | STO raised (through orchestration) | Stock at Base (SP12) | AB03 | 5300003606 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  | REFURB |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000097778 | 2 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | -19 | 9 | ON TIME |  | On Time | 0 | SOH | 00000977784542110447827000200063469 | #N/A | 000009777810447827000200063469 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-10 |  | 2024-05-09 | 2024-05-10 | MECH |  | 200063469 | 0010 | CALIBRATE RV ROTABLE (200063469) | PSV,PCV750030A,PCV FAIL (AB50.03PSV750061) | RETURN PSV TO WAREHOUSE (0100) | AB50 | [5 empty] | 20 | 20 | 10447827 | VALVE,REL,BROADY 3511N-CN-021,566-614KPA | -1 | 0 | 0 | ISSUE - RETURNS | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  | DAMAGED |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000097778 | 3 | 3 | 30 |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00000977784542210447827000200063469 | #N/A | 000009777810447827000200063469 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-05-04 | 2024-05-09 | 2024-05-10 | MECH |  | 200063469 | 0010 | CALIBRATE RV ROTABLE (200063469) | PSV,PCV750030A,PCV FAIL (AB50.03PSV750061) | CERTIFY PSV FROM STOCK (0010) | AB50 | 2024-05-09 | AB01 |  | AB02 |  | 20 | 20 | 10447849 | GASKET SET;BROADY P106652 | 4 | 7 | 0 | OK. - PDC. | 0 | STO raised (through orchestration) | Stock at Base (SP12) | AB02 | 5300003605 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | SET |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000097778 | 1 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | -23 | 5 | ON TIME | 4500007030, 4500008796 | After Turnround | 2024-06-07 | SOH | 00000977784542110447849000200063469 | #N/A | 000009777810447849000200063469 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-05 | 2024-03-13 | 2024-04-05 | 2024-04-08 | MECH |  | 200083257 | 0040 | 5Y PORTABLE FIRE EXT REPLACEMENT (200083257) | EXT FIRE,DP,9KG,B DECK FWD (AB50.05EXP017) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | 2024-04-05 |  |  | AB01 |  | 10 | 5 | 10451306 | EXTINGUISHER,FIRE;2.3KG,AMEREX AB500TAS | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003915 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120455 | 4 | 3 | 30 | 30 | Supply for Order 200083257, Item 4 cannot be changed 90001664 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-08 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001204554538710451306000200083257 | 00001204554538710451306000200083257 | 000012045510451306000200083257 | 0 | #N/A | 0
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-11 |  | 2024-04-11 | 2024-04-11 | MECH |  | 200083367 | 0020 | 1Y F15 FOAM FIRE EXT SPARES (200083367) | EXT FIRE,FOAM FIRE EXT SPARES-9LTR (AB50.EXT-FOAM-001) | INSPECT & TEST FIRE EXTINGUISHER (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10451345 | EXTINGUISHER,FIRE;FOAM,AR-AFFF,45L | 2 | 0 | 3 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120709 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-05 | Need Purchasing | 00001207094539310451345000200083367 | 00001207094539310451345000200083367 | 000012070910451345000200083367 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-10 |  | 2024-04-10 | 2024-04-11 | MECH |  | 200083535 | 0012 | 1Y BA COMPRESSOR INSPECTION & SERVICE (200083535) | COMPR,BREATHING AIR (AB50.03K600010) | CONDUCT SERVICE OF BA COMPRESSOR (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10451369 | SERV KIT;COMP,BAUER A120IIF7ABC1 | 1 | 1 | 2 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121112 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-13 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001211124539210451369000200083535 | 00001211124539210451369000200083535 | 000012111210451369000200083535 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-10 |  | 2024-04-10 | 2024-04-11 | MECH |  | 200083535 | 0022 | 1Y BA COMPRESSOR INSPECTION & SERVICE (200083535) | COMPR,BREATHING AIR (AB50.03K600010) | CONDUCT SERVICE OF BA COMPRESSOR (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10451370 | ELEMENT,FLT;AIR,BAUER N70 | 2 | 2 | 4 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121112 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-13 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001211124539210451370000200083535 | 00001211124539210451370000200083535 | 000012111210451370000200083535 |  |  | 1
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | OPS |  | 200056909 | 0010 | 3W BIOCIDE DOSING OF COOLING MEDIUM (200056909) | EDUCTOR,CHEM TREATMENT (AB50.05SP460042) | BIOCIDE DOSE OF COOLING MEDIUM (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10452835 | BIOCIDE;25L,CHAMPIONX BIOC77352A11R | 1 | 0 | 10 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CON |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000091197 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-06 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00000911974540010452835000200056909 | #N/A | 000009119710452835000200056909 |  |  | 1
24OKCO13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-05 |  | 2024-04-05 | 2024-04-05 | OPS |  | 200057510 | 0010 | 3W BIOCIDE DOSING OF COOLING MEDIUM (200057510) | EDUCTOR,CHEM TREATMENT (AB50.05SP460042) | BIOCIDE DOSE OF COOLING MEDIUM (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10452835 | BIOCIDE;25L,CHAMPIONX BIOC77352A11R | 1 | 0 | 10 | OK. - CAMPAIGN PICK PDC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CON |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000091798 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-15 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00000917984538710452835000200057510 | #N/A | 000009179810452835000200057510 |  |  | 1
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-05 |  | 2024-05-05 | 2024-05-06 | MECH |  | 200083040 | 0020 | 6M P05 INSP/LUBE OF TURRET SWIVEL UNITS (200083040) | TURRET,PRODUCTION SWIVEL 1 (AB50.04V020001) | INSPECT & LUBRICATE TURRET SWIVEL (0010) | AB50 |  | AB01 |  | AB02 |  | 10 | 5 | 10452872 | OIL,LUB;OMALAS4GX460,20L,SHELL 300011329 | 1 | 1 | 2 | OK. - OLC. | 0 |  | Stock at Base and Remote (SP11) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | DR |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000119827 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-07 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001198274541710452872000200083040 | 00001198274541710452872000200083040 | 000011982710452872000200083040 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 200064912 | 0020 | 1Y LUBE OIL PURIFIER OVERHAUL B (200064912) | PKG EQ,LO PURIFIER B (AB50.03A755890) | ISOLATIONS OF LUBE OIL PURIFIER (0020) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10453016 | OIL,GEAR,SHELL OMALA S2 GX 320,20L | 1 | 0 | 2 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CON |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000099214 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-26 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | Need Purchasing | 00000992144542110453016000200064912 | #N/A | 000009921410453016000200064912 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 200078320 | 0020 | 1Y LUBE OIL PURIFIER OVERHAUL A (200078320) | PKG EQ,LO PURIFIER A (AB50.03A755790) | ISOLATIONS OF LUBE OIL PURIFIER (0020) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10453016 | OIL,GEAR,SHELL OMALA S2 GX 320,20L | 1 | 0 | 2 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CON |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000112609 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-26 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | Need Purchasing | 00001126094542110453016000200078320 | 00001126094542110453016000200078320 | 000011260910453016000200078320 |  |  | 1
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0082 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10454267 | GASKET,CNAF,900MM,CL150,RF,3MM,B16.47 A | 2 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000188 | 90 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 17 | 1 | 30 | 30 | Supply for Order 100034857, Item 17 cannot be changed 90001632 item 90 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | SOH | 00001334014537910454267000100034857 | 00001334014537910454267000100034857 | 000013340110454267000100034857 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-12 | 2024-05-07 | 2024-04-04 | 2024-05-07 | 2024-05-08 | REFURB |  | 100038113 | 0090 | ER - Repl Spool Steam Sys CDR-28781 (100038113) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | Replace 25-SL-3750656-EXB3A-H (0020) | AB50 | 2024-05-07 |  |  | AB01 |  | 30 | 30 | 10458155 | GASKET;CNAF,JIS16K,40MM,3MM,FF,C4430 | 1 | 0 | 0 | ETA. - PROC. INV. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006460 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136617 | 19 | 1 | 30 | 30 | Supply for Order 100038113, Item 19 cannot be changed 90003391 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-09 | 5 | 33 | ON TIME | 4500003832 | After Turnround | 2024-04-04 | Need Purchasing | 00001366174541910458155000100038113 | 00001366174541910458155000100038113 | 000013661710458155000100038113 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-10 | MECH |  | 100036218 | 0052 | GT1 Repair leaks main tank & return line (100036218) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Confirm isolations of GT1 (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10458397 | GASKET SET;CHESTERTON 860MPG3MM | 1 | 0 | 2 | OK. - OLC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001022 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134750 | 7 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2023-12-29 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001347504542110458397000100036218 | 00001347504542110458397000100036218 | 000013475010458397000100036218 | 0 | #N/A | 0
24OKCM13 | Shipped qty below requirement qty |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-29 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0430 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-04-01 |  |  | AB01 | 2024-03-16 | 20 | 20 | 10458817 | FITTING,ENG,TURB;SOLAR 23607R1 | 4 | 0 | 1 | OK. - AIR - RFT. | 6 | Material work-packed @AB50 | Directs (Inventory) (SP14) | AB01 | 5300004702 | 50 | 21 | X | 1000003993 | 42 | 2024-02-29 | 2024-03-14 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 4500004813 | 5000041570_2024_0001 | 50 | 1 | EA | 2024-03-15 |  | 180012111 | 180012424 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 42 | 1 | 30 | 30 | Supply for Order 100037574, Item 42 cannot be changed 9000764 item 20 already exists | 101000000027132 | 1 | FALSE |  |  |  | WorkPackLink |  |  | 16 | 0 | 2024-06-30 | 0 | 0 | 2024-03-16 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538710458817000100037574 | 00001360984538710458817000100037574 | 000013609810458817000100037574 | 0 | #N/A | 0
24OKCM13 | PR due for release |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-23 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0400 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-03-26 |  |  | AB01 | 2024-03-10 | 20 | 20 | 10462880 | ELBOW,PIPE;UNION,0.375",SOLAR 952344C1 | 2 | 0 | 2 | OK. | 30 | PR approved; PO not issued | Directs (Inventory) (SP14) | AB01 | 5300004702 | 20 | 21 | X | 1000003478 | 39 | 2024-02-23 | 2024-03-08 |  |  |  | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 39 | 1 | 30 | 30 | Supply for Order 100037574, Item 39 cannot be changed 90002201 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 16 | 0 | 2024-06-30 | 0 | 0 | 2024-03-10 |  | 0 | 0 |  | 2 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 14 | 42 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538710462880000100037574 | 00001360984538710462880000100037574 | 000013609810462880000100037574 | 0 | #N/A | 0
24OKCM13 | PR due for release |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-23 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0410 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-03-26 |  |  | AB01 | 2024-03-10 | 20 | 20 | 10463080 | FITTING,PIPE,M,1"X 3/4",SAE/MS,964600C1 | 1 | 0 | 1 | OK. | 7 | PR approved; PO not issued | Directs (Inventory) (SP14) | AB01 | 5300004702 | 30 | 21 | X | 1000003478 | 40 | 2024-02-23 | 2024-03-08 |  |  |  | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 40 | 1 | 30 | 30 | Supply for Order 100037574, Item 40 cannot be changed 90002201 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 16 | 0 | 2024-06-30 | 0 | 0 | 2024-03-10 |  | 0 | 0 |  | 1 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 14 | 42 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538710463080000100037574 | 00001360984538710463080000100037574 | 000013609810463080000100037574 | 0 | #N/A | 0
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0470 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10463417 | FITTING,PIPE,1/2"X 1/2",SOLAR 960814C1 | 1 | 0 | 5 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 46 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001360984538710463417000100037574 | 00001360984538710463417000100037574 | 000013609810463417000100037574 |  |  | 1
24OKCM13 | Vendor Not able to deliver on-time |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-29 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0440 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-04-09 |  |  | AB01 | 2024-03-20 | 20 | 20 | 10463589 | CLAMP,SPLIT FLG,2",SS,RF,SOLAR 980656C1 | 2 | 0 | 2 | OK. - AIR - RFT. | 98 | Shipping notification from Vendor received | Directs (Inventory) (SP14) | AB01 | 5300004702 | 60 | 21 | X | 1000004043 | 43 | 2024-02-29 | 2024-03-18 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 4500004816 |  | 20 | 2 | EA | 2024-03-18 |  | 180012110 |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 43 | 1 | 30 | 30 | Supply for Order 100037574, Item 43 cannot be changed 90002704 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 20 | 0 | 2024-06-30 | 0 | 0 | 2024-03-20 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 8 | 36 | ON TIME | 4500004816 | During Turnaround | 2024-03-18 | Need Purchasing | 00001360984538710463589000100037574 | 00001360984538710463589000100037574 | 000013609810463589000100037574 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-02-22 | 2024-05-09 | 2024-02-22 | 2024-05-09 | 2024-05-10 | MECH |  | 200079587 | 0030 | 4Y F21 NRV LGC 1 REPLACE WITH ROTABLE (200079587) | VALVE,E043301,NRV,GAS OUTLET (AB50.05MV043065) | CHANGE OUT VALVE WITH SPARE (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 10 | 5 | 10467825 | GASKET,RJ;OCT,R46,SI | 4 | 0 | 0 | ETA, - PROC. - | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006997 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000113856 | 3 | 3 | 30 | 30 | Supply for Order 200079587, Item 3 cannot be changed 90002066 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 49 | 77 | ON TIME |  | During Turnaround | 2024-03-15 | Need Purchasing | 00001138564542110467825000200079587 | 00001138564542110467825000200079587 | 000011385610467825000200079587 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-02-21 | 2024-05-09 | 2024-05-12 | MECH |  | 100038290 | 0010 | Repl Motor & Align FGC Condensate Pp-B (100038290) | PUMP,FGC CONDENSATE B (AB50.05P041101B) | Remove FGC B Cond Motor (0030) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10468800 | MOTOR,AC;440V,2P,ABB M3GP132SMB2EXNAIIT3 | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001696 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136822 | 1 | 1 |  |  | Supply for Order 100038290, Item 1 cannot be changed 90001649 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 50 | 78 | ON TIME |  | On Time | 0 | SOH | 00001368224542110468800000100038290 | 00001368224542110468800000100038290 | 000013682210468800000100038290 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 | 2024-04-03 | 2024-04-04 | 2024-04-05 | INLEC |  | 100040735 | 0010 | Replace GMDSS HF RX Antenna (100040735) | ANTENNA,MF/HF DSC RX ANTENNA (AB50.03CAHF612805) | Replace GMDSS HF RX Antenna (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 10 | 5 | 10468906 | ANTENNA;COMROD AR62 | 1 | 0 | 1 | SOH @ AB50 | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002322 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000139267 | 1 | 3 | 30 | 30 | Supply for Order 100040735, Item 1 cannot be changed 90002428 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA Stores |  | 0 | 14 | 2024-05-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-07 | -27 | 1 | ON TIME |  | On Time | 2024-01-15 | Need Purchasing | 00001392674538610468906000100040735 | 00001392674538610468906000100040735 | 000013926710468906000100040735 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0230 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10473813 | VALVE,ARI 35.006R,PN40,DN25,CS,GLOBE | 1 | 0 | 0 | ETA 01.07.24 PO 4500000722 x 2 SCORE | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 190 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 28 | 2 | 30 | 30 | Supply for Order 200090465, Item 28 cannot be changed 90002701 item 180 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | After Turnround | 2024-07-01 | Need Purchasing | 00001287344539110473813000200090465 | 00001287344539110473813000200090465 | 000012873410473813000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0230 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10473813 | VALVE,ARI 35.006R,PN40,DN25,CS,GLOBE | 1 | 0 | 0 | ETA 01.07.24 PO 4500000722 x 2 SCORE | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 110 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 29 | 2 | 30 | 30 | Supply for Order 200091461, Item 29 cannot be changed 90002702 item 110 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | After Turnround | 2024-07-01 | Need Purchasing | 00001296914539510473813000200091461 | 00001296914539510473813000200091461 | 000012969110473813000200091461 | 0 | #N/A | 0
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 200078320 | 0032 | 1Y LUBE OIL PURIFIER OVERHAUL A (200078320) | PKG EQ,LO PURIFIER A (AB50.03A755790) | ISOLATIONS OF LUBE OIL PURIFIER (0020) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10473861 | SERV KIT;INTER,PURIFIER,LAVAL 55461001 | 1 | 1 | 10 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000112609 | 5 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-26 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001126094542110473861000200078320 | 00001126094542110473861000200078320 | 000011260910473861000200078320 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-22 | 2024-04-25 | INSP |  | 200082341 | 0010 | 5Y INT INSP/CLASS SURVEY 03E753050 (200082341) | VE,ATMOSPHERIC CONDENSER (AB50.03E753050) | RE-INSTATE SPOOL/HEAD POST INSPECTION (0060) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10476885 | GASKET;467MM ID X 570MM OD X 3MM THK | 4 | 0 | 4 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118169 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA |  | 0 | 0 | 2024-05-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-14 | Need Purchasing | 00001181694540610476885000200082341 | 00001181694540610476885000200082341 | 000011816910476885000200082341 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0470 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10477745 | GASKET;MANHOLE,LAVAL 9970054 | 1 | 0 | 4 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 35 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001287344539110477745000200090465 | 00001287344539110477745000200090465 | 000012873410477745000200090465 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-12 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0490 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | BOX UP ACCESS HATCHES (0160) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10477745 | GASKET;MANHOLE,LAVAL 9970054 | 1 | 0 | 4 | SOH @ AB50 | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 10 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-15 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001296914539410477745000200091461 | 00001296914539410477745000200091461 | 000012969110477745000200091461 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-12 |  | 2024-04-12 | 2024-04-13 | MECH |  | 200074182 | 0012 | 1Y PORTABLE FIRE EXT INSP & TEST (200074182) | EXT FIRE FOAM APPL,9L,TOPSIDES, MOD 11 (AB50.05EXAF013) | INSPECT & TEST FIRE EXTINBGUISHER (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10478596 | EXTINGUISHER,FIRE;FOAM,AFFF,9.4L,AMEREX | 204 | 204 | 18 | OK. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000108509 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-23 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-15 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001085094539410478596000200074182 | 00001085094539410478596000200074182 | 000010850910478596000200074182 |  |  | 1
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-11 |  | 2024-04-11 | 2024-04-11 | MECH |  | 200083367 | 0010 | 1Y F15 FOAM FIRE EXT SPARES (200083367) | EXT FIRE,FOAM FIRE EXT SPARES-9LTR (AB50.EXT-FOAM-001) | INSPECT & TEST FIRE EXTINGUISHER (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10478596 | EXTINGUISHER,FIRE;FOAM,AFFF,9.4L,AMEREX | 1 | 204 | 18 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120709 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001207094539310478596000200083367 | 00001207094539310478596000200083367 | 000012070910478596000200083367 |  |  | 1
24OKCO13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-05 |  | 2024-04-05 | 2024-04-05 | MECH |  | 200084013 | 0020 | 3M MAINT OF START/EMER AIR COMPRESSOR (200084013) | COMPR,A470004,STARTING AIR NO 4 (AB50.03K470004) | CONDUCT 3M MAINT ON START/EMER COMP (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10479633 | OIL,AIR COMP;SHELL 001D7788 | 3 | 7 | 0 | OK. - PDC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | PAI |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122114 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-12 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-04-02 | SOH | 00001221144538710479633000200084013 | 00001221144538710479633000200084013 | 000012211410479633000200084013 |  |  | 1
24OKCM19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0070 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10482346 | SEAL,METALLIC;12X18MM,SOLAR 912740C1 | 2 | 15 | 34 | OK. - PDC. | 0 |  | Stock at Base and Remote (SP11) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | PAC |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 7 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00000963414542110482346000200061999 | #N/A | 000009634110482346000200061999 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-27 | 2024-05-09 | 2024-05-09 | MECH |  | 200063635 | 0010 | 4Y RECERTIFY PSV DISPOSABLE (200063635) | PSV,K470006,2ND STAGE PRESS (AB50.03PSV471561) | CERTIFY PSV (0010) | AB50 | 2024-04-09 | AB01 |  | AB03 |  | 10 | 10 | 10482558 | VALVE,REL,SEETRU 616820073,3400KPAG | 1 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB03 | Stock at Base (SP12) | AB03 | 5300003634 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000097984 | 1 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-12 | -15 | 13 | ON TIME | W451779258 | After Turnround | 2024-05-15 | SOH | 00000979844539110482558000200063635 | #N/A | 000009798410482558000200063635 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-12 | 2024-05-07 | 2024-04-04 | 2024-05-07 | 2024-05-08 | REFURB |  | 100038113 | 0080 | ER - Repl Spool Steam Sys CDR-28781 (100038113) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | Replace 25-SL-3750656-EXB3A-H (0020) | AB50 | 2024-05-04 |  |  | AB01 | 2024-04-19 | 30 | 30 | 10484646 | GASKET,CNAF;JIS10K,25MM,3MM,FF,C4430 | 2 | 0 | 0 | ETA - 17 April - Procurement - Klinger. | 14 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006460 | 40 | 21 | X | 1000003365 | 18 | 2024-02-22 | 2024-04-17 | KLINGER LIMITED (30000403) | 4500003833 |  | 10 | 2 | EA | 2024-04-17 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136617 | 18 | 1 | 30 | 30 | Supply for Order 100038113, Item 18 cannot be changed 90003391 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 15 | 0 | 2024-05-27 | 0 | 0 | 2024-04-19 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-09 | 5 | 33 | ON TIME | 4500003833 | After Turnround | 2024-04-17 | Need Purchasing | 00001366174541910484646000100038113 | 00001366174541910484646000100038113 | 000013661710484646000100038113 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0140 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10485935 | VALVE,MONOFLG,50MM,CL1500,FLG,DSS,D15M8T | 2 | 0 | 1 | ETA - 1X - Procurement.? | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 10 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | FALSE | 2024-03-12 | Need Purchasing | 00001427824540910485935000100044230 | 00001427824540910485935000100044230 | 000014278210485935000100044230 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 | 2024-04-03 | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0052 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 | 2024-04-27 |  |  | AB01 |  | 30 | 30 | 10485937 | VALVE,MONOFLG;50MM,CL1500,HAST,H15M8 | 1 | 0 | 1 | OK. - OLC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002304 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 11 | 4 | 30 | 30 | Supply for Order 100044230, Item 11 cannot be changed 90003291 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | -4 | 24 | ON TIME |  | After Turnround | 2024-07-05 | Need Purchasing | 00001427824540910485937000100044230 | 00001427824540910485937000100044230 | 000014278210485937000100044230 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 | 2024-02-19 | 2024-04-26 | 2024-04-26 | MECH |  | 200089401 | 0052 | 4Y REPLACE HOSES - INHIB INJECT SKID (200089401) | HOSE,T74003,CHEMICAL STORAGE TANK FILL (AB50.05SP740039) | REPLACE HOSES (0020) | AB50 | 2024-04-26 |  |  | AB01 |  | 20 | 20 | 10493398 | HOSE ASY,BIOCIDE;CONVOLUTED TECH STANDA> | 1 | 0 | 1 | SOH @ AB50 | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003821 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000127599 | 5 | 3 | 30 | 30 | Supply for Order 200089401, Item 5 cannot be changed 90001663 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-08-21 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-29 | 39 | 67 | ON TIME |  | On Time | 0 | Need Purchasing | 00001275994540810493398000200089401 | 00001275994540810493398000200089401 | 000012759910493398000200089401 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200089401 | 0022 | 4Y REPLACE HOSES - INHIB INJECT SKID (200089401) | HOSE,T74003,CHEMICAL STORAGE TANK FILL (AB50.05SP740039) | REPLACE HOSES (0020) | AB50 | [5 empty] | 20 | 20 | 10493398 | HOSE ASY,BIOCIDE;CONVOLUTED TECH STANDA> | 1 | 0 | 0 | PR 2000020754 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000127599 | 2 | 3 | 30 |  | Supply Process could not be determined for item 2, material 10493398 Plant AB50, check config. |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-08-21 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001275994540810493398000200089401 | 00001275994540810493398000200089401 | 000012759910493398000200089401 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 | 2024-02-19 | 2024-04-26 | 2024-04-26 | MECH |  | 200089401 | 0062 | 4Y REPLACE HOSES - INHIB INJECT SKID (200089401) | HOSE,T74003,CHEMICAL STORAGE TANK FILL (AB50.05SP740039) | REPLACE HOSES (0020) | AB50 | 2024-04-26 |  |  | AB01 |  | 20 | 20 | 10493399 | HOSE ASY,EMULSION;CONVOLUTED TECH STAND> | 1 | 0 | 1 | OK. - OLC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003821 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000127599 | 6 | 3 | 30 | 30 | Supply for Order 200089401, Item 6 cannot be changed 90001663 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-08-21 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-29 | 39 | 67 | ON TIME |  | On Time | 0 | Need Purchasing | 00001275994540810493399000200089401 | 00001275994540810493399000200089401 | 000012759910493399000200089401 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200089401 | 0042 | 4Y REPLACE HOSES - INHIB INJECT SKID (200089401) | HOSE,T74003,CHEMICAL STORAGE TANK FILL (AB50.05SP740039) | REPLACE HOSES (0020) | AB50 | [5 empty] | 20 | 20 | 10493399 | HOSE ASY,EMULSION;CONVOLUTED TECH STAND> | 1 | 0 | 0 | OK. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000127599 | 3 | 3 | 30 |  | Supply Process could not be determined for item 3, material 10493399 Plant AB50, check config. |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-08-21 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001275994540810493399000200089401 | 00001275994540810493399000200089401 | 000012759910493399000200089401 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 | 2024-02-19 | 2024-04-26 | 2024-04-26 | MECH |  | 200089401 | 0072 | 4Y REPLACE HOSES - INHIB INJECT SKID (200089401) | HOSE,T74003,CHEMICAL STORAGE TANK FILL (AB50.05SP740039) | REPLACE HOSES (0020) | AB50 | 2024-04-26 |  |  | AB01 |  | 20 | 20 | 10493402 | HOSE ASY,COR INH;2000MM,05SP740042 | 1 | 0 | 1 | OK. - OLC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003821 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000127599 | 7 | 3 | 30 | 30 | Supply for Order 200089401, Item 7 cannot be changed 90001663 item 40 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-08-21 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-29 | 39 | 67 | ON TIME |  | On Time | 0 | Need Purchasing | 00001275994540810493402000200089401 | 00001275994540810493402000200089401 | 000012759910493402000200089401 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200089401 | 0032 | 4Y REPLACE HOSES - INHIB INJECT SKID (200089401) | HOSE,T74003,CHEMICAL STORAGE TANK FILL (AB50.05SP740039) | REPLACE HOSES (0020) | AB50 | [5 empty] | 20 | 20 | 10493402 | HOSE ASY,COR INH;2000MM,05SP740042 | 1 | 0 | 0 | OK. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000127599 | 4 | 3 | 30 |  | Supply Process could not be determined for item 4, material 10493402 Plant AB50, check config. |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-08-21 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001275994540810493402000200089401 | 00001275994540810493402000200089401 | 000012759910493402000200089401 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2024-02-07 | 2024-02-09 | 2024-04-18 | 2024-03-21 | 2024-04-18 | 2024-04-18 | ENG05 |  | 100072801 | 0010 | Replace MDO B purifier water hose (100072801) | PKG EQ,MDO PURIFIER B (AB50.03A443001B) | Replace MDO B purifier water hose (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 30 | 30 | 10493451 | HOSE ASY,CW;13.6MM,AFLEX HYPERLINESB | 1 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006327 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000219434 | 1 | 3 | 30 | 30 | Supply for Order 100072801, Item 1 cannot be changed 90002710 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-02-01 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 28 | ON TIME |  | FALSE | 2024-03-07 | Need Purchasing | 00002194344540010493451000100072801 | 00002194344540010493451000100072801 | 000021943410493451000100072801 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0142 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10498808 | CONNECTOR,MALE;SS316,0.5",HOKE 8CM8316 | 2 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000188 | 100 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 18 | 1 | 30 | 30 | Supply for Order 100034857, Item 18 cannot be changed 90001632 item 100 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | SOH | 00001334014537910498808000100034857 | 00001334014537910498808000100034857 | 000013340110498808000100034857 | 0 | #N/A | 0
24OKCM13 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0062 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10501971 | COOLANT,PROPYLENE GLYCOL,DRM/20L | 40 | 800 | 160 | OK. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | L |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 19 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001334014537910501971000100034857 | 00001334014537910501971000100034857 | 000013340110501971000100034857 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-19 | MECH |  | 100034735 | 0012 | CLASS Repl Steam Drain Vlv Stripping Pp (100034735) | VALVE,SP750434,MAN THROTTLE,INLET (AB50.03MV750338) | Perform Isolations 03MV750338 (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10503357 | VALVE,GLOBE;BC6,16K,15A,F7409,HSN | 1 | 1 | 0 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133239 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-21 | 0 | 0 | Missing Staging Date | 4500000887 | On Time | 2024-02-24 | SOH | 00001332394540010503357000100034735 | 00001332394540010503357000100034735 | 000013323910503357000100034735 |  |  | 1
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0020 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10503782 | TOOL,CLAMP,LIFTING FRAME,KSB UG1281712 | 1 | 0 | 0 | 25.03.24: RISK - Last tracked as Del: 80836728 in L-PORTDECK in April 2022 | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000188 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 2 | 1 | 30 | 30 | Supply for Order 100034857, Item 2 cannot be changed 90001632 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910503782000100034857 | 00001334014537910503782000100034857 | 000013340110503782000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0010 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10503783 | TOOL,CLAMP,LIFTING FRAME,KSB UG1279444 | 1 | 0 | 0 | 25.03.24: RISK - Last tracked as Del: 80836728 in L-PORTDECK in April 2022 | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000188 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 1 | 1 | 30 | 30 | Supply for Order 100034857, Item 1 cannot be changed 90001632 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910503783000100034857 | 00001334014537910503783000100034857 | 000013340110503783000100034857 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-29 | 2024-04-05 | 2024-04-27 | 2024-05-02 | OPS |  | 200082353 | 0012 | 1Y TEST PV VACUUM VALVE (200082353) | VALVE,OKHA9021,VACUUM (AB50.03A480012A) | Assit with IG header isolation (0020) | AB50 | 2024-04-29 |  |  | AB01 |  | 10 | 5 | 10503901 | SCREW,SET;HEX,HVY,7/8" X 120MM,A193,B7 | 24 | 0 | 0 | OK - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003508 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118257 | 2 | 4 | 30 | 30 | Supply for Order 200082353, Item 2 cannot be changed 90003335 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-01 | 0 | 0 |  |  | 0 | 0 |  | 24 |  |  |  | 0 | 0 | 0.5 | 2024-04-01 | -4 | 24 | ON TIME |  | After Turnround | 2024-04-10 | Need Purchasing | 00001182574541110503901000200082353 | 00001182574541110503901000200082353 | 000011825710503901000200082353 | 0 | #N/A | 0
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-28 |  | 2024-04-28 | 2024-04-28 | MECH |  | 200084010 | 0010 | 3M INSTRUMENT AIR COMPRESSOR INSP (200084010) | COMPR,A470001,AIR COMPRESSOR 1 (AB50.03K470001) | MECHANICAL INSPECTION OF COMPRESSOR (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10504876 | ELEMENT KIT,FLT;ATCOP 2901300011 | 1 | 5 | 1 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000122106 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-12 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-31 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-06-27 | SOH | 00001221064541010504876000200084010 | 00001221064541010504876000200084010 | 000012210610504876000200084010 |  |  | 1
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-27 | MECH |  | 200084011 | 0010 | 3M INSTRUMENT AIR COMPRESSOR INSP (200084011) | COMPR,A470002,AIR COMPRESSOR 2 (AB50.03K470002) | MECHANICAL INSPECTION OF COMPRESSOR (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10504876 | ELEMENT KIT,FLT;ATCOP 2901300011 | 1 | 5 | 1 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000122109 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-12 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-06-27 | SOH | 00001221094540910504876000200084011 | 00001221094540910504876000200084011 | 000012210910504876000200084011 |  |  | 1
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200084012 | 0010 | 3M INSTRUMENT AIR COMPRESSOR INSP (200084012) | COMPR,K470003,AIR COMPRESSOR 3 (AB50.03K470003) | MECHANICAL INSPECTION OF COMPRESSOR (0010) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10504876 | ELEMENT KIT,FLT;ATCOP 2901300011 | 1 | 5 | 1 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000122112 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-12 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | After Turnround | 2024-06-27 | SOH | 00001221124540810504876000200084012 | 00001221124540810504876000200084012 | 000012211210504876000200084012 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2024-01-11 | 2024-02-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-07-06 | INLEC |  | 600002860 | 0040 | Paint OKHA Cables - UV Damaged (600002860) | SWBD,TOPSIDES 11KV SWITCHGEAR,DEF41003 (AB50.05SB400101) | LGA L3 Rope Access Paint / Permit holder (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10506101 | TAPE,ELEC,25MM X 4.6M,3M SCOTCH 24-TAPE | 50 | 0 | 0 | OK. | 0 | STO raised (through orchestration) | Stock at Base (SP12) | AB01 | 5300005952 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000213591 | 4 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | -12 | 16 | ON TIME |  | After Turnround | 2024-04-08 | Need Purchasing | 00002135914542110506101000600002860 | 00002135914542110506101000600002860 | 000021359110506101000600002860 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2024-01-11 | 2024-02-02 | 2024-05-09 | 2024-03-13 | 2024-05-09 | 2024-07-06 | INLEC |  | 600002860 | 0010 | Paint OKHA Cables - UV Damaged (600002860) | SWBD,TOPSIDES 11KV SWITCHGEAR,DEF41003 (AB50.05SB400101) | LGA L3 Rope Access Paint / Permit holder (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10506101 | TAPE,ELEC,25MM X 4.6M,3M SCOTCH 24-TAPE | 50 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300005952 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000213591 | 1 | 3 | 30 | 30 | Supply for Order 600002860, Item 1 cannot be changed 90001689 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | 29 | 57 | ON TIME |  | After Turnround | 2024-04-08 | Need Purchasing | 00002135914542110506101000600002860 | 00002135914542110506101000600002860 | 000021359110506101000600002860 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-31 | 2024-05-04 | 2024-04-03 | 2024-05-04 | 2024-05-05 | REFURB |  | 100039045 | 0030 | ER - Repl Spool LP Steam Sys CDR-28782 (100039045) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | replace spool (0020) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10507576 | GASKET;SWCI,JIS 16K,15MM,316L/GR/316 | 2 | 0 | 0 | ETA. - Procurement - Inventory. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300005852 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137519 | 3 | 1 | 30 | 30 | Supply for Order 100039045, Item 3 cannot be changed 90003375 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-06 | 3 | 31 | ON TIME | 4500001460 | After Turnround | 2024-04-03 | Need Purchasing | 00001375194541610507576000100039045 | 00001375194541610507576000100039045 | 000013751910507576000100039045 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-02-22 | 2024-05-09 | 2024-02-22 | 2024-05-09 | 2024-05-10 | MECH |  | 200079587 | 0020 | 4Y F21 NRV LGC 1 REPLACE WITH ROTABLE (200079587) | VALVE,E043301,NRV,GAS OUTLET (AB50.05MV043065) | CHANGE OUT VALVE WITH SPARE (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 10 | 5 | 10507776 | VALVE,CHK;150MM,CL1500,RTJ,SS,AXIAL FLOW | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006997 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  | NEW |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000113856 | 2 | 3 | 30 | 30 | Supply for Order 200079587, Item 2 cannot be changed 90002066 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 49 | 77 | ON TIME |  | On Time | 0 | SOH | 00001138564542110507776000200079587 | 00001138564542110507776000200079587 | 000011385610507776000200079587 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-09 | INLEC |  | 100033135 | 0010 | Replace AFT Crane Aviation Lights MOC (100033135) | LIGHT,NAV,AFT CRANE,BOOM,-1 (AB50.05LT612482A) | RA Replace AFT Crane Boom Lts & Ex Insp (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10508764 | LIGHT,WARNING,AVIATION;ORGA L85EXRAC32 | 4 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004723 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131667 | 1 | 3 | 30 | 30 | Supply for Order 100033135, Item 1 cannot be changed 90003352 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME | 4500001334 | After Turnround | 2024-03-28 | SOH | 00001316674542110508764000100033135 | 00001316674542110508764000100033135 | 000013166710508764000100033135 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-05-16 | 2024-04-18 | 2024-04-19 | CRANE |  | 100037641 | 0040 | MID Install secondary ret to nav lights (100037641) | CRANE,MIDSHIP PS (AB50.05X790001) | Install sec retention to nav lights alon (0030) | AB50 | 2024-05-31 |  |  | AB01 |  | 30 | 30 | 10509009 | ROPE,WIRE;316SS,7X7,1.6MMX500M,ROLL | 1 | 1 | 0 | UserCommentLink | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001605 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136165 | 1 | 3 | 30 | 30 | Supply for Order 100037641, Item 1 cannot be changed 90003263 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 42 | 2024-09-02 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-22 | -55 | -27 | Delayed |  | On Time | 0 | SOH | 00001361654540110509009000100037641 | 00001361654540110509009000100037641 | 000013616510509009000100037641 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-07 |  | 2024-05-07 | 2024-05-07 | INLEC |  | 100033784 | 0010 | Replace EM & Exit Light Batteries LER (6 (100033784) | LIGHT,EMERG EXIT MOD 13 INTERNAL (AB50.05LT400302R0113) | Replace 6x Em Batteries & Ex Inspection (0020) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10509062 | BATTERY,CHARGEABLE;CCH NOR000000516012 | 1 | 0 | 4 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132276 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-09 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001322764541910509062000100033784 | 00001322764541910509062000100033784 | 000013227610509062000100033784 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 |  | 2024-05-01 | 2024-05-03 | MECH |  | 200082368 | 0032 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200082368) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10509101 | ELEMENT,FLT;INDUFIL 87472167 | 1 | 1 | 6 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118281 | 6 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001182814541410509101000200082368 | 00001182814541410509101000200082368 | 000011828110509101000200082368 |  |  | 1
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-27 | 2024-05-05 | 2024-04-04 | 2024-05-04 | 2024-05-07 | REFURB |  | 100038184 | 0050 | E/R - Repl Spool Steam Cond CDR-28783 (100038184) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | replace 15-SW-3750718-EXA1X-P (0030) | AB50 | 2024-05-05 |  |  | AB01 |  | 30 | 30 | 10515037 | GASKET,FLG;40MM,1.5MM,JIS 5K,FF,CNAF | 3 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300007229 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136688 | 5 | 1 | 30 | 30 | Supply for Order 100038184, Item 5 cannot be changed 90003426 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-07 | 3 | 31 | ON TIME | 4500004421 | After Turnround | 2024-04-04 | Need Purchasing | 00001366884541710515037000100038184 | 00001366884541710515037000100038184 | 000013668810515037000100038184 | 0 | #N/A | 0
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-02 | MECH |  | 200083256 | 0012 | 6M CERTIFY NRV FROM STOCK CARCASS BLEED (200083256) | VALVE,POPPET CHECK, VENT W3M TEST (AB50.4BL4167) | CERTIFY VALVE 0.5 BARG (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10520559 | VALVE,CHK;POPPET,SWAG SSCHF85 | 11 | 15 | 7 | OK. - PDC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000120451 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-02 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001204514541410520559000200083256 | 00001204514541410520559000200083256 | 000012045110520559000200083256 |  |  | 1
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0210 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10527555 | VALVE,GLOBE;ARI STOBU 23.006R DN80 PN25 | 1 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 170 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 26 | 2 | 30 | 30 | Supply for Order 200090465, Item 26 cannot be changed 90002701 item 160 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110527555000200090465 | 00001287344539110527555000200090465 | 000012873410527555000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0200 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10527555 | VALVE,GLOBE;ARI STOBU 23.006R DN80 PN25 | 1 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 160 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 25 | 2 | 30 | 30 | Supply for Order 200090465, Item 25 cannot be changed 90002701 item 150 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110527555000200090465 | 00001287344539110527555000200090465 | 000012873410527555000200090465 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-03-15 | 2024-04-22 | 2024-04-25 | INSP |  | 200082341 | 0020 | 5Y INT INSP/CLASS SURVEY 03E753050 (200082341) | VE,ATMOSPHERIC CONDENSER (AB50.03E753050) | RE-INSTATE SPOOL/HEAD POST INSPECTION (0060) | AB50 | 2024-04-24 |  |  | AB01 |  | 10 | 5 | 10530706 | STUDBOLT,M20 X 140MM,CAD+PTFE,B7 | 32 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300003505 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014444 | N | Preparation (05) | In Preparation (Order) (0055) | 0000118169 | 2 | 4 | 30 | 30 | Supply for Order 200082341, Item 2 cannot be changed 90002199 item 10 already exists | 101000000029743 | 16 | FALSE | 101000000029652 |  |  | WorkPackLink | OKHA | 2024-03-30 | 0 | 0 | 2024-05-20 | 0 | 0 |  |  | 0 | 0 | 01-Road | 32 | 5-Completed |  | 20000716 | 0 | 0 | 0.14286 | 2024-03-27 | 12 | 40 | ON TIME |  | On Time | 0 | Need Purchasing | 00001181694540610530706000200082341 | 00001181694540610530706000200082341 | 000011816910530706000200082341 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-03-15 | 2024-04-22 | 2024-04-25 | INSP |  | 200082341 | 0020 | 5Y INT INSP/CLASS SURVEY 03E753050 (200082341) | VE,ATMOSPHERIC CONDENSER (AB50.03E753050) | RE-INSTATE SPOOL/HEAD POST INSPECTION (0060) | AB50 | 2024-04-24 |  |  | AB01 |  | 10 | 5 | 10530706 | STUDBOLT,M20 X 140MM,CAD+PTFE,B7 | 32 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300003505 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014444 | N | Preparation (05) | In Preparation (Order) (0055) | 0000118169 | 2 | 4 | 30 | 30 | Supply for Order 200082341, Item 2 cannot be changed 90002199 item 10 already exists | 101000000029743 | 16 | FALSE | 101000000029651 |  |  | WorkPackLink | OKHA | 2024-03-30 | 0 | 0 | 2024-05-20 | 0 | 0 |  |  | 0 | 0 | 01-Road | 32 | 5-Completed |  | 20000716 | 0 | 0 | 0.14286 | 2024-03-27 | 12 | 40 | ON TIME |  | On Time | 0 | Need Purchasing | 00001181694540610530706000200082341 | 00001181694540610530706000200082341 | 000011816910530706000200082341 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-19 | MECH |  | 100034052 | 0022 | Replace Gasket EGC2 LO Cooler TCV (100034052) | VALVE,E042231,TEMP CTRL (AB50.05TCV042804) | Isolate 05TCV042804 and drain oil (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10533202 | OIL,LUB;SHELL TURBO S4,GX,46,209L | 3 | 6 | 0 | OK. - PDC - PICK. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | DR |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132606 | 2 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-16 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001326064540010533202000100034052 | 00001326064540010533202000100034052 | 000013260610533202000100034052 |  |  | 1
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0042 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534107 | CLAMP;CAT 8T4984 | 4 | 4 | 0 | OK - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000093 | 190 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 23 | 3 | 30 | 30 | Supply for Order 100034084, Item 23 cannot be changed 90003188 item 190 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | Okha Stores |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001325684540110534107000100034084 | 00001325684540110534107000100034084 | 000013256810534107000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0102 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534326 | VALVE;CAT 1081478 | 2 | 2 | 0 | OK - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000093 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 8 | 3 | 30 | 30 | Supply for Order 100034084, Item 8 cannot be changed 90003188 item 40 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001325684540110534326000100034084 | 00001325684540110534326000100034084 | 000013256810534326000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0132 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534346 | O-RING;CAT 3P0655 | 4 | 4 | 0 | OK. OLC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000093 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 11 | 3 | 30 | 30 | Supply for Order 100034084, Item 11 cannot be changed 90003188 item 70 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001325684540110534346000100034084 | 00001325684540110534346000100034084 | 000013256810534346000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0142 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534347 | O-RING;CAT 5S9134 | 4 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000093 | 80 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 12 | 3 | 30 | 30 | Supply for Order 100034084, Item 12 cannot be changed 90003188 item 80 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001325684540110534347000100034084 | 00001325684540110534347000100034084 | 000013256810534347000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0082 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534372 | SLEEVE;CAT 2027958 | 2 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000093 | 100 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 14 | 3 | 30 | 30 | Supply for Order 100034084, Item 14 cannot be changed 90003188 item 100 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001325684540110534372000100034084 | 00001325684540110534372000100034084 | 000013256810534372000100034084 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-10 | MECH |  | 100033628 | 0010 | Repl Swivel HPU Bursting Disc & Bladder (100033628) | ACC,A098200,HYDR OIL BACK-UP (AB50.04V098000A) | Carry out isolations (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10534478 | DISC,RUPTURE;385BAR,G1/4"BSPP | 2 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004738 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132149 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-11-02 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | -12 | 16 | ON TIME | 4500000548 | During Turnaround | 2024-03-27 | Need Purchasing | 00001321494542110534478000100033628 | 00001321494542110534478000100033628 | 000013214910534478000100033628 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-20 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0222 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-04-06 |  |  | AB01 |  | 20 | 20 | 10534799 | HOSE ASY,GLYCOL,12.45MMX20M | 1 | 0 | 1 | 25.03.24: RISK - No PO. Awaiting overdue RFQ: 6000002621 for PR: 2000041153 | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000188 | 140 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 23 | 1 | 30 | 30 | Supply for Order 100034857, Item 23 cannot be changed 90006083 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 9 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | -20 | 8 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910534799000100034857 | 00001334014537910534799000100034857 | 000013340110534799000100034857 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-25 | MECH |  | 200089100 | 0032 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200089100) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10537213 | ELEMENT,FLT;INDUFIL 87488642 | 1 | 1 | 5 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000127318 | 4 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-08-11 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001273184540610537213000200089100 | 00001273184540610537213000200089100 | 000012731810537213000200089100 |  |  | 1
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-02-09 | 2024-02-07 | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0010 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | FILL TANK WIH NEW OIL (0040) | AB50 | 2024-02-12 | AB01 |  | AB02 |  | 30 | 30 | 10537786 | OIL,LUB;SHELL TURBO S4GX46,1000L | 2 | 1 | 0 | OK. | 0 | Materials handed over to w/ Maintenance | Stock at Base (SP12) | AB02 | 5300006180 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180004007 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 9 | 3 | 30 | 30 | Supply for Order 100037577, Item 9 cannot be changed 90000814 item 10 already exists | 102000000001126 | 1 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 3 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 3-In Transit |  | 1000000437 | 0 | 0 | 0.11111 | 2024-01-12 | -26 | 2 | ON TIME |  | On Time | 0 | Need Purchasing | 00001361614533110537786000100037577 | 00001361614533110537786000100037577 | 000013616110537786000100037577 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-02-09 | 2024-02-07 | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0010 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | FILL TANK WIH NEW OIL (0040) | AB50 | 2024-02-12 | AB01 |  | AB02 |  | 30 | 30 | 10537786 | OIL,LUB;SHELL TURBO S4GX46,1000L | 2 | 1 | 0 | OK. | 0 | Materials handed over to w/ Maintenance | Stock at Base (SP12) | AB02 | 5300006180 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180004007 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 9 | 3 | 30 | 30 | Supply for Order 100037577, Item 9 cannot be changed 90000814 item 10 already exists | 102000000001124 | 1 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 3 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 3-In Transit |  | 1000000437 | 0 | 0 | 0.11111 | 2024-01-12 | -26 | 2 | ON TIME |  | On Time | 0 | Need Purchasing | 00001361614533110537786000100037577 | 00001361614533110537786000100037577 | 000013616110537786000100037577 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-27 | 2024-05-05 | 2024-04-04 | 2024-05-04 | 2024-05-07 | REFURB |  | 100038184 | 0040 | E/R - Repl Spool Steam Cond CDR-28783 (100038184) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | replace 15-SW-3750718-EXA1X-P (0030) | AB50 | 2024-05-05 |  |  | AB01 |  | 30 | 30 | 10543114 | GASKET;SWCI,JIS 16K,15MM,C4430 | 2 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300007229 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136688 | 4 | 1 | 30 | 30 | Supply for Order 100038184, Item 4 cannot be changed 90003426 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-07 | 3 | 31 | ON TIME | 4500004421 | After Turnround | 2024-04-04 | Need Purchasing | 00001366884541710543114000100038184 | 00001366884541710543114000100038184 | 000013668810543114000100038184 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-05-16 | 2024-04-18 | 2024-04-19 | CRANE |  | 100037641 | 0060 | MID Install secondary ret to nav lights (100037641) | CRANE,MIDSHIP PS (AB50.05X790001) | Install sec retention to nav lights alon (0030) | AB50 | 2024-05-31 |  |  | AB01 |  | 30 | 30 | 10546632 | FERRULE;CRIMP,1.6MM,CU,NI PLTD | 100 | 100 | 0 | UserCommentLink | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001605 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136165 | 3 | 3 | 30 | 30 | Supply for Order 100037641, Item 3 cannot be changed 90003263 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 42 | 2024-09-02 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-22 | -55 | -27 | Delayed |  | On Time | 0 | SOH | 00001361654540110546632000100037641 | 00001361654540110546632000100037641 | 000013616510546632000100037641 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-06 | 2024-04-24 |  | 2024-04-24 | 2024-04-24 | INLEC |  | 100033657 | 0010 | CLASS Replace ODME solenoid - V12 (100033657) | PKG EQ,SKID ASSEMBLY (AB50.03A450500) | Isolate ODME Supply (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10547280 | SENSOR,FLOW;SAMPLE,0.2-10L/M,WARTSILA R+ | 1 | 0 | 0 | ETA. - R. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132189 | 1 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001321894540610547280000100033657 | 00001321894540610547280000100033657 | 000013218910547280000100033657 |  |  | 1
24OKCM16 |  |  | Released | 2023-12-30 | 2024-02-06 | 2024-04-24 |  | 2024-04-24 | 2024-04-24 | INLEC |  | 100033657 | 0020 | CLASS Replace ODME solenoid - V12 (100033657) | PKG EQ,SKID ASSEMBLY (AB50.03A450500) | Isolate ODME Supply (0010) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10547281 | CELL;MEASURE,50/60HZ,WARTSILA | 1 | 0 | 0 | ETA. - R. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132189 | 2 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001321894540610547281000100033657 | 00001321894540610547281000100033657 | 000013218910547281000100033657 |  |  | 1
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-20 | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0050 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10547649 | CABLE,DATA;CAT 6,4PR,CU,LSZH,GRY | 100 | 0 | 0 | OK. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004682 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | M |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 5 | 2 | 30 | 30 | Supply for Order 600001447, Item 5 cannot be changed 90000821 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 9 | 37 | ON TIME |  | On Time | 2024-02-14 | Need Purchasing | 00000843624537910547649000600001447 | #N/A | 000008436210547649000600001447 | 0 | #N/A | 0
24OKCO19 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 200086992 | 0030 | 5Y FW AUTO VENT VALVE INSPECTION (200086992) | VALVE,AUTO VENT TO DECK SCUPPERING (AB50.03SP452654) | FW AUTO VENT VALVE INSPECTION 03SP452654 (0010) | AB50 |  |  |  | AB01 |  | 255 | 99 | 10561611 | MAINT KIT;AIR ELIMINATOR,S.SARCO 0170380 | 2 | 0 | 2 | 27.03.24: OK - Onboard Okha inside Store Bin: 10-14-02-02A | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000125250 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | 00000106000000000044 |  |  | 0 | 0 | 2024-02-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001252504542110561611000200086992 | 00001252504542110561611000200086992 | 000012525010561611000200086992 |  |  | 1
24OKCO16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-29 |  | 2024-04-29 | 2024-04-29 | MECH |  | 200073134 | 0010 | 2M VRU AUTO DRAIN STRAINERS CLEAN (200073134) | FILT,STRAINER, VRU SUCTION DRAIN (AB50.03SP040033) | REPLACE STRAINERS AND TIGHTEN TO 100NM (0030) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10563505 | GASKET,CAP;STRAINER,SPIRAX 0957212 | 4 | 0 | 16 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000107503 | 1 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001075034541110563505000200073134 | 00001075034541110563505000200073134 | 000010750310563505000200073134 |  |  | 1
24OKCM19 | No Issue identified |  | Released | 2024-01-11 | 2024-02-02 | 2024-05-09 | 2024-03-13 | 2024-05-09 | 2024-07-06 | INLEC |  | 600002860 | 0020 | Paint OKHA Cables - UV Damaged (600002860) | SWBD,TOPSIDES 11KV SWITCHGEAR,DEF41003 (AB50.05SB400101) | LGA L3 Rope Access Paint / Permit holder (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10564774 | TAPE;SPLC,RBR,FIRE SECURITY FS17 | 100 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300005952 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000213591 | 2 | 3 | 30 | 30 | Supply for Order 600002860, Item 2 cannot be changed 90001689 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | 29 | 57 | ON TIME |  | After Turnround | 2024-04-08 | Need Purchasing | 00002135914542110564774000600002860 | 00002135914542110564774000600002860 | 000021359110564774000600002860 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0202 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10565086 | CLAMP,PIPE;16MM,SS,CAT 8T4983 | 8 | 4 | 4 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 180 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 22 | 3 | 30 | 30 | Supply for Order 100034084, Item 22 cannot be changed 90003188 item 180 already exists | 101000000029743 | 4 | FALSE | 101000000029590 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110565086000100034084 | 00001325684540110565086000100034084 | 000013256810565086000100034084 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2024-01-11 | 2024-02-02 | 2024-05-09 | 2024-03-13 | 2024-05-09 | 2024-07-06 | INLEC |  | 600002860 | 0030 | Paint OKHA Cables - UV Damaged (600002860) | SWBD,TOPSIDES 11KV SWITCHGEAR,DEF41003 (AB50.05SB400101) | LGA L3 Rope Access Paint / Permit holder (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10565211 | PAINT,SPRAY;FR COATING | 6 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300005952 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000213591 | 3 | 3 | 30 | 30 | Supply for Order 600002860, Item 3 cannot be changed 90001689 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | 29 | 57 | ON TIME |  | After Turnround | 2024-04-08 | Need Purchasing | 00002135914542110565211000600002860 | 00002135914542110565211000600002860 | 000021359110565211000600002860 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0182 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10568264 | O-RING;SEAL,CAT 6K6307 | 4 | 4 | 0 | OK - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000093 | 130 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 17 | 3 | 30 | 30 | Supply for Order 100034084, Item 17 cannot be changed 90003188 item 130 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001325684540110568264000100034084 | 00001325684540110568264000100034084 | 000013256810568264000100034084 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0050 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10569059 | VALVE,GATE;200MM,PN25,RF,ST | 1 | 2 | 2 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 11 | 2 | 30 | 30 | Supply for Order 200091461, Item 11 cannot be changed 90002702 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | PK_STAGING |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510569059000200091461 | 00001296914539510569059000200091461 | 000012969110569059000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0052 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10569059 | VALVE,GATE;200MM,PN25,RF,ST | 1 | 2 | 2 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 170 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 43 | 2 | 30 | 30 | Supply for Order 200091461, Item 43 cannot be changed 90002702 item 170 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510569059000200091461 | 00001296914539510569059000200091461 | 000012969110569059000200091461 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-10 | MECH |  | 100036218 | 0092 | GT1 Repair leaks main tank & return line (100036218) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Confirm isolations of GT1 (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10569848 | GLOVES,CHEM;L,355MM,BUTYL,ANSELL | 2 | 2 | 0 | OK. - OLC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001022 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134750 | 6 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2023-12-29 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001347504542110569848000100036218 | 00001347504542110569848000100036218 | 000013475010569848000100036218 | 0 | #N/A | 0
24OKCM16 |  |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-25 | MECH |  | 200089100 | 0040 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200089100) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 |  |  |  | AB01 |  | 10 | 10 | 10572710 | O-RING;249.3X5.7,FLUOROCARB 90 | 2 | 2 | 2 | OK. - OLC. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000127318 | 3 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-08-11 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001273184540610572710000200089100 | 00001273184540610572710000200089100 | 000012731810572710000200089100 |  |  | 1
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-20 | 2024-03-28 | 2024-03-28 | MECH |  | 200085162 | 0010 | 2Y F21 BIOC INJ HP SEP NRV TEST/REPL (200085162) | VALVE,CHECK BIOCIDE INJ TO HP SEP (AB50.04MV020049) | CHANGE OUT VALVE (0020) | AB50 | 2024-03-28 |  |  | AB01 |  | 10 | 5 | 10574508 | VALVE,CHK;LIFT,DN20,316SS | 1 | 2 | 1 | 25.03.24: Check Valve for this job is not on Okha. Still in PDC Stock. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003501 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000123412 | 1 | 3 | 30 | 30 | Supply for Order 200085162, Item 1 cannot be changed 90001660 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-13 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-02-29 | 9 | 37 | ON TIME |  | On Time | 0 | SOH | 00001234124537910574508000200085162 | 00001234124537910574508000200085162 | 000012341210574508000200085162 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0022 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10575223 | VALVE,CHK;25MM,JIS16K,FF,BZE | 1 | 4 | 0 | OK - PDC Pick. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 270 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 45 | 2 | 30 | 30 | Supply for Order 200090465, Item 45 cannot be changed 90002701 item 260 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110575223000200090465 | 00001287344539110575223000200090465 | 000012873410575223000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0012 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10575223 | VALVE,CHK;25MM,JIS16K,FF,BZE | 1 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 260 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 44 | 2 | 30 | 30 | Supply for Order 200090465, Item 44 cannot be changed 90002701 item 250 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110575223000200090465 | 00001287344539110575223000200090465 | 000012873410575223000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0012 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10575223 | VALVE,CHK;25MM,JIS16K,FF,BZE | 1 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 180 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 44 | 2 | 30 | 30 | Supply for Order 200091461, Item 44 cannot be changed 90002702 item 180 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510575223000200091461 | 00001296914539510575223000200091461 | 000012969110575223000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0022 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10575223 | VALVE,CHK;25MM,JIS16K,FF,BZE | 1 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 190 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 45 | 2 | 30 | 30 | Supply for Order 200091461, Item 45 cannot be changed 90002702 item 190 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510575223000200091461 | 00001296914539510575223000200091461 | 000012969110575223000200091461 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0092 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 | 2024-05-09 |  |  | AB01 |  | 10 | 10 | 10576543 | INHIBITOR,CORROSION;COR BON D5010NS,12OZ | 1 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003081 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 9 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 2023-11-30 | Need Purchasing | 00000963414542110576543000200061999 | #N/A | 000009634110576543000200061999 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-09 | 2024-05-01 | 2024-04-23 | 2024-05-01 | 2024-05-02 | INLEC |  | 100032477 | 0020 | CLASS 4PCOT Install New Earth Bosses (100032477) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | 4PCOT Install New Earth Bosses & Cable (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 10 | 5 | 10583038 | BIT,DRILL;STEPPED,TSBT5.574S,HILTI | 3 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006318 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131021 | 2 | 3 | 30 | 30 | Supply for Order 100032477, Item 2 cannot be changed 90003387 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 8 | 2026-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-03 | -20 | 8 | ON TIME | 4500002479 | On Time | 2024-02-29 | Need Purchasing | 00001310214541310583038000100032477 | 00001310214541310583038000100032477 | 000013102110583038000100032477 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-09 | 2024-05-01 | 2024-04-23 | 2024-05-01 | 2024-05-02 | INLEC |  | 100032477 | 0010 | CLASS 4PCOT Install New Earth Bosses (100032477) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | 4PCOT Install New Earth Bosses & Cable (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 10 | 5 | 10583039 | STUD;THD,ELEC,M10,SDSS,HILTI | 100 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006318 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131021 | 1 | 3 | 30 | 30 | Supply for Order 100032477, Item 1 cannot be changed 90003387 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 8 | 2026-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-03 | -20 | 8 | ON TIME | 4500003280 | After Turnround | 2024-05-19 | Need Purchasing | 00001310214541310583039000100032477 | 00001310214541310583039000100032477 | 000013102110583039000100032477 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0082 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10584159 | WASHER,LK;SPLIT,0.5",SOLAR 964686C1 | 3 | 3 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002004 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | PAC |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 5 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT1 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001380454542110584159000100039544 | 00001380454542110584159000100039544 | 000013804510584159000100039544 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0042 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10584918 | VALVE,ANG;25A,JIS 16K,FLG,F7304 | 1 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 290 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 47 | 2 | 30 | 30 | Supply for Order 200090465, Item 47 cannot be changed 90002701 item 280 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110584918000200090465 | 00001287344539110584918000200090465 | 000012873410584918000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0032 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10584918 | VALVE,ANG;25A,JIS 16K,FLG,F7304 | 1 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 280 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 46 | 2 | 30 | 30 | Supply for Order 200090465, Item 46 cannot be changed 90002701 item 270 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110584918000200090465 | 00001287344539110584918000200090465 | 000012873410584918000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0042 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10584918 | VALVE,ANG;25A,JIS 16K,FLG,F7304 | 1 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 210 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 47 | 2 | 30 | 30 | Supply for Order 200091461, Item 47 cannot be changed 90002702 item 210 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510584918000200091461 | 00001296914539510584918000200091461 | 000012969110584918000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0032 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10584918 | VALVE,ANG;25A,JIS 16K,FLG,F7304 | 1 | 4 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004393 | 200 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 46 | 2 | 30 | 30 | Supply for Order 200091461, Item 46 cannot be changed 90002702 item 200 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510584918000200091461 | 00001296914539510584918000200091461 | 000012969110584918000200091461 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-21 | 2024-04-03 | 2024-04-21 | 2024-04-22 | REFURB |  | 100037863 | 0030 | OR - HSE10 Install Shelves T1054 (100037863) | PKG EQ,PRODUCTION STORE (AB50.05A800021) | install fabricated shelves (0020) | AB50 | 2024-04-21 |  |  | AB01 |  | 30 | 30 | 10586379 | BOLT ASY,HEX;M16X50MM,GDE 8.8,HDG,N+2W | 24 | 4 | 0 | OK - PDC. | 0 | Material In-Transit on-04-Sea | Stock at Base (SP12) | AB01 | 5300001647 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013683 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136344 | 3 | 1 | 30 | 30 | Supply for Order 100037863, Item 3 cannot be changed 90003266 item 30 already exists | 101000000028846 | 20 | FALSE | 101000000027603 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 24 | 1-Not Started |  | 1000000888 | 0 | 0 | 0.14286 | 2024-03-24 | -10 | 18 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363444540310586379000100037863 | 00001363444540310586379000100037863 | 000013634410586379000100037863 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-03 | 2024-04-09 | 2024-03-30 | 2024-04-08 | REFURB |  | 100040991 | 0070 | RA - HSE10 Install Bracket & Cable Tray (100040991) | TURRET,ELECTRICAL SWIVEL (AB50.04V098103) | Install bracket & cable tray (0030) | AB50 | 2024-04-24 |  |  | AB01 |  | 20 | 20 | 10586381 | BOLT ASY,HEX;M16X60MM,GDE 8.8,HDG,N+2W | 8 | 8 | 0 | ETA. - Procurement. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000284 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000139525 | 1 | 3 | 30 | 30 | Supply for Order 100040991, Item 1 cannot be changed 90003199 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 21 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 4 |  |  |  | 0 | 0 | 0.33333 | 2024-03-06 | -34 | -6 | Delayed |  | On Time | 0 | SOH | 00001395254538510586381000100040991 | 00001395254538510586381000100040991 | 000013952510586381000100040991 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-02-22 | 2024-05-09 | 2024-03-07 | 2024-05-09 | 2024-05-10 | MECH |  | 200079587 | 0040 | 4Y F21 NRV LGC 1 REPLACE WITH ROTABLE (200079587) | VALVE,E043301,NRV,GAS OUTLET (AB50.05MV043065) | CHANGE OUT VALVE WITH SPARE (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 10 | 5 | 10589262 | VALVE,CHK;DN150,CL1500,RTJ,LTCS,L15C8C | 1 | 0 | 0 | OK . - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300006997 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000113856 | 4 | 3 | 30 | 30 | Supply for Order 200079587, Item 4 cannot be changed 90004312 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 35 | 63 | ON TIME |  | After Turnround | 2024-08-12 | Need Purchasing | 00001138564542110589262000200079587 | 00001138564542110589262000200079587 | 000011385610589262000200079587 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0062 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10594202 | HOSE;CAT 2647811 | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000093 | 140 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 18 | 3 | 30 | 30 | Supply for Order 100034084, Item 18 cannot be changed 90003188 item 140 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001325684540110594202000100034084 | 00001325684540110594202000100034084 | 000013256810594202000100034084 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0072 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10601253 | NUT,HEX;0.5",13UNC,8M,SOLAR 964684C1 | 3 | 3 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002004 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | PAC |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 6 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001380454542110601253000100039544 | 00001380454542110601253000100039544 | 000013804510601253000100039544 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0012 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10601256 | TAPE,DROP WARP;50FT,SOLAR 1102786 | 2 | 2 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002004 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 9 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT1 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001380454542110601256000100039544 | 00001380454542110601256000100039544 | 000013804510601256000100039544 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2024-01-11 | 2024-02-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-07-06 | INLEC |  | 600002860 | 0050 | Paint OKHA Cables - UV Damaged (600002860) | SWBD,TOPSIDES 11KV SWITCHGEAR,DEF41003 (AB50.05SB400101) | LGA L3 Rope Access Paint / Permit holder (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10601282 | PAINT,SPRAY;BLUE,FR COATING | 1 | 0 | 0 | ETA. - Y. | 0 | STO raised (through orchestration) | Stock at Base (SP12) | AB01 | 5300005952 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000213591 | 5 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | -12 | 16 | ON TIME |  | After Turnround | 2024-05-14 | Need Purchasing | 00002135914542110601282000600002860 | 00002135914542110601282000600002860 | 000021359110601282000600002860 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-05-16 | 2024-04-18 | 2024-04-19 | CRANE |  | 100037641 | 0050 | MID Install secondary ret to nav lights (100037641) | CRANE,MIDSHIP PS (AB50.05X790001) | Install sec retention to nav lights alon (0030) | AB50 | 2024-05-31 |  |  | AB01 |  | 30 | 30 | 10602811 | TOOL,CRIMP;ALLOY ST,600MM | 1 | 1 | 0 | UserCommentLink | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001605 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136165 | 2 | 3 | 30 | 30 | Supply for Order 100037641, Item 2 cannot be changed 90003263 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 42 | 2024-09-02 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-22 | -55 | -27 | Delayed |  | On Time | 0 | SOH | 00001361654540110602811000100037641 | 00001361654540110602811000100037641 | 000013616510602811000100037641 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0042 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10605184 | BELLOWS,ASSY;EXH,SOLAR 2002217300 | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002004 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 8 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT1 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001380454542110605184000100039544 | 00001380454542110605184000100039544 | 000013804510605184000100039544 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0002 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10605188 | WASHER,FLAT;0.5",SOLAR 1010476 | 60 | 60 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002004 | 80 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 11 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT1 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001380454542110605188000100039544 | 00001380454542110605188000100039544 | 000013804510605188000100039544 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0052 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10605323 | BOLT,HEX HD;0.5"X3.00",SOLAR 1113905 | 66 | 66 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002004 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 10 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT1 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001380454542110605323000100039544 | 00001380454542110605323000100039544 | 000013804510605323000100039544 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0102 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10605423 | SET,BLANKET;EXH BELLOWS,SOLAR 2002220100 | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300002004 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 7 | 4 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT1 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001380454542110605423000100039544 | 00001380454542110605423000100039544 | 000013804510605423000100039544 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-05-15 | 2024-05-09 | 2024-05-13 | CRANE |  | 100038739 | 0012 | Replace HPU level sight glass (100038739) | GAUGE,X790001-AMD2023, LEVEL (AB50.05X790001-YMD8790) | Replace hyd tank level sight glass - aft (0010) | AB50 | 2024-05-30 |  |  | AB01 |  | 20 | 20 | 10605994 | GAUGE,MEASURE;LIQ LEV,APPLETON YMD8790 | 3 | 3 | 0 | UserCommentLink | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001746 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137260 | 4 | 4 | 30 | 30 | Supply for Order 100038739, Item 4 cannot be changed 90003273 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 21 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | -34 | -6 | Delayed |  | On Time | 0 | SOH | 00001372604542110605994000100038739 | 00001372604542110605994000100038739 | 000013726010605994000100038739 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-03-28 | 2024-03-30 | MECH |  | 100037795 | 0032 | CLASS Repl 4SWBT Draft Gauge Vlv (100037795) | VALVE,CP850370B,WBT 4 SB,DRAFT GAUGE (AB50.03SP752429) | Empty 4S WBT (0010) | AB50 | 2024-03-28 |  |  | AB01 |  | 10 | 5 | 10606651 | BOLT ASY;HEX,M16X65MM,CAD PLTD,ALLOY ST | 16 | 16 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300001629 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000136296 | 3 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2026-05-27 | 0 | 0 |  |  | 0 | 0 |  | 32 |  |  |  | 0 | 0 | 0.33333 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001362964537910606651000100037795 | 00001362964537910606651000100037795 | 000013629610606651000100037795 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0130 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10606781 | SEAL,CONN,HOSE;KSB 41273 | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000188 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 9 | 1 | 30 | 30 | Supply for Order 100034857, Item 9 cannot be changed 90001632 item 60 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | 2100354089 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | SOH | 00001334014537910606781000100034857 | 00001334014537910606781000100034857 | 000013340110606781000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0090 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10606782 | FLANGE,CONN,HOSE;KSB 72273 | 1 | 1 | 1 | OK. - OLC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000188 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 5 | 1 | 30 | 30 | Supply for Order 100034857, Item 5 cannot be changed 90001632 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | PK_STAGING |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | SOH | 00001334014537910606782000100034857 | 00001334014537910606782000100034857 | 000013340110606782000100034857 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0592 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10607195 | BOLT,STUD;M20X120MM,2.5P,CS,PLN FINISH | 24 | 24 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300004055 | 200 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 38 | 2 | 30 | 30 | Supply for Order 200090465, Item 38 cannot be changed 90002701 item 190 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110607195000200090465 | 00001287344539110607195000200090465 | 000012873410607195000200090465 | 0 | #N/A | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-02-20 | 2024-05-09 | 2024-05-10 | MECH |  | 200081677 | 0010 | 10Y TURRET UTIL WINCH INSP/MRRI (200081677) | WINCH,UTILITY LINEAR WINCH (AB50.04W790030) | WINCH INSP/MRRI (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 255 | 99 | 10607433 | BRAKE ASY;WINCH,PCT B82262 | 1 | 0 | 0 | ETA. - Y. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003273 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000116738 | 1 | 3 | 30 | 30 | Supply for Order 200081677, Item 1 cannot be changed 90001657 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-01-01 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001167384542110607433000200081677 | 00001167384542110607433000200081677 | 000011673810607433000200081677 | 0 | #N/A | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-02-20 | 2024-05-09 | 2024-05-11 | MECH |  | 200081679 | 0010 | 4Y TURRET UTIL WINCH WIRE ROPE REPL (200081679) | WINCH,UTILITY LINEAR WINCH (AB50.04W790030) | REPLACE WIRE ROPE (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 255 | 99 | 10608381 | ROPE,WIRE;WINCH,22MM,50M,ST,GALV | 1 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003276 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000116783 | 1 | 3 | 30 | 30 | Supply for Order 200081679, Item 1 cannot be changed 90001658 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-01-01 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001167834542110608381000200081679 | 00001167834542110608381000200081679 | 000011678310608381000200081679 | 0 | #N/A | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-02-20 | 2024-05-09 | 2024-05-11 | MECH |  | 200081722 | 0010 | 4Y TURRET TRLLY WINCH WIRE ROPE REPL (200081722) | WINCH,RTM BEAM TROLLEY (AB50.04X790010) | REPLACE WIRE ROPE (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 255 | 99 | 10608381 | ROPE,WIRE;WINCH,22MM,50M,ST,GALV | 1 | 0 | 0 | ETA. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300003297 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000116792 | 1 | 3 | 30 | 30 | Supply for Order 200081722, Item 1 cannot be changed 90001659 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-01-01 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001167924542110608381000200081722 | 00001167924542110608381000200081722 | 000011679210608381000200081722 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-09 | MECH |  | 100035706 | 0010 | Install GT1 Shield Blank Ex-Bellows MOC (100035706) | TURB,GT400001 TURBINE (AB50.05GT400001) | Install GT1 Shield blanket Ex-Bellows (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10608970 | SET,BLANKET;EXH BELLOWS,SOLAR 1091568100 | 1 | 1 | 0 | OK. - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000739 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134210 | 1 | 3 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | OKHAEC |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001342104542110608970000100035706 | 00001342104542110608970000100035706 | 000013421010608970000100035706 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0010 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10613168 | INJECTOR,FUEL;CAT 10R7231 | 12 | 5 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 1 | 3 | 30 | 30 | Supply for Order 100034084, Item 1 cannot be changed 90003188 item 10 already exists | 101000000029743 | 7 | FALSE | 101000000029624 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 7 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110613168000100034084 | 00001325684540110613168000100034084 | 000013256810613168000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0032 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10613351 | BOLT;CAT 8S9191 | 12 | 12 | 0 | OK - PDC. | 0 | Material avail; awaiting work-packing @AB01 | Stock at Base (SP12) | AB01 | 5300000093 | 150 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 19 | 3 | 30 | 30 | Supply for Order 100034084, Item 19 cannot be changed 90003188 item 150 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001325684540110613351000100034084 | 00001325684540110613351000100034084 | 000013256810613351000100034084 | 0 | #N/A | 0
24OKCM19 | Supply too early, consider delaying |  | Released | 2023-12-30 | 2024-01-09 | 2024-05-09 | 2024-02-15 | 2024-05-09 | 2024-05-10 | MECH |  | 100032134 | 0010 | FP8 Repl LGC1 Duplex Studs MOC-117600 (100032134) | COMPR,A043300,GAS COMPRESSOR (AB50.05K043300) | FP8 Repl LGC1 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-01 |  |  | AB01 | 2024-03-09 | 20 | 20 | 70000044 | STUDBOLT 1/2"-13UNC x 150mm S32760-3 | 56 | 0 | 0 | ETA. | 50 | Material In-Transit on-04-Sea | Directs (Inventory) (SP14) | AB01 | 5300004685 | 10 | 50 | X | 1000000410 | 1 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000045177_2024_0001/5000045168_2024_0001 | 100 | 56 | EA | 2024-02-28 |  | 180012224/ | 180013741 | N | Preparation (05) | In Preparation (Order) (0055) | 0000130646 | 1 | 1 |  |  | Supply for Order 100032134, Item 1 cannot be changed 90001675 item 10 already exists | 101000000028846 | 14 | FALSE | 101000000028736 | 101000000028732 |  | WorkPackLink |  |  | 23 | 0 | 2024-11-30 | 0 | 0 | 2024-03-09 |  | 0 | 0 | 04-Sea | 168 | 1-Not Started |  | 1000000888 | 0 | 0 | 0.25 | 2024-04-11 | 56 | 84 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | Need Purchasing | 00001306464542170000044000100032134 | 00001306464542170000044000100032134 | 000013064670000044000100032134 | 0 | #N/A | 0
24OKCM19 | Supply too early, consider delaying |  | Released | 2023-12-30 | 2024-01-09 | 2024-05-09 | 2024-02-15 | 2024-05-09 | 2024-05-10 | MECH |  | 100032134 | 0010 | FP8 Repl LGC1 Duplex Studs MOC-117600 (100032134) | COMPR,A043300,GAS COMPRESSOR (AB50.05K043300) | FP8 Repl LGC1 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-01 |  |  | AB01 | 2024-03-09 | 20 | 20 | 70000044 | STUDBOLT 1/2"-13UNC x 150mm S32760-3 | 56 | 0 | 0 | ETA. | 50 | Material In-Transit on-04-Sea | Directs (Inventory) (SP14) | AB01 | 5300004685 | 10 | 50 | X | 1000000410 | 1 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000045177_2024_0001/5000045168_2024_0001 | 100 | 56 | EA | 2024-02-28 |  | 180012224/ | 180013741 | N | Preparation (05) | In Preparation (Order) (0055) | 0000130646 | 1 | 1 |  |  | Supply for Order 100032134, Item 1 cannot be changed 90001675 item 10 already exists | 101000000028846 | 42 | FALSE | 101000000028736 | 101000000028735 |  | WorkPackLink |  |  | 23 | 0 | 2024-11-30 | 0 | 0 | 2024-03-09 |  | 0 | 0 | 04-Sea | 168 | 1-Not Started |  | 1000000888 | 0 | 0 | 0.25 | 2024-04-11 | 56 | 84 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | Need Purchasing | 00001306464542170000044000100032134 | 00001306464542170000044000100032134 | 000013064670000044000100032134 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-09 | 2024-04-18 | 2024-02-12 | 2024-04-18 | 2024-04-20 | MECH |  | 100032131 | 0020 | FP8 Repl FGC Duplex Studs MOC-117600 (100032131) | COMPR,K041100,1ST STG (AB50.05K041101) | FP8 Repl FGC Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-10 |  |  | AB01 | 2024-03-12 | 20 | 20 | 70000047 | STUDBOLT 5/8"-11UNC x 150mm S32760-S | 116 | 0 | 0 | ETA - 50 Day - 28 Feb - Tristar - Procurement. | 50 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004683 | 20 | 50 | X | 1000000338 | 4 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000045510_2024_0001/5000045505_2024_0001/5000045394_2024_0001/5000045386_2024_0001/5000045316_2024_0001/5000045221_2024_0001 | 20 | 116 | EA | 2024-02-28 |  | 180012224/ |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130643 | 4 | 1 |  |  | Supply for Order 100032131, Item 4 cannot be changed 90001672 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 29 | 0 | 2024-11-30 | 0 | 0 | 2024-03-12 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-21 | 38 | 66 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | Need Purchasing | 00001306434540070000047000100032131 | 00001306434540070000047000100032131 | 000013064370000047000100032131 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-09 | 2024-04-18 | 2024-02-12 | 2024-04-18 | 2024-04-19 | MECH |  | 100032133 | 0020 | FP8 Repl EGC2 Duplex Studs MOC-117600 (100032133) | COMPR,K042210,2ND STG (AB50.05K042212) | FP8 Repl EGC2 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-10 |  |  | AB01 | 2024-03-12 | 20 | 20 | 70000047 | STUDBOLT 5/8"-11UNC x 150mm S32760-S | 4 | 0 | 0 | ETA. | 50 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004684 | 20 | 50 | X | 1000000339 | 3 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000045574_2024_0001 | 60 | 4 | EA | 2024-02-28 |  | 180012224/ |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130645 | 3 | 1 |  |  | Supply for Order 100032133, Item 3 cannot be changed 90001674 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 29 | 0 | 2024-11-30 | 0 | 0 | 2024-03-12 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-21 | 38 | 66 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | Need Purchasing | 00001306454540070000047000100032133 | 00001306454540070000047000100032133 | 000013064570000047000100032133 | 0 | #N/A | 0
24OKCM19 | Supply too early, consider delaying |  | Released | 2023-12-30 | 2024-01-09 | 2024-05-09 | 2024-02-12 | 2024-05-09 | 2024-05-10 | MECH |  | 100032134 | 0020 | FP8 Repl LGC1 Duplex Studs MOC-117600 (100032134) | COMPR,A043300,GAS COMPRESSOR (AB50.05K043300) | FP8 Repl LGC1 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-10 |  |  | AB01 | 2024-03-12 | 20 | 20 | 70000047 | STUDBOLT 5/8"-11UNC x 150mm S32760-S | 8 | 0 | 0 | ETA. | 50 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004685 | 20 | 50 | X | 1000000410 | 2 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000045252_2024_0001 | 110 | 8 | EA | 2024-02-28 |  | 180012224/ |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130646 | 2 | 1 |  |  | Supply for Order 100032134, Item 2 cannot be changed 90001676 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 29 | 0 | 2024-11-30 | 0 | 0 | 2024-03-12 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 59 | 87 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | Need Purchasing | 00001306464542170000047000100032134 | 00001306464542170000047000100032134 | 000013064670000047000100032134 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-09 | 2024-04-18 | 2024-02-12 | 2024-04-18 | 2024-04-20 | MECH |  | 100032131 | 0030 | FP8 Repl FGC Duplex Studs MOC-117600 (100032131) | COMPR,K041100,1ST STG (AB50.05K041101) | FP8 Repl FGC Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-10 |  |  | AB01 | 2024-03-12 | 20 | 20 | 70000048 | STUDBOLT 3/4"-10UNC x 150mm S32760-S | 4 | 28 | 0 | OK. - PDC. | 50 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004683 | 30 | 50 | X | 1000000338 | 6 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000010483_2024_0001 | 30 | 4 | EA | 2024-02-28 |  | /180001509 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130643 | 6 | 1 |  |  | Supply for Order 100032131, Item 6 cannot be changed 90001672 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 29 | 0 | 2024-11-30 | 0 | 0 | 2024-03-12 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-21 | 38 | 66 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | SOH | 00001306434540070000048000100032131 | 00001306434540070000048000100032131 | 000013064370000048000100032131 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-09 | 2024-04-18 | 2024-02-12 | 2024-04-18 | 2024-04-19 | MECH |  | 100032133 | 0030 | FP8 Repl EGC2 Duplex Studs MOC-117600 (100032133) | COMPR,K042210,2ND STG (AB50.05K042212) | FP8 Repl EGC2 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-10 |  |  | AB01 | 2024-03-12 | 20 | 20 | 70000048 | STUDBOLT 3/4"-10UNC x 150mm S32760-S | 16 | 28 | 0 | ETA. | 50 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004684 | 30 | 50 | X | 1000000339 | 4 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000010484_2024_0001 | 70 | 16 | EA | 2024-02-28 |  | /180001509 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130645 | 4 | 1 |  |  | Supply for Order 100032133, Item 4 cannot be changed 90001674 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 29 | 0 | 2024-11-30 | 0 | 0 | 2024-03-12 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-21 | 38 | 66 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | SOH | 00001306454540070000048000100032133 | 00001306454540070000048000100032133 | 000013064570000048000100032133 | 0 | #N/A | 0
24OKCM19 | Supply too early, consider delaying |  | Released | 2023-12-30 | 2024-01-09 | 2024-05-09 | 2024-02-12 | 2024-05-09 | 2024-05-10 | MECH |  | 100032134 | 0030 | FP8 Repl LGC1 Duplex Studs MOC-117600 (100032134) | COMPR,A043300,GAS COMPRESSOR (AB50.05K043300) | FP8 Repl LGC1 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-10 |  |  | AB01 | 2024-03-12 | 20 | 20 | 70000048 | STUDBOLT 3/4"-10UNC x 150mm S32760-S | 8 | 28 | 0 | ETA. | 50 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004685 | 30 | 50 | X | 1000000410 | 3 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000010428_2024_0001 | 120 | 8 | EA | 2024-02-28 |  | /180001509 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130646 | 3 | 1 |  |  | Supply for Order 100032134, Item 3 cannot be changed 90001676 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 29 | 0 | 2024-11-30 | 0 | 0 | 2024-03-12 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 59 | 87 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | SOH | 00001306464542170000048000100032134 | 00001306464542170000048000100032134 | 000013064670000048000100032134 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-09 | 2024-04-18 | 2024-02-12 | 2024-04-18 | 2024-04-19 | MECH |  | 100032133 | 0040 | FP8 Repl EGC2 Duplex Studs MOC-117600 (100032133) | COMPR,K042210,2ND STG (AB50.05K042212) | FP8 Repl EGC2 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-10 |  |  | AB01 | 2024-03-12 | 20 | 20 | 70000049 | STUDBOLT 7/8"-9UNC x 150mm S32760-S | 12 | 32 | 0 | ETA. | 50 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004684 | 40 | 50 | X | 1000000339 | 6 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000010485_2024_0001 | 80 | 12 | EA | 2024-02-28 |  | /180001509 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130645 | 6 | 1 |  |  | Supply for Order 100032133, Item 6 cannot be changed 90001674 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 29 | 0 | 2024-11-30 | 0 | 0 | 2024-03-12 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-21 | 38 | 66 | ON TIME |  | On Time | 0 | SOH | 00001306454540070000049000100032133 | 00001306454540070000049000100032133 | 000013064570000049000100032133 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-09 | MECH |  | 100033231 | 0010 | Replace Hinge & Lock Vlv Deck Box #2 (100033231) | ENCL,SOLENOID VALVE BOX,DECK BOX NO 2 (AB50.03CP090012) | Replace Hinge & Lock Vlv Deck Box #2 (0010) | AB50 | 2024-04-21 |  |  | AB01 | 2024-04-21 | 20 | 20 | 70000094 | KNOB; 316 grade SS Quarter Turn Wing | 10 | 10 | 0 | OK. - PDC. | 26 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004730 | 10 | 26 | X | 1000000406 | 2 | 2024-03-15 | 2024-04-18 | TRINKOR PTY LTD (30001954) | 4500000625 | 5000012122_2024_0001 | 10 | 10 | EA | 2024-02-20 |  | /180002409 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131763 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 | 2024-04-21 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001317634542170000094000100033231 | 00001317634542170000094000100033231 | 000013176370000094000100033231 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-09 | MECH |  | 100033231 | 0020 | Replace Hinge & Lock Vlv Deck Box #2 (100033231) | ENCL,SOLENOID VALVE BOX,DECK BOX NO 2 (AB50.03CP090012) | Replace Hinge & Lock Vlv Deck Box #2 (0010) | AB50 | 2024-04-21 |  |  | AB01 | 2024-04-21 | 20 | 20 | 70000096 | HINGE; 100 x 75 x 2.5mm 316 Marine Grade | 38 | 38 | 0 | OK. - PDC. | 26 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004730 | 20 | 26 | X | 1000000406 | 4 | 2024-03-15 | 2024-04-18 | TRINKOR PTY LTD (30001954) | 4500000625 | 5000012142_2024_0001 | 20 | 38 | EA | 2024-02-20 |  | /180002409 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131763 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 | 2024-04-21 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001317634542170000096000100033231 | 00001317634542170000096000100033231 | 000013176370000096000100033231 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-09 | 2024-04-18 | 2024-02-12 | 2024-04-18 | 2024-04-19 | MECH |  | 100032133 | 0050 | FP8 Repl EGC2 Duplex Studs MOC-117600 (100032133) | COMPR,K042210,2ND STG (AB50.05K042212) | FP8 Repl EGC2 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-10 |  |  | AB01 | 2024-03-12 | 20 | 20 | 70000100 | STUDBOLT 1"-8UN x 150mm S32760-S | 28 | 0 | 0 | ETA. | 50 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004684 | 50 | 50 | X | 1000000339 | 8 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000045485_2024_0001/5000045167_2024_0001 | 90 | 28 | EA | 2024-02-28 |  | 180012224/ |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130645 | 8 | 1 |  |  | Supply for Order 100032133, Item 8 cannot be changed 90001674 item 40 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 29 | 0 | 2024-11-30 | 0 | 0 | 2024-03-12 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-21 | 38 | 66 | ON TIME | 4500004322 | After Turnround | 2024-04-15 | Need Purchasing | 00001306454540070000100000100032133 | 00001306454540070000100000100032133 | 000013064570000100000100032133 | 0 | #N/A | 0
24OKCM16 | Supply too early, consider delaying |  | Released | 2023-12-30 | 2024-02-19 | 2024-04-24 | 2024-04-03 | 2024-04-24 | 2024-04-26 | MECH |  | 100032076 | 0020 | Invstigate EDG1 Cooling System (100032076) | GEN,G400301,GENERATOR (AB50.03G400301) | Investigate EDG1 Cooling System/Flush (0005) | AB50 | 2024-03-30 |  |  | AB01 | 2024-03-30 | 20 | 20 | 70000589 | Cooling system flush | 1 | 0 | 0 | ETA - 14 Day Local. | 14 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006842 | 20 | 14 | X | 1000002945 | 6 | 2024-03-06 | 2024-03-27 | WESTRAC PTY LTD (30000280) | 4500003440 |  | 10 | 1 | EA | 2023-02-27 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130548 | 6 | 1 |  |  | Supply for Order 100032076, Item 6 cannot be changed 90003406 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-28 | 0 | 0 | 2024-03-30 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-27 | -7 | 21 | ON TIME | 4500003440 | On Time | 2023-02-27 | Need Purchasing | 00001305484540670000589000100032076 | 00001305484540670000589000100032076 | 000013054870000589000100032076 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-22 | 2024-04-29 | 2024-03-28 | 2024-04-28 | 2024-05-02 | REFURB |  | 100037132 | 0060 | E/R - Replace Spool HVAC CSW1 CDR-30357 (100037132) | PUMP,A/C COOLING,DUTY (AB50.03P753002A) | replace spool (0030) | AB50 | 2024-06-12 |  |  | AB01 | 2024-05-05 | 20 | 20 | 70001063 | D-WEL23-215-01/EH4530DX0007.0001 Spool 1 | 1 | 0 | 0 | ETA - ISSUE's - 8 May - Procurement - Legeneering. | 60 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006988 | 30 | 60 | X | 1000003314 | 8 | 2024-02-22 | 2024-04-29 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500004845 |  | 10 | 1 | EA | 2024-05-08 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135616 | 8 | 1 |  |  | Supply for Order 100037132, Item 8 cannot be changed 90003414 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 38 | 0 | 2024-11-30 | 0 | 0 | 2024-05-05 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-01 | 4 | 32 | ON TIME | 4500004845 | After Turnround | 2024-05-08 | Need Purchasing | 00001356164541170001063000100037132 | 00001356164541170001063000100037132 | 000013561670001063000100037132 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-02 | 2024-04-18 | 2024-05-15 | 2024-04-18 | 2024-04-19 | CRANE |  | 600001624 | 0010 | MOC FP8 Mid Crane Blinds & Tint (600001624) | CRANE,MIDSHIP PS (AB50.05X790001) | Install new tint film onto mid cr cab (0010) | AB50 | 2024-06-24 |  |  | AB01 | 2024-05-13 | 20 | 20 | 70001189 | TINT, MEP NS28 window film | 9 | 9 | 0 | UserCommentLink | 7 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300005990 | 10 | 7 | X | 1000001767 | 2 | 2024-04-26 | 2024-05-10 | TRINKOR PTY LTD (30001954) | 4500002013 | 5000017117_2024_0001 | 10 | 9 | EA | 2024-02-05 |  | /180003928 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000084480 | 2 | 3 |  |  | Supply for Order 600001624, Item 2 cannot be changed 90003380 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 42 | 2024-05-30 | 0 | 0 | 2024-05-13 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | -55 | -27 | Delayed |  | On Time | 0 | SOH | 00000844804540070001189000600001624 | #N/A | 000008448070001189000600001624 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-02 | 2024-04-18 | 2024-05-15 | 2024-04-18 | 2024-04-19 | CRANE |  | 600001624 | 0010 | MOC FP8 Mid Crane Blinds & Tint (600001624) | CRANE,MIDSHIP PS (AB50.05X790001) | Install new blinds in mid crane cab (0020) | AB50 | 2024-06-24 |  |  | AB01 | 2024-05-13 | 20 | 20 | 70001200 | Blinds, Cassette, Reflective Black/Black | 3 | 3 | 0 | UserCommentLink | 77 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300005990 | 20 | 77 | X | 1000001767 | 4 | 2024-02-16 | 2024-05-10 | TRINKOR PTY LTD (30001954) | 4500002013 | 5000027023_2024_0001/5000024603_2024_0001 | 20 | 3 | EA | 2024-04-23 |  | /180005719/180004342/180004018 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000084480 | 4 | 3 |  |  | Supply for Order 600001624, Item 4 cannot be changed 90003380 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 42 | 2024-05-30 | 0 | 0 | 2024-05-13 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | -55 | -27 | Delayed |  | On Time | 0 | SOH | 00000844804540070001200000600001624 | #N/A | 000008448070001200000600001624 | 0 | #N/A | 0
24OKCM16 | Supply too early, consider delaying |  | Released | 2023-12-30 | 2024-02-06 | 2024-04-24 | 2024-03-06 | 2024-04-24 | 2024-04-24 | INLEC |  | 100033657 | 0010 | CLASS Replace ODME solenoid - V12 (100033657) | PKG EQ,SKID ASSEMBLY (AB50.03A450500) | Install Control Solenoid V12 (0020) | AB50 | 2024-04-01 |  |  | AB02 | 2024-03-19 | 10 | 5 | 70001416 | SOLENOID VALVE | 1 | 0 | 0 | ETA. - G. - 3 Aprill. - PDC. | 42 | Vendor PO raised | Directs (Inventory) (SP14) | AB02 | 5300005950 | 10 | 42 | X | 1000001698 | 4 | 2024-02-01 | 2024-03-19 | WARTSILA AUSTRALIA PTY LTD (30000386) | 4500001633 |  | 10 | 1 | EA | 2024-04-11 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132189 | 4 | 1 |  |  | Supply for Order 100033657, Item 4 cannot be changed 90001776 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 13 | 0 | 2024-05-27 | 0 | 0 | 2024-03-19 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-27 | 21 | 49 | ON TIME |  | On Time | 0 | Need Purchasing | 00001321894540670001416000100033657 | 00001321894540670001416000100033657 | 000013218970001416000100033657 | 0 | #N/A | 0
24OKCM16 | Supply too early, consider delaying |  | Released | 2023-12-30 | 2024-01-31 | 2024-05-04 | 2024-03-28 | 2024-05-04 | 2024-05-05 | REFURB |  | 100039045 | 0010 | ER - Repl Spool LP Steam Sys CDR-28782 (100039045) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | replace spool (0020) | AB50 | 2024-04-07 |  |  | AB01 | 2024-04-02 | 30 | 30 | 70001493 | D-WEL23-200-01/EH0950DX0004.0001 Spool 1 | 1 | 0 | 0 | ETA - 8 April - *(49 Day Lead)* - Procurement - Legeneering. | 49 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300005852 | 30 | 49 | X | 1000001607 | 4 | 2024-01-31 | 2024-03-27 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001467 |  | 10 | 1 | EA | 2024-04-08 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137519 | 4 | 1 |  |  | Supply for Order 100039045, Item 4 cannot be changed 90003376 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 5 | 0 | 2023-05-27 | 0 | 0 | 2024-04-02 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-06 | 9 | 37 | ON TIME | 4500001467 | After Turnround | 2024-04-08 | Need Purchasing | 00001375194541670001493000100039045 | 00001375194541670001493000100039045 | 000013751970001493000100039045 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-09 | 2024-05-01 | 2024-04-23 | 2024-05-01 | 2024-05-02 | INLEC |  | 100032477 | 0030 | CLASS 4PCOT Install New Earth Bosses (100032477) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | 4PCOT Install New Earth Bosses & Cable (0010) | AB50 | 2024-04-29 |  |  | AB01 | 2024-04-21 | 10 | 5 | 70001522 | Cable, Green/ Yellow 10mm2. 1kV | 1 | 1 | 0 | OK. - PDC. | 14 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300006318 | 30 | 14 | X | 1000002281 | 4 | 2024-03-26 | 2024-04-18 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 4500002429 | 5000025167_2024_0001 | 10 | 1 | EA | 2024-02-25 |  | /180005891 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131021 | 4 | 3 |  |  | Supply for Order 100032477, Item 4 cannot be changed 90003387 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 8 | 2026-05-27 | 0 | 0 | 2024-04-21 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-03 | -20 | 8 | ON TIME |  | On Time | 0 | SOH | 00001310214541370001522000100032477 | 00001310214541370001522000100032477 | 000013102170001522000100032477 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-09 | 2024-05-01 | 2024-04-23 | 2024-05-01 | 2024-05-02 | INLEC |  | 100032477 | 0040 | CLASS 4PCOT Install New Earth Bosses (100032477) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | 4PCOT Install New Earth Bosses & Cable (0010) | AB50 | 2024-04-29 |  |  | AB01 | 2024-04-21 | 10 | 5 | 70001523 | Crimp Lug Copper 10mm2, 10mm Stud | 1 | 1 | 0 | OK. - PDC. | 7 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300006318 | 40 | 7 | X | 1000002281 | 6 | 2024-04-04 | 2024-04-18 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 4500002553 | 5000021181_2024_0001 | 10 | 1 | BOX | 2024-02-19 |  | /180004735 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131021 | 6 | 3 |  |  | Supply for Order 100032477, Item 6 cannot be changed 90003387 item 40 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 8 | 2026-05-27 | 0 | 0 | 2024-04-21 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-03 | -20 | 8 | ON TIME |  | On Time | 0 | SOH | 00001310214541370001523000100032477 | 00001310214541370001523000100032477 | 000013102170001523000100032477 | 0 | #N/A | 0
24OKCM19 | Vendor del date will not meet planned Work-packing |  | Released | 2023-12-30 | 2024-03-27 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-10 | MECH |  | 100034141 | 0010 | Replace scupper strainer mesh with SS (100034141) | STRUC,VESSEL HULL (AB50.03HULL01) | Replace scupper strainer mesh with SS (0010) | AB50 | 2024-05-05 |  |  | AB01 | 2024-04-29 | 20 | 20 | 70001542 | SHEET; SS Perforated, 300 x 235 x 1.5mm | 80 | 0 | 0 | MAINT. - R. | 21 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300008462 | 10 | 21 | X | 1000007193 | 3 | 2024-03-27 | 2024-04-26 | TRINKOR PTY LTD (30001954) | 4500009169 |  | 10 | 80 | EA | 2024-04-21 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132645 | 3 | 1 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 6 | 0 | 2024-12-31 | 0 | 0 | 2024-04-29 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME | 4500009169 | After Turnround | 2024-04-21 | Need Purchasing | 00001326454542170001542000100034141 | 00001326454542170001542000100034141 | 000013264570001542000100034141 | 0 | #N/A | 0
24OKCM19 | Vendor del date will not meet planned Work-packing |  | Released | 2023-12-30 | 2024-03-27 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-10 | MECH |  | 100034141 | 0020 | Replace scupper strainer mesh with SS (100034141) | STRUC,VESSEL HULL (AB50.03HULL01) | Replace scupper strainer mesh with SS (0010) | AB50 | 2024-05-05 |  |  | AB01 | 2024-04-29 | 20 | 20 | 70001543 | SHEET; SS Perforated, 300 x 285 x 1.5mm | 80 | 0 | 0 | MAINT. - R. | 21 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300008462 | 20 | 21 | X | 1000007193 | 4 | 2024-03-27 | 2024-04-26 | TRINKOR PTY LTD (30001954) | 4500009169 |  | 20 | 80 | EA | 2024-04-21 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132645 | 4 | 1 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 6 | 0 | 2024-12-31 | 0 | 0 | 2024-04-29 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME | 4500009169 | After Turnround | 2024-04-21 | Need Purchasing | 00001326454542170001543000100034141 | 00001326454542170001543000100034141 | 000013264570001543000100034141 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-03-13 | 2024-04-18 | 2024-03-28 | 2024-04-18 | 2024-04-19 | MECH |  | 100033044 | 0010 | Repl N2 Backup Cyl & Reg Fittings MOC (100033044) | PKG EQ,NITROGEN BOTTLE RACK (AB50.03A481004) | Repl N2 Backup Cylinders (0010) | AB50 | 2024-11-03 |  |  | AB01 | 2024-07-16 | 20 | 20 | 70001748 | 03PSV481061 set to 20MPA | 1 | 0 | 0 | ETA. | 112 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300007834 | 10 | 112 | X | 1000005319 | 4 | 2024-03-13 | 2024-07-10 | SCORE AUSTRALASIA PTY LTD (30000225) | 4500006563 |  | 10 | 1 | EA | 2024-07-03 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131525 | 4 | 1 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 110 | 0 | 2024-06-30 | 0 | 0 | 2024-07-16 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | -7 | 21 | ON TIME | 4500006563 | After Turnround | 2024-07-03 | Need Purchasing | 00001315254540070001748000100033044 | 00001315254540070001748000100033044 | 000013152570001748000100033044 | 0 | #N/A | 0
24OKCM19 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-02-02 | 2024-02-06 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0010 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | Install new trolley and hoist (0050) | AB50 | 2024-03-29 |  |  | AB01 | 2024-02-21 | 20 | 20 | 70002089 | 21m (cut length) x Ø5mm Hand Chain (KITO | 1 | 0 | 1 | OK. | 2 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300004592 | 20 | 2 | X | 1000001963 | 3 | 2024-02-06 | 2024-02-15 | LIFTING BY DESIGN PTY LTD (30002258) | 4500002711 |  | 10 | 1 | EA | 2024-02-20 |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 3 | 1 |  |  | Supply for Order 600001724, Item 3 cannot be changed 90001109 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 15 | 22 | 2024-06-02 | 0 | 0 | 2024-02-21 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-01-05 | -32 | -4 | Delayed |  | On Time | 0 | Need Purchasing | 00000845794532470002089000600001724 | #N/A | 000008457970002089000600001724 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-12 | 2024-04-22 | 2024-03-28 | 2024-04-22 | 2024-04-26 | REFURB |  | 100039046 | 0010 | E/R - Repl 3x LP Steam Spools CDR-27187 (100039046) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | Repl 3x LP Steam DN80 Spools (0020) | AB50 | 2024-05-01 |  |  | AB01 | 2024-04-14 | 30 | 30 | 70002317 | D-WEL23-201-01/EH0950DX0006.0001 Spool 1 | 1 | 0 | 0 | ETA - 8 April - *(49 Day Lead)* - Procurement - Legeneering. | 49 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006461 | 10 | 49 | X | 1000002389 | 7 | 2024-02-12 | 2024-04-08 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001467 |  | 20 | 1 | EA | 2024-04-08 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137520 | 7 | 1 |  |  | Supply for Order 100039046, Item 7 cannot be changed 90003392 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 17 | 0 | 2023-05-27 | 0 | 0 | 2024-04-14 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-25 | -3 | 25 | ON TIME | 4500001467 | After Turnround | 2024-04-08 | Need Purchasing | 00001375204540470002317000100039046 | 00001375204540470002317000100039046 | 000013752070002317000100039046 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-12 | 2024-04-22 | 2024-03-28 | 2024-04-22 | 2024-04-26 | REFURB |  | 100039046 | 0050 | E/R - Repl 3x LP Steam Spools CDR-27187 (100039046) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | Repl 3x LP Steam DN80 Spools (0020) | AB50 | 2024-05-01 |  |  | AB01 | 2024-04-14 | 30 | 30 | 70002318 | D-WEL23-201-02/EH0950DX0007.0001 Spool 1 | 1 | 0 | 0 | ETA - 8 April - *(49 Day Lead)* - Procurement - Legeneering. | 49 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006461 | 20 | 49 | X | 1000002389 | 8 | 2024-02-12 | 2024-04-08 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001467 |  | 30 | 1 | EA | 2024-04-08 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137520 | 8 | 1 |  |  | Supply for Order 100039046, Item 8 cannot be changed 90003392 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 17 | 0 | 2023-05-27 | 0 | 0 | 2024-04-14 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-25 | -3 | 25 | ON TIME | 4500001467 | After Turnround | 2024-04-08 | Need Purchasing | 00001375204540470002318000100039046 | 00001375204540470002318000100039046 | 000013752070002318000100039046 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-12 | 2024-04-22 | 2024-03-28 | 2024-04-22 | 2024-04-26 | REFURB |  | 100039046 | 0060 | E/R - Repl 3x LP Steam Spools CDR-27187 (100039046) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | Repl 3x LP Steam DN80 Spools (0020) | AB50 | 2024-05-01 |  |  | AB01 | 2024-04-14 | 30 | 30 | 70002319 | D-WEL23-201-03/EH0950DX0008.0001 Spool 1 | 1 | 0 | 0 | ETA - 8 April - *(49 Day Lead)* - Procurement - Legeneering. | 49 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006461 | 30 | 49 | X | 1000002389 | 9 | 2024-02-12 | 2024-04-08 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001467 |  | 40 | 1 | EA | 2024-04-08 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137520 | 9 | 1 |  |  | Supply for Order 100039046, Item 9 cannot be changed 90003392 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 17 | 0 | 2023-05-27 | 0 | 0 | 2024-04-14 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-25 | -3 | 25 | ON TIME | 4500001467 | After Turnround | 2024-04-08 | Need Purchasing | 00001375204540470002319000100039046 | 00001375204540470002319000100039046 | 000013752070002319000100039046 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-12 | 2024-05-07 | 2024-03-28 | 2024-05-07 | 2024-05-08 | REFURB |  | 100038113 | 0060 | ER - Repl Spool Steam Sys CDR-28781 (100038113) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | Replace 25-SL-3750656-EXB3A-H (0020) | AB50 | 2024-05-01 |  |  | AB01 | 2024-04-14 | 30 | 30 | 70002402 | D-WEL23-202-01/EH0950DX0005.0001 Spool 1 | 1 | 0 | 0 | ETA - 6 April - Procurement - Legeneering. | 49 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006460 | 20 | 49 | X | 1000002375 | 16 | 2024-02-12 | 2024-04-08 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001467 |  | 50 | 1 | EA | 2024-04-08 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136617 | 16 | 1 |  |  | Supply for Order 100038113, Item 16 cannot be changed 90003390 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 17 | 0 | 2024-05-27 | 0 | 0 | 2024-04-14 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-09 | 12 | 40 | ON TIME | 4500001467 | After Turnround | 2024-04-08 | Need Purchasing | 00001366174541970002402000100038113 | 00001366174541970002402000100038113 | 000013661770002402000100038113 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-12 | 2024-05-07 | 2024-03-28 | 2024-05-07 | 2024-05-08 | REFURB |  | 100038113 | 0070 | ER - Repl Spool Steam Sys CDR-28781 (100038113) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | Replace 25-SL-3750656-EXB3A-H (0020) | AB50 | 2024-05-01 |  |  | AB01 | 2024-04-14 | 30 | 30 | 70002403 | D-WEL23-202-01/EH0950DX0005.0001 Spool 2 | 1 | 0 | 0 | ETA - 6 April - Procurement - Legeneering. | 49 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006460 | 30 | 49 | X | 1000002375 | 17 | 2024-02-12 | 2024-04-08 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001467 |  | 60 | 1 | EA | 2024-04-08 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136617 | 17 | 1 |  |  | Supply for Order 100038113, Item 17 cannot be changed 90003390 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 17 | 0 | 2024-05-27 | 0 | 0 | 2024-04-14 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-09 | 12 | 40 | ON TIME | 4500001467 | After Turnround | 2024-04-08 | Need Purchasing | 00001366174541970002403000100038113 | 00001366174541970002403000100038113 | 000013661770002403000100038113 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-07 | 2024-02-12 | 2024-04-18 | 2024-04-19 | MECH |  | 100037513 | 0040 | Bosun - CLASS - Repl Port Filter Housing (100037513) | DAMP,SUPPLY AIR,BOSUN STORE (AB50.04HDR680855A) | Install replacement filter housing (0010) | AB50 | 2024-06-02 |  |  | AB01 | 2024-03-14 | 10 | 5 | 70002482 | FILTER; Single Stage, 1000mm x 1000mm x | 1 | 0 | 0 | ETA. | 21 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300006434 | 10 | 21 | X | 1000002382 | 5 | 2024-02-12 | 2024-03-11 | TRINKOR PTY LTD (30001954) | 4500002724 |  | 10 | 1 | EA | 2024-03-11 |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136037 | 5 | 1 |  |  | Supply for Order 100037513, Item 5 cannot be changed 90001695 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 31 | 49 | 2024-05-27 | 0 | 0 | 2024-03-14 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2023-12-10 | -64 | -36 | Delayed | 4500002724 | FALSE | 2024-03-11 | Need Purchasing | 00001360374529870002482000100037513 | 00001360374529870002482000100037513 | 000013603770002482000100037513 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-27 | 2024-05-05 | 2024-03-28 | 2024-05-04 | 2024-05-07 | REFURB |  | 100038184 | 0010 | E/R - Repl Spool Steam Cond CDR-28783 (100038184) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | replace 15-SW-3750718-EXA1X-P (0030) | AB50 | 2024-05-19 |  |  | AB01 | 2024-04-23 | 30 | 30 | 70003315 | D-WEL23-203-01 Spool 1 | 1 | 0 | 0 | ETA - 6 April - Procurement - Legeneering. | 42 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300007229 | 40 | 42 | X | 1000003771 | 7 | 2024-02-27 | 2024-04-17 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500004437 |  | 10 | 1 | EA | 2024-04-15 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136688 | 7 | 1 |  |  | Supply for Order 100038184, Item 7 cannot be changed 90003427 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 26 | 0 | 2024-05-27 | 0 | 0 | 2024-04-23 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-07 | 10 | 38 | ON TIME | 4500004437 | After Turnround | 2024-04-15 | Need Purchasing | 00001366884541770003315000100038184 | 00001366884541770003315000100038184 | 000013668870003315000100038184 | 0 | #N/A | 0
24OKCM16 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-02-27 | 2024-05-05 | 2024-03-28 | 2024-05-04 | 2024-05-07 | REFURB |  | 100038184 | 0020 | E/R - Repl Spool Steam Cond CDR-28783 (100038184) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | replace 15-SW-3750718-EXA1X-P (0030) | AB50 | 2024-05-19 |  |  | AB01 | 2024-04-23 | 30 | 30 | 70003316 | D-WEL23-203-01 Spool 2 | 1 | 0 | 0 | ETA - 6 April - Procurement - Legeneering. | 42 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300007229 | 50 | 42 | X | 1000003771 | 8 | 2024-02-27 | 2024-04-17 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500004437 |  | 20 | 1 | EA | 2024-04-15 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136688 | 8 | 1 |  |  | Supply for Order 100038184, Item 8 cannot be changed 90003427 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 26 | 0 | 2024-05-27 | 0 | 0 | 2024-04-23 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-07 | 10 | 38 | ON TIME | 4500004437 | After Turnround | 2024-04-15 | Need Purchasing | 00001366884541770003316000100038184 | 00001366884541770003316000100038184 | 000013668870003316000100038184 | 0 | #N/A | 0
24OKCM19 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-10 | 2024-03-01 | 2024-05-09 | 2024-05-12 | MECH |  | 100038290 | 0010 | Repl Motor & Align FGC Condensate Pp-B (100038290) | PUMP,FGC CONDENSATE B (AB50.05P041101B) | Install new FGC B Cond Motor (0050) | AB50 | 2024-06-25 |  |  | AB01 | 2024-04-28 | 20 | 20 | 70003475 | Toshiba Ex d IIC T4 Motor | 1 | 0 | 0 | ETA. | 42 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300001696 | 20 | 42 | X | 1000004218 | 2 | 2024-03-01 | 2024-04-22 | TOSHIBA INTERNATIONAL CORPORATION (30000272) | 4500005097 |  | 20 | 1 | EA | 2024-04-10 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136822 | 2 | 1 |  |  | Supply for Order 100038290, Item 2 cannot be changed 90003593 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 58 | 0 | 2023-06-30 | 0 | 0 | 2024-04-28 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-12 | 42 | 70 | ON TIME | 4500005097, 4500005097 | After Turnround | 2024-04-10 | Need Purchasing | 00001368224542270003475000100038290 | 00001368224542270003475000100038290 | 000013682270003475000100038290 | 0 | #N/A | 0
24OKCM19 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-03-01 | 2024-05-09 | 2024-05-14 | INLEC |  | 100038291 | 0010 | Replace Motor FGC Condensate Pp-A (100038291) | PUMP,FGC CONDENSATE A (AB50.05P041101A) | Remove/Replace Motor with new (0030) | AB50 | 2024-06-25 |  |  | AB01 | 2024-04-28 | 20 | 20 | 70003475 | Toshiba Ex d IIC T4 Motor | 1 | 0 | 0 | ETA. | 42 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300007421 | 10 | 42 | X | 1000004167 | 3 | 2024-03-01 | 2024-04-22 | TOSHIBA INTERNATIONAL CORPORATION (30000272) | 4500005097 |  | 10 | 1 | EA | 2024-04-10 |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000136823 | 3 | 1 |  |  | Supply for Order 100038291, Item 3 cannot be changed 90003598 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 58 | 0 | 2024-12-31 | 0 | 0 | 2024-04-28 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 41 | 69 | ON TIME | 4500005097, 4500005097 | After Turnround | 2024-04-10 | Need Purchasing | 00001368234542170003475000100038291 | 00001368234542170003475000100038291 | 000013682370003475000100038291 | 0 | #N/A | 0
24OKCM13 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-29 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0510 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-04-05 |  |  | AB01 | 2024-03-18 | 20 | 20 | 70003498 | Expediting Freight Fees | 1 | 0 | 0 | OK. | 7 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300004702 | 120 | 7 | X | 1000004043 | 52 | 2024-02-29 | 2024-03-15 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 4500004816 |  | 30 | 1 | EA | 2024-03-15 |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 52 | 1 |  |  | Supply for Order 100037574, Item 52 cannot be changed 90002704 item 90 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 18 | 0 | 2024-06-30 | 0 | 0 | 2024-03-18 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 8 | 36 | ON TIME | 4500004816 | During Turnaround | 2024-03-15 | Need Purchasing | 00001360984538770003498000100037574 | 00001360984538770003498000100037574 | 000013609870003498000100037574 | 0 | #N/A | 0
24OKCM19 | Vendor del date will not meet planned Work-packing |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0010 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | Commission and function test new system. (0080) | AB50 | 2024-03-29 |  |  | AB01 | 2024-03-21 | 20 | 20 | 70003722 | Q#27746 Air Line Tie Additional Fitting | 1 | 1 | 0 | ETA. | 5 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300004592 | 40 | 5 | X | 1000004610 | 6 | 2024-03-06 | 2024-03-18 | HYDRAULIC ENERGY AUST PTY LTD (30002606) | 4500005544 |  | 10 | 1 | EA | 2024-03-13 |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 6 | 1 |  |  | Supply for Order 600001724, Item 6 cannot be changed 90004209 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 8 | 0 | 2024-06-02 | 0 | 0 | 2024-03-21 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00000845794537970003722000600001724 | #N/A | 000008457970003722000600001724 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-10 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-09 | INLEC |  | 100033135 | 0020 | Replace AFT Crane Aviation Lights MOC (100033135) | LIGHT,NAV,AFT CRANE,BOOM,-1 (AB50.05LT612482A) | RA Replace AFT Crane Boom Lts & Ex Insp (0020) | AB50 | 2024-04-21 |  |  | AB01 | 2024-04-21 | 20 | 20 | 70003747 | Plate 230 x 230 | 4 | 0 | 0 | ETA. | 20 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300004723 | 20 | 20 | X | 1000004771 | 3 | 2024-03-21 | 2024-04-18 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500005715 |  | 20 | 4 | EA | 2024-03-28 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131667 | 3 | 3 |  |  | Supply for Order 100033135, Item 3 cannot be changed 90005583 item 10 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 | 2024-04-21 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | -12 | 16 | ON TIME | 4500005715 | After Turnround | 2024-03-28 | Need Purchasing | 00001316674542170003747000100033135 | 00001316674542170003747000100033135 | 000013166770003747000100033135 | 0 | #N/A | 0
24OKCM19 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-03-27 | 2024-05-09 | 2024-04-19 | 2024-05-09 | 2024-05-10 | MECH |  | 100032996 | 0070 | Replace Vlv FG Scrub Vessel MV441022 (100032996) | VALVE,LG441113,MAN DRAIN (AB50.05MV441022) | Isolate 05MV441022 (0010) | AB50 | 2024-05-15 |  |  | AB01 | 2024-05-02 | 30 | 30 | 70003767 | Carman, 20 NB x 300 Spec Blind to suit R | 1 | 0 | 0 | MAINT. - R. | 21 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300008461 | 30 | 21 | X | 1000007192 | 8 | 2024-03-27 | 2024-04-26 | SCORE AUSTRALASIA PTY LTD (30000225) | 4500009179 |  | 10 | 1 | EA | 2024-04-30 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131610 | 8 | 1 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 13 | 0 | 2024-12-31 | 0 | 0 | 2024-05-02 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | -8 | 20 | ON TIME | 4500009179 | After Turnround | 2024-04-30 | Need Purchasing | 00001316104542170003767000100032996 | 00001316104542170003767000100032996 | 000013161070003767000100032996 | 0 | #N/A | 0
24OKCM19 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0040 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | Commission and function test new system. (0080) | AB50 | 2024-04-16 |  |  | AB01 | 2024-03-30 | 20 | 20 | 70003940 | Stainless Steel Bolt Hex Set Screw SS316 | 150 | 0 | 0 | ETA. | 7 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300004592 | 60 | 7 | X | 1000005254 | 14 | 2024-03-13 | 2024-03-27 | J BLACKWOOD AND SON LTD (30000394) | 4500007066 |  | 20 | 150 | EA | 2024-03-27 |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 14 | 1 |  |  | Supply for Order 600001724, Item 14 cannot be changed 90004666 item 20 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA |  | 17 | 0 | 2024-06-02 | 0 | 0 | 2024-03-30 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-02-29 | -13 | 15 | ON TIME |  | During Turnaround | 2024-03-27 | Need Purchasing | 00000845794537970003940000600001724 | #N/A | 000008457970003940000600001724 | 0 | #N/A | 0
24OKCM19 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0050 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | Commission and function test new system. (0080) | AB50 | 2024-04-16 |  |  | AB01 | 2024-03-30 | 20 | 20 | 70003941 | Stainless Steel Nut Hex Standard SS316 S | 150 | 150 | 0 | ETA. | 7 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004592 | 70 | 7 | X | 1000005254 | 15 | 2024-03-13 | 2024-03-27 | J BLACKWOOD AND SON LTD (30000394) | 4500007066 | 5000040516_2024_0001 | 30 | 150 | EA | 2024-03-27 |  | /180011869 |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 15 | 1 |  |  | Supply for Order 600001724, Item 15 cannot be changed 90004666 item 30 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA |  | 17 | 0 | 2024-06-02 | 0 | 0 | 2024-03-30 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00000845794537970003941000600001724 | #N/A | 000008457970003941000600001724 | 0 | #N/A | 0
24OKCM19 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0060 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | Commission and function test new system. (0080) | AB50 | 2024-04-16 |  |  | AB01 | 2024-03-30 | 20 | 20 | 70003942 | Flat Round Washer Standard 316 Stainless | 150 | 150 | 0 | ETA. | 7 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004592 | 80 | 7 | X | 1000005254 | 16 | 2024-03-13 | 2024-03-27 | J BLACKWOOD AND SON LTD (30000394) | 4500007066 | 5000040477_2024_0001 | 40 | 150 | EA | 2024-03-27 |  | /180011869 |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 16 | 1 |  |  | Supply for Order 600001724, Item 16 cannot be changed 90004666 item 40 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA |  | 17 | 0 | 2024-06-02 | 0 | 0 | 2024-03-30 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00000845794537970003942000600001724 | #N/A | 000008457970003942000600001724 | 0 | #N/A | 0
24OKCM19 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0070 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | Commission and function test new system. (0080) | AB50 | 2024-04-16 |  |  | AB01 | 2024-03-30 | 20 | 20 | 70003943 | Stainless Steel Bolt Hex Set Screw SS316 | 150 | 150 | 0 | ETA. | 7 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004592 | 90 | 7 | X | 1000005254 | 18 | 2024-03-13 | 2024-03-27 | J BLACKWOOD AND SON LTD (30000394) | 4500007066 | 5000040506_2024_0001 | 50 | 150 | EA | 2024-03-27 |  | /180011869 |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 18 | 1 |  |  | Supply for Order 600001724, Item 18 cannot be changed 90004666 item 50 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA |  | 17 | 0 | 2024-06-02 | 0 | 0 | 2024-03-30 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00000845794537970003943000600001724 | #N/A | 000008457970003943000600001724 | 0 | #N/A | 0
24OKCM19 | Planned delivery after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0080 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | Commission and function test new system. (0080) | AB50 | 2024-05-14 |  |  | AB01 | 2024-04-13 | 20 | 20 | 70003950 | Monorail Beam End stops (L&R Pair) | 1 | 0 | 0 | ETA 10.04.24 PO 4500007060 BENDTECH GROUP | 21 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300004592 | 100 | 21 | X | 1000005254 | 20 | 2024-03-13 | 2024-04-10 | BENDTECH GROUP PTY LTD (30002958) | 4500007060 |  | 10 | 1 | SET | 2024-04-15 |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 20 | 1 |  |  | Supply for Order 600001724, Item 20 cannot be changed 90004666 item 60 already exists |  | 0 | FALSE |  |  |  | WorkPackLink | OKHA |  | 31 | 0 | 2024-06-02 | 0 | 0 | 2024-04-13 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-02-29 | -13 | 15 | ON TIME |  | After Turnround | 2024-04-15 | Need Purchasing | 00000845794537970003950000600001724 | #N/A | 000008457970003950000600001724 | 0 | #N/A | 0
24OKCM19 | Issue detected, please check message in derivation |  | Released | 2024-02-09 | 2024-03-26 | 2024-05-09 | 2024-04-23 | 2024-05-09 | 2024-05-09 | INLEC |  | 100072934 | 0010 | GT1 Install Terminal Covers (100072934) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Install Cover Over Exposed Terminals (0020) | AB50 | 2025-07-11 |  |  | AB01 | 2024-12-01 | 20 | 20 | 70004675 | KIT,INSTL,1-BAY METR/SW SHOCK | 4 | 0 | 0 | ETA 15.06.24 PO 4500008307 SOLAR TURBINES | 240 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300008210 | 10 | 240 | X | 1000006539 | 2 | 2024-03-22 | 2024-11-28 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 4500008307 |  | 10 | 4 | EA | 2024-06-15 |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000219896 | 2 | 1 |  |  | Supply for Order 100072934, Item 2 cannot be changed – 4500008307 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 222 | 0 | 2024-12-31 | 0 | 0 | 2024-12-01 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | -12 | 16 | ON TIME |  | After Turnround | 2024-06-15 | Need Purchasing | 00002198964542170004675000100072934 | 00002198964542170004675000100072934 | 000021989670004675000100072934 | 0 | #N/A | 0
24OKCO13 | Issue detected, please check message in derivation |  | Released | 2024-03-27 | 2024-03-27 | 2024-03-28 | 2024-03-27 | 2024-03-28 | 2024-03-28 | MECH |  | 100075531 | 0010 | Replace Linear Winch HPU Impulse Lines (100075531) | PKG EQ,LINEAR WINCH PACKAGE (AB50.04WM790001) | Replace Linear Winch HPU Impulse Lines (0010) | AB50 | 2024-06-03 |  |  | AB01 | 2024-04-22 | 20 | 20 | 70004851 | Linear Winch 630 Bar Test Lines 1500mm | 2 | 0 | 0 | UserCommentLink | 14 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300008427 | 10 | 14 | X | 1000007062 | 3 | 2024-03-27 | 2024-04-19 | HYDRAULIC ENERGY AUST PTY LTD (30002606) | 4500008855 |  | 10 | 2 | EA | 2024-04-11 |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000228982 | 3 | 1 |  |  | Supply for Order 100075531, Item 3 cannot be changed – 4500008855 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 26 | 16 | 2024-09-25 | 0 | 0 | 2024-04-22 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-29 | -27 | 1 | ON TIME |  | After Turnround | 2024-04-11 | Need Purchasing | 00002289824537970004851000100075531 | 00002289824537970004851000100075531 | 000022898270004851000100075531 | 0 | #N/A | 0
24OKCO13 | Issue detected, please check message in derivation |  | Released | 2024-03-27 | 2024-03-27 | 2024-03-28 | 2024-03-27 | 2024-03-28 | 2024-03-28 | MECH |  | 100075531 | 0020 | Replace Linear Winch HPU Impulse Lines (100075531) | PKG EQ,LINEAR WINCH PACKAGE (AB50.04WM790001) | Replace Linear Winch HPU Impulse Lines (0010) | AB50 | 2024-06-03 |  |  | AB01 | 2024-04-22 | 20 | 20 | 70004852 | Linear Winch 630 Bar Test Lines 2000mm | 2 | 0 | 0 | UserCommentLink | 14 | Vendor PO raised | Directs (Inventory) (SP14) | AB01 | 5300008427 | 20 | 14 | X | 1000007062 | 4 | 2024-03-27 | 2024-04-19 | HYDRAULIC ENERGY AUST PTY LTD (30002606) | 4500008855 |  | 20 | 2 | EA | 2024-04-11 |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000228982 | 4 | 1 |  |  | Supply for Order 100075531, Item 4 cannot be changed – 4500008855 already exists |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 26 | 16 | 2024-09-25 | 0 | 0 | 2024-04-22 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-29 | -27 | 1 | ON TIME |  | After Turnround | 2024-04-11 | Need Purchasing | 00002289824537970004852000100075531 | 00002289824537970004852000100075531 | 000022898270004852000100075531 | 0 | #N/A | 0
24OKCM19 | WO item has not been released yet |  | Created | 2023-12-30 |  | 2024-05-11 |  | 2024-05-09 | 2024-05-12 | PAINT |  | 100034411 | 0010 | ENG - CLASS - Repair IG Fresh Air Inlets (100034411) | SW,S480020,POS FRESH AIR INTAKE (AB50.03ZSC480958) | Re-install Rubber to Cover Plate (0070) | AB50 |  |  |  | AB01 |  | 10 | 5 | 10266028 | ADHESIVE;CONT GRIP,BOSTIK 156248 | 1 | 0 | 0 | MAINT. - R. | 0 |  | Directs (Inventory) (SP14) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CON |  |  |  |  | N | Planning (03) | In Planning (Order) (0035) | 0000132945 | 2 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-13 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001329454542310266028000100034411 | #N/A | 000013294510266028000100034411 |  |  | 0
24OKCM19 | WO item has not been released yet |  | Created | 2023-12-30 |  | 2024-05-11 |  | 2024-05-09 | 2024-05-12 | PAINT |  | 100034411 | 0010 | ENG - CLASS - Repair IG Fresh Air Inlets (100034411) | SW,S480020,POS FRESH AIR INTAKE (AB50.03ZSC480958) | Apply Belzona (0060) | AB50 | 2024-05-11 |  |  | AB01 |  | 10 | 5 | 10493611 | COMPOUND,REPAIR;BELZONA 1111 SUPER MTL | 2 | 57 | 0 | OK. - PDC. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  |  | N | Planning (03) | In Planning (Order) (0035) | 0000132945 | 1 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-13 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001329454542310493611000100034411 | #N/A | 000013294510493611000100034411 | 0 | #N/A | 0
24OKCM19 | WO item has not been released yet |  | Created | 2023-12-30 |  | 2024-05-13 |  | 2024-05-13 | 2024-05-14 | PAINT |  | 100037136 | 0010 | POOP - CDR-30137 - Blst & Pnt Emrgcy Gen (100037136) | LOOP,CORROSION,FLARE SYSTEM (AB50.03E14-GE01) | Blast & Paint Exhaust (Intertherm 751) (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10501084 | REPLACED BY 10607812 | 1 | 0 | 0 | MAINT. - R. | 0 |  | Directs (Inventory) (SP14) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Planning (03) | In Planning (Order) (0035) | 0000135620 | 1 | 2 | 30 | 99 |  |  | 0 | FALSE |  |  |  | WorkPackLink | Legeneering Paint |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-15 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001356204542510501084000100037136 | #N/A | 000013562010501084000100037136 |  |  | 0
24OKCM19 | WO item has not been released yet |  | Created | 2023-12-30 |  | 2024-05-13 |  | 2024-05-13 | 2024-05-14 | PAINT |  | 100037136 | 0020 | POOP - CDR-30137 - Blst & Pnt Emrgcy Gen (100037136) | LOOP,CORROSION,FLARE SYSTEM (AB50.03E14-GE01) | Blast & Paint Exhaust (Intertherm 751) (0010) | AB50 |  |  |  | AB01 |  | 30 | 30 | 10501085 | REPLACED BY 10607813 | 1 | 0 | 0 | MAINT. - R. | 0 |  | Directs (Inventory) (SP14) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Planning (03) | In Planning (Order) (0035) | 0000135620 | 2 | 2 | 30 | 99 |  |  | 0 | FALSE |  |  |  | WorkPackLink | Legeneering Paint |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-15 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001356204542510501085000100037136 | #N/A | 000013562010501085000100037136 |  |  | 0
24OKCM19 | WO item has not been released yet |  | Created | 2023-12-30 |  | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 200079582 | 0020 | 4Y F21 NRV WELL SERVICE PUMP REPLACEMENT (200079582) | VALVE,P010001 DISCHARGE,NRV (AB50.05SP010002) | CHANGE OUT VALVE (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 10 | 5 | 10464346 | GASKET,RJ;OCT,80MM,CL1500,R35,A182,F51 | 2 | 0 | 0 | MAINT. - R. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Planning (03) | In Planning (Order) (0035) | 0000113851 | 2 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001138514542110464346000200079582 | #N/A | 000011385110464346000200079582 | 0 | #N/A | 0
24OKCM19 | WO item has not been released yet |  | Created | 2023-12-30 |  | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 200079582 | 0010 | 4Y F21 NRV WELL SERVICE PUMP REPLACEMENT (200079582) | VALVE,P010001 DISCHARGE,NRV (AB50.05SP010002) | CHANGE OUT VALVE (0020) | AB50 | 2024-05-09 |  |  | AB01 |  | 10 | 5 | 10470892 | VALVE,CHK;CRANE 3NC150GGPR-638N,3",NOZ | 1 | 0 | 0 | MAINT. - R. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Planning (03) | In Planning (Order) (0035) | 0000113851 | 1 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001138514542110470892000200079582 | #N/A | 000011385110470892000200079582 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | INLEC |  | 100033021 | 0010 | Replace EM Light Batteries RTM All Level (100033021) | LIGHT,FLUOR,BAT,EQ DECK 1,DEM46002-2 (AB50.04LT400304B1605) | Batt Repl 04LT400304B1605 & Ex Insp (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 22 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131433 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013143345421000100033021 | #N/A | 0000131433000100033021 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | INLEC |  | 100033129 | 0010 | Replace EM Light Batt N/Deck LT400309B06 (100033129) | LIGHT,FLUOR,OUTSIDE,BAT,C083-E013.01 (AB50.03LT400309B0605) | Isolate LT400309B06 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131661 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-21 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013166145421000100033129 | #N/A | 0000131661000100033129 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-22 | MECH |  | 100033248 | 0020 | Check Torque Tst Separator (100033248) | VE,TEST SEPARATOR (AB50.05V020003) | Erect scaffold (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131749 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013174945400000100033248 | #N/A | 0000131749000100033248 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | MECH |  | 100033633 | 0010 | Replace SWLPB Inst Air Regulator (100033633) | VALVE,A453001B,DISCHARGE (AB50.03XV453251) | Isolate air to 03XV453251 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | ok. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132154 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-05-11 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013215445400000100033633 | #N/A | 0000132154000100033633 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | INLEC |  | 100034040 | 0010 | Replace SWLP-A ACB TU Contact S51 (100034040) | BREAKER,05MCC400101 FEEDR 03PM453001A (AB50.05MCC400101-A09) | Replace SWLP-A ACB TU Contact S51 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000132514 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013251445421000100034040 | #N/A | 0000132514000100034040 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 |  | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0190 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 30 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013256845401000100034084 | #N/A | 0000132568000100034084 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 |  | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0230 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013256845401000100034084 | #N/A | 0000132568000100034084 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 |  | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0070 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013256845401000100034084 | #N/A | 0000132568000100034084 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 |  | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0160 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013256845401000100034084 | #N/A | 0000132568000100034084 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-28 |  | 2024-03-28 | 2024-03-28 | INLEC |  | 100034116 | 0010 | Replace LVL TX PV Breaker (100034116) | TX,A480001,LEVEL (AB50.03LZT480012B) | Ex Inspection & I99 Ex Data Entry (0020) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000132637 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | L-ALLY05 |  | 0 | 0 | 2024-03-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013263745379000100034116 | #N/A | 0000132637000100034116 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 |  | 2024-04-19 | 2024-04-21 | MECH |  | 100034344 | 0020 | Replace AFT FWP Turbos (100034344) | PUMP,A600001A,FIRE WTR AFT (AB50.03P600001) | Isolate 03P600001 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132798 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013279845401000100034344 | #N/A | 0000132798000100034344 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 |  | 2024-04-19 | 2024-04-21 | MECH |  | 100034344 | 0030 | Replace AFT FWP Turbos (100034344) | PUMP,A600001A,FIRE WTR AFT (AB50.03P600001) | Isolate 03P600001 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | ETA. - G. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132798 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | PK_STAGING |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013279845401000100034344 | #N/A | 0000132798000100034344 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0040 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 10 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013340145379000100034857 | #N/A | 0000133401000100034857 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0050 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 10 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013340145379000100034857 | #N/A | 0000133401000100034857 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-19 | MECH |  | 100034863 | 0010 | Replace FWG 1&2 S/Water Outlet Vlvs (100034863) | VALVE,G452011,MAN ISOL (AB50.03MV753428) | Isolate 03MV753427 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133315 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-01-29 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013331545400000100034863 | #N/A | 0000133315000100034863 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-23 |  | 2024-04-23 | 2024-04-24 | MECH |  | 100035137 | 0020 | CLASS Replace FWD Foam Pump (100035137) | PUMP,A604031,FOAM (AB50.03P604031) | Remove and replace pump 03P604031 (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | Maint. - R. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000133689 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-26 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013368945405000100035137 | #N/A | 0000133689000100035137 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-23 |  | 2024-04-23 | 2024-04-24 | MECH |  | 100035137 | 0010 | CLASS Replace FWD Foam Pump (100035137) | PUMP,A604031,FOAM (AB50.03P604031) | Remove and replace pump 03P604031 (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | Simo to SRF back Direct to Vendor - ITT Blakers Perth - Wangara -Arjun Maradia | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000133689 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-26 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013368945405000100035137 | #N/A | 0000133689000100035137 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | HVAC |  | 100035206 | 0010 | Replace PDT Clean W/shop HVAC (100035206) | PKG EQ,CLEAN WORKSHOP HVAC PACKAGE (AB50.05HP680100) | Replace PDT Clean W/shop HVAC (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133710 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-01-06 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013371045400000100035206 | #N/A | 0000133710000100035206 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100035365 | 0020 | FRC - Annual rectification's (100035365) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | FRC - Annual rectifications (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000133869 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013386945421000100035365 | #N/A | 0000133869000100035365 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100035365 | 0040 | FRC - Annual rectification's (100035365) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | FRC - Annual rectifications (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 10 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000133869 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013386945421000100035365 | #N/A | 0000133869000100035365 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100035365 | 0010 | FRC - Annual rectification's (100035365) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | FRC - Annual rectifications (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 1 | 0 | 0 | 10314485 ROPE,FIB;PE,LIFE BUOY,SILVER,8M - On OKHA L-ALLEYFLR3 - Del: 80924926 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000133869 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013386945421000100035365 | #N/A | 0000133869000100035365 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100035365 | 0030 | FRC - Annual rectification's (100035365) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | FRC - Annual rectifications (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 12 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000133869 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013386945421000100035365 | #N/A | 0000133869000100035365 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | INLEC |  | 100035477 | 0010 | Upgrade GT1 I/O Modules (100035477) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Upgrade GT1 I/O Modules (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134011 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013401145421000100035477 | #N/A | 0000134011000100035477 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-23 |  | 2024-04-23 | 2024-04-23 | INLEC |  | 100035802 | 0010 | Replace 230V Cabinet Fan EGC1 UCP (100035802) | PANEL,EXPORT GAS COMPRESSOR T1 WITH A (AB50.05CP042200) | Replace 230V Cabinet Fan EGC1 UCP (0010) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000134294 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-09-11 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-26 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013429445405000100035802 | #N/A | 0000134294000100035802 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-21 |  | 2024-04-21 | 2024-04-24 | MECH |  | 100036033 | 0030 | HSE10 Install Accom Bag Store Shelves (100036033) | STRUCT,DECKHOUSE (AB50.05STRUCT021) | Fabricate support frames (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | BOX |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134557 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-24 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013455745403000100036033 | #N/A | 0000134557000100036033 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-21 |  | 2024-04-21 | 2024-04-24 | MECH |  | 100036033 | 0050 | HSE10 Install Accom Bag Store Shelves (100036033) | STRUCT,DECKHOUSE (AB50.05STRUCT021) | Fabricate support frames (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134557 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Okha |  | 0 | 0 | 2023-12-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-24 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013455745403000100036033 | #N/A | 0000134557000100036033 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-21 |  | 2024-04-21 | 2024-04-24 | MECH |  | 100036033 | 0010 | HSE10 Install Accom Bag Store Shelves (100036033) | STRUCT,DECKHOUSE (AB50.05STRUCT021) | Fabricate support frames (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134557 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-24 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013455745403000100036033 | #N/A | 0000134557000100036033 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-21 |  | 2024-04-21 | 2024-04-24 | MECH |  | 100036033 | 0020 | HSE10 Install Accom Bag Store Shelves (100036033) | STRUCT,DECKHOUSE (AB50.05STRUCT021) | Fabricate support frames (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | SHT |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134557 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-24 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013455745403000100036033 | #N/A | 0000134557000100036033 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-25 |  | 2024-04-25 | 2024-04-25 | INLEC |  | 100036077 | 0010 | Replace 03T400203B feeder module MCC (100036077) | SWBD,LV VESSEL ESS NO.2,DEV43015 (AB50.03MCC400205) | Replace 03T400203B feeder module MCC (0010) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134609 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-10-13 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013460945407000100036077 | #N/A | 0000134609000100036077 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-25 |  | 2024-04-25 | 2024-04-25 | INLEC |  | 100036077 | 0020 | Replace 03T400203B feeder module MCC (100036077) | SWBD,LV VESSEL ESS NO.2,DEV43015 (AB50.03MCC400205) | Replace 03T400203B feeder module MCC (0010) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134609 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-10-13 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013460945407000100036077 | #N/A | 0000134609000100036077 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0110 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 20 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 11 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0070 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 40 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0040 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0010 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0090 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0030 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0020 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0060 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0050 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0100 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 20 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 10 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-21 | 2024-04-28 | REFURB |  | 100036123 | 0080 | 5SCOT - Replace Brackets on Cargo deck (100036123) | BEACON,BCN RADIO,EEX,UPP DECK,FR 57 SB (AB50.03CIPA611138A) | replace corroded brackets (0099) | AB50 | [5 empty] | 10 | 10 |  |  | 18 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134615 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461545406000100036123 | #N/A | 0000134615000100036123 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | INLEC |  | 100036124 | 0020 | Replace GT2 Air Inlet RTD & Anaconda (100036124) | TXDCR,GT400002,AIR INLET TEMP (AB50.05TE400250-2) | Replace 05TE400252/2 anaconda run x 26" (0020) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | ETA. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000134616 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461645415000100036124 | #N/A | 0000134616000100036124 |  |  | 0
24OKCM16 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-02-17 |  | 2024-05-03 | 2024-05-03 | INLEC |  | 100036124 | 0030 | Replace GT2 Air Inlet RTD & Anaconda (100036124) | TXDCR,GT400002,AIR INLET TEMP (AB50.05TE400250-2) | Replace GT2 Air inlet RTD (0010) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | ETA. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000134616 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-01-20 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461645339000100036124 | #N/A | 0000134616000100036124 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | MECH |  | 100036126 | 0010 | Repair COP2 Actuation Valve (100036126) | SOL,A750023,ACTUATION (AB50.03XYV750251B) | Replace Actuation Valves 03XYV750251B 03 (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134618 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013461845400000100036126 | #N/A | 0000134618000100036126 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 100036218 | 0030 | GT1 Repair leaks main tank & return line (100036218) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Confirm isolations of GT1 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | 10458836 GASKET;SOLAR 10781561 - Del:71080335 on Okha: L-ALLYFLR2 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134750 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-29 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013475045421000100036218 | #N/A | 0000134750000100036218 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 100036218 | 0080 | GT1 Repair leaks main tank & return line (100036218) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Confirm isolations of GT1 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | 10569847 GLOVES,CHEM;XL - Del:71071638 on Okha: L-ALLYFLR2 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134750 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-29 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013475045421000100036218 | #N/A | 0000134750000100036218 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 100036218 | 0020 | GT1 Repair leaks main tank & return line (100036218) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Confirm isolations of GT1 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | 10418393 GASKET;SOLAR,1078159 - Del:71080335 on Okha: L-ALLYFLR2 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134750 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-29 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013475045421000100036218 | #N/A | 0000134750000100036218 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 100036218 | 0100 | GT1 Repair leaks main tank & return line (100036218) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Confirm isolations of GT1 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | 10612442 FILTER,CART;RESP,3M - Del:71077278 on Okha: L-ALLYFLR2 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134750 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-29 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013475045421000100036218 | #N/A | 0000134750000100036218 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | MECH |  | 100036218 | 0040 | GT1 Repair leaks main tank & return line (100036218) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | Confirm isolations of GT1 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | 10458837 GASKET;SOLAR 10781571 - Del:71080335 on Okha: L-ALLYFLR2 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134750 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-29 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013475045421000100036218 | #N/A | 0000134750000100036218 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100036395 | 0010 | Replace Light-Sewage Macerator CP (100036395) | PANEL,P640002,CONTROL (AB50.03CP640010) | Replace Macerator Healthy Lamp unit (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000134876 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013487645400000100036395 | #N/A | 0000134876000100036395 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100036478 | 0010 | Replace incorrect temp probe (100036478) | TX,A096010EXH,TEMP,EXHAUST GAS CYL 4 (AB50.03TT096040D) | Remove/ Replace 03TE096040D (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135042 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013504245400000100036478 | #N/A | 0000135042000100036478 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100036830 | 0040 | Replace C/Medium Vlv 05MV460015 (100036830) | VALVE,A043300,CM INLET (AB50.05MV460015) | Replace valve 05MV460015 (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000135362 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-03-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013536245421000100036830 | #N/A | 0000135362000100036830 |  |  | 0
24OKCO13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-28 |  | 2024-03-28 | 2024-03-28 | INLEC |  | 100036926 | 0010 | Replace Portable nav light - replace (100036926) | LIGHT,RISER,SOLAR POWERED (AB50.04LT612001) | Test, Charge & Store Portable Nav light (0010) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000135427 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013542745379000100036926 | #N/A | 0000135427000100036926 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-12 |  | 2024-05-09 | 2024-05-15 | PAINT |  | 100037085 | 0010 | 120 - Prep & Paint GT1 Gen Enclosure (100037085) | GEN,GT400001,GEN (AB50.05G400001) | Apply Coatings (Devcon + Paint) (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135597 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013559745424000100037085 | #N/A | 0000135597000100037085 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0080 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0120 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 11 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0040 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 30 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0050 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0030 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | BOX |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0090 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0010 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 30 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0060 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0070 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0020 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 60 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-06 | REFURB |  | 100037129 | 0100 | Bridge - Replace Spotlight Brackets (100037129) | STRUC,HELIDECK (AB50.05STRUCT020) | RA-L1 Replace 5x bridge Spotlight/mounts (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135613 | 10 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-09 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013561345416000100037129 | #N/A | 0000135613000100037129 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037152 | 0010 | Replace Galley 03MCC400201 Feeder Module (100037152) | FEEDER,LV MOD 03MCC400201 TO 03DB400502 (AB50.03MCC400201-B08E) | Isolate MCC and changeout CB (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135666 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013566645400000100037152 | #N/A | 0000135666000100037152 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037152 | 0020 | Replace Galley 03MCC400201 Feeder Module (100037152) | FEEDER,LV MOD 03MCC400201 TO 03DB400502 (AB50.03MCC400201-B08E) | Isolate MCC and changeout CB (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135666 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013566645400000100037152 | #N/A | 0000135666000100037152 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037153 | 0010 | Replace Spare 05MCC400101 Feeder Module (100037153) | FEEDER,LV MOD 05MCC400101 SPARE MODULE (AB50.05MCC400101-A08F) | Isolate MCC and changeout CB (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135667 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013566745400000100037153 | #N/A | 0000135667000100037153 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037153 | 0020 | Replace Spare 05MCC400101 Feeder Module (100037153) | FEEDER,LV MOD 05MCC400101 SPARE MODULE (AB50.05MCC400101-A08F) | Isolate MCC and changeout CB (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135667 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013566745400000100037153 | #N/A | 0000135667000100037153 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037173 | 0020 | Replace Steer/Gear-A Isolator MoC-55775 (100037173) | START,P756005A (AB50.03MS756005A) | Isolate Supply (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135725 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013572545400000100037173 | #N/A | 0000135725000100037173 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037173 | 0010 | Replace Steer/Gear-A Isolator MoC-55775 (100037173) | START,P756005A (AB50.03MS756005A) | Isolate Supply (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135725 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013572545400000100037173 | #N/A | 0000135725000100037173 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037173 | 0040 | Replace Steer/Gear-A Isolator MoC-55775 (100037173) | START,P756005A (AB50.03MS756005A) | Isolate Supply (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135725 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013572545400000100037173 | #N/A | 0000135725000100037173 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037173 | 0030 | Replace Steer/Gear-A Isolator MoC-55775 (100037173) | START,P756005A (AB50.03MS756005A) | Isolate Supply (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135725 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013572545400000100037173 | #N/A | 0000135725000100037173 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | INLEC |  | 100037307 | 0010 | Replace Galley 05MCC400101 Feeder Module (100037307) | FEEDER,LV MOD 05MCC400101 SPARE MODULE (AB50.05MCC400101-B05C) | Isolate MCC and changeout CB (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135821 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013582145400000100037307 | #N/A | 0000135821000100037307 |  |  | 0
24OKCM16 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-07 |  | 2024-04-18 | 2024-04-19 | MECH |  | 100037513 | 0020 | Bosun - CLASS - Repl Port Filter Housing (100037513) | DAMP,SUPPLY AIR,BOSUN STORE (AB50.04HDR680855A) | Install replacement filter housing (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 100 | 0 | 0 | OK. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136037 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2023-12-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013603745298000100037513 | #N/A | 0000136037000100037513 |  |  | 0
24OKCM16 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-07 |  | 2024-04-18 | 2024-04-19 | MECH |  | 100037513 | 0010 | Bosun - CLASS - Repl Port Filter Housing (100037513) | DAMP,SUPPLY AIR,BOSUN STORE (AB50.04HDR680855A) | Install replacement filter housing (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136037 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2023-12-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013603745298000100037513 | #N/A | 0000136037000100037513 |  |  | 0
24OKCM16 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-07 |  | 2024-04-18 | 2024-04-19 | MECH |  | 100037513 | 0030 | Bosun - CLASS - Repl Port Filter Housing (100037513) | DAMP,SUPPLY AIR,BOSUN STORE (AB50.04HDR680855A) | Install replacement filter housing (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 8 | 0 | 0 | OK. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136037 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2023-12-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013603745298000100037513 | #N/A | 0000136037000100037513 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-26 | REFURB |  | 100037555 | 0050 | MOD7 - Repl Spool CG-5130339 CDR-29137 (100037555) | LOOP,CORROSION, DEHYDRATION (AB50.05B02-CG01) | replace spool (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 8 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136067 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013606745406000100037555 | #N/A | 0000136067000100037555 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-26 | REFURB |  | 100037555 | 0020 | MOD7 - Repl Spool CG-5130339 CDR-29137 (100037555) | LOOP,CORROSION, DEHYDRATION (AB50.05B02-CG01) | replace spool (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136067 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013606745406000100037555 | #N/A | 0000136067000100037555 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-26 | REFURB |  | 100037555 | 0090 | MOD7 - Repl Spool CG-5130339 CDR-29137 (100037555) | LOOP,CORROSION, DEHYDRATION (AB50.05B02-CG01) | replace spool (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136067 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013606745406000100037555 | #N/A | 0000136067000100037555 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-26 | REFURB |  | 100037555 | 0030 | MOD7 - Repl Spool CG-5130339 CDR-29137 (100037555) | LOOP,CORROSION, DEHYDRATION (AB50.05B02-CG01) | replace spool (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136067 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013606745406000100037555 | #N/A | 0000136067000100037555 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-26 | REFURB |  | 100037555 | 0070 | MOD7 - Repl Spool CG-5130339 CDR-29137 (100037555) | LOOP,CORROSION, DEHYDRATION (AB50.05B02-CG01) | replace spool (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136067 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013606745406000100037555 | #N/A | 0000136067000100037555 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-24 |  | 2024-04-24 | 2024-04-24 | INLEC |  | 100037559 | 0010 | Repl Light Fitting MOD7 Cargo/D Port/S (100037559) | LIGHT,FLUOR,JN414-5102 (AB50.05LT400102R7605) | Replace light fitting (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136071 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-09-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013607145406000100037559 | #N/A | 0000136071000100037559 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0320 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 31 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0100 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 11 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0240 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 25 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0140 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 15 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0200 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 21 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0030 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0130 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 14 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0110 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 12 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0010 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | Solar Mars 100-15000 GP&PT ENGINE OVERHA (0150) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 37 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0160 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 17 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0020 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 3 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0330 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 32 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0260 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 27 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0060 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 7 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0130 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 14 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0040 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 5 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0150 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 16 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-02-18 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0370 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | CRANE ASSIST (0140) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 36 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | GT2 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-01-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845340000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0140 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 15 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0240 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 25 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0170 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 18 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0250 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 26 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0270 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 28 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0070 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 8 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0090 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | DR |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 10 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0190 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 20 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0100 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 11 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0180 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 19 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0080 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 9 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0290 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 5 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 29 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0050 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 6 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0320 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 31 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0200 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 21 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0310 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 30 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-25 |  | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0030 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | CONFIRM ISOLATION OF GT2 SYSTEM (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 2 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2023-12-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013616145316000100037577 | #N/A | 0000136161000100037577 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-25 |  | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0080 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | CONFIRM ISOLATION OF GT2 SYSTEM (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 6 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2023-12-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013616145316000100037577 | #N/A | 0000136161000100037577 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-25 |  | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0060 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | CONFIRM ISOLATION OF GT2 SYSTEM (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 6 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2023-12-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013616145316000100037577 | #N/A | 0000136161000100037577 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-25 |  | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0070 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | CONFIRM ISOLATION OF GT2 SYSTEM (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 8 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2023-12-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013616145316000100037577 | #N/A | 0000136161000100037577 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-25 |  | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0040 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | CONFIRM ISOLATION OF GT2 SYSTEM (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 6 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2023-12-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013616145316000100037577 | #N/A | 0000136161000100037577 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-25 |  | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0050 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | CONFIRM ISOLATION OF GT2 SYSTEM (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 4 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2023-12-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013616145316000100037577 | #N/A | 0000136161000100037577 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-01-27 |  | 2024-01-27 | 2024-01-28 | MECH |  | 100037577 | 0090 | Replace GT2 Lube Oil (100037577) | TURB,GT400002 TURBINE (AB50.05GT400002) | TAKE SAMPLE AFt 24HRS RUNNING (0060) | AB50 | [5 empty] | 30 | 30 |  |  | 2 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136161 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2023-12-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013616145318000100037577 | #N/A | 0000136161000100037577 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-11 |  | 2024-05-09 | 2024-05-12 | PAINT |  | 100037796 | 0010 | CT2 - CLASS - Coating 2SCOT AN006 Pittng (100037796) | TANK,CRUDE OIL STORAGE,NO 2 STBD (AB50.COT2-SB) | Apply Belzona + Coatings (0040) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000136297 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-13 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013629745423000100037796 | #N/A | 0000136297000100037796 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 |  | 2024-04-25 | 2024-04-26 | REFURB |  | 100037864 | 0020 | MOD7 - HSE10 Install Bump Protect T1024 (100037864) | VE,GLYCOL CONTACTOR (AB50.05V130002) | Install bump protection Mod7 (0020) | AB50 | [5 empty] | 30 | 30 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136345 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | PK_STAGING |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013634545407000100037864 | #N/A | 0000136345000100037864 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 |  | 2024-04-25 | 2024-04-26 | REFURB |  | 100037864 | 0040 | MOD7 - HSE10 Install Bump Protect T1024 (100037864) | VE,GLYCOL CONTACTOR (AB50.05V130002) | Install bump protection Mod7 (0020) | AB50 | [5 empty] | 30 | 30 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136345 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013634545407000100037864 | #N/A | 0000136345000100037864 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0120 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013634745416000100037866 | #N/A | 0000136347000100037866 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0140 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013634745416000100037866 | #N/A | 0000136347000100037866 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0130 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-04-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013634745416000100037866 | #N/A | 0000136347000100037866 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-22 |  | 2024-04-22 | 2024-04-22 | MECH |  | 100038083 | 0020 | Repl FWD Servo Winch Pp Oil & Filter (100038083) | PUMP,SERVO,WINCH CTRL FWD (AB50.03P756007) | Repl FWD Servo Winch Pp Oil & Filters (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 10 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136457 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-23 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-25 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013645745404000100038083 | #N/A | 0000136457000100038083 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-22 |  | 2024-04-22 | 2024-04-22 | MECH |  | 100038083 | 0010 | Repl FWD Servo Winch Pp Oil & Filter (100038083) | PUMP,SERVO,WINCH CTRL FWD (AB50.03P756007) | Repl FWD Servo Winch Pp Oil & Filters (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136457 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-23 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-25 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013645745404000100038083 | #N/A | 0000136457000100038083 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-31 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0230 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install Air Motor Control valve & tubing (0100) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 22 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | OEGMN01969 |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945382000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0040 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-31 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0240 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install Air Motor Control valve & tubing (0100) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 23 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | OKHAEC |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945382000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0210 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 21 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0030 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0050 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0060 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 8 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0070 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0080 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 8 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0020 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0090 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 10 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0100 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 10 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0010 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0110 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 11 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0120 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 12 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0130 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 10 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 13 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0200 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 20 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0190 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 19 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0180 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 5 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 18 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0170 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 5 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 17 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0160 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 16 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0150 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 15 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-29 |  | 2024-03-29 | 2024-04-03 | MECH |  | 100038185 | 0140 | Install New Air Motor - Spooler Door (100038185) | HOSEREEL,OFFLOADING HOSE (AB50.03A020100) | Install New Motor Assembly & Contr VLV (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136689 | 14 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Offtake Hose Reel |  | 0 | 0 | 2023-06-28 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.043478 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013668945380000100038185 | #N/A | 0000136689000100038185 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-14 | INLEC |  | 100038291 | 0010 | Replace Motor FGC Condensate Pp-A (100038291) | PUMP,FGC CONDENSATE A (AB50.05P041101A) | Isolate & Disconnect Motor for removal (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000136823 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013682345421000100038291 | #N/A | 0000136823000100038291 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-14 | MECH |  | 100038587 | 0010 | Paint hot bolt LGC1 flame arrestor bolts (100038587) | ARREST,LGC A,VENT 2ND SEAL GAS (AB50.05SP623004) | Build Scaffold (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 32 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137088 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013708845421000100038587 | #N/A | 0000137088000100038587 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-12 |  | 2024-05-09 | 2024-05-14 | MECH |  | 100038587 | 0050 | Paint hot bolt LGC1 flame arrestor bolts (100038587) | ARREST,LGC A,VENT 2ND SEAL GAS (AB50.05SP623004) | Hot Bolt Bolts where required (0030) | AB50 | [5 empty] | 20 | 20 |  |  | 12 | 0 | 0 | OK. - STAAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137088 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013708845424000100038587 | #N/A | 0000137088000100038587 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0030 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0020 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0060 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0010 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0110 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 11 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0100 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 10 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0070 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0080 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 8 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0040 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0050 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-10 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100038602 | 0090 | Overhaul P/Water Pp (100038602) | PUMP,PROD WTR A (AB50.05P450001A) | OVERHAUL PUMP BEARINGS (0050) | AB50 | [5 empty] | 10 | 10 |  |  | 12 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137106 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-04-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.071429 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013710645422000100038602 | #N/A | 0000137106000100038602 |  |  | 0
24OKCM16 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-02-15 |  | 2024-02-15 | 2024-02-19 | MECH |  | 100038738 | 0050 | Repl. Monoflanges SS Fitng to CS Flange (100038738) | VALVE,PDG043121,MAN ISOL (AB50.05MV043040) | Isolate and purge LGC1 Train (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 8 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137259 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-01-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013725945337000100038738 | #N/A | 0000137259000100038738 |  |  | 0
24OKCM16 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-02-15 |  | 2024-02-15 | 2024-02-19 | MECH |  | 100038738 | 0040 | Repl. Monoflanges SS Fitng to CS Flange (100038738) | VALVE,PDG043121,MAN ISOL (AB50.05MV043040) | Isolate and purge LGC1 Train (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137259 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-01-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013725945337000100038738 | #N/A | 0000137259000100038738 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-13 | CRANE |  | 100038739 | 0020 | Replace HPU level sight glass (100038739) | GAUGE,X790001-AMD2023, LEVEL (AB50.05X790001-YMD8790) | Replace hyd tank level sight glass - aft (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | TB |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137260 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013726045421000100038739 | #N/A | 0000137260000100038739 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-10 |  | 2024-05-09 | 2024-05-12 | MECH |  | 100038806 | 0040 | MOC110643 LGC1 Upgrade ASV Act Stem (100038806) | VALVE,K043300,SURGE CTRL (AB50.05FCV043103) | INSTALL NEW COMPONENTS IN ACTUATOR (0040) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137307 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013730745422000100038806 | #N/A | 0000137307000100038806 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 |  | 2024-04-25 | 2024-04-28 | MECH |  | 100038807 | 0080 | MOC110643 EGC2 Upgrade ASV Act Stem (100038807) | VALVE,FIC042503,ANTI-SURGE CTRL (AB50.05FCV042503) | INSTALL NEW COMPONENTS IN 05FCV042508 (0090) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137308 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013730845407000100038807 | #N/A | 0000137308000100038807 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-01 |  | 2024-03-29 | 2024-04-03 | PAINT |  | 100038880 | 0050 | CT2 - 2WBT STBD FWD Ramp Blast & Replace (100038880) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 7 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137381 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738145383000100038880 | #N/A | 0000137381000100038880 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-02 |  | 2024-03-29 | 2024-04-03 | PAINT |  | 100038880 | 0010 | CT2 - 2WBT STBD FWD Ramp Blast & Replace (100038880) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137381 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738145384000100038880 | #N/A | 0000137381000100038880 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-02 |  | 2024-03-29 | 2024-04-03 | PAINT |  | 100038880 | 0020 | CT2 - 2WBT STBD FWD Ramp Blast & Replace (100038880) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137381 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738145384000100038880 | #N/A | 0000137381000100038880 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-02 |  | 2024-03-29 | 2024-04-03 | PAINT |  | 100038880 | 0030 | CT2 - 2WBT STBD FWD Ramp Blast & Replace (100038880) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137381 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738145384000100038880 | #N/A | 0000137381000100038880 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-01 |  | 2024-03-29 | 2024-04-03 | PAINT |  | 100038880 | 0040 | CT2 - 2WBT STBD FWD Ramp Blast & Replace (100038880) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | 0312 - ETA Vendor PO#W451768705 - Procurement Chasing. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137381 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738145383000100038880 | #N/A | 0000137381000100038880 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-02 |  | 2024-03-29 | 2024-04-03 | PAINT |  | 100038880 | 0060 | CT2 - 2WBT STBD FWD Ramp Blast & Replace (100038880) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137381 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738145384000100038880 | #N/A | 0000137381000100038880 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-11 | 2024-04-16 | PAINT |  | 100038883 | 0020 | CT4 - 4WBT PORT AFT Ramp Blast & Replace (100038883) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | ETA. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137384 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738445397000100038883 | #N/A | 0000137384000100038883 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-14 |  | 2024-04-11 | 2024-04-16 | PAINT |  | 100038883 | 0040 | CT4 - 4WBT PORT AFT Ramp Blast & Replace (100038883) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137384 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-17 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738445396000100038883 | #N/A | 0000137384000100038883 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-14 |  | 2024-04-11 | 2024-04-16 | PAINT |  | 100038883 | 0050 | CT4 - 4WBT PORT AFT Ramp Blast & Replace (100038883) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137384 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-17 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738445396000100038883 | #N/A | 0000137384000100038883 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-11 | 2024-04-16 | PAINT |  | 100038883 | 0010 | CT4 - 4WBT PORT AFT Ramp Blast & Replace (100038883) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137384 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738445397000100038883 | #N/A | 0000137384000100038883 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-11 | 2024-04-16 | PAINT |  | 100038883 | 0030 | CT4 - 4WBT PORT AFT Ramp Blast & Replace (100038883) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137384 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738445397000100038883 | #N/A | 0000137384000100038883 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-11 | 2024-04-16 | PAINT |  | 100038883 | 0060 | CT4 - 4WBT PORT AFT Ramp Blast & Replace (100038883) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137384 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738445397000100038883 | #N/A | 0000137384000100038883 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-09 |  | 2024-04-06 | 2024-04-12 | PAINT |  | 100038887 | 0040 | CT2 - 2COT PORT X-Over Ramp Blst&Replace (100038887) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137388 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738845391000100038887 | #N/A | 0000137388000100038887 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-09 |  | 2024-04-06 | 2024-04-12 | PAINT |  | 100038887 | 0050 | CT2 - 2COT PORT X-Over Ramp Blst&Replace (100038887) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137388 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738845391000100038887 | #N/A | 0000137388000100038887 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-11 |  | 2024-04-06 | 2024-04-12 | PAINT |  | 100038887 | 0030 | CT2 - 2COT PORT X-Over Ramp Blst&Replace (100038887) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137388 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738845393000100038887 | #N/A | 0000137388000100038887 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-11 |  | 2024-04-06 | 2024-04-12 | PAINT |  | 100038887 | 0020 | CT2 - 2COT PORT X-Over Ramp Blst&Replace (100038887) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137388 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738845393000100038887 | #N/A | 0000137388000100038887 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-11 |  | 2024-04-06 | 2024-04-12 | PAINT |  | 100038887 | 0060 | CT2 - 2COT PORT X-Over Ramp Blst&Replace (100038887) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | 0312 - ETA Vendor PO#W451768705 - Procurement Chasing. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137388 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738845393000100038887 | #N/A | 0000137388000100038887 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-11 |  | 2024-04-06 | 2024-04-12 | PAINT |  | 100038887 | 0010 | CT2 - 2COT PORT X-Over Ramp Blst&Replace (100038887) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137388 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738845393000100038887 | #N/A | 0000137388000100038887 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-04 | 2024-04-09 | PAINT |  | 100038888 | 0030 | CT2 - 2COT STBD X-Over Ramp Blst&Replace (100038888) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137389 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738945390000100038888 | #N/A | 0000137389000100038888 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-04 | 2024-04-09 | PAINT |  | 100038888 | 0060 | CT2 - 2COT STBD X-Over Ramp Blst&Replace (100038888) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137389 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738945390000100038888 | #N/A | 0000137389000100038888 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-07 |  | 2024-04-04 | 2024-04-09 | PAINT |  | 100038888 | 0040 | CT2 - 2COT STBD X-Over Ramp Blst&Replace (100038888) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | 0312 - ETA Vendor PO#W451768705 - Procurement Chasing. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137389 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738945389000100038888 | #N/A | 0000137389000100038888 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-07 |  | 2024-04-04 | 2024-04-09 | PAINT |  | 100038888 | 0050 | CT2 - 2COT STBD X-Over Ramp Blst&Replace (100038888) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137389 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738945389000100038888 | #N/A | 0000137389000100038888 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-04 | 2024-04-09 | PAINT |  | 100038888 | 0010 | CT2 - 2COT STBD X-Over Ramp Blst&Replace (100038888) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137389 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738945390000100038888 | #N/A | 0000137389000100038888 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-04 | 2024-04-09 | PAINT |  | 100038888 | 0020 | CT2 - 2COT STBD X-Over Ramp Blst&Replace (100038888) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137389 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013738945390000100038888 | #N/A | 0000137389000100038888 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-31 |  | 2024-03-29 | 2024-04-02 | PAINT |  | 100038890 | 0030 | CT4 - 4WBT PORT FWD Ramp Blast & Replace (100038890) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137391 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739145382000100038890 | #N/A | 0000137391000100038890 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-31 |  | 2024-03-29 | 2024-04-02 | PAINT |  | 100038890 | 0020 | CT4 - 4WBT PORT FWD Ramp Blast & Replace (100038890) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137391 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739145382000100038890 | #N/A | 0000137391000100038890 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-31 |  | 2024-03-29 | 2024-04-02 | PAINT |  | 100038890 | 0010 | CT4 - 4WBT PORT FWD Ramp Blast & Replace (100038890) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137391 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739145382000100038890 | #N/A | 0000137391000100038890 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-30 |  | 2024-03-29 | 2024-04-02 | PAINT |  | 100038890 | 0050 | CT4 - 4WBT PORT FWD Ramp Blast & Replace (100038890) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137391 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-02 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739145381000100038890 | #N/A | 0000137391000100038890 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-30 |  | 2024-03-29 | 2024-04-02 | PAINT |  | 100038890 | 0040 | CT4 - 4WBT PORT FWD Ramp Blast & Replace (100038890) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137391 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-02 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739145381000100038890 | #N/A | 0000137391000100038890 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-31 |  | 2024-03-29 | 2024-04-02 | PAINT |  | 100038890 | 0060 | CT4 - 4WBT PORT FWD Ramp Blast & Replace (100038890) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | 0312 - ETA Vendor PO#W451768705 - Procurement Chasing. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137391 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739145382000100038890 | #N/A | 0000137391000100038890 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-16 |  | 2024-04-13 | 2024-04-19 | PAINT |  | 100038891 | 0040 | CT5 - 5COT PORT X-Over Ramp Blst&Replace (100038891) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137392 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-19 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739245398000100038891 | #N/A | 0000137392000100038891 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-17 |  | 2024-04-13 | 2024-04-19 | PAINT |  | 100038891 | 0060 | CT5 - 5COT PORT X-Over Ramp Blst&Replace (100038891) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | 0312 - ETA Vendor PO#W451768705 - Procurement Chasing. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CQ |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137392 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-20 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739245399000100038891 | #N/A | 0000137392000100038891 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-17 |  | 2024-04-13 | 2024-04-19 | PAINT |  | 100038891 | 0030 | CT5 - 5COT PORT X-Over Ramp Blst&Replace (100038891) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137392 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-20 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739245399000100038891 | #N/A | 0000137392000100038891 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-17 |  | 2024-04-13 | 2024-04-19 | PAINT |  | 100038891 | 0020 | CT5 - 5COT PORT X-Over Ramp Blst&Replace (100038891) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137392 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-20 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739245399000100038891 | #N/A | 0000137392000100038891 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-16 |  | 2024-04-13 | 2024-04-19 | PAINT |  | 100038891 | 0050 | CT5 - 5COT PORT X-Over Ramp Blst&Replace (100038891) | STRUC,VESSEL DECKING (AB50.03DECK01) | Install FRP Panels to Frame (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137392 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-19 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739245398000100038891 | #N/A | 0000137392000100038891 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-17 |  | 2024-04-13 | 2024-04-19 | PAINT |  | 100038891 | 0010 | CT5 - 5COT PORT X-Over Ramp Blst&Replace (100038891) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000137392 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-20 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013739245399000100038891 | #N/A | 0000137392000100038891 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-25 | 2024-05-01 | REFURB |  | 100038989 | 0050 | RTM - Refurbish Gas Detector Brackets (100038989) | DET,FZ0445,GAS IR LOS RECEIVER (AB50.0445GRX871002) | Hand Prep & Paint (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 60 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137493 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013749345408000100038989 | #N/A | 0000137493000100038989 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-25 | 2024-05-01 | REFURB |  | 100038989 | 0060 | RTM - Refurbish Gas Detector Brackets (100038989) | DET,FZ0445,GAS IR LOS RECEIVER (AB50.0445GRX871002) | Hand Prep & Paint (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 10 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137493 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013749345408000100038989 | #N/A | 0000137493000100038989 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-25 | 2024-05-01 | REFURB |  | 100038989 | 0070 | RTM - Refurbish Gas Detector Brackets (100038989) | DET,FZ0445,GAS IR LOS RECEIVER (AB50.0445GRX871002) | Hand Prep & Paint (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | SHT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137493 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013749345408000100038989 | #N/A | 0000137493000100038989 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-25 | 2024-05-01 | REFURB |  | 100038989 | 0080 | RTM - Refurbish Gas Detector Brackets (100038989) | DET,FZ0445,GAS IR LOS RECEIVER (AB50.0445GRX871002) | Hand Prep & Paint (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 16 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137493 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013749345408000100038989 | #N/A | 0000137493000100038989 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-25 | 2024-05-01 | REFURB |  | 100038989 | 0020 | RTM - Refurbish Gas Detector Brackets (100038989) | DET,FZ0445,GAS IR LOS RECEIVER (AB50.0445GRX871002) | Hand Prep & Paint (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | BOX |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137493 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013749345408000100038989 | #N/A | 0000137493000100038989 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-25 | 2024-05-01 | REFURB |  | 100038989 | 0040 | RTM - Refurbish Gas Detector Brackets (100038989) | DET,FZ0445,GAS IR LOS RECEIVER (AB50.0445GRX871002) | Hand Prep & Paint (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | BOX |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137493 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013749345408000100038989 | #N/A | 0000137493000100038989 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-25 | 2024-05-01 | REFURB |  | 100038989 | 0030 | RTM - Refurbish Gas Detector Brackets (100038989) | DET,FZ0445,GAS IR LOS RECEIVER (AB50.0445GRX871002) | Hand Prep & Paint (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 30 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137493 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013749345408000100038989 | #N/A | 0000137493000100038989 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-19 |  | 2024-04-18 | 2024-04-21 | MECH |  | 100039000 | 0030 | Paint Prod/W Pump-B Base (100039000) | MOTOR,P450001B,PROD WTR PUMP DRIVER (AB50.05PM450001B) | Install Motor/Coulping And Re-align (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 20 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137452 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013745245401000100039000 | #N/A | 0000137452000100039000 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-19 |  | 2024-04-18 | 2024-04-21 | MECH |  | 100039000 | 0020 | Paint Prod/W Pump-B Base (100039000) | MOTOR,P450001B,PROD WTR PUMP DRIVER (AB50.05PM450001B) | Install Motor/Coulping And Re-align (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137452 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013745245401000100039000 | #N/A | 0000137452000100039000 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-19 |  | 2024-04-18 | 2024-04-21 | MECH |  | 100039000 | 0040 | Paint Prod/W Pump-B Base (100039000) | MOTOR,P450001B,PROD WTR PUMP DRIVER (AB50.05PM450001B) | Install Motor/Coulping And Re-align (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137452 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013745245401000100039000 | #N/A | 0000137452000100039000 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-20 |  | 2024-04-18 | 2024-04-21 | MECH |  | 100039000 | 0060 | Paint Prod/W Pump-B Base (100039000) | MOTOR,P450001B,PROD WTR PUMP DRIVER (AB50.05PM450001B) | Denzo Tape Jacking Bolts (0100) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137452 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-23 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013745245402000100039000 | #N/A | 0000137452000100039000 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-19 |  | 2024-04-18 | 2024-04-21 | MECH |  | 100039000 | 0010 | Paint Prod/W Pump-B Base (100039000) | MOTOR,P450001B,PROD WTR PUMP DRIVER (AB50.05PM450001B) | Install Motor/Coulping And Re-align (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137452 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013745245401000100039000 | #N/A | 0000137452000100039000 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-19 |  | 2024-04-18 | 2024-04-21 | MECH |  | 100039000 | 0070 | Paint Prod/W Pump-B Base (100039000) | MOTOR,P450001B,PROD WTR PUMP DRIVER (AB50.05PM450001B) | Install Motor/Coulping And Re-align (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 8 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137452 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013745245401000100039000 | #N/A | 0000137452000100039000 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-19 |  | 2024-04-18 | 2024-04-21 | MECH |  | 100039000 | 0050 | Paint Prod/W Pump-B Base (100039000) | MOTOR,P450001B,PROD WTR PUMP DRIVER (AB50.05PM450001B) | Install Motor/Coulping And Re-align (0070) | AB50 | [5 empty] | 20 | 20 |  |  | 12 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137452 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-22 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013745245401000100039000 | #N/A | 0000137452000100039000 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-01 |  | 2024-03-31 | 2024-04-02 | PAINT |  | 100039195 | 0010 | CT6 - 6COT PORT AFT Ramp Blast & Paint (100039195) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp / Frame (0030) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137719 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013771945383000100039195 | #N/A | 0000137719000100039195 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-01 |  | 2024-03-31 | 2024-04-02 | PAINT |  | 100039195 | 0020 | CT6 - 6COT PORT AFT Ramp Blast & Paint (100039195) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Coatings to Ramp / Frame (0030) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | UserCommentLink | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137719 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Paint Team |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013771945383000100039195 | #N/A | 0000137719000100039195 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0070 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 3 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | PAC |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013804545421000100039544 | #N/A | 0000138045000100039544 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 100039544 | 0060 | Replace GT1 external exhaust bellows (100039544) | PKG EQ,MAIN GEN 1 (AB50.05A400001) | ISOLATE GT1 PACKAGE (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 130 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138045 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-11-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013804545421000100039544 | #N/A | 0000138045000100039544 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-18 | 2024-04-22 | INLEC |  | 100039819 | 0010 | "Earth Boss refurb, Riser, RTM, RA, Swiv (100039819) | PKG EQ,EARTHING VESSEL (AB50.03EARTH01) | Earth Boss refurb, Riser, RTM, RA, Swive (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CAN |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000138300 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013830045400000100039819 | #N/A | 0000138300000100039819 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-01 |  | 2024-05-01 | 2024-05-02 | MECH |  | 100039933 | 0070 | Replace 5x Cargo HPU Accum Cylinders (100039933) | ACC,A090001,BACK-UP PRESS (AB50.03V090001) | REPLACE - AU05.03V090001 (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000138434 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013843445413000100039933 | #N/A | 0000138434000100039933 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-01 |  | 2024-05-01 | 2024-05-02 | MECH |  | 100039933 | 0030 | Replace 5x Cargo HPU Accum Cylinders (100039933) | ACC,A090001,BACK-UP PRESS (AB50.03V090001) | REPLACE - AU05.03V090002 (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000138434 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013843445413000100039933 | #N/A | 0000138434000100039933 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-01 |  | 2024-05-01 | 2024-05-02 | MECH |  | 100039933 | 0060 | Replace 5x Cargo HPU Accum Cylinders (100039933) | ACC,A090001,BACK-UP PRESS (AB50.03V090001) | REPLACE - AU05.03V090005 (0050) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000138434 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013843445413000100039933 | #N/A | 0000138434000100039933 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-01 |  | 2024-05-01 | 2024-05-02 | MECH |  | 100039933 | 0040 | Replace 5x Cargo HPU Accum Cylinders (100039933) | ACC,A090001,BACK-UP PRESS (AB50.03V090001) | REPLACE - AU05.03V090003 (0030) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000138434 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013843445413000100039933 | #N/A | 0000138434000100039933 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-01 |  | 2024-05-01 | 2024-05-02 | MECH |  | 100039933 | 0050 | Replace 5x Cargo HPU Accum Cylinders (100039933) | ACC,A090001,BACK-UP PRESS (AB50.03V090001) | REPLACE - AU05.03V090004 (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000138434 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013843445413000100039933 | #N/A | 0000138434000100039933 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-03 |  | 2024-03-30 | 2024-04-08 | REFURB |  | 100040991 | 0060 | RA - HSE10 Install Bracket & Cable Tray (100040991) | TURRET,ELECTRICAL SWIVEL (AB50.04V098103) | Install bracket & cable tray (0030) | AB50 | [5 empty] | 20 | 20 |  |  | 8 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000139525 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-06 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013952545385000100040991 | #N/A | 0000139525000100040991 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-28 | MECH |  | 100043119 | 0030 | D - Replace EGC2 PDT Isol Valves (100043119) | VALVE,PDT460520,MAN ISOL (AB50.05MV460127) | Replace EGC2 PDT Isol Valves (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 16 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000141703 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2022-10-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014170345409000100043119 | #N/A | 0000141703000100043119 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0110 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014278245409000100044230 | #N/A | 0000142782000100044230 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0060 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 4 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014278245409000100044230 | #N/A | 0000142782000100044230 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0100 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 3 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014278245409000100044230 | #N/A | 0000142782000100044230 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0080 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014278245409000100044230 | #N/A | 0000142782000100044230 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0020 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014278245409000100044230 | #N/A | 0000142782000100044230 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 |  | 2024-04-27 | 2024-04-29 | MECH |  | 100044230 | 0130 | FP8 Replace 5x EGC2 Monoflanges (100044230) | VALVE,FT042508,MAN ISOL (AB50.05MV042445) | Replace Monoflange EGC 2 x 5 (0010) | AB50 | [5 empty] | 30 | 30 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000142782 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2021-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.090909 | 2024-03-30 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014278245409000100044230 | #N/A | 0000142782000100044230 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 |  | 2024-04-25 | 2024-04-25 | MECH |  | 100046259 | 0020 | "Replace monoflange @ 05MV042441, EGC2" (100046259) | VALVE,05MV042441,MAN ISOL (AB50.05MV042441) | Install Valve (0030) | AB50 | [5 empty] | 30 | 30 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000144760 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2021-06-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014476045407000100046259 | #N/A | 0000144760000100046259 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 |  | 2024-04-25 | 2024-04-25 | MECH |  | 100046259 | 0010 | "Replace monoflange @ 05MV042441, EGC2" (100046259) | VALVE,05MV042441,MAN ISOL (AB50.05MV042441) | Install Valve (0030) | AB50 | [5 empty] | 30 | 30 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000144760 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2021-06-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-28 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014476045407000100046259 | #N/A | 0000144760000100046259 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | FAEN |  | 100046363 | 0010 | Decommission BS&W System MOC-80559 (100046363) | ANLZ,HP SEPARATOR FAST LOOP (AB50.05AT020171) | Geoff D, Raise MOC to decommissio (0010) | AB50 | [5 empty] | 255 | 99 |  |  | 12 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000144847 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2020-04-12 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000014484745400000100046363 | #N/A | 0000144847000100046363 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-11 | MECH |  | 200061999 | 0040 | 6M SOLAR MARS 100 MECH & ELEC SERV/INSP (200061999) | TURB,GT400001 TURBINE (AB50.05GT400001) | SERVICE & INSPECT SOLAR TURBINE (0040) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000096341 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-08-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000009634145421000200061999 | #N/A | 0000096341000200061999 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-06 |  | 2024-04-06 | 2024-04-06 | MECH |  | 200075652 | 0020 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075652) | EXT FIRE,FOAM APPL,9L,ENG ROOM FLAT AFT (AB50.03EXAF010) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 6 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110008 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-09 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011000845388000200075652 | #N/A | 0000110008000200075652 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-06 |  | 2024-04-06 | 2024-04-06 | MECH |  | 200075652 | 0010 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075652) | EXT FIRE,FOAM APPL,9L,ENG ROOM FLAT AFT (AB50.03EXAF010) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110008 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-09 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011000845388000200075652 | #N/A | 0000110008000200075652 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-10 |  | 2024-04-10 | 2024-04-11 | MECH |  | 200075967 | 0020 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075967) | EXT FIRE,FOAM APPL,9L,EQUIP DECK1 REFUGE (AB50.04EXAF015) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 3 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110303 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-13 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011030345392000200075967 | #N/A | 0000110303000200075967 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-10 |  | 2024-04-10 | 2024-04-11 | MECH |  | 200075967 | 0010 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075967) | EXT FIRE,FOAM APPL,9L,EQUIP DECK1 REFUGE (AB50.04EXAF015) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110303 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-13 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011030345392000200075967 | #N/A | 0000110303000200075967 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-11 |  | 2024-04-11 | 2024-04-11 | MECH |  | 200075969 | 0030 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075969) | EXT FIRE,FOAM APPL,9L,EQUIP DECK2 FP RM (AB50.04EXAF017) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110304 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011030445393000200075969 | #N/A | 0000110304000200075969 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-11 |  | 2024-04-11 | 2024-04-11 | MECH |  | 200075969 | 0010 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075969) | EXT FIRE,FOAM APPL,9L,EQUIP DECK2 FP RM (AB50.04EXAF017) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110304 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011030445393000200075969 | #N/A | 0000110304000200075969 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-11 |  | 2024-04-11 | 2024-04-11 | MECH |  | 200075969 | 0020 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075969) | EXT FIRE,FOAM APPL,9L,EQUIP DECK2 FP RM (AB50.04EXAF017) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110304 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011030445393000200075969 | #N/A | 0000110304000200075969 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-11 |  | 2024-04-11 | 2024-04-11 | MECH |  | 200075970 | 0010 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075970) | EXT FIRE,FOAM APPL,9L,EQIP DK3 DISC HPU (AB50.04EXAF018) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110306 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011030645393000200075970 | #N/A | 0000110306000200075970 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-11 |  | 2024-04-11 | 2024-04-11 | MECH |  | 200075970 | 0020 | 5Y PORTABLE FIRE EXT REPLACEMENT (200075970) | EXT FIRE,FOAM APPL,9L,EQIP DK3 DISC HPU (AB50.04EXAF018) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000110306 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011030645393000200075970 | #N/A | 0000110306000200075970 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 200078320 | 0050 | 1Y LUBE OIL PURIFIER OVERHAUL A (200078320) | PKG EQ,LO PURIFIER A (AB50.03A755790) | ISOLATIONS OF LUBE OIL PURIFIER (0020) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000112609 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-26 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011260945421000200078320 | #N/A | 0000112609000200078320 |  |  | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-15 | MECH |  | 200078320 | 0010 | 1Y LUBE OIL PURIFIER OVERHAUL A (200078320) | PKG EQ,LO PURIFIER A (AB50.03A755790) | ISOLATIONS OF LUBE OIL PURIFIER (0020) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000112609 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-06-26 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011260945421000200078320 | #N/A | 0000112609000200078320 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-06 |  | 2024-03-04 | 2024-04-13 | MAMA |  | 200079030 | 0010 | 5Y P21 INTERNAL CLASS INSPECTION A (200079030) | TANK,WTR BALLAST NO 6 PORT (AB50.WBT6PS) | REPLACE HATCHES (0060) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000113312 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-01-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-07 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011331245357000200079030 | #N/A | 0000113312000200079030 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-06 |  | 2024-03-04 | 2024-04-13 | MAMA |  | 200079030 | 0020 | 5Y P21 INTERNAL CLASS INSPECTION A (200079030) | TANK,WTR BALLAST NO 6 PORT (AB50.WBT6PS) | REPLACE HATCHES (0060) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000113312 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-01-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-07 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011331245357000200079030 | #N/A | 0000113312000200079030 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-22 | 2024-04-25 | INSP |  | 200082341 | 0060 | 5Y INT INSP/CLASS SURVEY 03E753050 (200082341) | VE,ATMOSPHERIC CONDENSER (AB50.03E753050) | RE-INSTATE SPOOL/HEAD POST INSPECTION (0060) | AB50 | [5 empty] | 10 | 5 |  |  | 8 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118169 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-05-20 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011816945406000200082341 | #N/A | 0000118169000200082341 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 |  | 2024-05-01 | 2024-05-03 | MECH |  | 200082368 | 0050 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200082368) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 | [5 empty] | 10 | 10 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118281 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-08-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011828145414000200082368 | #N/A | 0000118281000200082368 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 |  | 2024-05-01 | 2024-05-03 | MECH |  | 200082368 | 0020 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200082368) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118281 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-08-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011828145414000200082368 | #N/A | 0000118281000200082368 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 |  | 2024-05-01 | 2024-05-03 | MECH |  | 200082368 | 0040 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200082368) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000118281 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-08-05 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011828145414000200082368 | #N/A | 0000118281000200082368 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-03-28 | INLEC |  | 200083034 | 0010 | 6M F19 WC FIR SUP SYS INS&TST(CLASS) (200083034) | PANEL,WET CHEMICAL RELEASE (AB50.03CP606001) | INSP WET CHEM FIRE SUPRESN SYS (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | ISSUE. - Possibly cannot find in location - 71070063 SW1R39L02A | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000119896 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-05-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000011989645379000200083034 | #N/A | 0000119896000200083034 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-05 |  | 2024-04-05 | 2024-04-08 | MECH |  | 200083257 | 0030 | 5Y PORTABLE FIRE EXT REPLACEMENT (200083257) | EXT FIRE,DP,9KG,B DECK FWD (AB50.05EXP017) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120455 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-05-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012045545387000200083257 | #N/A | 0000120455000200083257 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-05 |  | 2024-04-05 | 2024-04-08 | MECH |  | 200083257 | 0020 | 5Y PORTABLE FIRE EXT REPLACEMENT (200083257) | EXT FIRE,DP,9KG,B DECK FWD (AB50.05EXP017) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 35 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120455 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-05-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012045545387000200083257 | #N/A | 0000120455000200083257 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-05 |  | 2024-04-05 | 2024-04-08 | MECH |  | 200083257 | 0010 | 5Y PORTABLE FIRE EXT REPLACEMENT (200083257) | EXT FIRE,DP,9KG,B DECK FWD (AB50.05EXP017) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 15 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120455 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-05-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012045545387000200083257 | #N/A | 0000120455000200083257 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-10 |  | 2024-04-10 | 2024-04-11 | MECH |  | 200083535 | 0030 | 1Y BA COMPRESSOR INSPECTION & SERVICE (200083535) | COMPR,BREATHING AIR (AB50.03K600010) | CONDUCT SERVICE OF BA COMPRESSOR (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121112 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-13 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012111245392000200083535 | #N/A | 0000121112000200083535 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | MECH |  | 200083546 | 0050 | 1Y P23 INSP/LUBE OF TURRET MAIN BRG GEAR (200083546) | STRUC,MAIN ROLLER BEARING (AB50.BB0113) | INSPECT & LUBE ORIENTATION GEARING (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121088 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-08 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012108845397000200083546 | #N/A | 0000121088000200083546 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | MECH |  | 200083546 | 0010 | 1Y P23 INSP/LUBE OF TURRET MAIN BRG GEAR (200083546) | STRUC,MAIN ROLLER BEARING (AB50.BB0113) | INSPECT & LUBE ORIENTATION GEARING (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | PAI |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121088 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-08 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012108845397000200083546 | #N/A | 0000121088000200083546 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | MECH |  | 200083546 | 0030 | 1Y P23 INSP/LUBE OF TURRET MAIN BRG GEAR (200083546) | STRUC,MAIN ROLLER BEARING (AB50.BB0113) | INSPECT & LUBE ORIENTATION GEARING (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | DR |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121088 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-08 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012108845397000200083546 | #N/A | 0000121088000200083546 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | MECH |  | 200083546 | 0040 | 1Y P23 INSP/LUBE OF TURRET MAIN BRG GEAR (200083546) | STRUC,MAIN ROLLER BEARING (AB50.BB0113) | INSPECT & LUBE ORIENTATION GEARING (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121088 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-08 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012108845397000200083546 | #N/A | 0000121088000200083546 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | MECH |  | 200083546 | 0060 | 1Y P23 INSP/LUBE OF TURRET MAIN BRG GEAR (200083546) | STRUC,MAIN ROLLER BEARING (AB50.BB0113) | INSPECT & LUBE ORIENTATION GEARING (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | BAG |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121088 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-08 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012108845397000200083546 | #N/A | 0000121088000200083546 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | MECH |  | 200083546 | 0020 | 1Y P23 INSP/LUBE OF TURRET MAIN BRG GEAR (200083546) | STRUC,MAIN ROLLER BEARING (AB50.BB0113) | INSPECT & LUBE ORIENTATION GEARING (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | ISSUE. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | DR |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000121088 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-08 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-18 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012108845397000200083546 | #N/A | 0000121088000200083546 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0040 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0060 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0050 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0090 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0020 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0070 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0010 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0030 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-04-07 | 2024-04-07 | MECH |  | 200084026 | 0080 | 5Y PORTABLE FIRE EXT REPLACEMENT (200084026) | EXT FIRE,FOAM APPL,9L,2ND PLATF PURIF RM (AB50.03EXAF005) | REPLACE FIRE EXTINGUISHER (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122035 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012203545389000200084026 | #N/A | 0000122035000200084026 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 |  | 2024-04-04 | 2024-04-04 | INLEC |  | 200084031 | 0030 | 1Y RADAR MAGNETRON REPLACEMENT (200084031) | ANTENNA,S BAND ANTENNA (AB50.03CARD612806) | REMOVE & REPLACE RADAR MAGNETRON (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 3 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122040 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-07 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012204045386000200084031 | #N/A | 0000122040000200084031 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 |  | 2024-04-04 | 2024-04-04 | INLEC |  | 200084031 | 0020 | 1Y RADAR MAGNETRON REPLACEMENT (200084031) | ANTENNA,S BAND ANTENNA (AB50.03CARD612806) | REMOVE & REPLACE RADAR MAGNETRON (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 3 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122040 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-07 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012204045386000200084031 | #N/A | 0000122040000200084031 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-05-03 | 2024-05-11 | MECH |  | 200086050 | 0020 | 1Y E09 PS LIFEBOAT MAINTENANCE CHECKS (200086050) | LIFEBOAT,PORT SIDE LIFE BOAT,80 PERS (AB50.03A092001) | PERFORMING AUTHORITY & ASSIST VENDOR (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124279 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012427945415000200086050 | #N/A | 0000124279000200086050 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-05-03 | 2024-05-11 | MECH |  | 200086050 | 0030 | 1Y E09 PS LIFEBOAT MAINTENANCE CHECKS (200086050) | LIFEBOAT,PORT SIDE LIFE BOAT,80 PERS (AB50.03A092001) | PERFORMING AUTHORITY & ASSIST VENDOR (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124279 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012427945415000200086050 | #N/A | 0000124279000200086050 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-05-03 | 2024-05-11 | MECH |  | 200086050 | 0010 | 1Y E09 PS LIFEBOAT MAINTENANCE CHECKS (200086050) | LIFEBOAT,PORT SIDE LIFE BOAT,80 PERS (AB50.03A092001) | PERFORMING AUTHORITY & ASSIST VENDOR (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | M |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124279 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012427945415000200086050 | #N/A | 0000124279000200086050 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-04-24 | 2024-05-10 | MECH |  | 200086051 | 0030 | 1Y E09 SB LIFEBOAT MAINTENANCE CHECKS (200086051) | LIFEBOAT,STBD SIDE LIFE BOAT,80 PERS (AB50.03A092002) | PERFORMING AUTHORITY & ASSIST VENDOR (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124280 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012428045415000200086051 | #N/A | 0000124280000200086051 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-04-24 | 2024-05-10 | MECH |  | 200086051 | 0020 | 1Y E09 SB LIFEBOAT MAINTENANCE CHECKS (200086051) | LIFEBOAT,STBD SIDE LIFE BOAT,80 PERS (AB50.03A092002) | PERFORMING AUTHORITY & ASSIST VENDOR (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124280 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012428045415000200086051 | #N/A | 0000124280000200086051 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-04-24 | 2024-05-10 | MECH |  | 200086051 | 0010 | 1Y E09 SB LIFEBOAT MAINTENANCE CHECKS (200086051) | LIFEBOAT,STBD SIDE LIFE BOAT,80 PERS (AB50.03A092002) | PERFORMING AUTHORITY & ASSIST VENDOR (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | M |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124280 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012428045415000200086051 | #N/A | 0000124280000200086051 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-10 |  | 2024-05-09 | 2024-05-13 | HVAC |  | 200086290 | 0020 | 2Y REFRIG CHARGE & CONDENSER PRESS T/INS (200086290) | ACOND,CONDENSING UNIT RUNNING (AB50.03HP680011A) | Pressure Test condenser with nitrogen (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CYL |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124539 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-02-07 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012453945422000200086290 | #N/A | 0000124539000200086290 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-13 | HVAC |  | 200086290 | 0010 | 2Y REFRIG CHARGE & CONDENSER PRESS T/INS (200086290) | ACOND,CONDENSING UNIT RUNNING (AB50.03HP680011A) | Reclaim Refrigerant from condenser (0030) | AB50 | [5 empty] | 20 | 20 |  |  | 5 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124539 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-02-07 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012453945421000200086290 | #N/A | 0000124539000200086290 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | HVAC |  | 200086291 | 0010 | 3Y REPLACE COMPRESSOR SHAFT SEALS (200086291) | ACOND,CONDENSING UNIT RUNNING (AB50.03HP680011A) | Isolate Compressor Motor (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124540 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-02-07 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012454045421000200086291 | #N/A | 0000124540000200086291 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-03 | HVAC |  | 200086744 | 0010 | 1Y HVAC PACKAGE AC UNIT INSPECTION AER (200086744) | ACOND,CONDENSER OUTDOOR UNIT (AB50.03HP680010A) | VENDOR MAINTENANCE (0030) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124993 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-02-13 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-04 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012499345414000200086744 | #N/A | 0000124993000200086744 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-01 |  | 2024-05-01 | 2024-05-01 | HVAC |  | 200086747 | 0010 | 1Y HVAC PACKAGE AC UNIT INSPECTION CCR (200086747) | ACOND,CONDENSER OUTDOOR UNIT (AB50.03HP680013A) | VENDOR MAINTENANCE (0030) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000124996 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-02-12 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012499645413000200086747 | #N/A | 0000124996000200086747 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-01 |  | 2024-05-01 | 2024-05-01 | HVAC |  | 200086885 | 0010 | 1Y HVAC PCKG AC UNIT INSP TOPS STORAGE (200086885) | ACOND,FLOOR STANDNG FAN COIL INDOOR UNIT (AB50.03HP680592) | INSPECTION (0020) | AB50 | [5 empty] | 20 | 20 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000125154 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-02-12 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-03 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012515445413000200086885 | #N/A | 0000125154000200086885 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-10 |  | 2024-05-09 | 2024-05-13 | HVAC |  | 200087681 | 0010 | 2Y REFRIG CHARGE & CONDENSER PRESS T/INS (200087681) | ACOND,CONDENSING UNIT RUNNING (AB50.03HP680011B) | Pressure Test condenser with nitrogen (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 6 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | CYL |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000125870 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012587045422000200087681 | #N/A | 0000125870000200087681 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-13 | HVAC |  | 200087681 | 0020 | 2Y REFRIG CHARGE & CONDENSER PRESS T/INS (200087681) | ACOND,CONDENSING UNIT RUNNING (AB50.03HP680011B) | Reclaim Refrigerant from condenser (0030) | AB50 | [5 empty] | 20 | 20 |  |  | 5 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000125870 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012587045421000200087681 | #N/A | 0000125870000200087681 |  |  | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-10 | HVAC |  | 200087682 | 0010 | 3Y REPLACE COMPRESSOR SHAFT SEALS (200087682) | ACOND,CONDENSING UNIT RUNNING (AB50.03HP680011B) | Isolate Compressor Motor (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000125871 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-12-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012587145421000200087682 | #N/A | 0000125871000200087682 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-05-03 | 2024-05-06 | MECH |  | 200088430 | 0020 | 1Y E11 FRC INSPECTION AND SEA TRIALS (200088430) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | INSPECTION & SEA TRIAL OF FRC BOAT (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000126679 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012667945415000200088430 | #N/A | 0000126679000200088430 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-05-03 |  | 2024-05-03 | 2024-05-06 | MECH |  | 200088430 | 0010 | 1Y E11 FRC INSPECTION AND SEA TRIALS (200088430) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | INSPECTION & SEA TRIAL OF FRC BOAT (0010) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000126679 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-11-04 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012667945415000200088430 | #N/A | 0000126679000200088430 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-25 | MECH |  | 200089100 | 0020 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200089100) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000127318 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-08-11 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012731845406000200089100 | #N/A | 0000127318000200089100 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 |  | 2024-04-24 | 2024-04-25 | MECH |  | 200089100 | 0010 | 1Y INSP & MAINT OF GAS COMPRESSSOR 2 (200089100) | COMPR,A042210,GAS COMPRESSOR (AB50.05K042210) | CHANGE OUT SEAL GAS FILTER (0030) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000127318 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2023-08-11 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012731845406000200089100 | #N/A | 0000127318000200089100 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0280 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 3 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0500 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 11 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0330 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0190 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 25 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0150 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 5 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0510 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 2 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 12 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0130 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | KIT |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0350 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 40 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 10 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0200 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 24 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-02-17 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0030 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL INTERNAL ENCLOSURE BEAMS (0030) | AB50 | [5 empty] | 10 | 10 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-01-20 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445339000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0230 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 25 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 |  | 2024-04-08 | 2024-04-08 | MECH |  | 200089964 | 0220 | 4Y ROT EQ 05GT400002 ENG EXCH GT2 (200089964) | TURB,GT400002 TURBINE (AB50.05GT400002) | CHANGE OUT SOLAR ENGINE (0110) | AB50 | [5 empty] | 10 | 10 |  |  | 32 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000128034 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2025-11-14 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.083333 | 2024-03-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012803445390000200089964 | #N/A | 0000128034000200089964 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-07 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0620 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | BOILER WORKSCOPE - COMBUSTION (0140) | AB50 | [5 empty] | 10 | 5 |  |  | 6 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-10 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445389000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0340 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 29 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445391000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0460 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 34 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445391000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0610 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 37 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445391000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0600 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 36 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445391000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-29 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0500 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445380000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-29 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0490 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445380000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0450 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 33 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445391000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-29 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0560 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 8 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445380000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-29 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0510 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 3 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-01 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012873445380000200090465 | #N/A | 0000128734000200090465 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200090871 | 0010 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090871) | VALVE,NRV,GAS EXPORT TO TURRET (AB50.05MV042457) | Change Out Valve AU05.05MV042457 (0020) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129160 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916045400000200090871 | #N/A | 0000129160000200090871 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200090871 | 0060 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090871) | VALVE,NRV,GAS EXPORT TO TURRET (AB50.05MV042457) | Change Out Valve AU05.05SP042005 (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129160 | 5 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916045408000200090871 | #N/A | 0000129160000200090871 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200090871 | 0040 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090871) | VALVE,NRV,GAS EXPORT TO TURRET (AB50.05MV042457) | Change Out Valve AU05.05MV042457 (0020) | AB50 | [5 empty] | 10 | 5 |  |  | 2 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129160 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916045408000200090871 | #N/A | 0000129160000200090871 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200090871 | 0030 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090871) | VALVE,NRV,GAS EXPORT TO TURRET (AB50.05MV042457) | Change Out Valve AU05.05MV042457 (0020) | AB50 | [5 empty] | 10 | 5 |  |  | 12 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129160 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916045408000200090871 | #N/A | 0000129160000200090871 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200090871 | 0070 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090871) | VALVE,NRV,GAS EXPORT TO TURRET (AB50.05MV042457) | Change Out Valve AU05.05SP042005 (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129160 | 6 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916045408000200090871 | #N/A | 0000129160000200090871 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-26 |  | 2024-04-26 | 2024-04-26 | MECH |  | 200090871 | 0050 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090871) | VALVE,NRV,GAS EXPORT TO TURRET (AB50.05MV042457) | Change Out Valve AU05.05SP042005 (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 24 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129160 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916045408000200090871 | #N/A | 0000129160000200090871 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-28 |  | 2024-04-28 | 2024-04-28 | MECH |  | 200090873 | 0050 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090873) | VALVE,NRV,GAS TO TEG INLET FILET SEP (AB50.05MV042419) | Install Valve AU05.05SP042007 (0090) | AB50 | [5 empty] | 10 | 5 |  |  | 40 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129162 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-31 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916245410000200090873 | #N/A | 0000129162000200090873 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-28 |  | 2024-04-28 | 2024-04-28 | MECH |  | 200090873 | 0080 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090873) | VALVE,NRV,GAS TO TEG INLET FILET SEP (AB50.05MV042419) | Install Valve AU05.05SP042007 (0090) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129162 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-31 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916245410000200090873 | #N/A | 0000129162000200090873 |  |  | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-18 |  | 2024-04-28 | 2024-04-28 | MECH |  | 200090873 | 0070 | 2Y F21 NRV EGC 2 REPLACE WITH ROTABLE (200090873) | VALVE,NRV,GAS TO TEG INLET FILET SEP (AB50.05MV042419) | Install Valve AU05.05MV042419 (0020) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - Campaign - Delivered Pre S/4 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000129162 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012916245400000200090873 | #N/A | 0000129162000200090873 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-02 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0510 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145384000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0160 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 22 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0220 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 28 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0590 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 36 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0200 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 26 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-02 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0500 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 1 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145384000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-02 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0520 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145384000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0580 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 24 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 35 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-02 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0560 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 7 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145384000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0210 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 27 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0190 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 25 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0600 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 37 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-11 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0610 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | BOILER WORKSCOPE - COMBUSTION (0140) | AB50 | [5 empty] | 10 | 5 |  |  | 6 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 9 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-14 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145393000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0480 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 4 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 34 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0140 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 20 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0340 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 30 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0180 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | [5 empty] | 10 | 5 |  |  | 1 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 24 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145395000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-02 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0530 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | ISOLATE & SPADE (0030) | AB50 | [5 empty] | 10 | 5 |  |  | 3 | 0 | 0 | OK. - CAMPAIGN PICK PDC. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-05 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000012969145384000200091461 | #N/A | 0000129691000200091461 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0030 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 3 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-03-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000008436245379000600001447 | #N/A | 0000084362000600001447 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0040 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 4 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000008436245379000600001447 | #N/A | 0000084362000600001447 |  |  | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0020 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 2 | 3 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | Delivered Pre S/4 |  | 0 | 0 | 2024-03-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000008436245379000600001447 | #N/A | 0000084362000600001447 |  |  | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 | 2024-03-18 | 2024-04-26 | 2024-04-26 | MECH |  | 200083363 | 0010 | 4Y F21 RECERTIFY SC PSV DISPOSABLE (200083363) | VALVE,T604021,PRES/VAC BREATHER (AB50.03PSV604161) | CERTIFY PSV (0010) | AB50 | 2024-04-26 | AB01 |  | AB03 |  | 10 | 5 | 10528709 | VALVE,REL;434KPAG,FORT VALE CE3A002003B | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB03 | 5300003935 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011602 | N | Preparation (05) | In Preparation (Order) (0055) | 0000120656 | 1 | 3 | 30 | 30 | Supply for Order 200083363, Item 1 cannot be changed 90005902 item 10 already exists | 119000000002625 | 1 | TRUE | 119000000001651 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-10 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 3-In Transit |  | 20000657 | 0 | 0 | 1 | 2024-03-29 | 11 | 39 | ON TIME |  | On Time | 0 | Need Purchasing | 00001206564540810528709000200083363 | #N/A | 000012065610528709000200083363 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-28 | 2024-03-18 | 2024-04-28 | 2024-04-28 | MECH |  | 200083364 | 0010 | 4Y F21 RECERTIFY SC PSV DISPOSABLE (200083364) | VALVE,REL;FORT VALE 3000302B,434KPAG (AB50.03PSV604761) | CERTIFY PSV (0010) | AB50 | 2024-04-28 | AB01 |  | AB03 |  | 10 | 5 | 10528709 | VALVE,REL;434KPAG,FORT VALE CE3A002003B | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB03 | 5300003936 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011601 | N | Preparation (05) | In Preparation (Order) (0055) | 0000120659 | 1 | 3 | 30 | 30 | Supply for Order 200083364, Item 1 cannot be changed 90005903 item 10 already exists | 119000000002625 | 1 | TRUE | 119000000001469 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-10 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 3-In Transit |  | 20000657 | 0 | 0 | 1 | 2024-03-31 | 13 | 41 | ON TIME |  | On Time | 0 | Need Purchasing | 00001206594541010528709000200083364 | #N/A | 000012065910528709000200083364 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-17 | 2024-04-18 | 2024-02-20 | 2024-04-18 | 2024-04-18 | MECH |  | 100031824 | 0010 | Replace TSAIR#3 Oil level gauge (100031824) | PKG EQ,AIR COMPRESSOR 3 (AB50.03A470003) | Replace TSAIR#3 Oil level gauge (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10596891 | GAUGE,LEV;ATCOP 1614918400 | 1 | 1 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300004912 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014421 | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000130225 | 1 | 3 | 30 | 30 | Supply for Order 100031824, Item 1 cannot be changed 90001680 item 10 already exists | 101000000029743 | 1 | TRUE | 101000000029422 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-09-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 1 | 2024-03-21 | 30 | 58 | ON TIME |  | On Time | 0 | SOH | 00001302254540010596891000100031824 | #N/A | 000013022510596891000100031824 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-19 | 2024-04-24 | 2024-04-03 | 2024-04-24 | 2024-04-26 | MECH |  | 100032076 | 0010 | Invstigate EDG1 Cooling System (100032076) | GEN,G400301,GENERATOR (AB50.03G400301) | Investigate EDG1 Cooling System/Flush (0005) | AB50 | 2024-04-24 |  |  | AB01 |  | 20 | 20 | 10442621 | COOLANT;208L,CAT 3658397 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300006842 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | DR |  |  |  | 180014422 | N | Preparation (05) | In Preparation (Order) (0055) | 0000130548 | 1 | 1 | 30 | 30 | Supply for Order 100032076, Item 1 cannot be changed 90003406 item 10 already exists | 101000000023771 | 2 | TRUE |  |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-08-28 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.5 | 2024-03-27 | -7 | 21 | ON TIME |  | On Time | 0 | Need Purchasing | 00001305484540610442621000100032076 | #N/A | 000013054810442621000100032076 | 0 | #N/A | 0
24OKCM16 | PO Received; vendor delivered late |  | Released | 2023-12-30 | 2024-01-09 | 2024-04-18 | 2024-02-15 | 2024-04-18 | 2024-04-20 | MECH |  | 100032131 | 0010 | FP8 Repl FGC Duplex Studs MOC-117600 (100032131) | COMPR,K041100,1ST STG (AB50.05K041101) | FP8 Repl FGC Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-01 |  |  | AB01 | 2024-03-09 | 20 | 20 | 70000044 | STUDBOLT 1/2"-13UNC x 150mm S32760-3 | 56 | 0 | 0 | ETA - 50 Day - 28 Feb - Tristar - Procurement. | 50 | Material In-Transit on-04-Sea | Directs (Inventory) (SP14) | AB01 | 5300004683 | 10 | 50 | X | 1000000338 | 2 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000045218_2024_0001 | 10 | 56 | EA | 2024-02-28 |  | 180012224/ | 180013653 | N | Preparation (05) | In Preparation (Order) (0055) | 0000130643 | 2 | 1 |  |  | Supply for Order 100032131, Item 2 cannot be changed 90001671 item 10 already exists | 101000000028846 | 56 | TRUE | 101000000028730 |  |  | WorkPackLink |  |  | 23 | 0 | 2024-11-30 | 0 | 0 | 2024-03-09 |  | 0 | 0 | 04-Sea | 168 | 1-Not Started |  | 1000000888 | 0 | 0 | 0.33333 | 2024-03-21 | 35 | 63 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | Need Purchasing | 00001306434540070000044000100032131 | 00001306434540070000044000100032131 | 000013064370000044000100032131 | 0 | #N/A | 0
24OKCM16 | PO Received; vendor delivered late |  | Released | 2023-12-30 | 2024-01-09 | 2024-04-18 | 2024-02-15 | 2024-04-18 | 2024-04-19 | MECH |  | 100032133 | 0010 | FP8 Repl EGC2 Duplex Studs MOC-117600 (100032133) | COMPR,K042210,2ND STG (AB50.05K042212) | FP8 Repl EGC2 Duplex Studs MOC-117600 (0010) | AB50 | 2024-04-01 |  |  | AB01 | 2024-03-09 | 20 | 20 | 70000044 | STUDBOLT 1/2"-13UNC x 150mm S32760-3 | 56 | 0 | 0 | ETA. | 50 | Material In-Transit on-04-Sea | Directs (Inventory) (SP14) | AB01 | 5300004684 | 10 | 50 | X | 1000000339 | 2 | 2024-01-09 | 2024-03-06 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500000186 | 5000045222_2024_0001 | 40 | 56 | EA | 2024-02-28 |  | 180012224/ | 180013681 | N | Preparation (05) | In Preparation (Order) (0055) | 0000130645 | 2 | 1 |  |  | Supply for Order 100032133, Item 2 cannot be changed 90001673 item 10 already exists | 101000000028846 | 56 | TRUE | 101000000028733 |  |  | WorkPackLink |  |  | 23 | 0 | 2024-11-30 | 0 | 0 | 2024-03-09 |  | 0 | 0 | 04-Sea | 168 | 1-Not Started |  | 1000000888 | 0 | 0 | 0.2 | 2024-03-21 | 35 | 63 | ON TIME | 4500004322, 4500004322 | After Turnround | 2024-04-15 | Need Purchasing | 00001306454540070000044000100032133 | 00001306454540070000044000100032133 | 000013064570000044000100032133 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-10 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-18 | INLEC |  | 100032535 | 0010 | Repl TEG Transmitter 05LT130112 (100032535) | TX,LIC130112,LEVEL (AB50.05LT130112) | 05LC130112 in Man. Isolate & Disconnect (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10453776 | TX,DP:EMERSON 3051CD2A22A1KS2M5I7D4P1Q4+ | 1 | 1 | 0 | OK - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300004722 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131039 | 1 | 3 | 30 | 30 | Supply for Order 100032535, Item 1 cannot be changed 90003351 item 10 already exists | 101000000010166 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001310394540010453776000100032535 | #N/A | 000013103910453776000100032535 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-09 | 2024-04-18 | 2024-04-23 | 2024-04-18 | 2024-04-18 | HVAC |  | 100032702 | 0010 | Replace HP Switch LER HVAC-A (100032702) | ACOND,HAH680001,REFRIGERANT UNIT NO 1 (AB50.05HP680001) | Remove and install Switch & Ex Insp (0020) | AB50 | 2024-05-12 |  |  | AB01 | 2024-04-21 | 20 | 20 | 70001686 | Mechanical Pressure Switch RP2 | 1 | 0 | 1 | OK. | 63 | Material work-packed @AB50 | Directs (Inventory) (SP14) | AB01 | 5300005951 | 10 | 63 | X | 1000001705 | 2 | 2024-02-08 | 2024-04-18 | MOORE INDUSTRIES PACIFIC INC (30001975) | 4500001634 | 5000033021_2024_0001 | 10 | 1 | EA | 2024-04-02 |  | 180009136 | 180010532 | N | Preparation (05) | In Preparation (Order) (0055) | 0000131203 | 2 | 3 |  |  | Supply for Order 100032702, Item 2 cannot be changed 90003379 item 10 already exists | 101000000023543 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 21 | 2024-06-30 | 0 | 0 | 2024-04-21 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-21 | -33 | -5 | Delayed |  | On Time | 0 | Need Purchasing | 00001312034540070001686000100032702 | #N/A | 000013120370001686000100032702 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-22 | 2024-02-20 | 2024-04-22 | 2024-04-22 | MECH |  | 100033093 | 0020 | CLASS Repl Bilge P/p X/ver Vlv MV643405 (100033093) | VALVE,SCREWDWN,BILGEWTR TRANSFER PUMP (AB50.03MV643405) | Isolate 03MV643405 (0010) | AB50 | 2024-04-22 |  |  | AB01 |  | 10 | 5 | 10206293 | GASKET,CNAF,40MM,CL150,1.5MM,FF,C4430 | 4 | 0 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000020 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014450 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000131577 | 1 | 4 | 30 | 30 | Supply for Order 100033093, Item 1 cannot be changed 90001626 item 10 already exists | 101000000029743 | 4 | TRUE | 101000000029423 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.33333 | 2024-03-25 | 34 | 62 | ON TIME |  | On Time | 0 | Need Purchasing | 00001315774540410206293000100033093 | #N/A | 000013157710206293000100033093 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-22 | 2024-02-20 | 2024-04-22 | 2024-04-22 | MECH |  | 100033093 | 0030 | CLASS Repl Bilge P/p X/ver Vlv MV643405 (100033093) | VALVE,SCREWDWN,BILGEWTR TRANSFER PUMP (AB50.03MV643405) | Isolate 03MV643405 (0010) | AB50 | 2024-04-22 |  |  | AB01 |  | 10 | 5 | 10509086 | VALVE,CHECK;DN40,JIS 5K,BZE,F7351 | 2 | 0 | 2 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000020 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011975 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000131577 | 2 | 4 | 30 | 30 | Supply for Order 100033093, Item 2 cannot be changed 9001200 item 20 already exists | 101000000026546 | 2 | TRUE |  |  |  | WorkPackLink | OKHA STORES |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-03-25 | 34 | 62 | ON TIME |  | On Time | 0 | Need Purchasing | 00001315774540410509086000100033093 | #N/A | 000013157710509086000100033093 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-31 | 2024-04-19 | 2024-03-28 | 2024-04-19 | 2024-04-21 | REFURB |  | 100033230 | 0030 | FRC - CLASS - Replace Grating (100033230) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | Replace grating (0010) | AB50 | 2024-03-26 |  |  | AB01 | 2024-03-26 | 10 | 5 | 70001554 | GRATING GW325AS - Section B | 1 | 1 | 0 | OK. - Gr'd - 103 - 0180009155 | 20 | Material avail; awaiting work-packing @AB01 | Directs (Inventory) (SP14) | AB01 | 5300005854 | 30 | 20 | X | 1000001610 | 5 | 2024-02-22 | 2024-03-20 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001465 | 5000043435_2024_0001 | 20 | 1 | EA | 2024-03-07 |  | /180009155 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131762 | 5 | 3 |  |  | Supply for Order 100033230, Item 5 cannot be changed 90003378 item 20 already exists | 101000000028063 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 | 2024-03-26 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-22 | -6 | 22 | ON TIME |  | On Time | 0 | SOH | 00001317624540170001554000100033230 | #N/A | 000013176270001554000100033230 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-31 | 2024-04-19 | 2024-03-28 | 2024-04-19 | 2024-04-21 | REFURB |  | 100033230 | 0020 | FRC - CLASS - Replace Grating (100033230) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | Replace grating (0010) | AB50 | 2024-03-26 |  |  | AB01 | 2024-03-26 | 10 | 5 | 70001560 | GRATING GW325AS - Section A | 1 | 1 | 0 | OK. - Gr'd - 103 - 0180009155 | 20 | Material avail; awaiting work-packing @AB01 | Directs (Inventory) (SP14) | AB01 | 5300005854 | 20 | 20 | X | 1000001610 | 3 | 2024-02-22 | 2024-03-20 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001465 | 5000043452_2024_0001 | 10 | 1 | EA | 2024-03-07 |  | /180009155 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131762 | 3 | 3 |  |  | Supply for Order 100033230, Item 3 cannot be changed 90003378 item 10 already exists | 101000000028062 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 | 2024-03-26 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-22 | -6 | 22 | ON TIME |  | On Time | 0 | SOH | 00001317624540170001560000100033230 | #N/A | 000013176270001560000100033230 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-31 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-21 | REFURB |  | 100033230 | 0010 | FRC - CLASS - Replace Grating (100033230) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | Replace grating (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10295759 | CLIP SET;65X8MM,GALV ST,WEBFORGE C001MG | 12 | 0 | 0 | OK. | 0 | Material In-Transit on-04-Sea | Stock at Base (SP12) | AB01 | 5300005854 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | SET |  |  |  | 180008884 | N | Preparation (05) | In Preparation (Order) (0055) | 0000131762 | 1 | 3 | 30 | 30 | Supply for Order 100033230, Item 1 cannot be changed 90003377 item 10 already exists | 101000000022477 | 12 | TRUE | 101000000022319 | 101000000022318 |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 12 | 5-Completed |  | 1000000887 | 0 | 0 | 0.25 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001317624540110295759000100033230 | #N/A | 000013176210295759000100033230 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-31 | 2024-04-19 | 2024-03-28 | 2024-04-19 | 2024-04-21 | REFURB |  | 100033230 | 0040 | FRC - CLASS - Replace Grating (100033230) | BOAT,FAST RESC CRAFT,SB (AB50.03A092020) | Replace grating (0010) | AB50 | 2024-03-26 |  |  | AB01 | 2024-03-26 | 10 | 5 | 70001515 | GRATING GW325AS - Rescue winch peno | 1 | 1 | 0 | OK. - Gr'd - 103 - 0180009155 | 20 | Material avail; awaiting work-packing @AB01 | Directs (Inventory) (SP14) | AB01 | 5300005854 | 40 | 20 | X | 1000001610 | 10 | 2024-02-22 | 2024-03-20 | LEGENEERING AUSTRALIA PTY LTD (30000143) | 4500001465 | 5000043436_2024_0001 | 30 | 1 | EA | 2024-03-07 |  | /180009155 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000131762 | 10 | 3 |  |  | Supply for Order 100033230, Item 10 cannot be changed 90003378 item 30 already exists | 101000000028064 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 | 2024-03-26 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-03-22 | -6 | 22 | ON TIME |  | On Time | 0 | SOH | 00001317624540170001515000100033230 | #N/A | 000013176270001515000100033230 | 0 | #N/A | 0
24OKCO13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-17 | 2024-02-13 | 2024-04-17 | 2024-04-17 | INLEC |  | 100033247 | 0010 | Replace PCB - ER Column Light (100033247) | LIGHT,COLUMN,STEERING GEAR ROOM (AB50.03AP090500) | Replace PCB - ER Column Light (0010) | AB50 | 2024-04-17 |  |  | AB01 |  | 10 | 5 | 10536783 | BOARD,PRINTED CCT;HYUNJIN HJ1071 | 1 | 0 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000034 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180009219 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000131748 | 1 | 3 | 30 | 30 | Supply for Order 100033247, Item 1 cannot be changed 90001124 item 10 already exists | 101000000022690 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-20 | 36 | 64 | ON TIME |  | On Time | 0 | Need Purchasing | 00001317484539910536783000100033247 | #N/A | 000013174810536783000100033247 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-16 | 2024-04-27 | 2024-03-27 | 2024-04-27 | 2024-04-28 | INLEC |  | 100033799 | 0010 | Replace 20x CCR ICSS montiors (100033799) | PANEL,ICSS SERVER,SERVER ROOM (AB50.03CP850001A) | RPE / SEO -Replace 20x CCR ICSS montiors (0010) | AB50 | 2024-03-25 |  |  | AB01 | 2024-03-25 | 10 | 10 | 70002753 | P2422H Dell 24'' FHD LED Monitor | 20 | 20 | 0 | OK. | 10 | Workpack awaiting Shipment @AB01 | Directs (Inventory) (SP14) | AB01 | 5300006661 | 10 | 10 | X | 1000002770 | 2 | 2024-03-05 | 2024-03-22 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 4500003103 | 5000040347_2024_0001 | 10 | 20 | EA | 2024-03-22 |  | /180006793 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132351 | 2 | 3 |  |  | Supply for Order 100033799, Item 2 cannot be changed 90003399 item 10 already exists | 101000000026661 | 20 | TRUE | 101000000026660 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-31 | 0 | 0 | 2024-03-25 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-30 | 3 | 31 | ON TIME |  | On Time | 0 | SOH | 00001323514540970002753000100033799 | #N/A | 000013235170002753000100033799 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034052 | 0010 | Replace Gasket EGC2 LO Cooler TCV (100034052) | VALVE,E042231,TEMP CTRL (AB50.05TCV042804) | Isolate 05TCV042804 and drain oil (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10616638 | Set of 3-way valve seals, each set compr | 5 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000091 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014435 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132606 | 1 | 4 |  |  | Supply for Order 100034052, Item 1 cannot be changed 90003187 item 10 already exists | 101000000029743 | 5 | TRUE | 101000000029653 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-06-16 | 0 | 0 |  |  | 0 | 0 | 01-Road | 5 | 5-Completed |  | 20000716 | 0 | 0 | 0.5 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001326064540010616638000100034052 | #N/A | 000013260610616638000100034052 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0092 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534348 | O-RING;CAT 1121102 | 2 | 0 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 90 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 13 | 3 | 30 | 30 | Supply for Order 100034084, Item 13 cannot be changed 90003188 item 90 already exists | 101000000029743 | 2 | TRUE | 101000000029586 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110534348000100034084 | #N/A | 000013256810534348000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0122 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534344 | GASKET;CAT 2388708 | 1 | 0 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 9 | 3 | 30 | 30 | Supply for Order 100034084, Item 9 cannot be changed 90003188 item 50 already exists | 101000000029743 | 1 | TRUE | 101000000029584 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110534344000100034084 | #N/A | 000013256810534344000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0172 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10613354 | SEAL,O-RING;CAT 3E6773 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 170 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 21 | 3 | 30 | 30 | Supply for Order 100034084, Item 21 cannot be changed 90003188 item 170 already exists | 101000000029743 | 2 | TRUE | 101000000029589 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110613354000100034084 | #N/A | 000013256810613354000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0222 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10613353 | GAURD,ALTERNATOR;CAT 3529713 | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 160 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 20 | 3 | 30 | 30 | Supply for Order 100034084, Item 20 cannot be changed 90003188 item 160 already exists | 101000000029743 | 1 | TRUE | 101000000029588 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110613353000100034084 | #N/A | 000013256810613353000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0112 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534345 | GASKET;CAT 2388709 | 1 | 0 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 10 | 3 | 30 | 30 | Supply for Order 100034084, Item 10 cannot be changed 90003188 item 60 already exists | 101000000029743 | 1 | TRUE | 101000000029585 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110534345000100034084 | #N/A | 000013256810534345000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0052 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534150 | HOSE;CAT 371-8946 | 15 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 7 | 3 | 30 | 30 | Supply for Order 100034084, Item 7 cannot be changed 90003188 item 30 already exists | 101000000029743 | 15 | TRUE | 101000000029582 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 15 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110534150000100034084 | #N/A | 000013256810534150000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0022 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10534378 | COOLER;CAT 3996239 | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 110 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 15 | 3 | 30 | 30 | Supply for Order 100034084, Item 15 cannot be changed 90003188 item 110 already exists | 101000000029559 | 1 | TRUE |  |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110534378000100034084 | #N/A | 000013256810534378000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0212 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10568140 | O-RING;SEAL,CAT 8T0315 | 4 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 120 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 16 | 3 | 30 | 30 | Supply for Order 100034084, Item 16 cannot be changed 90003188 item 120 already exists | 101000000029743 | 4 | TRUE | 101000000029587 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110568140000100034084 | #N/A | 000013256810568140000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-24 | MECH |  | 100034084 | 0152 | CLASS Repl FWD FWP Inject&Turb/C After/C (100034084) | PUMP,A600011A,FIRE WTR FWD (AB50.03P600011) | Isolate 03P600011 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 10 | 5 | 10458410 | O-RING;CAT 6V3917 | 4 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000093 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014454 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132568 | 6 | 3 | 30 | 30 | Supply for Order 100034084, Item 6 cannot be changed 90003188 item 20 already exists | 101000000029743 | 4 | TRUE | 101000000029581 |  |  | WorkPackLink | OKHA STORES | 2024-03-30 | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.043478 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001325684540110458410000100034084 | #N/A | 000013256810458410000100034084 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-21 | MECH |  | 100034344 | 0012 | Replace AFT FWP Turbos (100034344) | PUMP,A600001A,FIRE WTR AFT (AB50.03P600001) | Isolate 03P600001 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 20 | 20 | 10606442 | GASKET;CAT 2264753 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000122 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014449 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132798 | 5 | 3 | 30 | 30 | Supply for Order 100034344, Item 5 cannot be changed 90003190 item 30 already exists | 101000000029743 | 2 | TRUE | 101000000029597 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.2 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001327984540110606442000100034344 | #N/A | 000013279810606442000100034344 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-21 | MECH |  | 100034344 | 0042 | Replace AFT FWP Turbos (100034344) | PUMP,A600001A,FIRE WTR AFT (AB50.03P600001) | Isolate 03P600001 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 20 | 20 | 10458413 | O RING;CAT 1123540 | 2 | 2 | 0 | OK - PDC. | 0 | Workpack awaiting Shipment @AB01 | Stock at Base (SP12) | AB01 | 5300000122 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000132798 | 4 | 3 | 30 | 30 | Supply for Order 100034344, Item 4 cannot be changed 90003190 item 20 already exists | 101000000029719 | 2 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001327984540110458413000100034344 | #N/A | 000013279810458413000100034344 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-19 | 2024-04-03 | 2024-04-19 | 2024-04-21 | MECH |  | 100034344 | 0032 | Replace AFT FWP Turbos (100034344) | PUMP,A600001A,FIRE WTR AFT (AB50.03P600001) | Isolate 03P600001 (0010) | AB50 | 2024-04-19 |  |  | AB01 |  | 20 | 20 | 10616647 | TURBOCHARGER,CARTRIDGE GP;CAT 10R8230 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000122 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014449 | N | Preparation (05) | In Preparation (Order) (0055) | 0000132798 | 3 | 3 | 30 | 30 | Supply for Order 100034344, Item 3 cannot be changed 90003190 item 10 already exists | 101000000029743 | 2 | TRUE | 101000000029622 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.2 | 2024-03-22 | -12 | 16 | ON TIME |  | On Time | 0 | Need Purchasing | 00001327984540110616647000100034344 | #N/A | 000013279810616647000100034344 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034735 | 0022 | CLASS Repl Steam Drain Vlv Stripping Pp (100034735) | VALVE,SP750434,MAN THROTTLE,INLET (AB50.03MV750338) | Perform Isolations 03MV750338 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 10 | 5 | 10058451 | STUDBOLT;0.500" X 45MM,B7,BLK | 8 | 0 | 0 | OK. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000167 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014418 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133239 | 2 | 4 | 30 |  |  | 101000000029743 | 8 | TRUE | 101000000029556 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 8 | 5-Completed |  | 20000716 | 0 | 0 | 0.33333 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001332394540010058451000100034735 | #N/A | 000013323910058451000100034735 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0202 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10443092 | CABLE,PWR,1C,50MM2,0.6/1KV,GRN/YL,SUBMER | 20 | 0 | 20 | 25.03.24: OK - Work-packed on Okha in 2001 SLOC | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000188 | 120 | 21 |  |  | 0 | [5 empty] | 0 | 0 | M |  |  |  | 180007223 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 21 | 1 | 30 | 30 | Supply for Order 100034857, Item 21 cannot be changed 9000150 item 120 already exists | 101000000020897 | 20 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910443092000100034857 | #N/A | 000013340110443092000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0092 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10606782 | FLANGE,CONN,HOSE;KSB 72273 | 1 | 1 | 1 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000188 | 110 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007223 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 20 | 1 | 30 | 30 | Supply for Order 100034857, Item 20 cannot be changed 9000150 item 110 already exists | 101000000020896 | 1 | TRUE |  |  |  | WorkPackLink | 2100354089 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | SOH | 00001334014537910606782000100034857 | 00001334014537910606782000100034857 | 000013340110606782000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-05 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0212 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 30000055 | PUMP ASY,KSB 9971528167/100,SW LIFT | 1 | 1 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000188 | 130 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180009702 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 22 | 1 | 30 | 30 | Supply for Order 100034857, Item 22 cannot be changed 90003748 item 10 already exists | 101000000000501 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001334014537930000055000100034857 | #N/A | 000013340130000055000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-05 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0212 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 30000055 | PUMP ASY,KSB 9971528167/100,SW LIFT | 1 | 1 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000188 | 130 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180009702 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 22 | 1 | 30 | 30 | Supply for Order 100034857, Item 22 cannot be changed 90003748 item 10 already exists | 101000000000501 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001334014537930000055000100034857 | #N/A | 000013340130000055000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0110 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10534799 | HOSE ASY,GLYCOL,12.45MMX20M | 1 | 0 | 1 | 25.03.24: OK - 1 only work-packed on Okha in 5001 SLOC | 0 | Materials handed over to w/ Maintenance | Stock at Base (SP12) | AB01 | 5300000188 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  | 180009704 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 7 | 1 | 30 | 30 | Supply for Order 100034857, Item 7 cannot be changed 9000462 item 50 already exists | 101000000022862 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 3-In Transit |  | 1000000882 | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910534799000100034857 | 00001334014537910534799000100034857 | 000013340110534799000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0072 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10060202 | GASKET,CNAF,20MM,CL150,1.5MM,RF | 10 | 0 | 10 | 25.03.24: OK - Work-packed on Okha in 5001 SLOC | 0 | Materials handed over to w/ Maintenance | Stock at Base (SP12) | AB01 | 5300000188 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007223 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 15 | 1 | 30 | 30 | Supply for Order 100034857, Item 15 cannot be changed 9000150 item 70 already exists | MINI 696541 | 10 | TRUE | 101000000020894 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910060202000100034857 | #N/A | 000013340110060202000100034857 | 0 | #N/A | 0
24OKCM13 | Voyage arrived: too late to meet planned Reqmt Dat |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0072 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10060202 | GASKET,CNAF,20MM,CL150,1.5MM,RF | 10 | 0 | 10 | 25.03.24: OK - Work-packed on Okha in 5001 SLOC | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300000188 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007223 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 15 | 1 | 30 | 30 | Supply for Order 100034857, Item 15 cannot be changed 9000150 item 70 already exists | 101000000020989 | 10 | TRUE | 101000000020894 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000781 | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910060202000100034857 | #N/A | 000013340110060202000100034857 | 0 | #N/A | 0
24OKCM13 | Issue detected, please check message in derivation |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-27 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0232 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-04-13 |  |  | AB01 |  | 20 | 20 | 10432379 | SEAL,MECH;Q1Q1VMG4,KSB 90070804 | 1 | 0 | 0 | UserCommentLink | 0 | Material In-Transit on-06-Air Passenger | Stock at Base (SP12) | AB01 | 5300000188 | 150 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013975 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 24 | 1 | 30 | 30 | Supply for Order 100034857, Item 24 cannot be changed 90006699 item 10 already exists | 101000000000964 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 16 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 06-Air Passenger | 1 | 3-In Transit |  | 1000001083 | 0 | 0 | 0.038462 | 2024-02-29 | -27 | 1 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910432379000100034857 | #N/A | 000013340110432379000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0032 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10060218 | GASKET;CNAF,900MM,CL150,RF,1.5MM | 2 | 0 | 2 | 25.03.24: OK - Work-packed on Okha in 2001 SLOC | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000188 | 80 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007223 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 16 | 1 | 30 | 30 | Supply for Order 100034857, Item 16 cannot be changed 9000150 item 80 already exists | 101000000020895 | 2 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910060218000100034857 | #N/A | 000013340110060218000100034857 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-21 | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0100 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10606783 | KIT,FASTENER;HOSE CONN,KSB 90173 | 2 | 0 | 2 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000188 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007223 | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 6 | 1 | 30 | 30 | Supply for Order 100034857, Item 6 cannot be changed 9000150 item 40 already exists | 101000000020893 | 2 | TRUE |  |  |  | WorkPackLink | 2100354089 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001334014537910606783000100034857 | #N/A | 000013340110606783000100034857 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034863 | 0022 | Replace FWG 1&2 S/Water Outlet Vlvs (100034863) | VALVE,G452011,MAN ISOL (AB50.03MV753428) | Isolate 03MV753427 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10610492 | BOLT,HEX;HVY,M16,2.0PX35MM,PLN | 32 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000187 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014429 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133315 | 2 | 3 | 30 | 30 |  | 101000000029743 | 32 | TRUE | 101000000029557 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-01-29 | 0 | 0 |  |  | 0 | 0 | 01-Road | 32 | 5-Completed |  | 20000716 | 0 | 0 | 0.5 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333154540010610492000100034863 | #N/A | 000013331510610492000100034863 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034901 | 0030 | Inst EGC2 Int/Strain Vac Break MOC116295 (100034901) | STRAIN,E042212,COOL MED SUPPLY (AB50.05SP460009) | Isolate 05SP460009 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10047929 | CONNECTOR,TBG;0.25",NPTF X COMP,SS | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000198 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014452 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133373 | 1 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029627 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333734540010047929000100034901 | #N/A | 000013337310047929000100034901 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034901 | 0052 | Inst EGC2 Int/Strain Vac Break MOC116295 (100034901) | STRAIN,E042212,COOL MED SUPPLY (AB50.05SP460009) | Isolate 05SP460009 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10609537 | TEE,PIPE;0.5",F,NPT,420BAR,SS316 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000198 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014452 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133373 | 5 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029598 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333734540010609537000100034901 | #N/A | 000013337310609537000100034901 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034901 | 0042 | Inst EGC2 Int/Strain Vac Break MOC116295 (100034901) | STRAIN,E042212,COOL MED SUPPLY (AB50.05SP460009) | Isolate 05SP460009 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10609536 | ELBOW,PIPE;90DEG,0.5",NPT,M&M,SS316 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000198 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014452 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133373 | 4 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029594 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333734540010609536000100034901 | #N/A | 000013337310609536000100034901 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034901 | 0022 | Inst EGC2 Int/Strain Vac Break MOC116295 (100034901) | STRAIN,E042212,COOL MED SUPPLY (AB50.05SP460009) | Isolate 05SP460009 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10609432 | TUBE,SMLS;6.3X1.6MM,PROCHEM T0060DASA | 2 | 4 | 0 | OK - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300000198 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | M |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133373 | 3 | 3 | 30 | 30 |  | 101000000029658 | 2 | TRUE |  |  |  | WorkPackLink | OKHAEC |  | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001333734540010609432000100034901 | #N/A | 000013337310609432000100034901 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034901 | 0062 | Inst EGC2 Int/Strain Vac Break MOC116295 (100034901) | STRAIN,E042212,COOL MED SUPPLY (AB50.05SP460009) | Isolate 05SP460009 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10042524 | BUSH,RED;M&F,0.50X0.25",NPT,SS316 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000198 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014452 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133373 | 6 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029591 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333734540010042524000100034901 | #N/A | 000013337310042524000100034901 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034901 | 0012 | Inst EGC2 Int/Strain Vac Break MOC116295 (100034901) | STRAIN,E042212,COOL MED SUPPLY (AB50.05SP460009) | Isolate 05SP460009 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10590371 | VALVE,CHK;0.25",NPT M,316SS,HOKE 6133M4Y | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000198 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014452 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133373 | 2 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029593 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333734540010590371000100034901 | #N/A | 000013337310590371000100034901 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034902 | 0052 | Inst EGC2 Disch/Strain VacBreakMOC116295 (100034902) | STRAIN,E042213,COOL MED SUPPLY (AB50.05SP460010) | Isolate 05SP460010 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10609537 | TEE,PIPE;0.5",F,NPT,420BAR,SS316 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000199 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014458 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133374 | 5 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029599 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333744540010609537000100034902 | #N/A | 000013337410609537000100034902 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034902 | 0012 | Inst EGC2 Disch/Strain VacBreakMOC116295 (100034902) | STRAIN,E042213,COOL MED SUPPLY (AB50.05SP460010) | Isolate 05SP460010 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10590371 | VALVE,CHK;0.25",NPT M,316SS,HOKE 6133M4Y | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000199 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014458 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133374 | 2 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029595 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333744540010590371000100034902 | #N/A | 000013337410590371000100034902 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034902 | 0022 | Inst EGC2 Disch/Strain VacBreakMOC116295 (100034902) | STRAIN,E042213,COOL MED SUPPLY (AB50.05SP460010) | Isolate 05SP460010 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10609432 | TUBE,SMLS;6.3X1.6MM,PROCHEM T0060DASA | 2 | 4 | 0 | OK - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300000199 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | M |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000133374 | 3 | 3 | 30 | 30 |  | 101000000029659 | 2 | TRUE |  |  |  | WorkPackLink | OKHAEC |  | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001333744540010609432000100034902 | #N/A | 000013337410609432000100034902 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034902 | 0042 | Inst EGC2 Disch/Strain VacBreakMOC116295 (100034902) | STRAIN,E042213,COOL MED SUPPLY (AB50.05SP460010) | Isolate 05SP460010 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10609536 | ELBOW,PIPE;90DEG,0.5",NPT,M&M,SS316 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000199 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014458 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133374 | 4 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029596 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333744540010609536000100034902 | #N/A | 000013337410609536000100034902 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034902 | 0030 | Inst EGC2 Disch/Strain VacBreakMOC116295 (100034902) | STRAIN,E042213,COOL MED SUPPLY (AB50.05SP460010) | Isolate 05SP460010 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10047929 | CONNECTOR,TBG;0.25",NPTF X COMP,SS | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000199 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014458 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133374 | 1 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029628 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333744540010047929000100034902 | #N/A | 000013337410047929000100034902 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100034902 | 0062 | Inst EGC2 Disch/Strain VacBreakMOC116295 (100034902) | STRAIN,E042213,COOL MED SUPPLY (AB50.05SP460010) | Isolate 05SP460010 (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10042524 | BUSH,RED;M&F,0.50X0.25",NPT,SS316 | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000199 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014458 | N | Preparation (05) | In Preparation (Order) (0055) | 0000133374 | 6 | 3 | 30 | 30 |  | 101000000029743 | 2 | TRUE | 101000000029592 |  |  | WorkPackLink | OKHAEC | 2024-03-30 | 0 | 0 | 2024-02-03 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001333744540010042524000100034902 | #N/A | 000013337410042524000100034902 | 0 | #N/A | 0
24OKCM16 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-02-15 | 2024-02-06 | 2024-02-15 | 2024-02-15 | INLEC |  | 100035867 | 0010 | Replace TX Fresh/W Chiller (100035867) | TX,K452030,TEMP (AB50.03TT452043) | Calibrate & Replace 03TT452043 (0010) | AB50 | 2024-02-21 |  |  | AB01 |  | 20 | 20 | 10591507 | TX ASY,TEMP;R/MOUNT 3144PD6A1I7M5C8C4Q4+ | 1 | 0 | 1 | OK - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300000807 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180006425 | N | Execution (07) | Main Work Started (Order) (0070) | 0000134339 | 1 | 3 | 30 | 30 | Supply for Order 100035867, Item 1 cannot be changed 90001105 item 10 already exists | 101000000020158 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 6 | 2024-03-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-01-18 | -19 | 9 | ON TIME |  | On Time | 0 | Need Purchasing | 00001343394533710591507000100035867 | #N/A | 000013433910591507000100035867 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-21 | 2024-02-19 | 2024-04-21 | 2024-04-24 | MECH |  | 100036033 | 0070 | HSE10 Install Accom Bag Store Shelves (100036033) | STRUCT,DECKHOUSE (AB50.05STRUCT021) | Fabricate support frames (0010) | AB50 | 2024-03-14 |  |  | AB01 | 2024-03-02 | 20 | 20 | 70002876 | PLYWOOD MARINE 1.2M X 2.4M X 18MM | 6 | 0 | 6 | OK. | 2 | Material work-packed @AB50 | Directs (Inventory) (SP14) | AB01 | 5300005760 | 20 | 2 | X | 1000002964 | 7 | 2024-02-19 | 2024-02-28 | J BLACKWOOD AND SON LTD (30000394) | 4500003337 | 5000022407_2024_0001 | 10 | 6 | SHT | 2024-02-27 |  | /180005686 | 180011310 | N | Scheduling (06) | Ready to Schedule (Order) (0060) | 0000134557 | 7 | 3 |  |  | Supply for Order 100036033, Item 7 cannot be changed 90001686 item 10 already exists | 101000000025164 | 6 | TRUE |  |  |  | WorkPackLink |  |  | 12 | 0 | 2023-12-03 | 0 | 0 | 2024-03-02 |  | 0 | 0 | 04-Sea | 0 | 3-In Transit |  | 1000000920 | 0 | 0 | 0.2 | 2024-03-24 | 34 | 62 | ON TIME |  | On Time | 0 | Need Purchasing | 00001345574540370002876000100036033 | #N/A | 000013455770002876000100036033 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | COMMS |  | 100036320 | 0012 | "Replace Stbd PA input station, no chime (100036320) | PANEL,IS HAZARDOUS AREA ACCESS PANEL (AB50.03CCSG611440) | Replace Stbd PA input station, no chime (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 30 | 30 | 10473696 | PANEL,ACCESS,SPECTOR ACETS01/F/1/2/IS | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001058 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014441 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000134844 | 1 | 3 | 30 | 30 | Supply for Order 100036320, Item 1 cannot be changed 90003230 item 10 already exists | 101000000029743 | 1 | TRUE | 101000000029564 |  |  | WorkPackLink | Okha Stores | 2024-03-30 | 0 | 0 | 2024-05-13 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 1 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001348444540010473696000100036320 | #N/A | 000013484410473696000100036320 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100036757 | 0040 | FP8 MOC Install EGC2 Motor Bearing Press (100036757) | MOTOR,K042210,GAS COMP DRIVER (AB50.05KM042210) | Install EGC2 Motor Bearing Pressure Bala (0020) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10048148 | TEE,TUBE;UN,0.5",SS316,GYROLOK 8TTT316 | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001257 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014451 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135291 | 3 | 3 | 30 | 30 |  | 101000000029743 | 1 | TRUE | 101000000029629 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.2 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001352914540010048148000100036757 | #N/A | 000013529110048148000100036757 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100036757 | 0030 | FP8 MOC Install EGC2 Motor Bearing Press (100036757) | MOTOR,K042210,GAS COMP DRIVER (AB50.05KM042210) | Install EGC2 Motor Bearing Pressure Bala (0020) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10048156 | UNION,COMP,STR;GYRO 8U316 | 4 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001257 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014451 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135291 | 2 | 3 | 30 | 30 |  | 101000000029743 | 4 | TRUE | 101000000029650 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.2 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001352914540010048156000100036757 | #N/A | 000013529110048156000100036757 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100036757 | 0052 | FP8 MOC Install EGC2 Motor Bearing Press (100036757) | MOTOR,K042210,GAS COMP DRIVER (AB50.05KM042210) | Install EGC2 Motor Bearing Pressure Bala (0020) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10462574 | FLANGE,THD;PRESSDYN FLANGEDN40CL15034NP> | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001257 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014451 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135291 | 5 | 3 | 30 | 30 |  | 101000000029743 | 1 | TRUE | 101000000029457 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.2 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001352914540010462574000100036757 | #N/A | 000013529110462574000100036757 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-18 | 2024-04-03 | 2024-04-18 | 2024-04-19 | MECH |  | 100036757 | 0012 | FP8 MOC Install EGC2 Motor Bearing Press (100036757) | MOTOR,K042210,GAS COMP DRIVER (AB50.05KM042210) | Install EGC2 Motor Bearing Pressure Bala (0020) | AB50 | 2024-04-18 |  |  | AB01 |  | 20 | 20 | 10431306 | TUBE;0.5",SS316,SMLS,PROCHEM T0127EASA | 1 | 1 | 0 | OK. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001257 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000135291 | 4 | 3 | 30 | 30 |  | 101000000029657 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-21 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001352914540010431306000100036757 | #N/A | 000013529110431306000100036757 | 0 | #N/A | 0
24OKCO13 | No issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-28 | 2024-03-15 | 2024-03-28 | 2024-03-28 | INLEC |  | 100036926 | 0020 | Replace Portable nav light - replace (100036926) | LIGHT,RISER,SOLAR POWERED (AB50.04LT612001) | Test, Charge & Store Portable Nav light (0010) | AB50 | 2024-04-02 |  |  | AB01 | 2024-03-22 | 10 | 10 | 70000051 | LANTERN; Navigation, Tideland Signal,SOL | 1 | 0 | 1 | OK. | 63 | Material work-packed @AB50 | Directs (Inventory) (SP14) | AB01 | 5300004666 | 10 | 63 | X | 1000000345 | 3 | 2024-01-09 | 2024-03-19 | TRINKOR PTY LTD (30001954) | 4500000170 | 5000030881_2024_0001 | 10 | 1 | EA | 2024-03-19 |  | /180007418 | 180010534 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000135427 | 3 | 3 |  |  | Supply for Order 100036926, Item 3 cannot be changed 90002200 item 10 already exists | 101000000022818 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 7 | 4 | 2023-10-22 | 0 | 0 | 2024-03-22 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-29 | -15 | 13 | ON TIME |  | On Time | 0 | Need Purchasing | 00001354274537970000051000100036926 | #N/A | 000013542770000051000100036926 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-22 | 2024-04-29 | 2024-03-28 | 2024-04-28 | 2024-05-02 | REFURB |  | 100037132 | 0070 | E/R - Replace Spool HVAC CSW1 CDR-30357 (100037132) | PUMP,A/C COOLING,DUTY (AB50.03P753002A) | replace spool (0030) | AB50 | 2024-06-12 |  |  | AB01 | 2024-05-05 | 20 | 20 | 70001064 | Gasket;DN80,RF,C4430,1.5mm, PN16 | 2 | 0 | 0 | ETA - 15 March - Procurement - Klinger. | 60 | Material In-Transit on-04-Sea | Directs (Inventory) (SP14) | AB01 | 5300006988 | 40 | 60 | X | 1000003314 | 9 | 2024-02-22 | 2024-04-29 | KLINGER LIMITED (30000403) | 4500004020 | 5000043154_2024_0001 | 10 | 2 | EA | 2024-03-15 |  | 180011759/ | 180013677 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135616 | 9 | 1 |  |  | Supply for Order 100037132, Item 9 cannot be changed 90003414 item 20 already exists | 101000000028846 | 2 | TRUE | 101000000027934 |  |  | WorkPackLink |  |  | 38 | 0 | 2024-11-30 | 0 | 0 | 2024-05-05 |  | 0 | 0 | 04-Sea | 2 | 1-Not Started |  | 1000000888 | 0 | 0 | 0.14286 | 2024-04-01 | 4 | 32 | ON TIME |  | On Time | 0 | Need Purchasing | 00001356164541170001064000100037132 | #N/A | 000013561670001064000100037132 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-15 | 2024-03-13 | 2024-04-15 | 2024-04-15 | INLEC |  | 100037134 | 0010 | Replace Aft FWP Transmitter Manifold (100037134) | TX,A600001A,PRESS IPF SD (AB50.03PZT601421) | Replace Tx & Manifold. Funct. test Trip (0010) | AB50 | 2024-04-15 |  |  | AB01 |  | 20 | 20 | 10453728 | TX,PRESS;EMERSON 3051TG,0/2000KPA | 1 | 0 | 0 | OK. | 0 | Material In-Transit on-04-Sea | Stock at Base (SP12) | AB01 | 5300001504 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180008876 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000135618 | 1 | 3 | 30 | 30 | Supply for Order 100037134, Item 1 cannot be changed 90001645 item 10 already exists | 101000000022477 | 1 | TRUE | 101000000021090 |  |  | WorkPackLink | OKHAOLC |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 1 | 5-Completed |  | 1000000887 | 0 | 0 | 1 | 2024-03-18 | 5 | 33 | ON TIME |  | On Time | 0 | Need Purchasing | 00001356184539710453728000100037134 | #N/A | 000013561810453728000100037134 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-20 | 2024-04-03 | 2024-04-20 | 2024-04-21 | REFURB |  | 100037219 | 0052 | MOD7 - HSE10 Replace Light Support T1018 (100037219) | LIGHT,EMERG MOD 7 UPPER DECK (AB50.05LT400302W3213) | Replace light bracket (0010) | AB50 | 2024-04-20 |  |  | AB01 |  | 30 | 30 | 10586381 | BOLT ASY,HEX;M16X60MM,GDE 8.8,HDG,N+2W | 4 | 8 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001513 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014455 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135763 | 4 | 3 | 30 | 30 | Supply for Order 100037219, Item 4 cannot be changed 90003253 item 40 already exists | 101000000029743 | 4 | TRUE | 101000000029550 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-23 | -11 | 17 | ON TIME |  | On Time | 0 | SOH | 00001357634540210586381000100037219 | 00001357634540210586381000100037219 | 000013576310586381000100037219 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-20 | 2024-04-03 | 2024-04-20 | 2024-04-21 | REFURB |  | 100037219 | 0010 | MOD7 - HSE10 Replace Light Support T1018 (100037219) | LIGHT,EMERG MOD 7 UPPER DECK (AB50.05LT400302W3213) | Replace light bracket (0010) | AB50 | 2024-04-20 |  |  | AB01 |  | 30 | 30 | 10616701 | Frame | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001513 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014455 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135763 | 1 | 3 |  |  | Supply for Order 100037219, Item 1 cannot be changed 90003253 item 10 already exists | 101000000023513 | 1 | TRUE |  |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-23 | -11 | 17 | ON TIME |  | On Time | 0 | Need Purchasing | 00001357634540210616701000100037219 | #N/A | 000013576310616701000100037219 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-20 | 2024-04-03 | 2024-04-20 | 2024-04-21 | REFURB |  | 100037219 | 0020 | MOD7 - HSE10 Replace Light Support T1018 (100037219) | LIGHT,EMERG MOD 7 UPPER DECK (AB50.05LT400302W3213) | Replace light bracket (0010) | AB50 | 2024-04-20 |  |  | AB01 |  | 30 | 30 | 10616702 | Cable Tray Support Bracket | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001513 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014455 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135763 | 2 | 3 |  |  | Supply for Order 100037219, Item 2 cannot be changed 90003253 item 20 already exists | 101000000029743 | 1 | TRUE | 101000000029654 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-23 | -11 | 17 | ON TIME |  | On Time | 0 | Need Purchasing | 00001357634540210616702000100037219 | #N/A | 000013576310616702000100037219 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-20 | 2024-04-03 | 2024-04-20 | 2024-04-21 | REFURB |  | 100037219 | 0030 | MOD7 - HSE10 Replace Light Support T1018 (100037219) | LIGHT,EMERG MOD 7 UPPER DECK (AB50.05LT400302W3213) | Replace light bracket (0010) | AB50 | 2024-04-20 |  |  | AB01 |  | 30 | 30 | 10616668 | MYLAR Insulating Sleeve | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001513 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014455 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135763 | 3 | 3 |  |  | Supply for Order 100037219, Item 3 cannot be changed 90003253 item 30 already exists | 101000000029743 | 2 | TRUE | 101000000029870 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-23 | -11 | 17 | ON TIME |  | On Time | 0 | Need Purchasing | 00001357634540210616668000100037219 | #N/A | 000013576310616668000100037219 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-20 | 2024-04-03 | 2024-04-20 | 2024-04-21 | REFURB |  | 100037219 | 0062 | MOD7 - HSE10 Replace Light Support T1018 (100037219) | LIGHT,EMERG MOD 7 UPPER DECK (AB50.05LT400302W3213) | Replace light bracket (0010) | AB50 | 2024-04-20 |  |  | AB01 |  | 30 | 30 | 10586963 | BOLT ASY,HEX;M12X50MM,GDE A4-70,N+2W | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001513 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014455 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135763 | 6 | 3 | 30 | 30 | Supply for Order 100037219, Item 6 cannot be changed 90003253 item 60 already exists | 101000000029743 | 2 | TRUE | 101000000029552 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-03-23 | -11 | 17 | ON TIME |  | On Time | 0 | Need Purchasing | 00001357634540210586963000100037219 | #N/A | 000013576310586963000100037219 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-20 | 2024-04-03 | 2024-04-20 | 2024-04-21 | REFURB |  | 100037219 | 0042 | MOD7 - HSE10 Replace Light Support T1018 (100037219) | LIGHT,EMERG MOD 7 UPPER DECK (AB50.05LT400302W3213) | Replace light bracket (0010) | AB50 | 2024-04-20 |  |  | AB01 |  | 30 | 30 | 10586379 | BOLT ASY,HEX;M16X50MM,GDE 8.8,HDG,N+2W | 4 | 4 | 0 | OK - PDC. | 0 | Material In-Transit on-04-Sea | Stock at Base (SP12) | AB01 | 5300001513 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013656 | N | Preparation (05) | In Preparation (Order) (0055) | 0000135763 | 5 | 3 | 30 | 30 | Supply for Order 100037219, Item 5 cannot be changed 90003253 item 50 already exists | 101000000028846 | 4 | TRUE | 101000000027604 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 24 | 1-Not Started |  | 1000000888 | 0 | 0 | 0.16667 | 2024-03-23 | -11 | 17 | ON TIME |  | On Time | 0 | SOH | 00001357634540210586379000100037219 | 00001357634540210586379000100037219 | 000013576310586379000100037219 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-04-03 | 2024-04-24 | 2024-04-26 | REFURB |  | 100037555 | 0082 | MOD7 - Repl Spool CG-5130339 CDR-29137 (100037555) | LOOP,CORROSION, DEHYDRATION (AB50.05B02-CG01) | replace spool (0020) | AB50 | 2024-04-24 |  |  | AB01 |  | 20 | 20 | 10616560 | 130x75x6mm Insulation Pad, PTFE | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001594 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014440 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136067 | 8 | 4 | 30 | 30 | Supply for Order 100037555, Item 8 cannot be changed 90003262 item 20 already exists | 101000000029743 | 1 | TRUE | 101000000029621 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.125 | 2024-03-27 | -7 | 21 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360674540610616560000100037555 | #N/A | 000013606710616560000100037555 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-04-03 | 2024-04-24 | 2024-04-26 | REFURB |  | 100037555 | 0062 | MOD7 - Repl Spool CG-5130339 CDR-29137 (100037555) | LOOP,CORROSION, DEHYDRATION (AB50.05B02-CG01) | replace spool (0020) | AB50 | 2024-04-24 |  |  | AB01 |  | 20 | 20 | 10616559 | EH2100XX1000.0048 Spool 1 | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001594 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014440 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136067 | 7 | 4 | 30 | 30 | Supply for Order 100037555, Item 7 cannot be changed 90003262 item 10 already exists | 101000000029743 | 1 | TRUE | 101000000029620 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.125 | 2024-03-27 | -7 | 21 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360674540610616559000100037555 | #N/A | 000013606710616559000100037555 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-29 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0520 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-07-10 |  |  | AB01 | 2024-05-05 | 20 | 20 | 11051939 | BOLT,HEX HD,1.5IN LG,SOLATURB 1010791 | 4 | 0 | 4 | OK. - AIR - RFT. | 56 | Material work-packed @AB50 | Directs (Inventory) (SP14) | AB01 | 5300004702 | 130 | 21 | X | 1000004024 | 53 | 2024-02-29 | 2024-05-03 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 4500004813 | 5000041551_2024_0001 | 10 | 4 | EA | 2024-03-15 |  | 180012111 | 180012424 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 53 | 1 | 30 | 30 | Supply for Order 100037574, Item 53 cannot be changed 9000764 item 100 already exists | 101000000027096 | 4 | TRUE |  |  |  | WorkPackLink |  |  | 66 | 0 | 2024-06-30 | 0 | 0 | 2024-05-05 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538711051939000100037574 | #N/A | 000013609811051939000100037574 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-29 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0420 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-04-05 |  |  | AB01 |  | 20 | 20 | 10461404 | FITTING,TORCH,SOLAR;SWAG 960813C1 | 2 | 0 | 2 | OK. - Air Freight | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300004702 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180012780 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 41 | 1 | 30 | 30 | Supply for Order 100037574, Item 41 cannot be changed 90002704 item 10 already exists | 101000000027880 | 2 | TRUE |  |  |  | WorkPackLink |  | 2024-03-23 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 06-Air Passenger | 0 | 3-In Transit |  | 1000000987 | 0 | 0 | 0.020408 | 2024-03-08 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538710461404000100037574 | #N/A | 000013609810461404000100037574 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-29 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0560 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-04-03 |  |  | AB01 | 2024-03-17 | 20 | 20 | 10462880 | ELBOW,PIPE;UNION,0.375",SOLAR 952344C1 | 2 | 0 | 2 | OK. - AIR - RFT. | 30 | Material work-packed @AB50 | Directs (Inventory) (SP14) | AB01 | 5300004702 | 170 | 21 | X | 1000004024 | 57 | 2024-02-29 | 2024-03-15 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 4500004813 | 5000041527_2024_0001 | 40 | 2 | EA | 2024-03-15 |  | 180012111 | 180012424 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 57 | 1 | 30 | 30 | Supply for Order 100037574, Item 57 cannot be changed 9000764 item 130 already exists | 101000000027099 | 2 | TRUE |  |  |  | WorkPackLink |  |  | 17 | 0 | 2024-06-30 | 0 | 0 | 2024-03-17 |  | 0 | 0 |  | 2 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538710462880000100037574 | 00001360984538710462880000100037574 | 000013609810462880000100037574 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-13 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0390 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-04-05 |  |  | AB01 |  | 20 | 20 | 10613300 | TOOL,KIT,SHIM;178X610MM,6HOLES,S G250 | 1 | 0 | 0 | OK. | 0 | Materials handed over to w/ Maintenance | Stock at Base (SP12) | AB01 | 5300004702 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180006424 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 38 | 1 | 30 | 30 | Supply for Order 100037574, Item 38 cannot be changed 90001110 item 10 already exists | 101000000020311 | 1 | TRUE |  |  |  | WorkPackLink | Midship Laydown | 2024-02-25 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000299 | 0 | 0 | 0.020408 | 2024-03-08 | 24 | 52 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538710613300000100037574 | #N/A | 000013609810613300000100037574 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-29 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0530 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-04-03 |  |  | AB01 | 2024-03-17 | 20 | 20 | 10462881 | FITTING,UNION,ELBOW,1/2",SOLAR 960808C1 | 1 | 0 | 1 | OK. - AIR - RFT. | 7 | Material work-packed @AB50 | Directs (Inventory) (SP14) | AB01 | 5300004702 | 140 | 21 | X | 1000004024 | 54 | 2024-02-29 | 2024-03-15 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 4500004813 | 5000041526_2024_0001 | 20 | 1 | EA | 2024-03-15 |  | 180012111 | 180012424 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 54 | 1 | 30 | 30 | Supply for Order 100037574, Item 54 cannot be changed 9000764 item 110 already exists | 101000000027097 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 17 | 0 | 2024-06-30 | 0 | 0 | 2024-03-17 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538710462881000100037574 | #N/A | 000013609810462881000100037574 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 | 2024-02-29 | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0550 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | 2024-04-03 |  |  | AB01 | 2024-03-17 | 20 | 20 | 10463080 | FITTING,PIPE,M,1"X 3/4",SAE/MS,964600C1 | 1 | 0 | 1 | OK. - AIR - RFT. | 7 | Material work-packed @AB50 | Directs (Inventory) (SP14) | AB01 | 5300004702 | 160 | 21 | X | 1000004024 | 56 | 2024-02-29 | 2024-03-15 | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 4500004813 | 5000041538_2024_0001 | 30 | 1 | EA | 2024-03-15 |  | 180012111 | 180012424 | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 56 | 1 | 30 | 30 | Supply for Order 100037574, Item 56 cannot be changed 9000764 item 120 already exists | 101000000027098 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 17 | 0 | 2024-06-30 | 0 | 0 | 2024-03-17 |  | 0 | 0 |  | 1 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 8 | 36 | ON TIME |  | On Time | 0 | Need Purchasing | 00001360984538710463080000100037574 | 00001360984538710463080000100037574 | 000013609810463080000100037574 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-03-28 | 2024-03-30 | MECH |  | 100037795 | 0010 | CLASS Repl 4SWBT Draft Gauge Vlv (100037795) | VALVE,CP850370B,WBT 4 SB,DRAFT GAUGE (AB50.03SP752429) | Empty 4S WBT (0010) | AB50 | 2024-03-28 |  |  | AB01 |  | 10 | 5 | 10439222 | VALVE,COMPL;SHIPHAM DM991209E | 1 | 0 | 2 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300001629 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180009376 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000136296 | 1 | 3 | 30 | 30 |  | 101000000021532 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2026-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-02-29 | -13 | 15 | ON TIME | 4500000792 | During Turnaround | 2024-03-27 | Need Purchasing | 00001362964537910439222000100037795 | 00001362964537910439222000100037795 | 000013629610439222000100037795 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-11 | 2024-04-26 | 2024-05-09 | 2024-05-12 | PAINT |  | 100037796 | 0020 | CT2 - CLASS - Coating 2SCOT AN006 Pittng (100037796) | TANK,CRUDE OIL STORAGE,NO 2 STBD (AB50.COT2-SB) | Apply Belzona + Coatings (0040) | AB50 | 2024-05-11 |  |  | AB01 |  | 10 | 5 | 10493611 | COMPOUND,REPAIR;BELZONA 1111 SUPER MTL | 2 | 57 | 34 | OK. - PDC. | 0 | Material In-Transit on-04-Sea | Stock at Base (SP12) | AB01 | 5300007411 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  | 180011888 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000136297 | 2 | 3 | 30 | 30 | Supply for Order 100037796, Item 2 cannot be changed 90003751 item 10 already exists | 101000000026618 | 2 | TRUE | 101000000026621 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 41 | 1-Not Started |  | 1000000888 | 0 | 0 | 0.5 | 2024-04-13 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001362974542310493611000100037796 | #N/A | 000013629710493611000100037796 | 0 | #N/A | 0
24OKCM16 | Voyage arrived: too late to meet planned Reqmt Dat |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-21 | 2024-01-11 | 2024-04-21 | 2024-04-22 | REFURB |  | 100037863 | 0070 | OR - HSE10 Install Shelves T1054 (100037863) | PKG EQ,PRODUCTION STORE (AB50.05A800021) | install fabricated shelves (0020) | AB50 | 2024-04-21 |  |  | AB01 |  | 30 | 30 | 10571577 | COMPOUND,HARD;BELZONA 1121SUPER XL-M,3KG | 1 | 0 | 1 | OK - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300001647 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180000802 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136344 | 7 | 1 | 30 | 30 | Supply for Order 100037863, Item 7 cannot be changed 90000023 item 10 already exists | 101000000013321 | 1 | TRUE |  |  |  | WorkPackLink | ALLY 05 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000034 | 0 | 0 | 0.14286 | 2024-03-24 | 73 | 101 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363444540310571577000100037863 | #N/A | 000013634410571577000100037863 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-21 | 2024-04-03 | 2024-04-21 | 2024-04-22 | REFURB |  | 100037863 | 0060 | OR - HSE10 Install Shelves T1054 (100037863) | PKG EQ,PRODUCTION STORE (AB50.05A800021) | install fabricated shelves (0020) | AB50 | 2024-04-21 |  |  | AB01 |  | 30 | 30 | 10543313 | WASHER,FLAT;M10,CS,HDG | 4 | 4 | 0 | OK - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001647 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136344 | 6 | 1 | 30 | 30 | Supply for Order 100037863, Item 6 cannot be changed 90003266 item 60 already exists | 101000000017434 | 4 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-24 | -10 | 18 | ON TIME |  | On Time | 0 | SOH | 00001363444540310543313000100037863 | #N/A | 000013634410543313000100037863 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-21 | 2024-04-03 | 2024-04-21 | 2024-04-22 | REFURB |  | 100037863 | 0040 | OR - HSE10 Install Shelves T1054 (100037863) | PKG EQ,PRODUCTION STORE (AB50.05A800021) | install fabricated shelves (0020) | AB50 | 2024-04-21 |  |  | AB01 |  | 30 | 30 | 10586385 | BOLT ASY,HEX;M16X80MM,GDE 8.8,HDG,N+2W | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001647 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014448 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136344 | 4 | 1 | 30 | 30 | Supply for Order 100037863, Item 4 cannot be changed 90003266 item 40 already exists | 101000000029743 | 2 | TRUE | 101000000029656 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.14286 | 2024-03-24 | -10 | 18 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363444540310586385000100037863 | #N/A | 000013634410586385000100037863 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-21 | 2024-04-03 | 2024-04-21 | 2024-04-22 | REFURB |  | 100037863 | 0010 | OR - HSE10 Install Shelves T1054 (100037863) | PKG EQ,PRODUCTION STORE (AB50.05A800021) | install fabricated shelves (0020) | AB50 | 2024-04-21 |  |  | AB01 |  | 30 | 30 | 10616704 | DWG ITEM 1 - Shelf Frame | 1 | 1 | 0 | OK - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001647 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136344 | 1 | 1 |  |  | Supply for Order 100037863, Item 1 cannot be changed 90003266 item 10 already exists | 101000000017396 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-24 | -10 | 18 | ON TIME |  | On Time | 0 | SOH | 00001363444540310616704000100037863 | #N/A | 000013634410616704000100037863 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-21 | 2024-04-03 | 2024-04-21 | 2024-04-22 | REFURB |  | 100037863 | 0020 | OR - HSE10 Install Shelves T1054 (100037863) | PKG EQ,PRODUCTION STORE (AB50.05A800021) | install fabricated shelves (0020) | AB50 | 2024-04-21 |  |  | AB01 |  | 30 | 30 | 10616705 | DWG ITEM 2 - Mesh Shelf | 3 | 3 | 0 | OK - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001647 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136344 | 2 | 1 |  |  | Supply for Order 100037863, Item 2 cannot be changed 90003266 item 20 already exists | 101000000017397 | 3 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-24 | -10 | 18 | ON TIME |  | On Time | 0 | SOH | 00001363444540310616705000100037863 | #N/A | 000013634410616705000100037863 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-21 | 2024-04-03 | 2024-04-21 | 2024-04-22 | REFURB |  | 100037863 | 0050 | OR - HSE10 Install Shelves T1054 (100037863) | PKG EQ,PRODUCTION STORE (AB50.05A800021) | install fabricated shelves (0020) | AB50 | 2024-04-21 |  |  | AB01 |  | 30 | 30 | 10616675 | 65RB 40mm LG Spacer, AS3679-300 | 2 | 2 | 0 | OK - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001647 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136344 | 5 | 1 |  |  | Supply for Order 100037863, Item 5 cannot be changed 90003266 item 50 already exists | 101000000017431 | 2 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.14286 | 2024-03-24 | -10 | 18 | ON TIME |  | On Time | 0 | SOH | 00001363444540310616675000100037863 | #N/A | 000013634410616675000100037863 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 | 2024-04-04 | 2024-04-25 | 2024-04-26 | REFURB |  | 100037864 | 0022 | MOD7 - HSE10 Install Bump Protect T1024 (100037864) | VE,GLYCOL CONTACTOR (AB50.05V130002) | Install bump protection Mod7 (0020) | AB50 | 2024-04-25 |  |  | AB01 |  | 30 | 30 | 10615685 | SHIMPACK | 1 | 1 | 0 | OK. - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001648 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136345 | 5 | 3 | 30 | 30 | Supply for Order 100037864, Item 5 cannot be changed 90003267 item 30 already exists | 101000000029561 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-28 | -7 | 21 | ON TIME |  | On Time | 0 | SOH | 00001363454540710615685000100037864 | #N/A | 000013634510615685000100037864 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 | 2024-04-04 | 2024-04-25 | 2024-04-26 | REFURB |  | 100037864 | 0012 | MOD7 - HSE10 Install Bump Protect T1024 (100037864) | VE,GLYCOL CONTACTOR (AB50.05V130002) | Install bump protection Mod7 (0020) | AB50 | 2024-04-25 |  |  | AB01 |  | 30 | 30 | 10615684 | Bump Protection Barrier | 1 | 1 | 0 | OK. - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001648 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136345 | 4 | 3 | 30 | 30 | Supply for Order 100037864, Item 4 cannot be changed 90003267 item 20 already exists | 101000000029560 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.2 | 2024-03-28 | -7 | 21 | ON TIME |  | On Time | 0 | SOH | 00001363454540710615684000100037864 | #N/A | 000013634510615684000100037864 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 | 2024-04-04 | 2024-04-25 | 2024-04-26 | REFURB |  | 100037864 | 0050 | MOD7 - HSE10 Install Bump Protect T1024 (100037864) | VE,GLYCOL CONTACTOR (AB50.05V130002) | Install bump protection Mod7 (0020) | AB50 | 2024-04-25 |  |  | AB01 |  | 30 | 30 | 10586383 | BOLT ASY,HEX;M16X70MM,GDE 8.8,HDG,N+2W | 2 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001648 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014446 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136345 | 3 | 3 | 30 | 30 | Supply for Order 100037864, Item 3 cannot be changed 90003267 item 10 already exists | 101000000029743 | 2 | TRUE | 101000000029551 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.2 | 2024-03-28 | -7 | 21 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363454540710586383000100037864 | #N/A | 000013634510586383000100037864 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 | 2024-04-03 | 2024-05-02 | 2024-05-03 | REFURB |  | 100037865 | 0022 | D/W - HSE10 Install Handrail Supp T1011 (100037865) | STRUC,TOPSIDES DIRTY WORKSHOP (AB50.05A800010) | Install handrail clamps (0010) | AB50 | 2024-05-02 |  |  | AB01 |  | 30 | 30 | 10615687 | A45-8 Kee Klamp Split Crossover HDG CS | 8 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001649 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014436 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136346 | 2 | 3 | 30 | 30 | Supply for Order 100037865, Item 2 cannot be changed 90003268 item 20 already exists | 101000000029743 | 8 | TRUE | 101000000029566 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 8 | 5-Completed |  | 20000716 | 0 | 0 | 0.5 | 2024-04-04 | 1 | 29 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363464541410615687000100037865 | #N/A | 000013634610615687000100037865 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 | 2024-04-03 | 2024-05-02 | 2024-05-03 | REFURB |  | 100037865 | 0012 | D/W - HSE10 Install Handrail Supp T1011 (100037865) | STRUC,TOPSIDES DIRTY WORKSHOP (AB50.05A800010) | Install handrail clamps (0010) | AB50 | 2024-05-02 |  |  | AB01 |  | 30 | 30 | 10615686 | DN40XS A106B 278mm with Ø48x6PL caps | 4 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001649 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014436 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136346 | 1 | 3 | 30 | 30 | Supply for Order 100037865, Item 1 cannot be changed 90003268 item 10 already exists | 101000000029743 | 4 | TRUE | 101000000029580 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.5 | 2024-04-04 | 1 | 29 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363464541410615686000100037865 | #N/A | 000013634610615686000100037865 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 | 2024-04-04 | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0082 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10442952 | SCREW,SET;HEX HD,M12 X 50MM,SS316L A4/80 | 6 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001650 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014453 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 9 | 3 | 30 | 30 | Supply for Order 100037866, Item 9 cannot be changed 90003269 item 60 already exists | 101000000029743 | 6 | TRUE | 101000000029454 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 6 | 5-Completed |  | 20000716 | 0 | 0 | 0.1 | 2024-04-06 | 2 | 30 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363474541610442952000100037866 | #N/A | 000013634710442952000100037866 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 | 2024-04-04 | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0160 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10418742 | PLUG;HANDRAIL,44X37X25MM,RBR | 4 | 4 | 0 | ISSUE - Procurement - Invntory. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001650 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 6 | 3 | 30 | 30 | Supply for Order 100037866, Item 6 cannot be changed 90003269 item 30 already exists | 101000000024837 | 4 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-04-06 | 2 | 30 | ON TIME |  | On Time | 0 | SOH | 00001363474541610418742000100037866 | #N/A | 000013634710418742000100037866 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 | 2024-04-04 | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0092 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10204779 | NUT,HEX,M12,ISO MTR,NYLOC,SS316 | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001650 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | BOX |  |  |  | 180014453 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 8 | 3 | 30 | 30 | Supply for Order 100037866, Item 8 cannot be changed 90003269 item 50 already exists | 101000000029743 | 1 | TRUE | 101000000029456 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.1 | 2024-04-06 | 2 | 30 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363474541610204779000100037866 | #N/A | 000013634710204779000100037866 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 | 2024-04-04 | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0110 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10418677 | ELBOW;HANDRAIL,90 DEG,KEE 158 | 4 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001650 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014453 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 1 | 3 | 30 | 30 | Supply for Order 100037866, Item 1 cannot be changed 90003269 item 10 already exists | 101000000029743 | 4 | TRUE | 101000000029389 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.1 | 2024-04-06 | 2 | 30 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363474541610418677000100037866 | #N/A | 000013634710418677000100037866 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 | 2024-04-04 | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0072 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10418735 | SCREW,CAP;PL,KEE 1008 | 20 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001650 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014453 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 7 | 3 | 30 | 30 | Supply for Order 100037866, Item 7 cannot be changed 90003269 item 40 already exists | 101000000029743 | 20 | TRUE | 101000000029453 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 20 | 5-Completed |  | 20000716 | 0 | 0 | 0.1 | 2024-04-06 | 2 | 30 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363474541610418735000100037866 | #N/A | 000013634710418735000100037866 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 | 2024-04-04 | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0102 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10059423 | WASHER,FLAT;RND,12 X 37 X 3MM,SS316 | 20 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001650 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014453 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 10 | 3 | 30 | 30 | Supply for Order 100037866, Item 10 cannot be changed 90003269 item 70 already exists | 101000000029743 | 20 | TRUE | 101000000029452 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 20 | 5-Completed |  | 20000716 | 0 | 0 | 0.1 | 2024-04-06 | 2 | 30 | ON TIME |  | On Time | 0 | Need Purchasing | 00001363474541610059423000100037866 | #N/A | 000013634710059423000100037866 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-04 | 2024-04-04 | 2024-05-04 | 2024-05-05 | REFURB |  | 100037866 | 0150 | MIDSHIP LAYDOWN -HSE10 Install Gate TEGR (100037866) | PUMP,GLYCOL (AB50.05P130010) | Fab/Install new Kee-klamp gate support (0010) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10418929 | PIPE,DN40,48.3MM x 4MM x 3050MM LONG | 1 | 1 | 0 | OK. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001650 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136347 | 5 | 3 | 30 | 30 | Supply for Order 100037866, Item 5 cannot be changed 90003269 item 20 already exists | 101000000025000 | 1 | TRUE | 101000000024834 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-04-06 | 2 | 30 | ON TIME |  | On Time | 0 | SOH | 00001363474541610418929000100037866 | #N/A | 000013634710418929000100037866 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-12 | 2024-05-07 | 2024-03-28 | 2024-05-07 | 2024-05-08 | REFURB |  | 100038113 | 0100 | ER - Repl Spool Steam Sys CDR-28781 (100038113) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | Replace 25-SL-3750656-EXB3A-H (0020) | AB50 | 2024-03-26 |  |  | AB01 | 2024-03-26 | 30 | 30 | 70003078 | STUDBOLT;0.625" X 75MM,B7,BLK | 8 | 0 | 0 | OK. | 7 | Material In-Transit on-04-Sea | Directs (Inventory) (SP14) | AB01 | 5300006460 | 60 | 7 | X | 1000003451 | 22 | 2024-03-06 | 2024-03-20 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500004016 | 5000028512_2024_0001 | 10 | 8 | EA | 2024-03-05 |  | /180006872 | 180008879 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136617 | 22 | 1 |  |  | Supply for Order 100038113, Item 22 cannot be changed 9000655 item 30 already exists | 101000000022477 | 8 | TRUE | 101000000022052 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 | 2024-03-26 |  | 0 | 0 | 04-Sea | 8 | 5-Completed |  | 1000000887 | 0 | 0 | 0.16667 | 2024-04-09 | 12 | 40 | ON TIME |  | On Time | 0 | Need Purchasing | 00001366174541970003078000100038113 | #N/A | 000013661770003078000100038113 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-12 | 2024-05-07 | 2024-03-28 | 2024-05-07 | 2024-05-08 | REFURB |  | 100038113 | 0110 | ER - Repl Spool Steam Sys CDR-28781 (100038113) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | Replace 25-SL-3750656-EXB3A-H (0020) | AB50 | 2024-03-26 |  |  | AB01 | 2024-03-26 | 30 | 30 | 70003079 | STUDBOLT;0.625" X 80MM,B7,BLK | 4 | 0 | 0 | OK. | 7 | Material In-Transit on-04-Sea | Directs (Inventory) (SP14) | AB01 | 5300006460 | 70 | 7 | X | 1000003451 | 23 | 2024-03-06 | 2024-03-20 | TRISTAR AUSTRALIA PTY LTD (30000148) | 4500004016 | 5000028495_2024_0001 | 20 | 4 | EA | 2024-03-05 |  | /180006872 | 180008879 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136617 | 23 | 1 |  |  | Supply for Order 100038113, Item 23 cannot be changed 9000655 item 40 already exists | 101000000022477 | 4 | TRUE | 101000000022050 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 | 2024-03-26 |  | 0 | 0 | 04-Sea | 4 | 5-Completed |  | 1000000887 | 0 | 0 | 0.16667 | 2024-04-09 | 12 | 40 | ON TIME |  | On Time | 0 | Need Purchasing | 00001366174541970003079000100038113 | #N/A | 000013661770003079000100038113 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-02-27 | 2024-05-05 | 2024-04-04 | 2024-05-04 | 2024-05-07 | REFURB |  | 100038184 | 0060 | E/R - Repl Spool Steam Cond CDR-28783 (100038184) | LOOP,CORROSION SW1 (AB50.03E10-SW1) | replace 15-SW-3750718-EXA1X-P (0030) | AB50 | 2024-05-05 |  |  | AB01 |  | 30 | 30 | 10422182 | U-BOLT;CLP,40MM,M10,BG181,BINDER 181005 | 2 | 0 | 0 | ETA. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300007229 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014430 | N | Preparation (05) | In Preparation (Order) (0055) | 0000136688 | 6 | 1 | 30 | 30 | Supply for Order 100038184, Item 6 cannot be changed 90003426 item 30 already exists | 101000000029743 | 2 | TRUE | 101000000029741 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-05-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.16667 | 2024-04-07 | 3 | 31 | ON TIME |  | On Time | 0 | Need Purchasing | 00001366884541710422182000100038184 | #N/A | 000013668810422182000100038184 | 0 | #N/A | 0
24OKCM19 | Voyage arrived: too late to meet planned Reqmt Dat |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-12 | 2024-02-23 | 2024-05-09 | 2024-05-14 | MECH |  | 100038587 | 0042 | Paint hot bolt LGC1 flame arrestor bolts (100038587) | ARREST,LGC A,VENT 2ND SEAL GAS (AB50.05SP623004) | Hot Bolt Bolts where required (0030) | AB50 | 2024-05-12 |  |  | AB01 |  | 20 | 20 | 10586568 | BOLT ASY,HEX;M16X35MM,GDE 8.8,HDG,N+2W | 16 | 0 | 16 | OK. - OLC. | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300001726 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007216 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137088 | 4 | 1 | 30 | 30 | Supply for Order 100038587, Item 4 cannot be changed 90001651 item 10 already exists | 101000000020989 | 16 | TRUE | 101000000020942 |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000781 | 0 | 0 | 0.16667 | 2024-04-14 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001370884542410586568000100038587 | #N/A | 000013708810586568000100038587 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-12 | 2024-02-23 | 2024-05-09 | 2024-05-14 | MECH |  | 100038587 | 0042 | Paint hot bolt LGC1 flame arrestor bolts (100038587) | ARREST,LGC A,VENT 2ND SEAL GAS (AB50.05SP623004) | Hot Bolt Bolts where required (0030) | AB50 | 2024-05-12 |  |  | AB01 |  | 20 | 20 | 10586568 | BOLT ASY,HEX;M16X35MM,GDE 8.8,HDG,N+2W | 16 | 0 | 16 | OK. - OLC. | 0 | Materials handed over to w/ Maintenance | Stock at Base (SP12) | AB01 | 5300001726 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007216 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137088 | 4 | 1 | 30 | 30 | Supply for Order 100038587, Item 4 cannot be changed 90001651 item 10 already exists | MINI 696541 | 16 | TRUE | 101000000020942 |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-14 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001370884542410586568000100038587 | #N/A | 000013708810586568000100038587 | 0 | #N/A | 0
24OKCM19 | Voyage arrived: too late to meet planned Reqmt Dat |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-02-20 | 2024-05-09 | 2024-05-14 | MECH |  | 100038587 | 0022 | Paint hot bolt LGC1 flame arrestor bolts (100038587) | ARREST,LGC A,VENT 2ND SEAL GAS (AB50.05SP623004) | Build Scaffold (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10524915 | STUDBOLT;0.500" X 130MM,B7,ZN+XYLAN | 16 | 0 | 16 | OK, - OLC. | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300001726 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007227 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137088 | 2 | 1 | 30 | 30 | Supply for Order 100038587, Item 2 cannot be changed 90001650 item 10 already exists | 101000000020989 | 16 | TRUE | 101000000020941 |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000781 | 0 | 0 | 0.16667 | 2024-04-11 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001370884542110524915000100038587 | #N/A | 000013708810524915000100038587 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-02-20 | 2024-05-09 | 2024-05-14 | MECH |  | 100038587 | 0022 | Paint hot bolt LGC1 flame arrestor bolts (100038587) | ARREST,LGC A,VENT 2ND SEAL GAS (AB50.05SP623004) | Build Scaffold (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 20 | 20 | 10524915 | STUDBOLT;0.500" X 130MM,B7,ZN+XYLAN | 16 | 0 | 16 | OK, - OLC. | 0 | Materials handed over to w/ Maintenance | Stock at Base (SP12) | AB01 | 5300001726 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007227 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137088 | 2 | 1 | 30 | 30 | Supply for Order 100038587, Item 2 cannot be changed 90001650 item 10 already exists | MINI 696541 | 16 | TRUE | 101000000020941 |  |  | WorkPackLink |  |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-04-11 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001370884542110524915000100038587 | #N/A | 000013708810524915000100038587 | 0 | #N/A | 0
24OKCM16 | Del to Maintenance after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-02-15 | 2024-02-08 | 2024-02-15 | 2024-02-19 | MECH |  | 100038738 | 0020 | Repl. Monoflanges SS Fitng to CS Flange (100038738) | VALVE,PDG043121,MAN ISOL (AB50.05MV043040) | Isolate and purge LGC1 Train (0010) | AB50 | 2024-02-23 |  |  | AB01 |  | 20 | 20 | 10449587 | MONOFLANGE,GALPERTI 090503-020-P-28,DBB | 1 | 1 | 2 | OK. - OLC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300001745 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180006430 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137259 | 1 | 1 | 30 | 30 | Supply for Order 100038738, Item 1 cannot be changed 9000343 item 10 already exists | 101000000020184 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 8 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000241 | 0 | 0 | 0.16667 | 2024-01-18 | -21 | 7 | ON TIME |  | On Time | 0 | SOH | 00001372594533710449587000100038738 | #N/A | 000013725910449587000100038738 | 0 | #N/A | 0
24OKCM16 | Del to Maintenance after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-02-15 | 2024-02-08 | 2024-02-15 | 2024-02-19 | MECH |  | 100038738 | 0030 | Repl. Monoflanges SS Fitng to CS Flange (100038738) | VALVE,PDG043121,MAN ISOL (AB50.05MV043040) | Isolate and purge LGC1 Train (0010) | AB50 | 2024-02-23 |  |  | AB01 |  | 20 | 20 | 10449587 | MONOFLANGE,GALPERTI 090503-020-P-28,DBB | 1 | 1 | 2 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300001745 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180006430 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137259 | 2 | 1 | 30 | 30 | Supply for Order 100038738, Item 2 cannot be changed 9000343 item 20 already exists | 101000000020187 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 8 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000241 | 0 | 0 | 0.16667 | 2024-01-18 | -21 | 7 | ON TIME |  | On Time | 0 | SOH | 00001372594533710449587000100038738 | #N/A | 000013725910449587000100038738 | 0 | #N/A | 0
24OKCM16 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-02-15 | 2024-02-08 | 2024-02-15 | 2024-02-19 | MECH |  | 100038738 | 0062 | Repl. Monoflanges SS Fitng to CS Flange (100038738) | VALVE,PDG043121,MAN ISOL (AB50.05MV043040) | Isolate and purge LGC1 Train (0010) | AB50 | 2024-02-23 |  |  | AB01 |  | 20 | 20 | 10058387 | STUDBOLT;0.875" X 165MM,B7,ZN+XYLAN | 16 | 0 | 16 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300001745 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180006430 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137259 | 5 | 1 | 30 | 30 | Supply for Order 100038738, Item 5 cannot be changed 9000343 item 30 already exists | 101000000020180 | 16 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 8 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-01-18 | -21 | 7 | ON TIME |  | On Time | 0 | Need Purchasing | 00001372594533710058387000100038738 | #N/A | 000013725910058387000100038738 | 0 | #N/A | 0
24OKCM16 | Del to Maintenance after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-02-15 | 2024-02-08 | 2024-02-15 | 2024-02-19 | MECH |  | 100038738 | 0012 | Repl. Monoflanges SS Fitng to CS Flange (100038738) | VALVE,PDG043121,MAN ISOL (AB50.05MV043040) | Isolate and purge LGC1 Train (0010) | AB50 | 2024-02-23 |  |  | AB01 |  | 20 | 20 | 10449583 | MONOFLANGE,GALPERTI 090503-010-P-11,DBB | 1 | 0 | 1 | OK. - OLC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300001745 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180009187 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137259 | 6 | 1 | 30 | 30 | Supply for Order 100038738, Item 6 cannot be changed 9000170 item 40 already exists | 101000000020182 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 8 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000241 | 0 | 0 | 0.16667 | 2024-01-18 | -21 | 7 | ON TIME |  | On Time | 0 | Need Purchasing | 00001372594533710449583000100038738 | #N/A | 000013725910449583000100038738 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-10 | 2024-02-21 | 2024-05-09 | 2024-05-12 | MECH |  | 100038806 | 0022 | MOC110643 LGC1 Upgrade ASV Act Stem (100038806) | VALVE,K043300,SURGE CTRL (AB50.05FCV043103) | INSTALL NEW COMPONENTS IN ACTUATOR (0040) | AB50 | 2024-05-10 |  |  | AB01 |  | 10 | 5 | 10605206 | STEM,VV;ACT,SS316,FISHER 1J3329X0022 | 1 | 0 | 1 | OK, - OLC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300001755 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007215 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137307 | 3 | 4 | 30 | 30 | Supply for Order 100038806, Item 3 cannot be changed 90001652 item 10 already exists | 101000000020943 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-12 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001373074542210605206000100038806 | #N/A | 000013730710605206000100038806 | 0 | #N/A | 0
24OKCM19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-10 | 2024-02-21 | 2024-05-09 | 2024-05-12 | MECH |  | 100038806 | 0032 | MOC110643 LGC1 Upgrade ASV Act Stem (100038806) | VALVE,K043300,SURGE CTRL (AB50.05FCV043103) | INSTALL NEW COMPONENTS IN ACTUATOR (0040) | AB50 | 2024-05-10 |  |  | AB01 |  | 10 | 5 | 10605251 | CONN ASY,STEM;SS316,FISHER 18A1671X092 | 1 | 0 | 1 | OK. - OLC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300001755 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007215 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137307 | 4 | 4 | 30 | 30 | Supply for Order 100038806, Item 4 cannot be changed 90001652 item 20 already exists | 101000000020944 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.25 | 2024-04-12 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001373074542210605251000100038806 | #N/A | 000013730710605251000100038806 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 | 2024-04-08 | 2024-04-25 | 2024-04-28 | MECH |  | 100038807 | 0072 | MOC110643 EGC2 Upgrade ASV Act Stem (100038807) | VALVE,FIC042503,ANTI-SURGE CTRL (AB50.05FCV042503) | INSTALL NEW COMPONENTS IN 05FCV042508 (0090) | AB50 | 2024-04-25 |  |  | AB01 |  | 10 | 5 | 10605252 | CONN ASY,STEM;SS316,FISHER 18A1672F032 | 1 | 0 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001756 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014438 | N | Preparation (05) | In Preparation (Order) (0055) | 0000137308 | 8 | 4 | 30 | 30 | Supply for Order 100038807, Item 8 cannot be changed 90003277 item 20 already exists | 101000000029743 | 1 | TRUE | 101000000029565 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.125 | 2024-03-28 | -11 | 17 | ON TIME |  | On Time | 0 | Need Purchasing | 00001373084540710605252000100038807 | #N/A | 000013730810605252000100038807 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 | 2024-04-04 | 2024-04-25 | 2024-04-28 | MECH |  | 100038807 | 0012 | MOC110643 EGC2 Upgrade ASV Act Stem (100038807) | VALVE,FIC042503,ANTI-SURGE CTRL (AB50.05FCV042503) | INSTALL NEW COMPONENTS IN ACTUATOR (0040) | AB50 | 2024-04-25 |  |  | AB01 |  | 10 | 5 | 10605250 | STEM,VV;ACT,SS316,FISHER 1V9656F0012 | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001756 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014459 | N | Preparation (05) | In Preparation (Order) (0055) | 0000137308 | 2 | 4 | 30 | 30 | Supply for Order 100038807, Item 2 cannot be changed 90003276 item 10 already exists | 101000000029743 | 1 | TRUE | 101000000029553 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.125 | 2024-03-28 | -7 | 21 | ON TIME |  | On Time | 0 | Need Purchasing | 00001373084540710605250000100038807 | #N/A | 000013730810605250000100038807 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 | 2024-04-04 | 2024-04-25 | 2024-04-28 | MECH |  | 100038807 | 0022 | MOC110643 EGC2 Upgrade ASV Act Stem (100038807) | VALVE,FIC042503,ANTI-SURGE CTRL (AB50.05FCV042503) | INSTALL NEW COMPONENTS IN ACTUATOR (0040) | AB50 | 2024-04-25 |  |  | AB01 |  | 10 | 5 | 10605253 | CONN ASY,STEM;SS316,FISHER 18A1685X022 | 1 | 0 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001756 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014459 | N | Preparation (05) | In Preparation (Order) (0055) | 0000137308 | 3 | 4 | 30 | 30 | Supply for Order 100038807, Item 3 cannot be changed 90003276 item 20 already exists | 101000000029743 | 1 | TRUE | 101000000029554 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.125 | 2024-03-28 | -7 | 21 | ON TIME |  | On Time | 0 | Need Purchasing | 00001373084540710605253000100038807 | #N/A | 000013730810605253000100038807 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 | 2024-04-08 | 2024-04-25 | 2024-04-28 | MECH |  | 100038807 | 0062 | MOC110643 EGC2 Upgrade ASV Act Stem (100038807) | VALVE,FIC042503,ANTI-SURGE CTRL (AB50.05FCV042503) | INSTALL NEW COMPONENTS IN 05FCV042508 (0090) | AB50 | 2024-04-25 |  |  | AB01 |  | 10 | 5 | 10605207 | STEM,VV;ACT,SS316,FISHER 1E8324X0012 | 1 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001756 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014438 | N | Preparation (05) | In Preparation (Order) (0055) | 0000137308 | 7 | 4 | 30 | 30 | Supply for Order 100038807, Item 7 cannot be changed 90003277 item 10 already exists | 101000000029743 | 1 | TRUE | 101000000029558 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.125 | 2024-03-28 | -11 | 17 | ON TIME |  | On Time | 0 | Need Purchasing | 00001373084540710605207000100038807 | #N/A | 000013730810605207000100038807 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-25 | 2024-04-04 | 2024-04-25 | 2024-04-28 | MECH |  | 100038807 | 0030 | MOC110643 EGC2 Upgrade ASV Act Stem (100038807) | VALVE,FIC042503,ANTI-SURGE CTRL (AB50.05FCV042503) | INSTALL NEW COMPONENTS IN ACTUATOR (0040) | AB50 | 2024-04-25 |  |  | AB01 |  | 10 | 5 | 10605255 | SCREW,ADJ;ACT,FISHER 1N1297X0062 | 1 | 0 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001756 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014459 | N | Preparation (05) | In Preparation (Order) (0055) | 0000137308 | 4 | 4 | 30 | 30 | Supply for Order 100038807, Item 4 cannot be changed 90003276 item 30 already exists | 101000000029743 | 1 | TRUE | 101000000029555 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2024-07-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.125 | 2024-03-28 | -7 | 21 | ON TIME |  | On Time | 0 | Need Purchasing | 00001373084540710605255000100038807 | #N/A | 000013730810605255000100038807 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-02 | 2024-03-15 | 2024-03-29 | 2024-04-03 | PAINT |  | 100038880 | 0020 | CT2 - 2WBT STBD FWD Ramp Blast & Replace (100038880) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | 2024-04-02 |  |  | AB01 |  | 20 | 20 | 10493611 | COMPOUND,REPAIR;BELZONA 1111 SUPER MTL | 2 | 57 | 34 | OK. | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300005825 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  | 180006920 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137381 | 8 | 4 | 30 | 30 | Supply for Order 100038880, Item 8 cannot be changed 90001902 item 10 already exists | 101000000019918 | 2 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 41 |  |  |  | 0 | 0 | 0.125 | 2024-03-05 | -10 | 18 | ON TIME |  | On Time | 0 | SOH | 00001373814538410493611000100038880 | #N/A | 000013738110493611000100038880 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-15 | 2024-02-13 | 2024-04-11 | 2024-04-16 | PAINT |  | 100038883 | 0020 | CT4 - 4WBT PORT AFT Ramp Blast & Replace (100038883) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | 2024-04-15 |  |  | AB01 |  | 20 | 20 | 10493611 | COMPOUND,REPAIR;BELZONA 1111 SUPER MTL | 2 | 57 | 34 | OK. | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300005828 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  | 180006413 | N | Execution (07) | Main Work Started (Order) (0070) | 0000137384 | 7 | 4 | 30 | 30 | Supply for Order 100038883, Item 7 cannot be changed 90001118 item 10 already exists | 101000000020358 | 2 | TRUE | 101000000019911 |  |  | WorkPackLink |  | 2024-01-31 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 41 | 3-In Transit |  | 1000000172 | 0 | 0 | 0.125 | 2024-03-18 | 34 | 62 | ON TIME |  | On Time | 0 | SOH | 00001373844539710493611000100038883 | #N/A | 000013738410493611000100038883 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-11 | 2024-03-15 | 2024-04-06 | 2024-04-12 | PAINT |  | 100038887 | 0030 | CT2 - 2COT PORT X-Over Ramp Blst&Replace (100038887) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | 2024-04-11 |  |  | AB01 |  | 20 | 20 | 10493611 | COMPOUND,REPAIR;BELZONA 1111 SUPER MTL | 2 | 57 | 34 | OK. | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300005837 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  | 180006930 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137388 | 8 | 4 | 30 | 30 | Supply for Order 100038887, Item 8 cannot be changed 90001906 item 10 already exists | 101000000019932 | 2 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 41 |  |  |  | 0 | 0 | 0.125 | 2024-03-14 | -1 | 27 | ON TIME |  | On Time | 0 | SOH | 00001373884539310493611000100038887 | #N/A | 000013738810493611000100038887 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-08 | 2024-03-15 | 2024-04-04 | 2024-04-09 | PAINT |  | 100038888 | 0020 | CT2 - 2COT STBD X-Over Ramp Blst&Replace (100038888) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | 2024-04-08 |  |  | AB01 |  | 20 | 20 | 10493611 | COMPOUND,REPAIR;BELZONA 1111 SUPER MTL | 2 | 57 | 34 | UserCommentLink | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300005838 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  | 180006929 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000137389 | 7 | 4 | 30 | 30 | Supply for Order 100038888, Item 7 cannot be changed 90001907 item 10 already exists | 101000000019933 | 2 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 41 |  |  |  | 0 | 0 | 0.125 | 2024-03-11 | -4 | 24 | ON TIME |  | On Time | 0 | SOH | 00001373894539010493611000100038888 | #N/A | 000013738910493611000100038888 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-03-31 | 2024-02-19 | 2024-03-29 | 2024-04-02 | PAINT |  | 100038890 | 0020 | CT4 - 4WBT PORT FWD Ramp Blast & Replace (100038890) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | 2024-03-31 |  |  | AB01 |  | 20 | 20 | 10493611 | COMPOUND,REPAIR;BELZONA 1111 SUPER MTL | 2 | 57 | 34 | UserCommentLink | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300005845 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  | 180006396 | N | Execution (07) | Main Work Started (Order) (0070) | 0000137391 | 7 | 4 | 30 | 30 | Supply for Order 100038890, Item 7 cannot be changed 90001120 item 10 already exists | 101000000020358 | 2 | TRUE | 101000000019916 |  |  | WorkPackLink |  | 2024-01-31 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 41 | 3-In Transit |  | 1000000172 | 0 | 0 | 0.125 | 2024-03-03 | 13 | 41 | ON TIME |  | On Time | 0 | SOH | 00001373914538210493611000100038890 | #N/A | 000013739110493611000100038890 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-17 | 2024-02-15 | 2024-04-13 | 2024-04-19 | PAINT |  | 100038891 | 0030 | CT5 - 5COT PORT X-Over Ramp Blst&Replace (100038891) | STRUC,VESSEL DECKING (AB50.03DECK01) | Apply Belzona to Ramp Edges (0060) | AB50 | 2024-04-17 |  |  | AB01 |  | 20 | 20 | 10493611 | COMPOUND,REPAIR;BELZONA 1111 SUPER MTL | 2 | 57 | 34 | OK. | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300005846 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | KG |  |  |  | 180006932 | N | Execution (07) | Main Work Started (Order) (0070) | 0000137392 | 8 | 4 | 30 | 30 | Supply for Order 100038891, Item 8 cannot be changed 90001121 item 10 already exists | 101000000020358 | 2 | TRUE | 101000000019807 |  |  | WorkPackLink |  | 2024-01-31 | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 41 | 3-In Transit |  | 1000000172 | 0 | 0 | 0.125 | 2024-03-20 | 34 | 62 | ON TIME |  | On Time | 0 | SOH | 00001373924539910493611000100038891 | #N/A | 000013739210493611000100038891 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-31 | 2024-05-04 | 2024-04-03 | 2024-05-04 | 2024-05-05 | REFURB |  | 100039045 | 0020 | ER - Repl Spool LP Steam Sys CDR-28782 (100039045) | LOOP,CORROSION SL1 (AB50.03E10-SL1) | replace spool (0020) | AB50 | 2024-05-04 |  |  | AB01 |  | 30 | 30 | 10058453 | STUDBOLT;0.500" X 65MM,B7,BLK | 8 | 8 | 0 | OK - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300005852 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137519 | 2 | 1 | 30 | 30 | Supply for Order 100039045, Item 2 cannot be changed 90003375 item 10 already exists | 101000000018400 | 8 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-05-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-04-06 | 3 | 31 | ON TIME |  | On Time | 0 | SOH | 00001375194541610058453000100039045 | #N/A | 000013751910058453000100039045 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-04-03 | 2024-04-24 | 2024-04-24 | MECH |  | 100039936 | 0022 | CLASS Replace ER Draft Gauge Vlv Potenti (100039936) | VALVE,CP850370C,ENG ROOM HYD HAND VALVE (AB50.03SP752427) | ROV Scope Awareness (0010) | AB50 | 2024-04-24 |  |  | AB01 |  | 10 | 5 | 10245447 | GASKET;CNAF,JIS10K,80MM,1.5MM,FF,C4430 | 2 | 2 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300002106 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014447 | N | Preparation (05) | In Preparation (Order) (0055) | 0000138437 | 2 | 3 | 30 | 30 | Supply for Order 100039936, Item 2 cannot be changed 90003285 item 20 already exists | 101000000029743 | 2 | TRUE | 101000000029623 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2026-05-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.33333 | 2024-03-27 | -7 | 21 | ON TIME |  | On Time | 0 | SOH | 00001384374540610245447000100039936 | 00001384374540610245447000100039936 | 000013843710245447000100039936 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-04-03 | 2024-04-24 | 2024-04-24 | MECH |  | 100039936 | 0032 | CLASS Replace ER Draft Gauge Vlv Potenti (100039936) | VALVE,CP850370C,ENG ROOM HYD HAND VALVE (AB50.03SP752427) | ROV Scope Awareness (0010) | AB50 | 2024-04-24 |  |  | AB01 |  | 10 | 5 | 10606651 | BOLT ASY;HEX,M16X65MM,CAD PLTD,ALLOY ST | 16 | 16 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300002106 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014447 | N | Preparation (05) | In Preparation (Order) (0055) | 0000138437 | 3 | 3 | 30 | 30 | Supply for Order 100039936, Item 3 cannot be changed 90003285 item 30 already exists | 101000000029743 | 16 | TRUE | 101000000029927 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2026-05-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 32 | 5-Completed |  | 20000716 | 0 | 0 | 0.33333 | 2024-03-27 | -7 | 21 | ON TIME |  | On Time | 0 | SOH | 00001384374540610606651000100039936 | 00001384374540610606651000100039936 | 000013843710606651000100039936 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 | 2024-02-20 | 2024-05-02 | 2024-05-02 | MECH |  | 100040126 | 0042 | Replace SAS Vessel 04BDV621081 (100040126) | VALVE,BLOWDOWN,TEST SEP PROD FLUIDS (AB50.04BDV621081) | REMOVE/REPLACE SAS VESSEL (0010) | AB50 | 2024-05-02 |  |  | AB01 |  | 20 | 20 | 10433043 | BOLT ASY,HEX HD;WITH NUT+WSH,M14X55MM | 12 | 0 | 15 | OK. - OLC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300002155 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007214 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000138627 | 2 | 3 | 30 | 30 | Supply for Order 100040126, Item 2 cannot be changed 90001655 item 20 already exists | 101000000020948 | 12 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-04 | 44 | 72 | ON TIME |  | On Time | 0 | Need Purchasing | 00001386274541410433043000100040126 | #N/A | 000013862710433043000100040126 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-02 | 2024-02-20 | 2024-05-02 | 2024-05-02 | MECH |  | 100040126 | 0022 | Replace SAS Vessel 04BDV621081 (100040126) | VALVE,BLOWDOWN,TEST SEP PROD FLUIDS (AB50.04BDV621081) | REMOVE/REPLACE SAS VESSEL (0010) | AB50 | 2024-05-02 |  |  | AB01 |  | 20 | 20 | 10433043 | BOLT ASY,HEX HD;WITH NUT+WSH,M14X55MM | 3 | 0 | 15 | OK. - OLC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300002155 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007214 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000138627 | 1 | 3 | 30 | 30 | Supply for Order 100040126, Item 1 cannot be changed 90001655 item 10 already exists | 101000000020946 | 3 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-04 | 44 | 72 | ON TIME |  | On Time | 0 | Need Purchasing | 00001386274541410433043000100040126 | #N/A | 000013862710433043000100040126 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 | 2024-04-03 | 2024-04-04 | 2024-04-05 | INLEC |  | 100040734 | 0012 | Replace GMDSS HF TX Antenna (100040734) | ANTENNA,MF/HF TX/RX ANTENNA (AB50.03CAHF612804) | Replace GMDSS HF TX Antenna (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 10 | 5 | 10426703 | ANTENNA;COMROD AT82 | 1 | 0 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300002319 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007209 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000139266 | 1 | 3 | 30 | 30 | Supply for Order 100040734, Item 1 cannot be changed 90002427 item 10 already exists | 101000000020962 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 14 | 2024-05-04 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000881 | 0 | 0 | 1 | 2024-03-07 | -27 | 1 | ON TIME |  | On Time | 0 | Need Purchasing | 00001392664538610426703000100040734 | #N/A | 000013926610426703000100040734 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 | 2024-04-03 | 2024-04-04 | 2024-04-05 | INLEC |  | 100040735 | 0020 | Replace GMDSS HF RX Antenna (100040735) | ANTENNA,MF/HF DSC RX ANTENNA (AB50.03CAHF612805) | Replace GMDSS HF RX Antenna (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 10 | 5 | 10468906 | ANTENNA;COMROD AR62 | 1 | 0 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300002322 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007205 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000139267 | 2 | 3 | 30 | 30 | Supply for Order 100040735, Item 2 cannot be changed 9000152 item 20 already exists | 101000000020964 | 1 | TRUE |  |  |  | WorkPackLink | Okha Stores |  | 0 | 14 | 2024-05-04 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000881 | 0 | 0 | 0.5 | 2024-03-07 | -27 | 1 | ON TIME |  | On Time | 2024-01-15 | Need Purchasing | 00001392674538610468906000100040735 | 00001392674538610468906000100040735 | 000013926710468906000100040735 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-03 | 2024-04-09 | 2024-03-30 | 2024-04-08 | REFURB |  | 100040991 | 0052 | RA - HSE10 Install Bracket & Cable Tray (100040991) | TURRET,ELECTRICAL SWIVEL (AB50.04V098103) | Install bracket & cable tray (0030) | AB50 | 2024-04-24 |  |  | AB01 |  | 20 | 20 | 10058034 | BOLT ASY;HEX HD,M10X40MM,SS316L,A480 | 4 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300000284 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014437 | N | Preparation (05) | In Preparation (Order) (0055) | 0000139525 | 3 | 3 | 30 | 30 | Supply for Order 100040991, Item 3 cannot be changed 90003199 item 20 already exists | 101000000029743 | 4 | TRUE | 101000000029567 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 21 | 2023-06-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.33333 | 2024-03-06 | -34 | -6 | Delayed |  | On Time | 0 | Need Purchasing | 00001395254538510058034000100040991 | #N/A | 000013952510058034000100040991 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 | 2024-04-03 | 2024-04-27 | 2024-04-28 | MECH |  | 100043119 | 0012 | D - Replace EGC2 PDT Isol Valves (100043119) | VALVE,PDT460520,MAN ISOL (AB50.05MV460127) | Replace EGC2 PDT Isol Valves (0020) | AB50 | 2024-04-27 |  |  | AB01 |  | 20 | 20 | 10446530 | VALVE,GATE;1.500",VALVITALIA 40GA0101T | 1 | 1 | 2 | OK. - OLC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300001154 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014420 | N | Preparation (05) | In Preparation (Order) (0055) | 0000141703 | 3 | 4 | 30 | 30 | Supply for Order 100043119, Item 3 cannot be changed 90003237 item 10 already exists | 101000000029362 | 1 | TRUE |  |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2022-10-30 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.25 | 2024-03-30 | -4 | 24 | ON TIME |  | On Time | 0 | SOH | 00001417034540910446530000100043119 | #N/A | 000014170310446530000100043119 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-27 | 2024-04-03 | 2024-04-27 | 2024-04-28 | MECH |  | 100043119 | 0022 | D - Replace EGC2 PDT Isol Valves (100043119) | VALVE,PDT460520,MAN ISOL (AB50.05MV460127) | Replace EGC2 PDT Isol Valves (0020) | AB50 | 2024-04-27 |  |  | AB01 |  | 20 | 20 | 10446530 | VALVE,GATE;1.500",VALVITALIA 40GA0101T | 1 | 1 | 2 | OK. - OLC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300001154 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000141703 | 4 | 4 | 30 | 30 | Supply for Order 100043119, Item 4 cannot be changed 90003237 item 20 already exists | 101000000025271 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2022-10-30 | 0 | 0 |  |  | 0 | 0 |  | 1 |  |  |  | 0 | 0 | 0.25 | 2024-03-30 | -4 | 24 | ON TIME |  | On Time | 0 | SOH | 00001417034540910446530000100043119 | #N/A | 000014170310446530000100043119 | 0 | #N/A | 0
24OKCM16 | Supply too early, consider delaying |  | Released | 2024-01-26 | 2024-02-09 | 2024-04-27 | 2024-04-03 | 2024-04-27 | 2024-04-27 | INLEC |  | 100072233 | 0010 | Replace magnetic compass lamp holder (100072233) | NAVAID,MAGNETIC COMPASS (AB50.03CEMC612822) | Replace mag compass lamp holder & Test (0010) | AB50 | 2024-03-30 |  |  | AB01 | 2024-03-30 | 10 | 5 | 11400347 | HOLDER,LAMP;75W,125V,MULTICOMPPRO CB25 | 1 | 1 | 0 | ETA. - R. | 21 | Material work-packed @AB01 | Directs (Inventory) (SP14) | AB01 | 5300006296 | 10 | 21 | X | 1000002197 | 1 | 2024-02-28 | 2024-03-28 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 4500006027 | 5000047659_2024_0001 | 10 | 1 | EA | 2024-04-01 |  | /180013463 |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000216769 | 1 | 1 | 30 | 30 | Supply for Order 100072233, Item 1 cannot be changed 90003385 item 10 already exists | 101000000030058 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-27 | 0 | 0 | 2024-03-30 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-03-30 | -4 | 24 | ON TIME |  | On Time | 0 | SOH | 00002167694540911400347000100072233 | #N/A | 000021676911400347000100072233 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2024-02-02 | 2024-02-22 | 2024-05-02 | 2024-04-30 | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0060 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING IG HEADER SPADES (0100) | AB50 | 2024-05-15 |  |  | AB01 |  | 10 | 5 | 10503901 | SCREW,SET;HEX,HVY,7/8" X 120MM,A193,B7 | 24 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300006987 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014428 | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 28 | 4 | 30 | 30 | Supply for Order 100072584, Item 28 cannot be changed 90003410 item 10 already exists | 101000000029743 | 24 | TRUE | 101000000029459 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 13 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 | 01-Road | 24 | 5-Completed |  | 20000716 | 0 | 0 | 0.0625 | 2024-04-04 | -26 | 2 | ON TIME |  | After Turnround | 2024-04-10 | Need Purchasing | 00002185114541410503901000100072584 | 00002185114541410503901000100072584 | 000021851110503901000100072584 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2024-02-02 | 2024-02-22 | 2024-04-30 | 2024-04-29 | 2024-04-25 | 2024-05-11 | INSP |  | 100072584 | 0040 | Re-inspect Wrap COT4P CDR-17778 (100072584) | TANK,CRUDE OIL STORAGE,NO 4 PORT (AB50.COT4-PS) | SWING LOAD HEADER SPADES (0080) | AB50 | 2024-05-14 |  |  | AB01 |  | 10 | 5 | 10208071 | STUDBOLT;0.875"X160MM,B7,CAD+XYLAN | 24 | 0 | 24 | OK - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300006987 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180010548 | N | Preparation (05) | In Preparation (Order) (0055) | 0000218511 | 24 | 4 | 30 | 30 | Supply for Order 100072584, Item 24 cannot be changed 9000393 item 10 already exists | 101000000024053 | 24 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 14 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.0625 | 2024-04-02 | -27 | 1 | ON TIME |  | On Time | 0 | Need Purchasing | 00002185114541210208071000100072584 | #N/A | 000021851110208071000100072584 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-03-15 | 2024-04-22 | 2024-04-25 | INSP |  | 200082341 | 0030 | 5Y INT INSP/CLASS SURVEY 03E753050 (200082341) | VE,ATMOSPHERIC CONDENSER (AB50.03E753050) | RE-INSTATE SPOOL/HEAD POST INSPECTION (0060) | AB50 | 2024-04-24 |  |  | AB01 |  | 10 | 5 | 10245442 | GASKET;CNAF,JIS5K,200MM,3MM,FF,C4430 | 4 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300003505 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014444 | N | Preparation (05) | In Preparation (Order) (0055) | 0000118169 | 3 | 4 | 30 | 30 | Supply for Order 200082341, Item 3 cannot be changed 90002199 item 20 already exists | 101000000029743 | 4 | TRUE | 101000000029625 |  |  | WorkPackLink | OKHA | 2024-03-30 | 0 | 0 | 2024-05-20 | 0 | 0 |  |  | 0 | 0 | 01-Road | 4 | 5-Completed |  | 20000716 | 0 | 0 | 0.14286 | 2024-03-27 | 12 | 40 | ON TIME |  | On Time | 0 | Need Purchasing | 00001181694540610245442000200082341 | #N/A | 000011816910245442000200082341 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-03-15 | 2024-04-22 | 2024-04-25 | INSP |  | 200082341 | 0040 | 5Y INT INSP/CLASS SURVEY 03E753050 (200082341) | VE,ATMOSPHERIC CONDENSER (AB50.03E753050) | RE-INSTATE SPOOL/HEAD POST INSPECTION (0060) | AB50 | 2024-04-24 |  |  | AB01 |  | 10 | 5 | 10299450 | STUDBOLT;M20 X 100MM,GDE B7,CAD+PTFE | 16 | 0 | 0 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300003505 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014444 | N | Preparation (05) | In Preparation (Order) (0055) | 0000118169 | 4 | 4 | 30 | 30 | Supply for Order 200082341, Item 4 cannot be changed 90002199 item 30 already exists | 101000000029743 | 16 | TRUE | 101000000029408 |  |  | WorkPackLink | OKHA | 2024-03-30 | 0 | 0 | 2024-05-20 | 0 | 0 |  |  | 0 | 0 | 01-Road | 16 | 5-Completed |  | 20000716 | 0 | 0 | 0.14286 | 2024-03-27 | 12 | 40 | ON TIME |  | On Time | 0 | Need Purchasing | 00001181694540610299450000200082341 | #N/A | 000011816910299450000200082341 | 0 | #N/A | 0
24OKCM16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-24 | 2024-03-15 | 2024-04-22 | 2024-04-25 | INSP |  | 200082341 | 0050 | 5Y INT INSP/CLASS SURVEY 03E753050 (200082341) | VE,ATMOSPHERIC CONDENSER (AB50.03E753050) | RE-INSTATE SPOOL/HEAD POST INSPECTION (0060) | AB50 | 2024-04-24 |  |  | AB01 |  | 10 | 5 | 10245445 | GASKET;CNAF,JIS5K,100MM,3MM,FF,C4430 | 2 | 6 | 8 | OK - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300003505 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014444 | N | Preparation (05) | In Preparation (Order) (0055) | 0000118169 | 5 | 4 | 30 | 30 | Supply for Order 200082341, Item 5 cannot be changed 90002199 item 40 already exists | 101000000029743 | 2 | TRUE | 101000000029569 |  |  | WorkPackLink | OKHA | 2024-03-30 | 0 | 0 | 2024-05-20 | 0 | 0 |  |  | 0 | 0 | 01-Road | 2 | 5-Completed |  | 20000716 | 0 | 0 | 0.14286 | 2024-03-27 | 12 | 40 | ON TIME |  | On Time | 0 | SOH | 00001181694540610245445000200082341 | #N/A | 000011816910245445000200082341 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-05 | 2024-05-13 | 2024-05-05 | 2024-05-06 | MECH |  | 200083040 | 0012 | 6M P05 INSP/LUBE OF TURRET SWIVEL UNITS (200083040) | TURRET,PRODUCTION SWIVEL 1 (AB50.04V020001) | INSPECT & LUBRICATE TURRET SWIVEL (0010) | AB50 | 2024-05-27 |  |  | AB01 |  | 10 | 5 | 10503159 | SAMPLE KIT,OIL;SGS OVERPACK250ML | 10 | 1 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300003857 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180014442 | N | Preparation (05) | In Preparation (Order) (0055) | 0000119827 | 3 | 4 | 30 | 30 | Supply for Order 200083040, Item 3 cannot be changed 90003342 item 10 already exists | 101000000029743 | 10 | TRUE | 101000000029458 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 22 | 2024-05-28 | 0 | 0 |  |  | 0 | 0 | 01-Road | 10 | 5-Completed |  | 20000716 | 0 | 0 | 0.33333 | 2024-04-07 | -36 | -8 | Delayed |  | On Time | 0 | Need Purchasing | 00001198274541710503159000200083040 | #N/A | 000011982710503159000200083040 | 0 | #N/A | 0
24OKCO13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-03-28 | 2024-04-04 | INLEC |  | 200083405 | 0012 | 6M F27 PORTABLE APPLIANCE TEST & TAG (200083405) | PKG EQ,PORTABLE EX AND NON-EX ELEC EQUIP (AB50.PORTELEQUIP) | INSPECT, TEST & RE-TAG PORTABLE EQUIP (0010) | AB50 | 2024-03-28 |  |  | AB01 |  | 10 | 5 | 10535547 | TAG,TEST;ORANGE,THERMAL,OPTIMA | 1 | 2 | 0 | OK. - PDC. | 0 | Material work-packed @AB01 | Stock at Base (SP12) | AB01 | 5300003941 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120685 | 1 | 3 | 30 | 30 | Supply for Order 200083405, Item 1 cannot be changed 90002064 item 10 already exists | 101000000023464 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001206854537910535547000200083405 | #N/A | 000012068510535547000200083405 | 0 | #N/A | 0
24OKCO13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-03-28 | 2024-04-04 | INLEC |  | 200083405 | 0022 | 6M F27 PORTABLE APPLIANCE TEST & TAG (200083405) | PKG EQ,PORTABLE EX AND NON-EX ELEC EQUIP (AB50.PORTELEQUIP) | INSPECT, TEST & RE-TAG PORTABLE EQUIP (0010) | AB50 | 2024-03-28 |  |  | AB01 |  | 10 | 5 | 10535548 | TAG,TEST;GRN,THERMAL,OPTIMA | 1 | 1 | 1 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300003941 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ROL |  |  |  | 180013488 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000120685 | 2 | 3 | 30 | 30 | Supply for Order 200083405, Item 2 cannot be changed 90002064 item 20 already exists | 696861 | 1 | TRUE | 101000000023465 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-05-10 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00001206854537910535548000200083405 | #N/A | 000012068510535548000200083405 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 | 2024-04-03 | 2024-04-04 | 2024-04-04 | INLEC |  | 200084031 | 0042 | 1Y RADAR MAGNETRON REPLACEMENT (200084031) | ANTENNA,S BAND ANTENNA (AB50.03CARD612806) | REMOVE & REPLACE RADAR MAGNETRON (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 10 | 5 | 10471895 | PCB ASY,MARKER,NORTHROP T65801805 | 1 | 0 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004084 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007220 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122040 | 6 | 4 | 30 | 30 | Supply for Order 200084031, Item 6 cannot be changed 90002426 item 30 already exists | 101000000020959 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 14 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-07 | -27 | 1 | ON TIME |  | On Time | 0 | Need Purchasing | 00001220404538610471895000200084031 | #N/A | 000012204010471895000200084031 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 | 2024-04-03 | 2024-04-04 | 2024-04-04 | INLEC |  | 200084031 | 0062 | 1Y RADAR MAGNETRON REPLACEMENT (200084031) | ANTENNA,S BAND ANTENNA (AB50.03CARD612806) | REMOVE & REPLACE RADAR MAGNETRON (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 10 | 5 | 10471894 | PCB ASY,POWER SUPPLY,NORTHROP T65801809 | 1 | 0 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004084 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007220 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122040 | 5 | 4 | 30 | 30 | Supply for Order 200084031, Item 5 cannot be changed 90002426 item 20 already exists | 101000000020958 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 14 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-07 | -27 | 1 | ON TIME |  | On Time | 0 | Need Purchasing | 00001220404538610471894000200084031 | #N/A | 000012204010471894000200084031 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-04 | 2024-04-03 | 2024-04-04 | 2024-04-04 | INLEC |  | 200084031 | 0052 | 1Y RADAR MAGNETRON REPLACEMENT (200084031) | ANTENNA,S BAND ANTENNA (AB50.03CARD612806) | REMOVE & REPLACE RADAR MAGNETRON (0010) | AB50 | 2024-04-18 |  |  | AB01 |  | 10 | 5 | 10471890 | PCB ASY,TRIGGER,NORTHROP T65801801 | 1 | 0 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004084 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007220 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000122040 | 4 | 4 | 30 | 30 | Supply for Order 200084031, Item 4 cannot be changed 90002426 item 10 already exists | 101000000020957 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 14 | 2024-04-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.16667 | 2024-03-07 | -27 | 1 | ON TIME |  | On Time | 0 | Need Purchasing | 00001220404538610471890000200084031 | #N/A | 000012204010471890000200084031 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-07 | 2024-02-20 | 2024-03-07 | 2024-03-19 | MECH |  | 200085163 | 0010 | 2Y F21 BIOC INJ TEST SEP NRV TEST/REPL (200085163) | VALVE,CHECK BIOCIDE INJ TO TEST SEP (AB50.04MV020050) | CHANGE OUT VALVE (0020) | AB50 | 2024-03-07 |  |  | AB01 |  | 10 | 5 | 10574508 | VALVE,CHK;LIFT,DN20,316SS | 1 | 2 | 1 | OK. - OLC. | 0 | Materials handed over to w/ Maintenance | Stock at Base (SP12) | AB01 | 5300003502 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007201 | N | Post Execution (08) | Work Done (Order) (0080) | 0000123413 | 1 | 1 | 30 | 30 | Supply for Order 200085163, Item 1 cannot be changed 90001661 item 10 already exists | MINI 696541 | 1 | TRUE | 101000000020951 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-13 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-08 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001234134535810574508000200085163 | 00001234134535810574508000200085163 | 000012341310574508000200085163 | 0 | #N/A | 0
24OKCM13 | Del to Maintenance after Reqmt Date |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-07 | 2024-02-20 | 2024-03-07 | 2024-03-19 | MECH |  | 200085163 | 0010 | 2Y F21 BIOC INJ TEST SEP NRV TEST/REPL (200085163) | VALVE,CHECK BIOCIDE INJ TO TEST SEP (AB50.04MV020050) | CHANGE OUT VALVE (0020) | AB50 | 2024-03-07 |  |  | AB01 |  | 10 | 5 | 10574508 | VALVE,CHK;LIFT,DN20,316SS | 1 | 2 | 1 | OK. - OLC. | 0 | Material is received @AB50 | Stock at Base (SP12) | AB01 | 5300003502 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007201 | N | Post Execution (08) | Work Done (Order) (0080) | 0000123413 | 1 | 1 | 30 | 30 | Supply for Order 200085163, Item 1 cannot be changed 90001661 item 10 already exists | 101000000020989 | 1 | TRUE | 101000000020951 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-04-13 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000781 | 0 | 0 | 0.5 | 2024-02-08 | -12 | 16 | ON TIME |  | On Time | 0 | SOH | 00001234134535810574508000200085163 | 00001234134535810574508000200085163 | 000012341310574508000200085163 | 0 | #N/A | 0
24OKCO19 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 | 2024-02-20 | 2024-05-09 | 2024-05-09 | MECH |  | 200086992 | 0010 | 5Y FW AUTO VENT VALVE INSPECTION (200086992) | VALVE,AUTO VENT TO DECK SCUPPERING (AB50.03SP452654) | FW AUTO VENT VALVE INSPECTION 03SP452654 (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 255 | 99 | 10206294 | GASKET,CNAF,50MM,CL150,1.5MM,FF,C4430 | 4 | 0 | 4 | OK. - OLC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300003698 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180007211 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000125250 | 1 | 4 | 30 | 30 | Supply for Order 200086992, Item 1 cannot be changed 90001662 item 10 already exists | 101000000020900 | 4 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-02-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-04-11 | 51 | 79 | ON TIME |  | On Time | 0 | Need Purchasing | 00001252504542110206294000200086992 | #N/A | 000012525010206294000200086992 | 0 | #N/A | 0
24OKCO16 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 | 2024-02-19 | 2024-04-26 | 2024-04-26 | MECH |  | 200089401 | 0010 | 4Y REPLACE HOSES - INHIB INJECT SKID (200089401) | HOSE,T74003,CHEMICAL STORAGE TANK FILL (AB50.05SP740039) | REPLACE HOSES (0020) | AB50 | 2024-04-26 |  |  | AB01 |  | 20 | 20 | 10493401 | HOSE ASY,COR INH;2000MM,05SP740039 | 1 | 0 | 0 | OK. - PDC. | 0 | Material In-Transit on-01-Road | Stock at Base (SP12) | AB01 | 5300003821 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | ASY |  |  |  | 180014439 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000127599 | 1 | 3 | 30 | 30 | Supply for Order 200089401, Item 1 cannot be changed 90001663 item 10 already exists | 101000000029743 | 1 | TRUE | 101000000029626 |  |  | WorkPackLink |  | 2024-03-30 | 0 | 0 | 2023-08-21 | 0 | 0 |  |  | 0 | 0 | 01-Road | 1 | 5-Completed |  | 20000716 | 0 | 0 | 0.14286 | 2024-03-29 | 39 | 67 | ON TIME |  | On Time | 0 | Need Purchasing | 00001275994540810493401000200089401 | #N/A | 000012759910493401000200089401 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0120 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 80 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 17 | 2 | 30 | 30 | Supply for Order 200090465, Item 17 cannot be changed 180011325 item 70 already exists | 101000000023419 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447461000200090465 | #N/A | 000012873410447461000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0050 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10569059 | VALVE,GATE;200MM,PN25,RF,ST | 1 | 2 | 2 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 10 | 2 | 30 | 30 | Supply for Order 200090465, Item 10 cannot be changed 180011325 item 10 already exists | 101000000023489 | 1 | TRUE |  |  |  | WorkPackLink | PK_STAGING |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110569059000200090465 | 00001287344539110569059000200090465 | 000012873410569059000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0392 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10590781 | STUDBOLT;M16 X 70MM,B7,PLN | 48 | 0 | 100 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 320 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 50 | 2 | 30 | 30 | Supply for Order 200090465, Item 50 cannot be changed 9001259 item 310 already exists | 696861 | 48 | TRUE | 101000000023475 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110590781000200090465 | #N/A | 000012873410590781000200090465 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0482 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | ISOLATE & ASSIST with SPADE (0020) | AB50 | 2024-03-28 |  |  | AB01 |  | 10 | 5 | 10590626 | FLANGE,BLIND;1",FF,16K,A516-GR70 | 4 | 0 | 4 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013486 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 1 | 2 | 30 | 30 | Supply for Order 200090465, Item 1 cannot be changed 90001666 item 10 already exists | 696861 | 4 | TRUE | 101000000023467 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344537910590626000200090465 | #N/A | 000012873410590626000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0372 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10590782 | STUDBOLT;M16 X 80MM,B7,PLN | 64 | 0 | 128 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 330 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 51 | 2 | 30 | 30 | Supply for Order 200090465, Item 51 cannot be changed 9001259 item 320 already exists | 696861 | 64 | TRUE | 101000000023476 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110590782000200090465 | #N/A | 000012873410590782000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0170 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 130 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 22 | 2 | 30 | 30 | Supply for Order 200090465, Item 22 cannot be changed 180011325 item 80 already exists | 101000000023430 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447461000200090465 | #N/A | 000012873410447461000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0382 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10590783 | STUDBOLT;M16 X 90MM,B7,PLN | 64 | 0 | 128 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 340 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 52 | 2 | 30 | 30 | Supply for Order 200090465, Item 52 cannot be changed 9001259 item 330 already exists | 696861 | 64 | TRUE | 101000000023477 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110590783000200090465 | #N/A | 000012873410590783000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0070 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 12 | 2 | 30 | 30 | Supply for Order 200090465, Item 12 cannot be changed 180011325 item 20 already exists | 101000000023413 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447461000200090465 | #N/A | 000012873410447461000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0362 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10526668 | STUDBOLT;M12 X 70MM,B7,STL,BLK | 72 | 0 | 144 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 240 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 42 | 2 | 30 | 30 | Supply for Order 200090465, Item 42 cannot be changed 9001259 item 230 already exists | 696861 | 72 | TRUE | 101000000023472 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110526668000200090465 | #N/A | 000012873410526668000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0150 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10355246 | VALVE,GLOBE;DN40,PN25,LAVAL AG9685005747 | 1 | 2 | 2 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 110 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 20 | 2 | 30 | 30 | Supply for Order 200090465, Item 20 cannot be changed 9001259 item 100 already exists | 696861 | 1 | TRUE | 101000000023569 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110355246000200090465 | 00001287344539110355246000200090465 | 000012873410355246000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0432 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10400603 | GASKET;CNAF,JIS16K,25MM,1.5MM,FF,C4430 | 12 | 1 | 24 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 230 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 41 | 2 | 30 | 30 | Supply for Order 200090465, Item 41 cannot be changed 9001259 item 220 already exists | 696861 | 12 | TRUE | 101000000023471 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110400603000200090465 | #N/A | 000012873410400603000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0292 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10590362 | TRAP,STEAM;FCD250,JIS 16K,TLV AF3N | 1 | 0 | 4 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 310 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 49 | 2 | 30 | 30 | Supply for Order 200090465, Item 49 cannot be changed 9001259 item 300 already exists | 696861 | 1 | TRUE | 101000000023474 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110590362000200090465 | #N/A | 000012873410590362000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0442 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10061194 | GASKET;SWCI,200MM,PN25,316L/GR/316 | 2 | 0 | 4 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 220 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 40 | 2 | 30 | 30 | Supply for Order 200090465, Item 40 cannot be changed 9001259 item 210 already exists | 696861 | 2 | TRUE | 101000000023470 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110061194000200090465 | #N/A | 000012873410061194000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0130 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10355246 | VALVE,GLOBE;DN40,PN25,LAVAL AG9685005747 | 1 | 2 | 2 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 90 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 18 | 2 | 30 | 30 | Supply for Order 200090465, Item 18 cannot be changed 9001259 item 80 already exists | 696861 | 1 | TRUE | 101000000023568 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110355246000200090465 | 00001287344539110355246000200090465 | 000012873410355246000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0572 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10058537 | STUDBOLT;1.000"X180MM,B7,BLK | 12 | 0 | 24 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 210 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 39 | 2 | 30 | 30 | Supply for Order 200090465, Item 39 cannot be changed 9001259 item 200 already exists | 696861 | 12 | TRUE | 101000000023468 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110058537000200090465 | #N/A | 000012873410058537000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0282 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10590362 | TRAP,STEAM;FCD250,JIS 16K,TLV AF3N | 1 | 0 | 4 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 300 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013490 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 48 | 2 | 30 | 30 | Supply for Order 200090465, Item 48 cannot be changed 9001259 item 290 already exists | 696861 | 1 | TRUE | 101000000023473 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | Need Purchasing | 00001287344539110590362000200090465 | #N/A | 000012873410590362000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0100 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 15 | 2 | 30 | 30 | Supply for Order 200090465, Item 15 cannot be changed 180011325 item 50 already exists | 101000000023416 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447461000200090465 | #N/A | 000012873410447461000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0090 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 14 | 2 | 30 | 30 | Supply for Order 200090465, Item 14 cannot be changed 180011325 item 40 already exists | 101000000023415 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447461000200090465 | #N/A | 000012873410447461000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0110 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 16 | 2 | 30 | 30 | Supply for Order 200090465, Item 16 cannot be changed 180011325 item 60 already exists | 101000000023418 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447461000200090465 | #N/A | 000012873410447461000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0080 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 13 | 2 | 30 | 30 | Supply for Order 200090465, Item 13 cannot be changed 180011325 item 30 already exists | 101000000023414 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110447461000200090465 | #N/A | 000012873410447461000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 | 2024-03-21 | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0052 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10569059 | VALVE,GATE;200MM,PN25,RF,ST | 1 | 2 | 2 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004055 | 250 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011325 | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 43 | 2 | 30 | 30 | Supply for Order 200090465, Item 43 cannot be changed 180011325 item 90 already exists | 101000000023540 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | -9 | 19 | ON TIME |  | On Time | 0 | SOH | 00001287344539110569059000200090465 | 00001287344539110569059000200090465 | 000012873410569059000200090465 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0110 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 60 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011320 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 17 | 2 | 30 | 30 | Supply for Order 200091461, Item 17 cannot be changed 9000963 item 60 already exists | 101000000023461 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510447461000200091461 | #N/A | 000012969110447461000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0292 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10590362 | TRAP,STEAM;FCD250,JIS 16K,TLV AF3N | 1 | 0 | 4 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 220 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 48 | 2 | 30 | 30 | Supply for Order 200091461, Item 48 cannot be changed 9001260 item 220 already exists | 696861 | 1 | TRUE | 101000000023481 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510590362000200091461 | #N/A | 000012969110590362000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0372 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10590783 | STUDBOLT;M16 X 90MM,B7,PLN | 64 | 0 | 128 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 260 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 52 | 2 | 30 | 30 | Supply for Order 200091461, Item 52 cannot be changed 9001260 item 260 already exists | 696861 | 64 | TRUE | 101000000023485 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510590783000200091461 | #N/A | 000012969110590783000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0432 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10400603 | GASKET;CNAF,JIS16K,25MM,1.5MM,FF,C4430 | 12 | 1 | 24 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 150 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 41 | 2 | 30 | 30 | Supply for Order 200091461, Item 41 cannot be changed 9001260 item 150 already exists | 696861 | 12 | TRUE | 101000000023479 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510400603000200091461 | #N/A | 000012969110400603000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0352 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10526668 | STUDBOLT;M12 X 70MM,B7,STL,BLK | 72 | 0 | 144 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 160 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 42 | 2 | 30 | 30 | Supply for Order 200091461, Item 42 cannot be changed 9001260 item 160 already exists | 696861 | 72 | TRUE | 101000000023480 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510526668000200091461 | #N/A | 000012969110526668000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0080 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 30 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011320 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 14 | 2 | 30 | 30 | Supply for Order 200091461, Item 14 cannot be changed 9000963 item 30 already exists | 101000000023268 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510447461000200091461 | #N/A | 000012969110447461000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0362 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10590782 | STUDBOLT;M16 X 80MM,B7,PLN | 64 | 0 | 128 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 250 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 51 | 2 | 30 | 30 | Supply for Order 200091461, Item 51 cannot be changed 9001260 item 250 already exists | 696861 | 64 | TRUE | 101000000023484 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510590782000200091461 | #N/A | 000012969110590782000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0442 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10061194 | GASKET;SWCI,200MM,PN25,316L/GR/316 | 2 | 0 | 4 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 140 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 40 | 2 | 30 | 30 | Supply for Order 200091461, Item 40 cannot be changed 9001260 item 140 already exists | 696861 | 2 | TRUE | 101000000023478 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510061194000200091461 | #N/A | 000012969110061194000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0120 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 70 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011320 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 18 | 2 | 30 | 30 | Supply for Order 200091461, Item 18 cannot be changed 9000963 item 70 already exists | 101000000023462 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510447461000200091461 | #N/A | 000012969110447461000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0100 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 50 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011320 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 16 | 2 | 30 | 30 | Supply for Order 200091461, Item 16 cannot be changed 9000963 item 50 already exists | 101000000023460 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510447461000200091461 | #N/A | 000012969110447461000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0382 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10590781 | STUDBOLT;M16 X 70MM,B7,PLN | 48 | 0 | 100 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 240 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 50 | 2 | 30 | 30 | Supply for Order 200091461, Item 50 cannot be changed 9001260 item 240 already exists | 696861 | 48 | TRUE | 101000000023483 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510590781000200091461 | #N/A | 000012969110590781000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0472 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10590576 | ADAPTOR;F,10BSPT,GYROLOK 8AF6316EC | 4 | 0 | 4 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 120 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 38 | 2 | 30 | 30 | Supply for Order 200091461, Item 38 cannot be changed 9001260 item 120 already exists | 696861 | 4 | TRUE | 101000000023466 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510590576000200091461 | #N/A | 000012969110590576000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0392 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10058537 | STUDBOLT;1.000"X180MM,B7,BLK | 12 | 0 | 24 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 130 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 39 | 2 | 30 | 30 | Supply for Order 200091461, Item 39 cannot be changed 9001260 item 130 already exists | 696861 | 12 | TRUE | 101000000023469 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510058537000200091461 | #N/A | 000012969110058537000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0170 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 100 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011320 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 23 | 2 | 30 | 30 | Supply for Order 200091461, Item 23 cannot be changed 9000963 item 100 already exists | 101000000023463 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510447461000200091461 | #N/A | 000012969110447461000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0282 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10590362 | TRAP,STEAM;FCD250,JIS 16K,TLV AF3N | 1 | 0 | 4 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 230 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180013487 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 49 | 2 | 30 | 30 | Supply for Order 200091461, Item 49 cannot be changed 9001260 item 230 already exists | 696861 | 1 | TRUE | 101000000023482 |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | Need Purchasing | 00001296914539510590362000200091461 | #N/A | 000012969110590362000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0070 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 20 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011320 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 13 | 2 | 30 | 30 | Supply for Order 200091461, Item 13 cannot be changed 9000963 item 20 already exists | 101000000023431 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510447461000200091461 | #N/A | 000012969110447461000200091461 | 0 | #N/A | 0
24OKCM13 | No Issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 | 2024-03-21 | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0090 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10447461 | VALVE,GLOBE;25MM,DI,ARI 23006PN25DN25 | 1 | 1 | 14 | OK. - PDC. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004393 | 40 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180011320 | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 15 | 2 | 30 | 30 | Supply for Order 200091461, Item 15 cannot be changed 9000963 item 40 already exists | 101000000023269 | 1 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | -5 | 23 | ON TIME |  | On Time | 0 | SOH | 00001296914539510447461000200091461 | #N/A | 000012969110447461000200091461 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-20 | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0070 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 | 2024-02-18 |  |  | AB01 | 2024-02-18 | 20 | 20 | 70000267 | H931P Transit Stayplate 3.5 Bar | 4 | 0 | 4 | OK. | 14 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | AB01 | 5300004682 | 40 | 14 | X | 1000000568 | 12 | 2024-01-24 | 2024-02-15 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 4500000291 | 5000009647_2024_0001 | 30 | 4 | EA | 2024-01-31 |  | /180001477 | 180004746 | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 12 | 2 |  |  | Supply for Order 600001447, Item 12 cannot be changed 9000421 item 40 already exists | 101000000017610 | 4 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-24 | 0 | 0 | 2024-02-18 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 9 | 37 | ON TIME |  | On Time | 0 | Need Purchasing | 00000843624537970000267000600001447 | #N/A | 000008436270000267000600001447 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-20 | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0060 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 | 2024-04-14 |  |  | AB01 | 2024-03-18 | 20 | 20 | 70000266 | Transit Compression Sys Complete HHF1642 | 3 | 0 | 3 | OK. | 56 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | AB01 | 5300004682 | 30 | 56 | X | 1000000568 | 11 | 2024-01-12 | 2024-03-15 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 4500000291 | 5000015282_2024_0001 | 20 | 3 | EA | 2024-02-02 |  | 180003346/ | 180004746 | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 11 | 2 |  |  | Supply for Order 600001447, Item 11 cannot be changed 9000421 item 30 already exists | 101000000017522 | 3 | TRUE |  |  |  | WorkPackLink |  |  | 27 | 0 | 2024-03-24 | 0 | 0 | 2024-03-18 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 9 | 37 | ON TIME |  | On Time | 0 | Need Purchasing | 00000843624537970000266000600001447 | #N/A | 000008436270000266000600001447 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-20 | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0080 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 | 2024-02-18 |  |  | AB01 | 2024-02-18 | 20 | 20 | 70000268 | Stayplate Transit | 4 | 0 | 4 | OK. | 14 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | AB01 | 5300004682 | 50 | 14 | X | 1000000568 | 13 | 2024-01-24 | 2024-02-15 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 4500000291 | 5000010399_2024_0001 | 40 | 4 | EA | 2024-01-31 |  | /180001477 | 180004746 | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 13 | 2 |  |  | Supply for Order 600001447, Item 13 cannot be changed 9000421 item 50 already exists | 101000000017569 | 4 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-24 | 0 | 0 | 2024-02-18 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 9 | 37 | ON TIME |  | On Time | 0 | Need Purchasing | 00000843624537970000268000600001447 | #N/A | 000008436270000268000600001447 | 0 | #N/A | 0
24OKCM13 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-02-20 | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0090 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 | 2024-02-18 |  |  | AB01 | 2024-02-18 | 20 | 20 | 70000265 | Cable Duct 80x80mm 2M PVC Grey | 3 | 0 | 3 | OK. | 14 | Materials handed over to w/ Maintenance | Directs (Inventory) (SP14) | AB01 | 5300004682 | 20 | 14 | X | 1000000568 | 10 | 2024-01-24 | 2024-02-15 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 4500000291 | 5000009121_2024_0001 | 10 | 3 | EA | 2024-01-17 |  | /180001119 | 180004746 | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 10 | 2 |  |  | Supply for Order 600001447, Item 10 cannot be changed 9000421 item 20 already exists | 101000000015016 | 3 | TRUE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-24 | 0 | 0 | 2024-02-18 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 9 | 37 | ON TIME |  | On Time | 0 | Need Purchasing | 00000843624537970000265000600001447 | #N/A | 000008436270000265000600001447 | 0 | #N/A | 0
24OKCM19 | Voyage arrived: too late to meet planned Reqmt Dat |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-01-22 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0030 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | HSE10 - Repl rigid arm m/rail hoist (0010) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10616642 | OKHA SUPPLY OF OVERHEAD HOIST MS1: | 1 | 0 | 1 | OK. | 0 | Material work-packed @AB50 | Stock at Base (SP12) | AB01 | 5300004592 | 10 | 21 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  | 180001924 | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 1 | 1 |  |  | Supply for Order 600001724, Item 1 cannot be changed 90000435 item 10 already exists | 101000000014456 | 1 | TRUE | 101000000014455 |  |  | WorkPackLink | OKHA |  | 0 | 0 | 2024-06-02 | 0 | 0 |  |  | 0 | 0 | 04-Sea | 0 | 5-Completed |  | 1000000243 | 0 | 0 | 0.11111 | 2024-02-29 | 38 | 66 | ON TIME |  | On Time | 0 | Need Purchasing | 00000845794537910616642000600001724 | #N/A | 000008457910616642000600001724 | 0 | #N/A | 0
24OKCM19 | No issue identified |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 | 2024-03-13 | 2024-02-02 | 2024-03-31 | CRANE |  | 600001724 | 0020 | HSE10 - Repl rigid arm m/rail hoist (600001724) | MONOFB,RIGID ARM TOP DECK (AB50.04B790004) | Commission and function test new system. (0080) | AB50 | 2024-04-16 |  |  | AB01 | 2024-03-30 | 20 | 20 | 70003898 | Stainless Steel Bolt Hex Standard SS316 | 100 | 100 | 0 | ETA. | 7 | Material is received @AB01 | Directs (Inventory) (SP14) | AB01 | 5300004592 | 50 | 7 | X | 1000005254 | 13 | 2024-03-13 | 2024-03-27 | J BLACKWOOD AND SON LTD (30000394) | 4500007066 | 5000040476_2024_0001 | 10 | 100 | EA | 2024-03-27 |  | /180011869 |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084579 | 13 | 1 |  |  | Supply for Order 600001724, Item 13 cannot be changed 90004666 item 10 already exists | PACKING | 100 | TRUE |  |  |  | WorkPackLink | OKHA |  | 17 | 0 | 2024-06-02 | 0 | 0 | 2024-03-30 |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.11111 | 2024-02-29 | -13 | 15 | ON TIME |  | On Time | 0 | SOH | 00000845794537970003898000600001724 | #N/A | 000008457970003898000600001724 | 0 | #N/A | 0
24OKCM19 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-05-09 |  | 2024-05-09 | 2024-05-09 | MECH |  | 100031885 | 0010 | Replace Hose GT1 Drain Hose (100031885) | TURB,GT400001 TURBINE (AB50.05GT400001) | GT1 Replace Hose (0010) | AB50 | 2024-05-09 |  |  | AB01 |  | 30 | 30 | 10291291 | HOSE ASSY;FLEX,1/2",SOLAR 2567232 | 1 | 0 | 0 | ETA. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000130257 | 1 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-08-27 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 2024-04-11 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001302574542110291291000100031885 | #N/A | 000013025710291291000100031885 | 0 | #N/A | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-10 | 2024-03-28 |  | 2024-03-28 | 2024-03-28 | INLEC |  | 100033880 | 0020 | Repl MOD6 G/Tray & EM Light Bat (2off) (100033880) | LIGHT,FLUOR,JN413-5102 (AB50.05LT400102W7106) | Isolate Lt cct's 05LT400102W71 & B27 (0010) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10605607 | FIXTURE,LGT;EX,60W,CHALMIT PRRE05LLE4KI+ | 1 | 0 | 0 | ETA. - R. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000132352 | 2 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001323524537910605607000100033880 | #N/A | 000013235210605607000100033880 | 0 | #N/A | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0180 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10616558 | Assorted bolts, Anode and Cable Brackets | 1 | 0 | 0 | ISSUE. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 13 | 1 | 30 |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | At Job Location |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001334014537910616558000100034857 | #N/A | 000013340110616558000100034857 |  |  | 1
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0160 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10616556 | Electical and Alignment Brackets | 1 | 0 | 0 | ISSUE. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 11 | 1 | 30 |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | At Job Location |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001334014537910616556000100034857 | #N/A | 000013340110616556000100034857 |  |  | 1
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0150 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10616555 | Chlorination and Glycol hoses + Gaskets | 4 | 0 | 0 | ISSUE. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 10 | 1 | 30 |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | At Job Location |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001334014537910616555000100034857 | #N/A | 000013340110616555000100034857 |  |  | 1
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0170 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 |  |  |  | AB01 |  | 20 | 20 | 10616557 | Assorted Small Bore Tubing | 1 | 0 | 0 | ISSUE. | 0 |  | Stock at Remote (SP13) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 12 | 1 | 30 |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | At Job Location |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001334014537910616557000100034857 | #N/A | 000013340110616557000100034857 |  |  | 1
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-04 | MECH |  | 100034857 | 0120 | Install SWLP B (100034857) | PKG EQ,SEAWTR LIFT PACKAGE B (AB50.03A453001B) | Install SWLP A (0040) | AB50 | 2024-03-28 |  |  | AB01 |  | 20 | 20 | 10534877 | BRACKET,CABLEANDHOSE,CLAMP KSB 01376719 | 2 | 0 | 0 | OK. - 2023 - Staged | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000133401 | 8 | 1 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | 2100354089 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.038462 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001334014537910534877000100034857 | #N/A | 000013340110534877000100034857 | 0 | #N/A | 0
24OKCO16 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-24 |  | 2024-04-24 | 2024-04-24 | INLEC |  | 100037559 | 0020 | Repl Light Fitting MOD7 Cargo/D Port/S (100037559) | LIGHT,FLUOR,JN414-5102 (AB50.05LT400102R7605) | Replace light fitting (0010) | AB50 | 2024-04-24 |  |  | AB01 |  | 20 | 20 | 10580017 | FIXTURE,LGT;LED,4FT,60W,EXE,CHALMIT | 1 | 7 | 0 | OK. - PDC. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000136071 | 6 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2023-09-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.5 | 2024-03-27 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001360714540610580017000100037559 | #N/A | 000013607110580017000100037559 | 0 | #N/A | 0
24OKCM16 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-26 |  | 2024-04-25 | 2024-05-01 | REFURB |  | 100038989 | 0090 | RTM - Refurbish Gas Detector Brackets (100038989) | DET,FZ0445,GAS IR LOS RECEIVER (AB50.0445GRX871002) | Hand Prep & Paint (0010) | AB50 | 2024-04-26 |  |  | AB01 |  | 20 | 20 | 10440803 | BLADE,SAW;254MM,CENGAR MB250 | 20 | 0 | 0 | ETS. - Procurement. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | PAC |  |  |  |  | N | Preparation (05) | In Preparation (Order) (0055) | 0000137493 | 8 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | ALLEY-FLR-1 13/12 |  | 0 | 0 | 2023-12-31 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.125 | 2024-03-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00001374934540810440803000100038989 | #N/A | 000013749310440803000100038989 | 0 | #N/A | 0
24OKCM19 | WO item has not been released yet |  | Released | 2024-03-05 | 2024-03-06 | 2024-03-07 |  | 2024-03-09 | 2024-03-09 | INLEC |  | 100074097 | 0020 | Install Monitoring SWLP-B MoC (100074097) | BREAKER,05MCC400101 FEEDR 03PM453001B (AB50.05MCC400101-B10) | Isolate SWLP - B (0010) | AB50 | 2024-03-07 |  |  | AB01 |  | 20 | 20 | 10605690 | METER,MOTOR;ARTESIS EMCMLVXAE | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000225256 | 2 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-09-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-02-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00002252564535810605690000100074097 | #N/A | 000022525610605690000100074097 | 0 | #N/A | 0
24OKCM19 | WO item has not been released yet |  | Released | 2024-03-05 | 2024-03-06 | 2024-03-07 |  | 2024-03-09 | 2024-03-09 | INLEC |  | 100074097 | 0030 | Install Monitoring SWLP-B MoC (100074097) | BREAKER,05MCC400101 FEEDR 03PM453001B (AB50.05MCC400101-B10) | Isolate SWLP - B (0010) | AB50 | 2024-03-07 |  |  | AB01 |  | 20 | 20 | 10541467 | PLUG,CRIMP;RJ45 8P8C CAT6,SHIELDED | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000225256 | 3 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-09-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-02-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00002252564535810541467000100074097 | #N/A | 000022525610541467000100074097 | 0 | #N/A | 0
24OKCM19 | WO item has not been released yet |  | Released | 2024-03-05 | 2024-03-06 | 2024-03-07 |  | 2024-03-09 | 2024-03-09 | INLEC |  | 100074097 | 0010 | Install Monitoring SWLP-B MoC (100074097) | BREAKER,05MCC400101 FEEDR 03PM453001B (AB50.05MCC400101-B10) | Isolate SWLP - B (0010) | AB50 | 2024-03-07 |  |  | AB01 |  | 20 | 20 | 10605691 | TXDCR,CURRENT;ARTESIS AC25R10100MA | 1 | 0 | 0 | OK. - STAGE 2023. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000225256 | 1 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-09-03 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.33333 | 2024-02-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00002252564535810605691000100074097 | #N/A | 000022525610605691000100074097 | 0 | #N/A | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-09 |  | 2024-03-28 | 2024-04-21 | MECH |  | 200090465 | 0060 | 2.5Y CLASS SURVEY BOILER 1 (200090465) | PKG EQ,AUXILARY BOILER NO 1 (AB50.03A750001) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-09 |  |  | AB01 |  | 10 | 5 | 10447458 | VALVE,GLOBE;80MM,ARI 23006PN25DN80C07A | 1 | 2 | 0 | OK. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Ready for Execution (Order) (0065) | 0000128734 | 11 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | Ex WO 2200566454 |  | 0 | 0 | 2024-10-19 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-12 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001287344539110447458000200090465 | 00001287344539110447458000200090465 | 000012873410447458000200090465 | 0 | #N/A | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-04-13 |  | 2024-03-31 | 2024-04-24 | MECH |  | 200091461 | 0060 | 2.5Y CLASS SURVEY BOILER 2 (200091461) | PKG EQ,AUXILARY BOILER NO 2 (AB50.03A750002) | REINSTATE PIPEWORK & VALVES (0170) | AB50 | 2024-04-13 |  |  | AB01 |  | 10 | 5 | 10447458 | VALVE,GLOBE;80MM,ARI 23006PN25DN80C07A | 1 | 2 | 0 | OK. - PDC. | 0 |  | Stock at Base (SP12) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000129691 | 12 | 2 | 30 | 30 |  |  | 0 | FALSE |  |  |  | WorkPackLink | Moved from WO 2200571221 |  | 0 | 0 | 2024-10-22 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.019231 | 2024-03-16 | 0 | 0 | Missing Staging Date |  | On Time | 0 | SOH | 00001296914539510447458000200091461 | #N/A | 000012969110447458000200091461 | 0 | #N/A | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0120 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 70003694 | DWR for Tool Box | 1 | 0 | 0 | OK. | 0 |  | Directs (Inventory) (SP14) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 19 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00000843624537970003694000600001447 | #N/A | 000008436270003694000600001447 |  |  | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-02 | 2024-03-28 |  | 2024-03-28 | 2024-04-19 | MECH |  | 600001447 | 0110 | Upgrage GMDSS System - Parts Purchasing (600001447) | GMDSS SYSTEM (AB50.OKH.F0801008) | GMDSS Full System Obsolescence for Repla (0010) | AB50 |  |  |  | AB01 |  | 20 | 20 | 70003694 | DWR for Tool Box | 1 | 0 | 0 | OK. | 0 |  | Directs (Inventory) (SP14) |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000084362 | 16 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-03-24 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.1 | 2024-02-29 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Need Purchasing | 00000843624537970003694000600001447 | #N/A | 000008436270003694000600001447 |  |  | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0380 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | INSTALL SOLAR ENGINE (0040) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 33 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | 2100358707 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-01 | 2024-02-18 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0350 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | CRANE ASSIST (0140) | AB50 | [5 empty] | 20 | 20 |  |  | 24 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 35 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink | 2200631608 |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-01-21 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845340000100037574 | #N/A | 0000136098000100037574 |  |  | 0
24OKCM13 | WO item has not been released yet |  | Released | 2023-12-30 | 2024-01-01 | 2024-04-05 |  | 2024-04-05 | 2024-04-12 | MECH |  | 100037574 | 0020 | Install new GT2 Eng - Blade Failure (100037574) | TURB,GT400002 TURBINE (AB50.05GT400002) | Solar Mars 100-15000 GP&PT ENGINE OVERHA (0150) | AB50 | [5 empty] | 20 | 20 |  |  | 1 | 0 | 0 | OK. - 2023 - Staged | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 | EA |  |  |  |  | N | Execution (07) | Main Work Started (Order) (0070) | 0000136098 | 59 | 2 |  |  |  |  | 0 | FALSE |  |  |  | WorkPackLink |  |  | 0 | 0 | 2024-06-30 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0.020408 | 2024-03-08 | 0 | 0 | Missing Staging Date |  | On Time | 0 | Delivered Pre S4H | 000013609845387000100037574 | #N/A | 0000136098000100037574 |  |  | 0
Formulas:
C-28 = [Requirement date (WO component)]-28
Delivery date (PO)2 = MAXIFS('Monitor PO'!E:E,'Monitor PO'!K:K,KGP[[#This Row],[Material / Component]])
Any order which is ahead (Date) = IF(MAXIFS(Reservation!$F:$F,Reservation!$A:$A,KGP[[#This Row],[Logic]])<KGP[[#This Row],[ETA @ Demand plant]],MAXIFS(Reservation!$F:$F,Reservation!$A:$A,KGP[[#This Row],[Logic]]),"")

## Reservation
Key2 | Key A | Reservation | Item number of reservation | Record type | Requirements date F | Movement type | Debit/Credit ind | Material | Requirement Quantity | Difference Quantity | Base Unit of Measure | Requirement Urgency | Requirement Priority | Account assignment of reservation | Account assignment | Movement allowed
| 0000936494552610006659000200059360 | 93649 | 8 |  | 2024-08-22 | 261 | H | 10006659 | 1 | 1 | EA | 10 | 10 | F | 000200059360 | X
| 0000936524552610006659000200059363 | 93652 | 8 |  | 2024-08-22 | 261 | H | 10006659 | 1 | 1 | EA | 10 | 10 | F | 000200059363 | X
| 0000963414542110006659000200061999 | 96341 | 8 |  | 2024-05-09 | 261 | H | 10006659 | 1 | 1 | EA | 10 | 10 | F | 000200061999 | X
| 0000963444546310006659000200062042 | 96344 | 8 |  | 2024-06-20 | 261 | H | 10006659 | 1 | 1 | EA | 10 | 10 | F | 000200062042 | X
| 00002228244562410006659000200139478 | 222824 | 30 |  | 2024-11-28 | 261 | H | 10006659 | 1 | 1 | EA | 10 | 10 | F | 000200139478 | X
| 00002228314562410006659000200139603 | 222831 | 30 |  | 2024-11-28 | 261 | H | 10006659 | 1 | 1 | EA | 10 | 10 | F | 000200139603 | X
| 0000936494552610006856000200059360 | 93649 | 1 |  | 2024-08-22 | 261 | H | 10006856 | 1 | 1 | EA | 10 | 10 | F | 000200059360 | X
| 0000936524552610006856000200059363 | 93652 | 1 |  | 2024-08-22 | 261 | H | 10006856 | 1 | 1 | EA | 10 | 10 | F | 000200059363 | X
| 0000963414542110006856000200061999 | 96341 | 1 |  | 2024-05-09 | 261 | H | 10006856 | 1 | 1 | EA | 10 | 10 | F | 000200061999 | X
| 0000963444546310006856000200062042 | 96344 | 1 |  | 2024-06-20 | 261 | H | 10006856 | 1 | 1 | EA | 10 | 10 | F | 000200062042 | X
| 0000936494552610006930000200059360 | 93649 | 2 |  | 2024-08-22 | 261 | H | 10006930 | 1 | 1 | EA | 10 | 10 | F | 000200059360 | X
| 0000936524552610006930000200059363 | 93652 | 2 |  | 2024-08-22 | 261 | H | 10006930 | 1 | 1 | EA | 10 | 10 | F | 000200059363 | X
| 0000963414542110006930000200061999 | 96341 | 2 |  | 2024-05-09 | 261 | H | 10006930 | 1 | 1 | EA | 10 | 10 | F | 000200061999 | X
| 0000963444546310006930000200062042 | 96344 | 2 |  | 2024-06-20 | 261 | H | 10006930 | 1 | 1 | EA | 10 | 10 | F | 000200062042 | X
| 00002228244562410006930000200139478 | 222824 | 28 |  | 2024-11-28 | 261 | H | 10006930 | 1 | 1 | EA | 10 | 10 | F | 000200139478 | X
| 00002228314562410006930000200139603 | 222831 | 28 |  | 2024-11-28 | 261 | H | 10006930 | 1 | 1 | EA | 10 | 10 | F | 000200139603 | X
| 00001371064542110017194000100038602 | 137106 | 12 |  | 2024-05-09 | 261 | H | 10017194 | 1 | 1 | EA | 10 | 10 | F | 000100038602 | X
| 00001373084540710021820000100038807 | 137308 | 6 |  | 2024-04-25 | 261 | H | 10021820 | 1 | 1 | EA | 5 | 10 | F | 000100038807 | X
| 00001373074542210021821000100038806 | 137307 | 1 |  | 2024-05-10 | 261 | H | 10021821 | 1 | 1 | EA | 5 | 10 | F | 000100038806 | X
| 00001373084540710021822000100038807 | 137308 | 1 |  | 2024-04-25 | 261 | H | 10021822 | 1 | 1 | EA | 5 | 10 | F | 000100038807 | X
| 00001334014537910034184000100034857 | 133401 | 14 |  | 2024-03-28 | 261 | H | 10034184 | 20 | 20 | EA | 20 | 20 | F | 000100034857 | X
| 0000950664533510038987000200060744 | 95066 | 3 |  | 2024-02-13 | 262 | S | 10038987 | 1 | 1 | EA | 20 | 20 | F | 000200060744 | X
| 0000992664542110038987000200064964 | 99266 | 1 |  | 2024-05-09 | 261 | H | 10038987 | 1 | 1 | EA | 20 | 20 | F | 000200064964 | X
| 00001253574546310038987000200087108 | 125357 | 2 |  | 2024-06-20 | 261 | H | 10038987 | 1 | 1 | EA | 20 | 20 | F | 000200087108 | X
| 00001352914540010047907000100036757 | 135291 | 1 |  | 2024-04-18 | 261 | H | 10047907 | 2 | 2 | EA | 20 | 20 | F | 000100036757 | X
| 00002185114541310058077000100072584 | 218511 | 25 |  | 2024-05-01 | 261 | H | 10058077 | 32 | 32 | EA | 5 | 10 | F | 000100072584 | X
| 00001356164541110058191000100037132 | 135616 | 4 |  | 2024-04-29 | 261 | H | 10058191 | 4 | 4 | EA | 20 | 20 | F | 000100037132 | X
| 0000950724544610058201000200060750 | 95072 | 2 |  | 2024-06-03 | 261 | H | 10058201 | 4 | 4 | EA | 10 | 10 | F | 000200060750 | X
| 00001356164541110058201000100037132 | 135616 | 3 |  | 2024-04-29 | 261 | H | 10058201 | 8 | 8 | EA | 20 | 20 | F | 000100037132 | X
| 00001381214541110058201000100039620 | 138121 | 8 |  | 2024-04-29 | 261 | H | 10058201 | 4 | 4 | EA | 20 | 20 | F | 000100039620 | X
| 00001356164541110058213000100037132 | 135616 | 5 |  | 2024-04-29 | 261 | H | 10058213 | 8 | 8 | EA | 20 | 20 | F | 000100037132 | X
| 00002185114541410058535000100072584 | 218511 | 29 |  | 2024-05-02 | 261 | H | 10058535 | 32 | 32 | EA | 5 | 10 | F | 000100072584 | X
| 00001315774540410058872000100033093 | 131577 | 3 |  | 2024-04-22 | 261 | H | 10058872 | 16 | 16 | EA | 5 | 10 | F | 000100033093 | X
| 00001356194620410058872000100037135 | 135619 | 1 |  | 2026-07-01 | 261 | H | 10058872 | 12 | 12 | EA | 20 | 20 | F | 000100037135 | X
| 00001366884541710058872000100038184 | 136688 | 3 |  | 2024-05-05 | 261 | H | 10058872 | 20 | 20 | EA | 30 | 30 | F | 000100038184 | X
| 00001375204540410058872000100039046 | 137520 | 2 |  | 2024-04-22 | 261 | H | 10058872 | 12 | 12 | EA | 30 | 30 | F | 000100039046 | X
| 00001404284620410058872000100041876 | 140428 | 1 |  | 2026-07-01 | 261 | H | 10058872 | 16 | 16 | EA | 5 | 10 | F | 000100041876 | X
| 00001404294620410058872000100041877 | 140429 | 1 |  | 2026-07-01 | 261 | H | 10058872 | 16 | 16 | EA | 5 | 10 | F | 000100041877 | X
| 00001404304620410058872000100041878 | 140430 | 1 |  | 2026-07-01 | 261 | H | 10058872 | 16 | 16 | EA | 5 | 10 | F | 000100041878 | X
| 00001404314620410058872000100041879 | 140431 | 1 |  | 2026-07-01 | 261 | H | 10058872 | 16 | 16 | EA | 5 | 10 | F | 000100041879 | X
| 00001404324620410058872000100041940 | 140432 | 1 |  | 2026-07-01 | 261 | H | 10058872 | 16 | 16 | EA | 5 | 10 | F | 000100041940 | X
| 00001408424620410058872000100042301 | 140842 | 1 |  | 2026-07-01 | 261 | H | 10058872 | 16 | 16 | EA | 5 | 10 | F | 000100042301 | X
| 0000950714546310058877000200060749 | 95071 | 3 |  | 2024-06-20 | 261 | H | 10058877 | 12 | 12 | EA | 5 | 10 | F | 000200060749 | X
| 0000984924546310058877000200064190 | 98492 | 3 |  | 2024-06-20 | 261 | H | 10058877 | 12 | 12 | EA | 5 | 10 | F | 000200064190 | X
| 00001353624542110058877000100036830 | 135362 | 1 |  | 2024-05-09 | 261 | H | 10058877 | 8 | 8 | EA | 20 | 20 | F | 000100036830 | X
| 00001360674540610058877000100037555 | 136067 | 3 |  | 2024-04-24 | 261 | H | 10058877 | 12 | 12 | EA | 20 | 20 | F | 000100037555 | X
| 00001375204540410058877000100039046 | 137520 | 3 |  | 2024-04-22 | 261 | H | 10058877 | 12 | 12 | EA | 30 | 30 | F | 000100039046 | X
| 00001316104542110058878000100032996 | 131610 | 2 |  | 2024-05-09 | 261 | H | 10058878 | 8 | 8 | EA | 30 | 30 | F | 000100032996 | X
| 00001360664620410058879000100037554 | 136066 | 4 |  | 2026-07-01 | 261 | H | 10058879 | 4 | 4 | EA | 20 | 20 | F | 000100037554 | X
| 00001364904546610058879000100037966 | 136490 | 2 |  | 2024-06-23 | 261 | H | 10058879 | 4 | 4 | EA | 20 | 20 | F | 000100037966 | X
| 00001375204540410058879000100039046 | 137520 | 4 |  | 2024-04-22 | 261 | H | 10058879 | 12 | 12 | EA | 30 | 30 | F | 000100039046 | X
| 00001427824540910058892000100044230 | 142782 | 4 |  | 2024-04-27 | 261 | H | 10058892 | 4 | 4 | EA | 30 | 30 | F | 000100044230 | X
| 00001440564548410058892000100045592 | 144056 | 5 |  | 2024-07-11 | 261 | H | 10058892 | 4 | 4 | EA | 20 | 20 | F | 000100045592 | X
| 00001447604540710058892000100046259 | 144760 | 3 |  | 2024-04-25 | 261 | H | 10058892 | 4 | 4 | EA | 30 | 30 | F | 000100046259 | X
| 00002185114541510058893000100072584 | 218511 | 39 |  | 2024-05-03 | 261 | H | 10058893 | 16 | 16 | EA | 5 | 10 | F | 000100072584 | X
| 00001328154537910058907000100034294 | 132815 | 2 |  | 2024-03-28 | 261 | H | 10058907 | 16 | 16 | EA | 20 | 20 | F | 000100034294 | X
| 00001427824540910058907000100044230 | 142782 | 6 |  | 2024-04-27 | 261 | H | 10058907 | 24 | 24 | EA | 30 | 30 | F | 000100044230 | X
| 00001332394540010060881000100034735 | 133239 | 1 |  | 2024-04-18 | 261 | H | 10060881 | 2 | 2 | EA | 5 | 10 | F | 000100034735 | X
| 00001375204540410060881000100039046 | 137520 | 10 |  | 2024-04-22 | 261 | H | 10060881 | 3 | 3 | EA | 30 | 30 | F | 000100039046 | X
| 00001273174556810060884000200089039 | 127317 | 5 |  | 2024-10-03 | 261 | H | 10060884 | 12 | 12 | EA | 20 | 20 | F | 000200089039 | X
| 00001400284621210060884000100041524 | 140028 | 4 |  | 2026-07-09 | 261 | H | 10060884 | 6 | 6 | EA | 5 | 10 | F | 000100041524 | X
| 00001401914544410060884000100041707 | 140191 | 1 |  | 2024-06-01 | 261 | H | 10060884 | 8 | 8 | EA | 20 | 20 | F | 000100041707 | X
| 00001417034540910060884000100043119 | 141703 | 2 |  | 2024-04-27 | 261 | H | 10060884 | 1 | 1 | EA | 20 | 20 | F | 000100043119 | X
| 00002134894539010060884000500003801 | 213489 | 22 |  | 2024-04-08 | 261 | H | 10060884 | 20 | 20 | EA | 99 | 255 | F | 000500003801 | X
| 00002252434536210060884000100074085 | 225243 | 1 |  | 2024-03-11 | 261 | H | 10060884 | 2 | 2 | EA | 99 | 255 | F | 000100074085 | X
| 0000899974546310060886000200055709 | 89997 | 3 |  | 2024-06-20 | 261 | H | 10060886 | 1 | 1 | EA | 10 | 10 | F | 000200055709 | X
| 0000950724544610060886000200060750 | 95072 | 5 |  | 2024-06-03 | 261 | H | 10060886 | 1 | 1 | EA | 10 | 10 | F | 000200060750 | X
| 00001287344538010060886000200090465 | 128734 | 6 |  | 2024-03-29 | 261 | H | 10060886 | 4 | 4 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914538410060886000200091461 | 129691 | 6 |  | 2024-04-02 | 261 | H | 10060886 | 4 | 4 | EA | 5 | 10 | F | 000200091461 | X
| 00001353624542110060886000100036830 | 135362 | 2 |  | 2024-05-09 | 261 | H | 10060886 | 2 | 2 | EA | 20 | 20 | F | 000100036830 | X
| 00001364904546610060886000100037966 | 136490 | 1 |  | 2024-06-23 | 261 | H | 10060886 | 2 | 2 | EA | 20 | 20 | F | 000100037966 | X
| 00001375204540410060886000100039046 | 137520 | 11 |  | 2024-04-22 | 261 | H | 10060886 | 9 | 9 | EA | 30 | 30 | F | 000100039046 | X
| 00001376084544610060886000100039107 | 137608 | 1 |  | 2024-06-03 | 261 | H | 10060886 | 4 | 4 | EA | 20 | 20 | F | 000100039107 | X
| 00002134894539010060886000500003801 | 213489 | 27 |  | 2024-04-08 | 261 | H | 10060886 | 20 | 20 | EA | 99 | 255 | F | 000500003801 | X
| 00001371064542110060889000100038602 | 137106 | 14 |  | 2024-05-09 | 261 | H | 10060889 | 1 | 1 | EA | 10 | 10 | F | 000100038602 | X
| 00001371064542110060890000100038602 | 137106 | 13 |  | 2024-05-09 | 261 | H | 10060890 | 1 | 1 | EA | 10 | 10 | F | 000100038602 | X
| 00001400284621210060890000100041524 | 140028 | 3 |  | 2026-07-09 | 261 | H | 10060890 | 2 | 2 | EA | 5 | 10 | F | 000100041524 | X
| 00001404784555610060890000100041977 | 140478 | 1 |  | 2024-09-21 | 261 | H | 10060890 | 2 | 2 | EA | 30 | 30 | F | 000100041977 | X
| 00001404794554710060890000100041978 | 140479 | 2 |  | 2024-09-12 | 261 | H | 10060890 | 2 | 2 | EA | 30 | 30 | F | 000100041978 | X
| 00001404804560910060890000100041979 | 140480 | 2 |  | 2024-11-13 | 261 | H | 10060890 | 2 | 2 | EA | 30 | 30 | F | 000100041979 | X
| 00002168304531810060890000100072246 | 216830 | 1 |  | 2024-01-27 | 261 | H | 10060890 | 1 | 1 | EA | 30 | 30 | F | 000100072246 | X
| 00002185114542010060890000100072584 | 218511 | 42 |  | 2024-05-08 | 261 | H | 10060890 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00002185114541210060891000100072584 | 218511 | 23 |  | 2024-04-30 | 261 | H | 10060891 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00002185114542010060891000100072584 | 218511 | 46 |  | 2024-05-08 | 261 | H | 10060891 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00001287344538010060903000200090465 | 128734 | 5 |  | 2024-03-29 | 261 | H | 10060903 | 4 | 4 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914538410060903000200091461 | 129691 | 5 |  | 2024-04-02 | 261 | H | 10060903 | 4 | 4 | EA | 5 | 10 | F | 000200091461 | X
| 00001346924544710060903000100036158 | 134692 | 1 |  | 2024-06-04 | 261 | H | 10060903 | 4 | 4 | EA | 20 | 20 | F | 000100036158 | X
| 00001358694544310060903000100037337 | 135869 | 1 |  | 2024-05-31 | 261 | H | 10060903 | 2 | 2 | EA | 20 | 20 | F | 000100037337 | X
| 00001316104542110060916000100032996 | 131610 | 3 |  | 2024-05-09 | 261 | H | 10060916 | 3 | 3 | EA | 30 | 30 | F | 000100032996 | X
| 00001287344538010060917000200090465 | 128734 | 7 |  | 2024-03-29 | 261 | H | 10060917 | 4 | 4 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914538410060917000200091461 | 129691 | 8 |  | 2024-04-02 | 261 | H | 10060917 | 4 | 4 | EA | 5 | 10 | F | 000200091461 | X
| 00001318504544610060917000100033329 | 131850 | 1 |  | 2024-06-03 | 261 | H | 10060917 | 2 | 2 | EA | 20 | 20 | F | 000100033329 | X
| 00001394964544710060917000100041024 | 139496 | 1 |  | 2024-06-04 | 261 | H | 10060917 | 2 | 2 | EA | 20 | 20 | F | 000100041024 | X
| 00001329294542110060929000100034425 | 132929 | 1 |  | 2024-05-09 | 261 | H | 10060929 | 2 | 2 | EA | 20 | 20 | F | 000100034425 | X
| 00001341194535810060929000100035665 | 134119 | 1 |  | 2024-03-07 | 261 | H | 10060929 | 2 | 2 | EA | 10 | 10 | F | 000100035665 | X
| 00001287344539110061160000200090465 | 128734 | 30 |  | 2024-04-09 | 261 | H | 10061160 | 19 | 19 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539510061160000200091461 | 129691 | 31 |  | 2024-04-13 | 261 | H | 10061160 | 19 | 19 | EA | 5 | 10 | F | 000200091461 | X
| 00001287344539110061164000200090465 | 128734 | 31 |  | 2024-04-09 | 261 | H | 10061164 | 10 | 10 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539510061164000200091461 | 129691 | 32 |  | 2024-04-13 | 261 | H | 10061164 | 10 | 10 | EA | 5 | 10 | F | 000200091461 | X
| 00001287344539110061172000200090465 | 128734 | 32 |  | 2024-04-09 | 261 | H | 10061172 | 13 | 13 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539510061172000200091461 | 129691 | 33 |  | 2024-04-13 | 261 | H | 10061172 | 13 | 13 | EA | 5 | 10 | F | 000200091461 | X
| 00001192474558610062327000200082767 | 119247 | 13 |  | 2024-10-21 | 261 | H | 10062327 | 1 | 1 | ROL | 5 | 10 | F | 000200082767 | X
| 00001294694621010062327000200091179 | 129469 | 12 |  | 2026-07-07 | 261 | H | 10062327 | 3 | 3 | ROL | 5 | 10 | F | 000200091179 | X
| 00001374524540010062327000100039000 | 137452 | 8 |  | 2024-04-18 | 261 | H | 10062327 | 1 | 1 | ROL | 20 | 20 | F | 000100039000 | X
| 00001412064548410062327000100042702 | 141206 | 1 |  | 2024-07-11 | 261 | H | 10062327 | 1 | 1 | ROL | 5 | 10 | F | 000100042702 | X
| 00001412074548410062327000100042703 | 141207 | 1 |  | 2024-07-11 | 261 | H | 10062327 | 1 | 1 | ROL | 30 | 30 | F | 000100042703 | X
| 00001380454542110062849000100039544 | 138045 | 1 |  | 2024-05-09 | 261 | H | 10062849 | 1 | 1 | CAN | 20 | 20 | F | 000100039544 | X
| 00001333184542110062910000100034866 | 133318 | 1 |  | 2024-05-09 | 261 | H | 10062910 | 3 | 3 | CQ | 20 | 20 | F | 000100034866 | X
| 00001333194542110062910000100034867 | 133319 | 1 |  | 2024-05-09 | 261 | H | 10062910 | 3 | 3 | CQ | 20 | 20 | F | 000100034867 | X
| 00001315254540010063416000100033044 | 131525 | 1 |  | 2024-04-18 | 261 | H | 10063416 | 6 | 6 | CYL | 20 | 20 | F | 000100033044 | X
| 00001198274541710063466000200083040 | 119827 | 2 |  | 2024-05-05 | 261 | H | 10063466 | 1 | 1 | PAC | 5 | 10 | F | 000200083040 | X
| 0000896934556810063554000200055424 | 89693 | 1 |  | 2024-10-03 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200055424 | X
| 0000896944556810063554000200055425 | 89694 | 1 |  | 2024-10-03 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200055425 | X
| 0000936404554710063554000200059318 | 93640 | 1 |  | 2024-09-12 | 261 | H | 10063554 | 5 | 5 | EA | 20 | 20 | F | 000200059318 | X
| 0000937214554710063554000200059319 | 93721 | 1 |  | 2024-09-12 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200059319 | X
| 0000963784548410063554000200062090 | 96378 | 1 |  | 2024-07-11 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200062090 | X
| 0000963794548410063554000200062091 | 96379 | 1 |  | 2024-07-11 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200062091 | X
| 00001067834542110063554000200072354 | 106783 | 1 |  | 2024-05-09 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200072354 | X
| 00001067844542110063554000200072355 | 106784 | 1 |  | 2024-05-09 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200072355 | X
| 00002187774537910063554000200136906 | 218777 | 1 |  | 2024-03-28 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200136906 | X
| 00002187784568310063554000200136907 | 218778 | 1 |  | 2025-01-26 | 261 | H | 10063554 | 15 | 15 | EA | 20 | 20 | F | 000200136907 | X
| 0000899914552610064932000200055703 | 89991 | 1 |  | 2024-08-22 | 261 | H | 10064932 | 32 | 32 | EA | 5 | 10 | F | 000200055703 | X
| 00001199004539010064932000200083035 | 119900 | 1 |  | 2024-04-08 | 261 | H | 10064932 | 79 | 79 | EA | 5 | 10 | F | 000200083035 | X
| 00001310244538010149809000100032520 | 131024 | 1 |  | 2024-03-29 | 261 | H | 10149809 | 4 | 4 | CQ | 30 | 30 | F | 000100032520 | X
| 00002185114541510204117000100072584 | 218511 | 40 |  | 2024-05-03 | 261 | H | 10204117 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00002185114542010204117000100072584 | 218511 | 41 |  | 2024-05-08 | 261 | H | 10204117 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00001162084548410204124000200081432 | 116208 | 1 |  | 2024-07-11 | 261 | H | 10204124 | 2 | 2 | EA | 30 | 30 | F | 000200081432 | X
| 00002185114541310204124000100072584 | 218511 | 26 |  | 2024-05-01 | 261 | H | 10204124 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00002185114542010204124000100072584 | 218511 | 45 |  | 2024-05-08 | 261 | H | 10204124 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00001162084548410205990000200081432 | 116208 | 2 |  | 2024-07-11 | 261 | H | 10205990 | 2 | 2 | EA | 30 | 30 | F | 000200081432 | X
| 00002185114541410205990000100072584 | 218511 | 27 |  | 2024-05-02 | 261 | H | 10205990 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00002185114542010205990000100072584 | 218511 | 44 |  | 2024-05-08 | 261 | H | 10205990 | 6 | 6 | EA | 5 | 10 | F | 000100072584 | X
| 00001162084548410205993000200081432 | 116208 | 3 |  | 2024-07-11 | 261 | H | 10205993 | 2 | 2 | EA | 30 | 30 | F | 000200081432 | X
| 00001182574540910205993000200082353 | 118257 | 1 |  | 2024-04-27 | 261 | H | 10205993 | 28 | 28 | EA | 5 | 10 | F | 000200082353 | X
| 00002185114541410205993000100072584 | 218511 | 30 |  | 2024-05-02 | 261 | H | 10205993 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00002185114542010205993000100072584 | 218511 | 43 |  | 2024-05-08 | 261 | H | 10205993 | 4 | 4 | EA | 5 | 10 | F | 000100072584 | X
| 00001356164541110206291000100037132 | 135616 | 2 |  | 2024-04-29 | 261 | H | 10206291 | 1 | 1 | EA | 20 | 20 | F | 000100037132 | X
| 00001206474535810206298000200083360 | 120647 | 3 |  | 2024-03-07 | 261 | H | 10206298 | 1 | 1 | EA | 5 | 10 | F | 000200083360 | X
| 00001356164541110206298000100037132 | 135616 | 1 |  | 2024-04-29 | 261 | H | 10206298 | 1 | 1 | EA | 20 | 20 | F | 000100037132 | X
| 0000936494552610209468000200059360 | 93649 | 3 |  | 2024-08-22 | 261 | H | 10209468 | 2 | 2 | EA | 10 | 10 | F | 000200059360 | X
| 0000936524552610209468000200059363 | 93652 | 3 |  | 2024-08-22 | 261 | H | 10209468 | 2 | 2 | EA | 10 | 10 | F | 000200059363 | X
| 0000963414542110209468000200061999 | 96341 | 3 |  | 2024-05-09 | 261 | H | 10209468 | 2 | 2 | EA | 10 | 10 | F | 000200061999 | X
| 0000963444546310209468000200062042 | 96344 | 3 |  | 2024-06-20 | 261 | H | 10209468 | 2 | 2 | EA | 10 | 10 | F | 000200062042 | X
| 00002228244562410209468000200139478 | 222824 | 24 |  | 2024-11-28 | 261 | H | 10209468 | 2 | 2 | EA | 10 | 10 | F | 000200139478 | X
| 00002228314562410209468000200139603 | 222831 | 24 |  | 2024-11-28 | 261 | H | 10209468 | 2 | 2 | EA | 10 | 10 | F | 000200139603 | X
| 00001340114542110218797000100035477 | 134011 | 1 |  | 2024-05-09 | 261 | H | 10218797 | 3 | 3 | EA | 20 | 20 | F | 000100035477 | X
| 00001340124533810218797000100035478 | 134012 | 1 |  | 2024-02-16 | 261 | H | 10218797 | 7 | 7 | EA | 20 | 20 | F | 000100035478 | X
| 00001340134542110218797000100035479 | 134013 | 1 |  | 2024-05-09 | 261 | H | 10218797 | 7 | 7 | EA | 20 | 20 | F | 000100035479 | X
| 00001340144542110218797000100035560 | 134014 | 1 |  | 2024-05-09 | 261 | H | 10218797 | 6 | 6 | EA | 20 | 20 | F | 000100035560 | X
| 00001316104542110227240000100032996 | 131610 | 6 |  | 2024-05-09 | 261 | H | 10227240 | 1 | 1 | EA | 30 | 30 | F | 000100032996 | X
| 00001427824540910227715000100044230 | 142782 | 1 |  | 2024-04-27 | 261 | H | 10227715 | 1 | 1 | EA | 30 | 30 | F | 000100044230 | X
| 00001333184542110228855000100034866 | 133318 | 2 |  | 2024-05-09 | 261 | H | 10228855 | 2 | 2 | KIT | 20 | 20 | F | 000100034866 | X
| 00001333194542110228855000100034867 | 133319 | 2 |  | 2024-05-09 | 261 | H | 10228855 | 2 | 2 | KIT | 20 | 20 | F | 000100034867 | X
| 00001373114534210233767000100038810 | 137311 | 8 |  | 2024-02-20 | 261 | H | 10233767 | 4 | 4 | CQ | 10 | 10 | F | 000100038810 | X
| 00001373124533910233767000100038811 | 137312 | 8 |  | 2024-02-17 | 261 | H | 10233767 | 4 | 4 | CQ | 10 | 10 | F | 000100038811 | X
| 00001373134534510233767000100038812 | 137313 | 7 |  | 2024-02-23 | 261 | H | 10233767 | 4 | 4 | CQ | 10 | 10 | F | 000100038812 | X
| 00001373144534610233767000100038813 | 137314 | 8 |  | 2024-02-24 | 261 | H | 10233767 | 4 | 4 | CQ | 10 | 10 | F | 000100038813 | X
| 00001373204536610233767000100038819 | 137320 | 10 |  | 2024-03-15 | 261 | H | 10233767 | 4 | 4 | CQ | 10 | 10 | F | 000100038819 | X
| 00001373814538410233767000100038880 | 137381 | 7 |  | 2024-04-02 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038880 | X
| 00001373824537610233767000100038881 | 137382 | 8 |  | 2024-03-25 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038881 | X
| 00001373834537610233767000100038882 | 137383 | 8 |  | 2024-03-25 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038882 | X
| 00001373844539710233767000100038883 | 137384 | 8 |  | 2024-04-15 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038883 | X
| 00001373854537310233767000100038884 | 137385 | 8 |  | 2024-03-22 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038884 | X
| 00001373864537410233767000100038885 | 137386 | 8 |  | 2024-03-23 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038885 | X
| 00001373874536610233767000100038886 | 137387 | 7 |  | 2024-03-15 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038886 | X
| 00001373884539310233767000100038887 | 137388 | 7 |  | 2024-04-11 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038887 | X
| 00001373894539010233767000100038888 | 137389 | 8 |  | 2024-04-08 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038888 | X
| 00001373904537510233767000100038889 | 137390 | 8 |  | 2024-03-24 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038889 | X
| 00001373914538210233767000100038890 | 137391 | 8 |  | 2024-03-31 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038890 | X
| 00001373924539910233767000100038891 | 137392 | 7 |  | 2024-04-17 | 261 | H | 10233767 | 4 | 4 | CQ | 20 | 20 | F | 000100038891 | X
| 00001204554538710236513000200083257 | 120455 | 3 |  | 2024-04-05 | 261 | H | 10236513 | 1 | 1 | EA | 5 | 10 | F | 000200083257 | X
| 00001372604542110241131000100038739 | 137260 | 3 |  | 2024-05-09 | 261 | H | 10241131 | 1 | 1 | PAC | 20 | 20 | F | 000100038739 | X
| 00001380454542110243755000100039544 | 138045 | 2 |  | 2024-05-09 | 261 | H | 10243755 | 12 | 12 | EA | 20 | 20 | F | 000100039544 | X
| 00001362964537910245447000100037795 | 136296 | 2 |  | 2024-03-28 | 261 | H | 10245447 | 2 | 2 | EA | 5 | 10 | F | 000100037795 | X
| 00001368644570410245447000100038383 | 136864 | 2 |  | 2025-02-16 | 261 | H | 10245447 | 2 | 2 | EA | 5 | 10 | F | 000100038383 | X
| 00001384374540610245447000100039936 | 138437 | 2 |  | 2024-04-24 | 261 | H | 10245447 | 2 | 2 | EA | 5 | 10 | F | 000100039936 | X
| 00001220404538610249942000200084031 | 122040 | 1 |  | 2024-04-04 | 261 | H | 10249942 | 3 | 3 | EA | 5 | 10 | F | 000200084031 | X
| 00001323534542110251722000100033881 | 132353 | 1 |  | 2024-05-09 | 261 | H | 10251722 | 1 | 1 | EA | 20 | 20 | F | 000100033881 | X
| 00002135104537910251722000500003742 | 213510 | 9 |  | 2024-03-28 | 261 | H | 10251722 | 10 | 10 | EA | 99 | 255 | F | 000500003742 | X
| 00001242874539110288499000200086029 | 124287 | 1 |  | 2024-04-09 | 261 | H | 10288499 | 32 | 32 | EA | 5 | 10 | F | 000200086029 | X
| 00001326094540010294417000100034055 | 132609 | 1 |  | 2024-04-18 | 261 | H | 10294417 | 1 | 1 | KIT | 20 | 20 | F | 000100034055 | X
| 00001333164535810300759000100034864 | 133316 | 2 |  | 2024-03-07 | 261 | H | 10300759 | 1 | 1 | EA | 20 | 20 | F | 000100034864 | X
| 00001372604542110300759000100038739 | 137260 | 2 |  | 2024-05-09 | 261 | H | 10300759 | 1 | 1 | EA | 20 | 20 | F | 000100038739 | X
| 0000846314542110304033000600001695 | 84631 | 14 |  | 2024-05-09 | 261 | H | 10304033 | 1 | 1 | EA | 99 | 255 | F | 000600001695 | X
| 0000851964529010304033000500001825 | 85196 | 128 |  | 2023-12-30 | 261 | H | 10304033 | 30 | 30 | EA | 20 | 20 | F | 000500001825 | X
| 00001316824544210304033000100033161 | 131682 | 1 |  | 2024-05-30 | 261 | H | 10304033 | 7 | 7 | EA | 30 | 30 | F | 000100033161 | X
| 00001322714541610304033000100033739 | 132271 | 1 |  | 2024-05-04 | 261 | H | 10304033 | 9 | 9 | EA | 30 | 30 | F | 000100033739 | X
| 00001322734541710304033000100033781 | 132273 | 1 |  | 2024-05-05 | 261 | H | 10304033 | 6 | 6 | EA | 30 | 30 | F | 000100033781 | X
| 00001322744541810304033000100033782 | 132274 | 1 |  | 2024-05-06 | 261 | H | 10304033 | 4 | 4 | EA | 30 | 30 | F | 000100033782 | X
| 00001322754541810304033000100033783 | 132275 | 1 |  | 2024-05-06 | 261 | H | 10304033 | 5 | 5 | EA | 30 | 30 | F | 000100033783 | X
| 00001322764541910304033000100033784 | 132276 | 2 |  | 2024-05-07 | 261 | H | 10304033 | 5 | 5 | EA | 30 | 30 | F | 000100033784 | X
| 00001322774539910304033000100033785 | 132277 | 1 |  | 2024-04-17 | 261 | H | 10304033 | 1 | 1 | EA | 30 | 30 | F | 000100033785 | X
| 00001322784537910304033000100033786 | 132278 | 1 |  | 2024-03-28 | 261 | H | 10304033 | 1 | 1 | EA | 30 | 30 | F | 000100033786 | X
| 00001323524537910304033000100033880 | 132352 | 1 |  | 2024-03-28 | 261 | H | 10304033 | 1 | 1 | EA | 20 | 20 | F | 000100033880 | X
| 00001323534542110304033000100033881 | 132353 | 2 |  | 2024-05-09 | 261 | H | 10304033 | 4 | 4 | EA | 20 | 20 | F | 000100033881 | X
| 00001310394540010305744000100032535 | 131039 | 2 |  | 2024-04-18 | 261 | H | 10305744 | 4 | 4 | EA | 20 | 20 | F | 000100032535 | X
| 00001389424620410305744000100040461 | 138942 | 2 |  | 2026-07-01 | 261 | H | 10305744 | 4 | 4 | EA | 10 | 10 | F | 000100040461 | X
| 00001287344539110355246000200090465 | 128734 | 18 |  | 2024-04-09 | 261 | H | 10355246 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001287344539110355246000200090465 | 128734 | 20 |  | 2024-04-09 | 261 | H | 10355246 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539510355246000200091461 | 129691 | 19 |  | 2024-04-13 | 261 | H | 10355246 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 00001296914539510355246000200091461 | 129691 | 21 |  | 2024-04-13 | 261 | H | 10355246 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 0000936494552610402509000200059360 | 93649 | 5 |  | 2024-08-22 | 261 | H | 10402509 | 2 | 2 | DR | 10 | 10 | F | 000200059360 | X
| 0000936524552610402509000200059363 | 93652 | 5 |  | 2024-08-22 | 261 | H | 10402509 | 2 | 2 | DR | 10 | 10 | F | 000200059363 | X
| 0000963414542110402509000200061999 | 96341 | 5 |  | 2024-05-09 | 261 | H | 10402509 | 2 | 2 | DR | 10 | 10 | F | 000200061999 | X
| 0000963444546310402509000200062042 | 96344 | 5 |  | 2024-06-20 | 261 | H | 10402509 | 2 | 2 | DR | 10 | 10 | F | 000200062042 | X
| 00001240894531610402509000200085795 | 124089 | 4 |  | 2024-01-25 | 261 | H | 10402509 | 1 | 1 | DR | 10 | 10 | F | 000200085795 | X
| 00001246014533810402509000200086292 | 124601 | 5 |  | 2024-02-16 | 261 | H | 10402509 | 1 | 1 | DR | 10 | 10 | F | 000200086292 | X
| 00002228244562410402509000200139478 | 222824 | 12 |  | 2024-11-28 | 261 | H | 10402509 | 2 | 2 | DR | 10 | 10 | F | 000200139478 | X
| 00002228314562410402509000200139603 | 222831 | 12 |  | 2024-11-28 | 261 | H | 10402509 | 2 | 2 | DR | 10 | 10 | F | 000200139603 | X
| 00001321494542110423729000100033628 | 132149 | 3 |  | 2024-05-09 | 261 | H | 10423729 | 1 | 1 | SET | 20 | 20 | F | 000100033628 | X
| 0000936494552610424330000200059360 | 93649 | 6 |  | 2024-08-22 | 261 | H | 10424330 | 1 | 1 | EA | 10 | 10 | F | 000200059360 | X
| 0000936524552610424330000200059363 | 93652 | 6 |  | 2024-08-22 | 261 | H | 10424330 | 1 | 1 | EA | 10 | 10 | F | 000200059363 | X
| 0000963414542110424330000200061999 | 96341 | 6 |  | 2024-05-09 | 261 | H | 10424330 | 1 | 1 | EA | 10 | 10 | F | 000200061999 | X
| 0000963444546310424330000200062042 | 96344 | 6 |  | 2024-06-20 | 261 | H | 10424330 | 1 | 1 | EA | 10 | 10 | F | 000200062042 | X
| 00002228244562410424330000200139478 | 222824 | 7 |  | 2024-11-28 | 261 | H | 10424330 | 1 | 1 | EA | 10 | 10 | F | 000200139478 | X
| 00002228314562410424330000200139603 | 222831 | 7 |  | 2024-11-28 | 261 | H | 10424330 | 1 | 1 | EA | 10 | 10 | F | 000200139603 | X
| 00001021234542110430531000200067754 | 102123 | 1 |  | 2024-05-09 | 261 | H | 10430531 | 1 | 1 | EA | 20 | 20 | F | 000200067754 | X
| 00001126094542110438411000200078320 | 112609 | 4 |  | 2024-05-09 | 261 | H | 10438411 | 1 | 1 | KIT | 5 | 10 | F | 000200078320 | X
| 0000992144542110438413000200064912 | 99214 | 3 |  | 2024-05-09 | 261 | H | 10438413 | 1 | 1 | EA | 5 | 10 | F | 000200064912 | X
| 00002272104572310438413000200142104 | 227210 | 1 |  | 2025-03-07 | 261 | H | 10438413 | 1 | 1 | EA | 5 | 10 | F | 000200142104 | X
| 0000992144542110438563000200064912 | 99214 | 2 |  | 2024-05-09 | 261 | H | 10438563 | 2 | 2 | EA | 5 | 10 | F | 000200064912 | X
| 00002272104572310438563000200142104 | 227210 | 2 |  | 2025-03-07 | 261 | H | 10438563 | 2 | 2 | EA | 5 | 10 | F | 000200142104 | X
| 00001362964537910439222000100037795 | 136296 | 1 |  | 2024-03-28 | 261 | H | 10439222 | 1 | 1 | EA | 5 | 10 | F | 000100037795 | X
| 00001368644570410439222000100038383 | 136864 | 1 |  | 2025-02-16 | 261 | H | 10439222 | 1 | 1 | EA | 5 | 10 | F | 000100038383 | X
| 00001384374540610439222000100039936 | 138437 | 1 |  | 2024-04-24 | 261 | H | 10439222 | 1 | 1 | EA | 5 | 10 | F | 000100039936 | X
| 00001321494542110440971000100033628 | 132149 | 2 |  | 2024-05-09 | 261 | H | 10440971 | 2 | 2 | KIT | 20 | 20 | F | 000100033628 | X
| 00001182814541410443257000200082368 | 118281 | 5 |  | 2024-05-02 | 261 | H | 10443257 | 1 | 1 | SET | 10 | 10 | F | 000200082368 | X
| 0000902854560410444408000200055956 | 90285 | 1 |  | 2024-11-08 | 261 | H | 10444408 | 2 | 2 | EA | 5 | 10 | F | 000200055956 | X
| 0000961674551410444408000200061838 | 96167 | 1 |  | 2024-08-10 | 261 | H | 10444408 | 2 | 2 | EA | 5 | 10 | F | 000200061838 | X
| 00001221144538710444408000200084013 | 122114 | 1 |  | 2024-04-05 | 261 | H | 10444408 | 2 | 2 | EA | 5 | 10 | F | 000200084013 | X
| 00002228894569610444408000200139557 | 222889 | 2 |  | 2025-02-08 | 261 | H | 10444408 | 2 | 2 | EA | 5 | 10 | F | 000200139557 | X
| 00002252344536110444408000100074108 | 225234 | 1 |  | 2024-03-10 | 261 | H | 10444408 | 1 | 1 | EA | 20 | 20 | F | 000100074108 | X
| 0000874084564210445237000200053140 | 87408 | 5 |  | 2024-12-16 | 261 | H | 10445237 | 1 | 1 | EA | 10 | 10 | F | 000200053140 | X
| 00001182814541410445237000200082368 | 118281 | 4 |  | 2024-05-02 | 261 | H | 10445237 | 1 | 1 | EA | 10 | 10 | F | 000200082368 | X
| 00001229624544710445237000200084673 | 122962 | 2 |  | 2024-06-04 | 261 | H | 10445237 | 2 | 2 | EA | 10 | 10 | F | 000200084673 | X
| 00001261964546310445237000200087947 | 126196 | 3 |  | 2024-06-20 | 261 | H | 10445237 | 1 | 1 | EA | 10 | 10 | F | 000200087947 | X
| 00001268114535810445237000200088601 | 126811 | 2 |  | 2024-03-07 | 261 | H | 10445237 | 1 | 1 | EA | 10 | 10 | F | 000200088601 | X
| 00001329294542110445243000100034425 | 132929 | 2 |  | 2024-05-09 | 261 | H | 10445243 | 1 | 1 | EA | 20 | 20 | F | 000100034425 | X
| 00001287344539110447452000200090465 | 128734 | 23 |  | 2024-04-09 | 261 | H | 10447452 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001287344539110447453000200090465 | 128734 | 19 |  | 2024-04-09 | 261 | H | 10447453 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001287344539110447453000200090465 | 128734 | 21 |  | 2024-04-09 | 261 | H | 10447453 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001287344539110447458000200090465 | 128734 | 24 |  | 2024-04-09 | 261 | H | 10447458 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001287344539110447458000200090465 | 128734 | 27 |  | 2024-04-09 | 261 | H | 10447458 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 0000977784542110447827000200063469 | 97778 | 2 |  | 2024-05-09 | 261 | H | 10447827 | 1 | 1 | EA | 20 | 20 | F | 000200063469 | X
| 0000977784542210447827000200063469 | 97778 | 3 |  | 2024-05-10 | 262 | S | 10447827 | 1 | 1 | EA | 20 | 20 | F | 000200063469 | X
| 0000977784542110447849000200063469 | 97778 | 1 |  | 2024-05-09 | 261 | H | 10447849 | 4 | 4 | SET | 20 | 20 | F | 000200063469 | X
| 00001204554538710451306000200083257 | 120455 | 4 |  | 2024-04-05 | 261 | H | 10451306 | 1 | 1 | EA | 5 | 10 | F | 000200083257 | X
| 00001207094539310451345000200083367 | 120709 | 2 |  | 2024-04-11 | 261 | H | 10451345 | 2 | 2 | EA | 5 | 10 | F | 000200083367 | X
| 00001211124539210451369000200083535 | 121112 | 3 |  | 2024-04-10 | 261 | H | 10451369 | 1 | 1 | KIT | 5 | 10 | F | 000200083535 | X
| 00001211124539210451370000200083535 | 121112 | 2 |  | 2024-04-10 | 261 | H | 10451370 | 2 | 2 | EA | 5 | 10 | F | 000200083535 | X
| 0000876744546010452835000200053366 | 87674 | 1 |  | 2024-06-17 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200053366 | X
| 0000890404543910452835000200054732 | 89040 | 1 |  | 2024-05-27 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200054732 | X
| 0000911974540010452835000200056909 | 91197 | 1 |  | 2024-04-18 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200056909 | X
| 0000917984538710452835000200057510 | 91798 | 1 |  | 2024-04-05 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200057510 | X
00009381710452835000200059528 | 0000938174536510452835000200059528 | 93817 | 1 |  | 2024-03-14 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200059528 | X
000021584310452835000200134937 | 00002158434548110452835000200134937 | 215843 | 1 |  | 2024-07-08 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200134937 | X
000021786610452835000200136429 | 00002178664550210452835000200136429 | 217866 | 1 |  | 2024-07-29 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136429 | X
| 00002178714552310452835000200136430 | 217871 | 1 |  | 2024-08-19 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136430 | X
| 00002178744554410452835000200136431 | 217874 | 1 |  | 2024-09-09 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136431 | X
| 00002178764556510452835000200136432 | 217876 | 1 |  | 2024-09-30 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136432 | X
| 00002178794558610452835000200136433 | 217879 | 1 |  | 2024-10-21 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136433 | X
| 00002178814560710452835000200136434 | 217881 | 1 |  | 2024-11-11 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136434 | X
| 00002178844562810452835000200136435 | 217884 | 1 |  | 2024-12-02 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136435 | X
| 00002178854564910452835000200136436 | 217885 | 1 |  | 2024-12-23 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136436 | X
| 00002178864567010452835000200136437 | 217886 | 1 |  | 2025-01-13 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200136437 | X
| 00002202454569110452835000200137449 | 220245 | 1 |  | 2025-02-03 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200137449 | X
| 00002251134570610452835000200140824 | 225113 | 1 |  | 2025-02-18 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200140824 | X
| 00002284704573310452835000200142496 | 228470 | 1 |  | 2025-03-17 | 261 | H | 10452835 | 1 | 1 | CON | 10 | 10 | F | 000200142496 | X
| 0000896884562010452872000200055359 | 89688 | 1 |  | 2024-11-24 | 261 | H | 10452872 | 1 | 1 | DR | 5 | 10 | F | 000200055359 | X
| 0000896884562110452872000200055359 | 89688 | 3 |  | 2024-11-25 | 261 | H | 10452872 | 1 | 1 | DR | 5 | 10 | F | 000200055359 | X
| 00001198274541710452872000200083040 | 119827 | 1 |  | 2024-05-05 | 261 | H | 10452872 | 1 | 1 | DR | 5 | 10 | F | 000200083040 | X
| 00001403794571010452872000100041867 | 140379 | 21 |  | 2025-02-22 | 261 | H | 10452872 | 1 | 1 | DR | 10 | 10 | F | 000100041867 | X
| 0000990814547010453016000200064753 | 99081 | 1 |  | 2024-06-27 | 261 | H | 10453016 | 1 | 1 | CON | 10 | 10 | F | 000200064753 | X
| 0000992144542110453016000200064912 | 99214 | 1 |  | 2024-05-09 | 261 | H | 10453016 | 1 | 1 | CON | 5 | 10 | F | 000200064912 | X
| 00001126094542110453016000200078320 | 112609 | 2 |  | 2024-05-09 | 261 | H | 10453016 | 1 | 1 | CON | 5 | 10 | F | 000200078320 | X
| 00002272104572310453016000200142104 | 227210 | 3 |  | 2025-03-07 | 261 | H | 10453016 | 1 | 1 | CON | 5 | 10 | F | 000200142104 | X
| 00001334014537910454267000100034857 | 133401 | 17 |  | 2024-03-28 | 261 | H | 10454267 | 2 | 2 | EA | 20 | 20 | F | 000100034857 | X
| 00001366174541910458155000100038113 | 136617 | 19 |  | 2024-05-07 | 261 | H | 10458155 | 1 | 1 | EA | 30 | 30 | F | 000100038113 | X
| 00001347504542110458397000100036218 | 134750 | 7 |  | 2024-05-09 | 261 | H | 10458397 | 1 | 1 | KIT | 20 | 20 | F | 000100036218 | X
| 00001347514548410458397000100036219 | 134751 | 5 |  | 2024-07-11 | 261 | H | 10458397 | 1 | 1 | KIT | 20 | 20 | F | 000100036219 | X
| 00001360984538710458817000100037574 | 136098 | 42 |  | 2024-04-05 | 261 | H | 10458817 | 4 | 4 | EA | 20 | 20 | F | 000100037574 | X
| 00001360984538710462880000100037574 | 136098 | 39 |  | 2024-04-05 | 261 | H | 10462880 | 2 | 2 | EA | 20 | 20 | F | 000100037574 | X
| 00001360984538710462880000100037574 | 136098 | 57 |  | 2024-04-05 | 261 | H | 10462880 | 2 | 2 | EA | 20 | 20 | F | 000100037574 | X
| 00001360984538710463080000100037574 | 136098 | 40 |  | 2024-04-05 | 261 | H | 10463080 | 1 | 1 | EA | 20 | 20 | F | 000100037574 | X
| 00001360984538710463080000100037574 | 136098 | 56 |  | 2024-04-05 | 261 | H | 10463080 | 1 | 1 | EA | 20 | 20 | F | 000100037574 | X
| 00001360984538710463417000100037574 | 136098 | 46 |  | 2024-04-05 | 261 | H | 10463417 | 1 | 1 | EA | 20 | 20 | F | 000100037574 | X
| 00001360984538710463589000100037574 | 136098 | 43 |  | 2024-04-05 | 261 | H | 10463589 | 2 | 2 | EA | 20 | 20 | F | 000100037574 | X
| 00001138564542110467825000200079587 | 113856 | 3 |  | 2024-05-09 | 261 | H | 10467825 | 4 | 4 | EA | 5 | 10 | F | 000200079587 | X
| 00001368224542110468800000100038290 | 136822 | 1 |  | 2024-05-09 | 261 | H | 10468800 | 1 | 1 | EA | 20 | 20 | F | 000100038290 | X
| 00001392674538610468906000100040735 | 139267 | 1 |  | 2024-04-04 | 261 | H | 10468906 | 1 | 1 | EA | 5 | 10 | F | 000100040735 | X
| 00001392674538610468906000100040735 | 139267 | 2 |  | 2024-04-04 | 261 | H | 10468906 | 1 | 1 | EA | 5 | 10 | F | 000100040735 | X
| 00001287344539110473813000200090465 | 128734 | 28 |  | 2024-04-09 | 261 | H | 10473813 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539510473813000200091461 | 129691 | 29 |  | 2024-04-13 | 261 | H | 10473813 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 00001126094542110473861000200078320 | 112609 | 5 |  | 2024-05-09 | 261 | H | 10473861 | 1 | 1 | KIT | 5 | 10 | F | 000200078320 | X
| 0000857124529110476885000500002406 | 85712 | 100 |  | 2023-12-31 | 261 | H | 10476885 | 2 | 2 | EA | 20 | 20 | F | 000500002406 | X
| 00001181694540610476885000200082341 | 118169 | 1 |  | 2024-04-24 | 261 | H | 10476885 | 4 | 4 | EA | 5 | 10 | F | 000200082341 | X
| 00001287344539110477745000200090465 | 128734 | 35 |  | 2024-04-09 | 261 | H | 10477745 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539410477745000200091461 | 129691 | 10 |  | 2024-04-12 | 261 | H | 10477745 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 00001085094539410478596000200074182 | 108509 | 1 |  | 2024-04-12 | 261 | H | 10478596 | 204 | 204 | EA | 10 | 10 | F | 000200074182 | X
| 00001207094539310478596000200083367 | 120709 | 1 |  | 2024-04-11 | 261 | H | 10478596 | 1 | 1 | EA | 5 | 10 | F | 000200083367 | X
| 0000902854560410479633000200055956 | 90285 | 2 |  | 2024-11-08 | 261 | H | 10479633 | 3 | 3 | PAI | 5 | 10 | F | 000200055956 | X
| 0000961674551410479633000200061838 | 96167 | 2 |  | 2024-08-10 | 261 | H | 10479633 | 3 | 3 | PAI | 5 | 10 | F | 000200061838 | X
| 00001221144538710479633000200084013 | 122114 | 2 |  | 2024-04-05 | 261 | H | 10479633 | 3 | 3 | PAI | 5 | 10 | F | 000200084013 | X
| 00002135084530010479633000500003740 | 213508 | 3 |  | 2024-01-09 | 261 | H | 10479633 | 3 | 3 | PAI | 99 | 255 | F | 000500003740 | X
| 00002228894569610479633000200139557 | 222889 | 3 |  | 2025-02-08 | 261 | H | 10479633 | 2 | 2 | PAI | 5 | 10 | F | 000200139557 | X
| 0000936494552610482346000200059360 | 93649 | 7 |  | 2024-08-22 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200059360 | X
| 0000936524552610482346000200059363 | 93652 | 7 |  | 2024-08-22 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200059363 | X
| 0000963414542110482346000200061999 | 96341 | 7 |  | 2024-05-09 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200061999 | X
| 0000963444546310482346000200062042 | 96344 | 7 |  | 2024-06-20 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200062042 | X
| 00001240894526710482346000200085795 | 124089 | 3 |  | 2023-12-07 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200085795 | X
| 00001246014533810482346000200086292 | 124601 | 1 |  | 2024-02-16 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200086292 | X
| 00001246014533810482346000200086292 | 124601 | 4 |  | 2024-02-16 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200086292 | X | 0001277024541510060883000200089392 | 00001277024541510060883000200089392 | FALSE
| 00001246014533810482346000200086292 | 124601 | 30 |  | 2024-02-16 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200086292 | X
| 00001246834532410482346000200086394 | 124683 | 1 |  | 2024-02-02 | 261 | H | 10482346 | 14 | 14 | PAC | 5 | 10 | F | 000200086394 | X
| 00002228244562410482346000200139478 | 222824 | 2 |  | 2024-11-28 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200139478 | X
| 00002228314562410482346000200139603 | 222831 | 2 |  | 2024-11-28 | 261 | H | 10482346 | 2 | 2 | PAC | 10 | 10 | F | 000200139603 | X
| 0000979844539110482558000200063635 | 97984 | 1 |  | 2024-04-09 | 261 | H | 10482558 | 1 | 1 | EA | 10 | 10 | F | 000200063635 | X
| 00001366174541910484646000100038113 | 136617 | 18 |  | 2024-05-07 | 261 | H | 10484646 | 2 | 2 | EA | 30 | 30 | F | 000100038113 | X
| 00001427824540910485935000100044230 | 142782 | 10 |  | 2024-04-27 | 261 | H | 10485935 | 2 | 2 | EA | 30 | 30 | F | 000100044230 | X
| 00001427824540910485937000100044230 | 142782 | 11 |  | 2024-04-27 | 261 | H | 10485937 | 1 | 1 | EA | 30 | 30 | F | 000100044230 | X
| 00001275994540810493398000200089401 | 127599 | 2 |  | 2024-04-26 | 261 | H | 10493398 | 1 | 1 | ASY | 20 | 20 | F | 000200089401 | X
| 00001275994540810493398000200089401 | 127599 | 5 |  | 2024-04-26 | 261 | H | 10493398 | 1 | 1 | ASY | 20 | 20 | F | 000200089401 | X
| 00001275994540810493399000200089401 | 127599 | 3 |  | 2024-04-26 | 261 | H | 10493399 | 1 | 1 | ASY | 20 | 20 | F | 000200089401 | X
| 00001275994540810493399000200089401 | 127599 | 6 |  | 2024-04-26 | 261 | H | 10493399 | 1 | 1 | ASY | 20 | 20 | F | 000200089401 | X
| 00001275994540810493402000200089401 | 127599 | 4 |  | 2024-04-26 | 261 | H | 10493402 | 1 | 1 | ASY | 20 | 20 | F | 000200089401 | X
| 00001275994540810493402000200089401 | 127599 | 7 |  | 2024-04-26 | 261 | H | 10493402 | 1 | 1 | ASY | 20 | 20 | F | 000200089401 | X
| 00002194344540010493451000100072801 | 219434 | 1 |  | 2024-04-18 | 261 | H | 10493451 | 1 | 1 | ASY | 30 | 30 | F | 000100072801 | X
| 00001334014537910498808000100034857 | 133401 | 18 |  | 2024-03-28 | 261 | H | 10498808 | 2 | 2 | EA | 20 | 20 | F | 000100034857 | X
| 00001334014537910501971000100034857 | 133401 | 19 |  | 2024-03-28 | 261 | H | 10501971 | 40 | 40 | L | 20 | 20 | F | 000100034857 | X
| 00001332394540010503357000100034735 | 133239 | 3 |  | 2024-04-18 | 261 | H | 10503357 | 1 | 1 | EA | 5 | 10 | F | 000100034735 | X
| 00001334014537910503782000100034857 | 133401 | 2 |  | 2024-03-28 | 261 | H | 10503782 | 1 | 1 | EA | 20 | 20 | F | 000100034857 | X
| 00001334014537910503783000100034857 | 133401 | 1 |  | 2024-03-28 | 261 | H | 10503783 | 1 | 1 | EA | 20 | 20 | F | 000100034857 | X
| 00001182574541110503901000200082353 | 118257 | 2 |  | 2024-04-29 | 261 | H | 10503901 | 24 | 24 | EA | 5 | 10 | F | 000200082353 | X
| 00002185114541410503901000100072584 | 218511 | 28 |  | 2024-05-02 | 261 | H | 10503901 | 24 | 24 | EA | 5 | 10 | F | 000100072584 | X
| 0000902834560410504876000200055954 | 90283 | 1 |  | 2024-11-08 | 261 | H | 10504876 | 1 | 1 | KIT | 10 | 10 | F | 000200055954 | X
| 0000902844560410504876000200055955 | 90284 | 1 |  | 2024-11-08 | 261 | H | 10504876 | 1 | 1 | KIT | 10 | 10 | F | 000200055955 | X
| 00001221064541010504876000200084010 | 122106 | 1 |  | 2024-04-28 | 261 | H | 10504876 | 1 | 1 | KIT | 10 | 10 | F | 000200084010 | X
| 00001221094540910504876000200084011 | 122109 | 1 |  | 2024-04-27 | 261 | H | 10504876 | 1 | 1 | KIT | 10 | 10 | F | 000200084011 | X
| 00001221124540810504876000200084012 | 122112 | 1 |  | 2024-04-26 | 261 | H | 10504876 | 1 | 1 | KIT | 10 | 10 | F | 000200084012 | X
| 00002228104569610504876000200139546 | 222810 | 3 |  | 2025-02-08 | 261 | H | 10504876 | 3 | 3 | KIT | 10 | 10 | F | 000200139546 | X
| 00002228814569810504876000200139548 | 222881 | 3 |  | 2025-02-10 | 261 | H | 10504876 | 3 | 3 | KIT | 20 | 20 | F | 000200139548 | X
| 00002228834569610504876000200139552 | 222883 | 3 |  | 2025-02-08 | 261 | H | 10504876 | 3 | 3 | KIT | 20 | 20 | F | 000200139552 | X
| 00002135914542110506101000600002860 | 213591 | 1 |  | 2024-05-09 | 261 | H | 10506101 | 50 | 50 | ROL | 20 | 20 | F | 000600002860 | X
| 00002135914542110506101000600002860 | 213591 | 4 |  | 2024-05-09 | 261 | H | 10506101 | 50 | 50 | ROL | 20 | 20 | F | 000600002860 | X
| 00001375194541610507576000100039045 | 137519 | 3 |  | 2024-05-04 | 261 | H | 10507576 | 2 | 2 | EA | 30 | 30 | F | 000100039045 | X
| 00001138564542110507776000200079587 | 113856 | 2 |  | 2024-05-09 | 261 | H | 10507776 | 1 | 1 | ASY | 5 | 10 | F | 000200079587 | X
| 00001316674542110508764000100033135 | 131667 | 1 |  | 2024-05-09 | 261 | H | 10508764 | 4 | 4 | EA | 20 | 20 | F | 000100033135 | X
| 00001316684537910508764000100033136 | 131668 | 1 |  | 2024-03-28 | 261 | H | 10508764 | 4 | 4 | EA | 20 | 20 | F | 000100033136 | X
| 00001361654540110509009000100037641 | 136165 | 1 |  | 2024-04-19 | 261 | H | 10509009 | 1 | 1 | ROL | 30 | 30 | F | 000100037641 | X
| 00001322764541910509062000100033784 | 132276 | 1 |  | 2024-05-07 | 261 | H | 10509062 | 1 | 1 | EA | 30 | 30 | F | 000100033784 | X
| 0000874084564210509101000200053140 | 87408 | 2 |  | 2024-12-16 | 261 | H | 10509101 | 1 | 1 | EA | 10 | 10 | F | 000200053140 | X
| 00001182814541410509101000200082368 | 118281 | 6 |  | 2024-05-02 | 261 | H | 10509101 | 1 | 1 | EA | 10 | 10 | F | 000200082368 | X
| 00001366884541710515037000100038184 | 136688 | 5 |  | 2024-05-05 | 261 | H | 10515037 | 3 | 3 | EA | 30 | 30 | F | 000100038184 | X
| 00001204514541410520559000200083256 | 120451 | 1 |  | 2024-05-02 | 261 | H | 10520559 | 11 | 11 | EA | 20 | 20 | F | 000200083256 | X
| 00002156924559710520559000200134900 | 215692 | 1 |  | 2024-11-01 | 261 | H | 10520559 | 11 | 11 | EA | 20 | 20 | F | 000200134900 | X
| 00001287344539110527555000200090465 | 128734 | 25 |  | 2024-04-09 | 261 | H | 10527555 | 1 | 1 | ASY | 5 | 10 | F | 000200090465 | X
| 00001287344539110527555000200090465 | 128734 | 26 |  | 2024-04-09 | 261 | H | 10527555 | 1 | 1 | ASY | 5 | 10 | F | 000200090465 | X
| 00001181694540610530706000200082341 | 118169 | 2 |  | 2024-04-24 | 261 | H | 10530706 | 32 | 32 | EA | 5 | 10 | F | 000200082341 | X
| 00001326064540010533202000100034052 | 132606 | 2 |  | 2024-04-18 | 261 | H | 10533202 | 3 | 3 | DR | 20 | 20 | F | 000100034052 | X
| 00001325684540110534107000100034084 | 132568 | 23 |  | 2024-04-19 | 261 | H | 10534107 | 4 | 4 | EA | 5 | 10 | F | 000100034084 | X
| 00001325684540110534326000100034084 | 132568 | 8 |  | 2024-04-19 | 261 | H | 10534326 | 2 | 2 | EA | 5 | 10 | F | 000100034084 | X
| 00001325684540110534346000100034084 | 132568 | 11 |  | 2024-04-19 | 261 | H | 10534346 | 4 | 4 | EA | 5 | 10 | F | 000100034084 | X
| 00001325684540110534347000100034084 | 132568 | 12 |  | 2024-04-19 | 261 | H | 10534347 | 4 | 4 | EA | 5 | 10 | F | 000100034084 | X
| 00001325684540110534372000100034084 | 132568 | 14 |  | 2024-04-19 | 261 | H | 10534372 | 2 | 2 | EA | 5 | 10 | F | 000100034084 | X
| 00001321494542110534478000100033628 | 132149 | 1 |  | 2024-05-09 | 261 | H | 10534478 | 2 | 2 | EA | 20 | 20 | F | 000100033628 | X
| 00001334014537910534799000100034857 | 133401 | 7 |  | 2024-03-28 | 261 | H | 10534799 | 1 | 1 | ASY | 20 | 20 | F | 000100034857 | X
| 00001334014537910534799000100034857 | 133401 | 23 |  | 2024-03-28 | 261 | H | 10534799 | 1 | 1 | ASY | 20 | 20 | F | 000100034857 | X
| 0000874084564210537213000200053140 | 87408 | 3 |  | 2024-12-16 | 261 | H | 10537213 | 1 | 1 | EA | 10 | 10 | F | 000200053140 | X
| 00001273184540610537213000200089100 | 127318 | 4 |  | 2024-04-24 | 261 | H | 10537213 | 1 | 1 | EA | 10 | 10 | F | 000200089100 | X
| 00001333164535810537786000100034864 | 133316 | 1 |  | 2024-03-07 | 261 | H | 10537786 | 3 | 1 | EA | 20 | 20 | F | 000100034864 | X
| 00001361614533110537786000100037577 | 136161 | 9 |  | 2024-02-09 | 261 | H | 10537786 | 2 | 2 | EA | 30 | 30 | F | 000100037577 | X
| 00001366884541710543114000100038184 | 136688 | 4 |  | 2024-05-05 | 261 | H | 10543114 | 2 | 2 | EA | 30 | 30 | F | 000100038184 | X
| 00001361654540110546632000100037641 | 136165 | 3 |  | 2024-04-19 | 261 | H | 10546632 | 100 | 100 | EA | 30 | 30 | F | 000100037641 | X
| 00001321894540610547280000100033657 | 132189 | 1 |  | 2024-04-24 | 261 | H | 10547280 | 1 | 1 | EA | 5 | 10 | F | 000100033657 | X
| 00001321894540610547281000100033657 | 132189 | 2 |  | 2024-04-24 | 261 | H | 10547281 | 1 | 1 | EA | 5 | 10 | F | 000100033657 | X
| 0000843624537910547649000600001447 | 84362 | 5 |  | 2024-03-28 | 261 | H | 10547649 | 100 | 100 | M | 20 | 20 | F | 000600001447 | X
| 00001252504542110561611000200086992 | 125250 | 3 |  | 2024-05-09 | 261 | H | 10561611 | 2 | 2 | EA | 99 | 255 | F | 000200086992 | X
| 0000902594560510563505000200055931 | 90259 | 1 |  | 2024-11-09 | 261 | H | 10563505 | 4 | 4 | EA | 20 | 20 | F | 000200055931 | X
| 0000947854554410563505000200060437 | 94785 | 1 |  | 2024-09-09 | 261 | H | 10563505 | 4 | 4 | EA | 20 | 20 | F | 000200060437 | X
| 0000974304548210563505000200063108 | 97430 | 1 |  | 2024-07-09 | 261 | H | 10563505 | 4 | 4 | EA | 20 | 20 | F | 000200063108 | X
| 00001075034541110563505000200073134 | 107503 | 1 |  | 2024-04-29 | 261 | H | 10563505 | 4 | 4 | EA | 20 | 20 | F | 000200073134 | X
| 00002157584566610563505000200134932 | 215758 | 1 |  | 2025-01-09 | 261 | H | 10563505 | 4 | 4 | EA | 20 | 20 | F | 000200134932 | X
| 00002272004572510563505000200142018 | 227200 | 1 |  | 2025-03-09 | 261 | H | 10563505 | 4 | 4 | EA | 20 | 20 | F | 000200142018 | X
| 00002135914542110564774000600002860 | 213591 | 2 |  | 2024-05-09 | 261 | H | 10564774 | 100 | 100 | ROL | 20 | 20 | F | 000600002860 | X
| 00001325684540110565086000100034084 | 132568 | 22 |  | 2024-04-19 | 261 | H | 10565086 | 8 | 8 | EA | 5 | 10 | F | 000100034084 | X
| 00002135914542110565211000600002860 | 213591 | 3 |  | 2024-05-09 | 261 | H | 10565211 | 6 | 6 | EA | 20 | 20 | F | 000600002860 | X
| 00001325684540110568264000100034084 | 132568 | 17 |  | 2024-04-19 | 261 | H | 10568264 | 4 | 4 | EA | 5 | 10 | F | 000100034084 | X
| 00001287344539110569059000200090465 | 128734 | 10 |  | 2024-04-09 | 261 | H | 10569059 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001287344539110569059000200090465 | 128734 | 43 |  | 2024-04-09 | 261 | H | 10569059 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539510569059000200091461 | 129691 | 11 |  | 2024-04-13 | 261 | H | 10569059 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 00001296914539510569059000200091461 | 129691 | 43 |  | 2024-04-13 | 261 | H | 10569059 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 00001347504542110569848000100036218 | 134750 | 6 |  | 2024-05-09 | 261 | H | 10569848 | 2 | 2 | EA | 20 | 20 | F | 000100036218 | X
| 0000874084564210572710000200053140 | 87408 | 4 |  | 2024-12-16 | 261 | H | 10572710 | 2 | 2 | EA | 10 | 10 | F | 000200053140 | X
| 00001273184540610572710000200089100 | 127318 | 3 |  | 2024-04-24 | 261 | H | 10572710 | 2 | 2 | EA | 10 | 10 | F | 000200089100 | X
| 00001234124537910574508000200085162 | 123412 | 1 |  | 2024-03-28 | 261 | H | 10574508 | 1 | 1 | EA | 5 | 10 | F | 000200085162 | X
| 00001234134535810574508000200085163 | 123413 | 1 |  | 2024-03-07 | 261 | H | 10574508 | 1 | 1 | EA | 5 | 10 | F | 000200085163 | X
| 00001287344539110575223000200090465 | 128734 | 44 |  | 2024-04-09 | 261 | H | 10575223 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001287344539110575223000200090465 | 128734 | 45 |  | 2024-04-09 | 261 | H | 10575223 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539510575223000200091461 | 129691 | 44 |  | 2024-04-13 | 261 | H | 10575223 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 00001296914539510575223000200091461 | 129691 | 45 |  | 2024-04-13 | 261 | H | 10575223 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 0000936494552610576543000200059360 | 93649 | 9 |  | 2024-08-22 | 261 | H | 10576543 | 1 | 1 | EA | 10 | 10 | F | 000200059360 | X
| 0000936524552610576543000200059363 | 93652 | 9 |  | 2024-08-22 | 261 | H | 10576543 | 1 | 1 | EA | 10 | 10 | F | 000200059363 | X
| 0000963414542110576543000200061999 | 96341 | 9 |  | 2024-05-09 | 261 | H | 10576543 | 1 | 1 | EA | 10 | 10 | F | 000200061999 | X
| 0000963444546310576543000200062042 | 96344 | 9 |  | 2024-06-20 | 261 | H | 10576543 | 1 | 1 | EA | 10 | 10 | F | 000200062042 | X
| 00002228244562410576543000200139478 | 222824 | 1 |  | 2024-11-28 | 261 | H | 10576543 | 1 | 1 | EA | 10 | 10 | F | 000200139478 | X
| 00002228314562410576543000200139603 | 222831 | 1 |  | 2024-11-28 | 261 | H | 10576543 | 1 | 1 | EA | 10 | 10 | F | 000200139603 | X
| 00001310214541310583038000100032477 | 131021 | 2 |  | 2024-05-01 | 261 | H | 10583038 | 3 | 3 | EA | 5 | 10 | F | 000100032477 | X
| 00001310214541310583039000100032477 | 131021 | 1 |  | 2024-05-01 | 261 | H | 10583039 | 100 | 100 | EA | 5 | 10 | F | 000100032477 | X
| 00001380454542110584159000100039544 | 138045 | 5 |  | 2024-05-09 | 261 | H | 10584159 | 3 | 3 | PAC | 20 | 20 | F | 000100039544 | X
| 00001287344539110584918000200090465 | 128734 | 46 |  | 2024-04-09 | 261 | H | 10584918 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001287344539110584918000200090465 | 128734 | 47 |  | 2024-04-09 | 261 | H | 10584918 | 1 | 1 | EA | 5 | 10 | F | 000200090465 | X
| 00001296914539510584918000200091461 | 129691 | 46 |  | 2024-04-13 | 261 | H | 10584918 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 00001296914539510584918000200091461 | 129691 | 47 |  | 2024-04-13 | 261 | H | 10584918 | 1 | 1 | EA | 5 | 10 | F | 000200091461 | X
| 00001357634540210586379000100037219 | 135763 | 5 |  | 2024-04-20 | 261 | H | 10586379 | 4 | 4 | EA | 30 | 30 | F | 000100037219 | X
| 00001363444540310586379000100037863 | 136344 | 3 |  | 2024-04-21 | 261 | H | 10586379 | 24 | 24 | EA | 30 | 30 | F | 000100037863 | X
| 00001357634540210586381000100037219 | 135763 | 4 |  | 2024-04-20 | 261 | H | 10586381 | 4 | 4 | EA | 30 | 30 | F | 000100037219 | X
| 00001395254538510586381000100040991 | 139525 | 1 |  | 2024-04-03 | 261 | H | 10586381 | 8 | 8 | EA | 20 | 20 | F | 000100040991 | X
| 00001138564542110589262000200079587 | 113856 | 4 |  | 2024-05-09 | 261 | H | 10589262 | 1 | 1 | EA | 5 | 10 | F | 000200079587 | X
| 00002163684549010589262000100072009 | 216368 | 4 |  | 2024-07-17 | 261 | H | 10589262 | 2 | 2 | EA | 99 | 255 | F | 000100072009 | X
| 00001325684540110594202000100034084 | 132568 | 18 |  | 2024-04-19 | 261 | H | 10594202 | 1 | 1 | EA | 5 | 10 | F | 000100034084 | X
| 00001380454542110601253000100039544 | 138045 | 6 |  | 2024-05-09 | 261 | H | 10601253 | 3 | 3 | PAC | 20 | 20 | F | 000100039544 | X
| 00001380454542110601256000100039544 | 138045 | 9 |  | 2024-05-09 | 261 | H | 10601256 | 2 | 2 | EA | 20 | 20 | F | 000100039544 | X
| 00002135914542110601282000600002860 | 213591 | 5 |  | 2024-05-09 | 261 | H | 10601282 | 1 | 1 | EA | 20 | 20 | F | 000600002860 | X
| 00001361654540110602811000100037641 | 136165 | 2 |  | 2024-04-19 | 261 | H | 10602811 | 1 | 1 | EA | 30 | 30 | F | 000100037641 | X
| 00001380454542110605184000100039544 | 138045 | 8 |  | 2024-05-09 | 261 | H | 10605184 | 1 | 1 | EA | 20 | 20 | F | 000100039544 | X
| 00001380454542110605188000100039544 | 138045 | 11 |  | 2024-05-09 | 261 | H | 10605188 | 60 | 60 | EA | 20 | 20 | F | 000100039544 | X
| 00001380454542110605323000100039544 | 138045 | 10 |  | 2024-05-09 | 261 | H | 10605323 | 66 | 66 | EA | 20 | 20 | F | 000100039544 | X
| 00001380454542110605423000100039544 | 138045 | 7 |  | 2024-05-09 | 261 | H | 10605423 | 1 | 1 | EA | 20 | 20 | F | 000100039544 | X
| 00001372604542110605994000100038739 | 137260 | 4 |  | 2024-05-09 | 261 | H | 10605994 | 3 | 3 | EA | 20 | 20 | F | 000100038739 | X
| 00001362964537910606651000100037795 | 136296 | 3 |  | 2024-03-28 | 261 | H | 10606651 | 16 | 16 | EA | 5 | 10 | F | 000100037795 | X
| 00001368644570510606651000100038383 | 136864 | 3 |  | 2025-02-17 | 261 | H | 10606651 | 16 | 16 | EA | 5 | 10 | F | 000100038383 | X
| 00001384374540610606651000100039936 | 138437 | 3 |  | 2024-04-24 | 261 | H | 10606651 | 16 | 16 | EA | 5 | 10 | F | 000100039936 | X
| 00001334014537910606781000100034857 | 133401 | 9 |  | 2024-03-28 | 261 | H | 10606781 | 1 | 1 | EA | 20 | 20 | F | 000100034857 | X
| 00001334014537910606782000100034857 | 133401 | 5 |  | 2024-03-28 | 261 | H | 10606782 | 1 | 1 | EA | 20 | 20 | F | 000100034857 | X
| 00001334014537910606782000100034857 | 133401 | 20 |  | 2024-03-28 | 261 | H | 10606782 | 1 | 1 | EA | 20 | 20 | F | 000100034857 | X
| 00001287344539110607195000200090465 | 128734 | 38 |  | 2024-04-09 | 261 | H | 10607195 | 24 | 24 | EA | 5 | 10 | F | 000200090465 | X
| 00001167384542110607433000200081677 | 116738 | 1 |  | 2024-05-09 | 261 | H | 10607433 | 1 | 1 | EA | 99 | 255 | F | 000200081677 | X
| 00001167814544210607433000200081678 | 116781 | 1 |  | 2024-05-30 | 261 | H | 10607433 | 1 | 1 | EA | 99 | 255 | F | 000200081678 | X
| 00001167834542110608381000200081679 | 116783 | 1 |  | 2024-05-09 | 261 | H | 10608381 | 1 | 1 | EA | 99 | 255 | F | 000200081679 | X
| 00001167924542110608381000200081722 | 116792 | 1 |  | 2024-05-09 | 261 | H | 10608381 | 1 | 1 | EA | 99 | 255 | F | 000200081722 | X
| 00001342104542110608970000100035706 | 134210 | 1 |  | 2024-05-09 | 261 | H | 10608970 | 1 | 1 | EA | 20 | 20 | F | 000100035706 | X
| 00001325684540110613168000100034084 | 132568 | 1 |  | 2024-04-19 | 261 | H | 10613168 | 12 | 12 | EA | 5 | 10 | F | 000100034084 | X
| 00001325684540110613351000100034084 | 132568 | 19 |  | 2024-04-19 | 261 | H | 10613351 | 12 | 12 | EA | 5 | 10 | F | 000100034084 | X
| 00001306434540070000044000100032131 | 130643 | 2 |  | 2024-04-18 | 261 | H | 70000044 | 56 | 56 | EA | 20 | 20 | F | 000100032131 | X
| 00001306444548470000044000100032132 | 130644 | 1 |  | 2024-07-11 | 261 | H | 70000044 | 56 | 56 | EA | 20 | 20 | F | 000100032132 | X
| 00001306454540070000044000100032133 | 130645 | 2 |  | 2024-04-18 | 261 | H | 70000044 | 56 | 56 | EA | 20 | 20 | F | 000100032133 | X
| 00001306464542170000044000100032134 | 130646 | 1 |  | 2024-05-09 | 261 | H | 70000044 | 56 | 56 | EA | 20 | 20 | F | 000100032134 | X
| 00001306474548470000044000100032135 | 130647 | 1 |  | 2024-07-11 | 261 | H | 70000044 | 56 | 56 | EA | 20 | 20 | F | 000100032135 | X
| 00001306434540070000047000100032131 | 130643 | 4 |  | 2024-04-18 | 261 | H | 70000047 | 116 | 116 | EA | 20 | 20 | F | 000100032131 | X
| 00001306444548470000047000100032132 | 130644 | 2 |  | 2024-07-11 | 261 | H | 70000047 | 4 | 4 | EA | 20 | 20 | F | 000100032132 | X
| 00001306454540070000047000100032133 | 130645 | 3 |  | 2024-04-18 | 261 | H | 70000047 | 4 | 4 | EA | 20 | 20 | F | 000100032133 | X
| 00001306464542170000047000100032134 | 130646 | 2 |  | 2024-05-09 | 261 | H | 70000047 | 8 | 8 | EA | 20 | 20 | F | 000100032134 | X
| 00001306474548470000047000100032135 | 130647 | 2 |  | 2024-07-11 | 261 | H | 70000047 | 8 | 8 | EA | 20 | 20 | F | 000100032135 | X
| 00001306434540070000048000100032131 | 130643 | 6 |  | 2024-04-18 | 261 | H | 70000048 | 4 | 4 | EA | 20 | 20 | F | 000100032131 | X
| 00001306444548470000048000100032132 | 130644 | 3 |  | 2024-07-11 | 261 | H | 70000048 | 4 | 4 | EA | 20 | 20 | F | 000100032132 | X
| 00001306454540070000048000100032133 | 130645 | 4 |  | 2024-04-18 | 261 | H | 70000048 | 16 | 16 | EA | 20 | 20 | F | 000100032133 | X
| 00001306464542170000048000100032134 | 130646 | 3 |  | 2024-05-09 | 261 | H | 70000048 | 8 | 8 | EA | 20 | 20 | F | 000100032134 | X
| 00001306474548470000048000100032135 | 130647 | 3 |  | 2024-07-11 | 261 | H | 70000048 | 8 | 8 | EA | 20 | 20 | F | 000100032135 | X
| 00001306444548470000049000100032132 | 130644 | 4 |  | 2024-07-11 | 261 | H | 70000049 | 4 | 4 | EA | 20 | 20 | F | 000100032132 | X
| 00001306454540070000049000100032133 | 130645 | 6 |  | 2024-04-18 | 261 | H | 70000049 | 12 | 12 | EA | 20 | 20 | F | 000100032133 | X
| 00001306474548470000049000100032135 | 130647 | 4 |  | 2024-07-11 | 261 | H | 70000049 | 16 | 16 | EA | 20 | 20 | F | 000100032135 | X
| 00001317634542170000094000100033231 | 131763 | 2 |  | 2024-05-09 | 261 | H | 70000094 | 10 | 10 | EA | 20 | 20 | F | 000100033231 | X
| 00001317634542170000096000100033231 | 131763 | 4 |  | 2024-05-09 | 261 | H | 70000096 | 38 | 38 | EA | 20 | 20 | F | 000100033231 | X
| 00001306444548470000100000100032132 | 130644 | 5 |  | 2024-07-11 | 261 | H | 70000100 | 28 | 28 | EA | 20 | 20 | F | 000100032132 | X
| 00001306454540070000100000100032133 | 130645 | 8 |  | 2024-04-18 | 261 | H | 70000100 | 28 | 28 | EA | 20 | 20 | F | 000100032133 | X
| 00001305484540670000589000100032076 | 130548 | 6 |  | 2024-04-24 | 261 | H | 70000589 | 1 | 1 | EA | 20 | 20 | F | 000100032076 | X
| 00001356164541170001063000100037132 | 135616 | 8 |  | 2024-04-29 | 261 | H | 70001063 | 1 | 1 | EA | 20 | 20 | F | 000100037132 | X
| 0000844804540070001189000600001624 | 84480 | 2 |  | 2024-04-18 | 261 | H | 70001189 | 9 | 9 | EA | 20 | 20 | F | 000600001624 | X
| 0000844804540070001200000600001624 | 84480 | 4 |  | 2024-04-18 | 261 | H | 70001200 | 3 | 3 | EA | 20 | 20 | F | 000600001624 | X
| 00001321894540670001416000100033657 | 132189 | 4 |  | 2024-04-24 | 261 | H | 70001416 | 1 | 1 | EA | 5 | 10 | F | 000100033657 | X
| 00001375194541670001493000100039045 | 137519 | 4 |  | 2024-05-04 | 261 | H | 70001493 | 1 | 1 | EA | 30 | 30 | F | 000100039045 | X
| 00001310214541370001522000100032477 | 131021 | 4 |  | 2024-05-01 | 261 | H | 70001522 | 1 | 1 | EA | 5 | 10 | F | 000100032477 | X
| 00001310214541370001523000100032477 | 131021 | 6 |  | 2024-05-01 | 261 | H | 70001523 | 1 | 1 | BOX | 5 | 10 | F | 000100032477 | X
| 00001326454542170001542000100034141 | 132645 | 3 |  | 2024-05-09 | 261 | H | 70001542 | 80 | 80 | EA | 20 | 20 | F | 000100034141 | X
| 00001326454542170001543000100034141 | 132645 | 4 |  | 2024-05-09 | 261 | H | 70001543 | 80 | 80 | EA | 20 | 20 | F | 000100034141 | X
| 00001315254540070001748000100033044 | 131525 | 4 |  | 2024-04-18 | 261 | H | 70001748 | 1 | 1 | EA | 20 | 20 | F | 000100033044 | X
| 0000845794532470002089000600001724 | 84579 | 3 |  | 2024-02-02 | 261 | H | 70002089 | 1 | 1 | EA | 20 | 20 | F | 000600001724 | X
| 00001375204540470002317000100039046 | 137520 | 7 |  | 2024-04-22 | 261 | H | 70002317 | 1 | 1 | EA | 30 | 30 | F | 000100039046 | X
| 00001375204540470002318000100039046 | 137520 | 8 |  | 2024-04-22 | 261 | H | 70002318 | 1 | 1 | EA | 30 | 30 | F | 000100039046 | X
| 00001375204540470002319000100039046 | 137520 | 9 |  | 2024-04-22 | 261 | H | 70002319 | 1 | 1 | EA | 30 | 30 | F | 000100039046 | X
| 00001366174541970002402000100038113 | 136617 | 16 |  | 2024-05-07 | 261 | H | 70002402 | 1 | 1 | EA | 30 | 30 | F | 000100038113 | X
| 00001366174541970002403000100038113 | 136617 | 17 |  | 2024-05-07 | 261 | H | 70002403 | 1 | 1 | EA | 30 | 30 | F | 000100038113 | X
| 00001360374529870002482000100037513 | 136037 | 5 |  | 2024-01-07 | 261 | H | 70002482 | 1 | 1 | EA | 5 | 10 | F | 000100037513 | X
| 00001366884541770003315000100038184 | 136688 | 7 |  | 2024-05-05 | 261 | H | 70003315 | 1 | 1 | EA | 30 | 30 | F | 000100038184 | X
| 00001366884541770003316000100038184 | 136688 | 8 |  | 2024-05-05 | 261 | H | 70003316 | 1 | 1 | EA | 30 | 30 | F | 000100038184 | X
| 00001368224542270003475000100038290 | 136822 | 2 |  | 2024-05-10 | 261 | H | 70003475 | 1 | 1 | EA | 20 | 20 | F | 000100038290 | X
| 00001368234542170003475000100038291 | 136823 | 3 |  | 2024-05-09 | 261 | H | 70003475 | 1 | 1 | EA | 20 | 20 | F | 000100038291 | X
| 00001360984538770003498000100037574 | 136098 | 52 |  | 2024-04-05 | 261 | H | 70003498 | 1 | 1 | EA | 20 | 20 | F | 000100037574 | X
| 0000845794537970003722000600001724 | 84579 | 6 |  | 2024-03-28 | 261 | H | 70003722 | 1 | 1 | EA | 20 | 20 | F | 000600001724 | X
| 00001316674542170003747000100033135 | 131667 | 3 |  | 2024-05-09 | 261 | H | 70003747 | 4 | 4 | EA | 20 | 20 | F | 000100033135 | X
| 00001316104542170003767000100032996 | 131610 | 8 |  | 2024-05-09 | 261 | H | 70003767 | 1 | 1 | EA | 30 | 30 | F | 000100032996 | X
| 0000845794537970003940000600001724 | 84579 | 14 |  | 2024-03-28 | 261 | H | 70003940 | 150 | 150 | EA | 20 | 20 | F | 000600001724 | X
| 0000845794537970003941000600001724 | 84579 | 15 |  | 2024-03-28 | 261 | H | 70003941 | 150 | 150 | EA | 20 | 20 | F | 000600001724 | X
| 0000845794537970003942000600001724 | 84579 | 16 |  | 2024-03-28 | 261 | H | 70003942 | 150 | 150 | EA | 20 | 20 | F | 000600001724 | X
| 0000845794537970003943000600001724 | 84579 | 18 |  | 2024-03-28 | 261 | H | 70003943 | 150 | 150 | EA | 20 | 20 | F | 000600001724 | X
| 0000845794537970003950000600001724 | 84579 | 20 |  | 2024-03-28 | 261 | H | 70003950 | 1 | 1 | SET | 20 | 20 | F | 000600001724 | X
| 00002198964542170004675000100072934 | 219896 | 2 |  | 2024-05-09 | 261 | H | 70004675 | 4 | 4 | EA | 20 | 20 | F | 000100072934 | X
| 00002289824537970004851000100075531 | 228982 | 3 |  | 2024-03-28 | 261 | H | 70004851 | 2 | 2 | EA | 20 | 20 | F | 000100075531 | X
| 00002289824537970004852000100075531 | 228982 | 4 |  | 2024-03-28 | 261 | H | 70004852 | 2 | 2 | EA | 20 | 20 | F | 000100075531 | X

## Monitor PO
Purchase Order | Item | Material | Supplier | Next Delivery Date | Next Delivery Quantity | Order Quantity | Net Order Value | Quantity to be Delivered | Value to be Invoiced | Material Number | Account Assignment Category | Central Purchasing Block on Supplier | Company Code | Company Name | Created By | Created On | Delivered Quantity | Delivered Value | Delivery Complete | End of Performance Period | Expected Value | Final Invoice | Fully Delivered & Invoiced | Goods Receipt | Goods-Receipt-Based Invoice Verification | Info Record Update | Invoice Receipt | Invoiced Quantity | Invoiced Value | Item Category | Item Count | Material Group | Material Group Description | Material Name | Net Order Price | Next Delivery Status | Non-Valuated Goods Receipt | Order Currency | Order Date | Order Status | Order Type | Order Unit | Overall Limit | Plant | Plant Name | Price Unit | Product Type Group | Purchase Contract | Purchase Contract Item | Purchase Order Item | Purchase Requisition | Purchase Requisition Item | Purchasing Category | Purchasing Group | Purchasing Group Name | Purchasing Info Record | Purchasing Organization | Purchasing Organization Name | Quantity to be Invoiced | Request For Quotation | Request For Quotation Item | Requirement Tracking Number | Returns Item | Service Performer | Service Performer Name | Short Text | Start of Performance Period | Stock Segment | Storage Location | Supplier ID | Supplier Name | Supplier Quotation | Supplier Quotation Item | Supplying Plant | Supplying Plant Name | Value to be Delivered
4500000548 | 00020 | DISC,RUPTURE;385BAR,G1/4"BSPP (10534478) | HYDRAULIC ENERGY AUST PTY LTD (30002606) | 2024-03-27 | 2 | 2 | 3325.6 | 2 | 3325.6 | 10534478 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-19 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | Standard () | 1 | Pipe piping/fittings (40170000) | Pipe piping/fittings | DISC,RUPTURE;385BAR,G1/4"BSPP | 1662.8 | Overdue | 0 | Australian Dollar (AUD) | 2024-01-19 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500000548/00020 | 2000002505 | 00010 |  | AUS Operations (106) | AUS Operations | 5300000411 | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | DISC,RUPTURE;385BAR,G1/4"BSPP |  |  | Main Store (1001) | 30002606 | HYDRAULIC ENERGY AUST PTY LTD | 6000000106 | 20 |  |  | 3325.6
4500000722 | 00010 | VALVE,ARI 35.006R,PN40,DN25,CS,GLOBE (10473813) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-07-01 | 2 | 2 | 4768.3 | 2 | 4768.3 | 10473813 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,ARI 35.006R,PN40,DN25,CS,GLOBE | 2384.15 | Due Later | 0 | Australian Dollar (AUD) | 2024-01-23 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000098 | 08280 | 4500000722/00010 | 2000002536 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | VALVE,ARI 35.006R,PN40,DN25,CS,GLOBE |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 4768.3
4500000792 | 00010 | VALVE,COMPL;SHIPHAM DM991209E (10439222) | PILS CO LTD (30002423) | 2024-03-27 | 1 | 1 | 3621.23 | 1 | 3621.23 | 10439222 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Brayden Tomkinson | 2024-01-23 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,COMPL;SHIPHAM DM991209E | 3621.23 | Overdue | 0 | United States Dollar (USD) | 2024-01-23 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500000792/00010 | 2000002506 | 00010 |  | AUS Operations (106) | AUS Operations | 5300000611 | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | VALVE,COMPL;SHIPHAM DM991209E |  |  | Main Store (1001) | 30002423 | PILS CO LTD | 6000000111 | 10 |  |  | 3621.23
4500000887 | 00030 | VALVE,GLOBE;BC6,16K,15A,F7409,HSN (10503357) | PILS CO LTD (30002423) | 2024-02-24 | 7 | 7 | 432.91 | 7 | 432.91 | 10503357 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-24 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,GLOBE;BC6,16K,15A,F7409,HSN | 61.84 | Overdue | 0 | United States Dollar (USD) | 2024-01-24 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500000887/00030 | 2000003348 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 7 |  |  |  | 0 |  |  | VALVE,GLOBE;BC6,16K,15A,F7409,HSN |  |  | Main Store (1001) | 30002423 | PILS CO LTD | 6000000134 | 30 |  |  | 432.91
4500001334 | 00010 | LIGHT,WARNING,AVIATION;ORGA L85EXRAC32 (10508764) | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 2024-03-28 | 4 | 4 | 8476.04 | 4 | 8476.04 | 10508764 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Lighting Fixt/ accs. (39110000) | Lighting Fixt/ accs. | LIGHT,WARNING,AVIATION;ORGA L85EXRAC32 | 2119.01 | Overdue | 0 | Australian Dollar (AUD) | 2024-01-31 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001334/00010 | 2000002402 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  |  | 0 |  |  | LIGHT,WARNING,AVIATION;ORGA L85EXRAC32 |  |  | Main Store (1001) | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD | 6000000056 | 10 |  |  | 8476.04
4500001334 | 00060 | CABLE,DATA;CAT 6,4PR,CU,LSZH,GRY (10547649) | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 2024-02-14 | 100 | 100 | 237 | 100 | 0 | 10547649 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 100 | 237 | Standard () | 1 | Elec wire/cable/harn (26120000) | Elec wire/cable/harn | CABLE,DATA;CAT 6,4PR,CU,LSZH,GRY | 2.37 | Overdue | 0 | Australian Dollar (AUD) | 2024-01-31 | Follow-On Documents | WEG Purchase Order (ZNB) | Meter (M) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001334/00060 | 2000003056 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 0 |  |  |  | 0 |  |  | CABLE,DATA;CAT 6,4PR,CU,LSZH,GRY |  |  | Main Store (1001) | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD | 6000000056 | 60 |  |  | 237
4500001352 | 00050 | NUT,LK;SOLAR 903112C1 (10243755) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-03-01 | 12 | 12 | 101.38 | 12 | 101.38 | 10243755 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 101.54 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | NUT,LK;SOLAR 903112C1 | 33.79 | Overdue | 0 | United States Dollar (USD) | 2024-01-31 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000324 | 31960 | 4500001352/00050 | 2000002823 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 12 |  |  |  | 0 |  |  | NUT,LK;SOLAR 903112C1 |  |  | Main Store (1001) | 30000400 | SOLAR TURBINES INTERNATIONAL COMPANY |  | 0 |  |  | 101.38
4500001460 | 00010 | GASKET;SWCI,JIS 16K,15MM,316L/GR/316 (10507576) | KLINGER LIMITED (30000403) | 2024-04-03 | 2 | 2 | 17.18 | 2 | 17.18 | 10507576 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,JIS 16K,15MM,316L/GR/316 | 8.59 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-01 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 14580 | 4500001460/00010 | 2000012622 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | GASKET;SWCI,JIS 16K,15MM,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 17.18
4500001467 | 00010 | D-WEL23-200-01/EH0950DX0004.0001 Spool 1 (70001493) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-04-08 | 1 | 1 | 6821.11 | 1 | 6821.11 | 70001493 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-200-01/EH0950DX0004.0001 Spool 1 | 6821.11 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-01 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001467/00010 | 1000001607 | 00004 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100039045 | 0 |  |  | D-WEL23-200-01/EH0950DX0004.0001 Spool 1 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 6821.11
4500001467 | 00020 | D-WEL23-201-01/EH0950DX0006.0001 Spool 1 (70002317) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-04-08 | 1 | 1 | 5742.32 | 1 | 5742.32 | 70002317 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-201-01/EH0950DX0006.0001 Spool 1 | 5742.32 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-01 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001467/00020 | 1000002389 | 00007 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100039046 | 0 |  |  | D-WEL23-201-01/EH0950DX0006.0001 Spool 1 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 5742.32
4500001467 | 00030 | D-WEL23-201-02/EH0950DX0007.0001 Spool 1 (70002318) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-04-08 | 1 | 1 | 5742.32 | 1 | 5742.32 | 70002318 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-201-02/EH0950DX0007.0001 Spool 1 | 5742.32 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-01 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001467/00030 | 1000002389 | 00008 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100039046 | 0 |  |  | D-WEL23-201-02/EH0950DX0007.0001 Spool 1 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 5742.32
4500001467 | 00040 | D-WEL23-201-03/EH0950DX0008.0001 Spool 1 (70002319) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-04-08 | 1 | 1 | 5742.32 | 1 | 5742.32 | 70002319 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-201-03/EH0950DX0008.0001 Spool 1 | 5742.32 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-01 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001467/00040 | 1000002389 | 00009 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100039046 | 0 |  |  | D-WEL23-201-03/EH0950DX0008.0001 Spool 1 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 5742.32
4500001467 | 00050 | D-WEL23-202-01/EH0950DX0005.0001 Spool 1 (70002402) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-04-08 | 1 | 1 | 5794.82 | 1 | 5794.82 | 70002402 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-202-01/EH0950DX0005.0001 Spool 1 | 5794.82 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-01 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001467/00050 | 1000002375 | 00016 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100038113 | 0 |  |  | D-WEL23-202-01/EH0950DX0005.0001 Spool 1 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 5794.82
4500001467 | 00060 | D-WEL23-202-01/EH0950DX0005.0001 Spool 2 (70002403) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-04-08 | 1 | 1 | 5036.62 | 1 | 5036.62 | 70002403 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-01-31 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-202-01/EH0950DX0005.0001 Spool 2 | 5036.62 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-01 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001467/00060 | 1000002375 | 00017 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100038113 | 0 |  |  | D-WEL23-202-01/EH0950DX0005.0001 Spool 2 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 5036.62
4500001554 | 00340 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML (10233767) | J BLACKWOOD AND SON LTD (30000394) | 2024-03-15 | 2 | 2 | 43.98 | 2 | 43.98 | 10233767 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Adhesives/sealants (31200000) | Adhesives/sealants | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 21.99 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-01 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000820 | 03350 | 4500001554/00340 | 2000009725 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML |  |  | Main Store (1001) | 30000394 | J BLACKWOOD AND SON LTD |  | 0 |  |  | 43.98
4500001554 | 00350 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML (10233767) | J BLACKWOOD AND SON LTD (30000394) | 2024-02-22 | 32 | 32 | 703.68 | 32 | 703.68 | 10233767 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Adhesives/sealants (31200000) | Adhesives/sealants | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 21.99 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-01 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000820 | 03350 | 4500001554/00350 | 2000012543 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 32 |  |  |  | 0 |  |  | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML |  |  | Main Store (1001) | 30000394 | J BLACKWOOD AND SON LTD |  | 0 |  |  | 703.68
4500001554 | 00360 | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML (10233767) | J BLACKWOOD AND SON LTD (30000394) | 2024-03-08 | 12 | 32 | 703.68 | 12 | 263.88 | 10233767 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-01 | 20 | 439.8 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 20 | 439.8 | Standard () | 1 | Adhesives/sealants (31200000) | Adhesives/sealants | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML | 21.99 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-01 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000820 | 03350 | 4500001554/00360 | 2000012544 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 12 |  |  |  | 0 |  |  | ADHESIVE;WHT,SIKAFLEX 252,CART 300ML |  |  | Main Store (1001) | 30000394 | J BLACKWOOD AND SON LTD |  | 0 |  |  | 263.88
4500001717 | 00010 | VALVE,MONOFLG;50MM,CL1500,HAST,H15M8 (10485937) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-07-05 | 1 | 1 | 23360.93 | 1 | 23360.93 | 10485937 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-02 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,MONOFLG;50MM,CL1500,HAST,H15M8 | 23360.93 | Due Later | 0 | British Pound (GBP) | 2024-02-02 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001717/00010 | 2000002517 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | VALVE,MONOFLG;50MM,CL1500,HAST,H15M8 |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD | 6000000120 | 10 |  |  | 23360.93
4500001908 | 00010 | PAINT,SPRAY;FR COATING (10565211) | INTERNATIONAL CORROSION SERVICES PTY LTD (30002531) | 2024-04-08 | 6 | 6 | 13170 | 6 | 13170 | 10565211 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-05 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Paint/primer/finish (31210000) | Paint/primer/finish | PAINT,SPRAY;FR COATING | 2195 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-05 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001908/00010 | 2000012992 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 6 |  |  |  | 0 |  |  | PAINT,SPRAY;FR COATING |  |  | Main Store (1001) | 30002531 | INTERNATIONAL CORROSION SERVICES PTY LTD | 6000000775 | 10 |  |  | 13170
4500001908 | 00020 | TAPE;SPLC,RBR,FIRE SECURITY FS17 (10564774) | INTERNATIONAL CORROSION SERVICES PTY LTD (30002531) | 2024-04-08 | 100 | 100 | 8500 | 100 | 8500 | 10564774 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-05 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Adhesives/sealants (31200000) | Adhesives/sealants | TAPE;SPLC,RBR,FIRE SECURITY FS17 | 85 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-05 | Sent | WEG Purchase Order (ZNB) | Roll (ROL) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001908/00020 | 2000012999 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 100 |  |  |  | 0 |  |  | TAPE;SPLC,RBR,FIRE SECURITY FS17 |  |  | Main Store (1001) | 30002531 | INTERNATIONAL CORROSION SERVICES PTY LTD | 6000000775 | 30 |  |  | 8500
4500001908 | 00030 | TAPE,ELEC,25MM X 4.6M,3M SCOTCH 24-TAPE (10506101) | INTERNATIONAL CORROSION SERVICES PTY LTD (30002531) | 2024-04-08 | 50 | 50 | 5500 | 50 | 5500 | 10506101 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-05 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Adhesives/sealants (31200000) | Adhesives/sealants | TAPE,ELEC,25MM X 4.6M,3M SCOTCH 24-TAPE | 110 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-05 | Sent | WEG Purchase Order (ZNB) | Roll (ROL) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001908/00030 | 2000012995 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 50 |  |  |  | 0 |  |  | TAPE,ELEC,25MM X 4.6M,3M SCOTCH 24-TAPE |  |  | Main Store (1001) | 30002531 | INTERNATIONAL CORROSION SERVICES PTY LTD |  | 0 |  |  | 5500
4500001908 | 00040 | TAPE,ELEC,25MM X 4.6M,3M SCOTCH 24-TAPE (10506101) | INTERNATIONAL CORROSION SERVICES PTY LTD (30002531) | 2024-04-08 | 50 | 50 | 5500 | 50 | 5500 | 10506101 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-05 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Adhesives/sealants (31200000) | Adhesives/sealants | TAPE,ELEC,25MM X 4.6M,3M SCOTCH 24-TAPE | 110 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-05 | Sent | WEG Purchase Order (ZNB) | Roll (ROL) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500001908/00040 | 2000040436 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 50 |  |  |  | 0 |  |  | TAPE,ELEC,25MM X 4.6M,3M SCOTCH 24-TAPE |  |  | Main Store (1001) | 30002531 | INTERNATIONAL CORROSION SERVICES PTY LTD |  | 0 |  |  | 5500
4500002229 | 00010 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L (10305744) | KLINGER LIMITED (30000403) | 2024-05-17 | 2 | 2 | 18.54 | 2 | 18.54 | 10305744 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 9.27 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-08 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 10240 | 4500002229/00010 | 1000002139 | 00005 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  | 100043385 | 0 |  |  | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 18.54
4500002479 | 00010 | BIT,DRILL;STEPPED,TSBT5.574S,HILTI (10583038) | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 2024-02-29 | 3 | 3 | 240.57 | 3 | 240.57 | 10583038 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-09 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Metal cut mch/accs. (23240000) | Metal cut mch/accs. | BIT,DRILL;STEPPED,TSBT5.574S,HILTI | 80.19 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-09 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000818 | 09610 | 4500002479/00010 | 2000016436 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 3 |  |  |  | 0 |  |  | BIT,DRILL;STEPPED,TSBT5.574S,HILTI |  |  | Main Store (1001) | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD |  | 0 |  |  | 240.57
4500002724 | 00010 | FILTER; Single Stage, 1000mm x 1000mm x (70002482) | TRINKOR PTY LTD (30001954) | 2024-03-11 | 1 | 1 | 516.31 | 1 | 516.31 | 70002482 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-13 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | HVAC equip/component (40100000) | HVAC equip/component | FILTER; Single Stage, 1000mm x 1000mm x | 516.31 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-13 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500002724/00010 | 1000002382 | 00005 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100037513 | 0 |  |  | FILTER; Single Stage, 1000mm x 1000mm x |  |  | Main Store (1001) | 30001954 | TRINKOR PTY LTD |  | 0 |  |  | 516.31
4500003280 | 00010 | STUD;THD,ELEC,M10,SDSS,HILTI (10583039) | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 2024-05-19 | 100 | 100 | 1857 | 100 | 1857 | 10583039 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-18 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUD;THD,ELEC,M10,SDSS,HILTI | 18.57 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-19 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500003280/00010 | 2000016432 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 100 |  |  |  | 0 |  |  | STUD;THD,ELEC,M10,SDSS,HILTI |  |  | Main Store (1001) | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD | 6000001129 | 10 |  |  | 1857
4500003416 | 00010 | FILTER KIT,ELEM,LUBE OIL;SOLAR 10647286 (10424330) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-03-30 | 2 | 2 | 1212.98 | 2 | 0 | 10424330 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-20 | 0 | 1206.6 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 1215.96 | Standard () | 1 | Ind filter/purific (40160000) | Ind filter/purific | FILTER KIT,ELEM,LUBE OIL;SOLAR 10647286 | 606.49 | Due Later | 0 | United States Dollar (USD) | 2024-02-20 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000324 | 23940 | 4500003416/00010 | 2000020515 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 0 |  |  |  | 0 |  |  | FILTER KIT,ELEM,LUBE OIL;SOLAR 10647286 |  |  | Main Store (1001) | 30000400 | SOLAR TURBINES INTERNATIONAL COMPANY |  | 0 |  |  | 1212.98
4500003440 | 00010 | Cooling system flush (70000589) | WESTRAC PTY LTD (30000280) | 2023-02-27 | 1 | 1 | 427 | 1 | 427 | 70000589 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-20 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Additives (12160000) | Additives | Cooling system flush | 427 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-20 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500003440/00010 | 1000002945 | 00006 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100032076 | 0 |  |  | Cooling system flush |  |  | Main Store (1001) | 30000280 | WESTRAC PTY LTD |  | 0 |  |  | 427
4500003832 | 00010 | GASKET;400MM,406MM,FF,KLINGER 864434161 (10205993) | KLINGER LIMITED (30000403) | 2024-04-29 | 4 | 4 | 256.84 | 4 | 256.84 | 10205993 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;400MM,406MM,FF,KLINGER 864434161 | 64.21 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-22 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 07700 | 4500003832/00010 | 2000022490 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  |  | 0 |  |  | GASKET;400MM,406MM,FF,KLINGER 864434161 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 256.84
4500003832 | 00020 | GASKET,RJ;OCT,R46,SI (10467825) | KLINGER LIMITED (30000403) | 2024-03-15 | 4 | 4 | 310.16 | 4 | 310.16 | 10467825 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,RJ;OCT,R46,SI | 77.54 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-22 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 11160 | 4500003832/00020 | 2000022494 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  |  | 0 |  |  | GASKET,RJ;OCT,R46,SI |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 310.16
4500003832 | 00030 | GASKET;CNAF,20MM,CL150,1.5MM,FF,C4430 (10206291) | KLINGER LIMITED (30000403) | 2024-04-04 | 1 | 1 | 3.03 | 1 | 3.03 | 10206291 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;CNAF,20MM,CL150,1.5MM,FF,C4430 | 3.03 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-22 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 07790 | 4500003832/00030 | 2000022496 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | GASKET;CNAF,20MM,CL150,1.5MM,FF,C4430 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 3.03
4500003832 | 00040 | GASKET,FLG;125MM,1.5MM THK,CNAF,CL150 (10204117) | KLINGER LIMITED (30000403) | 2024-05-01 | 4 | 4 | 20.16 | 4 | 20.16 | 10204117 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,FLG;125MM,1.5MM THK,CNAF,CL150 | 5.04 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-22 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 07180 | 4500003832/00040 | 2000022522 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  |  | 0 |  |  | GASKET,FLG;125MM,1.5MM THK,CNAF,CL150 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 20.16
4500003832 | 00050 | GASKET,FLG;125MM,1.5MM THK,CNAF,CL150 (10204117) | KLINGER LIMITED (30000403) | 2024-05-07 | 4 | 4 | 20.16 | 4 | 20.16 | 10204117 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,FLG;125MM,1.5MM THK,CNAF,CL150 | 5.04 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-22 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 07180 | 4500003832/00050 | 2000022523 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  |  | 0 |  |  | GASKET,FLG;125MM,1.5MM THK,CNAF,CL150 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 20.16
4500003832 | 00060 | GASKET;CNAF,JIS16K,40MM,3MM,FF,C4430 (10458155) | KLINGER LIMITED (30000403) | 2024-04-04 | 1 | 1 | 8.21 | 1 | 8.21 | 10458155 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;CNAF,JIS16K,40MM,3MM,FF,C4430 | 8.21 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-22 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 11150 | 4500003832/00060 | 2000022530 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | GASKET;CNAF,JIS16K,40MM,3MM,FF,C4430 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 8.21
4500003833 | 00010 | GASKET,CNAF;JIS10K,25MM,3MM,FF,C4430 (10484646) | KLINGER LIMITED (30000403) | 2024-04-17 | 2 | 2 | 14.42 | 2 | 14.42 | 10484646 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,CNAF;JIS10K,25MM,3MM,FF,C4430 | 7.21 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-22 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 14070 | 4500003833/00010 | 1000003365 | 00018 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  | 100038113 | 0 |  |  | GASKET,CNAF;JIS10K,25MM,3MM,FF,C4430 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 14.42
4500003941 | 00010 | STUDBOLT;0.750"X125MM,B7,CAD+XYLAN (10058893) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-29 | 16 | 16 | 59.2 | 16 | 59.2 | 10058893 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-23 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT;0.750"X125MM,B7,CAD+XYLAN | 3.7 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-23 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000000 | 00300 | 4500003941/00010 | 2000022502 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 16 |  |  |  | 0 |  |  | STUDBOLT;0.750"X125MM,B7,CAD+XYLAN |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 59.2
4500003941 | 00030 | STUDBOLT;1.000"X 165MM,B7,CAD+XYLAN (10058535) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-29 | 32 | 32 | 252.8 | 32 | 252.8 | 10058535 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-23 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT;1.000"X 165MM,B7,CAD+XYLAN | 7.9 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-23 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000000 | 00810 | 4500003941/00030 | 2000022501 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 32 |  |  |  | 0 |  |  | STUDBOLT;1.000"X 165MM,B7,CAD+XYLAN |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 252.8
4500004017 | 00010 | GASKET;400MM,406MM,FF,KLINGER 864434161 (10205993) | KLINGER LIMITED (30000403) | 2024-03-09 | 2 | 2 | 128.42 | 2 | 128.42 | 10205993 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-25 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;400MM,406MM,FF,KLINGER 864434161 | 64.21 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-26 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 07700 | 4500004017/00010 | 2000022491 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | GASKET;400MM,406MM,FF,KLINGER 864434161 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 128.42
4500004017 | 00020 | GASKET,CNAF,150MM,CL150,1.5MM,FF,C4430 (10206298) | KLINGER LIMITED (30000403) | 2024-03-09 | 1 | 1 | 12.83 | 1 | 12.83 | 10206298 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-25 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,CNAF,150MM,CL150,1.5MM,FF,C4430 | 12.83 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-26 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004017/00020 | 2000022499 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | GASKET,CNAF,150MM,CL150,1.5MM,FF,C4430 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 12.83
4500004235 | 00010 | HOSE ASY,CW;13.6MM,AFLEX HYPERLINESB (10493451) | ALFA LAVAL AUSTRALIA PTY LTD (30000326) | 2024-03-07 | 1 | 1 | 165.04 | 1 | 0 | 10493451 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-26 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 165.04 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | HOSE ASY,CW;13.6MM,AFLEX HYPERLINESB | 165.04 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-27 | Follow-On Documents | WEG Purchase Order (ZNB) | Assembly (ASY) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004235/00010 | 2000016423 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 0 |  |  |  | 0 |  |  | HOSE ASY,CW;13.6MM,AFLEX HYPERLINESB |  |  | Main Store (1001) | 30000326 | ALFA LAVAL AUSTRALIA PTY LTD | 6000001164 | 10 |  |  | 165.04
4500004322 | 00010 | STUDBOLT 1/2"-13UNC x 150mm S32760-3 (70000044) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-15 | 56 | 56 | 1901.2 | 56 | 1901.2 | 70000044 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT 1/2"-13UNC x 150mm S32760-3 | 33.95 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004322/00010 | 1000003746 | 00001 |  | AUS Operations (106) | AUS Operations | 5300000120 | AU00 | WEG Australia | 56 |  |  | 100032132 | 0 |  |  | STUDBOLT 1/2"-13UNC x 150mm S32760-3 |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 1901.2
4500004322 | 00020 | STUDBOLT 5/8"-11UNC x 150mm S32760-S (70000047) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-15 | 4 | 4 | 190.2 | 4 | 190.2 | 70000047 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT 5/8"-11UNC x 150mm S32760-S | 47.55 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004322/00020 | 1000003746 | 00002 |  | AUS Operations (106) | AUS Operations | 5300000121 | AU00 | WEG Australia | 4 |  |  | 100032132 | 0 |  |  | STUDBOLT 5/8"-11UNC x 150mm S32760-S |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 190.2
4500004322 | 00030 | STUDBOLT 3/4"-10UNC x 150mm S32760-S (70000048) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-15 | 4 | 4 | 149 | 4 | 149 | 70000048 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT 3/4"-10UNC x 150mm S32760-S | 37.25 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004322/00030 | 1000003746 | 00003 |  | AUS Operations (106) | AUS Operations | 5300000122 | AU00 | WEG Australia | 4 |  |  | 100032132 | 0 |  |  | STUDBOLT 3/4"-10UNC x 150mm S32760-S |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 149
4500004322 | 00050 | STUDBOLT 1"-8UN x 150mm S32760-S (70000100) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-15 | 28 | 28 | 3281.6 | 28 | 3281.6 | 70000100 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT 1"-8UN x 150mm S32760-S | 117.2 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004322/00050 | 1000003746 | 00005 |  | AUS Operations (106) | AUS Operations | 5300000124 | AU00 | WEG Australia | 28 |  |  | 100032132 | 0 |  |  | STUDBOLT 1"-8UN x 150mm S32760-S |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 3281.6
4500004322 | 00060 | STUDBOLT 1/2"-13UNC x 150mm S32760-3 (70000044) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-15 | 56 | 56 | 1901.2 | 56 | 1901.2 | 70000044 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT 1/2"-13UNC x 150mm S32760-3 | 33.95 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004322/00060 | 1000003749 | 00001 |  | AUS Operations (106) | AUS Operations | 5300000120 | AU00 | WEG Australia | 56 |  |  | 100032135 | 0 |  |  | STUDBOLT 1/2"-13UNC x 150mm S32760-3 |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 1901.2
4500004322 | 00070 | STUDBOLT 5/8"-11UNC x 150mm S32760-S (70000047) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-15 | 8 | 8 | 380.4 | 8 | 380.4 | 70000047 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT 5/8"-11UNC x 150mm S32760-S | 47.55 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004322/00070 | 1000003749 | 00002 |  | AUS Operations (106) | AUS Operations | 5300000121 | AU00 | WEG Australia | 8 |  |  | 100032135 | 0 |  |  | STUDBOLT 5/8"-11UNC x 150mm S32760-S |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 380.4
4500004322 | 00080 | STUDBOLT 3/4"-10UNC x 150mm S32760-S (70000048) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-15 | 8 | 8 | 298 | 8 | 298 | 70000048 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT 3/4"-10UNC x 150mm S32760-S | 37.25 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004322/00080 | 1000003749 | 00003 |  | AUS Operations (106) | AUS Operations | 5300000122 | AU00 | WEG Australia | 8 |  |  | 100032135 | 0 |  |  | STUDBOLT 3/4"-10UNC x 150mm S32760-S |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 298
4500004421 | 00010 | GASKET,FLG;40MM,1.5MM,JIS 5K,FF,CNAF (10515037) | KLINGER LIMITED (30000403) | 2024-04-04 | 3 | 3 | 11.13 | 3 | 11.13 | 10515037 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,FLG;40MM,1.5MM,JIS 5K,FF,CNAF | 3.71 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 14750 | 4500004421/00010 | 2000025015 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 3 |  |  |  | 0 |  |  | GASKET,FLG;40MM,1.5MM,JIS 5K,FF,CNAF |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 11.13
4500004421 | 00020 | GASKET;SWCI,JIS 16K,15MM,C4430 (10543114) | KLINGER LIMITED (30000403) | 2024-04-04 | 2 | 2 | 5.7 | 2 | 5.7 | 10543114 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,JIS 16K,15MM,C4430 | 2.85 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-27 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 15610 | 4500004421/00020 | 2000025031 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | GASKET;SWCI,JIS 16K,15MM,C4430 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 5.7
4500004437 | 00010 | D-WEL23-203-01 Spool 1 (70003315) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-04-15 | 1 | 1 | 6201.73 | 1 | 6201.73 | 70003315 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-203-01 Spool 1 | 6201.73 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-28 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004437/00010 | 1000003771 | 00007 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100038184 | 0 |  |  | D-WEL23-203-01 Spool 1 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 6201.73
4500004437 | 00020 | D-WEL23-203-01 Spool 2 (70003316) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-04-15 | 1 | 1 | 7235.35 | 1 | 7235.35 | 70003316 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-203-01 Spool 2 | 7235.35 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-28 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004437/00020 | 1000003771 | 00008 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100038184 | 0 |  |  | D-WEL23-203-01 Spool 2 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 7235.35
4500004522 | 00010 | SCREW,SET;HEX,HVY,7/8" X 120MM,A193,B7 (10503901) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-04-10 | 24 | 24 | 1503.6 | 24 | 1503.6 | 10503901 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Brayden Tomkinson | 2024-02-28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | SCREW,SET;HEX,HVY,7/8" X 120MM,A193,B7 | 62.65 | Due Later | 0 | Australian Dollar (AUD) | 2024-02-28 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004522/00010 | 2000022532 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 24 |  |  |  | 0 |  |  | SCREW,SET;HEX,HVY,7/8" X 120MM,A193,B7 |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD | 6000001624 | 10 |  |  | 1503.6
4500004680 | 00010 | BOLT ASY,HEX HD;WITH NUT,1.125"X100MM (10058077) | KONNECT COVENTRY GROUP LTD (30001930) | 2024-03-28 | 32 | 32 | 5315.2 | 32 | 5315.2 | 10058077 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-02-29 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | BOLT ASY,HEX HD;WITH NUT,1.125"X100MM | 166.1 | Overdue | 0 | Australian Dollar (AUD) | 2024-02-29 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004680/00010 | 2000022509 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 32 |  |  |  | 0 |  |  | BOLT ASY,HEX HD;WITH NUT,1.125"X100MM |  |  | Main Store (1001) | 30001930 | KONNECT COVENTRY GROUP LTD | 6000001634 | 10 |  |  | 5315.2
4500004816 | 00020 | CLAMP,SPLIT FLG,2",SS,RF,SOLAR 980656C1 (10463589) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-03-18 | 2 | 2 | 71.71 | 2 | 71.71 | 10463589 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-01 | 0 | 71.19 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | CLAMP,SPLIT FLG,2",SS,RF,SOLAR 980656C1 | 35.85 | Overdue | 0 | United States Dollar (USD) | 2024-03-01 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000324 | 29470 | 4500004816/00020 | 1000004043 | 00043 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  | 100037574 | 0 |  |  | CLAMP,SPLIT FLG,2",SS,RF,SOLAR 980656C1 |  |  | Main Store (1001) | 30000400 | SOLAR TURBINES INTERNATIONAL COMPANY |  | 0 |  |  | 71.71
4500004816 | 00030 | Expediting Freight Fees (70003498) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-03-15 | 1 | 1 | 307.1 | 1 | 307.1 | 70003498 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Pipe piping/fittings (40170000) | Pipe piping/fittings | Expediting Freight Fees | 307.1 | Overdue | 0 | United States Dollar (USD) | 2024-03-01 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004816/00030 | 1000004043 | 00052 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100037574 | 0 |  |  | Expediting Freight Fees |  |  | Main Store (1001) | 30000400 | SOLAR TURBINES INTERNATIONAL COMPANY |  | 0 |  |  | 307.1
4500004845 | 00010 | D-WEL23-215-01/EH4530DX0007.0001 Spool 1 (70001063) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-05-08 | 1 | 1 | 36260.5 | 1 | 36260.5 | 70001063 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fabricated pipe assy (31310000) | Fabricated pipe assy | D-WEL23-215-01/EH4530DX0007.0001 Spool 1 | 36260.5 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-01 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500004845/00010 | 1000003314 | 00008 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100037132 | 0 |  |  | D-WEL23-215-01/EH4530DX0007.0001 Spool 1 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 36260.5
4500005097 | 00010 | Toshiba Ex d IIC T4 Motor (70003475) | TOSHIBA INTERNATIONAL CORPORATION (30000272) | 2024-04-10 | 1 | 1 | 4500 | 1 | 4500 | 70003475 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-04 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Electrical equipment (39120000) | Electrical equipment | Toshiba Ex d IIC T4 Motor | 4500 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-05 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500005097/00010 | 1000004167 | 00003 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100038291 | 0 |  |  | Toshiba Ex d IIC T4 Motor |  |  | Main Store (1001) | 30000272 | TOSHIBA INTERNATIONAL CORPORATION |  | 0 |  |  | 4500
4500005097 | 00020 | Toshiba Ex d IIC T4 Motor (70003475) | TOSHIBA INTERNATIONAL CORPORATION (30000272) | 2024-04-10 | 1 | 1 | 4500 | 1 | 4500 | 70003475 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-04 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Electrical equipment (39120000) | Electrical equipment | Toshiba Ex d IIC T4 Motor | 4500 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-05 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500005097/00020 | 1000004218 | 00002 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100038290 | 0 |  |  | Toshiba Ex d IIC T4 Motor |  |  | Main Store (1001) | 30000272 | TOSHIBA INTERNATIONAL CORPORATION |  | 0 |  |  | 4500
4500005670 | 00010 | VALVE;MONOFLG,15MM,CL600,SS,S6M1L (10227715) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-10-14 | 2 | 2 | 6477.54 | 2 | 6477.54 | 10227715 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE;MONOFLG,15MM,CL600,SS,S6M1L | 3238.77 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000098 | 13470 | 4500005670/00010 | 2000030799 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | VALVE;MONOFLG,15MM,CL600,SS,S6M1L |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 6477.54
4500005670 | 00020 | VALVE,CHK;DN150,CL1500,RTJ,LTCS,L15C8C (10589262) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-07-17 | 1 | 1 | 5178.66 | 1 | 5178.66 | 10589262 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,CHK;DN150,CL1500,RTJ,LTCS,L15C8C | 5178.66 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000098 | 17320 | 4500005670/00020 | 2000030908 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | VALVE,CHK;DN150,CL1500,RTJ,LTCS,L15C8C |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 5178.66
4500005671 | 00010 | HOSE ASY;WTR/FOAM,RED,38MMX18M LG (10288499) | ARA MARINE PTY LTD (30000279) | 2024-04-15 | 2 | 2 | 3131.04 | 2 | 3131.04 | 10288499 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | HOSE ASY;WTR/FOAM,RED,38MMX18M LG | 1565.52 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000267 | 02380 | 4500005671/00010 | 2000030801 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | HOSE ASY;WTR/FOAM,RED,38MMX18M LG |  |  | Main Store (1001) | 30000279 | ARA MARINE PTY LTD |  | 0 |  |  | 3131.04
4500005671 | 00020 | EXTINGUISHER,FIRE;FOAM,AR-AFFF,45L (10451345) | ARA MARINE PTY LTD (30000279) | 2024-04-05 | 2 | 2 | 8102.52 | 2 | 8102.52 | 10451345 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fire protection (46190000) | Fire protection | EXTINGUISHER,FIRE;FOAM,AR-AFFF,45L | 4051.26 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000267 | 05350 | 4500005671/00020 | 2000030860 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | EXTINGUISHER,FIRE;FOAM,AR-AFFF,45L |  |  | Main Store (1001) | 30000279 | ARA MARINE PTY LTD |  | 0 |  |  | 8102.52
4500005685 | 00020 | GASKET;SWCI,40MM,PN10-40,316L/GR/316 (10061164) | KLINGER LIMITED (30000403) | 2024-04-02 | 21 | 21 | 326.13 | 21 | 326.13 | 10061164 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,40MM,PN10-40,316L/GR/316 | 15.53 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 05990 | 4500005685/00020 | 2000030836 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 21 |  |  |  | 0 |  |  | GASKET;SWCI,40MM,PN10-40,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 326.13
4500005685 | 00030 | GASKET;SWCI,25MM,PN10-40,316L/GR/316 (10061160) | KLINGER LIMITED (30000403) | 2024-04-02 | 38 | 38 | 418.76 | 38 | 418.76 | 10061160 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,25MM,PN10-40,316L/GR/316 | 11.02 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 05950 | 4500005685/00030 | 2000030864 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 38 |  |  |  | 0 |  |  | GASKET;SWCI,25MM,PN10-40,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 418.76
4500005685 | 00040 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L (10305744) | KLINGER LIMITED (30000403) | 2024-05-09 | 8 | 8 | 74.16 | 8 | 74.16 | 10305744 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 9.27 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 10240 | 4500005685/00040 | 2000031050 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 8 |  |  |  | 0 |  |  | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 74.16
4500005685 | 00050 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L (10305744) | KLINGER LIMITED (30000403) | 2024-06-04 | 2 | 2 | 18.54 | 2 | 18.54 | 10305744 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 9.27 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 10240 | 4500005685/00050 | 2000031051 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 18.54
4500005685 | 00060 | GASKET,SWCI;15MM,CL150,4.5MM,316L/GR/316 (10060881) | KLINGER LIMITED (30000403) | 2024-04-02 | 8 | 8 | 16.16 | 8 | 16.16 | 10060881 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SWCI;15MM,CL150,4.5MM,316L/GR/316 | 2.02 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04470 | 4500005685/00060 | 2000031072 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 8 |  |  |  | 0 |  |  | GASKET,SWCI;15MM,CL150,4.5MM,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 16.16
4500005685 | 00080 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR (10060884) | KLINGER LIMITED (30000403) | 2024-05-09 | 13 | 13 | 46.41 | 13 | 46.41 | 10060884 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 3.57 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04500 | 4500005685/00080 | 2000031133 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 13 |  |  |  | 0 |  |  | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 46.41
4500005685 | 00100 | GASKET;SWCI,80MM,CL150,316L/GR/316 (10060886) | KLINGER LIMITED (30000403) | 2024-04-11 | 9 | 9 | 63.27 | 9 | 63.27 | 10060886 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,80MM,CL150,316L/GR/316 | 7.03 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04520 | 4500005685/00100 | 2000031137 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 9 |  |  |  | 0 |  |  | GASKET;SWCI,80MM,CL150,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 63.27
4500005685 | 00110 | GASKET;SWCI,80MM,CL150,316L/GR/316 (10060886) | KLINGER LIMITED (30000403) | 2024-05-28 | 6 | 6 | 42.18 | 6 | 42.18 | 10060886 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,80MM,CL150,316L/GR/316 | 7.03 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04520 | 4500005685/00110 | 2000031138 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 6 |  |  |  | 0 |  |  | GASKET;SWCI,80MM,CL150,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 42.18
4500005685 | 00130 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 (10060917) | KLINGER LIMITED (30000403) | 2024-04-02 | 5 | 5 | 16.4 | 5 | 16.4 | 10060917 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 3.28 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04760 | 4500005685/00130 | 2000031140 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 5 |  |  |  | 0 |  |  | GASKET;SWCI,25MM,CL300/600,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 16.4
4500005690 | 00010 | BATTERY PACK;4AH,NICAD,SAFT SAFTV (10304033) | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 2024-05-10 | 51 | 51 | 10557 | 51 | 10557 | 10304033 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Battery/cells/accs. (26111700) | Battery/cells/accs. | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 207 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-07 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000818 | 00930 | 4500005690/00010 | 2000030872 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 51 |  |  |  | 0 |  |  | BATTERY PACK;4AH,NICAD,SAFT SAFTV |  |  | Main Store (1001) | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD |  | 0 |  |  | 10557
4500005715 | 00020 | Plate 230 x 230 (70003747) | LEGENEERING AUSTRALIA PTY LTD (30000143) | 2024-03-28 | 4 | 4 | 2231 | 4 | 2231 | 70003747 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Machinings (31390000) | Machinings | Plate 230 x 230 | 557.75 | Overdue | 0 | Australian Dollar (AUD) | 2024-03-08 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500005715/00020 | 1000004771 | 00003 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  | 100033135 | 0 |  |  | Plate 230 x 230 |  |  | Main Store (1001) | 30000143 | LEGENEERING AUSTRALIA PTY LTD |  | 0 |  |  | 2231
4500005739 | 00030 | OIL,GEAR,SHELL OMALA S2 GX 320,20L (10453016) | VIVA ENERGY AUSTRALIA LTD SHELL COMPANY OF AUSTRALIA LIMITED (30000303) | 2024-04-02 | 2 | 2 | 240 | 2 | 240 | 10453016 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Lubricants and oils (15120000) | Lubricants and oils | OIL,GEAR,SHELL OMALA S2 GX 320,20L | 120 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-08 | Follow-On Documents | WEG Purchase Order (ZNB) | Container (CON) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000008 | 01030 | 4500005739/00030 | 2000030788 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | OIL,GEAR,SHELL OMALA S2 GX 320,20L |  |  | Main Store (1001) | 30000303 | VIVA ENERGY AUSTRALIA LTD SHELL COMPANY OF AUSTRALIA LIMITED |  | 0 |  |  | 240
4500005739 | 00040 | OIL,AIR COMP;SHELL 001D7788 (10479633) | VIVA ENERGY AUSTRALIA LTD SHELL COMPANY OF AUSTRALIA LIMITED (30000303) | 2024-04-02 | 3 | 3 | 1131 | 3 | 1131 | 10479633 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Lubricants and oils (15120000) | Lubricants and oils | OIL,AIR COMP;SHELL 001D7788 | 377 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-08 | Follow-On Documents | WEG Purchase Order (ZNB) | Pail (PAI) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000008 | 01411 | 4500005739/00040 | 2000031231 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 3 |  |  |  | 0 |  |  | OIL,AIR COMP;SHELL 001D7788 |  |  | Main Store (1001) | 30000303 | VIVA ENERGY AUSTRALIA LTD SHELL COMPANY OF AUSTRALIA LIMITED |  | 0 |  |  | 1131
4500005739 | 00050 | OIL,AIR COMP;SHELL 001D7788 (10479633) | VIVA ENERGY AUSTRALIA LTD SHELL COMPANY OF AUSTRALIA LIMITED (30000303) | 2024-04-02 | 3 | 3 | 1131 | 3 | 1131 | 10479633 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Lubricants and oils (15120000) | Lubricants and oils | OIL,AIR COMP;SHELL 001D7788 | 377 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-08 | Follow-On Documents | WEG Purchase Order (ZNB) | Pail (PAI) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000008 | 01411 | 4500005739/00050 | 2000031232 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 3 |  |  |  | 0 |  |  | OIL,AIR COMP;SHELL 001D7788 |  |  | Main Store (1001) | 30000303 | VIVA ENERGY AUSTRALIA LTD SHELL COMPANY OF AUSTRALIA LIMITED |  | 0 |  |  | 1131
4500005774 | 00010 | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 (10402509) | SOLIDUS INDUSTRIES PTY LTD (30002657) | 2024-03-15 | 3 | 3 | 1569.42 | 3 | 0 | 10402509 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1569.42 | Standard () | 1 | Clean/janitorial sup (47130000) | Clean/janitorial sup | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 | 523.14 | Overdue | 0 | Australian Dollar (AUD) | 2024-03-08 | Follow-On Documents | WEG Purchase Order (ZNB) | Drum (DR) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500005774/00010 | 2000030840 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 0 |  |  |  | 0 |  |  | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 |  |  | Main Store (1001) | 30002657 | SOLIDUS INDUSTRIES PTY LTD | 6000002097 | 20 |  |  | 1569.42
4500005774 | 00020 | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 (10402509) | SOLIDUS INDUSTRIES PTY LTD (30002657) | 2024-03-15 | 6 | 6 | 3138.84 | 6 | 0 | 10402509 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 6 | 3138.84 | Standard () | 1 | Clean/janitorial sup (47130000) | Clean/janitorial sup | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 | 523.14 | Overdue | 0 | Australian Dollar (AUD) | 2024-03-08 | Follow-On Documents | WEG Purchase Order (ZNB) | Drum (DR) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500005774/00020 | 2000030841 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 0 |  |  |  | 0 |  |  | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 |  |  | Main Store (1001) | 30002657 | SOLIDUS INDUSTRIES PTY LTD | 6000002097 | 30 |  |  | 3138.84
4500005822 | 00010 | GASKET;SS,SOLAR 304649100 (10209468) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-06-25 | 10 | 10 | 343.94 | 10 | 343.94 | 10209468 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SS,SOLAR 304649100 | 34.39 | Due Later | 0 | United States Dollar (USD) | 2024-03-08 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000324 | 32030 | 4500005822/00010 | 2000031012 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 10 |  |  |  | 0 |  |  | GASKET;SS,SOLAR 304649100 |  |  | Main Store (1001) | 30000400 | SOLAR TURBINES INTERNATIONAL COMPANY | 6000002088 | 10 |  |  | 343.94
4500005822 | 00020 | MODULE,IF;8-INPUT,AB 1794IRT8XT (10218797) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-06-25 | 9 | 9 | 37383.83 | 9 | 37383.83 | 10218797 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Comp bcast/telecom (43200000) | Comp bcast/telecom | MODULE,IF;8-INPUT,AB 1794IRT8XT | 4153.76 | Due Later | 0 | United States Dollar (USD) | 2024-03-08 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000324 | 32170 | 4500005822/00020 | 2000031049 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 9 |  |  |  | 0 |  |  | MODULE,IF;8-INPUT,AB 1794IRT8XT |  |  | Main Store (1001) | 30000400 | SOLAR TURBINES INTERNATIONAL COMPANY | 6000002088 | 20 |  |  | 37383.83
4500005927 | 00010 | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP (10063554) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-06-18 | 4 | 4 | 17.4 | 4 | 17.4 | 10063554 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Lab supplies/fixture (41120000) | Lab supplies/fixture | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP | 4.35 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-08 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000011 | 02300 | 4500005927/00010 | 2000032180 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  |  | 0 |  |  | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP |  |  | Main Store (1001) | 30000347 | ROWE SCIENTIFIC PTY LTD |  | 0 |  |  | 17.4
4500006185 | 00060 | ELEMENT KIT,FLT;ATCOP 2901300011 (10504876) | ATLAS COPCO COMPRESSORS AUSTRALIA ATLAS COPCO AUSTRALIA PTY LTD (30002292) | 2024-06-27 | 8 | 8 | 25170.8 | 8 | 25170.8 | 10504876 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Ind filter/purific (40160000) | Ind filter/purific | ELEMENT KIT,FLT;ATCOP 2901300011 | 3146.35 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-12 | Sent | WEG Purchase Order (ZNB) | Kit (KIT) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500006185/00060 | 2000030847 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 8 |  |  |  | 0 |  |  | ELEMENT KIT,FLT;ATCOP 2901300011 |  |  | Main Store (1001) | 30002292 | ATLAS COPCO COMPRESSORS AUSTRALIA ATLAS COPCO AUSTRALIA PTY LTD | 6000002196 | 60 |  |  | 25170.8
4500006185 | 00070 | ELEMENT KIT,FLT;ATCOP 2901300011 (10504876) | ATLAS COPCO COMPRESSORS AUSTRALIA ATLAS COPCO AUSTRALIA PTY LTD (30002292) | 2024-06-27 | 3 | 3 | 9439.05 | 3 | 9439.05 | 10504876 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Ind filter/purific (40160000) | Ind filter/purific | ELEMENT KIT,FLT;ATCOP 2901300011 | 3146.35 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-12 | Sent | WEG Purchase Order (ZNB) | Kit (KIT) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500006185/00070 | 2000030848 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 3 |  |  |  | 0 |  |  | ELEMENT KIT,FLT;ATCOP 2901300011 |  |  | Main Store (1001) | 30002292 | ATLAS COPCO COMPRESSORS AUSTRALIA ATLAS COPCO AUSTRALIA PTY LTD | 6000002196 | 70 |  |  | 9439.05
4500006214 | 00010 | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP (10063554) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-05 | 20 | 20 | 87 | 20 | 87 | 10063554 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Lab supplies/fixture (41120000) | Lab supplies/fixture | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP | 4.35 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-12 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000011 | 02300 | 4500006214/00010 | 2000030868 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 20 |  |  |  | 0 |  |  | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP |  |  | Main Store (1001) | 30000347 | ROWE SCIENTIFIC PTY LTD | 6000002186 | 10 |  |  | 87
4500006214 | 00020 | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP (10063554) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-05 | 30 | 30 | 130.5 | 30 | 130.5 | 10063554 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Lab supplies/fixture (41120000) | Lab supplies/fixture | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP | 4.35 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-12 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000011 | 02300 | 4500006214/00020 | 2000030869 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 30 |  |  |  | 0 |  |  | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP |  |  | Main Store (1001) | 30000347 | ROWE SCIENTIFIC PTY LTD | 6000002186 | 20 |  |  | 130.5
4500006214 | 00030 | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP (10063554) | ROWE SCIENTIFIC PTY LTD (30000347) | 2024-04-05 | 15 | 15 | 65.25 | 15 | 65.25 | 10063554 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Lab supplies/fixture (41120000) | Lab supplies/fixture | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP | 4.35 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-12 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000011 | 02300 | 4500006214/00030 | 2000030870 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 15 |  |  |  | 0 |  |  | BOTTLE;SAMPLE,125ML,PL,C/W SCR TOP |  |  | Main Store (1001) | 30000347 | ROWE SCIENTIFIC PTY LTD | 6000002186 | 30 |  |  | 65.25
4500006254 | 00010 | GASKET;467MM ID X 570MM OD X 3MM THK (10476885) | COENS CO LTD (30002296) | 2024-04-14 | 2 | 2 | 776.05 | 2 | 776.05 | 10476885 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-12 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;467MM ID X 570MM OD X 3MM THK | 388.03 | Due Later | 0 | United States Dollar (USD) | 2024-03-12 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500006254/00010 | 2000030803 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | GASKET;467MM ID X 570MM OD X 3MM THK |  |  | Main Store (1001) | 30002296 | COENS CO LTD | 6000002095 | 10 |  |  | 776.05
4500006260 | 00010 | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 (10402509) | SOLIDUS INDUSTRIES PTY LTD (30002657) | 2024-04-15 | 4 | 4 | 2074.72 | 4 | 0 | 10402509 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-12 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 4 | 2074.72 | Standard () | 1 | Clean/janitorial sup (47130000) | Clean/janitorial sup | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 | 518.68 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-12 | Follow-On Documents | WEG Purchase Order (ZNB) | Drum (DR) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500006260/00010 | 2000030842 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 0 |  |  |  | 0 |  |  | CLEANER,COMPRESSOR,TURB,DRM/25L,ZOK 27 |  |  | Main Store (1001) | 30002657 | SOLIDUS INDUSTRIES PTY LTD | 6000002199 | 10 |  |  | 2074.72
4500006448 | 00010 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L (10305744) | KLINGER LIMITED (30000403) | 2024-06-04 | 2 | 2 | 18.54 | 2 | 18.54 | 10305744 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-12 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 9.27 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-12 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 10240 | 4500006448/00010 | 2000034017 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 18.54
4500006563 | 00010 | 03PSV481061 set to 20MPA (70001748) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-07-03 | 1 | 1 | 4490.1 | 1 | 4490.1 | 70001748 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-13 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | 03PSV481061 set to 20MPA | 4490.1 | Due Later | 0 | European Euro (EUR) | 2024-03-13 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500006563/00010 | 1000005319 | 00004 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100033044 | 0 |  |  | 03PSV481061 set to 20MPA |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 4490.1
4500006785 | 00010 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR (10060884) | KLINGER LIMITED (30000403) | 2024-03-28 | 12 | 12 | 42.84 | 12 | 42.84 | 10060884 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-14 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 3.57 | Overdue | 0 | Australian Dollar (AUD) | 2024-03-14 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04500 | 4500006785/00010 | 2000031134 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 12 |  |  |  | 0 |  |  | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED | 6000002189 | 10 |  |  | 42.84
4500006785 | 00020 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR (10060884) | KLINGER LIMITED (30000403) | 2024-03-28 | 6 | 6 | 21.42 | 6 | 21.42 | 10060884 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-14 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 3.57 | Overdue | 0 | Australian Dollar (AUD) | 2024-03-14 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04500 | 4500006785/00020 | 2000031135 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 6 |  |  |  | 0 |  |  | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED | 6000002189 | 20 |  |  | 21.42
4500007030 | 00010 | GASKET SET;BROADY P106652 (10447849) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-05-27 | 1 | 1 | 434.77 | 1 | 434.77 | 10447849 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-15 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET SET;BROADY P106652 | 434.77 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-15 | Sent | WEG Purchase Order (ZNB) | Set (SET) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000098 | 14360 | 4500007030/00010 | 2000037954 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | GASKET SET;BROADY P106652 |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 434.77
4500007060 | 00010 | Monorail Beam End stops (L&R Pair) (70003950) | BENDTECH GROUP PTY LTD (30002958) | 2024-04-15 | 1 | 1 | 1859 | 1 | 1859 | 70003950 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-16 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Machinings (31390000) | Machinings | Monorail Beam End stops (L&R Pair) | 1859 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-17 | Sent | WEG Purchase Order (ZNB) | Set (SET) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500007060/00010 | 1000005254 | 00020 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 600001724 | 0 |  |  | Monorail Beam End stops (L&R Pair) |  |  | Main Store (1001) | 30002958 | BENDTECH GROUP PTY LTD |  | 0 |  |  | 1859
4500007066 | 00020 | Stainless Steel Bolt Hex Set Screw SS316 (70003940) | J BLACKWOOD AND SON LTD (30000394) | 2024-03-27 | 150 | 150 | 159 | 150 | 159 | 70003940 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-16 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | Stainless Steel Bolt Hex Set Screw SS316 | 1.06 | Overdue | 0 | Australian Dollar (AUD) | 2024-03-17 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500007066/00020 | 1000005254 | 00014 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 150 |  |  | 600001724 | 0 |  |  | Stainless Steel Bolt Hex Set Screw SS316 |  |  | Main Store (1001) | 30000394 | J BLACKWOOD AND SON LTD |  | 0 |  |  | 159
4500007388 | 00010 | WASHER;65MM,MOULDED RBR,BS 336 (10064932) | ARA MARINE PTY LTD (30000279) | 2024-04-19 | 21 | 21 | 370.86 | 21 | 370.86 | 10064932 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-19 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | WASHER;65MM,MOULDED RBR,BS 336 | 17.66 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-19 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000267 | 04850 | 4500007388/00010 | 2000031011 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 21 |  |  |  | 0 |  |  | WASHER;65MM,MOULDED RBR,BS 336 |  |  | Main Store (1001) | 30000279 | ARA MARINE PTY LTD | 6000002085 | 10 |  |  | 370.86
4500007393 | 00010 | KIT,FILTER ELM;JOHN CRANE 89689834 (10443257) | SIEMENS ENERGY PTY LTD (30000222) | 2024-09-16 | 2 | 2 | 38445.45 | 2 | 38445.45 | 10443257 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-19 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Ind filter/purific (40160000) | Ind filter/purific | KIT,FILTER ELM;JOHN CRANE 89689834 | 19222.73 | Due Later | 0 | European Euro (EUR) | 2024-03-19 | Sent | WEG Purchase Order (ZNB) | Set (SET) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500007393/00010 | 2000031275 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | KIT,FILTER ELM;JOHN CRANE 89689834 |  |  | Main Store (1001) | 30000222 | SIEMENS ENERGY PTY LTD |  | 0 |  |  | 38445.45
4500007919 | 00070 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR (10060884) | KLINGER LIMITED (30000403) | 2024-04-05 | 11 | 11 | 39.27 | 11 | 39.27 | 10060884 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 3.57 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-21 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04500 | 4500007919/00070 | 2000033194 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 11 |  |  |  | 0 |  |  | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED | 6000002135 | 70 |  |  | 39.27
4500007919 | 00080 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR (10060884) | KLINGER LIMITED (30000403) | 2024-04-05 | 9 | 9 | 32.13 | 9 | 32.13 | 10060884 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 3.57 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-21 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04500 | 4500007919/00080 | 2000033195 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 9 |  |  |  | 0 |  |  | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED | 6000002135 | 80 |  |  | 32.13
4500007919 | 00090 | GASKET;SWCI,80MM,CL150,316L/GR/316 (10060886) | KLINGER LIMITED (30000403) | 2024-04-05 | 5 | 5 | 35.15 | 5 | 35.15 | 10060886 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,80MM,CL150,316L/GR/316 | 7.03 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-21 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04520 | 4500007919/00090 | 2000033196 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 5 |  |  |  | 0 |  |  | GASKET;SWCI,80MM,CL150,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED | 6000002135 | 90 |  |  | 35.15
4500007919 | 00100 | GASKET;SWCI,80MM,CL150,316L/GR/316 (10060886) | KLINGER LIMITED (30000403) | 2024-04-05 | 9 | 9 | 63.27 | 9 | 63.27 | 10060886 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,80MM,CL150,316L/GR/316 | 7.03 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-21 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04520 | 4500007919/00100 | 2000033197 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 9 |  |  |  | 0 |  |  | GASKET;SWCI,80MM,CL150,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED | 6000002135 | 100 |  |  | 63.27
4500007919 | 00110 | GASKET;SWCI,80MM,CL150,316L/GR/316 (10060886) | KLINGER LIMITED (30000403) | 2024-04-05 | 6 | 6 | 42.18 | 6 | 42.18 | 10060886 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,80MM,CL150,316L/GR/316 | 7.03 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-21 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04520 | 4500007919/00110 | 2000033198 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 6 |  |  |  | 0 |  |  | GASKET;SWCI,80MM,CL150,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED | 6000002135 | 110 |  |  | 42.18
4500007962 | 00010 | TAPE;COR INH,50MM,10MRL,DENSO 600050 (10062327) | J BLACKWOOD AND SON LTD (30000394) | 2024-03-24 | 6 | 6 | 87.24 | 6 | 87.24 | 10062327 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Adhesives/sealants (31200000) | Adhesives/sealants | TAPE;COR INH,50MM,10MRL,DENSO 600050 | 14.54 | Overdue | 0 | Australian Dollar (AUD) | 2024-03-21 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000820 | 01840 | 4500007962/00010 | 2000030865 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 6 |  |  |  | 0 |  |  | TAPE;COR INH,50MM,10MRL,DENSO 600050 |  |  | Main Store (1001) | 30000394 | J BLACKWOOD AND SON LTD | 6000002087 | 20 |  |  | 87.24
4500007993 | 00010 | ELEMENT ASY,FLT;SIEMENS 64441565 (10445237) | SIEMENS ENERGY PTY LTD (30000222) | 2024-11-21 | 2 | 2 | 35445.97 | 2 | 35445.97 | 10445237 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Brayden Tomkinson | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Ind filter/purific (40160000) | Ind filter/purific | ELEMENT ASY,FLT;SIEMENS 64441565 | 35445.97 | Due Later | 0 | European Euro (EUR) | 2024-03-21 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 2 | Material (1) |  |  | 4500007993/00010 | 2000030844 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | ELEMENT ASY,FLT;SIEMENS 64441565 |  |  | Main Store (1001) | 30000222 | SIEMENS ENERGY PTY LTD | 6000002117 | 10 |  |  | 35445.97
4500008059 | 00010 | GASKET;SWCI,300MM,CL150,316L/GR/316 (10060891) | KLINGER LIMITED (30000403) | 2024-04-16 | 10 | 10 | 256.7 | 10 | 256.7 | 10060891 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;SWCI,300MM,CL150,316L/GR/316 | 25.67 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-21 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000001 | 04570 | 4500008059/00010 | 2000041961 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 10 |  |  |  | 0 |  |  | GASKET;SWCI,300MM,CL150,316L/GR/316 |  |  | Main Store (1001) | 30000403 | KLINGER LIMITED |  | 0 |  |  | 256.7
4500008063 | 00010 | PAINT,SPRAY;BLUE,FR COATING (10601282) | INTERNATIONAL CORROSION SERVICES PTY LTD (30002531) | 2024-05-14 | 1 | 1 | 3125 | 1 | 3125 | 10601282 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Paint/primer/finish (31210000) | Paint/primer/finish | PAINT,SPRAY;BLUE,FR COATING | 3125 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-22 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500008063/00010 | 2000040433 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | PAINT,SPRAY;BLUE,FR COATING |  |  | Main Store (1001) | 30002531 | INTERNATIONAL CORROSION SERVICES PTY LTD | 6000002599 | 10 |  |  | 3125
4500008307 | 00010 | KIT,INSTL,1-BAY METR/SW SHOCK (70004675) | SOLAR TURBINES INTERNATIONAL COMPANY (30000400) | 2024-06-15 | 4 | 4 | 1325.77 | 4 | 1325.77 | 70004675 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-25 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Electrical equipment (39120000) | Electrical equipment | KIT,INSTL,1-BAY METR/SW SHOCK | 331.44 | Due Later | 0 | United States Dollar (USD) | 2024-03-25 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500008307/00010 | 1000006539 | 00002 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  | 100072934 | 0 |  |  | KIT,INSTL,1-BAY METR/SW SHOCK |  |  | Main Store (1001) | 30000400 | SOLAR TURBINES INTERNATIONAL COMPANY |  | 0 |  |  | 1325.77
4500008796 | 00010 | GASKET SET;BROADY P106652 (10447849) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-06-07 | 3 | 3 | 1304.31 | 3 | 1304.31 | 10447849 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-26 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET SET;BROADY P106652 | 434.77 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-26 | Sent | WEG Purchase Order (ZNB) | Set (SET) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000098 | 14360 | 4500008796/00010 | 2000045188 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 3 |  |  |  | 0 |  |  | GASKET SET;BROADY P106652 |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 1304.31
4500008855 | 00010 | Linear Winch 630 Bar Test Lines 1500mm (70004851) | HYDRAULIC ENERGY AUST PTY LTD (30002606) | 2024-04-11 | 2 | 2 | 646.8 | 2 | 646.8 | 70004851 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | Linear Winch 630 Bar Test Lines 1500mm | 323.4 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-27 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500008855/00010 | 1000007062 | 00003 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  | 100075531 | 0 |  |  | Linear Winch 630 Bar Test Lines 1500mm |  |  | Main Store (1001) | 30002606 | HYDRAULIC ENERGY AUST PTY LTD |  | 0 |  |  | 646.8
4500008855 | 00020 | Linear Winch 630 Bar Test Lines 2000mm (70004852) | HYDRAULIC ENERGY AUST PTY LTD (30002606) | 2024-04-11 | 2 | 2 | 779.64 | 2 | 779.64 | 70004852 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | Linear Winch 630 Bar Test Lines 2000mm | 389.82 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-27 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500008855/00020 | 1000007062 | 00004 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  | 100075531 | 0 |  |  | Linear Winch 630 Bar Test Lines 2000mm |  |  | Main Store (1001) | 30002606 | HYDRAULIC ENERGY AUST PTY LTD |  | 0 |  |  | 779.64
4500009019 | 00010 | VALVE,BALL;20MM,CL300,RF,CS,C3B1F (10227240) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-06-19 | 1 | 1 | 4713 | 1 | 4713 | 10227240 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,BALL;20MM,CL300,RF,CS,C3B1F | 4713 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-27 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000098 | 14480 | 4500009019/00010 | 2000045783 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  |  | 0 |  |  | VALVE,BALL;20MM,CL300,RF,CS,C3B1F |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 4713
4500009169 | 00010 | SHEET; SS Perforated, 300 x 235 x 1.5mm (70001542) | TRINKOR PTY LTD (30001954) | 2024-04-21 | 80 | 80 | 5103.2 | 80 | 5103.2 | 70001542 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | SHEET; SS Perforated, 300 x 235 x 1.5mm | 63.79 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-28 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500009169/00010 | 1000007193 | 00003 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 80 |  |  | 100034141 | 0 |  |  | SHEET; SS Perforated, 300 x 235 x 1.5mm |  |  | Main Store (1001) | 30001954 | TRINKOR PTY LTD |  | 0 |  |  | 5103.2
4500009169 | 00020 | SHEET; SS Perforated, 300 x 285 x 1.5mm (70001543) | TRINKOR PTY LTD (30001954) | 2024-04-21 | 80 | 80 | 5103.2 | 80 | 5103.2 | 70001543 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | SHEET; SS Perforated, 300 x 285 x 1.5mm | 63.79 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-28 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500009169/00020 | 1000007193 | 00004 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 80 |  |  | 100034141 | 0 |  |  | SHEET; SS Perforated, 300 x 285 x 1.5mm |  |  | Main Store (1001) | 30001954 | TRINKOR PTY LTD |  | 0 |  |  | 5103.2
4500009179 | 00010 | Carman, 20 NB x 300 Spec Blind to suit R (70003767) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-04-30 | 1 | 1 | 319.66 | 1 | 319.66 | 70003767 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | Carman, 20 NB x 300 Spec Blind to suit R | 319.66 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-28 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | 4500009179/00010 | 1000007192 | 00008 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 100032996 | 0 |  |  | Carman, 20 NB x 300 Spec Blind to suit R |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 319.66
4500009183 | 00010 | STUDBOLT;0.625"X95MM,B7,CAD+XYLAN (10058878) | TRISTAR AUSTRALIA PTY LTD (30000148) | 2024-05-10 | 8 | 8 | 19.52 | 8 | 19.52 | 10058878 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd | Terrey Gill | 2024-03-28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Hardware (31160000) | Hardware | STUDBOLT;0.625"X95MM,B7,CAD+XYLAN | 2.44 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-28 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000000 | 00480 | 4500009183/00010 | 2000045782 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 8 |  |  |  | 0 |  |  | STUDBOLT;0.625"X95MM,B7,CAD+XYLAN |  |  | Main Store (1001) | 30000148 | TRISTAR AUSTRALIA PTY LTD |  | 0 |  |  | 19.52
4500009244 | 00010 | VALVE,CHK;DN150,CL1500,RTJ,LTCS,L15C8C (10589262) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-08-12 | 2 | 2 | 10357.32 | 2 | 10357.32 | 10589262 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-03-28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,CHK;DN150,CL1500,RTJ,LTCS,L15C8C | 5178.66 | Due Later | 0 | Australian Dollar (AUD) | 2024-03-28 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000098 | 17320 | 4500009244/00010 | 2000046477 | 00010 |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 2 |  |  |  | 0 |  |  | VALVE,CHK;DN150,CL1500,RTJ,LTCS,L15C8C |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 10357.32
W451758633 | 00010 | VALVE,MONOFLG,50MM,CL1500,FLG,DSS,D15M8T (10485935) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-01-25 | 1 | 1 | 12265.41 | 1 | 12265.41 | 10485935 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,MONOFLG,50MM,CL1500,FLG,DSS,D15M8T | 12265.41 | Overdue | 0 | Australian Dollar (AUD) | 2023-04-06 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451758633/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | AU05-0503 | 0 |  |  | VALVE,MONOFLG,50MM,CL1500,FLG,DSS,D15M8T |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 12265.41
W451761463 | 00010 | VALVE,MONOFLG,50MM,CL1500,FLG,DSS,D15M8T (10485935) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-03-12 | 1 | 1 | 12265.41 | 1 | 12265.41 | 10485935 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,MONOFLG,50MM,CL1500,FLG,DSS,D15M8T | 12265.41 | Overdue | 0 | Australian Dollar (AUD) | 2023-05-09 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451761463/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | AU05-0503 | 0 |  |  | VALVE,MONOFLG,50MM,CL1500,FLG,DSS,D15M8T |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 12265.41
W451765389 | 00030 | EXTINGUISHER,FIRE;FOAM,FOAM,ARC,9L,PORT (10236513) | WORMALD AUSTRALIA PTY LTD (30000072) | 2023-09-14 | 1 | 1 | 348 | 1 | 348 | 10236513 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fire protection (46190000) | Fire protection | EXTINGUISHER,FIRE;FOAM,FOAM,ARC,9L,PORT | 348 | Overdue | 0 | Australian Dollar (AUD) | 2023-06-19 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451765389/00030 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 2200668648 | 0 |  |  | EXTINGUISHER,FIRE;FOAM,FOAM,ARC,9L,PORT |  |  | Main Store (1001) | 30000072 | WORMALD AUSTRALIA PTY LTD |  | 0 |  |  | 348
W451776601 | 00010 | INHIBITOR,CORROSION;COR BON D5010NS,12OZ (10576543) | AIRFLITE PTY LTD (30002381) | 2023-11-30 | 1 | 1 | 93.06 | 1 | 0 | 10576543 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 93.06 | Standard () | 1 | Additives (12160000) | Additives | INHIBITOR,CORROSION;COR BON D5010NS,12OZ | 93.06 | Overdue | 0 | Australian Dollar (AUD) | 2023-10-01 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451776601/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 0 |  |  | 2200705182 | 0 |  |  | INHIBITOR,CORROSION;COR BON D5010NS,12OZ |  |  | Main Store (1001) | 30002381 | AIRFLITE PTY LTD |  | 0 |  |  | 93.06
W451776601 | 00020 | INHIBITOR,CORROSION;COR BON D5010NS,12OZ (10576543) | AIRFLITE PTY LTD (30002381) | 2023-11-30 | 1 | 1 | 93.06 | 1 | 0 | 10576543 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 93.06 | Standard () | 1 | Additives (12160000) | Additives | INHIBITOR,CORROSION;COR BON D5010NS,12OZ | 93.06 | Overdue | 0 | Australian Dollar (AUD) | 2023-10-01 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451776601/00020 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 0 |  |  | 2200705185 | 0 |  |  | INHIBITOR,CORROSION;COR BON D5010NS,12OZ |  |  | Main Store (1001) | 30002381 | AIRFLITE PTY LTD |  | 0 |  |  | 93.06
W451777676 | 00010 | VALVE,GATE;25MM,CL1500,SIEMENS 11788565 (10445243) | SIEMENS ENERGY PTY LTD (30000222) | 2024-04-12 | 1 | 1 | 23577.49 | 1 | 23577.49 | 10445243 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,GATE;25MM,CL1500,SIEMENS 11788565 | 23577.49 | Due Later | 0 | European Euro (EUR) | 2023-10-10 | Not Yet Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451777676/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 2100366328 | 0 |  |  | VALVE,GATE;25MM,CL1500,SIEMENS 11788565 |  |  | Main Store (1001) | 30000222 | SIEMENS ENERGY PTY LTD |  | 0 |  |  | 23577.49
W451778135 | 00010 | BATTERY PACK;4AH,NICAD,SAFT SAFTV (10304033) | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 2023-12-09 | 67 | 67 | 13869 | 67 | 13869 | 10304033 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Battery/cells/accs. (26111700) | Battery/cells/accs. | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 207 | Overdue | 0 | Australian Dollar (AUD) | 2023-10-14 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000818 | 00930 | W451778135/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 67 |  |  | AU05-0503 | 0 |  |  | BATTERY PACK;4AH,NICAD,SAFT SAFTV |  |  | Main Store (1001) | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD |  | 0 |  |  | 13869
W451779258 | 00010 | VALVE,REL,SEETRU 616820073,3400KPAG (10482558) | SCORE AUSTRALASIA PTY LTD (30000225) | 2024-05-15 | 1 | 1 | 1249.11 | 1 | 1249.11 | 10482558 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,REL,SEETRU 616820073,3400KPAG | 1249.11 | Due Later | 0 | Australian Dollar (AUD) | 2023-10-25 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) | 4700000098 | 08610 | W451779258/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | AU60-6001 | 0 |  |  | VALVE,REL,SEETRU 616820073,3400KPAG |  |  | Main Store (1001) | 30000225 | SCORE AUSTRALASIA PTY LTD |  | 0 |  |  | 1249.11
W451779281 | 00010 | VALVE,SLND;BIFOLD FP15S30632S78A155 (10430531) | ROTORK AUSTRALIA PTY LTD (30000103) | 2024-04-19 | 1 | 1 | 5727.57 | 1 | 5727.57 | 10430531 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Fluid/gas distribut (40140000) | Fluid/gas distribut | VALVE,SLND;BIFOLD FP15S30632S78A155 | 5727.57 | Due Later | 0 | Australian Dollar (AUD) | 2023-10-25 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451779281/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | WINRPA | 0 |  |  | VALVE,SLND;BIFOLD FP15S30632S78A155 |  |  | Main Store (1001) | 30000103 | ROTORK AUSTRALIA PTY LTD |  | 0 |  |  | 5727.57
W451780469 | 00010 | BATTERY PACK;4AH,NICAD,SAFT SAFTV (10304033) | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD (30002422) | 2024-01-31 | 22 | 22 | 4554 | 22 | 4554 | 10304033 | Order (F) | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Battery/cells/accs. (26111700) | Battery/cells/accs. | BATTERY PACK;4AH,NICAD,SAFT SAFTV | 207 | Overdue | 0 | Australian Dollar (AUD) | 2023-11-06 | Sent | WEG Purchase Order (ZNB) | Each (EA) | 0 | OKH Okha - NWS OIL (AB50) | OKH Okha - NWS OIL | 1 | Material (1) |  |  | W451780469/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 22 |  |  | 2100368459 | 0 |  |  | BATTERY PACK;4AH,NICAD,SAFT SAFTV |  |  |  | 30002422 | MACLEAN INTERNATIONAL GROUP AUSTRAL PTY LTD |  | 0 |  |  | 4554
W451782182 | 00010 | GASKET;467MM ID X 570MM OD X 3MM THK (10476885) | COENS CO LTD (30002296) | 2024-03-26 | 4 | 4 | 2438.52 | 4 | 2438.52 | 10476885 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 2438.92 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Standard () | 1 | Gaskets (31400000) | Gaskets | GASKET;467MM ID X 570MM OD X 3MM THK | 609.63 | Overdue | 0 | United States Dollar (USD) | 2023-11-24 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451782182/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 4 |  |  | 2200670621 | 0 |  |  | GASKET;467MM ID X 570MM OD X 3MM THK |  |  | Main Store (1001) | 30002296 | COENS CO LTD |  | 0 |  |  | 2438.52
W451782184 | 00010 | ANTENNA;COMROD AR62 (10468906) | ELECTROTECH AUSTRALIA PTY LIMITED (30001073) | 2024-01-15 | 1 | 1 | 3257 | 1 | 3257 | 10468906 |  | 0 | Woodside Energy Ltd (1001) | Woodside Energy Ltd |  | 2024-01-01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | Standard () | 1 | Media Nwork eqp/Plat (43220000) | Media Nwork eqp/Plat | ANTENNA;COMROD AR62 | 3257 | Overdue | 0 | Australian Dollar (AUD) | 2023-11-24 | Follow-On Documents | WEG Purchase Order (ZNB) | Each (EA) | 0 | PDC - NWS OIL (AB01) | PDC - NWS OIL | 1 | Material (1) |  |  | W451782184/00010 |  |  |  | AUS Operations (106) | AUS Operations |  | AU00 | WEG Australia | 1 |  |  | 2100346318 | 0 |  |  | ANTENNA;COMROD AR62 |  |  | Main Store (1001) | 30001073 | ELECTROTECH AUSTRALIA PTY LIMITED |  | 0 |  |  | 3257